358 | Bouvier, H - 0000000000 : NO@ADDRESS.GIVEN; Blosiu, J - | Bouvier, H - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan Solar Array Drive Jitter | A jitter in the solar array drive control loop during Venus mapping operations was caused by a deficiency, at oblique sun angles, in the algorithm that is used in Flight Software (FSW) to determine whether a solar panel position correction is required. Conduct thorough reviews to verify math models of hardware and to understand the implications of simplification of math models on performance in flight. Use finer resolution display scales to identify subtle instabilities. | Stability analyses for all geometries are an important part of attitude control hardware and software development and testing. | Because of the difficulties involved in ground testing spacecraft attitude and articulation control systems in a one G field, it is extremely important to conduct thorough reviews to verify math models of hardware and to understand the implications of simplification of math models on performance in flight. These reviews should involve hardware, analysis, software and systems engineers. Finer resolution display scales should be used around worst-case conditions to identify subtle instabilities. | JPL | 12/13/1994 | During Venus mapping operations at high (over 64 degrees) incidence angles of the sun to the solar panels, a jitter occurred in the solar array drive control loop. This jitter excited a structural resonance in the solar panels, causing severe vibration. The problem was caused by a deficiency, at oblique sun angles, in the algorithm that is used in Flight Software (FSW) to determine whether a solar panel position correction is required. The deficiency was caused by not accounting for high sun incidence angles (geometrical effects) in setting the minimum step size software parameter. As a result, the algorithm continually determined that a correction was required -- first in one direction, then in the reverse, then in the first direction, etc. The jitter was actually present in simulations performed by the flight team before the incident occurred on the spacecraft, but was not recognized because of the plotting scale used. Once recognized, the problem was solved by switching the solar array control to an open-loop mode, i.e., not using the sun sensors, while the celestial geometry was unfavorable. A complete description of the problem can be found in the references. Additional Keyword(s): AACS, Mathematical Models Reference(s): PFR #52242, ISA 8775, ISA 9049, ISA 8536 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.11 ("Engineering Practices: System Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 01/16/1992
274 | Harrell, J - 0000000000 : NO@ADDRESS.GIVEN | Harrell, J - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Observer Payload Data System (PDS) Exposure to Low Temperature | During thermal vacuum testing of the flight Mars Observer PDS, the subsystem was exposed to a temperature of about -47 degrees Celsius, well below the desired limit of -20 degrees C. The problem was caused by a failure in a temperature controller and was compounded by a chamber operator evaluation error. The recommendations involve use of alarm and “fail safe” circuits, pretest functional verification of the test facility, procedures required before manual override of “fail safe” devices, and continuous quality assurance monitoring of tests. | Environmental testing of flight hardware is a necessary but potentially hazardous activity in the preparation of a spacecraft or instrument for launch. Adherence to proper procedures and alertness by environmental test hardware and facility personnel are important safeguards against facility and/or equipment failure. Despite the use of properly calibrated and tested environmental test facility protection circuits and alarm systems, overlimit test conditions can still occur. | Alarm and "fail safe" circuits must always be utilized with sensors located appropriately on the hardware and test facility to prevent the hardware from exceeding environmental limits. During the pretest functional verification of the test facility controls and alarm systems, attention should be given to the adequacy of transient data sampling and recording to assure timely recognition of "out of tolerance" test conditions. Require communication between test facility engineering personnel and cognizant hardware engineering personnel for approval prior to any override of "fail safe" devices. Program offices should give consideration, during the planning and initial stages of a project, to provide continuous quality assurance monitoring of all environmental tests as an additional safeguard against overlimit test conditions. | JPL | 07/09/1993 | During testing of the flight Mars Observer PDS (Serial No. 1) in a thermal vacuum chamber, the subsystem was exposed to a temperature of about -47 degrees Celsius, well below the desired limit of -20 degrees C. The problem was caused by a failure in a temperature controller and was compounded by a chamber operator evaluation error. The failure of the controller during the planned descent to -20 C was detected by an alarm circuit and a "fail safe" circuit, both of which functioned properly by closing off the supply of cold gas to the PDS baseplate heat exchanger. The chamber operator overrode the protection circuits, choosing to believe the recently calibrated temperature controller rather than the alarms. The subsystem engineer observed from a separate data source that the hardware was exceeding the specified temperature and requested a test termination. Following analysis, evaluation and test facility corrective actions, the test of the PDS was continued and successfully completed with no further difficulty. Reference(s): PFR #55545 AND #56161 (includes Review Board report) | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 09/26/1991
285 | Enmark, H - 0000000000 : NO@ADDRESS.GIVEN | Enmark, H - 0000000000 : NO@ADDRESS.GIVEN |  | Wide Field/Planetary Camera II (WF/PC II) Charge Coupled Device (CCD) Failure | Although an alert had been issued on a thermal wire stripper, its use during the WF/PC II CCD assembly process resulted in damage to the engineering model camera head. The alert process should be re-examined and consideration given to reissue of certain alerts on a periodic basis. Assembly involving flight components should be controlled by the appropriate practices and procedures required for flight hardware. | The current scope of distribution of alerts does not assure that people using similar equipment will be alerted, particularly if some time has elapsed. Use of any equipment with the potential of feeding electrical energy into sensitive electronic devices must be planned with great care to eliminate the risk of damage. | The alert process should be re-examined and consideration given to reissue of certain alerts on a periodic basis. Assembly involving flight components, even in non-flight equipment such as engineering models, should be controlled by the appropriate practices and procedures required for flight hardware, including grounding of soldering tips and wire strippers. | JPL | 08/06/1993 | The WF/PC II engineering model camera head did not image properly during initial power-on electrical tests. The malfunction was determined to be a failure of the CCD. After a new CCD was installed, the camera head was again found to be inoperative due to the same type of CCD failure. It was determined that both failures were caused by the use of an ungrounded thermal wire stripper during the CCD assembly process. The strippers had a measured voltage of 32 volts AC on the tips, more than enough to damage the CCDS. Investigation into the cause of the failures revealed that alerts had been issued some six years ago on this particular model of wire stripper. The devices that were destroyed in this event were two of only 28 remaining units in existence (one CCD is required for each of the 8 camera heads in the WF/PC II flight assembly). Obtaining additional devices would have extreme cost and schedule impact on the WF/PC II build. Additional Keyword(s): Electrostatic Discharge Reference(s): PFR #53937 and #53934 JPL Quality Assurance Alert QAA 019 (9/14/84) Government-Industry Data Exchange Program Problem (GIDEP) Advisory H6-P-90-01 (no date) | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5.5 ("Safety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisition") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 08/09/1991
289 | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN; Sevilla, D - | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan In-Flight Solar Array Deployment Indication | Although shuttle astronauts observed Magellan solar panel deployment, a microswitch failed to provide a “panels-latched” indication. Ensure that telemetry transducers measure the desired function-- not just a related function. Microswitch design should account for the need for overtravel in the actuation stroke. Perform a FMECA early in the spacecraft life cycle. | Microswitches on Magellan were mounted such that they would detect the position of the solar panels (as opposed to the status of the latching mechanism). As a result, they were just a position indicator and not a "panels latched" indicator. A marginal microswitch actuation stroke plus zero-g effects can result in failure of the microswitch to close. Failure Mode Effects and Criticality Analysis (FMECA) is a worthwhile activity and can result in problem workarounds being built into flight sequences ahead of time. | Care should be taken in deciding where to mount telemetry transducers to assure that the desired function is actually being measured, and not just a related function. All applications of microswitches should take into account the need for overtravel in the actuation stroke. Perform a Failure Mode Effects and Criticality Analysis (FMECA) early in the spacecraft life cycle, and involve the cognizant design personnel. | JPL | 07/13/1993 | During the launch sequence of the Magellan spacecraft, the two solar panels were observed by the space shuttle astronauts to have deployed, but the "panels-latched" telemetry indication was not transmitted. The deployment mechanism Failure Mode Effects and Criticality Analysis (FMECA) had identified the potential for latching indication problems, therefore in the planned launch sequence the panels were rotated such that the subsequent Inertial Upper Stage (IUS) burn would drive the panels toward the latched position. Analysis has shown that the anomaly was due to the combination of marginal microswitch actuation stroke and zero-g effects on the solar array hinge mechanism. This combination caused one or both of the series-wired microswitches to fail to close. During the IUS burn, a small shift of the panels resulted in microswitch closure and provided the proper telemetry indication. Except for the time spent addressing the initial concern, the anomaly did not impact the Magellan mission. Reference(s): PFR #52230 IOM 3524-90-503, From D. Sevilla to B. Wagoner, dated November 5, 1990 | JPL has referenced the lesson as supporting Paragraph 4.12.5.5 ("Flight Electronics Hardware System Design: Interfaces - Restricted Usage"), Paragraph 4.2.2.9 ("Mechanical Configuration/Systems Design: Configuration - Design Deployables for Test"), and Paragraph 8.3.3.2 ("System Assembly, Integration and Test: System Functional Verification - Deployments and Articulations") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Science | Public | Not Specified |  | 07/11/1991
288 | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Spacecraft Safing During Star Scanner Calibration | An unintended in-flight mode change impacted a planned Galileo sequence only because of a hardware failure during the sequence. The spacecraft entered safing, necessitating a difficult recovery process that could have impacted science return had it happened during encounter. When simulating and testing command sequences, assure that the software and hardware states exactly match the expected in-flight states. Any anomaly that changes a fundamental spacecraft state must be scrutinized for potential impacts. | Test bed simulators provide a valuable tool for analyzing/verifying spacecraft operations and anomalies. Spacecraft mode changes caused by in-flight anomalies can affect subsequent planned activity sequences. | When simulating and testing command sequences, care must be taken to guarantee that the software and hardware states used during the test exactly match the software and hardware states that are expected in flight. Whenever a spacecraft anomaly changes any of the fundamental spacecraft states, all subsequent activities must be scrutinized for potential impacts. | JPL | 07/13/1993 | An Attitude and Articulation Control Subsystem (AACS) sequence designed to collect data for calibration of the spacecraft star scanners in the AACS inertial mode (gyros on), was tested on the Galileo test bed simulator. Prior to the transmission and execution of this calibration sequence on the spacecraft, a star misidentification event caused the AACS to switch from the "inertial" to the "cruise" mode (gyros off). Because of the importance of getting the calibration data and limited open time in the few weeks before venus encounter, it was decided to proceed with the star scanner calibration. The mode change was evaluated and not believed to have an effect on the planned sequence. However, during the execution of the calibration sequence, a spin bearing controller instability occurred due to an unexpected incompatibility between the mode and AACS software. This caused a series of hardware swaps within the AACS, ultimately causing the spacecraft to go into safing. A subsequent test on the Galileo test bed simulator duplicated the spacecraft response. This event occurred twenty-five days before Venus encounter and the difficult recovery process from safing took three weeks. Had this anomaly occurred closer to the encounter, significant impact on science data return could have resulted. Reference(s): PFR #52608 | JPL has referenced the lesson as supporting Paragraph 8.3.4.1 ("System Assembly, Integration and Test: Flight Sequence Verification - Sequence Integrity") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Science | Public | Not Specified |  | 04/18/1991
271 | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Observer Pressure Modulator Infrared Radiometer (PMIRR) Cooler Failure During Vibration Testing | A severe structural failure occurred during flight acceptance vibration testing of the PMIRR radiative cooler. An erroneous assumption was made that the inherited design was acceptable despite a change in launch vehicle. Hold a complete and thorough design review for “inherited” flight hardware designs. Assure that inheritance is considered in the dynamic test model. Analyze interrelationships between modified and unmodified elements of flight hardware designs. | Use of inherited designs does not preclude the necessity of performing in-depth analyses of all elements, whether redesigned or not, especially if environmental requirements change and are not identical to those for which inheritance is claimed. A dynamic test model for developmental testing can detect design flaws resulting from the use of inherited hardware and save more than its cost in terms of dollars and time. Weight reduction efforts and design changes of some elements of an assembly can adversely affect the behavior of unmodified elements. | A complete and thorough design review should be held for "inherited" designs of flight hardware. This review should examine changes in planned application, changes in design and plans for reanalysis and retest. Assure use of a dynamic test model for developmental testing of hardware designs based on "inheritance". Perform an in-depth analysis of interrelationships between modified and unmodified elements of flight hardware designs. | JPL | 07/07/1993 | During flight acceptance vibration testing of the PMIRR radiative cooler assembly, a severe structural failure occurred. As a result of this failure, the detectors and other internal elements of the cooler assembly were severely damaged. The PMIRR cooler assembly is a modification to a flight-proven design which had flown successfully as a part of the thematic mapper instrument for several years. Cost and schedule considerations had dictated the choice of modifying an existing design over designing a custom cooler for the PMIRR instrument. An erroneous assumption was made that the inherited design was acceptable. Investigation into the event by a review board revealed that the failure was the result of the significant increase in vibration test levels required because of the change in launch vehicle for the PMIRR instrument. The thematic mapper had experienced much more benign launch environments and insufficient analysis of the failed component had taken place, particularly in the area, which was inherited from the original design. It was also determined, however, that the original analysis of the unmodified component was flawed in that it assumed an incorrect value for allowable stress for the material and manufacturing processes used. This failure created a major cost and schedule impact to accommodate the reanalysis, rebuilding, and retesting of the cooler assembly. Reference(s): PFR #54605 PMIRR Failure Review Board Report |  | N/A |  |  | Public | Not Specified |  | 03/28/1991
399 | Mine, H - 0000000000 : NO@ADDRESS.GIVEN | Mine, H - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Arc Welding Anomaly | During arc welding of a Galileo propulsion fuel line, an arc to the spacecraft caused an uncontrolled transient pulse of current that flowed through portions of the spacecraft structure and electronics. The potential for anomalies to introduce transient currents prompted recommendations involving interface design, planning of welding operations, and evaluation of electrical and insulation characteristics. | The complicated thermal and mechanical interface design of the RPM forced welding assembly and disassembly operations into a confined area, leading directly to a hazardous operation. Unforeseen anomalies can introduce uncontrolled transient pulses of current into mechanisms which are not designed to conduct electricity. | Spacecraft design should emphasize simplicity in interface design. Attempts should be made to allow for the design, development, assembly and test of subsystems as independent units. In planning welding operations, a simulation of the physical configuration of the components in the area of the welding operation should be included, in addition to the existing tests for weld integrity. Contact start welders should be considered where welding operations present the possibility of arcing problems such as were encountered during the assembly and welding of the Galileo Propulsion subsystem fuel line. The electrical and insulation characteristics of mechanisms such as the ball bearings in the Spin Bearing Assembly, which are not designed to conduct electricity, should be evaluated during the design process and consideration be given to electrical isolation of such mechanisms. | JPL | 06/07/1995 | During final reassembly and welding of the 400-N Rocket Engine Assembly fuel line (part of the Galileo Retro Propulsion Module - RPM), an arc was seen to jump between the welding head and the RPM oxidizer line (a distance less than 0.1"). The result of this arc was a pit in the oxidizer line (determined non-critical) and an uncontrolled transient pulse of current which flowed through portions of the spacecraft structure and electronics. It was recognized that this welding procedure was potentially hazardous. This welding procedure had been used when the RPM had been previously assembled on the flight spacecraft and two separate reviews were conducted prior to performing the final weld. Review of the anomaly identified several subsystems (Spin Bearing Assembly ball bearings, oxidizer tubing, encoder electronics, slip rings, RPM rocket engine pressure transducers, and RPM heaters) which were along the potential current paths of the arc from the arc contact point on the oxidizer line. Analysis of these subsystems determined that the subsystems had not been compromised. Tests simulating the worst case conditions on identical ball bearings demonstrated that there was no change to the surface after the current pulse which would degrade the bearing performance. A review of the welding anomaly concluded that the spacecraft was not damaged or overstressed. There was, however, the impact of the additional work and analysis required to respond to the anomaly. Reference(s): PFR #54818 and #54282 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.3 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/28/1991
287 | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan Power Control Unit Failure During Test | Following rework of the Magellan Power Control Unit (PCU), an engineer performed an after-hours test of the unit without quality assurance assistance or adequate test procedures. Reverse polarity voltage was applied to electronic circuitry within the unit, causing blown fuses and potential damage to electronic parts. Test or retest of flight hardware should always be performed with adequate personnel in attendance, with QA surveillance, and with approved test procedures. Prior to tests, review the use of test instrumentation to verify the proper configuration and precautions. | Testing of flight critical hardware without approved test procedures, and without the presence of quality assurance, can lead to serious problems. Test instrumentation, used improperly, can induce voltages and currents in components, resulting in degradation or failures. | Test or retest of flight hardware should always be performed with adequate personnel in attendance, with QA surveillance and with approved test procedures. Clarification of this requirement in the flight project practices document should be considered. Prior to the use of test instrumentation, reviews should be conducted to verify that proper configuration and adequate precautions have been taken to prevent damage to flight hardware. | JPL | 07/13/1993 | While the Magellan Power Control Unit (PCU) underwent test following rework, an engineer was performing a test of the unit at a contractor facility after hours and without quality assurance (QA) assistance and adequate test procedures. During this continuity and resistance testing, test instrumentation applied reverse polarity voltage to electronic circuitry within the unit. This resulted in three blown fuses and potential damage to other electronic parts. After analysis, repair, and testing the PCU was reinstalled in the Magellan spacecraft at Kennedy Space Center, fortunately with no delay in launch operations. Additional Keyword(s): Subsystem Test Reference(s): Mars #B 16003 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 (Protection and Security of Flight Hardware) and 7.3.4 (Quality Assurance) in the Jet Propulsion Laboratory standard ¿Flight Project Practices, Rev. 6,¿ JPL DocID 58032. | N/A |  |  | Public | Not Specified |  | 01/31/1991
286 | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo NIMS Cooler Cover Ejection Anomaly | Contrary to design assumptions and the original flight plan, a decision was made to energize the Galileo Near Infrared Mapping Spectrometer (NIMS) cover heater prior to ejecting the covers. The cover failed to deploy until the heater was switched off. The lesson offers recommendations that would deter untested flight sequences and incomplete reviews of mission operations flight rules. | Untested flight sequences frequently result in unexpected events. Incomplete reviews of mission operations flight rules can cause problems. Problems are created due to the loss of information in the transfer of responsibility from design to operations. | All primary and backup spacecraft flight configurations should be tested or analyzed before launch, including the most probable failure-mode configurations. Subsystem constraints that impose system constraints should be evaluated at system design reviews for their system impacts and their possible elimination. The flight rules generation cycle should be initiated early in the mission operations design, and emphasis should be placed on their review, including additions or revisions thereto, by all essential personnel (such as design cognizant engineers). Reviews of critical spacecraft operations should be initiated early in the design cycle and should include design specialists. For long duration missions, re-review before initiation of critical operations is highly desirable. | JPL | 07/13/1993 | At launch, the Near Infrared Mapping Spectrometer (NIMS) on the Galileo spacecraft had two covers in place to protect the instrument from contamination. Two and a half months after launch, when contamination was deemed to be negligible, an attempt was made to eject the covers. The "cooler cover" failed to eject, as determined by not receiving expected temperature changes. Analysis of the data revealed that the temperature of the cooler shield was 38 degrees C., due to the shield heater being energized. This resulted in a temperature differential between the cover and the shield that caused a mechanical distortion sufficient to prevent the cover from ejecting. All ejection tests before launch were conducted with the shield heater unenergized, which was the original in-flight plan. Because of a concern for contamination caused by spacecraft outgassing, a flight rule was modified prior to launch requiring the shield heater to be energized before cover deployment. The flight rule was in error by not requiring the shield heater to be off sometime prior to cover deployment. The shield heater was commanded off and twenty-two minutes later the "cooler cover" ejected properly, as shown by the instrument temperature telemetry. Had the "cooler cover" not ejected, the NIMS experiment would have been considered a failure. Additional Keyword(s): Testing, Mechanical Devices Reference(s): PFR #52603 Review Board Report, IOM 340-90-030-JLS |  | N/A |  |  | Public | Not Specified |  | 11/08/1990
352 | Miles, R - 0000000000 : NO@ADDRESS.GIVEN | Miles, R - 0000000000 : NO@ADDRESS.GIVEN |  | Contamination Control for Susceptible Instruments | During thermal-vacuum testing of Wide-Field/Planetary Camera, the sensitivity of the charge coupled device detectors decreased due to contamination. It was concluded that the standard criteria for the selection of organic and inorganic materials and associated processes with respect to outgassing are not acceptable with a new class of instruments. Each project with contamination-susceptible instruments should specify design criteria and should use decontamination procedures consistent with instrument-sensitivity objectives and project resources. | The standard criteria for the selection of organic and inorganic materials and associated processes with respect to outgassing are not acceptable with a new class of instruments -- those having susceptible optics and sensors operating at cold temperatures. | A task should be undertaken to understand the limits to which spacecraft and instrument contamination can be reduced for various levels of funding, and to develop design criteria and decontamination procedures to achieve these limits. Each project, for each contamination-susceptible instrument, should specify instrument-sensitivity objectives achievable with project resources. Each project with contamination-susceptible instruments should specify design criteria and should use decontamination procedures consistent with instrument-sensitivity objectives and project resources. A task is presently being funded by the WF/PC project to characterize the contamination sources for WF/PC-II. Carry this task through to completion and make the data available for future projects. | JPL | 12/08/1994 | During thermal-vacuum testing of Wide-Field/Planetary Camera (WF/PC-1), the sensitivity of the charge coupled device detectors decreased due to contamination. It was subsequently determined that the source of the contamination was in the instrument, and not in the test equipment. Standard criteria have been used on JPL flight hardware for the selection of materials and processes, for which the selection of outgassing characteristics were of prime consideration. The criteria have required that organic materials have a total mass loss of less than one percent and a collected volatile condensable mass of less than 0.1 percent when tested in accordance with ASTM method E595-77. These standard criteria are no longer adequate and have resulted in the reduction of the useful wavelength ranges of instruments such as WF/PC. These instruments have orders of magnitude increases in susceptibility to contamination because of the low temperatures at which the optics and sensors operate. The standard techniques of boiling off the contamination with flash heating has not proven to be effective, either because the time constant for return of the contamination is too short (minutes to hours) or because polymerization causes the contamination to be permanently adhered. Reference(s): PFR # 53912. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.5 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.2.2.11 ("Mechanical Configuration/Systems Design: Configuration - Contamination Avoidance") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.” | N/A |  |  | Public | Not Specified |  | 06/21/1990
217 | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Retro Propulsion Module Oxidizer Leak During Loading | During propellant loading operations for the Galileo retro propulsion module prior to launch, an oxidizer loading flex line developed a small leak. The leak was caused by an electrostatic charge generated by the flow of the non-conductive oxidizer through the teflon flex line, discharging to the wire mesh covering. Investigate the suitability of using flex lines not susceptible to this type of failure. Verify that electrostatic buildup can be controlled or contained. Consider using new flex lines when hazardous loading operations are performed. Determine maximum flow rates that will prevent electrostatic discharges. | Even if a propellant loading flex line has successfully passed proof and leak tests, a leak can develop when oxidizer is flowing through it, as a result of electrostatic discharge through the wall of the line. | Investigate the suitability of using flex lines not susceptible to this type of failure (i.e. stainless steel bellows). Re-examine the loading procedures to minimize the failure mode, and verify by testing that electrostatic buildup can be controlled or contained. Consider using new flex lines when hazardous loading operations are performed. Investigate the physics of this failure type and determine maximum flow rates that will prevent, by a conservative margin, electrostatic discharges for each combination of non-conducting fluid through non-conducting tubes used in spaceflight operations. | JPL | 11/18/1992 | During final propellant loading operations for the Galileo retro propulsion module in preparations for launch at Kennedy Space Center, an oxidizer loading flex line developed a small leak. No damage to the spacecraft (protected by plastic) or to personnel (protected by scape suits) occurred from the highly toxic, volatile nitrogen tetroxide oxidizer dripping and vaporizing from the line. Microscopic examination of the flex line leak area revealed that the leak was caused by an electrostatic charge generated by the flow of the non-conductive oxidizer through the teflon flex line, discharging to the wire mesh covering. Initial damage may have been caused by carbonized tracks in the teflon line developed during the line cleaning process. Approved procedures for cleaning, proof and leak testing had been performed on the flex line prior to use in the loading process. This particular line was approximately twelve years old. Additional Keyword(s): ESD Reference(s): PFR #54310 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5.4 ("Safety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisition") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.10.1.1 ("System EMC/EMI Design: General - MC Approach") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/19/1990
302 | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN; Billitti, J - | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Wiring Harness Contact Crimp Problem | After a wiring modification to the Galileo Computer Data System (CDS) wiring harness, a wire pulled out of a crimped contact barrel that was too large for the wire. When crimped contacts are to be used in cable harness assemblies, require that color coded contacts and pull tests be incorporated into acceptance test procedures. | Visual inspections and continuity checks are not adequate verification that cable harness assemblies have been fabricated correctly. | When crimped contacts are to be used in spacecraft or ground support equipment cable harness assemblies, a requirement should be imposed on the fabricators, that color coded contacts and pull tests be incorporated into acceptance test procedures. | JPL | 09/15/1993 | During a continuity test of the Galileo Computer Data System (CDS) wiring harness, after a wiring modification, an open circuit was detected between two connectors. Investigation revealed that a wire had pulled out of a crimped contact barrel in a connector, causing the open. Further analysis revealed that the problem was caused by a crimp contact sized for No. 20 AWG wire being used for a No. 28 AWG wire. The fabrication error was difficult to detect because the crimp connection failed only after extensive handling stress to the harness. The resolution of the problem was to color band the smaller crimp contacts for positive identification, and the development of a pull-test tool for 100% verification of each crimped wire in a connector. No crimped contact failures have reoccurred at JPL since the inception of this practice in 1984. Reference(s): PFR #40886 and PFR #41229 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.17.9.1 ("Engineering Practices: Hardware Development - Electronic Packaging/Cabling Design and Fabrication") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 01/26/1990
381 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Antenna Test Difficulty at Air Force Eastern Test Range | Although measurements at JPL suggested that the Voyager antenna system and its RF probe were not strongly affected by the building environment, the building environment at the test range location caused noticeable RF variations. When planning RF tests in different facilities, pathfinder tests should be conducted. Use RF probes with high directivity and shield the antenna from metallic surroundings that cause RF reflections. | RF testing can be strongly affected by the building environment. | When planning RF tests in different facilities, pathfinder tests should be conducted to minimize loss in measurement precision or to eliminate the need for extensive workarounds. In conducting RF tests it is important to use RF probes with high directivity and to shield the antenna from metallic surroundings which cause RF reflections. | JPL | 02/13/1995 | The extreme Radio Frequency (RF) reflections due to the building environment at the Air Force Eastern Test Range (AFETR) hindered system measurements on the Voyager flight radio and antenna. The intended measurements were to be made using a small directive RF probe mounted on the antenna reflector. Previous repeatable JPL measurements in the JPL Spacecraft Assembly Facility high bay led to an erroneous assumption that the Voyager antenna system and its RF probe were not strongly affected by the building environment. At the AFETR, the location and the movement of overhead cranes caused noticeable RF variations. Additional Keyword(s): Performance Verification |  | N/A |  |  | Public | Not Specified |  | 12/19/1989
379 | Marr, J - 0000000000 : NO@ADDRESS.GIVEN | Marr, J - 0000000000 : NO@ADDRESS.GIVEN |  | Violation of Magellan Electrical and Grounding Specification | A violation of electrical interfacing and grounding requirements for Magellan resulted in substantial damage to the CDS analog telemetry circuitry. Care must be taken to ensure that design changes are properly reviewed. A formal project waiver of requirements should be obtained. | Violations of electrical interfacing and grounding requirements can have serious consequences and should not be undertaken lightly or without a formal project waiver. | Care must be taken to ensure that design changes are properly reviewed. | JPL | 02/01/1995 | In an effort to take advantage of spare telemetry channels in the Command and Data System (CDS) hardware, the Attitude Reference Unit (ARU) motor current telemetry was added to the CDS analog telemetry channels of the Magellan (MGN) Spacecraft. This addition was made late in the design of the spacecraft and utilized the spacecraft chassis for the ARU motor current telemetry signal return path which was in direct violation of VRM 2-260, "Electrical Grounding and Interfacing" specification. A waiver of the VRM 2-260 requirements for this design was not initiated. Subsequent failure of the chassis ground path, caused by a poor mechanical connection at the attitude and articulation control subsystem single point ground, resulted in substantial damage to the MGN CDS analog telemetry circuitry. This required rework of the CDS, resulting in a late delivery to the spacecraft at Kennedy Space Center. Reference(s): Martin Marrieta Aerospace Group MARS #B16065. JPL IOM 5211-89-305, "Removal of Red Flag Rating from MGN Mars #B16065," dated 25 April 1989, by M. Boyles, J. Quinn. | JPL has referenced the lesson as supporting Paragraph 2.3 ("Introduction: Compliance Assessment") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 11/16/1989
382 | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan Solid Rocket Motor Safe and Arm Device | Given unclear procedures, had an assembly technician not questioned the assembly of the SRM Safe and Arm (S&A) devices, the SRM would have failed to ignite at the time of Venus orbit insertion. Recommendations involve providing cognizant personnel, clear procedures, independent checks, and training. Seal unused mechanical or electrical connections. | Unclear procedures and lack of cognizant technical personnel in attendance can result in incorrect assembly of mission critical mechanical or electrical connections. | Cognizant personnel, thoroughly familiar with the hardware, must be involved during the conduct of any critical or hazardous operation. Prior to performing any critical or hazardous operation on a spacecraft, procedures must be reviewed for clarity and correctness, and approved by cognizant technical personnel. If an assembly operation is untestable for verification, an independent check should be incorporated in the procedure (picture, X-ray, etc.). Unused mechanical or electrical connections should be sealed or otherwise protected to avoid misconnection by assembly technicians. Personnel involved in critical or hazardous operations on a spacecraft must practice the procedures and be qualified by hands-on experience. | JPL | 02/13/1995 | During final preparations for the Magellan launch at Kennedy Space Center, the Solid Rocket Motor (SRM) Explosive Transfer Assembly (ETA) lines were incorrectly assembled to the inert ports of the Safe and Arm (S&A) devices. The assembly error was caused by unclear procedures, an improperly labeled diagram in a field service manual, no cognizant personnel familiar with the S&A device in attendance and inadequate mechanical locking of the plug in the S&A inert port. The assembly technician had second thoughts and concerns over the correctness of the installation. At the manufacturing facility he examined the S&A device data package and checked with knowledgeable engineering personnel to verify that the assembly was in error. Had the error not been corrected, the solid rocket motor would have failed to ignite at the time of Venus orbit insertion. Additional Keyword(s): Propulsion | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.8 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 07/27/1989
386 | Marr, J - 0000000000 : NO@ADDRESS.GIVEN | Marr, J - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan Battery Fire | A technician inadvertently shorted a connector on the test battery to a wrong harness connector. The resultant battery short circuit destroyed the test battery, the battery wiring harness, and the flight harness connector, and ignited the thermal blanket. Batteries should be mated to flight spacecraft only in a fully discharged state, and several cable and connector design suggestions are made. | Inadvertent shorting of a battery when connecting it to the spacecraft can damage flight hardware. Design of spacecraft connector locations with no direct visual access can result in mismating of connectors during spacecraft assembly operations. Connector designs which allow pin contact prior to full engagement of the alignment keys can result in direct shorts if connectors are inadvertently mismated. Design of spacecraft connector locations with no direct visual access can result in mismating of connectors during spacecraft assembly activity. Connector designs which allow pin contact prior to full engagement of the alignment keys can result in direct shorts if connectors are inadvertently mismated. Kapton wire insulation can be a significant contributor to the cause of fire in wiring harnesses and cables. | Batteries should be mated to flight spacecraft only in a fully discharged state. Cables should be dressed and tied such that connections to wrong connectors are physically impossible. Connector designs should be selected such that pins can only make contact after full engagement of all alignment keys. This is particularly important when power connections are involved. Spacecraft design should avoid, whenever possible, connector locations that require blind mating of connectors. Design umbilical and direct access circuitry with protection to withstand direct shorts at the external connector interface without damage to the spacecraft. Use of Kapton insulation should be critically examined, particularly in spacecraft power circuit applications. | JPL | 02/23/1995 | During Magellan prelaunch activity at Kennedy Space Center, a technician, attempting to connect a test battery to the spacecraft, inadvertently shorted the battery connector to a wrong harness connector. The resultant battery short circuit destroyed the test battery, the battery wiring harness, the flight harness connector and ignited the thermal blanket. The use of Kapton insulated wire in the battery wiring harness was a significant contributor to the cause of the fire and resultant destruction of the harness. As a result of the event, the spacecraft was impounded until a NASA review board conducted an investigation. Fortunately all spacecraft damage was repairable; however, this resulted in over a week's impact on an already tight schedule. The event was caused by: The connector connection had to be made with no direct visual access because of the location and thermal blanket obstruction. The connectors were thought to be designed to prevent pin contact until the alignment keys of the connectors were sufficiently engaged to ensure a correct connection. This was not the case and sufficient contact was made between at least two pins of the mismated connectors to cause the short and resultant damage. Reference(s): Magellan Investigation Board Report, 3/24/89 | JPL has referenced the lesson as supporting Paragraph 4.2.2.2 ("Mechanical Configuration/Systems Design: Configuration - "Blind" Connectors") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 06/29/1989
385 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN; Wilson, R - | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | Hydra-Set* Applications and Hazards | Lifting incidents with Magellan and the Delta Star instrument show that lifting flight hardware with cranes using hydraulic Hydra-Sets involves potential hazards, including Hydra-Set up pump handle breakage, seal failure and oil leakage. Use only modified hydraulic Hydra-Sets, take protective measures when sensitive or optical surfaces must be exposed to potential Hydra-Set leakage, and review Hydra-Set handling procedures. | Lifting flight hardware with cranes using hydraulic Hydra-Sets involves potential hazards, including Hydra-Set up pump handle breakage, seal failure and oil leakage. | Handling spacecraft flight hardware is potentially hazardous and should be entrusted only to trained and skilled technicians, whether JPL or contractor, who are familiar with the laboratory's established practices and their rationale. The Del Mar Avionics company has modified the Hydra-Set design to reduce the probability of up pump handle breakage. Only appropriately modified hydraulic Hydra-Sets should be used. When sensitive or optical surfaces must be exposed to potential Hydra-Set leakage, consideration should be given to protective measures. Prior to initiation of any assembly or major equipment handling operations; Safety, Quality Assurance and handling procedures should be reviewed to assure that the appropriate cautions and restrictions on the use of Hydra-Sets are included. | JPL | 02/21/1995 | For the last several years, JPL has required the use of hydraulic Hydra-Sets when lifting spacecraft flight hardware with cranes. The Hydra-Set is a crane hook mounted device that permits precision raising and lowering, avoiding the shocks and stresses associated with attempting small movement using the crane on/off controls. Recently, two events occurred involving Hydra-Set usage. One involved hydraulic oil leakage onto the Delta Star instrument due to the Hydra-Set up pump handle breaking off internally during an assembly activity during launch preparations at McDonnell Douglas. The second was with the Magellan Spacecraft during launch preparation at KSC when a Hydra-Set seal burst because of an overload due to using the wrong size Hydra-Set. Fortunately, neither event caused any catastrophic damage. *Hydra-Set is a trademark of Del Mar Avionics Co., Irvine, CA. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.4 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 04/03/1989
355 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Photopolarimeter Radiometer (PPR) Cover Damage During Assembly and Test | The Galileo Photopolarimeter Radiometer subsystem cover was damaged on three separate occasions during assembly and test operations. Design all external areas of spacecraft flight hardware with consideration for assembly and handling operations: avoid sharp or pointed corners. Conduct physical surveys to identify hardware that is susceptible to handling damage. | When external areas of spacecraft flight hardware are not designed with regard for assembly and test operations, protective guards and other procedural safeguards can be inadequate to prevent damage to delicate hardware. | All external areas of spacecraft flight hardware should be designed with consideration for assembly and handling operations. In particular, sharp or pointed corners, which could easily snag protective clothing should be avoided. This should be a topic for preliminary and critical design reviews at subsystem, instrument and system levels. Physical surveys should be conducted early in the assembly operations to identify hardware that is susceptible to handling damage. Protective guards and other procedural safeguards should be developed early before damage occurs. In situations where these safeguards are not possible or adequate, a second technician (buddy system) should be assigned to monitor and assist in the operation to provide another level of protection. | JPL | 12/12/1994 | The Galileo Photopolarimeter Radiometer (PPR) subsystem cover was damaged on three separate occasions during assembly and test operations. The PPR cover is very delicate and has sharp corners that make it vulnerable to snagging. The damage occurred during thermal blanket operations which required access to areas behind the PPR location and was caused by a technician's protective clothing snagging on the sharp edges of the PPR cover. After the first incident, when damage was relatively minor and easily repaired, the workers were cautioned to avoid this problem. In the second incident, damage was serious and required rework. A protective guard was then built to protect the cover. The third incident happened after this protective guard had been removed to permit further thermal blanket fitting activity. All of the incidents occurred even though the work was being performed by well trained, experienced and highly qualified technicians under the watchful eye of QA personnel. After the third incident, the mechanical assembly procedures were revised to require a second technician (buddy system) to continuously monitor and provide a shielding arm or hand to protect sensitive areas not observable by the technician doing the work. Additional Keyword(s): Hardware Integration Reference(s): PFRS # 45429, 45463, and 45482 | JPL has referenced the lesson as supporting Paragraph 4.2.2.3 ("Mechanical Configuration/Systems Design: Configuration - Sharp Edges") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.” | N/A |  |  | Public | Not Specified |  | 03/02/1989
301 | Koch, J - 0000000000 : NO@ADDRESS.GIVEN | Koch, J - 0000000000 : NO@ADDRESS.GIVEN |  | Electrostatic Discharge (ESD) Wrist Strap Contamination of Magellan Flight Hardware | A short circuit during subsystem level testing of the Magellan Command and Data Subsystem (CDS) was traced to a conductive fiber likely shed by an ESD wrist strap. Use non-shedding ESD wrist straps. All personnel who work near critical hardware must take special care to avoid contamination. | Electrostatic Discharge (ESD) wrist straps can shed conductive metallic fibers into electronic hardware. | Fabric type Electrostatic Discharge (ESD) wrist straps containing conductive metallic fibers should not be used in the assembly, fabrication, or handling of electronic hardware. Nonshedding ESD wrist straps are available. Special care is required from all personnel who work in close proximity to critical hardware to avoid contamination of any type. All aspects of fabrication and test of critical hardware should be carefully reviewed before initiation of an activity. | JPL | 09/15/1993 | During subsystem level testing of the Magellan Command and Data Subsystem (CDS), the test support equipment indicated an extra event for the relay controlling Critical Enable (CE) Event B03. It was theorized that a short between two specific pins of the CE relay could have caused the observed failure. When the relay was probed to verify the cause, the failure characteristic disappeared. Close visual inspection revealed a fine hairlike structure lying on one relay pin and possibly making contact with others. The object was removed and analyzed using a Scanning Electron Microscope (SEM) and an Energy Dispersive Spectrometer (EDS). The analysis revealed that the object was a conductive metal fiber, identical in diameter (.0003"), surface characteristics and composition to metal fibers woven into the fabric of elastic Electrostatic Discharge (ESD) wrist straps. Reference(s): PFR #44931 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.1 ("Engineering Practices: Materials, Processes and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/05/1988
392 | Marr, J - 0000000000 : NO@ADDRESS.GIVEN | Marr, J - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo AACS Excessive Memory Keep Alive (MKA) Current Draw | Excessive Memory Keep Alive (MKA) current draw in the Galileo AACS was traced to 41 sneak paths between the MKA power supply and the memory's unpowered interface power supply. Look for potential sneak paths through interfaces between powered and unpowered portions of a subsystem. Address these interfaces at CDR and in the ECR approval process. | Sneak paths between subsystems or between powered and unpowered portions of a subsystem can result in excessive current draw. | The cognizant engineer must pay particularly careful attention to interfaces between powered and unpowered portions of his subsystem or between his subsystem and other subsystems to allow early detection and correction of potential sneak paths. These interfaces should be singled out for special attention during the design and development of all subsystems. Interfaces between powered and unpowered portions of subsystem circuitry should be specifically addressed at Critical Design Reviews (CDR) and in the Engineering Change Request (ECR) approval process. | JPL | 02/24/1995 | Memory Keep Alive (MKA) current draw in excess of the maximum specification was observed in the Galileo Attitude and Articulation Control Subsystem (AACS) on the spacecraft in the Spacecraft Assembly Facility (SAF) prior to the scheduled 1986 launch. This occurred again during subsystem test of modifications made to the AACS in preparation for the Galileo VEEGA Mission. Excessive MKA current draw had the potential of endangering the integrity of both AACS memories by pulling the MKA voltage below the minimum required for memory retention. It also had the potential for causing loss of contents of both AACS memories by blowing the MKA supply fuses in the power subsystem. Investigation led to the discovery of forty-one (41) sneak paths between the 10 volt MKA supply and the memory's unpowered 5 volt TTL interface supply. These sneak paths resulted in the 5 volt supply voltage being raised sufficiently to partially turn on many of the forty-one 78L12 interface drivers such that they were in an intermediate logic state, allowing each to draw as much as 30 milliamps of current. This provided the potential to draw as much as three times the maximum specified AACS MKA current. Reference(s): PFR # 45982 and #50424. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.3 ("Safety and Mission Assurance Practices - Reliability Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/20/1988
371 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | SEASAT Failure | The SEASAT Spacecraft failed in orbit due to arcing between adjacent slip ring brush assemblies. It was discovered that the Agena bus had been substantially modified, but were treated as a heritage design not requiring requalification. Plans should be made early in the project to fully evaluate the heritage of previously used equipment. When conducting a FMECA on electrical components, electrical short failure modes should be considered. | "Heritage" hardware designs, previously flown on prior missions, can still contain design errors. Consideration of electrical shorts as a potential failure mode during FMECA of the power system is of critical importance. | The uncritical acceptance of equipment that has been classified as "standard" or "flight proven" should be avoided, especially if modifications of any level have been made on this equipment. Plans should be made early in the project to fully evaluate the heritage of previously used equipment. The degree of evaluation may have to be contractually defined on fixed-price contracts. When conducting a FMECA on the power system and other electrical components, electrical shorts should be considered as one of the potential failure modes. | JPL | 01/24/1995 | The SEASAT Spacecraft failed in orbit due to a massive and progressive short in the slip ring assembly connecting the rotating solar array to the power subsystem. The most probable cause of this short was the initiation of an arc between adjacent slip ring brush assemblies. The slip ring assembly was connected into the power system such that the adjacent brush assemblies were of opposite polarity, an arrangement particularly prone to shorting. The SEASAT prime contractor was aware of instances of slip ring failures due to shorting on other projects, but did not communicate this information to the SEASAT project office. This lack of communication may have been the result of the classified nature of the other projects. The failure to give the slip ring assembly the attention it deserved was rooted in the contract structure and the SEASAT implementation policy. SEASAT was a dual contract; a fixed price for the Agena bus containing flight proven subsystems and a cost-plus award fee for the payload module which was integrated with the Agena bus. By contract, implementation plan, and resource constraints, JPL had no significant oversight of the Agena bus. The failure review board established that the Agena power, attitude control, and data subsystems were substantially modified, but were treated as closely similar designs not requiring requalification. This consideration of the Agena bus as flight-proven standard equipment led to the failure to report significant component failures, waiving tests and weak compliance with specifications. In addition, the Failure Mode Effects and Criticality Analysis (FMECA) conducted on the power system did not consider shorts as a potential failure mode. Additional Keyword(s): Inherited Equipment, Slip Rings |  | N/A |  |  | Public | Not Specified |  | 10/05/1988
377 | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN; Bryant, J - | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN |  | Performance Decrease due to Propulsion Thruster Plume Impingement on the Voyager Spacecraft | A 21% shortfall in Voyager's velocity change was suspected to be due to exhaust plume impingement. Due to the complexity of spacecraft/thruster configurations, additional care must be taken in the development and utilization of spacecraft and plume models. Analysis should be conducted on early and final designs. | Rocket engine plume effects can vary dramatically as a function of thruster type, location, and operating conditions, and interaction of plumes with the spacecraft structure and/or other subsystems can have a substantial impact on spacecraft performance. | Due to the complexity of spacecraft/thruster configurations, additional care must be taken in the development and utilization of spacecraft and plume models. Analysis should be conducted on early and final designs, as part of the normal design team activity. | JPL | 01/31/1995 | The initial Voyager Spacecraft Trajectory Correction Maneuver (TCM) delivered approximately 21 percent less velocity change than had been predicted. Since the spacecraft telemetry indicated that pointing accuracy, thruster performance, and spacecraft equipment all were normal, it was suspected that the degradation was due to exhaust plume impingement effects. Subsequent analysis indicated that pre-flight models underestimated the effects of plume impingement due to over-simplified geometry models and inadequate characterization of rarefied gas dynamics flow fields. Reference(s): PFR #41003. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.2.2.6 ("Mechanical Configuration/Systems Design: Configuration - Plume Impingement") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/22/1988
383 | Marr, J - 0000000000 : NO@ADDRESS.GIVEN; Lisman, P - | Marr, J - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo AACS Computer Memory Access Contention Problem | Galileo AACS checksum errors resulted from bus contentions caused by noise from electromagnetic coupling within the AACS intra-subsystem harness. Recommendations included simulations and other methods for thoroughly characterizing the electrical performance of cables. | Design to JPL or project standards is not always sufficient to ensure adequate performance of subsystem cabling. In this era of rapid technological change, design standards, used successfully in the past, may not be sufficient to preclude problems in the present. Simulators of subsystem interfaces with other subsystems may not always provide adequate performance assessment for the spacecraft environment. Limited fidelity of simulators used during subsystem testing can prevent diagnosis of subsystem problems prior to spacecraft integration. | The cognizant engineer must fully consider the electrical performance of the cable in his specific subsystem application. The subsystem impact of simulator limitations should be thoroughly understood and documented. Additionally, testing with integrated breadboards instead of simulators should be encouraged. Subsystem equipment must be adequately tested on the spacecraft in all redundant configurations to ensure that equipment configuration dependent problems are found. Noise on intra-subsystem cabling must be thoroughly investigated as to cause and effects as early as possible in subsystem testing. | JPL | 02/15/1995 | During system level testing, repeated Attitude and Articulation Control Subsystem (AACS) checksum errors occurred without the presence of actual memory content errors (miscompares). These checksum errors occurred only when in one of the four possible CPU-memory configurations and only when the Command and Data Subsystem (CDS) was accessing the off-line memory. Extensive troubleshooting on the spacecraft showed that the anomalous checksum errors were being caused by both AACS memories placing data on the data bus at the same time (bus contention). After further subsystem testing and analysis, subsystem engineers determined that the bus contentions were caused by electromagnetic coupling within the AACS intra-subsystem harness while simultaneously accessing both AACS memories. Specifically, data being placed on the data bus by the on-line memory induced noise on the address lines which caused the off-line memory to turn on its data line drivers during an off-line CDS Direct Memory Access (DMA) cycle. The noise coupling between the Address and Data lines occurred in spite of AACS bay harness design which was in compliance with JPL and Galileo design standards. Further, the limited fidelity CDS simulator used during subsystem testing prevented finding the problem prior to spacecraft integration. Additional Keyword(s): Circuit Noise Reference(s): PFR #44836. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.3 ("Engineering Practices: Design and Verification for Environmental Compatibility") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.10.1.2 ("System EMC/EMI Design - Minimizing EMI") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/01/1988
281 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Attitude Control Power on Reset Problem | A potentially catastrophic Power On Reset (POR) was discovered during testing of the Galileo orbiter. The problem was traced to noise from a capacitive coupling path between flight subsystem ground and support equipment ground. AC ground paths should be testable and should be verified in system interface verification tests. Interface circuits should be analyzed to identify any AC coupling paths between independent ground trees. | AC as well as DC ground paths can be significant in noise coupling between circuits. | AC ground paths should be testable and should be verified in system interface verification tests. Interface circuits should be analyzed to identify any AC coupling paths between independent ground trees. | JPL | 07/12/1993 | During testing of the Galileo orbiter, an anomaly occurred at infrequent intervals: an unexpected Power On Reset (POR) event would reinitialize the attitude control subsystem. The POR was recognized as a serious, potentially catastrophic problem, and high priority was given to isolating a cause and verifying a fix. Despite exhaustive investigations and significant design changes to improve noise immunity, the problem continued to occur, infrequently but persistently. Ultimately, a cause and cure were identified. Although exhaustive test and analysis of ground paths had been carried out, the noise source was identified as a capacitive coupling path between flight subsystem ground and support equipment ground. When spacecraft power surges such as turning on the Travelling Wave Tube Amplifier (TWTA) occurred, the two grounds would experience a transient oscillatory voltage difference of over seven (7) volts. The "AC Ground Loop" fed the transient into the POR sensing circuit and occasionally triggered it. Eliminating the capacitor in the support equipment solved the problem. Additional Keyword(s): Grounding |  | N/A |  |  | Public | Not Specified |  | 08/11/1988
366 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | Infrared Astronomical Satellite (IRAS) Contamination Control Challenges | IRAS posed new challenges to contamination control due to the extremely low temperatures (3 degrees Kelvin) required to achieve successful low noise infrared signal detector operation in the focal plane assembly. The elaborate contamination control precautions listed in the lesson were believed critical to mission success. | When spacecraft design requires extremely low temperatures to achieve successful operation, elaborate contamination control precautions are critical to mission success. | Required contamination control precautions include: Design for avoidance and control of contaminants. Measure contaminants in test environments and facilities. Identify and control contamination sources. Provide for protection during the transportation and launch environments. Design to minimize contaminant migration. Plan to clean contaminants off. Design for in-mission contaminant removal (heaters, wipers and covers). | JPL | 01/13/1995 | IRAS was a cooperative Dutch Space Agency/NASA undertaking in which the spacecraft bus was built in Europe, then integrated with the NASA Infrared Telescope. The new challenges to contamination control were related to the extremely low temperatures (3 degrees Kelvin) required to achieve successful low noise infrared signal detector operation in the focal plane assembly. At these low temperatures, all gases except helium are solid. There are two separate contamination problems. The first is caused by air leakage into the plumbing when the system is cold and sub-atmospheric, resulting in plugged vents, tubes and valves, creating major safety problems or system malfunction. The solution includes care in the selection of transfer line and flight plumbing hardware, control of procedures, and use of purge covers to maintain a helium atmosphere on the high pressure side of any valve which may allow air leakage into the cold plumbing. The second problem is that exposed surfaces this cold can readily condense vapors from normal outgasing even in the vacuum of space, causing performance degradation by contamination of the optical surfaces or affecting temperature control surfaces. This complicated the development, assembly and test program for IRAS by the need to avoid contamination by any materials that could later evaporate and condense on the cold surfaces. Facility air environments had to be monitored and controlled to avoid contaminants, and handling and shipping equipment required the same extreme precautions. The contamination control situation was further complicated by the air shipments to Europe for integration, back to JPL for space simulator testing, and transportation to Vandenberg Air Force Base for launch. The successful completion of the IRAS mission attests to the success of the design and control measures accomplished. No apparent performance degradation occurred during the mission. Additional Keyword(s): Cryogenics Reference(s): JPL D-842, IRAS Telescope Development: Technical Lessons Learned. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.5 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.2.2.11 ("Mechanical Configuration/Systems Design: Configuration - Contamination Avoidance") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.” | N/A |  |  | Public | Not Specified |  | 08/04/1988
305 | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Retro Propulsion Module (RPM) Flow Decay Problem | To reduce costs, the Mars Observer propulsion and other subsystems followed design practices more common to earth-orbiting satellites than to planetary missions. Consider contractor experience in bipropellant spacecraft propulsion system design in source selection. To manage risk on one-of-a-kind developments, assure thorough technical oversight of contractors with limited experience in the design of interplanetary spacecraft. | Contaminants created by the interaction of stainless steel lines and components with nitrogen tetroxide oxidizer can result in the blockage of small oxidizer flow passages and filters. | The use of stainless steel components in combination with nitrogen tetroxide should be eliminated where obstruction in small passages may occur. Projects of long mission duration that use nitrogen tetroxide oxidizer systems and cannot avoid the use of stainless steel should develop a mechanism to predict flow decay hazard conditions. Oxidizers should be purified immediately before loading to minimize contamination products. | JPL | 09/01/1993 | When the Galileo launch date was delayed from 1986 to 1989 with an increase in mission duration from four to eight years, the RPM design was re-evaluated. It was determined that a significant risk existed of in-flight loss of propulsion capability over the extended mission due to oxidizer flow decay. Flow decay is due to blockage of small oxidizer flow passages and filters by the accumulation of contamination products caused by interaction between the stainless steel lines and components with the nitrogen tetroxide oxidizer. Replacement of most of the stainless steel oxidizer feed system with titanium has alleviated the concern. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.14.1 ("Management Practices: Acquisition and Surveillance"), and Paragraph 6.10.1 ("Engineering Practices: Materials, Processes, and Contamination Control - Practices") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 04/07/1988
384 | Flynn, K - 0000000000 : NO@ADDRESS.GIVEN | Flynn, K - 0000000000 : NO@ADDRESS.GIVEN |  | Cone Angle Anomaly in Canopus Star Tracker | An anomaly in the cone angle circuitry of the Voyager Canopus Star Tracker was probably due to a Delrin insulating sleeve decomposing after exposure to Jupiter radiation fields, causing a high resistance path through the Delrin. Ground metal shielding boxes and metal masses on circuit boards, analyze/test materials that could be exposed to ionizing radiation, and maintain spare hardware to enable failure analysis. | Charging of internal elements to as high as several hundred volts can occur due to radiation fields. Exposure to ionizing radiation can degrade spacecraft materials. Availability of spare hardware is extremely useful in verifying in-flight failure modes. | All metal shielding boxes and metal masses on circuit boards should be grounded even though they are inside equipment housings. All materials that could be exposed to ionizing radiation should be analyzed/ tested to insure that unacceptable degradation will not occur. A set of spare hardware should be maintained to enable analysis of in-flight failures and validation of proposed corrective actions. | JPL | 02/15/1995 | Shortly after Voyager I Jupiter encounter, an anomaly occurred in the cone angle circuitry of the Canopus Star Tracker (CST). The cause of the problem was determined to be a base-emitter or collector-emitter leakage in a transistor circuit that drives the cone angle deflection plates. This problem was duplicated in a spare CST. The most probable cause of the leakage path in the transistor circuitry is believed to be two-fold; 1) a Delrin insulating sleeve decomposed after exposure to Jupiter radiation fields and 2) development of a high resistance path through the Delrin by electrostatic discharge from an ungrounded tungsten radiation shield box. Additional Keyword(s): Grounding Reference(s): Failure Investigation Report EM 343-494 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.1 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.1.5.1 ("Flight Electronics Hardware System Design: General - Radiation Design Factors") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/14/1988
353 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | Facility Failure During Testing of the Galileo Near Infrared Mapping Spectrometer (NIMS) | During a recalibration test of the Galileo NIMS flight instrument in a subsystem vacuum chamber, a facility failure subjected it to subjected to a temperature below its qualification limits. Subsystem facilities must be critically examined for the probability of any failure modes which may subject flight hardware to out-of-specification environments. Specification limits should be alarmed, and there should be straightforward safing procedures available to the operator. | Environmental test chambers are subject to several hazards not familiar to most practicing engineers and technicians. Cryogenics, vacuum systems, and thermal control systems all have serious potential safety risks if wrong materials, parts, or assembly techniques are used. Once incorporated, these improper elements may perform well for indefinite periods before bursting, leaking, or otherwise failing. They look ok, they work ok, but they aren't ok. | Subsystem facilities must be critically examined for the probability of any failure modes which may subject flight hardware to out-of-specification environments. Specification limits should be alarmed separately from control system limits. Operator response to alarms should be covered by straightforward safing procedures. The proposed use of nonstandard facilities for flight hardware should be very carefully weighed during the planning phase of a project or task and the following should be considered: Safety certification isn't a foolproof process. Availability of qualified operators is a greater problem for small subsystem teams than for the officially prescribed environmental test lab, particularly if long-term tests are planned. Upgrading facilities to meet requirements that are imposed because of the testing of flight hardware is likely to be expensive in schedule and dollars. Damage and subsequent repair to flight instruments or subsystems is costly in both schedule and dollars and could have severe project and mission impact. | JPL | 12/09/1994 | During a recalibration test of the Galileo NIMS flight instrument in a subsystem vacuum chamber, a facility failure occurred. A liquid nitrogen supply line fitting separated, causing liquid nitrogen to spray on the outside of the chamber, and filling the room with fog. After the break was repaired and in preparation to restart the test, four additional failures occurred, one of which caused the flight instrument to be subjected to a temperature below its qualification limits. These failures can be attributed to substandard liquid nitrogen plumbing, a known idiosyncrasy in a control circuit and human error. Before the flight instrument was permitted to be tested in the subsystem facility, the required safety certification process had been accomplished and a flight projects office waiver had been requested and approved. The reason for requesting to test in a facility other than the JPL environmental test lab was so as not to introduce unknowns into the recalibration process. Additional Keyword(s): Science Instruments | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/17/1987
398 | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Command and Data Subsystem (CDS) Marginal Power Supply Voltages | After rework of a Galileo subsystem, it was discovered that the size of PWB traces in a subsystem power supply had the effect of limiting voltages elsewhere in the system. The problem was corrected by adding conductors in parallel with the traces. Subsystem design analysis must consider all aspects of the end-to-end implementation, and subsystem testing must duplicate all aspects of the flight system configuration that could affect subsystem performance. | The trace size of subsystem printed wiring board conductors can affect system level voltages. | Subsystem design analysis must not only include the circuit design, but all aspects of the end-to-end implementation, including such things as current carrying capacity of printed wiring board conductors. Testing at the subsystem level must include realistic duplication of the flight system configuration that could affect subsystem performance, including consideration for worst case system conditions. | JPL | 06/07/1995 | Following rework of the Galileo Spin Bearing Assembly (SBA), tests were conducted at the system level to assure that the changes made in the SBA did not affect spacecraft operation. Results of the tests showed lower than expected CDS voltages on the despun side of the CDS. These low voltages were isolated to the trace size of the printed wiring board conductors within the main CDS power supply. The problem was corrected by adding conductors in parallel with the power supply printed wiring board traces. Reference(s): PFR #44928 | JPL has referenced the lesson as supporting Paragraph 4.3.3.2 ("Power/Pyrotechnics Design: Power Generation - Power Demands") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 11/17/1987
276 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate Ground Data Processor | Contractor proposals for digital processors were rejected for cost reasons in favor of upgrading a unit under development by JPL. However, the use of R&D equipment resulted in unacceptable performance and reliability. When funding constraints require consideration of trade-offs or use of R&D equipment, evaluate the reliability and capability of the equipment. | The Ground Data Processor is a key element in any end-to-end data system such as a Synthetic Aperture Radar system. | When funding constraints require that trade-offs be made and the use of R&D equipment is contemplated, one must evaluate the operability and maintainability for continued reliable operations support. | JPL | 07/09/1993 | To process the Synthetic Aperture Radar (SAR) data received from the SEASAT spacecraft, the project first evaluated contractor proposals for digital processors. They rejected all as too expensive and chose instead to upgrade an existing JPL "research and development" (R&D) optical correlator. The R&D correlator did successfully process SEASAT SAR images. However, the project had insufficient funds remaining to include the planned automatically controlled mode. The R&D correlator also proved less reliable than operational equipment, thus did not process the expected volume of data. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.3 ("Engineering Practices: System Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/13/1987
368 | Dumas, L - 0000000000 : NO@ADDRESS.GIVEN; Coyle, G - | Dumas, L - 0000000000 : NO@ADDRESS.GIVEN |  | Damage of Galileo Flight Antenna from Testing | Galileo: The spare Galileo high gain antenna was damaged during modal, acoustic, and pyro shock testing, resulting in the revocation of the flight qualification of the spare. Be cautious of informal environmental testing to validate analytical models; it is typically conducted without the strict test controls and unambiguous assignment of responsibility that are required for testing of flight subsystems and spacecraft. | Informal environmental testing to validate analytical models is typically conducted without the strict test controls and unambiguous assignment of responsibility that are required for testing of flight subsystems and spacecraft. The use of flight or flight spare hardware as aids in developmental testing can result in increased risk to mission critical hardware. | The consequences and risk of damage to flight or developmental hardware imposed by test levels and test environment must be evaluated by the project office and the supporting technical division(s) with a formality commensurate with the consequences. To clearly understand the results of environmental tests, especially those that include exploratory or characterization aspects, detailed physical and functional inspection should be performed between "separate tests" to isolate any problems attributable to each particular test. The responsibility for the care and handling of any flight hardware should be unambiguously assigned throughout its preflight operational lifetime. Transfer of this responsibility should be unambiguous and formal. Kinematically indeterminate structures, not capable of detailed analysis, should be tested with prototype hardware rather than flight hardware. | JPL | 01/13/1995 | The Galileo Spacecraft Development Test Model (DTM) included the spare flight antenna subsystem (SXA-1). Informal characterization testing used to validate the analytical model included extensive modal vibration testing. Several organizations were involved in both developing and conducting the tests. At the conclusion of three tests (modal, acoustic, and pyro shock), three problems were identified: 1) the surface mesh, restraining cords, certain fittings, and sunshade were damaged, 2) the number of vibration cycles permitted by Space Transportation System (STS) safety criteria had been exceeded, and 3) the antenna failed to deploy properly due to a cord snag. The first problem, which reduced RF output by 3.4 dB at X-band, was probably caused by fatigue-type wear during modal testing. The second problem was the result of a calculation error during the test and would have precluded the use of the antenna for STS launch without some sort of refurbishment and requalification. The third problem, potentially mission catastrophic, was the third observed occurrence of a snag, indicating underlying design problems. The project declared the SXA-1 antenna nonflight qualified due to gain loss, noncompliance with STS criteria, and questionable deployment reliability. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.7 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/13/1987
388 | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Command Data Subsystem Memory Devices (Leadless Chip Carriers) Rework Problems | When large strips of conformal coating were removed from Galileo CDS boards, the process caused the coating to expand and stress the solder joints. The recommendations provide cautions on modification of existing procedures to include methods and processes which have not been proven and qualified. | The modification of existing procedures to include methods and processes which have not been proven and qualified, especially when applied to new technology, greatly increases program risk. | Use of existing procedures, particularly in the materials and fabrication areas, should be carefully reviewed and followed. Extensions or modifications to standard procedures beyond their planned use should be carefully evaluated before use in a new application. Utilization of laboratory areas of expertise and standard documentation should be maximized by all designers of subsystems and modules. This is especially beneficial in the areas of packaging, materials and processes. New technology applications should be carefully reviewed. | JPL | 03/09/1995 | The Galileo Command Data Subsystem tests uncovered a "read disturb" problem of the memory chips which required extensive rework of the flight boards. Due to the extensive rework and short schedule, the conformal coating was removed in large strips rather than in small areas. The flight memory boards were submerged in an alcohol bath, the conformal coating removed, and the failed parts replaced. Subsequently it was discovered that the parts adjacent to those replaced exhibited some fractures in the solder joints. The combination of the prolonged alcohol bath and the subsequent heating of the conformal coating around and under adjacent parts caused the coating to expand and stress the solder joints. Lack of experience with leadless chip carriers was a contributing factor in this event. Additional Keyword(s): Repair | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.2.1 ("Engineering Practices: Project and System Level Functional Verification and Validation - Verification and Validation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 09/04/1987
400 | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Structure Dynamical Interaction with Attitude Control | As Mariner 10 approached Venus encounter, an uncontrolled oscillation occurred due to spacecraft structural interaction with the Attitude Control Subsystem. The result was a severe consumption of control gas that would have caused failure of the mission had it continued. The recommendations center on design and operational measures to cope with subtle and complex dynamical interactions between the spacecraft structure and the ACS. | Spacecraft structural dynamical interactions with the Attitude Control Subsystem can be very subtle and complex. | During the spacecraft design phase, consideration should be given to: Increasing the amount of analysis on and simulation of structural / control interactions. Placing additional or tighter controls on key parameters at interfaces between structures and attitude control. Establishing procedures for communicating key parameter data between subsystem engineers and analysts, initially and when changed. In situations where there is significant uncertainty in simulations, models, or analysis results, the spacecraft subsystem software should be designed so as to accommodate changes late in the development, test, and post-launch periods. Techniques such as modular design and parameter tables vs. hard coding should be considered. The capability to cope with this type of anomaly, by analysis and simulation, should be maintained throughout the mission. | JPL | 06/08/1995 | As Mariner 10 (MVM'73) was nearing encounter with Venus, an uncontrolled oscillation occurred due to spacecraft structural interaction with the Attitude Control Subsystem. The problem was first detected during a platform calibration sequence, which required a series of roll turns using roll gyroscope inertial control, and science scan platform motion. The result was a severe consumption of control gas which would have caused failure of the mission had it continued. The oscillation was due to a control instability exciting a structural mode of the spacecraft. The primary cause of the resonance was attributed to the flexibility of the solar panels. Additional Keyword(s): Flexible Body Analysis Reference(s): PFR #5024. | JPL has referenced the lesson as supporting Paragraph 4.2.2.6 ("Flight System Design: Mechanical Configuration/Systems Design - Configuration (Plume Impingement)"), and Paragraph 4.6.1.3 ("Guidance, Navigation & Control Design: Gain-Stabilized Resonance Modes"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 07/16/1987
369 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Software Deadly Embrace |  | A continuous software looping operation, or "deadly embrace", can occur undetected in the flight software. | A flight project should invoke a software policy which specifies that no single parameter error or single spacecraft malfunction can lead to a "deadly embrace" in the flight software. There should be a rigorous software verification and failure mode analysis conducted at the system level. One subsystem checking on another subsystem's functions should be used only when absolutely necessary. "Try Again" responses may be undesirable unless a recovery mode is incorporated. | JPL | 01/24/1995 | During a walk-through of the Galileo Spacecraft System fault protection implementation a possible "deadly embrace" in the flight software was uncovered. A deadly embrace is a continuous software looping operation that may preclude the achievement of an acceptable spacecraft state. Refer to IOM GLL-BGL-85-003 for additional details. | JPL has referenced the lesson as supporting Paragraph 4.11.4.7 ("Design Robustness: Response to Incorrect Commands, Loads, Data or Memory") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.” | N/A |  |  | Public | Not Specified |  | 05/14/1987
280 | Mallis, R - 0000000000 : NO@ADDRESS.GIVEN | Mallis, R - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Power Subsystem Internal Voltage Drop | The high resistivity of nickel ribbon used for electrical interconnections within power modules caused excessive voltage drops at subsystem power interfaces. Voltage drop analyses should be conducted to assure that voltages at the subsystem power distribution interfaces will always remain within the specified tolerances. Perform early subsystem bench level tests using representative external interface circuits to verify adequate performance. | The high resistivity of nickel ribbon used for electrical interconnections can result in an excessive voltage drop. | End-to-end voltage drop analyses should be conducted during the design phase, using flight component characteristics, to assure that in the worst case condition, voltages at the subsystem power distribution interfaces are within the specified tolerances. Subsystem bench level tests should be performed early using representative external interface circuits to verify adequate performance. | JPL | 07/12/1993 | During system tests, lower than expected voltages were measured at subsystem power interfaces indicating excessive voltage drop in either the interconnecting cables or the power subsystem. Subsequent testing isolated the excessive voltage drop to the power subsystem. Power system subassembly tests demonstrated that the voltage drop was across the relay welded modules in the power distribution assemblies and was caused by the high resistivity of the nickel ribbon used for electrical interconnections in these modules. These measured voltage drops were verified by JPL analysis. |  | N/A |  |  | Public | Not Specified |  | 04/17/1987
356 | Lord, D - 0000000000 : NO@ADDRESS.GIVEN | Lord, D - 0000000000 : NO@ADDRESS.GIVEN |  | Loss of Spacecraft due to Shroud Failure During Launch | A failure shortly after launch in the honeycomb shroud (nose cone) structure, due to a lack of proper venting, caused Mariner '64 mission failure. Analyze the pressure profiles that the honeycomb structure will be exposed to, and assure adequate venting under worst case environment conditions. | Internal pressures within honeycomb structures, in adverse environmental conditions, can build to a point sufficient to cause break up of spacecraft components. | Whenever honeycomb structures are used an analysis should be conducted of the temperature and ambient pressure profiles that the honeycomb structure will be exposed to during all phases of pre-launch and post-launch activities. It should then be verified to ensure that the honeycomb structure design provides for adequate venting or is structurally capable of withstanding the expected temperature and ambient pressure profiles. The design of the honeycomb structure is verified by conducting a thermal vacuum test that accurately simulates the worst case environment that it will be exposed to during all phases of pre-launch and post-launch activities. The actual pressure vs. time profile that will occur during the worst case environment conditions should be used during this test. | JPL | 12/13/1994 | Within minutes after the launch of the first Mariner '64 spacecraft to Mars, it was determined that there were mechanical problems with the deployment of the solar panels and other appendages. The spacecraft eventually went dead from loss of electrical power when the battery power was depleted. Analysis of the incident indicated a failure in the honeycomb shroud (nose cone) structure due to a lack of proper venting. Internal pressures in the honeycomb structure itself, built up during the rapid change of ambient pressure during launch, combined with high shroud temperatures due to frictional forces in the near earth atmosphere, caused the shroud to break up. It was established that the shroud contractor had not performed a combined thermal vacuum test that represented the launch profile conditions. Additional Keyword(s): Materials, Outgassing | JPL has referenced the lesson as supporting Paragraph 4.2.5.5 ("Mechanical Configuration/Systems Design: Structural Design - Thermally-Induced Loading Factor of Safety"), Paragraph 4.2.5.7 ("Mechanical Configuration/Systems Design: Structural Design - Design Temperature Range for Spacecraft Structure"), and Paragraph 4.2.5.9 ("Mechanical Configuration/Systems Design: Structural Design - Design Validation") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.” | N/A |  |  | Public | Not Specified |  | 03/26/1987
390 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager Subsystem Interface Noise Problems | Problems due to waveform irregularities and the resultant induced noise on the Voyager Spacecraft system interfaces were not validated until 500 hours of system testing had been completed. Lessons involve the need for early system tests to determine subsystem compatibility and design requirements for electrical noise and transients, and extensive interface testing under flight-like conditions. | Early testing of subsystem compatibility can detect problems and avoid extensive subsystem modifications. Waveform transition irregularities and resultant induced noise problems on spacecraft system interfaces, if not validated prior to system testing of flight hardware, can require circuit modifications to affected subsystems and extensive regression testing. It is virtually impossible to simulate the real noise environment of the complete spacecraft in the subsystem test facility. | System tests to determine subsystem compatibility should begin as early as possible using prototype or breadboard hardware. Testing of the system without the subsystem support equipment cables attached should also be conducted as early as possible. It has been found that these cables can alter the flight configuration noise environment considerably. Critical system level interface electrical noise and transient design requirements should be generated early by systems engineering. These should be reviewed and understood by the subsystem design engineers prior to circuit design. Critical subsystems interface circuit design should be reviewed by the system engineer prior to implementation. It is essential that early and extensive interface testing be conducted with as many system loading and flight-like conditions as possible. Where noise immunity is critical, injection of noise on the signal lines during subsystem tests may be necessary to demonstrate adequate margins. | JPL | 03/21/1995 | Problems due to waveform irregularities and the resultant induced noise on the Voyager Spacecraft system interfaces were not validated until after in excess of 500 hours of system testing had been completed. The problem manifested itself in the following two ways: A digital, coded interface design was utilized on the Voyager Spacecraft for transferring command data between the Computer Command Subsystem (CCS) and the power subsystem. This interface, under certain spacecraft system loading configurations with the support equipment disconnected, resulted in several cases of either "no response" or "incorrect response" to commands. The problem was traced to the 2.4 kHz power subsystem waveform transitions (variable with system load configuration) coupling into the command circuits via its circuit returns causing spurious clock pulses. A related but not identical problem occurred on the CCS to the Attitude and Articulation Control Subsystem (AACS) Command Interface. In this case, waveform transition irregularities of the 2.4 kHz clock signal (again, variable with system load configuration) could, under certain conditions, result in trigger circuits interpreting these irregularities as clock pulses. To correct these problems required circuit modifications to all affected subsystems which entailed extensive regression testing. Details can be found in Voyager PFR 39802 and IOM 3132-76-179. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.6.2 ("Engineering Practices: Design and Verification for Environmental Compatibility - Test Configuration") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 01/02/1987
370 | Mallis, R - 0000000000 : NO@ADDRESS.GIVEN | Mallis, R - 0000000000 : NO@ADDRESS.GIVEN |  | DDM Power Supply Failure | A power supply failure in the Drop Dynamics Module may not have occurred if the payload had been designed to JPL D-1489, “Payload Classification Product Assurance Provisions.” Design and test to standards consistent with the class of payload. This lesson is probably obsolete as D-1489 has been withdrawn and there are no longer payload classes. | Experiences such as the DDM power supply failure reinforce the need for design and testing to standards consistent with the class of payload. | For payloads of a specified class (particularly those using commercial equipment), one should ensure that the provisions of JPL document D-1489 are met with respect to reviews, problem failure accountability, parts selection, materials and processes, environmental testing, quality assurance, and commercial equipment qualification. | JPL | 01/24/1995 | The Drop Dynamics Module (DDM) is a Class C experiment which is flown on the Shuttle (STS). On its first flight, one of the set of seven commercial power supplies used by the DDM failed when an internal short caused the main circuit breaker to trip. Repeated attempts to energize the system were unsuccessful and an in-flight work-around was accomplished by the JPL payload specialist. Although the location of the failure was known, failure analysis did not determine the cause since the internal damage to the two failed transistors precluded a reconstruction of the event. Circuit analysis did indicate an over-stressed design. However, this condition had not prevented several hundred power supply turn-ons prior to the failure and several thousand turn-ons of the set of power supplies. In addition, the work-around solution to the power supply failure was to rewire the configuration such that two of the remaining power supplies would assume the load of the failed power supply. Those two power supplies successfully picked up the extra load. Since this failure occurred after launch, the possibility of a vibration-induced failure cannot be disregarded. The DDM was designed and implemented prior to the release of JPL document D-1489 (Flight Project Document FPO 600-3), entitled "Payload Classification Product Assurance Provisions." This document provides a description of the principal product assurance elements and the specific provisions which are to be applied as a function of payload class. Additional Keyword(s): Reliability | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.3 ("Safety and Mission Assurance Practices: Reliability Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/12/1986
375 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Telemetry Data Return and Telecom Link Margin Strategy | Viking adopted a simple single-number criterion for managing the risk in selecting “optimum” downlink science data rates, and used it consistently in sequence planning. Formal adoption by the project of a clear and consistent set of telecom link criteria is an effective strategy for risk management of varying telecom performance. | Formal adoption by the project of a clear and consistent set of telecom link criteria is an effective strategy for risk management of varying telecom performance. | Each project must thoughtfully establish its own criteria for using the project resource of telecom link performance, based on sufficient pre-launch and in-flight telecom link characterization. Desirable characteristics of a set of criteria include (a) being clear and without ambiguity, (b) having balance between risk, complexity and consequence, and (c) providing a means to measure (compare) the predictions against actual performance. The project must formally authorize the selected criteria, ensure their consistent use among all elements of the project and formally communicate any changes required from further experience. | JPL | 01/25/1995 | After several months of flight experience, the Viking project adopted a simple single-number criterion for managing the risk in selecting "optimum" downlink science data rates in the face of varying telecom performance. The rule, developed with inputs from the Deep Space Network and the Telecommunications Systems Section, is to pick from the available set the highest rate that the downlink can support at that time, assuming the downlink is 32% (1 dB) less capable than the best estimate of performance. After a further period of validation, the project widely disseminated this rule and used it consistently in sequence planning. The conclusions at the end of the project were (a) the chosen rule was right for an S-band downlink and the Viking science data, and (b) this approach provided a good balance between the total data received and the total data lost. Additional Keyword(s): Operations Planning | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.2.4 ("Engineering Practices: Telecommunications Design") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 11/20/1986
396 | Flynn, K - 0000000000 : NO@ADDRESS.GIVEN | Flynn, K - 0000000000 : NO@ADDRESS.GIVEN |  | SIR-B Antenna Feed Anomaly | Shortly after transmitter turn-on, SIR-B suffered a radiated power drop. After Shuttle landing, troubleshooting discovered a sliver of metal embedded in the center conductor of the GFE antenna cable. For critical GFE components, obtain copies of the test procedures and the test data; perform RF breakdown and end-to-end system tests. | Review and verification of test procedures and test data from critical components supplied as GFE by other organizations ensures that project testing requirements have been met. RF breakdown tests on RF generation or amplification and antenna feed system components provide assurance that the components meet flight operational requirements. End-to-end system tests are particularly critical if the system includes data generation and data flow. | If critical components are manufactured and tested and supplied GFE by organizations other than the laboratory, the cognizant development organization should request copies of the test procedures and the data derived from these tests to determine that the equipment meets the project testing requirements. RF breakdown tests should be conducted on all radio frequency generation or amplification and antenna feed system components that are susceptible to breakdown. Test plans should include sufficient system perspective to ensure that the tests are conducted at power levels that demonstrate a margin over the flight power levels and for a period of time commensurate with the planned flight operating duration. End-to-end system tests should be conducted on large complicated systems to verify RF breakdown margins. | JPL | 06/07/1995 | The SIR-B Shuttle Mission 41-G exhibited a SIR-B transmitter radiated power drop of 8-10 dB shortly after transmitter turn-on. A corresponding increase in the reverse power (as noted in the telemetry) and a drop in received echo amplitude were also noted. Troubleshooting performed at KSC after Shuttle landing revealed a low resistance path (approximately 5 ohms) from the center conductor of the antenna cable to the coax shield. The cable assembly (AE9492) was part of the antenna system, which was provided as GFE by the Johnson Space Center who returned it to the manufacturer for failure analysis. The manufacturer found that a sliver of metal was embedded in the teflon dielectric of the connector. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.17.6 ("Engineering Practices: Hardware Development") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/13/1986
364 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Retro Propulsion Module and Pyro Power System Interaction | Galileo design optimizations over the years exacerbated interactions between spacecraft power and the propellant tanks. During the cruise phase, high power and heat dissipation near the propellant tanks combined with an enhanced tank load to increase the tank pressure. A thorough analysis should be conducted before changes are made to one or more of the flight project elements that occur late in the development cycle or well into the test program. | Design of the various elements of a flight project (trajectories, science, mission operations, spacecraft design, spacecraft integration and test, etc.) is usually conducted in parallel. Although the designs are not conducted independently, there are always subtle but significant interactions which can occur within one of the elements or between several elements. | A thorough analysis should be conducted before changes are made to one or more of the flight project elements late in the development cycle where the test program is well advanced or actually may be completed for some of the elements. This analysis should be conducted in concert with designers of the other elements. If discovered after changes are made, these interactions and couplings may (1) reduce the flexibility to make later changes necessary to recover from failures, or (2) negate the opportunity to enhance future science return, or (3) require complicated and costly operational workarounds. | JPL | 12/22/1994 | Over a period of several years, design optimizations were made to the Galileo Spacecraft system including the increase in the Retro Propulsion Module (RPM) tank load from 84% to 94%. This was to assure adequate propellant to accomplish the mission objectives and was done late in the spacecraft development cycle. However, the change resulted in a high degree of coupling between the RPM tank pressure and the spacecraft system power demand due to the spacecraft power dissipation mechanism. During the cruise phase, the spacecraft power demand will be low and the excess electrical power is to be dissipated by shunt heaters located near the RPM tanks. The power dissipation increases the RPM tanks temperature with a concomitant rise in the RPM tank pressure. The RPM design is such that relatively small temperature increases combined with the low ullage (tanks nearly full), will cause a dangerous increase in the internal RPM tank pressure. The shunt heater circuit already had a requirement for a minimum dissipation level in order to assure adequate power margin for blowing fuses in case of a spacecraft fault. The RPM tank pressure concern now added an upper limit on the shunt heat dissipations. Maintaining this dissipation within the required range causes a significant impact to the spacecraft system fault detection and control software. In addition, the operational sequence design after launch and during the cruise will be more complex and require the use of additional resources. | JPL has referenced the lesson as supporting Paragraph 4.8.1.1 ("System Thermal Design: General - Design Tailored to Specific Application") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.” | N/A |  |  | Public | Not Specified |  | 09/30/1986
284 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | In-Flight Spacecraft Fault Recovery | Voyager 2 suffered two potentially mission-catastrophic in-flight faults that were recoverable due to the availability of spare spacecraft hardware that was used to test workaround solutions. Maintain a functionally identical, properly configured, test bed of spare spacecraft hardware and associated support equipment, enabling detailed analysis of in-flight faults and candidate corrective actions. | The availability of spare spacecraft hardware and associated ground support equipment can mean the difference between restoring a lost spacecraft capability or flying with a reduced or lost capability due to the inability to adequately correct a fault. | Maintain a functionally identical, properly configured, test bed of spare spacecraft hardware and associated support equipment, enabling detailed analysis of suspected causes of in-flight faults and validation of proposed corrective actions or workarounds. | JPL | 07/12/1993 | During the prime Voyager mission, Voyager 2 suffered two potentially mission-catastrophic faults. These were: 1) failure of the spacecraft receiver plus significant degradation in the signal acquisition capability of the redundant spacecraft receiver, and 2) the azimuth scan platform actuator ceased operation. A significant contribution to the successful recovery from these faults was the availability of spare spacecraft hardware and associated support equipment, which was used to simulate postulated failures plus evaluate and validate proposed solutions and workaround procedures. The specific details of the corrections and workarounds are described in the paper entitled "Voyager Engineering Improvements for Uranus Encounter" by Howard P. Marderness. Additional Keyword(s): Mission Operations | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.1 ("Management Practices: Spares, Testbeds, and Models - Practices") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 09/11/1986
401 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager Enhanced Mission Science Return | An extended Voyager mission was feasible due to engineering improvements that permitted the use of redundant hardware to enhance science return. | A spacecraft design which enables the implementation of an image motion compensation capability can make possible extremely long image exposures while minimizing image smear. Spacecraft system architecture and subsystem implementations which allow utilization of redundant elements for operational elements during critical periods of the mission are key to enabling expanded spacecraft mission operations. These redundant elements can be utilized even though the prime elements remain operational. Maintenance of a complete flight software development and validation capability during the mission, to allow utilization of the designed spacecraft software flexibility after launch, will enable significant enhancement of science data return. | Consider that a spacecraft system design which facilitates on-board algorithm modifications to optimize performance, based on detailed analysis and understanding of the measured inflight spacecraft operational characteristics, allows significant post-launch mission enhancement. Use of spacecraft design which enables utilization of redundant hardware, to increase the sequence software on-board storage capacity, should be considered. Projects should allocate sufficient resources to maintain a complete flight software development and validation capability during long duration missions. | JPL | 06/08/1995 | After completion of the Voyager primary mission (Jupiter and Saturn encounters), a follow-on mission to encounter Uranus and Neptune was made possible by the DSN arraying antennas and the project incorporating the following: A spacecraft design which enabled the implementation of an image motion compensation capability which made possible extremely long image exposures while minimizing image smear. A spacecraft design which enables utilization of redundant hardware, such as the Flight Data System memory, to increase the sequence software on-board storage capacity. This capability has been developed and tested for potential future use to enhance science return. The specific details of the types of spacecraft system and subsystem designs to accomplish this are described in the paper entitled "Voyager Engineering Improvements for Uranus Encounter" by Howard P. Marderness. | JPL has referenced the lesson as supporting Paragraph 6.3.1.2 ("Managed Margins: Flight System Technical Resource Margins - Technical Resource Margins for Flight Operations Phase") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Science | Public | Not Specified |  | 09/11/1986
367 | Koch, J - 0000000000 : NO@ADDRESS.GIVEN | Koch, J - 0000000000 : NO@ADDRESS.GIVEN |  | Pyro Multiple Event Indication | A Voyager post-fire squib short resulted in anomalous spacecraft telemetry signals. Design initiation and sensing circuits to prevent sneak paths. Recognize post-fire squib shorts as a “normal” occurrence to be taken into consideration when designing squib activation or sensing circuits. | Post-fire squib shorts can result in anomalous spacecraft telemetry signals. | Initiation and sensing circuits must be designed and analyzed with great care to prevent sneak paths which permit unwanted current flows. This is especially true in sensing circuits which could result in anomalous telemetry indications. Post-fire squib shorts must be recognized by the design engineer as a "normal" occurrence and should be taken into consideration when designing squib activation or sensing circuits. | JPL | 01/13/1995 | The Voyager Spacecraft utilized a super-zip separation band initiated by a Pyro Switching Unit (PSU) for separation from the launch vehicle. Initiation of either of the two redundant Mild Detonating Fuses (MDF) in the super-zip separation band would cause separation, while detonation of both MDFs could rupture the tube containing the MDFs and probably contaminate the spacecraft. Telemetry from both Voyagers 1 and 2 indicated that both MDFs received current from the PSU. Current to the secondary MDF should have occurred only if the primary MDF failed to cause separation from the launch vehicle. The anomalous telemetry signal indicating a current to the secondary MDF was traced to a primary detonator post-fire short to the spacecraft frame which resulted in a reverse current through the PSU's sensing circuit caused by a noise decoupling RC network between the PSU common and the spacecraft frame. The anomaly was reproduced in the laboratory thus verifying that the secondary MDF did not detonate. |  | N/A |  |  | Public | Not Specified |  | 09/11/1986
393 | Mallis, R - 0000000000 : NO@ADDRESS.GIVEN | Mallis, R - 0000000000 : NO@ADDRESS.GIVEN |  | ATMOS Laser Failure | A failure in the ATMOS instrument laser was attributed to a pressure loss caused by use of machine screws of excessive length in a modified housing. Sealed flight equipment requiring container integrity should be designed to provide continuous passive indication of leaks. When modifying equipment, ascertain that the as-built configuration is understood. | Failure to provide verification of seal integrity of pressurized containers can result in failure of flight equipment. All flight equipment modifications require evaluation of resulting configuration changes. | Sealed flight equipment requiring container integrity should be designed to provide continuous passive indication of leaks by pressurizing above atmospheric pressure and monitoring with pressure transducers to provide evidence of proper pressure and seal integrity. When modifying equipment, care should be taken to ascertain that the as-built configuration is understood. Equipment can be modified by Engineering Change Notices or corrective actions based on Material Review Board decisions. | JPL | 05/30/1995 | After some two days of flight aboard Spacelab 3, the Atmospheric Trace Molecule Spectroscopy (ATMOS) instrument failed when the laser did not turn on for occultation 75. The laser failed due to a high voltage arc-over, which resulted from a pressure loss in the laser housing. Investigation revealed that the pressure loss was caused by use of machine screws of excessive length. The housing had been modified, based on a Material Review Board decision, which resulted in threaded holes, which were of a different length than the original design drawings. Machine screws were used which matched the original design drawing but were too long when used in the as-built configuration, causing the integrity of the housing to be violated. Additional Keyword(s): Leak Testing | JPL has referenced the lesson as supporting Paragraph 8.3.3.3 ("Flight System Verification and Validation Design: System Assembly, Integration and Test: System Functional Verification - Mechanical Clearances") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/11/1986
372 | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN |  | Loss of Instruments Caused by Balloon-Gondola Incident | A JPL built balloon gondola free-fell from an altitude of 102,000 feet, destroying the payload. The gondola attachment fixture was designed to the requirements of the National Scientific Balloon Facility (NSBF), but the requirements were insufficient. The failure showed that FMECA analysis of flight hardware design is necessary to prevent excessive risk to high cost equipment. The hardware interface design requirements of a non-JPL organization may not be sufficient to safeguard JPL flight equipment. | Failure to conduct a Failure Mode Effects and Criticality Analysis (FMECA) of flight hardware design can result in excessive risk to high cost equipment. Hardware interface design requirements of a non-JPL organization may not be sufficient to safeguard JPL flight equipment. | All anomalies or indications of potential failure should be thoroughly investigated, analyzed, and if indicated, corrective action should be taken and the results verified. When undertaking research and development experiments with high cost equipment, all modes of possible damage or destruction should be thoroughly analyzed and an assessment made of the risk. When interfacing at the working level with a non-JPL organization that is not responsive to JPL needs or concerns, the problem should be escalated up the JPL management chain to the level where resolution is obtained. | JPL | 01/25/1995 | A JPL built balloon gondola, weighing approximately 4000 pounds and carrying a complement of five scientific instruments, free-fell from an altitude of 102,000 feet. The gondola and all five instruments valued at $10M were totally destroyed upon impact. An accident review board concluded that the free-fall resulted from a structural failure of a "clevis base adapter" which attached the gondola to the parachute, and that the adapter failed because of excessive loads imposed on it by unusual parachute/gondola dynamics during the flight termination sequence. It was found that the design of the adapter met all requirements of the National Scientific Balloon Facility (NSBF), a NASA operated center for high altitude balloon support to scientific investigators. Investigative efforts subsequent to the accident found the NSBF requirements to be insufficient and also revealed that the flight termination sequence and its dynamics were not understood by NSBF. It is noteworthy that this flight was not the first flight of this type of balloon-borne payload, and that in several prior flight terminations, heavy stresses had been encountered that resulted in structural damage to gondolas, but not in catastrophic failures. For more details on the event refer to the report of the accident review board, JPL document D-1114. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.3 ("Safety and Mission Assurance Practices: Reliability Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 08/14/1986
303 | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Spin Bearing Lubricant Problem | Although, the synthetic lubricant on Galileo slip ring bearings had been replaced with KG80 oil, the porous, phenolic ball retainer had absorbed some of the previous lubricant. Under vacuum, this residual synthetic lubricant reacted with the KG80 to form a black goo. When cleaning spaceflight components, the cleaning process must be followed by an outgassing vacuum-bake treatment-- particularly for porous materials | Even careful cleaning of spaceflight components can leave residues which may eventually react with adjacent materials. | When cleaning spaceflight components, the cleaning process must be followed by an outgassing vacuum-bake treatment. This is particularly important for porous materials which may have absorbed various fluids, including the cleaning medium itself. | JPL | 09/15/1993 | The Galileo flight control slip ring test fixture bearings had once been lubricated with a synthetic lubricant. This was eventually replaced with KG80 oil to simulate actual Spin Bearing Assembly (SBA) operating conditions in space. After approximately 3 months of life testing (under vacuum) at 3 RPM, the bearing lubricant had a thick, black, gooey appearance and the bearing friction torque was higher than expected. It was discovered that even with careful cleaning prior to the test, some of the original synthetic lubricant remained in the porous, phenolic ball retainer. Under vacuum, this residual synthetic lubricant migrated to the surface, reacting with the KG80 to form the black gooey material. A new bearing with a nonporous steel ball retainer was installed. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.5 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 06/25/1986
357 | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN | Langmaier, J - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Slip Ring Cleaning Problem | During the process of cleaning the Galileo slip rings, the PCA cleaning fluid obtained from JPL stores was found to contain chemical and particulate contaminants. When cleaning critical spacecraft components, the cleaning fluid should be carefully checked, not just visually, for chemical and particulate contaminants prior to use. | Cleaning fluid, obtained from approved sources and assumed to be "pure", may in fact contain chemical and/or particulate contaminants. | When cleaning critical spacecraft components, the cleaning fluid should be carefully checked, not just visually, for chemical and particulate contaminants prior to use. The source of the contaminants could be the container or the manufacturing process or both. | JPL | 12/13/1994 | During the process of cleaning the Galileo slip rings, the PCA cleaning fluid obtained from JPL stores was found to contain chemical and particulate contaminants. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.5 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 06/25/1986
376 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Spacecraft Transporter Excessive Humidity (2007 Revision) | The Galileo spacecraft sustained water damage when its environmentally controlled shipping container was left open at the launch facility, allowing humid air to enter throughout a holiday weekend. Controlled environment containers should have continuously visible indicating recorders including an alarm feature. Novel operational modes require hazard analysis. | If the humidity inside the transporter had been monitored, the super saturation condition produced by 70 degree room air entering the 50 degree transporter environment would have been detected early and negligible damage to the spacecraft would have occurred. | Whenever environmental conditions are specified for a container, the specified parameters should be provided with continuously visible indicating recorders including an alarm feature if limits are exceeded. When a device is operated in a mode which was not contemplated, analysis should be conducted to determine whether this new operational mode could be hazardous to the device or personnel. | JPL | 01/30/1995 | The Galileo Spacecraft was shipped to the launch site in a custom made transporter with the RHUs (Radioisotope Heating Units) installed. Removal of the heat from the RHUs required external cooling to an ambient air temperature between 48 degrees and 59 degrees F., which was provided by the transporter air conditioning system. The spacecraft also had an internal purge system which protected sensitive elements from uncontrolled humidity and airborne contamination during shipment. Upon arrival at The Cape, the transporter was placed indoors under guard in environmentally controlled conditions. Once inside the transporter air conditioners were transferred to facility power and the purge gas supply was transferred to facility nitrogen. The pressurized enclosure seal of the transporter door was relieved. Since the S/C was not to begin processing until after the year-end holiday interval at KSC, it remained in the controlled environment under guard with periodic monitoring until after the holidays when the mechanical crew arrived and commenced KSC operations. When the transporter was opened, puddles of water were noted on the floor of the transporter and external spacecraft surfaces exhibited corrosion, characteristic evidence of excessive humidity. The conclusion after intensive inspection and extensive additional analysis by all subsystem cognizant personnel was that only external and cleanable damage occurred. Additional Keyword(s): Environmental Control | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 05/30/1986
308 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Solder Balls in Flight Modules | Because a design change had been made to the proven Mariner design, the Viking orbiter flight radio modules developed short circuits caused by solder balls shorting terminal lugs to ground. Review related applications for known solder ball problems, and evaluate each design to determine whether solder can flow into uninspectable areas. | Changing a design having a successful history always carries some risk. A simple design change, made for good reasons, may cause unanticipated new problems. | Before making design changes, related applications should be reviewed for known problems with this solder ball effect. Evaluate each design to determine whether solder can flow into uninspectable areas. | JPL | 09/21/1993 | Viking orbiter flight radio modules developed short circuits caused by solder balls shorting terminal lugs to ground. For solderability and several other reasons, a design change had been made to the proven Mariner design. Solving the solder ball problem required $250k (in the mid-1970s) for the rework of one flight subsystem and several assembled and tested modules. Additional Keyword(s): Fabrication, Soldering | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6.2 ("Engineering Practices: Inheritance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/19/1985
277 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Closure of the TDL During Flight Operations | Voyager inflight receiver failures required rapid development of operational workaround procedures. This required the facilities of the Telecommunications Development Laboratory (TDL), but it had been shut down after Voyager launch. Projects should plan to keep development facilities functional after launch to permit inflight troubleshooting, else they should have a plan in place to quickly reactivate critical facilities. | A project development facility may be required for inflight spacecraft troubleshooting. | Projects should plan to keep development facilities functional after launch to a level necessary to accomplish inflight troubleshooting. If, for funding reasons, it is necessary to shut down project development facilities after launch, the project should develop a plan with the requisite funding which will reactivate the facility in a very short period of time. | JPL | 07/09/1993 | The Telecommunications Development Laboratory (TDL) shut down after Voyager launch, upon termination of that project's funding. Galileo planned to fund its TDL support at a later date. The Voyager inflight receiver failures required rapid development of operational workaround procedures to accomplish the Jupiter encounter with one spacecraft receiver with limited capability. Reactivation of TDL to a usable state took more than six months because personnel had to be reassigned and equipment had to be retrieved, repaired, and calibrated. Additional Keyword(s): Management, Institutional, RF Performance Verification | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.18.10 ("Engineering Practices: Mission Operations System Development") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/19/1985
282 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Relay Hangup Upon Power Removal | One Voyager Solid State Amplifier (SSA) failed to operate upon application of input power during spacecraft system test. Post-test analysis determined that a relay hangup had occurred following the previous application of power, and the original analysis had not considered decaying stored energy in the relay. Take all operating modes into consideration in circuit design. Design relay circuits so that the circuit can still apply energy to activate relay coils, even if the relay hangs up between contacts. | Circuits can behave in an unexpected and unacceptable manner when applied power is removed and the stored energy decays. | In the design of circuits, all operating modes must be taken into consideration. Relay circuits should be designed so that the circuit can still apply energy to activate relay coils, even if the relay hangs up between contacts. | JPL | 07/12/1993 | One Voyager 20-watt Solid State Amplifier (SSA) failed to operate upon application of input power during spacecraft system test. The SSA provides RF power for the downlink. This problem had not occurred during many previous power applications to this SSA nor on any other SSA. In flight, this failure would render the SSA useless. Post-test analysis determined that a relay hangup had occurred following the previous application of power. The relay anomaly involves OP-AMP operation below normal voltage, energy stored in capacitors, and the relay switching voltage threshold. The original analysis had not considered decaying stored energy. |  | N/A |  |  | Public | Not Specified |  | 12/19/1985
395 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | In-Flight Spacecraft Antenna Gain and Polarization Changes | Before the first Mercury encounter, the MVM'73 high gain antenna suddenly lost 3 dB in gain and changed from circular to linear in polarization. It was suspected that either particles or chips left in the S-band feed cavity after antenna assembly caused a short circuit, or a combination of tolerance build-up and thermal effects caused a dimensional change. Worst case analysis should be preformed on any equipment suspected to be sensitive to assembly practices or tolerance build-up. | A worst case analysis could have predicted potential performance anomalies of equipment susceptible to tolerance build-up. During critical spaceflight events it proved to be extremely valuable to have the original development engineers committed and available to assist in any in-flight anomaly analysis and correction. | Any equipment suspected to be sensitive to assembly practices of tolerance build-up should have a worst case analysis to reveal any potential performance anomalies. Consideration should be given to planning for original development engineers to participate as members of the in-flight anomaly recovery team. | JPL | 06/06/1995 | Before the first Mercury encounter, the MVM'73 high gain antenna suddenly lost 3 dB in gain and changed from circular to linear in polarization. Ground testing on a similar antenna determined that a short circuit within the S-band feed cavity reproduced these effects as well as the observed changes in internal antenna temperature and standing wave ratio. Successful anomaly resolution during the flight included an induced temperature change by solar illumination to "heal" the antenna, permitting the planned mission. The development organization was very instrumental in the correction of the problem. They theorize that either a short circuit occurred as the result of particles or chips left in the cavity after antenna assembly or a combination of tolerance build-up and thermal effects caused a dimensional change. Additional Keyword(s): Operations | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.3 ("Engineering Practices: Reliability Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/19/1985
378 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Untestable System Mode In Flight | An essential in-flight test of the Viking Lander transmitter output could not be conducted due to the antenna's proximity to the Orbiter receiver antenna when Lander and Orbiter were mated. During the system design phase, system engineers must be sensitive to the various configurations to be encountered during the system test program. | System engineers cannot rely on the individual subsystem engineers to predict problems of their subsystems interacting with other subsystems during system tests. | During the system design phase, system engineers must be sensitive to the various configurations to be encountered during the system test program. | JPL | 02/01/1995 | Prior to launch, telecommunication analysts responsible for the Viking Orbiter and the Lander identified that in-flight checkout of the Lander transmitter could be a potential problem. The transmitter outputs are 1, 10, and 30 watts. When the Orbiter and Lander are mated, there is only a small separation between the Lander relay transmitter antenna and the Orbiter relay receiver antenna. The analysts realized that at the higher relay transmitter output levels, the relay receiver would be subject to an overload condition and could suffer possible damage. Prelaunch tests of the antenna geometry and Orbiter/Lander mated tests were insufficient because of limited modeling capability, nonflight conditions, and noisy environments. To verify a working Lander transmitter output before the first descent to Mars surface, an in-flight test was essential. Engineers, working at the bounds of analysis with nonlinear telemetry, deemed a 10-watt test safe. Because of parameter tolerance buildup, they could not guarantee damage-free testing at the 30-watt level. Therefore, the project decided the critical Lander-1 Mars-descent data would be transmitted at 10 watts, thereby accepting the risk of some data loss due to atmospheric fading. Additional Keyword(s): RF System Design | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.1 ("Engineering Practices: Design and Verification for Environmental Compatibility - Practices") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.10.1.1 ("System EMC/EMI Design: General - EMC Approach"), and Paragraph 4.2.2.1 ("Mechanical Configuration/Systems Design: Configuration - Accessibility") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 12/19/1985
389 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | In-Flight Power Converter Failure | During a switch between Voyager radio receivers, a failure occurred due to a short circuit traced to a screw contacting components insufficiently coated by the solithane conformal coating. Designers should be aware of tolerance build-up in assemblies and assure that there is adequate margin. | Build-up of design tolerances in assemblies can result in in-flight equipment failure. | Designers should be aware of tolerance build-up in assemblies and assure that there is adequate margin. | JPL | 03/13/1995 | This event involved both Voyager radio receivers. The failure occurred when a flight operations software command loss routine switched the S/C configuration from Receiver 1 to Receiver 2. Receiver 1 had operated normally from launch until the inadvertent switch to Receiver 2 and subsequent controlled switch back to Receiver 1. The Receiver 1 power converter failed 11 seconds after the switch back. Other subsystem telemetry was also noted to be anomalous during this short time. Receiver 2 on first use after the inadvertent switch was discovered to have a shorted loop capacitor and thus unable to lock to normal uplink. After the Receiver 1 failure, the spacecraft switched Receiver 2 on. Receiver 2 has subsequently continued to support the mission. Its use required special Deep Space Network (DSN) uplink acquisition tuning procedures and periodic in-flight receiver best lock frequency checks to compensate for the failed loop capacitor. The analysis indicates that the short circuit within Receiver 1 was screws. The metal particle contacted components insufficiently coated by the solithane conformal coating. | JPL has referenced the lesson as supporting Paragraph 8.3.3.3 ("Flight System Verification and Validation Design: System Assembly, Integration and Test: System Functional Verification - Mechanical Clearances") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 12/19/1985
365 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Antenna Performance Specifications Not Met | The system and end-to-end testing programs for the SEASAT synthetic aperture radar were impacted by schedule and cost constraints that contributed to failure to meet the primary mission objective. The development organization and the project should understand the consequences of an inadequate test program. The risks associated with any reduction of testing should be clearly documented and communicated to the project. | The testing phases of a project, both system and end-to-end, are usually impacted by both schedule and cost constraints, which may affect system performance or reliability. | The development organization and the project should understand the consequences of an inadequate test program. This understanding is best accomplished by the development organization defining a comprehensive test program, which will verify all design parameters prior to launch. This test program should have sharp justification and be based on a good technical analysis and previous experience. The risks associated with any reduction of testing or the deletion of any test should be clearly documented and communicated to the project. The project in turn should carefully consider the risks to performance and reliability if any subsequent changes are made to the test program due to schedule or budget constraints. | JPL | 12/22/1994 | For an end-to-end system test of the SEASAT synthetic aperture radar, the development organization assembled a large radar antenna system, made of eight microstrip panels, each about 4 x 7 feet. The system also required a support structure for pointing and rigidity. The tight project schedule did not permit full-scale gain and pattern measurement before shipment of the antenna system to the SEASAT system contractor. The system test failed to meet its primary objective, to image the earth-orbiting Skylab satellite. It did accomplish the backup objective, to image a Learjet plane at 26,000 feet. The antenna was not designed for the heavy rain and severe wind occurring during the test program. Antenna phasing errors and cabling losses may have contributed to post-test antenna gain 6 dB lower and sidelobes 7 dB higher than expected. Without pre-test measurements, it was impossible to ascribe the test degradation either to the antenna or to other factors (such as uncertainties in the Skylab radar cross-section). Additional Keyword(s): Prototype System Development, Cost vs. Risk Tradeoff | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.1.4 ("Engineering Practices: Project and System Level Functional Verification and Validation - Planning") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/19/1985
363 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Receiver Degradation at Launch Site | Four days before scheduled launch, routine tests on both Viking Orbiter receivers showed degraded performance. These results were believed to have been influenced by the test environment. When designing system and subsystem tests one should carefully consider the environment and its possible effects on the test results. | Environments can significantly influence hardware testing, resulting in degraded performance. | When designing system and subsystem tests one should carefully consider the environment and its possible effects on the test results. Those environments most likely to influence test results are temperature; electro-magnetic radiation; radio-frequency radiation, reflection and interactions; gravity; and humidity. Care should also be taken to test all components and assemblies prior to the system test so as to detect and correct all performance degradations. | JPL | 12/22/1994 | Four days before scheduled launch, both Viking Orbiter receivers exhibited degraded thresholds during a routine precount test on the launch pad. This degradation would directly affect the ability of the Viking Orbiter to receive commands. Subsequent on-pad tests did not convincingly isolate the cause of the noise. Either the launch RF environment or the spacecraft hardware could be the cause of the problem. The decision was made to replace all the microwave components between the radio assembly and the high gain antenna, thus delaying the launch five days. No receiver degradation occurred during the mission. Subsequent tests on the removed microwave hardware and dual-frequency rotary joints showed a possible noisy connector, though not to the degree of severity experienced on the pad. Additional Keyword(s): Launch Operations | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.7 ("Management Practices: Spares, Testbeds, and Models") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/19/1985
373 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | In-Flight TWTA Anomaly | A bad weld in the cathode support structure of a Traveling Wave Tube Amplifier was postulated as the failure mode for degradation of the Mariner '71 downlink signal level. Adequately monitor the parts screening methods as well as contractor-specified manufacturing processes and test procedures, and improve contingency planning for the mission operations phase. | Contractor quality assurance programs and process controls may not be adequate for providing flight components capable of meeting mission requirements. Potential partial failure modes during the mission operations phase require contingency planning. | The projects should allocate enough resources so that JPL personnel can adequately monitor the parts screening methods as well as contractor-specified manufacturing processes and test procedures. Contingency planning for the mission operations phase should take into consideration potential partial failure modes, particularly where functionally redundant units are involved. | JPL | 01/25/1995 | The anomaly happened during Earth occultation on Mariner '71s forty-eighth orbit of Mars. When the DSN reestablished telemetry reception after occultation, several temperature and spacecraft power channels associated with Traveling Wave Tube Amplifier (TWTA) 2 were in alarm. The station confirmed a loss of 0.5 dB in downlink signal level that was indicated in the telemetry. The project elected to switch to the redundant TWTA-1 by ground command about two hours after the first observation. JPL and the subcontractors were never able to pinpoint the cause of the anomaly, even as to location in the tube itself or in the amplifier. Recommendations from the investigators included contingency plans in the event of yet more severe TWTA-1 problems, as they deemed TWTA-2 still operable in the low-power mode. (These TWTA-1 problems never occurred.) During the anomaly investigation, contractor quality assurance programs were reviewed and the process procedures used to assure high quality welds were found to be inadequate. One possible failure model postulated a weld failure in the cathode support structure. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.3 ("Safety and Mission Assurance Practices: Quality Assurance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/19/1985
374 | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN | Taylor, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Higher Data Rates Possible Through Station Arraying | Because the MVM '73 project went to a degraded telemetry mode after failure of an onboard tape recorder, the project had to use DSN arraying schemes to provide higher mission telemetry data rates. The project and the DSN must foresee and plan the use of complex and previously unused capabilities sufficiently in advance to allow the proper analysis and configuration testing to be completed. | The use of DSN arraying schemes can provide higher mission telemetry data rates than might otherwise have been possible. | The project and the DSN must foresee and plan the use of complex and previously unused capabilities sufficiently in advance to allow the proper analysis and configuration testing to be completed. Otherwise, prediction accuracy is degraded. | JPL | 01/25/1995 | A previous failure of the onboard tape recorder had made the "full resolution, full frame 117.6 kbps" mode the primary telecommunications mode at the second Mercury encounter. The increased Mercury to Earth range, relative to first Mercury encounter, required (1) a communications improvement of at least one dB over the performance obtained at the first Mercury encounter, and (2) commitment by the MVM '73 project to a bit error rate higher than .0333. The Telecommunications Division and the Deep Space Network (DSN) worked together to devise an arraying scheme to improve the signal-to-noise ratio. This consisted of real-time arraying of DSS-14, DSS-13, and DSS-12 at Goldstone through microwave connections. Testing one week before encounter showed a signal-to-noise ratio improvement of 0.8 dB; the actual improvement on encounter day was 1.0 dB. In addition, non real-time arraying of the signals from DSS-14 at Goldstone and DSS-43 at Canberra was to be attempted. This would consist of combining the tape-recorded signals from each of these stations to gain additional signal-to-noise ratio. This was accomplished at the DSN's Compatibility Test Area 21 and in the Division 33 Telecommunications Development Laboratory. The bit error rate achieved in real time met the .0333 criterion for more than five hours during the encounter. Additional Keyword(s): Tracking Station | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.2.2 ("Engineering Practices: Telecommunication Design") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 3.1.3 ("Mission Design: General - Protection of Critical Data") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 12/19/1985
279 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Exclusive use of Relative Spatial Positioning Commands for Mechanisms | The Mariner '69 Scan Platform and the Viking Orbiter Imaging Instrument Filter Wheel were operated with relative position stepping commands. In both cases, anomalies caused actual position to become different than the desired position. (This lesson largely duplicates #0405) Provide an explicit or absolute positioning capability in which the device can be commanded to a specific position, allowing development of sequences in which periodic positioning to absolute locations can be executed. (This recommendation largely duplicates #0405 (D)) | The potential for getting out of step and unnecessarily losing data due to use of relative positioning exclusively is quite high. | Provide an explicit or absolute positioning capability in which the device can be commanded to a specific position, allowing development of sequences in which periodic positioning to absolute locations can be executed. | JPL | 07/12/1993 | The Mariner '69 Scan Platform and the Viking Orbiter Imaging Instrument Filter Wheel were operated with relative position stepping commands. In both cases, anomalies caused actual position to become different than the desired position. Because each new position selection is based upon the previous position, all post-anomaly positions were incorrect until corrected via ground based interaction. This resulted in loss of science data. Additional Keyword(s): Design, Operations |  | N/A |  |  | Public | Not Specified |  | 12/18/1985
380 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate Knowledge of Spacecraft Tape Recorder Tape Position | For Voyager and Viking, tape position error accumulation on the onboard spacecraft tape recorder required arduous workarounds to reset the position indicator. Specifically, up/down counters should be used in all bidirectional divide by stages whenever accurate position information is needed. | Tape position error accumulation on an onboard spacecraft tape recorder can require arduous workarounds to reset the position indicator. | The capability to both observe and control movable elements to an appropriate precision (e.g. tape position, platform position, boom position, etc.) Without the possibility of significant error buildup through normal use should be incorporated into the basic spacecraft system design. Specifically, up/down counters should be used in all bidirectional divide by stages whenever accurate position information is needed. | JPL | 02/01/1995 | The Viking and Voyager onboard tape recorders contain a mechanism to provide knowledge, via downlink telemetry, of the position of the tape. The project can also command the tape to a desired position by uplink telemetry. The design is such that an intolerable amount of error accumulates during normal use requiring an arduous workaround involving periodic interruption in use to reset the position indicator at a known tape position (i.e. beginning of tape). Additional Keyword(s): Positioning Devices | JPL has referenced the lesson as supporting Paragraph 4.4.4.1 ("Information System Design: Commanding and Sequencing - Use of Toggle and Step Commands") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 12/18/1985
262 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Concurrent Real-Time Operations and Advanced Planning | The magnitude of both the real-time cruise activities and the work required to perform advanced planning for future activities, such as encounter, landing site certification, test and training, and orbit insertion activities during the Viking mission were significantly underestimated and required an unplanned organizational change during the cruise operations. When spacecraft mission encounter and post-encounter planning are not completed prior to launch, separate organizations should be established for conducting the cruise activities and accomplishing the encounter planning. | When an organization conducts real-time operations and future planning concurrently, all resources tend to be used in support of real-time activities. | When spacecraft mission encounter and post-encounter planning are not completed prior to launch, separate organizations should be established for conducting the cruise activities and accomplishing the encounter planning. | JPL | 06/28/1993 | The magnitude of both the real-time cruise activities and the work required to perform advanced planning for future activities, such as encounter, landing site certification, test and training, and orbit insertion activities during the Viking mission were significantly underestimated and required an unplanned organizational change during the cruise operations. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 12/10/1985
270 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Planning for Spacecraft Real-Time Commanding |  | Although on-board sequence control is the primary spacecraft command mode, a flexible interface with real-time ground based commanding is required. | Ensure that the back-up real-time ground command system has the necessary capability and flexibility for continuous use during all phases of the mission. | JPL | 07/07/1993 | Voyager flight operations strategy and system design was based upon a philosophy of very limited real-time ground commanding, assuming the vast majority of activity could be preloaded onto the spacecraft. Flight experience, particularly early in the mission, proved that the need for real-time commanding was significantly greater than planned. The end-to-end system design which was based upon the above strategy was cumbersome to use in a real-time commanding environment. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 12/10/1985
278 | Larman, B - 0000000000 : NO@ADDRESS.GIVEN | Larman, B - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate Time Allocated for Planning for DSN Support | Planning for the two-spacecraft Voyager mission did not consider the extra time needed to arrange for the allocation of Deep Space Network (DSN) coverage for the operation of both spacecraft. Lead times for project and institutional planning must be considered at the time the project mission operations plan is being developed. | Significant lead time is required for planning the allocation of Deep Space Network (DSN) facilities in support of spacecraft operations. | Lead times of project and institutional planning processes must be considered at the time the project mission operations system implementation plan is being developed. | JPL | 07/12/1993 | Flight sequence timelines for the two concurrently operating Voyager spacecraft were inadequate because of omissions due to failure to consider in a timely manner trajectory data and DSN coverage plans for both spacecraft. Significant lead time is required for planning the allocation of Deep Space Network (DSN) facilities in support of spacecraft tracking, telemetry, and command operations. Conversely, spacecraft sequences are designed far in advance and are dependent upon expected DSN configurations. The entire effect is exacerbated when multiple spacecraft and trajectories must be accommodated. |  | N/A |  | Science | Public | Not Specified |  | 12/10/1985
307 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | Anomalous AMPTE/CCD Command Counter Readings | Five times during one month the “Unexecuted Command Counter” value was anomalous. Possible causes included incorrect incrementing of the counter, incrementing due to noise, or commands that were rejected due to incorrect bit patterns. The telemetry formats should be designed considering all potential analyses that may require time-tagged data. | Counter status is more valuable if transmitted in real-time telemetry data which is time-tagged and permits the counter readings to be continuously correlated with command events. | The telemetry formats should be designed considering all potential analyses that may require time-tagged data. | JPL | 09/20/1993 | During a one month period, the Active Magnetospheric Particle Tracer Explorer/Charge Composition Explorer Spacecraft experienced five occasions when the "Unexecuted Command Counter" value was anomalous and no explanation could be found. Real-time and delayed commands had all been executed and correctly accounted for in the "Executed Command Counter". These counters are only read out in the memory readout at the beginning and/or end of a pass and not in the normal real-time telemetry. Three possible causes of the anomaly are as follows: The counter incremented anomalously. The counter was incremented by noise or other stimuli. The system received commands from an unidentified source but rejected them for incorrect bit patterns. Additional Keyword(s): Operations | JPL has referenced the lesson as supporting Paragraph 4.4.6 ("Information System Design: Telemetry Visibility - Visibility of S/C Status") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 12/05/1985
354 | Collins, R - 0000000000 : NO@ADDRESS.GIVEN | Collins, R - 0000000000 : NO@ADDRESS.GIVEN |  | ATMOS Hygroscopic Optics Degradation | The ATMOS instrument suffered damage to its optical system as a result of excess humidity due to a climate control failure. Provide indicators and alarms for environmentally sensitive hardware, and ensure that adequate safeguards are in place. | Failure of environmental control systems, especially when no fail-safe alarms have been incorporated into the system, can result in significant degradation of environmentally sensitive flight hardware. | Environmentally sensitive hardware must be protected with indicators and alarms from loss or degradation of the environmental control system. Safeguards must also include a method for alerting appropriate personnel in the event of a failure of the environmental control system. If the alerting system does not provide for adequate time for recovery action, redundant systems should be considered. A review of the environmental control system design and implementation by user and facility cognizant personnel should be performed to assure that appropriate safeguards are in place and that they are adequate for the level of protection required. System failure modes should be exercised to check out the safeguards and train the appropriate personnel. | JPL | 12/09/1994 | On May 25, 1983, the ATMOS instrument suffered damage to its optical system as a result of a temporary outage of the special environmental control system due to a failure of the freon compressor. This environmental control system was necessary to meet the stringent humidity requirements of ATMOS while in the Spacecraft Assembly Facility (SAF). The failure caused the temperature in the ATMOS room to rise quickly to 77 degrees F. and the humidity to 66%, a condition which damages the unprotected potassium bromide optics. The design constraint for the ATMOS humidity control is to remain below 40% relative humidity. The loss of control of temperature and humidity were caused by failure modes inherent in the humidity control system design, which were not adequately evaluated. When the failure occurred, no alarm was sounded as no sensors with alarms had been incorporated into the environmental control system. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/02/1985