1137 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Work Documentation/Unincorporated Changes |  | Although progress has been made to improve the quality, accuracy, and traceability of the work instructions ("paperwork" used in the processing of Space Shuttle Orbiters) much remains to be done to provide correct and unambiguous procedures. There are still too many unincorporated changes. | Efforts to improve the quality, accuracy, and traceability of the work paper as well as the timeliness of incorporation of changes to work instructions must be given higher priority by both NASA and USA in a coordinated, systematic effort. | HQ | 02/01/2000 | Space Shuttle Program/Work Documentation/Unincorporated Changes | NASA concurs with the ASAP recommendation. During the 1999 calendar year, numerous initiatives were accomplished which established the foundation to improve the quality, accuracy, and traceability of work instructions. Examples of these initiatives include appointment of a USA documentation manager and four dedicated project leads, the creation of a new work instruction format and style guide, development of a systematic procedure to perform task and document analysis, development of the new work authorization document authoring and validation environment (WAVE) computer software to allow engineers to quickly and easily modify work instructions, and reduction of deviation backlog. With this foundation, priority was given by USA shuttle engineering to establishing a Year 2000 Strategic Initiative to "Increase the quality and level of workability of work-authorizing documentation." In addition, a comprehensive Category I Document Evaluation & Restructure (CDER) Plan was established to effectively improve the quality, accuracy, and tractability of both flight and groundwork instructions. The CDER Plan will ensure document simplification as the WAVE software, Maximo, and PeopleSoft initiatives are implemented. Work instructions, rewritten to the new standards established in 1999, will include restructuring to only include the work steps needed for that specific task as defined by the needs of the Maximo Job Plan and PeopleSoft Product Structure. Contingency steps, or steps applicable to other hardware, will be removed and placed in a separate work instruction package to avoid confusion. Also, work instructions that could be in multiple formats due to numerous previous contractor requirements will be converted to standard formats. Finally, any existing deviations will be incorporated as part of the rewrite. The end result will be a smaller, cleaner, concise work instruction package, including more graphics and pictures. The procedures will be reviewed and agreed to by the end user. This plan has two primary paths-- one for flight operations and another for ground operations. The determination of which of these paths a work instruction will follow is dependent on the criteria set forth in the PeopleSoft Product Structure and the Maximo Job Plan. PeopleSoft and Maximo are management systems through which a reduction in the time required to incorporate paperwork can be achieved. The conversion of documents to PeopleSoft and Maximo will be heavily site and flow dependent. The goal is to complete approximately 500 planned flight hardware processing work instructions for calendar year 2000, with continued emphasis in subsequent years. Selection of those work instructions is based on pre-established criteria involving run frequency and criticality. By the end of FY 1999, USA had reduced deviations approximately 25 percent, from 7,300 to 5,535. A technical standard panel has been implemented and is chartered to review errors detected by audit teams, determine the root cause of the discrepancies, and take real-time action to prevent their re-occurrence. Also, the implementation of a distributed authoring approach allows engineers to write their work instructions, provide ownership, control and accountability of their work instructions, and increase the number of operational maintenance instructions with zero deviations. To allow the engineer to make quick and easy incorporation of changes and provide on-line review and concurrence by USA and NASA prior to the work instruction being issued to processing operations, a single Universal Test Operations Procedure format has been established for all flight documents in Documentum/PeopleSoft, and a single Job Plan format has been developed for all ground documents in Maximo. A standard electronic deviation template has also been developed. These actions will assure succinct, technically accurate, and user-friendly work instructions. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1138 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Facilities, Test Equipment, and Ground Support Equipment (GSE)/Supportability |  | There is no systematic plan to counter obsolescence and assure the availability of adequate facilities, GSE, and specialized test-and-checkout equipment throughout the expected lifetime of the Space Shuttle. | There is no systematic plan to counter obsolescence and assure the availability of adequate facilities, GSE, and specialized test-and-checkout equipment throughout the expected lifetime of the Space Shuttle. | HQ | 02/01/2000 | Lack of Systematic Plan to Counter Obsolescence of Shuttle Facilities, Test Equipment, and Ground Support Equipment (GSE) | NASA concurs with the ASAP recommendation. A specific focus on SSP infrastructure has been established for FY 2000, identifying issues and concerns throughout the program. The SSP initiated an effort in November 1999 to develop a plan and identify the requirements and resource levels required to address the infrastructure backlog and supportability needs for the SSP through FY 2012. This effort has incorporated all SSP elements and support functions at Office of Space Flight Centers and the Dryden Flight Research Center. The completed plan will define infrastructure project funding requirements for vital components that support or directly impact the SSP. The plan spans across multiple years and will address the SSP short-term as well as long-range needs. Supporting SSP element infrastructure long-range assessments/plans have been completed or are in the process of completion. Two examples of SSP element supporting efforts are the Ground Systems Survivability Assessment, which addresses obsolescence by providing a component level assessment of requirements to maintain or improve existing capabilities, and the External Tank Project's 15-year plan. The completion of the Infrastructure Plan is a major Space Shuttle initiative whose results will be included in the Program Operating Plan strategy. The SSP has assigned a lead at KSC to formulate the SSP infrastructures upgrades requirements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1139 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Workforce/Workload Sustainment |  | Space Shuttle processing workload is sufficiently high that it is unrealistic to depend on the current staff to support higher flight rates and simultaneously develop productivity improvements to compensate for reduced head counts. NASA and Shuttle Processing Contract (SPC) cannot depend solely on improved productivity to meet increasing launch demands. | Hire additional personnel and support them with adequate training. | HQ | 02/01/2000 | Higher Shuttle Flight Rates Driving Higher Workloads | NASA concurs with the ASAP recommendation. Both NASA and SPC recognize the need to assure adequately staffed and trained personnel for processing the Shuttle and, simultaneously, pursue productivity improvements that can help meet the planned flight-rate increases. To address this concern, KSC civil servant Shuttle Processing has authorization for additional staff, and SPC is increasing their workforce at KSC from 3,650 to approximately 3,900 to support Shuttle processing. Recruitment for these positions is in progress and expected to be completed in FY 2000. Finally, a replenishment rate for FY 2001 has been authorized at KSC, which will permit continued infusion of skills to offset anticipated attrition. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1140 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Workforce/Qualification |  | Due to attrition of experienced personnel, NASA and its contractors are assigning more newly trained personnel to Space Shuttle operations tasks. This has led to concerns in the workforce regarding the qualifications of some newly-assigned personnel. | NASA and its contractors must ensure that their training, certification, and task assignment processes are such that only suitably qualified engineering and technical personnel are performing Space Shuttle operations. Any training and licensing program to certify new personnel must include both testing of acquired skills and demonstrated proficiency on the assigned task. | HQ | 02/01/2000 | Workforce Attrition Driving the Use of Less Experienced Personnel | NASA concurs with the ASAP recommendation. NASA and the contractor agree that demonstrated proficiency for operational tasks is a key factor to safety and success. NASA and the contractor recognize the direct relationship between personnel proficiency and flight safety, and this is reflected in the training, certification, and operator assignment processes implemented by both NASA and contractor. For ground operations involved in processing and operating the Space Shuttle systems, all newly hired contractor personnel are provided applicable training for security, safety, and the critical skills required for the area and system of their assignment. In addition to this general training, contractor personnel begin their orientation by becoming familiar with procedures, drawings, physical surroundings, etc. Once they have an understanding of these requirements, they accompany other experienced, skilled personnel on the job performing formal and informal on-the-job-training (OJT). In addition to the certification provided upon the successful completion of OJT, engineers must also complete Stand Board examinations for critical systems. Processing tasks are assigned based on the experience level of the employee. Processing tasks are not all equally critical, and newly-certified personnel are generally assigned to low criticality tasks. This allows the more experienced personnel to focus on critical tasks. Employees are required to be recertified on a regular basis. The recertification involves varying degrees of proficiency testing based on the functional criticality of the task. The concerns and needs for assuring that the contractor workforce has the appropriate skills and proficiency to perform Space Shuttle processing responsibilities are applicable to the NASA civil service workforce as well. Training plans are defined for all entry-level technical positions within NASA Shuttle Processing. These plans include both formal classroom training and OJT packages required for the performance of the NASA Space Shuttle operations role. Newly-hired or transferred personnel are required to accomplish this training prior to performing unsupervised engineering or technical tasks. The supervisor is responsible for assuring that the training has been accomplished and adequate proficiency has been demonstrated. There is also continuous involvement with critical task surveillance, out-of-family disposition, and NASA-retained functions to maintain the critical skills of the workforce. While the level of direct NASA involvement has decreased with the planned transition of more responsibility to the contractor, NASA Shuttle Processing has increased its focus on simulation training to augment the need for engineers to maintain their knowledge of systems performance and operations. Increased utilization of Tier 3 training (integrated simulation training) has been implemented. Tier 1 (single system) and Tier 2 (multisystem) simulation training is also being planned to ensure proficiency. Requirements definition for system development is now complete for Tier 1/Tier 2 training, and implementation plans are in work. In the flight operations area of Space Shuttle support, the Mission Operations Directorate and USA have jointly defined and documented training and certification criteria for all personnel assigned to mission-critical functions. These plans are based on the position requirements and criticality of the assigned position. The training and certification plans and processes are unique for flight designers, training instructors, and flight controllers. Personnel are not assigned mission-critical responsibilities without having executed formal training and certification plans, as well as successfully demonstrating the capabilities consistent with the level of responsibility required by the position. Extensive use of simulations for mission control teams and individual operators is used in both the initial certification and the continuous proficiency training of flight control operators. Experience level is a critical part of successful flight operations. To ensure that training, certification, and task assignment processes are such that only qualified personnel are performing Space Shuttle operations, NASA uses trending and root-cause analysis of quality and safety occurrences to indicate those traceable to training processes. This approach allows for a continuous assessment of the process of providing qualified personnel for performance of Shuttle processing and operations. USA has a performance management program to: Ensure communication between the employee and management Ensure that responsibilities and expectations are clearly understood Review employee job performance Make recommendations to improve employee job performance Establish a record of the performance achieved by each employee. This performance management program is an ongoing process of planning, coaching, and reviewing. Management meets with each employee to discuss and establish individual objectives, including training, each year, and agree on how employee success will be measured. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1132 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Computer Hardware-Software/International Space Station/Software Development |  | Several software developments are on the critical path for launch and operation of the ISS. While some software elements have had the early involvement of a multi-disciplinary team that includes users and operators, many have not. The lack of user involvement results in increased schedule and safety risk to the program. | The ISS program should follow a concurrent engineering approach to building software that involves users and other key discipline specialists early in the software development process to provide a full range of perspectives and improve the understanding of requirements before code is developed. | HQ | 02/01/1999 | Consistent User Involvement in Software Development Process | NASA concurs with the recommendation. The US portion of the ISS is structured around an Integrated Product Team approach. This approach did, and does, include specialists from users and operators during all phases of development. The international partner's development is followed closely by subsystem and operations working groups to enhance system understanding and involvement by system experts, crew, and operations personnel. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1127 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Computer Hardware-Software/Checkout and Launch Control System (CLCS) |  | Present plans depend on human procedures to achieve lockout to prevent inadvertent or unauthorized access to actual hardware when using the new Checkout and Launch Control System (CLCS). | NASA should use a computerized authorization to achieve lockout of commands to actual hardware from anyone not authorized to issue such a command in CLCS. | HQ | 02/01/1999 | Potential Unauthorized Access to Checkout and Launch Control System (CLCS) | NASA concurs with the ASAP recommendation. The CLCS Project will undertake a study with the Shuttle engineering community to determine how these lockouts could be implemented. The results will include a preliminary set of requirements for CLCS and other systems, such as the Shuttle Data Center and Simulation Systems, an operational risk assessment for implementing these changes, and a rough order of magnitude cost assessment for implementing these changes. The study will be completed in a timely manner so that implementation can be accomplished in time to avoid extensive revalidation of CLCS application software. Progress reports will be presented to the ASAP during their CLCS review meetings. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1131 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Computer Hardware-Software/International Space Station/Software Development |  | The ISS presently has no program-wide software development standards to manage software activities performed by NASA, its contractors, and the international partners. | The ISS program should establish program-wide standards to aid in specifying, designing, developing, and managing all future ISS software projects. These standards can be as simple as a set of best practices. | HQ | 02/01/1999 | Lack of Program-Wide Software Development Standards | The ISS program should establish program-wide standards to aid in specifying, designing, developing, and managing all future ISS software projects. These standards can be as simple as a set of best practices. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1144 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Supportability |  | The EVA Project Office has several planned initiatives to ensure the availability of adequate EVA resources to support the ISS and Space Shuttle. These initiatives cover acquisition of material, development of procedures, and improved training. | Expedite completion of the planned initiatives related to the safety of EVA so that maximum benefit can be realized during the upcoming intensive ISS assembly schedule. | HQ | 02/01/2000 | Potential International Space Station (ISS) Supportability Problems With Existing Extravehicular Activity (EVA) Assets | NASA concurs with the ASAP recommendation. In June 1999, the EVA Project Office initiated the development of a small planar hard upper torso (HUT) in addition to the medium, large, and extra-large HUT's already developed. With four HUT sizes, the broadest range of crewmembers (~5th percentile Asian female to 95th percentile Caucasian male) will be accommodated. The small planar HUT has successfully completed the concept development phase, and the preliminary design review is scheduled for May 2000. The first flight item is on schedule for delivery in October 2002. Redesign of the (EMU) to allow for on-orbit replacement of a primary life support subsystem, HUT, displays and control module, and secondary oxygen pack is ahead of schedule to support the ISS 6A flight. The EVA Project Office is assessing the feasibility of flying the EMU on-orbit replacement unit configuration on ISS flight 5A prior to the need to leave an EMU onboard the ISS during 6A. Single mission certification for the phase VI glove was accomplished prior to ISS flights 2A and 2A.1. Full certification (up to 19 EVA's) was completed in March 2000, approximately 1 year prior to leaving phase VI gloves onboard the ISS for ~90-day increments. Like the phase VI glove, the U.S. Simplified Aid for EVA Rescue (SAFER) has flown with single-mission certification on five previous missions. Anomalies identified during three of these previous missions - STS-86 (failed NASA standard initiator (NSI) drive circuit), STS-88 (erroneous indication of no remaining gaseous nitrogen), and STS-96 (inadvertent NSI firing) - have all been successfully resolved through hardware redesign and/or procedures modification. A final anomaly relative to the battery gauge, which supports the requirement to remain onorbit continuously for 1 year, has been resolved, and the hardware will be certified prior to ISS flight 2A.2a (STS-101) in May 2000. Development of the Russian SAFER (RSAFER) was transferred to the RSA in April 1999 when they offered to cost share the hardware production and successfully completed the project preliminary design review. Currently, the critical design review is planned for FY 2001. One open issue to be resolved is the contractual authority to develop the RSAFER. The original plan included the RSAFER in the $35M contract modification between NASA and the RSA; however, due to congressional concerns this contract modification is currently on hold. The baseline plan to launch the RSAFER on ISS flight 7A.1 will need to be readdressed following official contract authority with the RSA. Lastly, NASA has successfully completed all of the technical and medical work necessary to implement a 2-hour EVA prebreathe protocol from a 14.7 psi atmosphere. NASA Headquarters has given approval, and plans are being developed to demonstrate the 2-hour protocol procedures (either on the ground or as part of a detailed test objective demonstration on ISS flight 5A or 6A) prior to implementation on ISS flight 7A when the joint airlock is launched. Additionally, decompression sickness contingency plans and flight rules have been developed, and crew and flight surgeon training has been initiated. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1141 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/CRV/Schedule Delay |  | Acquisition of the ISS Crew Return Vehicle (CRV) has been lagging and appears to be facing further delay. The full-crew CRV is needed for long-term safe operation of the ISS with a crew larger than three astronauts. | Take whatever steps are necessary to halt the delays to the CRV program without jeopardizing adequate demonstration of safety of design and certification of human-rating. | HQ | 02/01/2000 | Crew Return Vehicle (CRV) Schedule Requirement for ISS Crew Greater Than 3 | NASA concurs with the ASAP recommendation. Significant progress has been made in establishing the CRV project in the last year due to commitment at all levels within NASA - from the Administrator, the Office of Space Flight, JSC, the ISS Program Office, and the X-38/CRV Project Office. The original Office of Management and Budget (OMB) decision and Congressional markup reduced the project funding in FY 2000, which delayed the start of CRV Phase 1 (engineering development through critical design review). NASA Headquarters successfully argued for the necessity of starting Phase 1 in FY 2000 and obtained OMB concurrence to transfer funding to start this phase in late FY 2000. The request for proposals for CRV Phase 1 has been released since the last ASAP review. Bids have been received from three offerors and are currently being evaluated. The current evaluation schedule will allow a Phase 1 contract award in the August-September 2000 timeframe, and the funding is in place. In support of this planned CRV Phase 1 start, the X-38 Project Office has worked with the Langley Research Center (LaRC), Independent Program Assessment Office, to close out all open actions from the LaRC independent assessment (IA). Approximately 90 percent of the 110 "maturity gates" identified by the IA team have been closed to date, and an acceptable status of all of the 110 items is expected prior to a final Headquarters Program Management Council presentation in July 2000. Progress on these items confirms a significant reduction in risk prior to the start of Phase 1. The X-38/CRV prototype project has successfully completed five atmospheric flight tests and numerous parafoil tests. A major milestone was achieved in January 2000, with the first flight test of the full-scale parafoil for the space vehicle. This parafoil is the size necessary for a CRV carrying seven crewmembers and contains all required design features for a human-rated system. This test was conducted without any anomalies, demonstrating NASA's clear understanding of all the basic technical issues of parafoil flight as well as our ability to extrapolate from sub-scale testing to full-scale testing. The atmospheric vehicle flight tests have demonstrated many of the new technologies (lifting-body aerodynamics, flight control systems, parafoil deployment, and electromechanical actuators) planned for the CRV. A fifth test is scheduled prior to the end of July 2000, which will confirm performance characteristics of the improved body shape. In addition, the critical element in the CRV navigation system will be tested in space aboard the Space Shuttle on STS-101 in May 2000. A critical CRV technology - global positioning system-based attitude determination - will be demonstrated on this flight. In the aggregate, all of these tests significantly reduce the technology risks of the CRV. Assembly and testing of the X-38 space test vehicle is proceeding, and the first simplex power-up to the vehicle occurred in March 2000, verifying end-to- end system power. The Space Shuttle program is currently manifesting the X-38 space test for April 2002. This will support a start of CRV Phase 2 (production) at the start of FY 2003, and a CRV operational date in late FY 2005 to early FY 2006, based on final production funding profiles. NASA remains firm in its commitment to review results from the space test prior to production. NASA has further established decision logic to be used to determine if a space test of the production vehicle will be necessary after the X-38 space test. This decision logic will ensure that critical evaluation and testing are not compromised by the accelerated CRV schedule. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1143 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Solid Fuel Oxygen Generator (SFOG) Utilization |  | The Russian Solid Fuel Oxygen Generator (SFOG) is baselined as the backup oxygen supply system for the ISS. This device has experienced problems in its application on Mir and thus may be a potential safety hazard when operated on the ISS. | Examine ways to eliminate the risks posed by the use of the Russian SFOG such as by determining the availability of a better, "off-the-shelf," safety-proven SFOG or by initiating an R&D effort to produce a safer alternative. | HQ | 02/01/2000 | Utilization of Russian-Built SFOG May Pose a Safety Hazard Aboard International Space Station (ISS) Given Past Problems With the Solid Fuel Oxygen Generator (SFOG) | NASA concurs with the ASAP recommendation. A joint NASA-Russian Space Agency (RSA) team has completed an investigation of the SFOG experience on Mir. The failure mode has been identified and has been reproduced and verified during ground tests. The position of the NASA-RSA team is that the Mir experience was an isolated incident. Units planned for use on the ISS have been subjected to lot testing and screening of manufacturing and quality records and test reports. A non-flammable containment system to prevent propagation of a fire has been developed and tested as an additional safety enhancement. The conclusion of a joint NASA-RSA engineering, safety and mission assurance, and program management team is that this system is safe for operation on the ISS. A parallel effort to develop a commercial off-the-shelf oxygen generation system was initiated by NASA during the SFOG failure investigation. This system has been certified for use, if necessary. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1142 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Crew Health/Radiation |  | The NASA personnel who are involved in finding solutions for the problems of radiation in space have developed an excellent long-range plan to define approaches for crew protection. | Continue to support the nascent, but better defined, radiation effects research and development program. | HQ | 02/01/2000 | Radiation Research and Protection Implementation Planning at NASA | NASA concurs with the ASAP recommendation. NASA has focused on solutions for the radiation program. Our recommendations include: (1) Completing and expanding on efforts made in the May 1999 EVA Radiation Protection Summit held at JSC to improve radiation protection. This involves development of an active personnel dosimeter to be worn on the extravehicular mobility unit (EMU) (first test flight to be in Fall of 2000), study of possible shielding improvements for EMU and design of localized shielding enhancements to ISS, and development of trapped radiation models; (2) Increasing coordination between NASA's Office of Life and Microgravity Sciences and Applications, the JSC Radiation Health Program, the National Oceanic and Atmospheric Administration (NOAA), and NASA's Office of Space Science on forecasting and monitoring changes in space weather; and (3) Improving coordination of radiation protection across NASA. To further the coordination across NASA, Dr. Richard Williams, from NASA Headquarters, Office of Life and Microgravity Sciences and Applications, has been appointed as head of a task group to develop an Agencywide plan to implement this objective. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/25/2002
1098 | Woloshin, Mark - 0000000000 : NO@ADDRESS.GIVEN; Montague, Ronald - | Woloshin, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | Establishing common policies and rules for multi-organizational processes |  | Processes requiring the support and participation of multiple entities must be pre-established by the host facility prior to need | The 2A team established standard work policies to ensure consistent processing of the flight hardware. The policies and processes were documented in a "2A Team Instruction" which was approved by all the effected organizations. The Team Instruction documented all approved processes for processing the hardware. Documented under the team instruction were tool control in and around the flight hardware, access to the flight hardware, contamination and foreign object debris (FOD) control methods, test readiness review and constraint review processes, configuration control procedures, red streamer and mate/demate log procedures, etc. Team Instructions have been established for other missions; however, it is recommended that a consistent set of Team Instructions be established for all Space Stations hardware. In addition, the methods and process learned should be applicable to all other ISS segments. Discipline should continue to be maintained by the facility host or responsible prime contractor. | JSC | 05/26/1999 | There were a number of different organizations involved in the processing of the 2A hardware and each organization had its own set of work rules. This often caused confusion among the different organizations and KSC personnel that were required to work on the hardware. There were also policies and work practices that were new to the organizations and were not documented for a consistent implementation. These policies and rules ranged from topics like tool control and access control to topics such as scheduling and test readiness reviews. The confusion with the rules and policies often led to work delays and the loss of a team atmosphere. Root cause: Integration of multiple players was not factored into program planning at the lowest levels. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1097 | Rush, Carol - 0000000000 : NO@ADDRESS.GIVEN; Montague, Ron - | Rush, Carol - 0000000000 : NO@ADDRESS.GIVEN |  | Safety & Mission Assurance (S&MA) Concurrence on International Space Station (ISS) Chits |  | Many flight program chits have safety implications; approval without Safety concurrence may compromise Hazard Controls, Flight Rules, or Critical Items | Ensure that Safety signature requirement is incorporated into CHIT processes such as ISSA MER. | JSC | 01/01/2001 | The STS-88/2A mission had around 150 Chits written requesting information from the Mission Evaluation Room (MER), Flight Control Team, or Moscow. The ISS MER Chits did not require Safety concurrence prior to closure by the MER Manager. Many Chits had safety implications; approval without Safety concurrence might have negatively affected Hazard Controls, Flight Rules, or Critical Items. Users of Chits may not be aware of existence of Safety concurrence or disapproval of Chits. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1099 | Dutton, Jeff - 0000000000 : NO@ADDRESS.GIVEN; Montague, Ronald - | Dutton, Jeff - 0000000000 : NO@ADDRESS.GIVEN |  | Integration of Multiple Mission Objectives Amongst Programmatic Disciplines |  | Communication and assessment of technical objectives throughout complex flight programs is essential to ensuring successful integration of multiple activities | Ensure the widest range of communications at the program level to preclude interelement conflicts during integrated operations. | JSC | 02/18/1999 | Space Vision System (SVS) targets have become an undue burden during EVA. The requirement to restrain cables away from SVS targets added 45 minutes to 1 hour EVA time and will change during the mission. The EVA community has been informed that the targets can be easily damaged by EVA loads, yet the targets are in or near translation paths. A better understanding of the criticality of keeping the targets free of obstructions and the sensitivity of the targets to EVA contact is required. The SVS community must understand the EVA environment and not place unrealistic constraints on the conduct of the EVA. The EVA Project Office is working with the SVS community to resolve these issues. Root cause: Insufficient coordination and understanding between the SVS and EVA communities. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1110 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Radiation Exposure/Research in Health Physics |  | By virtue of the several ongoing programs for the human exploration of space, NASA is pioneering the study of radiation exposure in space and its effects on the human body. Research that could develop and expand credible knowledge in this field of unknowns is not keeping pace with operational progress. | Provide the resources to support more completely research in radiation health physics. | HQ | 02/01/1999 | Adequate Resources for the Study of Radiation Exposure | NASA concurs with the recommendation. The funding for radiation research has been augmented over the past couple of years. Expanding support for radiation health physics research will benefit the mitigation of effects of space radiation and the accurate determination of organ doses. NASA's Space Radiation Health Program supports basic research in radiobiology and biological countermeasures. The Radiation Health Program has initiated efforts to provide reference dosimetry capabilities for flight dosimetry at Loma Linda University and Brookhaven National Laboratory. A phantom torso is being used to assess organ doses on Shuttle and ISS. JSC has initiated efforts to improve measurements of the neutron contribution to doses in LEO. These efforts include increasing opportunities to use neutron detector systems and the development of a high-energy neutron detector by the National Space Biomedical Research Institute (NSBRI). Improved understanding of radiation transport properties of the GCR and neutrons can be used to develop shielding augmentation approaches for crew sleep quarters and exercise rooms on ISS. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1109 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Crew/Radiation Exposure |  | In the ASAP Annual Report for 1997, the Panel expressed concern for the high doses of radiation recorded by the U.S. astronauts during extended Phase I missions in Mir. Subsequent and continuing review of this potential problem revalidates that unresolved concern. The current NASA limit for radiation exposure is 40 REM per year to the blood-forming organs, twice the limit for the U.S. airline pilots and four times the limit for Navy nuclear operators (see also Finding #23). | In the ASAP Annual Report for 1997, the Panel expressed concern for the high doses of radiation recorded by the U.S. astronauts during extended Phase I missions in Mir. Subsequent and continuing review of this potential problem revalidates that unresolved concern. The current NASA limit for radiation exposure is 40 REM per year to the blood-forming organs, twice the limit for the U.S. airline pilots and four times the limit for Navy nuclear operators (see also Finding #23). | HQ | 02/01/1999 | Reduction in the Annual Limit for Radiation Exposure | NASA concurs with the recommendation. However, in keeping with the "as low as reasonably achievable" (ALARA) radiation protection principle, NASA is proposing a set of administrative spaceflight exposure limits which are significantly below the NCRP recommended annual limits. The administrative limits are designed to improve the management of astronaut radiation exposures and ensure that any exposures are minimized. The proposed administrative BFO exposure limits range from 5 cSv (REM) for a one month exposure period to 16 cSv (REM) for a twelve month exposure period. These limits have been proposed for inclusion in section B14 of the Flight Rules and are currently awaiting concurrence from Energia and the Russian Space Agency. The National Council on Radiation Protection and Measurements (NCRP) developed these limits in 1989 for NASA. The NCRP is a congressionally chartered organization responsible for developing radiation protection limits. The NASA Administrator, OSHA, and the Department of Labor approved these limits. NASA has adapted 30 day and annual dose limits of 0.25 Sv and 0.5 Sv, respectively. The purpose of these limits is to prevent acute health effects, such as nausea, vomiting, etc. NASA also maintains career limits intended to limit the probability of cancer below 3% excess cancer mortality. These career limits are comparable to the US career limits for other radiation workers. Furthermore, the annual limits also serve to spread out career radiation exposure over time. The NCRP completed a re-evaluation of astronaut exposure limits in 1998 using the most recent results from longitudinal studies of Japanese atomic bomb survivors. Currently, the NCRP has a draft report undergoing full NCRP review and approval, which is expected to be released in the fall of 1999. When this report is released, NASA will consider its recommendations and, if appropriate, will proceed to implement any recommended reductions. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1108 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Crew Return Vehicle (CRV)/X-38 Risk Assessment and Testing |  | Plans calling for availability on orbit in early 2003 of a U.S. CRV based on the X-38 technology demonstrator are highly ambitious. Although much of the X-38 technology is off the shelf, there are numerous features that rely on yet unproven approaches. | NASA must not allow the limited CRV development time to comprise the conduct of a thorough risk assessment and testing program. | HQ | 02/01/1999 | Thorough Risk Assessment and Testing Program for the Crew Return Vehicle (CRV) | Concur. The new CRV acquisition strategy requires the developing contractor to take responsibility/accountability for the CRV's flight readiness. The CRV RFP Synopsis asked candidate contractors about CRV risks. None identified 2003 launch readiness as a significant risk. For government developed technologies (i.e. parafoil and OML aero) the test programs are ongoing and will be demonstrated with flight tests. Although much of the X-38 design is based upon off-the-shelf technology, it is recognized that features such as the parafoil landing system are unproven. Where this is the case, extra testing is being performed to certify and human rate these systems. The extensive parafoil test program at the Yuma Proving Ground is an example of the rigorous testing of an unproven design. The last several successful parachute tests are beginning to show the fruits of this approach. Once parafoil testing has reached a point, which has a proven safety and maturity of its design, the parafoil design will not be allowed to be changed by the contractor in their CRV design. Safety and Mission Assurance play an important role in the X-38 Phase 1 activity. Each contractor will be required to develop at least an S&MA Plan, Risk Management Plan, Vehicle Certification Plan, Vehicle fault tolerance studies & recommendations, Failure Mode, Effect, and Criticality Analysis, and Human Rating Assessment for their CRV design. Quality of these S&MA tasks will play a major role in the selection by NASA personnel of one contractor to perform the Phase 2 task of building the CRV. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1107 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Crew Return Vehicle (CRV)/Accelerated Development |  | The current ISS requirement is for a single Crew Return Vehicle (CRV). Crew safety over the life of the ISS requires the availability on orbit of two CRV's, both of which is capable of accommodating the entire crew. The Soyuz capsule, designated as the interim CRV, does not have a full crew capability. Also, it is uncertain that sufficient Soyuz capsules and their launches will be available to supply the needs of the ISS. | NASA should accelerate its program to develop and deploy two full-crew CRV's and take whatever measures are necessary now to ensure the availability of sufficient Soyuz capsules and launchers until the CRV's are ready. | HQ | 02/01/1999 | Initial Operational Capability of Crew Return Vehicle (CRV) | The item remains open and under assessment. The ISS Program has assessed the need and feasibility for a second CRV on-orbit aboard the Space Station. A Tiger Team, led by the Astronaut Office, was chartered to assess the overall effectiveness. The Tiger Team presented its findings to the Lead Center Director and the Associate Administrator for Space Flight, who requested that additional analysis be performed in alternative configurations. NASA is engaged in on-going discussions with the Russian Space Agency regarding the acquisition of additional Soyuz vehicles. Due to the current Russian economic problems, NASA closely monitors the status of the Soyuz production required to support the ISS at the manufacturer, Energia. NASA is engaged in on-going discussions of the procurement of additional goods and services from RSA. The procurement will provide the cash flow necessary to sustain the production levels of Soyuz vehicles that the ISS requires until the CRV is available. These discussions will continue in the overall context of determining Russia's ability to satisfy its commitment as an international partner. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1084 | Johnson, Suzanne - 0000000000 : NO@ADDRESS.GIVEN; Raynor, Eric - | Johnson, Suzanne - 0000000000 : NO@ADDRESS.GIVEN |  | Mishap Investigation Board Report Findings for the GSFC Building 24 Pressurized Steam Line Close Call of August 19, 1999 | The primary cause of this Central Power Plant (CPP) pressurized steam line incident was that no one took responsibility for coordinating all aspects of executing the outage. Recommendations included revising procedures, conducting an independent safety audit of the CPP, Developing as-built drawings for the CPP, and establishing “Locked And Tagged Out” processes and requirements. | The primary cause of the pressurized steam line incident was that no one took responsibility for coordinating all aspects of executing the outage. Each group involved in the outage focused on what they believed to be their role and did not concern themselves with what the other groups were doing. Consequently, issues that required a coordinated effort such as blowing down the de-energized lines or informing the contractor when it was safe to commence work were not adequately addressed. The MIB believes that if one person/organization had coordinated the entire job, the contractors would not have started jack-hammering before the steam line was de-energized. A second primary cause of this incident is that is that no procedures exist for shutting down the north High Pressure Steam (HPS) line in the CPP and no prior planning occurred. Workers had to trace the steam line the day of the outage to determine what valves to close. Their efforts were hindered by such contributing causes as unlabeled valves, no visual pressure indicators on the line, inadequate access to the valves and a leaking valve. This resulted in the line not being completely de-energized until after the contractors had completed their shift for the day. Corrective Action Plans from past mishap investigations must be implemented in a timely manner and the actions sustained over time. No clearly identified leader to coordinate all aspects of a task involving multiple organizations can result in a failure to communicate safety-critical information that could prevent a mishap. Such tasks should have a clearly identified leader who has the responsibility of coordinating all aspects of the job and communicating safety-critical information to all personnel involved in the task. Outdated or inaccurate facility drawings/documentation and poor labeling of a facility such as the CPP increases the difficulty of accomplishing tasks of all levels of complexity and therefore increases the likelihood of errors and mistakes that could result in a mishap. Accurate and up-to-date drawings/documentation and clear labeling of such facilities on the other hand, assist workers in understanding the detailed design and operations of the facilities and therefore minimize the likelihood or errors and mistakes. Division safety guidance documents should be reviewed periodically and updated to reflect changes in NASA/GSFC safety policies, organizational structure or evolved ways of doing business. | Revise the Code 220 S & HPP instructions on utility outages to: a) identify what organization is responsible for coordinating outages; b) schedule a pre-task meeting between all participants; c) each Code 227 section involved in the outage to provide a detailed description of their portion of the outage procedure and approval signature. Conduct an independent safety audit of the CPP. Clearly label all valves in CPP so they are distinguishable from safely accessible areas. Install additional pressure gauges that are easily accessible and readable. Develop detailed procedures that include specific valve identification for shutting down each side of the CPP and include in the Building 24 Boiler Plant O&M Manual. Revise the O&M Manual to include missing information and correct errors. Develop as-built drawings for the CPP and provide to CPP personnel for reference. Provide refresher training on use of LOTO for high pressure stream operations, with particular emphasis on situations where more than one organization is required to LOTO. Establish a process for regular CPP management audits of LOTO logbook against outage requests/steam line isolations/etc., to ensure LOTO policies are being adhered to. Establish a requirement for Construction/Project Manager to LOTO valves to protect contractors exposed to hazardous conditions (e.g., high pressure steam) on their project. | GSFC | 03/24/2000 | On August 19, 1999, contractors were removing concrete from around steam lines with a jackhammer. These steam lines should have been de-energized prior to commencement of the work but one line was found to still be pressurized with 100 psi steam. Background: The pressurized steam line incident occurred in and around Building 24, the Goddard Space Flight Center (GSFC) Central Power Plant (CPP), Steam Manhole (STW # 30 and an excavated hole outside of the north side of the CPP. A work request (#8002) was submitted in June 1998 to reroute the Condensate and High Pressure Drip (HPD) lines entering Building 24 at the north wall into the blow-down pit. The corrosive atmosphere in the pit was degrading the pipes so plans called for rerouting them above ground and bringing them through the wall above the pit. The plans developed to complete this task would include excavation of the site to expose the lines and the cutting and rerouting of the lines above ground. Detailed drawings and plans for this task were developed and in April 1999 the work commenced. After excavation of the site, it was discovered that the concrete kicker that held the pipes in place was much larger and closer to the wall than anticipated. This required a Field Change Request (#8002-1) to allow for jackhammer removal of the concrete kicker surrounding the condensate and HPD lines so that the necessary modifications could be made. The Project Manager (PM) for the re-routing project submitted a Utility Outage Request (UOR) to de-energize the condensate, the HPD and the adjoining High Pressure Steam (BPS) line prior to removal of the concrete. Note that the concrete kicker in question surrounded all three pipes. The contractors never intended to jackhammer the concrete around the HPS line but requested it to be de-energized as a precaution. The UOR submitted for de-energizing the condensate, HPD and BPS line requested the outage for 7:00 a.m. on August 19, 1999 through 3:30 p.m. August 20, 1999. Securing these three lines required actions on the part of the Mechanical Maintenance Shop (MMS) and the CPP. The back of the UOR is the Utility Outage Safe Clearance Plan (UOSCP). One section of the UOSCP is reserved for the organization with the action to fill out what procedure is necessary to complete the outage. This section for the subject UOSCP was filled out by the MMS supervisor and included a brief statement about what action was necessary by CPP personnel. A CPP representative did not fill out the CPP procedure portion of the form, despite a note from the MMS supervisor requesting the CPP supervisor to review the section and sign off. The correct method for de-energizing the BPS line consists of closing the appropriate valves in STMH #30 and closing valves #1 through #3. After all valves are closed, the line must be "blown down", that is, a pressure relief valve should be opened in the blow-down pit to allow the existing steam to escape. Contractor personnel involved in the excavation and pipe re-routing project were the Construction Manager (CM), the Project Manager (PM), and the excavators, jack-hammerers, and pipe fitters. Personnel that were responsible for de-energizing the steam lines being worked on were civil servants from the MMS and the CPP. The following incident description describes the sequence of events that happened August 19, 1999 as best as the Mishap Investigation Board (MIB) could reconstruct from witness testimony. Although many events were described by more than one witness as having occurred, the timeframes and order in which they occurred were often in conflict. The MIB felt that the descriptions of events were more accurate than the times associated with them by individuals' memories and therefore based this incident description on the most common version of events. On the morning of August 19, 1999, the contractor began preparations to commence jack-hammering the concrete kicker. Preparations included clearing debris from the excavated hole, setting up an air compressor to power the jackhammer and talking with CPP personnel about the UOR. The contractor's on-site supervisor and the CPP Maintenance Leader walked around inside the CPP identifying which valves needed to be shut off. Testimony is conflicting on whether or not they discussed the need to secure the HPS line at this time. Around the same time, MMS workers entered STMH #30 and closed, locked and tagged out (LOTO) the appropriate valves. After the valves were secured a MMS worker entered the CPP to inform them that the valves under MMS control were closed. While in STMH #30, MMS personnel discovered a leaking valve gasket on the line going from STMH #30 into building 4 that needed repair. This leaking valve gasket had no impact on the section of line being de-energized. MMS personnel then proceeded to STMH # 15 to secure valves so that the gasket could be repaired later in the day. This is a common procedure in the MMS known as a 'piggy-back' job, where the MMS takes advantage of an already existing UOR to complete some of their work. At some time on the morning of August 19, 1999, the CPP Maintenance Leader, an Operations Leader and a Boiler Operator began the task of closing valves. According to testimony, the Maintenance Leader was leading the task and instructing the Boiler Operator in which valves to close. The condensate and BPD lines were reportedly secured without incident. Due to the complexity of the main north header lines, the lack of "as built" CPP drawings, the lack of a procedure for securing the north side of the CPP and the lack of valve labels, closure of the BPS line required that the personnel involved trace the north header line down to identify the valves that needed to be closed. The first valve closed was Steam System Valve (SSV)-003. The second valve closed was SSV-0 17. While CPP personnel were in the process of closing the HPS valves, MMS personnel returned to STMH# 30 to replace the leaking valve gasket going into Bldg 4. They noticed the HPS line was still hot. It should have cooled off by this time if the line had been properly secured in the morning per the UOR. The MMS Shift Leader testified that they also noticed that the subcontractor was jack-hammering at this time. The MMS workers went to the CPP to investigate. This is believed to have occurred just before 1:00 p.m. In approximately the same time frame, the contractors also noticed that the BPS line seemed hot. They notified the CM, who came to the site to investigate. He also went into the CPP to investigate. Both the MMS workers and the CM confronted the CPP Maintenance Leader to find out why the HPS line had not been de-energized. When the MMS and CM confronted the CPP Maintenance Leader and he realized the BPS line was still pressurized, he directed the CPP workers to close the third valve, SSV-007. The MMS workers and Boiler Operator then entered the blow-down pit in the CPP and set up the blow-down to de-energize the HPS line. Once the blow-down was set, the MMS workers left. The CM also left the CPP and informed the contractor that the line was now secured. Later in the day, CPP personnel noticed that the blow-down was still going on after it should have been completed. The CPP Maintenance Leader consulted with the MMS Shift Leader and they concluded that it was likely that one or more of the valves previously closed was leaking through. They suspected valve SSV-0 17 since it had not been replaced during the recent renovations. As it was time for a shift change (approximately 3:00 p.m.), the Maintenance Leader requested that the second shift Operations Leader have one of his workers close the fourth valve, SSV-0 16. The MIB notes that SSV-0 16 is extremely difficult and hazardous to reach and that this fact may have influenced the CPP personnel's decision not to attempt to close it earlier. It is also documented in the Operations Leader's Log that the first shift Operations Leader asked the second shift Operations Leader to "chain lock the North Main Header Valve" (i.e., lock out the valve). The CPP LOTO log does not have an entry for any LOTO on valves for that day, August 19, 1999. This implies that the BPS line valves were not locked or tagged out at the time they were closed. Once these tasks were completed and the line was completely blown down, it could be considered de-energized and safe for the contractors to begin jack-hammering concrete. Follow on Events: The MMS Shift Leader realized that the sub-contractors jack-hammering in the vicinity of a pressurized HPS line was a hazardous event and therefore reported these events to his supervisor. The MMS supervisor reported them to the General Foreman, who is in charge of both the MMS and CPP operations. The General Foreman called a meeting the next day between MMS and CPP personnel involved so that they could determine exactly what happened and how to prevent it from happening in the future. The primary result of that meeting was the establishment of a new policy for future outages involving the MMS and CPP. The new policy calls for a face-to-face meeting between the workers executing the outage to work out what needs to be done and verify that it has been done. An action was given to write a Standard Operating Procedure (SOP) documenting that policy. Testimony conflicts as to who actually received that action. The MIB could find no evidence that it had been done. The Board notes that face-to-face meetings did in fact occur between MMS and CPP personnel during this outage; however, these meetings did not prevent the close call from occurring. Therefore, the proposed corrective actions generated by this meeting did not adequately address the cause (s) of the close call. The MMS Shift Leader also contacted the GSFC Safety and Environmental Branch and informed the Occupational Safety and Health (OSH) Manager of the incident. The OSA Manager requested that the MMS Shift Leader write down his recollections of the events. The MMS Shift Leader did this and handed it over to the OSH representative, expecting them to investigate the incident. Representatives from OSH testified that they decided at this point not to investigate but rather to wait for Code 220 to officially notify them of the close call via a NASA Mishap Report form (1627 form). They wanted to see if a new close call reporting initiative instituted by Code 220 would work. A Mishap Report form was not submitted by Code 220, the MMS or the CPP immediately following the incident so nothing was done for approximately 2 months. When Code 205.2 received word that this MIB was being formed to investigate this close call they assisted Code 227 in writing a Mishap Report form. This form does not accurately reflect the written witness statement previously provided to Code 205.2 nor do the corrective actions listed fully address the incident root causes. |  | N/A |  | Science | Public | Not Specified |  | 02/12/2002
1085 | Johnson, Suzanne - 0000000000 : NO@ADDRESS.GIVEN; Raynor, Eric - | Johnson, Suzanne - 0000000000 : NO@ADDRESS.GIVEN |  | Mishap Investigation Board Report Findings for the GSFC Building 3/13/14 Electrical Manhole Close Call of December 26, 1998 | An attendant left workers unattended in an electrical manhole, suggesting a lax attitude towards confined space guidelines. Improve training, audit, and onsite management of high voltage electrician employees. | The primary cause of the electrical manhole incident is an error in judgment made by the attendant that left the workers in the manhole unattended. The Mishap Investigation Board (MIB) identified two contributing causes. Testimony indicated that non-adherence to the Code 220 confined space guidelines was the norm in this organization at the time of this incident. This mode of operation was either condoned by or unknown to management. All workers involved in the incident had received some confined space training; however records indicated that it was not complete or recent. The attendant had not received training while a GSFC employee. The MIB believes that inadequate training contributed to the relaxed attitude of employees towards adherence to the confined space entry guidelines, which in turn contributed to the attendant's decision. A lax attitude towards safety has a cumulative effect: Lapses in OSHA-required training leads to non-adherence to important safety-related practices and to employees that do not have safety upper most in their minds. New employees get the impression that safety is not all that important. Lapses in adhering to safety requirements and/or enforcement of adhering to safety requirements leads to the perception that the rules are not based on a real need to prevent mishaps (i,.e., we never follow the rules and nothing bad happens). Eventually, these lapses will result in a mishap. | Require all new high voltage electrician employees receive Confined Space training at GSFC. Develop and implement Code. 227.1 policy that requires yearly refresher training for all employees that work in confined spaces. Establish a process for regular audits of Confined Space work sites to insure that workers are following the Code 220 Confined Space Entry Guidelines. Results of audits should be documented and briefed to Code 220 management on a regular basis. Develop and implement an official Code 227.1 policy to: a) have assigned task leaders for every job; b) require a 'tail-gate' meeting is held with all team members and the role of each member of the team is defined; c) the task leader be informed of any team member's departure from the work site. | GSFC | 03/24/2000 | On December 26, 1998, two employees were left working in an electrical manhole unattended in violation of confined space entry requirements. The Electrical Manhole incident occurred in and around Electrical Manhole #PM-70 (labeled as a Telephone Manhole) which is located on the south side of Building 13 at GSFC. All Personnel involved in this incident were civil servants from the Electrical Distribution Section (Code 227. 1). A call came in to the GSFC emergency console at approximately 5:30 a.m. on December 25, 1998 that there was a loss of power on feeder 7 in buildings 3/13/14. Electricians worked throughout that day and into the next to isolate and identify the problem. It was determined to be a fault on phase A feeder B-7 located in manhole PM-70. By the end of the 1' shift/beginning of the 2' shift on December 26, the four workers involved in the incident began working together to fix the problem. The four workers (two from the 1' shift and two from the 2' shift) arrived at PM-70 and began setting up to complete the task. The workers informally discussed the task prior to commencing work. One of the V shift workers assumed the lead although there was no 'official' task leader. Testimony is conflicting on whether or not proper confined space entry procedures were followed. Although there was some testimony that a gas/air check was completed prior to workers entering the manhole (MH), there is no documentation to support that assertion. The investigation did not reveal a confined space entry permit, a gas/air check log book entry or evidence that a work life station was established per the GSFC Facilities Maintenance Division (FMD) (Code 220) Policy and Operational Procedures for Confined Space Guidelines or OSHA Standard 1910.146 requirements (References C and D, respectively). The two 1' shift workers entered the manhole and commenced work (now referred to as the MH workers) and the two 2' shift workers remained above ground (now referred to as the AG workers). The MH was very small so the AG workers removed the ladder to give the MH workers more room. While the MH workers were working in the MH, one of the AG workers (now referred to as AG 1) left the area to do the east sub-station checks. The second AG worker (now referred to as AG 2) remained as safety monitor above the MH. No one informed the MH workers that AG I had left. The MH workers requested that AG 2 get them a specific tool. AG 2 informed the MH workers that the tool was not at the worksite and he would have to retrieve it from the shop (located in Building 24). The MH workers acknowledged that AG 2 would be leaving the site. Since they did not know AG I had left, they were unaware that AG 2 leaving left them in the MH unattended. AG 2 believed that retrieving the tool would only take a few minutes and that AG I would be returning shortly, probably before he returned. The MH workers discovered they were alone when they called for AG I and got no response. One MH worker stood on the shoulders of the other to peer out of the MH and saw AG I in his truck. The MH workers immediately proceeded to exit the MH and confront AG 1. The MH workers believed that AG I was in the truck to stay warm rather than monitoring the MH. At approximately the same time, AG 2 returned to the site and observed the MH workers were angry at having been left unattended in hole. Testimony does not indicate that the four workers cleared up what exactly had transpired at this time. Testimony indicates that the time the MH workers were left unattended was from 1 to 5 minutes. The workers continued to work on the task after this incident occurred (the job was not completed for several days). |  | N/A |  | Science | Public | Not Specified |  | 02/12/2002
1113 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Simplified Aid for EVA Rescue (SAFER) |  | The EVA project lacks sufficient operational assets to meet unplanned contingencies. There are no spare Extravehicular Mobility Units (EMU's). Only five U.S. Simplified Aid for EVA Rescue (SAFER) flight units will be available to meet a requirement to maintain three units on orbit. In addition, only four Russian SAFER units are planned. | To meet contingencies that are almost certain to arise, additional EMU's and SAFER units or their critical long lead components should be procured as soon as possible. | HQ | 02/01/1999 | Lack of Sufficient Operational Assets to Procure Necessary Safety Hardware | NASA concurs with the ASAP recommendation. With respect to the EMU, the inventory of life support system (LSS) hardware will be 14 (13 Class I and 1 Class II) by October 1999.Exceedences to our supply begin in 2000. In order to achieve a 90 percent probability of sufficiency, NASA must increase its inventory by two LSS's. NASA plans on addressing this issue within the Program Operating Plan (POP) 99. We plan to upgrade the current Class II LSS to Class I and upgrade the certification unit to Class II. This will increase our inventory to 15. NASA also plans to go forward with the recommendation to procure an additional LSS to achieve 16 LSS's. Additionally, the current space suit assembly (SSA) flight hardware models predict SSA demand beyond the current inventory of 15. The demand peaks at 23 for one month, but there are 15 months where it is at 18 through 2004. The current plan is to procure hardware to 18 through the POP 99.SS. A hardware shortages can be determined once crewmembers are selected. The lead times for SSA hardware are such that once shortages are determined, specific hardware shortages can be procured. The current training model for the EMU predicts demand not to exceed the procured inventory of 10; therefore, sufficient inventory exists for training. With respect to the USA SAFER, NASA concurs with the ASAP recommendation on obtaining critical long lead components. In fact, the majority of the long lead components have already been procured. These components are expected to support the USA SAFER flight units for their 7-year life. NASA can normally support the requirement to maintain three USA SAFER flight units on orbit with five flight units in service. The current rotation plan utilizes two of the flight units to accommodate rotation of back-to-back missions where the turn-around time is approximately 1 month. With one flight unit out of service, four USA SAFER flight units can be rotated to maintain three units on orbit for 92 percent of the flights per the International Space Station (ISS) assembly sequence dated February 22, 1999.The remaining 8 percent of the flights can also be supported with contingent coordination ahead of time to reduce the turnaround time from approximately 1.5 months to approximately 1 month. Another option was already planned to deal with the margin in the rotation of five USA SAFER flight units. In order to increase the USA SAFER logistics margin, an extension of the 1-year certification will be assessed based on flight performance. Being able to leave the units on orbit longer will allow the rotation rate to decrease sufficiently to eliminate any problems with having one unit out of service. Data will be collected for analysis immediately after the flight units are declared fully operational. At the present, additional USA SAFER flight units are not needed for the following reasons: The rotation of five flight units can fully support the flight requirement The rotation of four flight units can support the flight requirement for at least 92 percent of the current ISS assembly flights The turnaround time can be reduced for special cases The on-orbit certification is expected to be extended with additional flight data. However, in the event a USA SAFER flight unit is not available for any reason, the EVA crew is trained to use the two-fault tolerant tethering scheme to meet the safety requirement. This tethering scheme is fully certified and has been used successfully during several EVA's, including those on the recent STS-88 mission. Lastly, with respect to the Russian SAFER, NASA has revised its plan and will now produce five flight units, rather than four, in order to support the logistics model consistent with the USA SAFER plan. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1111 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Extravehicular Activity (EVA)/Pyrotechnic Initiators |  | Many deployable structures on the ISS and satellites on which astronauts must work during EVA's use pyrotechnic initiators. There is often no simple way for an EVA astronaut to know by visual inspection whether or not an initiator has fired when a structure has failed to deploy properly. | NASA should develop and require the use of pyrotechnic initiators that leave clear visual evidence that they have fired. These "fire-evident" initiators should be required for all applications that may be encountered by an EVA astronaut. | HQ | 02/01/1999 | Use of "Fire-Evident" Pyrotechnic Initiators | The NASA Standard Initiator (NSI) is required for use in all electrically initiated pyrotechnic systems whether the application may be encountered by an EVA astronaut or not. The NSI does not provide any means for external visual inspection of fired condition when it is installed in a mechanism. Currently, the only test being performed to verify that the initiator fired, without disassembly of the pyrotechnic mechanism, is to measure firing circuit resistance before and after firing. This function can be built into the firing unit. It is not foolproof however, since it cannot detect a smart short. To date this has not been a problem with the NSI since in nearly 100,000 units produced and certified there are no documented failures. That is why the NSI carries a reliability of 0.999 at a 90% confidence level. All failures to fire have been traced directly to the electrical wiring, connectors, firing unit or flight computer. Breaks in the electrical firing circuit can be identified by a pre-fire circuit resistance check. The desire of visual identification is further compounded by the physical location of the initiator. In many applications it is located internal to a mechanism and is not directly accessible or visible. For those applications where it is external to the mechanism it is still not visible since half the device is torqued into the mechanism and the other half is covered by the electrical connector. Stretching the device to make a portion of it visible would require a re-design and re-qualification of the initiator at an extremely high cost as well as making it larger and heavier in a size and weight conscious world. Two types of visual indicators have been considered for incorporation into the initiator. The first is a temperature sensitive tape that could be placed on the outside of the initiator body that would change colors due to temperature rise generated from firing the initiator. This is not considered practical. The temperature rise of the NSI body is small and further effected by heat sinking of the mechanism it is inserted into. The actual temperature rise that would result is lower than the temperature rise generated by direct solar radiation. It would be unknown whether the color change was due to the initiator firing or the sun. The tape would also not be visible due to coverage by the electrical connector without redesign of the initiator body. The second possibility of a visual indicator is a pop-up pin that would be pressure driven by the NSI firing. Incorporating the pin into the NSI would be both complex and expensive. The NSI is a hermetically sealed device, there is no way to incorporate a pop-out pin without violating the hermetic seal. The size of the NSI would have to be greatly expanded to accommodate the pin/piston, which would have to withstand pressures from 600 psia to as high as 25,000 psia. The pin/piston orientation would also affect the pressure output and function time of the initiator. One final consideration that is very significant is that there are over 1000 pyrotechnic devices and mechanisms that have been flight qualified and certified to function with the NSI. Those devices are in repeated use on numerous crewed and uncrewed programs. The intrusion of a new initiator would not only be a reduction in reliability but would require re-qualification of associated components at a tremendous cost. Currently, there are no plans to pursue recommendation #16. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1114 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Extravehicular Mobility Unit (EMU) Planar Hard Upper Torso (HUT) |  | The three available sizes of Extravehicular Mobility Unit (EMU) planar Hard Upper Torso (HUT) units will accommodate crewmembers from the 40th percentile female to the 95th percentile male. Assumptions were made regarding the ability of crewmembers to upsize or down-size to fit the three available HUT sizes and operate safely and effectively in them. | To validate the ability of crewmembers to actually use the various available HUT sizes, crewmembers in each of the several size combinations/configurations should be required to perform normal and emergency functions in training mockups to demonstrate that full capability is available to each. | HQ | 02/01/1999 | Validation of Extravehicular Mobility Unit (EMU) Planar Hard Upper Torso (HUT) Capability | NASA agrees with the ASAP recommendation, as it is part of our standard process. Crewmembers are sized in 1-G and suit fit is verified during Neutral Buoyancy Laboratory (NBL) and vacuum chamber testing. Nominal suit fit capability is verified in the NBL, while emergency procedures are demonstrated under vacuum conditions using flight hardware. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1112 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Workforce/Training |  | In the event that a primary crewmember is unable to fly on an assigned ISS mission, current plans call for substituting a crewmember from a backup crew. Backup crewmembers do not, however, train extensively with the primary crew. | If backup crewmembers are to be substituted individually to the primary crew, then those crews should conduct some meaningful degree of joint training. | HQ | 02/01/1999 | Joint Training for Backup ISS Crewmembers | NASA concurs with the recommendation. Clearly, crews that are going to be flying together need to spend time together on the ground. Our current training process includes numerous training sessions where the backup crew is in attendance with the prime crew. And while there are not specific simulator sessions with joint or mixed crews, more importantly, the Expedition 1 and 3 crews do spend quite a bit of time together (as do the Expedition 2 crew and their backups, Expedition 4). The current policy of the organization is that backup crews can be substituted for the prime crew right up until launch. However, the decision will be made on a case-by-case basis whether one person or the entire crew is changed out. Our current plan does make provision for the former to occur. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1117 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Prereathe Protocol |  | There is an initiative to modify the prebreathe protocol for EVA operations on the ISS. The target is a 2-hour prebreathe from any pressure with the same or better bends risk than the protocol currently used in Space Shuttle operations. | Prior to authorizing any reduction in prebreathe protocol for EVA on the ISS, NASA should conduct a study to ensure that there is no increase in the risk of bends associated with the special circumstances of the proposed new protocol. | HQ | 02/01/1999 | Modification of Prebreathe Protocol for Extravehicular Activity (EVA) Operations | NASA concurs with the ASAP recommendation, and believes that the recommended study efforts have already been initiated. In 1997, the EVA IPT initiated a Prebreathe Reduction Program (PRP) to address the risk of decompression sickness (DCS) associated with reduced prebreathe protocols. The PRP Team developed a detailed 2-year plan to: Develop and test an operationally implementable 2-hour prebreathe protocol Perform a detailed risk assessment of acceptable DCS risk to provide prospective accept/reject criteria so that there was a clear metric by which to judge the success or failure of the laboratory trials Develop improved methods for treating DCS on orbit Develop flight rules to document in advance the specific actions that would be taken to manage a DCS contingency should one occur. Items 2,3,and 4 from above form the NASA "DCS Risk Definition and Contingency Plan." Effort required by that plan has been completed and favorably reviewed by an external review committee chaired by Dr. C. J. Lambertsen. Accept/reject criteria developed from the above plan was used in an extensive, multi-phase laboratory-testing program of an operationally implementable 2-hour prebreathe protocol. This effort was initiated in November 1997 as a multi-center effort led and managed by NASA and involving three external laboratories (Duke University, the Canadian Defense and Civil Institute of Environmental Medicine, and the University of Texas Hermann Hospital).A review of the multi-phased laboratory-testing program results and the entire PRP project conducted by medical experts of the International Partners (the Multi-Lateral Medical Operations Panel subcommittee for EVA) resulted in a committee recommendation that the 2-hour protocol should be safe to implement for EVA's from the ISS. Furthermore, additional internal and external reviews of the laboratory data are planned for June 1999. Pending the recommendations of that review, NASA believes there to be no increase in the risk of bends associated with the special circumstances of the proposed new protocol, and the 2-hour protocol will be implemented for operations on ISS Flight 7A, which includes the first U.S. space walks from the ISS joint airlock. The PRP Team has also developed a 5-year operational research plan with the goals of providing a better understanding of the underlying science of DCS in microgravity and the possibility of further reductions in prebreathe without compromise to safety. This 5-year research program will include four external laboratories, including the Brooks Air Force Base Armstrong Laboratory and the onsite NASA JSC facilities. Finally, NASA is committed to continued investigative/research efforts to address any relevant data obtained from past, current, or future testing in order to assure no increase in the risk of bends associated with the special circumstances of current or proposed new protocol. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1115 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Research and Technology (R&T) Program |  | The EVA Research and Technology (R&T) program has been highly successful, and its products have led to the development of significant safety and operational improvements to EVA hardware and procedures. Current funding for advanced R&T for EVA is extremely limited. | Restore the EVA R&T program to a level that will permit further development of not only near-term safety and operability improvements but also long-term products. | HQ | 02/01/1999 | Limited Funding for Advanced Research and Technology (R&T) for Extravehicular Activity (EVA) | NASA recognizes the importance of the EVA R&T program. The EVA Project Office maintains the EVA technology roadmap, and, when appropriate, makes recommendations to the existing Programs when it is prudent to pursue R&T development (e.g., reduced prebreathe protocol). Also, NASA continues to provide R&T funding support, prioritized against requirements from NASA Headquarters on an annual basis. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1116 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Training |  | The safety implications of EVA training for U.S. and international partner astronauts in the Russian Hydrolab are not well understood. In particular, the implications of higher suit pressures and Russian bends protocols have not been thoroughly analyzed. | NASA should study the procedures used in the Russian Hydrolab to determine their safety and monitor all Hydrolab testing when U.S. astronauts are involved. | HQ | 02/01/1999 | Safety Implications of Extravehicular Activity (EVA) Training in the Russian Hydrolab | NASA concurs with the ASAP recommendation. The Gagarin Cosmonaut Training Center (GCTC) Hydrolab facility is an established cosmonaut training facility. The GCTC Hydrolab is a neutral buoyancy training facility. The facility is an above-ground, circular tank with a maximum depth of 12 meters; however, a false floor limits the maximum useable depth to 10 meters. The false floor can be raised above the water level for positioning mockups, walk-through training, or hardware repair and modification. The standards applied to the Hydrolab's design and operations are not NASA standards but instead the Russian equivalent. NASA safety and medical representatives have performed a safety assessment of the GCTC Hydrolab facility utilizing the NASA Safety Standard for Underwater Facility and Non Open Water Operations, NSS/WS 1740.10, and other JSC requirements as a guide for directing the safety evaluation of the Hydrolab. The assessment focused on the suit hardware and its interfaces, including the effects of suit pressure/physiological depth, facility systems that support training, and pool deck systems. The Hydrolab is an acceptable facility for conducting operations with NASA personnel and equipment with one caveat, NASA medical personnel have requested that the Russians demonstrate proficiency in the use of the hyperbaric chamber at the GCTC. This demonstration was planned to occur prior to April 30, 1999. Beyond the hyperbaric chamber proficiency demonstration, the condition of this training facility does not pose a direct or unreasonable risk to U.S. personnel or vital NASA equipment. NASA and GCTC have agreed to several procedural and hardware related enhancements that will be made to the Hydrolab facility to increase the overall safety. JSC safety and medical representatives will be available in the Hydrolab as part of the test team during all suited operations in the Hydrolab and will continue to monitor safety and take further action as required. For additional information, the complete agreement is documented in EVA Project Office memo XA-99-031, dated February 18, 1999, subject: Gagarin Cosmonaut Training Center (GCTC) Hydrolab Safety For U.S. Personnel. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1088 | Haro, Peter - 0000000000 : NO@ADDRESS.GIVEN; Raynor, Eric - | Haro, Peter - 0000000000 : NO@ADDRESS.GIVEN |  | ARC Table Saw Mishap Investigation Board Report of March 9, 1992 |  | Simple formal or informal refresher courses on the proper use of equipment at regular intervals may help to prevent this type of accident. Shop equipment is located throughout the entire ARC facility and is necessary for day-to-day activities. Some of that equipment is used infrequently. Operators that receive training or guidance on a regular basis will keep their skills up to par. The fact that the health unit doctor did not respond to this particular accident probably did not affect the outcome in any way. However, the perception that a doctor was available and did not respond should be addressed. Just the presence of a doctor in an emergency situation has a calming effect on injured parties and their coworkers. The health unit should respond to all medical emergencies while they are on call. Contractors need to work within the purview of their contracts. Organizational Directors should participate with civil servant contracting staff to accomplish this objective. Many areas throughout ARC are still not equipped with proper first aid equipment. Updated kits are available through ARC stores stock. Area supervisors should evaluate which kits would be the most appropriate and accordance with Code DQH to make them available. With those accidents that are major, it is imperative that the accident scene be preserved as soon after the accident as is practical. The investigators' task can be made easier and more effective if early preservation of evidence is included as part of the accident response preparations. Preserving the accident scene should include securing the area by roping off or barricading it, and limiting access to the investigation team(s). These steps will prevent people from scattering evidence or relocating equipment and materials. They will also help protect people from remaining hazards and prevent activation of equipment or systems that may lead to a second accident. Findings and Observations: The contractor does not have a Health and Safety Plan. According to witnesses, other than training prior to employment with the contractor, they were not aware of written procedures of any formal training program provided by the contractor on the actual operation of shop equipment. General safety training is provided by the contractor, however it is not combined with specific guidelines on how to operate the equipment safely. The saw blade was dull and set too high for the task. The wood blocks the contractor employee was cutting were three-fourths of an inch thick. Normal practice is to adjust the saw blade so that it clears the top of the stock by about one-eighth to one-fourth inch. Three witnesses stated that the saw blade was set at approximately three inches. A dull blade can reject the material being cut. Contractor personnel interviewed stated that there were sharp blades available. The safety guard on the saw was not used. The contractor employee stated he was not able to use the guard due to the size of the wood and the cut he was making. No "push stick" was used to guide the wood through the blade path. During the tour of the accident site no push sticks were observed in the shop area. The contractor employee stated that he could not use a push stick because he needed to keep the material against the fence to get a straight cut. This put his hand within three and one-half to four inches of the saw blade. In accordance with the contractor's Safety and Health Plan, they hold periodic safety meetings to discuss general safety issues and employee concerns. The injured employee is the Flight Simulator Support Group's shop safety coordinator. In addition, contractor shop personnel all have extensive first aid and CPR training. There is no scheduled maintenance for the table saw. No maintenance records of past service were available. It is unclear whether the saw was ever serviced; these were not determining factors in the cause of the accident. The accident occurred on Thursday, January 30, 1992. The Mishap Investigation Board toured the accident site on Friday, January 31, 1992. At that time the accident area had been cleaned and the job setup on the table saw had been dismantled. The accident scene had to be reassembled for the Board to better understand the circumstances of the accident. The contract task for the Flight Simulation Support Group supports mechanical, hydraulic and electronic maintenance, repair, fabrication and modification, simulator cab outfitting, simulator operation and mechanical systems design. Limited wood work also is done in support of the simulators. Quite apparently, however, the work being done by the injured employee was outside the scope of the contract. Witnesses stated that the injured employee was tasked with the majority of the wood work performed by contractor. There was a lack of quality first aid supplies in the shop area. When the contractor employees who initially responded to the accident attempted to get gauze or compresses from the shop's first aid kit, they did not find anything suitable. Fortunately, another person present had his DART medical emergency kit, which had the supplies needed. The ARC Health Unit Doctor or Nurse failed to respond to the injury scene. The presence of a Doctor or Nurse could have provided a calming effect to the situation in addition to professional assistance. However, the individual with DART training who responded provided outstanding support. There were a number of comments made by those on the scene stating that the ambulance took too long to arrive. Records of the communications between the ARC Duty Office, Security and the Moffett Field Fire Department show that the ambulance was called at 15:20 hours and it arrived at 15:32 hours, which is 12 minutes. In 1991, the overall average time for ambulance response at ARC was 13.8 minutes. | The contractor's Safety and Health Plan should be reviewed and revised to include a training/certification program for individuals on the safe operation of major (table saw, lathe, automatic punch/press, drill press, etc.) shop equipment. Periodic refresher courses should be considered as part of this plan. Specific written procedures should be developed for the proper and safe operation of major shop equipment. This should include both basic and critical recommendations. A table saw should never be used for cutting small pieces of wood if a push stick cannot be employed or if the stock being cut makes it necessary for the operator's hand to be within six inches of the saw blade. Insure that safety meetings are held on a regular monthly basis in accordance with the contractor's Health and Safety Plan. These meetings should involve a free flow of safety information between management and the workers. Management should provide support for all reasonable safety requests. This forum should also be used to conduct updates/reviews of good safety practices of the operation of different major equipment each time. All major shop equipment should be on a scheduled preventive maintenance program. The program should not only check for the condition of the equipment, but also evaluate and advise on the condition of the cutting tools and other peripheral items associated with the safe operation of the equipment. In the future, it is imperative that after a serious accident nothing at the accident scene be altered. Preserving the accident scene will allow the investigators the chance to review and study the actual conditions and allow photographs to be taken for the record. Regular meetings should be held between the Contracting Officer (CO), Contracting Officer's Technical Representative (COTR), Sub COTR and contractor to insure that work performed is within the scope of the contract. First aid supplies are available through the ARC Stores Stock Catalog. This information needs to be conveyed to the ARC Staff and supplies need to be distributed to the appropriate areas. During operating hours, the Ames Health Unit should respond to all 911 emergency calls of a medical nature. Even if their presence is not needed, it could have a calming/stabilizing effect at the accident scene. | ARC | 03/09/1992 | On Thursday, January 30, 1992, a NASA contractor employee was tasked by his supervisor with putting casters on a number of office chairs for the Flight Systems and Simulation Research Division Office. The contractor employee had already cut approximately three inches off each chair leg. Since it was not possible to mount the casters directly to the legs of the chair, he was cutting small blocks of oak wood to attach the casters. The blocks then could be attached to the legs of the chair. At approximately 15:15 hours, the contractor employee was cutting the small wooden blocks (approximately three-fourths by three and one-half by four inches) using a Government-owned Rockwell Delta ten-inch Unisaw (table saw), Model and Serial No.'s 34-450 and GE 7834 respectively, located in the shop area of N243. The employee was cutting approximately one-sixteenth of an inch off each block to custom fit to each leg. He had set the blade height to approximately three inches. As he was pushing the fourth, and final, block through the blade path with his right hand, the wood block was rejected by the saw blade. This reaction pushed his hand into the blade. The employee severed two fingers (ring finger and middle finger) and fractured the bone and severed the tendon of the index finger of his right hand. The two fingers were severed between the first and second knuckles. Three of the employee's co-workers responded; 911 was called at 15:20 hours and first aid was administered. One of the co-workers is a member of DART and he immediately took command of the situation. He administered first aid, stabilized the injured employee and gave directions to properly secure and package the severed fingers. The Moffett Field Fire Department was called at 151:21 hours; they responded within three to four minutes of the emergency call from the Ames Duty Office; the time was approximately 15:25 hours. First aid continued and oxygen was administered until an ambulance responded at 15:32 hours (approximately 12 minutes from the time 911 was called) to take the injured employee to the hospital for further treatment. The Emergency Room Physician was able to save the index finger, but advised him that due to the excessive skin and bone damage, his ring and middle fingers could not be reattached. The Emergency Room Physician commended the efforts made in preserving the severed fingers. The injured employee was released from the hospital that evening at approximately 19:30 hours. A review of the contract under which this person was working was conducted with the Contracting Officer and an inspection of the accident site and the table saw was performed. Three experts on use of wood saws were consulted and one equipment maintenance individual was utilized to evaluate the condition of the table saw. A review of the Center's accident response system was conducted, consisting of the Duty Office, the 911 system, the ARC Health Unit, the Moffett Field Fire Department and the Bay Area ambulance service. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 02/12/2002
1087 | Lehman, D - 0000000000 : NO@ADDRESS.GIVEN | Lehman, D - 0000000000 : NO@ADDRESS.GIVEN |  | Plan Timely Implementation of Backups In Case Breakthrough Technologies Fail to Meet Readiness Gates - 1998 | Although the Deep Space 1 mission exceeded its overall technology demonstration objectives, certain important technologies under development never achieved flight readiness. Develop a project implementation plan with preplanned alternatives that addresses technology readiness and risk mitigation. Cease development when technology readiness gates for critical technologies are not met and implement preplanned alternatives. Avoid a spacecraft architecture where one new technology relies on another in order to demonstrate them in-flight. | During formulation of technology demonstration missions, develop a project implementation plan with preplanned alternatives that addresses technology readiness and risk mitigation. Devise meaningful technology readiness gates and criteria to assess development progress. When gates are not met for critical technologies/subsystems, the project should cease development and implement preplanned alternatives. Avoid a spacecraft architecture where one new technology relies on another in order to demonstrate them in-flight. | See Lessons Learned | JPL | 12/06/2001 | The Deep Space 1 (DS1) mission included breakthrough technologies that were critical to mission success and had not been proven in space flight. Although DS1 exceeded its overall technology demonstration objectives, certain important technologies under development never achieved flight readiness. Specifically, the Three Dimensional Stack (3DS) flight computer was deferred to a subsequent mission, and the Remote Agent Flight Software was downgraded to an in-flight experiment. A set of technology readiness "gates" had been established for evaluating the flight readiness of the breakthrough technologies. However, these gates were poorly defined, and the Integrated Product Development Teams and the Program Office did not fully commit to them. Further, the development schedules for these advanced technologies were too short. Plans were in place for backups for some of these technologies (but not all) should their development prove unsuccessful. Certain technologies were coupled such that problems with one could hinder the successful development of another. In-flight demonstration of the autonomous onboard optical navigation system (AutoNav) was required for mission success, yet its use depended on the performance of the Miniature Integrated Camera/Spectrometer (MICAS). Both AutoNav and MICAS involved new technologies: there was no backup for MICAS in the event its development proved unsuccessful. MICAS performance problems during both development and flight significantly compromised the in-flight demonstration of AutoNav, forcing major software modifications. References: "Deep Space 1 Lessons Learned," JPL internal presentation, David H. Lehman, December 1, 2000. "Controlling Risk on Cost-Capped, Schedule-Driven, Technology Validation Projects", NASA Lessons Learned "Reference Lesson #1033" Additional Key Words: Autonomous Navigation, Flight Qualification, Management and Planning, Technology Plan, Technology Readiness Level | A JPL Corrective Action Notice may be assigned and practices modified as appropriate. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1086 | Johnson, Suzanne - 0000000000 : NO@ADDRESS.GIVEN; Raynor, Eric - | Johnson, Suzanne - 0000000000 : NO@ADDRESS.GIVEN |  | Lack of Close Call Reporting and Corrective Action Development at GSFC | The incidents described in Lessons Learned #1084 and #1085 suggest a lack of awareness of what constitutes a close call and the fact that close calls should be reported into the NASA Mishap Reporting System. The lesson recommendations include a number of steps to provide more specific safety guidance, including definition of what constitutes a “close call.” | The primary cause of the lack of close call reporting of these incidents was a lack of awareness of what constitutes a close call and the fact that close calls should be reported into the NASA Mishap Reporting System via the 1627 Form. Personnel involved in the pressurized steam line incident were unaware that the 1627 Form should have been submitted. The delayed submittal of this form was due to the pending appointment of the MIB. Personnel involved in the electrical manhole incident did not believe it was a close call. The MIB identified two significant contributing causes to these perceptions. The Code 220, Code 227 and NASA level guidance documents on close call/mishap reporting as well as the mishap Form 1627 itself focus on mishaps. Most of the guidance provided is mishap-specific such as attending to the injured and securing the scene, things that do not typically exist in close calls. While Code 220 and 227 guidance do require close call reporting, testimony indicated that it had become common practice to address close calls as an internal issue (in the branch/section in which they occurred) and not pass the information up the management chain or to the GSFC Safety and Environmental Branch. Corrective actions were developed for both of these close call incidents. However, in the pressurized steam line incident the corrective actions were not adequate to prevent recurrence since they did not address the root causes of the incident. Employees cannot follow policies they are not aware of or are not clear. Even though NASA policies do require the reporting of close calls into the NASA mishap reporting system, if that information is not passed on to all employees in an easily understood and visible manner it will not be followed. Resolution of close calls is best accomplished through close cooperation between the organization in which the close call occurred and the Center's safety organization. Each organization brings unique knowledge skills and abilities to the table that can be used to determine what went wrong and what can be done to prevent recurrence. If close calls are not investigated and addressed in a timely manner, the possible benefits derived from them (i.e., preventing mishaps caused by similar events) are lost. Lack of Knowledge of What Constitutes a Close Call: In both the Pressurized Steam Line and Electrical Manhole close calls, a general lack of knowledge of the definition of what constitutes a close call was evident. Witnesses testified in both cases that they did not consider the incidents close calls. In the Steam line case, the Mechanical Maintenance Shop (MMS) worker did consider it a close call and did report it to his supervisor (as required) and the Safety and Environmental Branch (Code 205.2). The MMS supervisor informed the General Foreman and he brought the MMS and CPP groups together to solve the issue. They were not aware that a close call should be reported on a NASA Mishap Reporting Form (1627 Form). The MMS workers expected Code 205.2 to investigate and assist in resolving the issue. Code 205.2 expected Code 220 to file the 1627 Form and take action to resolve the issue. When the 1627 Form was filled out 2 months later it appears to have been done without the information originally provided to Code 205.2 by the MMS worker. In the Electrical manhole incident, the supervisor did not consider the incident a close call and therefore did not consider taking any official action. Discussion of Close Call Reporting In Guidance Documents: The MIB reviewed the following documents to determine if they provided adequate instructions on how to handle close calls: A) Code 227 Safety Manual, Reference E; B) GSFC Facilities Management Division (Code 220) Safety and Health Program Plan (S&HPP), Reference F; C) NPD 862 1.1.G, NASA Mishap Reporting and Investigating Policy, Reference A; and D) NHB; 1700.1 (-VI-B), NASA Safety Policy and Requirements Document, Reference B. In general, the documents coverage of close calls is sparse. Close calls are identified as being one of the types of incidents covered, however, the majority of the guidance focuses heavily on aspects of mishaps that are not part of close calls (i.e., injuries, emergency situations). Discussion of close call reporting in the Code 227 Safety Manual is particularly unclear. A close call or near miss is not separately defined but is included as part of an incident definition. The steps to be taken by personnel involved in incidents and their supervisors focus on mishaps. This could lead readers to believe that close calls are not included in reporting policies. The Code 220 S&HPP's discussion of close calls is nearly identical to that included in NPD 8621.1G and NHB 1700.1 (VI-B). All of these documents specify that close calls are to be included in reporting policies and on the 1627 Form. Mishap Reporting Form: The NASA Mishap Report form (1627 Form) is also geared primarily towards mishaps. The only indication that the form is also used for reporting close calls is one box to be checked. The rest of the form is focused on reporting injuries and equipment damage, items not normally a part of close calls. The form design could mislead employees into believing that it is not for close calls, only mishaps. GSFC Close Call Hazard Reporting System: During the course of interviews the Board asked witnesses about their knowledge of the new GSFC Close Call Hazard Reporting System. Most witnesses were aware of the new system and felt it to be easier to use than the 1627 form for close call reporting. The MIB concurs with this assessment. Fear of Reprisals: Several Witnesses expressed an unwillingness to report close calls due to the fear of reprisals. Contractors were concerned with losing future contracts if they reported civil servants caused close calls. Even if contractors did it anonymously, they feared that it could still be ascertained who submitted the report. Note these 2 incidents the MIB investigated were submitted anonymously through the NSRS system but several witnesses were convinced they knew who the submitter was, and their guesses were different. Therefore, even anonymous submittals may have a negative impact on the submitter (or on those thought to be the submitter). Lack of Corrective Actions Development: The MIB found that corrective actions were developed in both incidents commensurate: with the supervisor's perception of the incident and its level of severity. In the pressurized steam line incident, the corrective actions listed on the mishap report form were not adequate to address the incident. The actions called for the development of a Standard Operating Procedure for face-to-face meetings between Mechanical Maintenance Shop (MMS) and Central Power Plant (CPP) personnel when outages involve both shops, the incorporation of that procedure into the branch safety manual and refresher training for all personnel in lock out/tag out procedures. Face-to-face meetings did occur the day of the incident and did not prevent it. While lock out/tag out was not done correctly during the incident, that fact did not contribute to the failure to inform the contractor that the lines were not secured or the failure to secure the lines in a timely manner. In addition, the MIB could find no evidence that the corrective actions had been completed. In the electrical manhole incident the corrective actions were appropriate. | MIB recommendations related to this issue include but are not limited to: Establish GSFC-level policy/procedure to implement NPD 8621.1G. Provide specific guidance addressing Code 205's responsibilities for investigation & documentation of mishap/close call investigations & conclusions. Develop a GSFC Close Call Hazard Reporting System Implementation Policy that includes: a detailed close call definition/explanation; an explanation of the types of incidents that should be reported, the type of corrective actions should be developed by the reporting organization, calls for notification of the nature of close calls and corrective actions to the reporting organization's management chain, and feedback on the results of Code 205's close call hazard reporting system to GSFC employees. Update the Code 227 Safety Manual to define close calls and near-misses separately from incidents and to list the steps to be taken in their reporting. Increase management involvement in Code 227 proactive investigation of close calls and development of appropriate corrective actions. | GSFC | 03/24/2000 | A NASA Mishap Investigation Board (MIB) was tasked with investigating the perceived lack of corrective actions and lack of close call reporting of two incidents into the NASA Mishap Reporting System: the GSFC Building 24 pressurized steam line close call of August 19, 1999, and the GSFC Building 3/13/14 electrical manhole close call of December 26, 1998. For more detailed information about these two close calls, please refer to separately published lessons learned findings for each close call incident in the NASA Lessons Learned Information System (LLIS). |  | N/A |  | Science | Public | Not Specified |  | 02/12/2002
1104 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Hardware-Software/Qualification Testing-Verification and Validation |  | Some hardware is being used in MEIT before it has completed qualification testing. Software is also often used before its verification and validation is complete. In both cases, modification to the hardware or software may be required before certification is completed, thereby potentially invalidating the results of the initial MEIT testing. | When it makes sense to deliver hardware or software to system-level testing such as MEIT before qualification/certification is complete, the effect of any qualification-induced changes must be carefully evaluated for implications for regression testing. Final testing should always be run with validated software and qualified hardware. | HQ | 02/01/1999 | Use of Hardware Before Qualification Testing and the Use of Software Before Verification and Validation | NASA concurs with the recommendation and notes that the ISS Program requires regression evaluation for all modifications performed on flight hardware to assess whether certification, acceptance, or integration testing results are invalidated and must be performed again. The final flight configuration will be verified by regression testing as well as acceptance, mission sequence, end-to-end, and integration tests. The Space Station and Shuttle Payloads Office at KSC (Code NN) utilizes Flight, Flight Equivalent and GSE hardware and software for MEIT that has been certified through ISS Program Office control boards and panels for these tests. The boards and panels also specify regression tests with flight units when required through the directives they provide. The NN MEIT test schedules currently have regression tests planned for modified or repaired hardware units and revised software per ISS Program Office control board and panel directives and requirements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1106 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Hardware-Software/Integration Testing |  | Astronaut crew participation in testing improves fidelity of the test and better familiarizes the crew with systems and procedures. | NASA should continue to involve the crew in integration testing and do so more heavily and at an earlier stage. | HQ | 02/01/1999 | Crew Involvement in Integration Testing | NASA concurs with the recommendation. The Flight Crew Operations Directorate (FCOD) at JSC is making every effort to ensure that astronauts are actively involved in hardware and software testing of Space Station components at all phases of their development. FCOD heartily concurs that this involvement needs to continue at an early stage and with a high level of participation. This involvement is accomplished through the technical assignments that are filled by astronauts who are not assigned to a specific mission and by the assigned flight crews responsible for the assembly of the hardware on orbit. Traditionally, flight crews are assigned about 1 year ahead of time for a shuttle mission. In the case of Space Station assembly missions, an attempt has been made to assign crews at least a year and a half ahead of time so that they are actively involved in the development of the on orbit procedures and the test and checkout of the hardware. Early involvement ensures that crews are able to make engineering inputs based on operational experience to correct problems before they result in time consuming and difficult on orbit workarounds. All test activities are tracked by the Vehicle Integration Test Team (VITT) within FCOD. To accomplish this, personnel are assigned the responsibility to monitor the hardware at the various sites where it is being built, including overseas sites, as well as at the Kennedy Space Center. These personnel provide the astronauts with the current status of the hardware, coordinate crew visits to the sites and ensure that astronauts are participants in all critical tests. Additionally, the increment crews that will actually be living on the station after it is constructed have been made active participants in the test and checkout of the hardware while it is still on the ground. FCOD will continue to ensure that this crew involvement continues and is not just limited to Space Station assembly missions but also encompasses Orbiter upgrades, the Crew Return Vehicle, payloads, and any future program that requires astronaut participation. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1105 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Hardware/Multi-Element Integration Testing (MEIT) |  | MEIT is the highest level of integrated testing available before committing ISS elements to launch. In order to produce valid results, this testing requires a high level of fidelity in emulators/simulators used in place of missing components. | The ISS Program should ensure that high-fidelity simulations of on-orbit components are used in the MEIT and that the configurations of those simulators are validated to be in agreement with what has actually been orbited. | HQ | 02/01/1999 | Use of High-Fidelity Simulations of On-Orbit Components in MEIT | NASA concurs with the recommendation. The node emulator for MEIT I was built as certified GSE as was the Lab Emulator for MEIT II and III. Emulator design requirements include the emulated flight article's ICDs to the elements under test in MEIT. Activation/Validation and integrated testing confirms emulators meet the emulated flight article's interface requirements and compares emulator performance with the flight article's performance in similar testing. The primary objective of these tests is to certify the emulators act like the flight article for the interfaces under test. The emulators are under configuration management (CM) control and any updates to the flight elements will be checked for potential impacts to the emulators. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1103 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Training |  | The use of simulated Space Shuttle launch and flight operations for training and rehearsal has proven to be an effective technique for enhancing safety and efficiency and is especially valuable in the case of special or rarely performed procedures or after a long hiatus of effort. | Simulation-based training should be included in difficult or infrequent Space Shuttle operations whenever feasible. This type of training is especially needed after there has been a significant hiatus in performing an operation. | HQ | 02/01/1999 | Enhanced Safety and Efficiency Due to Simulated Space Shuttle Launches and Flight Operations | NASA concurs with the recommendation. NASA and Shuttle Processing Contract (SPC) have beneficially increased simulation-based training at KSC. The pursuit of a separate simulation training room and simulation team will allow NASA and SPC to further increase the number of simulations that can be performed each flow. Additionally, KSC will use the new collaborative engineering environment to enhance simulation capabilities. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1089 | Ploszaj, Ronald - 0000000000 : NO@ADDRESS.GIVEN; Raynor, Eric - | Ploszaj, Ronald - 0000000000 : NO@ADDRESS.GIVEN |  | TOPEX/POSEIDON Spacecraft Handling Anomaly Special Review Board Final Report of May 29, 1992 | Support equipment was damaged during a lift because the fixture assembly used for lifting the spacecraft into the thermal vacuum chamber was unstable in the TOPEX/POSEIDON configuration. The lesson provides 7 recommendations involving the need for stability analysis, formal mechanical GSE design reviews, peer review of lifting fixture design, high fidelity dry runs, and involvement of host center personnel. | Root Cause of Problem: The T/V Fixture Assembly used for lifting the spacecraft into the thermal vacuum chamber was unstable in the TOPEX/POSEIDON configuration. Contributing Factors: A stability analysis of the total lifted assembly that was used in the T/V lift was not performed. The lifting fixture guidelines contained in JPL900-501, Ground Handling Equipment Design Notebook were not adequately applied. A GSE Review which would have included a review of the T/V handling fixture assembly, was repeatedly postponed, and not held prior to its use for lifting the spacecraft into the T/V chamber. Additional Observations: The overall review process, at all levels (peer review to formal review) failed to identify the lifting fixture deficiency. No precursor run through (dry run) of the T/V lifting exercise, using either the actual or a high fidelity simulation of the lifted assembly, was run prior to the lift with the flight spacecraft. There was a low fidelity dry run with the TOPEX/POSEIDON handling fixture, but it was performed without a spacecraft mass simulation and at different locations and orientations than the flight spacecraft handling. (The stated purpose for the dry run was to check the SHSS and thermal shroud interfaces and clearances to the T/V chamber, not to dry run the actual spacecraft lift.) Just prior to the final crane move, the T/V Fixture Assembly was lifted by the crane and a "rocking test" was performed on the assembly by the test team to assess its stability. The T/V Fixture Assembly appeared to be stable at that time because the lifting clevis friction was not exceeded during the rocking test. Lessons Learned: GSE Review - Ground support handling equipment should always be reviewed/approved by experienced designers and handling personnel prior to handling operations. Review material - Released drawings, analysis, and procedures for handling equipment should be available for review at least 60 days before a test to permit adequate evaluation. Lifting Equipment Stability Analysis - No lifting equipment should ever be used without a complete stability analysis of the equipment with the load in its complete configuration. Precursor Handling Experience - On protoflight spacecraft, the only precursor handling experience is with a dry run and mass mockups. The mass mockups handling dynamics, geometries, and sequences used for the dry run should simulate the protoflight spacecraft. Analysis and procedural checks are not always adequate to ensure surprises won't occur. Project overview of contract - Project support from the cognizant JPL (or other NASA Center) divisions should ensure, for the area of overview of their organization, that the contractor is adhering to all applicable requirements. All contractual documents (such as JPL 900-501) relating to potentially hazardous operations should be clearly identified and should receive special attention. Dedicated Briefing - A detailed and dedicated briefing structured to review the wording, text, diagrams, etc. is also a mandatory part of any functional demonstration. This briefing serves to inform the personnel who may not have had the opportunity to read or review the written material or see the diagrams, etc. More importantly it is an opportunity for anyone who does not understand his assignment to have a clarification. If there are any reservations with regard to the technical approach of the upcoming activity this forum is the place to discuss them. Functional Demonstration - A functional demonstration of all critical lifts, handling or maneuvers should be performed just prior to any event involving flight hardware. It may be judged too costly or redundant to a detailed procedure, but the value of such an exercise is particularly worthwhile if a high value item such as a one of a kind spacecraft is involved. The actual demonstration (dry run), will reveal discrepancies in the written procedure. When the procedure lacks detail, the demonstration affords the opportunity to try out, or practice, different variations to the step-by-step approach. The unwritten or unspoken, yet implied instruction must be practiced and executed by the actual personnel involved. Where coordinated actions are required the exercise will help assure that everyone has the same response and timing to obtain the same end result. An exact physical and mass mock up would be an ideal item to use for the demonstration, but it is rarely a possibility because of resource or other limitations. The importance of the duplication of the center of gravity with a mass mock up is self evident. The interface points or pickup points of the load can usually be replicated or borrowed from the flight article. However, in no case should they be overloaded or mispositioned from the designated lifting pattern. All shackles, rings, slings, chains, and everything in the load line should be assembled from a sketch or a pictorial equivalent in the procedure which identifies each item as to capacity, size or other details. All parts should carry a dated tag stating the level of proof load sustained, and witnessed by the appropriate project official. Loadlines should not be torn down after a proof or demonstration load test to the levels and conditions stated in the procedure. If a partial tear down is required, the exact reassembly must be assured. This is particularly important with multiple joint assemblies using what appears to be identical hardware, but may have different loadings. Clevis pins must never be mixed from assembly to assembly. One final note on the load line drawings. It has been shown on numerous occasions that the facility does not fit the load line or vice versa even though everyone's opinion was to the contrary. It is prudent to include key dimensions on the load line sketch for later use. Tilt Angle Requirements - Although it did not contribute to the TOPEX overturning incident, the yielding of the spreader bar at a tilt angle of only 8 degrees to 10 degrees raises an important point. Historically, there has been no design requirement for lifting equipment to tolerate a specified tilt angle. Lifting equipment requirements should be revised so the usual safety factors must be met at a specified, tilt angle. Host Center Review of Hazardous Procedures - Host center personnel should perform a review of all hazardous procedures/operations planned by outside user organizations. In addition, development of requirements for advance notification of the host center safety organization of the expected date and time of the actual performance of each hazardous operation should be considered. Video Recording of Hazardous Operations - All hazardous operations should be video recorded. The video recording of the overturning anomaly and the preceding and following activities was extremely helpful in the investigation and evaluation of this incident. Since mishaps may also occur during normal operations, consideration should be given to video recording all operations involving unique high value equipment. Use of inexpensive, off-the-shelf video cameras and recorders would permit very economical routine video recording of all activities The TOPEX/POSEIDON overturning incident had the potential for being classified as a NASA Type A Mishap. Only a series of uncontrolled, but fortunate occurrences prevented this from initially being a much more serious anomaly with severe consequences. Major damage to both the spacecraft and the T/V chamber were avoided only because the T/V Fixture Assembly was lifted higher than necessary to clear the lip of the chamber. This was done in the erroneous belief that the higher lift (shorter crane to assembly distance) would improve stability by reducing swaying of the load. If the lift had been at the same height as the dry run, the T/V Fixture Assembly might have struck the chamber lip during the rollover resulting in major damage to both the Spacecraft and the chamber. The H-Frame spreader bar was severely damaged, and probably would have failed completely if one of the suspension cables had not snagged on one of the upper SHSS clevis lugs. Complete failure of the spreader bar would have dropped the 8000 pound load approximately equal to 40 feet to the floor of the T/V chamber, destroying both the Spacecraft and the chamber. The Spacecraft fortuitously rolled with the -X side down, where a significant amount of GSE structure was mounted. If the Spacecraft had rotated with the +X side down (or if it had fully inverted) placing it on the floor of the T/V chamber to relieve the loads on the H-Frame spreader bar might not have been possible without significant additional damage to the spacecraft. Following the anomaly only the quick and professional response of the test team and contractor personnel prevented further (and potentially severe) damage to the Spacecraft and chamber facility. | FINDINGS AND RECOMMENDATIONS Root Cause of Problem.- The T/V Fixture Assembly used for lifting the spacecraft into the T/V chamber was unstable in the TOPEX/POSEIDON configuration. Contributing Causes Lack of Stability Analysis - A stability analysis of the total T/V Fixture Assembly (T/V Lift Fixture, Cables, SHSS, Satellite, supporting thermal shrouds, and instrumentation) was not performed, reviewed, or approved prior to the overturning incident. Recommendation: A Stability analysis must be performed on all lifting devices in all lift configurations and must be repeated with each new application assigned. A stability factor of 1.5 or greater should be analytically demonstrated to cover possible differences between analysis and the actual lifted assembly. The stability analysis should be treated as a formal mandatory item in the same manner that stress analysis is addressed. Inadequate Stability Testing - Stability testing was done during the proof loading tests of the lifting fixture, and again with the complete T/V Fixture Assembly. Because the impact of clevis friction was not taken into account, neither of these tests revealed the underlying instability. The two "rocking" tests were not analyzed for their adequacy in determining fixture instability. Recommendation: Detailed review of all elements of planned testing must be done to assure the testing will accomplish the goals of the test. Stability analysis of lifted assemblies should be done whether or not stability testing is planned. This analysis is essential to determine the need for and the adequacy of any stability testing. Continued Postponement of GSE Review - A GSE Review which would have included a review of the T/V Fixture Assembly was repeatedly Postponed, and not held prior to use of the Assembly for lifting the spacecraft into the T/V chamber. (In preparation for thermal vacuum testing an Environmental Test Readiness Review was held November 20-21, 1991. There was one page that addressed the entire mechanical GSE in the review documentation. This page was simply a listing of the mechanical GSE and its status.) A supplemental handout available at the November 20, 1991, Environmental Test Readiness Review (ETRR) included an assembly drawing of the lift configuration, but the drawing reproduction did not clearly show the cable attach points. A viewgraph of the lift configuration drawing was not shown at the ETRR. However, it was shown at the previous Monthly Status Review (MSR). Recommendation: Formal mechanical GSE design reviews must be held to assure adequate design evaluation of the proposed lifting configurations. Discussions must include a detailed review of the proposed drawings and procedures for specific attach points, stability analyses, direction of motion, and expected accelerations for all moves. Lack of Designer Experience and Peer Reviews - The Principal Engineer was not familiar with stability analysis of lifting fixtures for loads lifted below the C.G. and did not follow the lifting fixture guidelines contained in JPL900-501, Ground Handling Equipment Design Notebook. Furthermore, no peer review, internal contractor review, or project review of the total T/V Fixture Assembly occurred. The review process failed. Recommendation: Accepted guidelines should be followed in the design of all lifting fixtures. This is especially true when the designer has not designed a lifting fixture before and is unfamiliar with the shortfalls of various lifting fixture configurations. In all cases, a review of the design and margins should be held with peers and supervision to assure the design meets all requirements. A checklist which includes all aspects of the design e.g., stability, loads analysis, proof loading, etc. should be developed. GSE Project reviews should be held and attended by personnel who are capable of assessing the adequacy of the design being reviewed. Lack of Functional Demonstration - A functional demonstration (dry run) of the chamber lift activities was not performed prior to the incident. However, a lift of the T/V Fixture Assembly (without the spacecraft) was done earlier for a form fit of the SHSS and thermal shrouds. There were significant, differences in C.G., fixture alignment, and personnel assignments between this lift and the actual spacecraft lift. Recommendation: A high fidelity dry run, using the lifting fixture with the proper mass and C.G. simulator and following the procedures that will be used for the actual lift should be conducted. A formal briefing before the dry run and debriefing after the dry run of the personnel involved should be made for all high value one of a kind spacecraft and equipment. On protoflight spacecraft, the only precursor handling experience is with a dry run and mass mockups. The mass mockups handling dynamics, geometries, and sequences used for the dry run should simulate the protoflight spacecraft. Analysis and procedural checks are not always adequate to ensure surprises won't occur. Lack of Host Center Review of Hazardous Operations Procedures - The host center (GSFC) did not review the hazardous procedures/operations planned by the outside user organizations. Also the GSFC did not require advance notification of the Center Code 205 or 302 safety organizations of the expected date and time of the actual performance of each hazardous operation. Recommendation: Host center personnel should be required to review all hazardous procedures/operations planned by outside user organization. Host center personnel are much more familiar with the characteristics (and quirks, if any) of their equipment and facilities. Also, they are more likely than the visiting organization to be highly experienced in the type of operations involved. A requirement for formal Host Center "Buy-Off" (signature of concurrence) would help ensure proper visibility and attention to hazardous procedures/operations. In addition, the development of requirements for advance notification of the host center safety organization of the expected date and time of the actual performance of each hazardous operation should be considered. Advance notification would allow the safety organization the option of monitoring or witnessing selected hazardous activities and ensuring that all internal and external safety requirements are being satisfied. Remaining Spacecraft Handling Operations: At this time the T/V spacecraft handling equipment has been redesigned, tested, analyzed, reviewed and used to move the spacecraft back into the T/V Chamber. Recommendation: The TOPEX Project must examine and approve the stability analysis for all remaining handling configurations, including those at the launch site. A GSE review should be conducted for all remaining handling operations as soon as possible. | GSFC | 05/29/1992 | On Sunday March 8, 1992 the TOPEX/POSEIDON Spacecraft was being prepared for thermal vacuum (T/V) testing by a test team in Building 10 of the Goddard Space Flight Center (GSFC). As part of the procedure, the T/V Fixture Assembly consisting of the spacecraft, thermal test shrouding and instrumentation mounted on the Spacecraft Horizontal Support Structure (SHSS), suspended by four vertical cables from an H-frame spreader bar was lifted and positioned above the T/V chamber. At approximately 11:25 a.m., during final north / south crane positioning maneuvers, the suspended assembly began a slow overturning rotation. The assembly rotated approximately 135 degrees from horizontal before being halted by the entanglement of one of the four suspension cables with the SHSS. After some bouncing and jostling, it came to rest at approximately 115 degrees. While resting in this anomalous position (+X end up), the Test Team visually determined that the H frame spreader bar assembly had sustained considerable damage during the rotation and might fail. A decision was made by the Spacecraft Manager to remove the vertical load from the overstressed and damaged H frame spreader assembly as quickly as possible by lowering the spacecraft and test fixture to the chamber floor. Within ten minutes of the overturning incident the Test Team, augmented by personnel from a GSFC contractor, lowered the rotated assembly to the chamber floor where it was temporarily secured. During the subsequent visual inspection of the secured assembly it was noted that sections of the thermal test shroud and support fixturing had partially yielded. However, no apparent damage to the spacecraft or to the lower frame of the SHSS could be seen. An on site "failure review board" of civil servant and contractor personnel was convened to review and discuss the situation. A decision was made by the board that the Spacecraft/SHSS assembly should be removed and reoriented to a horizontal position outside of the chamber to minimize any further yielding of the supporting structures. A rigging crew was on the scene at this time, and was given the go ahead by the board to proceed with the removal of the Spacecraft/SHSS assembly from the chamber. The damaged H-frame spreader bar and the four suspension cables were removed. A pair of nylon slings were attached from the +X end of the SHSS to the crane hook and the Spacecraft/Thermal Shroud/SHSS assembly was raised vertically out of the T/V chamber and moved directly adjacent to it. The assembly remained there suspended a few inches above the floor while the team attached additional slings from the -X end of the SHSS to a forklift positioned on the -Z side of the load. By alternating operations of the crane and the forklift, the spacecraft and fixture were reoriented horizontally and lowered to the floor. At approximately 6:51 p.m. the operation was completed with the Spacecraft/SHSS assembly safely on the floor in the normal attitude. A video recording of both the anomaly and the recovery operation was made and is available from the TOPEX Project office for viewing. |  | N/A |  | Science | Public | Not Specified |  | 02/12/2002
1090 | Duke, Joseph - 0000000000 : NO@ADDRESS.GIVEN; Raynor, Eric - | Duke, Joseph - 0000000000 : NO@ADDRESS.GIVEN |  | Pegasus/SCD 1 Launch Anomaly Review Committee Final Report of March 1993 | An apparent momentary dropout of the Command Destruct Receiver initiated an abort during the launch of a Pegasus vehicle. The lesson offers 10 recommendations (dealing mostly with mission rules, launch constraints, and communications) to prevent similar incidents in the future and improve overall range operations. | The Review Committee concluded that the primary cause for this incident was that the Range Safety abort was rescinded without on net authority and range awareness. The principal contributing factors to this incident were the off net communications; and confusion that resulted from having two separate operational nets, the lack of sufficiently detailed and attended prelaunch briefings, and the lengthy process of communicating with the B-52. The Review Committee during its investigation has compiled a list of findings and conclusions. They have been grouped in the following categories: Abort Process Mission Rules Communications Launch Day Roles and Responsibilities Mission Planning and Preparation ABORT PROCESS FINDINGS An abort was initiated by the WFF/RSO, the abort was rescinded by the contractor TC without on net authority and range awareness. The B-52 was required to reduce altitude just prior to the CDR dropout abort call. WFF, Eastern Range (ER), Merritt Island Tracking Station (MILA) and Bermuda Tracking Station (BDA) responded in a manner which allowed continued flight of the Pegasus after launch There was no procedure in the WFF/OSD or the Contractor Launch Checklist (LC) that detailed the procedure for rescinding an abort. CONCLUSIONS From the above findings, the Committee reached the following conclusions: The contractor TC method of rescinding the abort was inadequate. Fin battery actuation was a consideration in the decision to rescind the abort. The altitude problem may have contributed to the confusion concerning the abort. Capability to destruct the Pegasus was maintained throughout the flight. Quick positive reaction by all supporting personnel allowed this flight to continue to a successful conclusion. MISSION RULES FINDINGS An apparent dropout of a Flight Termination System (FTS) CDR occurred. This apparent dropout required an abort of the launch according to the mission rules. Not all key personnel were aware of all mission rules. Additionally, in some cases, key personnel had different interpretations of mission rules. CONCLUSIONS There were misunderstandings among key personnel concerning the mission rules. Lack of awareness and misinterpretation of mission rules may have contributed to this incident. The FTS CDR dropout mission rule produced a high risk of mission abort. The complex routing of the data stream (vehicle/aircraft to ground, ground to Time Division Multiple Access (TDMA) satellite, satellite to ground) and the amount of support equipment necessary to provide this data (decoms, bit syncs, cabling) produced a high probability of data loss not related to CDR health. COMMUNICATIONS FINDINGS No single Intercom Channel (IC) was understood by all key participants as the primary launch net. The WFF/RSO chain of communication to the B-52 required 3 intermediaries. The configuration of communication equipment used by NASA 1 and the contractor TC was operationally awkward. Formal intercom net protocol was not consistently used. CONCLUSIONS The lack of a single IC for all critical calls that was monitored by all key personnel contributed to confusion and to the range's lack of knowledge of impending launch. The chain of communication between the WFF/RSO and the B-52 contained too many elements. Improved intercom net discipline may have prevented misunderstandings leading to the unplanned launch. The contractor TC had expected to receive Range abort calls from the WFF/RCO on IC 4. The fact that the abort was only transmitted on IC 1 by the WFF/TD and heard off net by the contractor TC caused the contractor TC to question the abort call and delayed the passing of the abort to the B-52. LAUNCH DAY ROLES AND RESPONSIBILITIES FINDINGS There were no clear lines of authority and responsibility for launch decisions. The OSC/TC rescinded the abort command without proper on net authority and range awareness. CONCLUSIONS The primary cause of this incident was that the OSC/TC rescinded the abort without on net authority and range awareness. The lack of clear lines of authority and responsibility contributed to his/her actions. The limited abort scenarios exercised during the dress rehearsal were not sufficient to identify all authority and responsibility conflicts. MISSION PLANNING AND PREPARATION FINDINGS No pre-launch briefing was held at which all key participants reviewed mission rules, constraints, and procedures. The WFF/Operations and Safety Directive (OSD) and the Contractor's Launch Operations and Mission Constraints (LOMC) document contained conflicting information that was not completely integrated in the mission planning process. A complete dress rehearsal was not conducted for this mission. CONCLUSIONS The pre-mission planning and preparation process was inadequate for a mission of the scope and complexity of the Pegasus / SCD-1 launch. Conflicting Information in the various organizations' documentation may have contributed to this incident. The lack of a pre-mission briefing attended by all organizations that reviewed roles, responsibilities, mission rules/constraints, IC assignments, and the launch decision process contributed to this incident. | Based on the findings and conclusions, the Committee identified the following recommendations which should prevent similar incidents in the future and improve overall range operations: Management for both the Range User and the Range should ensure that the roles and responsibilities of critical decision making personnel are clearly defined and understood. The Range User and the Range should establish, document, and fully coordinate all mission rules and launch constraints. A final pre-mission briefing should be conducted as near the intended launch date as possible (1 to 2 days before launch). All key participants should be represented at this briefing. This briefing should include but not be limited to: a. Roles and responsibilities of all key participants and the launch decision process b. Mission rules and launch constraints c. Operational procedures including standard abort/hold terminology d. Communication channels assignments and protocol A direct link should be provided (either voice or electronic) from the WFF RSO/TD to the flight crew that enables the WFF RSO/TD to hold the launch in the latter stages of the count should an abort/hold condition arise. The terminal countdown should be conducted on a single communications net. All critical mission status calls should be made on this net. The FTS CDR mission rule should be reviewed. All inflight non-reversible countdown items such as battery activation should be preceded by a "go for" command. Video from carrier and/or chase aircraft is a highly desirable source of information and should be provided for all future missions. Prior to launch, various scenarios should be conducted that exercise abort calls from the various mission support elements. A dress rehearsal which exercises as many assets as possible should be conducted prior to each launch. There should be a recovery day between dress rehearsal and launch. | GSFC | 03/05/1993 | During the launch of the Pegasus/SCD 1 on February 9, 1993, an incident occurred in the final minute of the countdown where an abort was initiated by the Wallops Flight Facility (WFF) Range Safety Officer (RSO); however, the operation continued with the launch of the Pegasus vehicle. At T minus 0:59, the WFF/RSO initiated an abort due to an apparent momentary dropout of the Command Destruct Receiver (CDR). The abort call was picked up by the WFF Test Director (TD), who immediately enunciated the abort, at T minus 0:56 and T minus 0:47. The countdown clock was stopped at T minus 0:52 seconds and was not restarted until Pegasus release at T minus 0:00. A contractor Test Conductor (TC) announced the abort at T minus 0:44, and the abort was passed by NASA 1 to the B-52 at approximately T minus 0:34. The B-52 crew replied that the fin batteries were on and that they understood the abort. Following this discussion, the contractor TC rescinded the abort call, and NASA 1 passed the negative on the abort to the B-52 at T minus 0:22. The Pegasus vehicle was then dropped from the B-52 near T minus 0:00 time. Key WFF personnel in the Range Control Center (RCC) were not expecting the drop due to the abort call. However, the drop was observed on video, the alert was sounded that Pegasus had been launched, and all supporting personnel and stations responded immediately. Their timely response allowed the successful completion of this mission. At no time during the flight was the ability to destruct the Pegasus jeopardized. |  | N/A |  |  | Public | Not Specified |  | 02/12/2002
1091 | Parrish, Kevin - 0000000000 : NO@ADDRESS.GIVEN; Montague, Ronald - | Parrish, Kevin - 0000000000 : NO@ADDRESS.GIVEN |  | Synchronizing Customer Requirements with Service Provisions |  | The requirements of the test requestor must be fully consistent with the resulting test procedure developed by the service provider though a two-way collaboration / discipline | Include a walkthrough, dry run, or mental simulation of the TP prior to start of test and have the TP&RD a part of that review. The TP&RD and TP must be very carefully reviewed for complete integration by several groups test, quality/safety and engineering. Have qualified technicians follow the procedure as written. The procedures should go through a dry run with the test technicians. | JSC | 07/15/1999 | During pre-operations for the 5A US Lab Closed Hatch Environmental Control & Life Support System/Thermal Control System (ECLSS/TCS) testing, a water separator fault occurred in the Common Cabin Air Assembly (CCAA). The inlet ORU was pulled and found to be wet inside. Three to four ounces of water were noted on the rack floor under the separator/heat exchanger. A small amount of water was found inside the separator but not enough to touch electronics. Water was also found in other areas (hydroflow fitting and coupler of the inlet hose and the inside of the inlet). Root cause: The Test Procedure (TP) and Test Preparaton and Restoration Document (TP&RD) were not synchronized. The TP&RD placed a valve in series between the water separator and the GSE collection tank. The TP&RD also, appropriately, had the valve closed to keep water in the line after it was filled and before water separator was started. The TP did not open the valve before initaiation of water separator operations. The TP&RD & TP WERE NOT carefully reviewed for complete integration. | Test safety requirements at JSC use a two-way review system for this type of test. The customer requesting a test will provide a test plan to be reviewed by the service provider. Once the test provider understands the test plan and objectives, the provider will write a test procedure that is reviewed by test participants and the test requestor. Theory behind this approach is that both the requestor and reviewer will arrive at a consensus on the test that will minimize any escapes such as occurred in the described event. Dry runs are also done where warranted. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1092 | Salute, Joan - 0000000000 : NO@ADDRESS.GIVEN; Mendoza, NO_FIRST - | Salute, Joan - 0000000000 : NO@ADDRESS.GIVEN |  | Project management processes for addressing off-track performance |  | People, especially those not familiar with each other, may not be comfortable about discussing work performance issues and asking for help. To overcome these communication barriers, Projects should have a process for reporting when assigned tasks will not meet their requirements. This process should be a requirement on all Project personnel so that management can address concerns prior to them becoming problems. | In addition to developing and implementing work processes for standard organizational performance, establish a process for reporting when assigned tasks will not meet their requirements and their corresponding corrective actions. This process should include trigger points (such as percent off schedule or spending) that require project personnel to seek management attention. Having this process in place throughout the project lifecycle will overcome the barriers people may have about asking for help and off-plan performance can be corrected appropriately. | ARC | 01/01/2002 | Several design drawings were delivered late because the responsible engineer (RE) did not have the appropriate level of experience to complete the work and did not ask for help. In addition to not asking for help or communicating any other concerns about the drawings, the RE assumed they could recover the slip in schedule by their own efforts and relayed this to the Project Manager (PM). Therefore, the PM who was addressing known issues did not see sufficient evidence to become involved. Eventually, the PM could not rely on the RE's assurances and decided to enlist the help of drawing experts to complete the drawings. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1095 | Tryon, Roy - 0000000000 : NO@ADDRESS.GIVEN | Tryon, Roy - 0000000000 : NO@ADDRESS.GIVEN |  | Construction Site Safety: Coordination of Requirements, Power Compatibility, Design Review, Submittal Review |  | The design Project Manager must coordinate mechanical equipment with electrical power service. The mechanical designer should not rely on very precise and specific brand name catalog order numbers when specifying long-lead, high cost equipment. When using more generic descriptions the designer should include an actually specification of the available power supply. This mistake could have been caught and corrected during the submittal review process. Catching it there would have saved the additional contract cost or time. Submittal reviewers need to do more than just compare similar catalog numbers. They should also double check on all utility service connection requirements for major equipment. | In the course of the submittal review process ensure that construction reviews substantiate both mechanical equipment with electrical power service requirements for major equipment during the design phase. Key point for better construction reviews is to focus on electrical and other utility service requirements for major equipment items. Provide careful submittal reviews during construction. Make sure that the reviewer understands what every one of those specific model code numbers and letters means. Avoid specific brand/model # specifications without also adding more generic and descriptive requirements to tell the contractor/supplier exactly what is needed. | AFRC | 08/27/2001 | The Center has an existing campus complex of modular buildings fed by a main distribution panel (MDP) with 120-208 volt/3 phase power output. A recent project added 3 more buildings to the complex, each having its own 120-208 volt/3 phase power panel. The mechanical engineer specified HVAC units by specific brand name and numeric catalog number, "or approved equal". Embedded in that catalog number was a letter code that denoted the specific voltage for the HVAC equipment motors. In this case it denoted 480 volt power. The electrical drawings and specifications (provided by NASA) showed 120-208 volt power supply. Therefore, the mechanical subcontractor furnished and installed exactly what NASA specified and approved during product submittals. It was only when the HVAC equipment was actually installed in the field, and the electrical subcontractor tried to connect up the 208 volt circuit feeder that anyone realized that there was insufficient voltage to power the specified 480 volt HVAC motors. NASA had several options: (1) Remove the 480 volt equipment and replace them with new 208 volt equipment. (2) Run new 480 volt circuits back to the campus main switchgear. (3) Install new additional step-up transformers for each of the 3 HVAC units. Due to constructability, cost and schedule impacts, option #3 was selected. | Enter this problem/mistake into the NASA Lessons Learned Data Base. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 02/12/2002
1093 | Salute, Joan - 0000000000 : NO@ADDRESS.GIVEN; Mendoza, NO_FIRST - | Salute, Joan - 0000000000 : NO@ADDRESS.GIVEN |  | Manufacturing one-of-a-kind or cutting edge technology |  | The risk involved between using in-house hardware manufacturing shops and commercial vendors should be weighed carefully. For several reasons including attrition and Center priorities, In-house capabilities may lack the experience and resources to meet Project requirements. However, their proximity and familiarity with NASA missions may overcome this. On the other hand, while a commercial vendor may appear to have both the experience and resources to meet Project requirements, they actually may have less capability than their NASA in-house counterparts to devote to the Project due to their non-Project commitments. | When developing NASA unique and/or one-shot hardware for launches and missions, strongly consider using in-house shops and processing instead of commercial manufacturers who may give priority to their repeat high volume customers and thereby increase the risk to NASA's interest. In cases where a commercial manufacturer is used, monitor the work during the process closely to ensure it remains on schedule, meets specifications for materials, environmental stresses, and tolerances. | ARC | 01/01/2002 | The Project chose a commercial vendor to build a unique piece of hardware for a one-shot NASA launch mission. In addition to its contract with NASA, this vendor had several repeat high volume customers. Therefore, as commitments to other customers taxed the vendor's resources, the vendor demoted NASA's requirements to a lower priority and were not able to meet schedule or cost. An alternate vendor had to be brought in to help in the recovery and the Project was forced to accept additional risk in the flight hardware. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1094 | Salute, Joan - 0000000000 : NO@ADDRESS.GIVEN; Mendoza, NO_FIRST - | Salute, Joan - 0000000000 : NO@ADDRESS.GIVEN |  | Partnering with outside agencies or entities |  | While other Government Agencies may have specific operating requirements and environments, not all may be applicable to your project. Unless the Project has a thorough understanding of how these other entities operate, it may expend more resources than necessary to complete agreements and meet requirements. | Enlist, use, recruit, or call in part-time advisors with expertise in working with particular agencies. Get other Agency commitments in writing, and monitor commitment fulfillment closely. | ARC | 01/01/2002 | The Project had several Government partners and each had a their own rules of engagement with regard to agreements and sharing of responsibilities. While some of these differences were cultural, many were driven by higher-level requirements such as treaties and other international agreements. The Project's unfamiliarity with these differences lead to difficult negotiations and un-necessary uncertainty in several of the Project's data requirements. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1096 | Sun, Ron - 0000000000 : NO@ADDRESS.GIVEN | Sun, Ron - 0000000000 : NO@ADDRESS.GIVEN |  | Construction Site Safety/Handling Pressurized Pipes/Compressed Air Line |  | Do not work on a pressurized pipeline. Reduce pipeline pressure before attempting to locate leak in the pipeline. Personal protective equipment (PPE) does save lives. The accident could have caused more serious injury had the worker not been wearing PPE. Pay extra attention to construction safety procedures during the last working day before a weekend or holiday. Construction workers tend to rush the last working before a weekend or holiday. Preparatory inspection is very important. Make sure specified materials are being used. Silver solder was specified for the 3" copper underground compressed air line. The Contractor used 95-5 solder instead. Silver solder grarantees a much higher strength of the joint. | Do not allow contractors or other workers to work on a pipeline while conducting high pressure test. Reduce pipeline pressure to 40 PSI to 60 PSI to locate a leak. Use silver solder on 2" and larger copper pipes. Strictly enforce the three phases of control in construction: preparatory inspection, initial inspection, and follow-on inspection. Have a safety meeting with the construction crew a day or two before a long weekend or holiday. | AFRC | 08/28/1997 | On 8/28/97, the last working day before Labor Day weekend, a Contractor's was installing a 3" copper underground compressed air line into a trench approximately 18" wide and 3 feet deep. After having completed about 100 feet of pipe, the Contractor's crew began a pressure test of the 3" pipeline for acceptance. The test was performed prior to installation of a secondary fiberglass pipe to cover the 3" copper pipe and backfill the trench. The specified working pressure of the 3" copper compressed air line was 125 PSI. The specified test pressure was 188 PSI. While the 3" copper line was still under pressure test, the crew began to install the secondary fiberglass pipe to encase the 3" copper primary pipe. As the crew was lowering the pipe into the trench, approximately 2:45 PM, the crew heard the sound of a "pop" and then the sound of leaking air coming from a pipe joint coupling. While the 3" copper line was still under pressure, one worker went into the trench attempting to check the location and the extent of the leak. While the worker was checking the position and direction of the leak from the pipe coupling, the soldered joint failed and the pipeline de-pressurized explosively. An 84-foot section of the pipeline that lead from the bottom of the trench to ground level was propelled approximately 8 to 9 feet longitudinally along the edge of the trench. Air from the explosive depressurization blew sand and soil on the worker in the trench. The sand abraded the worker's arms, chest, and abdominal. The pipe also struck the worker in the left knee and groin area. The worker was taken to the Edwards AFB Hospital for treatment. The worker was released from the hospital after treatment that evening. The worker was wearing personal protective equipment (PPE) including a hardhat, boots, safety glasses, and gloves at the time of the accident. |  | N/A |  |  | Public | Not Specified |  | 02/12/2002
1102 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Aircraft Operations/NASA Aircraft |  | NASA aircraft used for both Space Shuttle operations and astronaut training are increasingly out of date and, in several respects, may be approaching the unsafe. This is noticeably so in the case of the Shuttle Training Aircraft (STA) and T-38 aircraft. | Continue to execute and accelerate as much as possible the current plans for the modernization and safety assessment of astronaut training aircraft. | HQ | 02/01/1999 | Aging NASA Training Aircraft | NASA believes that the current aircraft used as astronaut training aircraft are maintained in a safe condition. NASA remains committed to safe operation of all the training aircraft. Measures to ensure that the NASA T-38's and STA's used for astronaut training are maintained in a safe configuration and in good material and structural condition are in place. A summary of current efforts is as follows: T-38: NASA's approach to maintaining and modernizing the T-38's is two-fold. The first approach consists of maintaining and upgrading the fleet in consonance with the USAF programs. (The USAF Air Training Command plans to use the T-38 for flight training to 2020 and beyond.) This includes engine component upgrades, replacement of structural members, including entire wings, and comprehensive nondestructive inspections at prescribed intervals. Additionally, a 1995 NASA contracted limited damage tolerance assessment study confirmed that the aircraft structures can be maintained with standard inspection criteria at intervals. The second approach encompasses NASA unique programs that are tailored to the specific use of the NASA T-38's for the astronauts' space flight readiness training. NASA unique programs include: An Avionics Upgrade Program which modernized the communications and navigation systems, replaced high failure rate and outdated avionics, and added a weather radar, a flight management system, an altitude alerter, and modern controls and displays. This program has been completed on the T-38 operational fleet and has resulted in a redesignation of the USAF T-38A to the NASA T-38N. Intended follow-on avionics enhancements, as they become practical and economically acceptable for the T-38N, includes modification to a Global Positioning Satellite (GPS)-based flight management system and the incorporation of the terminal collision avoidance system. Modified engine inlets to increase the takeoff performance and the margin of safety of the aircraft over the standard configuration. A successful flight test program on the prototype aircraft has been completed, and the T-38 corrosion control and structural modification team at El Paso, Texas, has completed the first pilot production aircraft. Replacing the T-38 ejection seats with state-of-the-art seats that will meet the full range of astronaut anthropometrics and are highly reliable, zero-altitude/zero-air-speed capable. A just completed flight test of an engine ejector modification designed to improve the in-flight range of the T-38. This modification should enhance both efficiency and flight safety. NASA will continue to evaluate new programs and seek new initiatives to meet the requirements as they evolve, such as adding avionics for compatibility with the future free flight concept in the air traffic control system. STA: NASA has four STA's and one spare Gulfstream II (GII) that will be modified into an STA when it is either required by the Shuttle flight rate or in the event that one of the four STA's becomes unusable. In regards to STA maintenance, the initial aircraft maintenance and inspection program developed by the aircraft manufacturer, Grumman, in concert with NASA engineers included a short interval comprehensive nondestructive inspection program. That maintenance program was designed to ensure close monitoring of the structural health and material condition of the STA, which was and is operated in a much more demanding flight regime than the corporate GII aircraft. Furthermore, a 1993 and 1994 NASA contracted effort with Science Applications International Corporation resulted in the determination that the STA fleet can operate safely within the established flight training profiles and that structural integrity can be monitored through the ongoing inspection program. Modernization of the aircraft includes recent avionics systems upgrades with an incorporated differential GPS approach guidance system and the modification of the Shuttle simulation system to include the orbiter MEDS to provide astronaut pilot orbiter landing training for MEDS-equipped orbiters. Based on the basic STA GII remaining service life and the NASA maintenance program, there should be ample service life remaining on the four aircraft to provide astronaut training well into the second decade of the 21st century. However, repair and component costs due to systems obsolescence or frequency of structural repairs could conceivably indicate a need for either systems redesigns or an earlier selection of a replacement aircraft type. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1101 | Dutton, Jeff - 0000000000 : NO@ADDRESS.GIVEN; Montague, Ronald - | Dutton, Jeff - 0000000000 : NO@ADDRESS.GIVEN |  | Hardware losses during STS-88 Extravehicular Activities (EVAs, also known as space walks) |  | Careful planning from design through training, flight rules, and operations is required to prevent loss of equipment and tooling during space walk operations. | Slidewire carrier - implement an operational constraint to require that items in Tool stanchion and other similar bayonets also be tethered. OIWIF/retractable tether - reemphasize crew training to visually verify hook mate/demate on mini workstation. Trunnion pin cover - update trainer to include tether loop. Tether hook clips - Include integral ring/spring to allow clip to be attached back to itself. | JSC | 01/01/2001 | Several items of EVA hardware were lost during the EVAs on STS-88. Impact to immediate mission is loss of availability of needed tools. Lost tooling, when unretrieved, also adds to on orbit debris. The flight support equipment (FSE) for the EVA installable slidewire and an on-orbit installed worksite interface (OIWIF) with an attached retractable tether were lost on EVA1. One of the trunnion pin covers was lost on EVA2. Two of the safety tether hook guards were also lost during the EVAs. There is no identified common hardware cause for the lost hardware. The EVA Project Office chartered a team to investigate the issue and make recommendations for corrective action. Root cause: Slidewire Carrier - inconclusive, most probable cause is inadvertent opening of Tool Stanchion bayonet. On orbit installed WIF/retractable tether - inconclusive, most probable cause was the hardware was tethered to another end item and was released when that end item was removed from the mini workstation. Trunnion pin cover - was not properly tethered due to a lack of a tether loop on the mockup/trainer. Tether hook clips - inadequate restraint in design. | All the recommendations were implemented for 2A.1 with no recurrence of loss. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1100 | Dover, Alan - 0000000000 : NO@ADDRESS.GIVEN; Montague, Ronald - | Dover, Alan - 0000000000 : NO@ADDRESS.GIVEN |  | Selection and Monitoring Supplier Quality |  | Procured space craft components must have their quality assured regardless of flight criticality | Procurement of flight hardware (including source selection) must be based more on risk and supplier historical data as opposed to criticality of the hardware. Sufficient source inspection requirements and resources must be developed and implemented. The process for developing supplier Statements of Work (SOWs) must be sufficiently detailed and incorporate upper level requirements to a level of detail to ensure the required level of performance, reliability and quality. | JSC | 09/24/1998 | The High Powered Amplifiers for the Early Communications Projects (ECOMM) provided by a prime contractor's supplier failed to meet performance and quality requirements (defective soldering workmanship) resulting in schedule impacts. Root cause: The procurement process for Criticality 3 (non-critical) hardware, by JSC contractors, has in some cases not received the same quality assurance rigors as the procurement process involving critical hardware. The quality assurance activities to be performed at source by, the prime contractor, should be predicated on risk and proven ability of a subcontractor to supply conforming items. In this case the decision to forego source activities was based solely on the criticality of the hardware and did not take into consideration the complexity of the hardware and lack of subcontractor historical data. Deficiencies were noted in the following areas for this particular procurement: Inadequate supplier selection process. A site survey was not performed to verify subcontractor capabilities. Inadequate contract monitoring of supplier performance and progress. Source inspection was not performed by the prime. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1120 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Simplified Aid for EVA Rescue (SAFER) |  | The NASA Standard Initiator (NSI) on a SAFER unit tested on STS-86 on October 1, 1997, did not activate because of a marginal design of the activating power supply. As a result, the unit could not function. The certification testing for the firing circuit did not identify the power supply inadequacy. Also, an inadequate NSI emulator was used for most of the original SAFER certification (qualification) and acceptance tests (see also Finding #14). | 25a. The design and implementation of flight systems critical to safety and mission success should, at least, provide redundancy for system startup. 25b. All NASA Centers should review the design requirements for reliable activation of the NSI and assure they are adequate to be communicated to their suppliers, especially those who are responsible for the design of firing circuits. All designs currently using NSI's should be reviewed to assure that the firing circuits are adequate and have been appropriately tested. 25c. Qualification tests of safety-critical equipment must use flight-quality hardware. Any exceptions must require high-level program approval. | HQ | 02/01/1999 | Redundancy of Safety-Critical Flight Systems | 25a. NASA concurs with the ASAP finding that the NSI drive circuit of the USA SAFER was marginal in its design to the point where the drive circuit failed to activate the NSI during a demonstration on STS-86. The failure was due to lack of margin within the subsystem to drive the NSI and not due to lack of redundancy (a backup subsystem) to the subsystem. Adding redundancy (a backup subsystem) to drive the NSI would not resolve the lack of margin as both the primary and backup subsystems would still fail to drive the NSI without sufficient margin. This condition was addressed by addition of a new NSI circuit with increased margin to fire the NSI on demand. In addition the new NSI contains redundant components where possible. The USA SAFER is categorized as emergency hardware and is designed for use only after the EVA crewmember had inadvertently separated from structure due to a tether failure or a tether disconnection. The combination of the tether and USA SAFER provide a functional redundancy to each other and a fail-operational system, which can sustain one failure in the tether (functional after one failure) and still retains the capability to continue with the EVA. A subsequent failure of the tether (two failures) and a functional USA SAFER provide a fail-safe system, which still retains the capability to successfully terminate the mission by using the USA SAFER to bring the inadvertently-separated EVA crewmember back to safety. Once the USA SAFER is needed to perform self-rescue in its role as the fail-safe device, its failure to perform due to any reason would result in loss of the EVA crewmember. Because the USA SAFER is to provide the fail-safe capability, as the functional redundancy to the tether, it was designed as a single-string system. As such, redundancy was not required for all subsystems and components. Adding redundancy to the activation subsystem alone would not increase the probability of saving an inadvertently separated crewmember since other critical subsystems (propulsion and mechanism) are still single-string. NASA will evaluate redesigning the next generation SAFER to be fully redundant in critical functions. 25b. NASA agrees with the ASAP recommendation. The new USA SAFER NSI circuit employs the capacitive discharge approach which has been well proven by the SSP. Peer reviews were held to evaluate the new circuit design, and a series of tests were performed with the complete flight circuit. Also, the Engineering Directorate's Pyrotechnic Subsystem Manager performed a comprehensive review of all known uses of the NSI to ensure an acceptable design existed and that appropriate certification/acceptance tests had been accomplished. Lastly, a User's Guide (JSC-28596) for the NSI was developed to assist developers in selecting the appropriate NSI, designing the appropriate NSI drive circuit, and testing the complete NSI subsystem. 25c. NASA concurs with ASAP recommendation to use flight-quality hardware to support qualification testing. The new USA SAFER circuit certification was completed with the successful firing of 15 flight NSI's consecutively. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1118 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/Radiation Exposure |  | The greatest potential for overexposure of the crew to ionizing radiation exists during EVA operations. Furthermore, the magnitude of any overexposure cannot be predicted using current models. | NASA should determine the most effective method of increasing EMU shielding without adversely affecting operability and then implement that shielding for the EMU's. | HQ | 02/01/1999 | Increasing Extravehicular Mobility Unit (EMU) Shielding to Reduce Crew Radiation Exposure | NASA concurs with the ASAP recommendation. Efforts are in work to both minimize radiation exposure and to obtain data relative to increased EMU shielding. Efforts to minimize EVA doses include coordination to minimize the South Atlantic anomaly passes between the Space Radiation Analysis Group, Medical Operations, EVA Office, and Flight Director. Monitoring of EVA doses on ISS will include the use of crew dosimeters and the external vehicle charge particle detector systems (EVCPDS). Developing active dosimeters to be worn inside the EMU that would augment the EVCPDS as a warning system and improve the monitoring of crew doses is being considered. A proposal to deploy an external tissue equivalent proportional counter prior to EVCPDS deployment on ISS Increment 8A that would provide improved EVA dose enhancement warning capability is being developed. JSC in collaboration with the Lawrence Berkeley National Laboratory is assessing ways to measure the shielding capacity of the EMU and the Russian Orlan suit using proton and electron exposure facilities at Loma Linda University. These measurements would support a study of the effectiveness of increasing EMU shielding. In addition, the development of an electron belt enhancement model and improved solar particle event forecasting and Earth geomagnetic field models that would provide large improvements in predictive capabilities for the occurrence of enhanced EVA doses is being considered. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1119 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Extravehicular Activity (EVA)/EMU-Orlan Suit |  | EVA ground rule 4.3.2.12, "No Simultaneous EMU/Orlan ISS Extravehicular Activity," is constraining and reduces flexibility. | NASA should reexamine this ground rule and consider a criterion for selecting either an EMU or the Orlan suit for a particular EVA based on the specific requirements of the EVA or the specific crewmembers performing the EVA. | HQ | 02/01/1999 | Extravehicular Mobility Unit (EMU) and Orlan Suit Criterion | NASA concurs with the intent of ASAP recommendation. Current mission planning requires one-fault tolerance for both EVA hardware and personnel. Additionally, all EVA crewmembers (a minimum of three will be onboard the vehicle) will be trained to operate in both the U.S. EMU and Russian Orlan. Therefore, for example, a crewmember planning to perform an EVA in the EMU would have the following fault tolerance capability: 1) primary EMU; 2) backup EMU; then 3) Orlan. Fault tolerance alone precludes the need to plan for a simultaneous EMU/Orlan EVA; however, the primary rationale for not planning for this is the safety risks associated with two different suit procedures/parameters during a single EVA. Primary spacesuit monitoring responsibility will reside with the country responsible for the development of the hardware (i.e., Russians will have primary responsibility for the Orlan and Americans for the EMU).Therefore, if both the Orlan and EMU were in use during a single EVA, a shared responsibility for monitoring spacesuit performance exists. If an emergency occurs, there are increased safety risks that result from the shared responsibilities. Based on the increased safety risks and given the fault tolerance capability defined above, NASA does not believe it is prudent to plan for the option to use both the EMU and Orlan simultaneously. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1122 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Aero-Space Technology/X-34 In-Flight Separation from L-1011 Carrier |  | The X-34 technology demonstrator program faces safety risks related to the vehicle's separation from the L-1011 carrier aircraft and to the validation of flight software. Moreover, safety functions seem to be distributed among the numerous contractors, subcontractors, and NASA without a clear definition of roles and responsibilities. | NASA should review and assure that adequate attention is focused on the potentially dangerous flight separation maneuver, the thorough and proper validation of flight software, and the pinpointing and integration of safety responsibilities in the X-34 program. | HQ | 02/01/1999 | Validation of Flight Software for X-34 and L-1011 Carrier Aircraft Flight Separation | Wind tunnel separation tests simulating the separation of the X-34 from the L-1011 have been successfully completed, using scale wind tunnel models of the X-34 and L-1011. The X-34 release mechanism is based on the flight-proven Pegasus release mechanism designed by Orbital Sciences Corporation. The A-1 vehicle will be flown in captive carry mode under the L-1011; additionally, the A-2 vehicle will be flown in dress rehearsal attached to the L-1011.The aerodynamic forces and flying qualities of the combined vehicles will be assessed during these flights. The flight software will be carried through a thorough Verification and Validation testing process by Orbital Sciences Corporation. Performance tests of the X-34 navigation system (hardware and flight software) have already been conducted at the White Sands Missile Range using an aircraft platform. Subjecting the flight software to IV and V remains an option to the program if concerns about the software dictate. In May 1998, Code Q conducted a detailed review of safety and mission assurance processes being used by the X-34 program, and found the existing processes in place at Orbital Sciences Corporation and its subs to be satisfactory. Recommendations from the review have been addressed, and are available for review. A follow-up review with Code Q and the X-34 Project Office was held on December 10, 1998. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 02/12/2002
1123 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Aero-Space Technology/X-Vehicle Range Safety/Authority |  | Because X-33 and X-34 flight range safety is the responsibility of another agency, NASA may have a tendency to pay less attention to that aspect of the programs. | Because X-33 and X-34 flight range safety is the responsibility of another agency, NASA may have a tendency to pay less attention to that aspect of the programs. | HQ | 02/01/1999 | Lack of NASA Range Safety Authority for X-33 and X-34 Programs | The X-33 flight test profiles have met the long established requirements for flight safety for all military Ranges. Additionally, the flight test program has undergone scrutiny from all potentially impacted organizations, both private and government, through the public process for an Environment Impact Statement (EIS). All overflight routes, trajectories, and landing sites were included in the EIS analyses. The X-33 filed its Record of Decision on November 4, 1997. Public law and Department of Defense regulations place Range safety responsibility in the hands of the Range Commander not NASA. The NASA X-33 Program Office is satisfying every Air Force Range requirement and risk analysis. NASA, as the user, is supporting the Range and is applying expertise from both Dryden Flight Research Center and Marshall Space Flight Center in every topic of flight and ground safety. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 02/12/2002
1124 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Computer Hardware-Software/Space Shuttle/General Purpose Computer (GPC) Limitations |  | Outmoded Design of Space Shuttle General Purpose Computer (GPC) Limit Software and Hardware Upgrades | Outmoded Design of Space Shuttle General Purpose Computer (GPC) Limit Software and Hardware Upgrades | HQ | 02/01/1999 | Outmoded Design of Space Shuttle General Purpose Computer (GPC) Limit Software and Hardware Upgrades | The Space Shuttle Program is addressing the finding and recommendation identified by the ASAP.A review of the GPC and its flight software was performed in April 1998. Based on current estimates on GPC mean time between failures, the flight hardware and spares are expected to be available through at least 2016 (and likely significantly later). The flight software estimate on memory availability and usage has projected that memory capacity would be expected to reach its limit in the 2005-2006 time-frame. A software architecture strategy as part of the overall SSP avionics upgrade effort is being developed which will mitigate the memory capacity concern. This strategy will partition the critical software such as flight control and guidance from software that requires periodic change. The result of this partition would allow those stable software functions like flight control to remain within the current GPC's while allowing those functions that frequently change to be migrated to a newer computer technology. The offloading of the software functions such as display processing and systems management from the current GPC's should permit current GPC memory capacity to remain acceptable through at least 2020. Additionally the software subject to frequent change would be located within a system, which will be designed to be more easily reconfigurable than the existing system. In summary, a supportability concern does not exist for the current GPC's. Continued use of the existing GPC's and their established processes will maintain high levels of safety. Software partitioning involving the offloading of software functions to a more flexible system will provide sufficient memory availability for future GPC software changes. This approach will provide an evolutionary and a migration path to full GPC upgrade if it is later required. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 02/12/2002
1121 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Aero-Space Technology/NASA's Three Pillars/Global Civil Aviation |  | Achieving the objectives of the first of NASA's Three Pillars, Global Civil Aviation, requires greater involvement and support by the Federal Aviation Administration (FAA). | NASA should pursue further commitment from the FAA to participate in the first of NASA's Three Pillars, Global Civil Aviation. | HQ | 02/01/1999 | Aero-Space Technology/NASA's Three Pillars/Global Civil Aviation | In 1998 and 1999 our commitment to the President's aviation safety challenge was met through early safety products from each of our Base Research and Technology programs. In 2000, the Aviation Safety focused program begins, in addition to some investment in the Base. The planning for our investment was done in complete harmony with the FAA's activities-both their research investment, as well as their operational efforts. Implementing the results of our collaborative research and technology efforts are fundamental to achieving our safety goal. The recent commitment between the FAA Administrator, Ms. Garvey, and Mr. Goldin committed our two agencies to our two agencies' goals. Further, our Aviation Safety Program is part of the Safety Joint Working Group, and reports to the FAA-NASA Executive Committee that oversees all cooperative activities between the two agencies. The Program also works as partners with FAA to implement the program and will maintain close coordination with the Department of Defense and other government agencies. And, significantly, the Safety Program Manager is member of Commercial Aviation Safety Team and General Aviation Joint Steering Committee-government-industry leadership groups developing and managing overall National safety strategies. NASA aviation safety research and technology efforts therefore complements both FAA and industry activities as a coordinated overall effort. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 02/12/2002
1125 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Computer Hardware-Software/Space Shuttle/I-Loads |  | There is no formal requirement that dependent Space Shuttle I-loads be recalculated or checked when an I-load patch is to be uplinked. | NASA should create a dependency matrix of all I-loads. Furthermore, it should assess its Space Shuttle and ISS procedures and ensure that they are all fully documented. | HQ | 02/01/1999 | Lack of Dependency Matrix for I-Load Recalculation | NASA believes that we already meet the intent of the recommendation. Flight Operations processes and documentation ensures proper I-load change implementation for all flight design I-loads, including uplinkable I-loads. These procedures include positive verification that the selected or uplinked values do not violate sub-system, element, or integrated vehicle certification and that the update meets mission requirements. I-load dependencies are verified as part of the certification assessment. Procedures for verifying I-loads to be uplinked vary. In some instances uplinked I-loads change vehicle response in a way that impacts several of the remaining I-loads; i.e., Day-of-Launch I-load Update (DOLILU). Those verification assessments include an analysis, which uses a high fidelity computer model to simulate integrated vehicle response to the new I-loads. These simulations include models of the onboard flight software of sufficient detail to verify that all applicable I-load interactions are assessed. In other cases, specific I-load dependencies are evaluated. A number of flight design uplinks involve an uplink of values that are generated and verified days or sometimes months before launch. These I-loads include vehicle navigation, targeting, and abort parameters. Verification procedures for these I-loads are identical to that used during the normal flight design template. For all cases, procedures clearly specifying verification requirements including specific I-load dependency evaluations, as applicable, are in place and under configuration control. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 02/12/2002
1074 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Cannibalization |  | As reported last year, long-term projections are still suggesting increasing cannibalization rates, increasing component repair turnaround times, and loss of repair capability for the Space Shuttle logistics programs. If the present trend is not arrested, support difficulties may arise in the next 3 or 4 years. | NASA and USA should reexamine and take action to reverse the more worrying trends highlighted by the statistical trend data. | HQ | 02/01/1998 | Increased Cannibalization Trends | The Space Shuttle Program has recognized the concerns for long-term supportability and is proactively pursuing improvements. Cannibalizations continue to be closely monitored and are well within limits. There have been several concerns during this past year (seals and cryo heater controllers) that are requiring the adjustment of sparing levels. The Logistics organization is aggressively pursuing a solution to specific problems as well as pursuing innovations to keep the rate below the standard. As mentioned in the response to Finding #9, the NSLD backlog is now decreasing as a result of USA action. This should ultimately reduce the repair turn around time for hardware although short-term increases can be expected. Other initiatives such as the replacement of unserviceable test equipment at vendors are also in progress. Logistics and Engineering are developing common tools to integrate upgrade actions, resolve supportability issues, and mitigate the loss of repair capability. The Problem Resolution Teams have increased the interfaces with Logistics, Engineering, and management to ensure a proactive and integrated effort in identifying problem areas and identifying solutions. Numerous initiatives are under way. Finally, NASA has funded through Space Shuttle upgrades the prototyping of a new expert logistics system which shows promise in ranking issues according to severity. This data might then be used to assure that limited funding available is used as economically and wisely as possible in order to minimize risk in the most vulnerable areas. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1077 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Reusable Solid Rocket Motor (RSRM)/Flight Support Motor (FSM) |  | Obsolescence changes to the RSRM processes, materials, and hardware are continuous because of changing regulations and other issues impacting RSRM suppliers. It is extremely prudent to qualify all changes in timely, large-scale Flight Support Motor (FSM) firings prior to produce/ship/fly. NASA has recently reverted from its planned 12-month FSM firing interval to tests on 18-month intervals. | Potential safety risks outweigh the small amount of money that might be saved by scheduling the FSM motor tests at 18-month intervals rather than 12 months. NASA should realistically reassess the test intervals for FSM static test firings to ensure that they are sufficiently frequent to qualify, prior to motor flight, the continuing large number of materials, process, and hardware changes. | HQ | 02/01/1998 | Flight Support Motor (FSM) Test Intervals | Evaluation of all known reusable solid rocket motor (RSRM) future material, process, and hardware changes (by NASA and Thiokol) has confirmed no safety risk impact resulting from FSM static tests every 18 months, in lieu of every 12 months. The RSRM Project goal to "include all changes in a static test prior to flight incorporation" has not changed, and any exceptions will continue to be approved by the Space Shuttle Program Manager before flight incorporation. If a change is planned in the future wherein an 18-month FSM static test frequency is insufficient to support qualification prior to motor flight, program funding requirements will be considered to accelerate an FSM static test to ensure no increased program flight safety risk. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1078 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/External Tank (ET)/Super Light Weight Tank (SLWT) |  | The design requirements for the SLWT include operating with a maximum Space Shuttle Main Engine (SSME) power of only 106%, even at abort conditions. The Space Shuttle program has approved a baseline plan to examine the possibility of certifying the Space Shuttle for intact aborts at a 109% SSME power setting. | NASA should complete its evaluation of a 109% power setting for intact aborts as soon as practicable and reevaluate the ability of the SLWT to accommodate this higher power setting. | HQ | 02/01/1998 | Increased Space Shuttle Main Engine (SSME) Power Setting for Intact Aborts | NASA concurs with the ASAP recommendation. Specific evaluations with regards to orbiter and SLWT have already been completed or are near completion. The Block II Space Shuttle main engine (SSME) certification program will provide the capability for intact abort at 109 percent power level. This certification program is planned to be complete by October 1, 1998. A change request to baseline the 109 percent intact abort loads and thermal environments shall be released by the end of 1998 following completion of Block II SSME 109 percent certification. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1076 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Spares Support |  | Support of the Space Shuttle fleet with operational spares has been maintained by the effective efforts of the logistics function. While spares support has been adequate for the current flight rate, any increase in flight rate might not be supportable. | Although NASA has established programs for dealing with suppliers and bringing additional component overhaul "in house," efforts in these areas need to be continuously reexamined to speed up the restoration and upgrading of line-replaceable units. Such efforts are especially needed to eliminate "dead" time while units are awaiting restoration. | HQ | 02/01/1998 | Line-Replaceable Unit (LRU) Restoration and Upgrading | The Space Shuttle Program concurs with the ASAP concerns for the availability of line replaceable units (LRU's). Logistics monitors LRU spares posture through the probability of sufficiency calculations within the LRU data system. This system can be programmed to determine spares requirements for various flight rates. At this time, an appreciable increase in flight rate would be required to jeopardize supporting the Space Shuttle Program with most of the current LRU's. The Program has been proactive in upgrading LRU's where the most pressing fleet support concerns exist. The following upgrades are in progress: The air data transducer assembly is being replaced by the advanced air data transducers. The master events controller is being replaced by the advanced master events controller. The Global Positioning System is being installed in the orbiters at the orbiter major modification. This could potentially eliminate a number of LRU's in the displays and controls system and tactical air navigation system. New shop replaceable units were purchased to repair the Microwave Scanning Beam Land Station decoders. This decreases turnaround time and increases reliability of the units. Solid state recorders are being considered as replacements for the operations and payload recorders. This effort is presently in the design definition phase. Additionally, through the use of industrial engineering principles and work teams, Logistics has taken action to reduce the NASA Shuttle Logistics Depot (NSLD) backlog and increase output for fiscal year 1998. To date, backlog has decreased 8 percent since October 1 by increasing output. These efforts are aimed at providing better support at the current flight rate but are also the type of efforts that will allow higher flight rates in the future. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1075 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Workforce |  | Transition and development of the logistics tasks for the orbiter and its ground operations under the SFOC are proceeding efficiently and according to plan. | NASA and USA should continue the task of management integration of the formerly separate logistics contracts and retain and expand the roles of the experienced logistics specialists therein. | HQ | 02/01/1998 | Implementation of logistics functions under the Space Flight Operations Contract (SFOC) | The Space Shuttle Program concurs with the ASAP philosophy of logistics integration. Integrated Logistics has been successful in integrating Ground Logistics and more recently, Flight Operations Logistics with Orbiter Logistics insight. As new elements are integrated within USA, the sharing of new techniques and best in class practices is occurring. Logistics is recognized as a key member of both the NASA and contractor teams; their input is actively sought on key decisions, and they are members of key decision-making boards and panels. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1079 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/External Tank (ET)/Super Light Weight Tank (SLWT) |  | The design requirements for the SLWT include operating with a maximum Space Shuttle Main Engine (SSME) power of only 106%, even at abort conditions. The Space Shuttle program has approved a baseline plan to examine the possibility of certifying the Space Shuttle for intact aborts at a 109% SSME power setting. | NASA should complete its evaluation of a 109% power setting for intact aborts as soon as practicable and reevaluate the ability of the SLWT to accommodate this higher power setting. | HQ | 02/01/1998 | Increased Space Shuttle Main Engine (SSME) Power Setting for Intact Aborts | NASA concurs with the ASAP recommendation. Specific evaluations with regards to orbiter and SLWT have already been completed or are near completion. The Block II Space Shuttle main engine (SSME) certification program will provide the capability for intact abort at 109 percent power level. This certification program is planned to be complete by October 1, 1998. A change request to baseline the 109 percent intact abort loads and thermal environments shall be released by the end of 1998 following completion of Block II SSME 109 percent certification. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1067 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Documentation |  | A principal cause of Space Shuttle processing errors is incorrect documentation ("paperwork"). | NASA and Shuttle Processing Contract (SPC) must place increased priority on determining error sources, causes, and corrective actions for inadequacies in the documentation on which Space Shuttle processing is based and develop a management system that drastically reduces the time that it takes to incorporate paperwork changes. | HQ | 02/01/1999 | Incorrect Documentation "Paperwork" is Causing Processing Errors | NASA concurs with the recommendation. NASA and SPC have established metrics to identify the types of errors and error sources in the processing documentation. During daily interface, NASA and SPC discuss these metrics and perform causal analysis to identify the need for corrective action. For critical procedures, SPC has implemented a check and balance in the work instruction generation process to increase the procedure quality before it is worked. Additionally, NASA and SPC have an initiative to reduce the complexity of work procedures, increase the procedure standardization, and reduce the time for paperwork generation for work not requiring engineering disposition. More importantly, SPC is developing, as a high priority, a paperless system. Specifically, the Ground Operations organization at KSC is implementing an integrated on-line system that ensures total process rigor and mitigates the potential for human error in accomplishing space flight work. This system incorporates recognized "best practices" for authoring work documents including on-line review and approval, and the ability for authors to automatically update and incorporate work document deviations. Required checks and balances are inherent in the system to maintain the integrity, safety and quality of both flight and ground work performed. Work documents will clarify user understanding by incorporating enhanced explanations with in-line graphics, sound and video where required. The goal of this activity is to ensure that a properly certified person, utilizing the right work instructions, has safely accomplished all required work. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1071 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Radiation Exposure/Effects on Crew |  | Radiation exposures of U.S. astronauts recorded over several Mir missions of 115 to 180 days duration have been approximately 10.67 to 17.20 REM. If similar levels of exposure are experienced during ISS operations, the cumulative effects of radiation could affect crew health and limit the number of ISS missions to which crewmembers could be assigned. | Determine projected ISS crew radiation exposure levels. If appropriate, based on study results, initiate a design program to modify habitable ISS modules to minimize such exposures or limit crew stay time as required. | HQ | 02/01/1998 | Effects of Radiation Exposure on ISS Expedition Crews | Crew radiation exposure requirements for the primary elements of the United States On-orbit Segment (USOS), including the habitation and laboratory modules, as defined in the Primary Item Development Specifications (Section 3.3.10.3) state the design of these modules shall limit the ionizing radiation dose to crew members to 40 Roentgen equivalent man (rem) Blood Forming Organs (BFO) per year. This requirement was developed in coordination with the JSC Space Radiation Analysis Group and is more stringent than the overall NASA Flight Rule requirement (14-10) of 50 rem BFO per year. This requirement also meets the intent of the Presidential Directive concerning Federal Radiation Protection Guidance for Occupational Exposure (Federal Register Vol. 52, No. 17). Detailed analyses documented in SAIC-TN-96065 (August 1996) and SAIC-TN-9601 (January 1996) indicates that the maximum dose for any location in the USOS is less than 23 rem BFO per year. Detailed shielding analyses performed by Khrunichev and documented in EN-10-13, Protection from Space Environment (November 1996), indicate calculated values of absorbed dose in the FGB crew-habitable zone range from 16-39 rads/year. Using a quality factor value of 1.4 obtained from NCRP Report No. 98 (Guidance on Radiation Received in Space Activities pg. 45) to convert from rads to rem gives 22-55 rem per year. Based on these analyses and the nominal crew rotation schedule (90 days on-orbit, not to exceed 180 days), ISS concludes that adequate protection is provided to the crew by the shielding and design of the ISS. In addition, the federal guideline is an exposure of 50 rem BFO per year. The International Space Station requirement is 40 rem BFO per year. Current analysis of USOS predicts maximum exposure of 16 rem BFO per year. Although the actual crew exposure level will be monitored with actual flight data, the ISSP concludes that no redesign is necessary to consider increased shielding requirements. Technical Reference: Letter from Boeing Environments Team dated February 12, 1998 | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1068 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Spares Support |  | While spares support of the Space Shuttle fleet has been generally satisfactory, repair turnaround times (RTAT's) have shown indications of rising. Increased flight rates will exacerbate this problem. | Refocus on adequate acquisition of spares and logistic system staffing levels to preclude high RTAT's, which contribute to poor reliability and could lead to a mishap. | HQ | 02/01/1999 | Shuttle Spares Support Will Likely Decline With an Increased Flight Rate | NASA concurs with the recommendation. During calendar year 1998, RTAT's for both the NASA Shuttle Logistics Depot and the original equipment manufacturer fluctuated, but at year's end, the overall trend was downward through concerted NASA and vendor efforts. These efforts are aimed at providing better support at the current flight rate and for higher flight rates in the future. Logistics is working to find innovative ways to extend the lives of aging line replaceable units (LRU's) and their support/test equipment. Logistics has initiated the Space Council (an industry group with 11 other company executives addressing such topics as verification reduction, ISO compliance, and upgrades) to assure the supplier base continues its outstanding support to the SSP. Examples of LRU's being evaluated and enhanced include: Star Trackers, auxiliary power units, inertial measurement units, multifunction electronic display system (MEDS), Ku-b and, orbiter tires, and manned maneuvering units. NASA/KSC Logistics and Shuttle Processing Contract (SPC) Integrated Logistics have made progress on a long-term supportability tool. The tool will provide information, including historical repair trend data for major LRU's, RTAT's, and "what if" scenarios based on manipulation of factors (e.g., flight rate, turnaround times, loss of assets, etc.) to determine their effect on the probability of sufficiency. This will be a tool, not a substitute, for human analytical decision-making. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1069 | Thomas, John - 0000000000 : NO@ADDRESS.GIVEN; Koudelka, John - | Thomas, John - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Quick Release V-Band on Pressure Vessel |  | Pressurized containers that use quick-release V-bands need to have an additional lid restraining element or pressure interlock. A lid restrain needs to capture the lid in the case the V-band is released when the chamber is pressurized. A pressure interlock would maintain the lid seal integrity whenever the chamber pressure is above the external atmosphere. | Chamber and lid were modified to provide a mechanical obstruction that would capture the lid if the V-band was released when the chamber was pressurized. The obstruction permitted the lid to break the seal and relief the pressure but limited its travel / separation to prevent any safety issue. The procedures were also modified to make the chamber relieving steps more obvious. | GRC | 04/18/2001 | Safety Mishap on the KC-135. An experiment rig that is flown on the KC-135 utilized a quick-release V-band to seal a pressurized chamber. The chamber was used to conduct combustion experiments during the KC-135 flight. The v-band was implemented in order to permit quick and easy access to the chamber interior in order to change samples and access interior components and instrumentation. During the KC-135, the V-band was released when the chamber was still pressurized. Once the V-band was released, the chamber lid was propelled off the chamber and across the plane's cabin area. The lid just missed one of the experiment operators and caused damage to one of the plane's interior lights. The experiment operation procedures had steps to identify relief of pressure, but those were skipped, and the V-band and chamber lid design contain no other lid retention element. | The experiment rig was flown again in with no mishap, mainly due to the procedural changes. The lid restraint was verified to its ability to keep the lid from being a loose item | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
1072 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Shuttle-Mir/Lessons Learned |  | The ISS Phase I Shuttle-Mir program has reaffirmed what was learned on Skylab: that a manned space station can be surprisingly resilient in emergency situations. Much has been learned from the operations on Mir to date and much more may be learned from continued analysis of joint operations on Mir. | The ISS team should continue to examine the Shuttle-Mir program carefully for examples from which ISS operations can benefit and to provide policies and procedures to implement effective action should similar events occur on the ISS. The effort should be expanded beyond Mir to focus as well on possible weaknesses in the ISS design and operations. ISS should assemble a special team including, persons with system-level perspectives as well as with design, operations, and human factors experience, to address these issues. | HQ | 02/01/1998 | Shuttle-Mir Lessons Learned Analysis and Application | The ISS Program (ISSP) has benefited greatly from the Phase I Program experiences in the areas of operational feasibility and validation, procedures development and logistics manifesting, and in some cases, hardware modifications. A more rigorous process for evaluating Shuttle/Mir lessons learned has been implemented and will assure that ISS realizes maximum benefit from Shuttle/Mir lessons learned. Phase I management screens and prioritizes lessons learned from each Shuttle/Mir flight increment to document significant and applicable lessons to ISS. These lessons are thoroughly reviewed by ISS Lessons Learned Screening Panel. For each lesson, actionee(s) are assigned to analyze ISS applicability and possible implementation or rationale for nonimplementation. The Lessons Learned Screening Panel and ISSP management will assure that the proposed implementation is appropriate. This screening process includes representatives from numerous organizations to ensure that all these issues are adequately addressed. This same process is used to incorporate lessons learned which are discovered within the ISS Program as well. (Note: Process is depicted in the accompanying figure.) o Identify Significant Lessons from Phase I Each Phase I working group to identify key lessons Eliminate duplication and focus on high impact lessons o Front End Analysis Determine root causes and add appropriate level of detail o Screen Lessons ISS Lessons Learned Screening Panel has been established to prioritize and categorize lessons Determine responsible person/organization to respond o Document and Track Enter lessons into database and track disposition o Decompose, Analyze, and Disposition Lessons Systems Engineering used to determine applicability and impacts Disposition: implement, partially implement, or no practical implementation Another specific example of Phase I lessons learned implementation: Unplanned events on Mir resulted in the requirement to provide late stowage of items on the Shuttle. The requirement to support this activity has reinforced the importance of building flexibility into our ground processing capabilities and operational planning for the ISS Phase 2 resupply missions. In order to accommodate the potential for similar requirements during Phase 2, we have designed and are in the process of developing support equipment, which will permit contingency access to the Multi-Purpose Logistics Module (MPLM) after it is installed in the orbiter at the Pad. This will enhance our ability to react to changes, which require the addition of items late in the processing flow. The Manager, Phase 1 Program, has been directed by the Lead Center director to perform a comprehensive review of current planning for space station operations. This review will assess ISS operations and mission management processes, including but not limited to, mission planning, the real-time mission management process, the Mission Management Team (MMT) structure, and other elements of flight operations. Additionally, he will review the Certificate of Flight Operations (COFR) process and other key activities leading up to and the execution of ISS flights. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 01/07/2002
722 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Electrical Harness Design Practice |  | If this practice is not implemented, electrical harnesses used on spacecraft and instruments may not conform to their electrical and space environmental requirements. Harnesses may not be properly tested, cleaned, and certified prior to installation into spacecraft and instruments. This could result in early mission failures. | Design and fabricate space flight electrical harnesses to meet the minimum requirements of the GSFC Design and Manufacturing Standard for Electrical Harnesses. | GSFC | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1238; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Designing and testing flight harnesses in accordance with the requirements of the GSFC Design and Manufacturing Standard (Ref. 1) for Electrical Harnesses enhances the probability of mission success (Reliability) by ensuring that harnesses meet high standards of quality as well as the electrical and environmental requirements of space flight missions. The occurrence of early failures is minimized. Implementation: Flight electrical harnesses are designed in accordance with the requirements and specifications of the GSFC Design and Manufacturing Standard for Electrical Harnesses (reference 1) which establishes the minimum requirements for the design and fabrication of space flight harnesses. Parts and materials are used as specified in the harness standard that can perform satisfactorily in the environments to be encountered. Fabrication methods and techniques are used as defined to ensure high quality electrical harnesses. The GSFC Design and Manufacturing Standard for Electrical Harnesses incorporates and references applicable requirements from a wide range of Federal, Military, and NASA specifications, standards, and publications. Maximum current-carrying capacity is defined for wire sizes ranging from size AWG 12 to AWG 24 to ensure that the total temperature of wire does not exceed the operating temperature ratings of the wire. The total temperature of the wire includes the ambient space temperatures and the temperature rises due to current flows. The maximum voltage drop between power supplies and loads due to the impedance of wire and ground return paths are specified for various power supply voltage levels. The minimum size of individual wires used in harnesses is AWG 24 except for power harnesses where the minimum size of wires is limited to AWG 22. A number of EMI design and construction techniques are used to minimize electromagnetic coupling between wires within harness assemblies. These techniques include isolation of different signal types such as high level and pulse signals from low level and continuous wave signals by using separate harnesses and connectors where possible. When these signal types must be included within the sane harness, the best possible isolation is obtained by grouping wires of similar signal types within the harness and on connectors. Other methods include shielding of individual wires or groupings of wires within the harness and using separate connectors where possible. Twisted pair leads, shielded when necessary, are used for power and balanced signal circuits. RG type RF cables terminated at both ends with coaxial connectors are used for RF signals. A number of physical parameters and limitations are used as defined in the Design and Manufacturing Standard for Electrical Harnesses. The diameter of the harness is kept to a minimum and limited to one inch in diameter consistent with requirements for routing, installation, and handling. The Design and Manufacturing Standard for Harnesses contains information and a method for estimating the diameter of a harness. The lengths of harnesses are made to provide enough additional wire length for reworking connections at least one time. Minimum bend radiuses, location and support of wire breakouts, shielding and termination of shields are followed as defined in the harness standard. Harnesses are secured with lacing tape or tie wraps and movement is controlled by means of cable clamps or tie wraps. Electrical connector types including protective covers, sealing grommets, wire splices, and potting compounds are selected and fabricated as required by the harness standard. Probing or testing flight harnesses or connectors is always accomplished via connector savors or breakout boxes. Mate/demate logs are maintained and connector inspections are instituted once the connector mate/demate count reaches 15 and inspected every 10 mates/demates thereafter. Connector hardware is staked with an approved epoxy after torquing. The staking is an indication that the hardware has been torqued and that it has not been disturbed. A number of quality assurance provisions are followed as defined in the Design and Manufacturing Standard for Electrical Harnesses. Visual inspection includes harness documentation, materials used, design and fabrication methods, identification of components, and workmanship. Harness assemblies are tested for point to point electrical continuity in accordance with applicable wiring diagrams or wire lists. Values, within a connector bundle of the same conductor size and wire length, must be consistent within 10%. Insulation resistance is measured between each conductor and every other conductor and each conductor and shield. The insulation resistance must be greater than 100 megohm at an applied voltage voltage of 500v dc for a maximum of one minute. Essentially all harnesses have strict contamination control and certification requirements. To meet these requirements shielding braids are ultrasonically cleaned with an approved solvent and wires and cable are wiped with clean lint free cloths and an approved solvent before fabrication into the harness. After harness fabrication is complete and certified, the complete harness is cleaned with an approved solvent, inspected with both black and white light. Technical Rationale: The proper design, fabrication, testing, and certification of electrical harnesses significantly reduces the probability of spacecraft failures due to harness material deterioration in space, wire and connector failures due to current overloading, excessive stresses, and crosstalk and arcing between wires and harnesses. The use of appropriate materials and cleaning technique's during and following fabrication of harnesses controls contamination that can cause deterioration and failure of spacecraft hardware particularly many types of scientific instruments. References Design and Manufacturing Standard for Electrical Harnesses, Document No. GSFC-733-HARN-01 |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 01/04/2002
1064 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | Shortfalls in workforce training within both NASA and USA, caused by downsizing and the related difficulty of hiring new people to fill skill shortages, can jeopardize otherwise safe operations. | NASA and USA should review critical skills training and certification requirements and institute programs to ensure the full proficiency of the workforce and the safety of the products being released. | HQ | 02/01/1999 | Workforce Training Shortfalls Have the Potential to Jeopardize Safety | NASA concurs in the recommendation and, in cooperation with USA, has already reviewed certification requirements for flight controllers, training instructors, and other key operating positions. Training plans and certification requirements for critical positions have been documented and maintained. For example, the management role in launch countdown and landing is supported by a well-defined training and certification plan. NASA and its contractors are continually reviewing critical skills training and certification requirements to ensure controls are in place to validate and ensure employee proficiency. Quality initiatives are being developed to provide improved processes for cross training, automated training tools, inline automated certification validation, and enhancements in the closed loop verification of operators and system operational performance. Meanwhile, training capacity for new employees, both NASA and contractor, has been increased through intensive simulator training at a new USA "training academy." A saturation-type training environment has been designed to improve training at the beginning of the regular certification process and produce employees better qualified for critical process work. In training and orientation programs, NASA emphasizes the priority of safety and the responsibility of employees to voice their concerns about inadequate assurances of safe products. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/19/2001
1065 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | The combined effect of workforce downsizing, the recent hiring freeze, and the Shuttle Processing contract (SPC) transition, especially at KSC, has raised the possibility that NASA senior managers in the future will lack the necessary hands-on technical knowledge and in-line experience to provide effective insight of operations. | NASA should develop and promulgate training and career paths, with a special focus on providing hands-on technical knowledge and experience, so that NASA's future senior managers will possess the range of skills and experience required for effective insight of the SPC. | HQ | 02/01/1999 | Effects of Lack of Knowledge and Experience on Operations | NASA concurs in the recommendation and is intensifying and refocusing its efforts in training and in support of career development at all levels. At the operating level, NASA managers are instructed to plan and to take advantage of all opportunities to obtain operational experience through audit, surveillance, and other interfaces to provide hands-on experience to NASA personnel. These include, in addition to the simulator training discussed in the response to Recommendation #2: co-op assignments partnered with contractor systems engineers direct observation or procedure review of critical tasks management of Shuttle launch countdown, launch, and landing/recovery participation in flight and ground systems development and enhancements processing mid-decks, utilization payloads, and partial Shuttle payloads participation in contractor testing, and anomaly resolution ensuring adequately designed, tested, and assembled hardware Additionally, employees are provided cross training and specialized training as needed and strongly encouraged to take advantage of program related training. The key to developing future generations of senior managers is to provide hands-on experience, with progressively more responsible assignments through one's career. Both NASA and the contractors continually seek improvements in the succession planning and preparations for the next generation of supervisors and managers. Special consideration is given to assuring that broad training and hands-on operational/technical job assignments and opportunities are consciously addressed for promising candidates for future senior management positions. NASA's training philosophy also emphasizes on-the-job work experiences supplemented by classroom instruction, participation in outside academic programs and industry through assignments in such private sector organizations as contractors. At the agency planning level, the training budget has provided for an increase of 20% for the Office of Space Flight from FY1997 through FY2000. Current agency Program Operating Plan (POP) guidelines call for funding training at 2-3.25% of salary levels, an extremely generous ratio for government and rivaling progressive private sector organizations. The NASA Academy of Program and Project Leadership (APPL) is building on ten years of educational and developmental activities and is striving to facilitate the flow of current knowledge and techniques to the full engineering and science workforce. APPL is making available information and automated tools on-line and seeking to develop expert systems. APPL is also working directly to support intact teams with information and techniques and attempting to better organize case studies and archives into a more effective knowledge base. The APPL program is also adding an Accelerated Leadership Option to the Project Management Development Process (PMDP) which will enable NASA engineers to obtain a Master's of Science in Engineering and Management degree from MIT. APPL is continuing and expanding a multifaceted program of classroom work, developmental work assignments, and dissemination of information and guidance. Finally, NASA is well along in an update of its Leadership Development Model; documenting the technical, managerial, and executive competencies required to direct the work of the agency through the foreseeable future. This model will guide the scope and emphasis of training and development programs, including a new approach to succession planning, to ensure that NASA's leaders at all levels have the knowledge and skills to meet their responsibilities. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/19/2001
1066 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Metrics |  | It is often difficult to find meaningful metrics that directly show safety risks or unsafe conditions. Safety risks for a mature vehicle, such as the Space Shuttle, are identifiable primarily in specific deviations from established procedures and processes, and they are meaningful only on a case-by-case basis. NASA and Shuttle Processing Contract (SPC) have a procedure for finding and reporting mishaps and "close calls" that should produce far more significant insight into safety risks than would mere metrics. | In addition to standard metrics, NASA should be intimately aware of the mishaps and close calls that are discovered, followup in a timely manner, and concur on the recommended corrective actions. | HQ | 02/01/1999 | Finding and Reporting of Mishaps and "Close Calls" | NASA agrees with the recommendation. In addition to standard metrics, NASA is intimately aware of the mishaps and close calls and is directly involved in the investigations and approval of corrective actions. Current requirements contained in various NASA Center and contractor safety plans include procedures for reporting of mishaps and close calls. These reports are investigated and resolved under the leadership of NASA representatives with associated information being recorded and reported to NASA management. NASA is intimately aware of and participates in the causal analysis and designation of corrective action for each mishap. Additionally, NASA performs trend analysis of metrics as part of the required insight activities. Definitions relating to "close call" have been expanded to include any observation or employee comment related to safety improvement. Close call reporting has been emphasized in contractor and NASA civil servant performance criteria and a robust management information system is being incorporated to monitor and analyze conditions and behavior having the potential to result in a mishap. Various joint NASA/contractor forums exist to review, evaluate, and assign actions associated with reported close calls. As an example, the KSC NASA Human Factors Integration Office leads the NASA/Contractor Human Factors Integrated Product Team (IPT) in the collection, integration, analysis, and dissemination of root cause and contributing cause data across all KSC organizations. The KSC Human Factors IPT is also enhancing the current close call process, which includes tracking of mishaps with damage below $1000 and injuries with no lost workdays. The SSP has revised it's Preventive/Corrective Action Work Instruction to include mandatory quarterly review of close call reports. Several initiatives are in place to increase awareness of the importance of close call reporting and preventive/corrective action across the SSP and the supporting NASA Centers and contractors. Under this new approach to close call reporting, a metric indicating an increase in close call reporting and preventive action is considered highly desirable as it indicates an increased involvement by the workforce in identifying and resolving potential hazards. Care is taken in over emphasizing the number of close calls reported as a performance metric to prevent reluctance in reporting. NASA is working hard to shift the paradigm from the negative aspects of reporting close calls under the previous definition to being a positive aspect of employee identification of close calls under the new definition. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/19/2001
1055 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Shuttle-Mir/Lessons Learned |  | The ISS Phase I Shuttle-Mir program has reaffirmed what was learned on Skylab: that a manned space station can be surprisingly resilient in emergency situations. Much has been learned from the operations on Mir to date and much more may be learned from continued analysis of joint operations on Mir. | The ISS team should continue to examine the Shuttle-Mir program carefully for examples from which ISS operations can benefit and to provide policies and procedures to implement effective action should similar events occur on the ISS. The effort should be expanded beyond Mir to focus as well on possible weaknesses in the ISS design and operations. ISS should assemble a special team including, persons with system-level perspectives as well as with design, operations, and human factors experience, to address these issues. | HQ | 02/01/1998 | Shuttle-Mir Lessons Learned Analysis and Application | The ISS Program (ISSP) has benefited greatly from the Phase I Program experiences in the areas of operational feasibility and validation, procedures development and logistics manifesting, and in some cases, hardware modifications. A more rigorous process for evaluating Shuttle/Mir lessons learned has been implemented and will assure that ISS realizes maximum benefit from Shuttle/Mir lessons learned. Phase I management screens and prioritizes lessons learned from each Shuttle/Mir flight increment to document significant and applicable lessons to ISS. These lessons are thoroughly reviewed by ISS Lessons Learned Screening Panel. For each lesson, actionee(s) are assigned to analyze ISS applicability and possible implementation or rationale for nonimplementation. The Lessons Learned Screening Panel and ISSP management will assure that the proposed implementation is appropriate. This screening process includes representatives from numerous organizations to ensure that all these issues are adequately addressed. This same process is used to incorporate lessons learned which are discovered within the ISS Program as well. (Note: Process is depicted in the accompanying figure.) o Identify Significant Lessons from Phase I Each Phase I working group to identify key lessons Eliminate duplication and focus on high impact lessons o Front End Analysis Determine root causes and add appropriate level of detail o Screen Lessons ISS Lessons Learned Screening Panel has been established to prioritize and categorize lessons Determine responsible person/organization to respond o Document and Track Enter lessons into database and track disposition o Decompose, Analyze, and Disposition Lessons Systems Engineering used to determine applicability and impacts Disposition: implement, partially implement, or no practical implementation Another specific example of Phase I lessons learned implementation: Unplanned events on Mir resulted in the requirement to provide late stowage of items on the Shuttle. The requirement to support this activity has reinforced the importance of building flexibility into our ground processing capabilities and operational planning for the ISS Phase 2 resupply missions. In order to accommodate the potential for similar requirements during Phase 2, we have designed and are in the process of developing support equipment, which will permit contingency access to the Multi-Purpose Logistics Module (MPLM) after it is installed in the orbiter at the Pad. This will enhance our ability to react to changes which require the addition of items late in the processing flow. The Manager, Phase 1 Program, has been directed by the Lead Center director to perform a comprehensive review of current planning for space station operations. This review will assess ISS operations and mission management processes, including but not limited to, mission planning, the real-time mission management process, the Mission Management Team (MMT) structure, and other elements of flight operations. Additionally, he will review the Certificate of Flight Operations (COFR) process and other key activities leading up to and the execution of ISS flights. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1057 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Radiation Exposure/Effects on Crew |  | Radiation exposures of U.S. astronauts recorded over several Mir missions of 115 to 180 days duration have been approximately 10.67 to 17.20 REM. If similar levels of exposure are experienced during ISS operations, the cumulative effects of radiation could affect crew health and limit the number of ISS missions to which crewmembers could be assigned. | Determine projected ISS crew radiation exposure levels. If appropriate, based on study results, initiate a design program to modify habitable ISS modules to minimize such exposures or limit crew stay time as required. | HQ | 02/01/1998 | Effects of Radiation Exposure on ISS Expedition Crews | Crew radiation exposure requirements for the primary elements of the United States On-orbit Segment (USOS), including the habitation and laboratory modules, as defined in the Primary Item Development Specifications (Section 3.3.10.3) state the design of these modules shall limit the ionizing radiation dose to crew members to 40 Roentgen equivalent man (rem) Blood Forming Organs (BFO) per year. This requirement was developed in coordination with the JSC Space Radiation Analysis Group and is more stringent than the overall NASA Flight Rule requirement (14-10) of 50 rem BFO per year. This requirement also meets the intent of the Presidential Directive concerning Federal Radiation Protection Guidance for Occupational Exposure (Federal Register Vol. 52, No. 17). Detailed analyses documented in SAIC-TN-96065 (August 1996) and SAIC-TN-9601 (January 1996) indicate that the maximum dose for any location in the USOS is less than 23 rem BFO per year. Detailed shielding analyses performed by Khrunichev and documented in EN-10-13, Protection from Space Environment (November 1996), indicate calculated values of absorbed dose in the FGB crew-habitable zone range from 16-39 rads/year. Using a quality factor value of 1.4 obtained from NCRP Report No. 98 (Guidance on Radiation Received in Space Activities pg. 45) to convert from rads to rem gives 22-55 rem per year. Based on these analyses and the nominal crew rotation schedule (90 days on-orbit, not to exceed 180 days), ISS concludes that adequate protection is provided to the crew by the shielding and design of the ISS. In addition, the federal guideline is an exposure of 50 rem BFO per year. The International Space Station requirement is 40 rem BFO per year. Current analysis of USOS predicts maximum exposure of 16 rem BFO per year. Although the actual crew exposure level will be monitored with actual flight data, the ISSP concludes that no redesign is necessary to consider increased shielding requirements. Technical Reference: Letter from Boeing Environments Team dated February 12, 1998 | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1056 | Dominguez, Manuel - 0000000000 : NO@ADDRESS.GIVEN; Raynor, Eric - | Dominguez, Manuel - 0000000000 : NO@ADDRESS.GIVEN |  | X-33 Structural Test Article (STA) Tank Incident |  | Future planning for such trips must include emphasis on following the lead vehicle, especially on the approach to the bridge where the incident occurred. | A comprehensive engineering assessment of the damage shall be completed to determine the integrity of the STA. A plan to qualify the tank for use at GRC shall be developed and concurred with by OSAT and PDS project personnel The GRC Executive Safety Board shall approve the tank repair plan. The GRC Office of Safety and Assurance Technologies (OSAT) shall verify that all plan elements are successfully completed prior to GRC use. The planning for the return trip of the STA to MSFC should include increased emphasis on the following the lead vehicle, especially on the approach to the bridge where the incident occurred. | GRC | 07/28/1999 | The X-33 STA tank was sent from Marshall Space Flight Center (MSFC), Huntsville, Alabama, to NASA Glenn Research Center, Cleveland, Ohio via commercial ground carrier. The carrier and the project team at GRC planned the route and coordinated it with the Department of Transportation of every state the carrier was to pass through. The truck carrying the tank left on June 24, 1999. On Sunday, June 27, 1999 the truck failed to clear an underpass in West Virginia. The tank was hit on the upper corner on the driver's side. Some insulation was damaged and some bolts were sheared. At the time of the incident, the truck was following a lead truck with a frame that simulated the configuration of the tank in the main truck. The vehicles were traveling at 5 miles per hour at the time of impact. This particular underpass was not considered a problem in the original plan. Based on the information collected by the investigation team, it is the team's conclusion that the driver of the main truck failed to follow the lead vehicle in a manner that would allow it to clear the underpass safely. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/14/2001
1054 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Hardware/Qualification Testing |  | Node #1 was shipped to KSC before completion, and it is planned or anticipated that other ISS hardware will be shipped before qualification tests are completed. This disrupts the desirable continuity of effort and can lead to safety problems. | NASA should assure that ISS assemblies shipped before completion of the manufacturing, testing, and qualification processes have been carefully scrutinized to make sure that no safety-related steps are subverted. | HQ | 02/01/1998 | Shipment of Hardware to KSC Before Qualification Testing | The generation, implementation and tracking of ISS assembly, checkout and test requirements is provided by engineering, configuration management and safety and mission assurance processes that are in place and actively monitored. Should a decision be made to transfer flight articles to a different location for completion of planned assembly and checkout activities, these processes ensure an accurate status of accomplished and traveled work is known and documented. In addition, a predetermined set of criteria identifies the set of minimum essential requirements to be accomplished prior to shipment. All ISS assemblies undergo a rigorous predelivery review prior to shipment to KSC. This high-level review is attended by Senior NASA and contractor representatives from all the major functional disciplines involved in the specific assembly in question, including Engineering, Quality, Safety, Hardware Integration Office, and KSC Processing. Open work items that are candidates for completion at KSC are specifically addressed, validated and accepted by all in attendance prior to being forwarded for integration into the contractors existing work plan for KSC. No work practices or safety related practices are compromised by this process. Boeing remains completely accountable for work completion and providing complete and fully tested ISS components to NASA regardless of the physical location of the assembly process. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1051 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Spares Support |  | Support of the Space Shuttle fleet with operational spares has been maintained by the effective efforts of the logistics function. While spares support has been adequate for the current flight rate, any increase in flight rate might not be supportable. | Although NASA has established programs for dealing with suppliers and bringing additional component overhaul "in house," efforts in these areas need to be continuously reexamined to speed up the restoration and upgrading of line-replaceable units. Such efforts are especially needed to eliminate "dead" time while units are awaiting restoration. | HQ | 02/01/1998 | Line-Replaceable Unit (LRU) Restoration and Upgrading | The Space Shuttle Program concurs with the ASAP concerns for the availability of line replaceable units (LRU's). Logistics monitors LRU spares posture through the probability of sufficiency calculations within the LRU data system. This system can be programmed to determine spares requirements for various flight rates. At this time, an appreciable increase in flight rate would be required to jeopardize supporting the Space Shuttle Program with most of the current LRU's. The Program has been proactive in upgrading LRU's where the most pressing fleet support concerns exist. The following upgrades are in progress: The air data transducer assembly is being replaced by the advanced air data transducers. The master events controller is being replaced by the advanced master events controller. The Global Positioning System is being installed in the orbiters at the orbiter major modification. This could potentially eliminate a number of LRU's in the displays and controls system and tactical air navigation system. New shop replaceable units were purchased to repair the Microwave Scanning Beam Land Station decoders. This decreases turnaround time and increases reliability of the units. Solid state recorders are being considered as replacements for the operations and payload recorders. This effort is presently in the design definition phase. Additionally, through the use of industrial engineering principles and work teams, Logistics has taken action to reduce the NASA Shuttle Logistics Depot (NSLD) backlog and increase output for fiscal year 1998. To date, backlog has decreased 8 percent since October 1 by increasing output. These efforts are aimed at providing better support at the current flight rate but are also the type of efforts that will allow higher flight rates in the future. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1053 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Cannibalization |  | As reported last year, long-term projections are still suggesting increasing cannibalization rates, increasing component repair turnaround times, and loss of repair capability for the Space Shuttle logistics programs. If the present trend is not arrested, support difficulties may arise in the next 3 or 4 years. | NASA and USA should reexamine and take action to reverse the more worrying trends highlighted by the statistical trend data. | HQ | 02/01/1998 | Increased Cannibalization Trends | The Space Shuttle Program has recognized the concerns for long-term supportability and is proactively pursuing improvements. Cannibalizations continue to be closely monitored and are well within limits. There have been several concerns during this past year (seals and cryo heater controllers) that are requiring the adjustment of sparing levels. The Logistics organization is aggressively pursuing a solution to specific problems as well as pursuing innovations to keep the rate below the standard. As mentioned in the response to Finding #9, the NSLD backlog is now decreasing as a result of USA action. This should ultimately reduce the repair turn around time for hardware although short- term increases can be expected. Other initiatives such as the replacement of unserviceable test equipment at vendors are also in progress. Logistics and Engineering are developing common tools to integrate upgrade actions, resolve supportability issues, and mitigate the loss of repair capability. The Problem Resolution Teams have increased the interfaces with Logistics, Engineering, and management to ensure a proactive and integrated effort in identifying problem areas and identifying solutions. Numerous initiatives are under way. Finally, NASA has funded through Space Shuttle upgrades the prototyping of a new expert logistics system which shows promise in ranking issues according to severity. This data might then be used to assure that limited funding available is used as economically and wisely as possible in order to minimize risk in the most vulnerable areas. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1052 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Workforce |  | Transition and development of the logistics tasks for the orbiter and its ground operations under the SFOC are proceeding efficiently and according to plan. | NASA and USA should continue the task of management integration of the formerly separate logistics contracts and retain and expand the roles of the experienced logistics specialists therein. | HQ | 02/01/1998 | Implementation of logistics functions under the Space Flight Operations Contract (SFOC) | The Space Shuttle Program concurs with the ASAP philosophy of logistics integration. Integrated Logistics has been successful in integrating Ground Logistics and more recently, Flight Operations Logistics with Orbiter Logistics insight. As new elements are integrated within USA, the sharing of new techniques and best in class practices is occurring. Logistics is recognized as a key member of both the NASA and contractor teams; their input is actively sought on key decisions, and they are members of key decision-making boards and panels. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1059 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Computer Hardware-Software/Checkout and Launch Control System (CLCS) |  | The Checkout and Launch Control System (CLCS) program at KSC has not been provided with funding for Independent Verification and Validation (IV&V) that is safety critical for a software effort of this size. | The Checkout and Launch Control System (CLCS) should be provided with adequate funding for software IV&V. | HQ | 02/01/1998 | Independent Verification and Validation (IV&V) of Checkout and Launch Control System (CLCS) | KSC concurs with the ASAP recommendation relative to IV&V funding for the CLCS Project. A Memorandum of Agreement (MOA) was signed on May 5, 1998, between the Software IV&V Facility and KSC, for the performance application of IV&V techniques and methods to the CLCS software. The scope of this memorandum will include performing IV&V on selected catastrophic/critical/high risk CLCS software components. The selected software components will consist of CLCS system software. The specific areas to be analyzed will be system redundancy, command support, data distribution and processing, constraint management, and the safing system related software. The software related to safing includes the Emergency Safing System and those control logic modules associated with safing (some of which may reside within application software). The analysis will consist of requirements, design, code, and test analysis, as applicable for the life cycle of the software being analyzed. The application interfaces with the system software will also be analyzed. In addition, the IV&V Facility will perform system level analysis of the system test plan and system tests performed along with software engineering and integration analysis of the CLCS system as a whole. This MOA is effective from May 1, 1998, until September 30, 2000. The work identified in this MOA will require a staffing level of about 16 full time equivalents (FTE's). This staffing level will be comprised of 15 FTE's from the IV&V contractor located at the IV&V Facility and at KSC. The remaining one FTE will be a civil service personnel. Staffing at KSC will be comprised of eight contractor FTE's with the remainder residing at the Fairmont Facility. The Space Shuttle Program has agreed to fund this effort at $4.5M over the life of the MOA. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1060 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Computer Hardware-Software/Hardware |  | The computer system being developed for the ISS is already at a point where NASA should begin planning for upgrading it. The ISS program presently has no plans for upgrading the ISS computer system. | NASA should upgrade the computer system as soon as possible and coordinate the upgrade with its solution to the long-term development tool maintenance problem. | HQ | 02/01/1998 | International Space Station (ISS) Computer Hardware Upgrades | The Program's computer system must be viewed in two parts: 1) the core infrastructure; i.e. multiplexers/ demultiplexers (MDM's) and 2) the user interface; i.e. Portable Computer System. The core infrastructure maintains the facility environment and basic command and control interface. This functionality will require minimal growth, but obviously must be capable of being maintained over the period of ISS life. The user interface, on the other hand, must be capable of growth to enhance productivity as well as be maintainable. With this in mind, the user interface is developed using commercially available hardware and software and will be upgraded as technology progresses. In fact, one upgrade is already being implemented at 5A. Provisions for maintenance of the computer system is provided in the ISS Sustaining Engineering Plan. Funding is provided to maintain critical skills to support flight and ground hardware, including support engineering and touch labor to repair cards and provide new spares; this includes maintaining critical facilities. An ISS Pre-Planned Program Improvement (P3I) study is under review to evaluate a more current design upgrade to the MDM "386" processor in FY 99, to ensure MDM core infrastructure sustainability and adequate growth potential during the ISS lifetime. In addition a technical new start for an enhanced mass storage device for the MDM is also under review to improve reliability and storage capability. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1058 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | Budget and personnel ceiling constraints on the hiring of engineers, scientists, and technical workers are moving NASA toward a crisis of losing the core competencies needed to conduct the Nation's space flight and aerospace programs in a safe and effective manner. | Provide NASA's human space flight Field Centers, particularly KSC, JSC, and MSFC, with the budgetary resources and administrative flexibility needed to strengthen their human resource capabilities. | HQ | 02/01/1999 | Loss of Core Competencies Due to Budget and Personnel Ceiling Constraints | NASA concurs with the recommendation; and, we fully recognize the near heroic efforts at each of our installations that have brought us within striking distance of our downsizing targets. At the beginning of fiscal year 1993, the NASA employment level was 24,900 FTE. As a result of the March 1993 Executive Order to reduce Federal Civilian FTE by 100,000, the NPR recommendations and additional OMB directed cuts in 1994, NASA received an out-year target of 20,906. Additional budget reductions occurred that required us to initiate the Zero Base Review, which was completed in 1995.The ZBR recommended an FY 2000 FTE level of 17,488. Since that time we have carefully managed an FTE reduction to a planned 18,545 FTE for FY 99 and 17,970 for FY00. Our final "go to" target is now 17,574 FTE for FY 04. Currently 7 of our 10 Centers are at or below our lowest "go to" numbers. To NASA's credit, our accomplishments were achieved without resort to the ravages of a reduction-in-force. Voluntary losses to date include in excess of 4,500 buyouts, 1,300 early outs, and more than 800 inter-center transfers. As a result of the downsizing challenges, we provided relief to the OSF Centers in the FY 00 budget process as follows: FY 99-153 FTE; FY 00-110 FTE; FY 01-103 FTE; FY 02-59 FTE; and, FY 03-68 FTE. This relief has enabled the innovative use of temporary and extended term appointments, as well as increasing the number of permanent hires available to fill critical skill positions. In addition, we are currently reviewing their request for additional relief, as identified in the recent Core Capability Assessment (CCA). OSF management has proposed several augmentation and/or hiring models that address both short and long term needs regarding replacement and enhancement of critical workforce competencies. One objective of the current CCA review is to help chart a strategy that will provide the OSF Centers with the requisite flexibility to attract and retain the core competency talent pool necessary to ensure safe mission and program success. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1061 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Computer Hardware-Software/Software |  | NASA does not yet have adequate plans for the long-term maintenance of the software development tools being used to produce the ISS software. | NASA should recognize the importance of maintaining its software development tools, plan now for how these are to be maintained over a period of decades, and provide adequate funding to support this activity. | HQ | 02/01/1998 | Maintenance of Software Development Tools | Provision for support of software development tools is provided in the ISS Sustaining Engineering Plan. Funding is also provided to maintain Ada compiler license and software support. This includes a clause requiring delivery of source code in the event of a provider decision not to support the compiler users at a later date. The GFE software is maintained by inter-organizational Technical Task Agreements (TTA's), which will be managed by the same Sustaining Engineering organization that is responsible for all ISS integrated software maintenance's and upgrades. Activity is also underway to investigate the impact of upgrading the Ada compiler to a more current design or even to consider moving away from Ada to other widely universally supported languages, as a part of the ISS Pre-planned Production Improvement activity. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1063 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Caution and Warning (C&W)/Systems Engineering |  | Although considerable progress has been made during this past year in ISS Caution and Warning (C&W) system design, systems engineering is still not sufficiently evident in the whole spectrum of alarm and warning, situation assessment, and damage control and repair. | Initiate a high-priority systems engineering review of the C&W system to define a path for development and implementation of fully integrated alarm, situation assessment, countermeasure functions, and crew actions. Finalize and document C&W system design requirements. | HQ | 02/01/1998 | Lack of Systems Engineering in ISS Caution and Warning (C&W) System Design | The ISS Program concurs with these concerns and has instituted a C&W Systems Integration Team (CWSIT) to provide direction and management of all C&W development activities, design reviews, C&W display development, event definition, and International Partner (IP) integration. Since the last ASAP review, the strength of the CWSIT has grown substantially. Four dedicated engineers were added to support systems engineering, design development, and verification activities. These engineers add to the existing team of mission operations, flight crew, Program Office, sub-system representatives, human factors, safety, and independent assessment representatives and meet at least weekly to ensure integration of the C&W system, procedures, and display and controls. To finalize system engineering and integration associated with the C&W system design requirements, response procedure development, and display and controls design, the CWSIT conducted a program wide C&W System Integration Review (SIR). The C&W SIR was held between October and December of 1997, and included participants from across the Program and International Partner Communities. This review consisted of two phases, one geared specifically towards SSP 50005, Flight Crew Integration Standards, and another dedicated to identifying integration and design issues within the fault detection, isolation, and recovery display development, audio interfaces, flight rules/procedures, and IP development areas. The C&W review resulted in a total of 35 issues requiring resolution. These issues ranged from editorial comments against the C&W Description Document to the identification of Russian audio interface concerns, Japanese Experiment Module C&W Panel Latencies, requirements modifications, and needed display design changes. The finalized C&W system requirements are documented and controlled within the formal ISS configuration managed specification hierarchy, and any modification, waiver, or deviation requires official Program direction. The CWSIT, which has oversight and extensive involvement with the class 1/emergency procedures, has developed and retains ownership of the classification guidelines/requirements, and maintains control of these requirements through the C&W Working Group. The actual procedure development is assigned to the Mission Operations Directorate (MOD), who is responsible for the particular system, under the direction of the MOD management and Joint Operations Panel. The CWSIT has briefed the development organizations on the general philosophy of the class 1/2/3 procedures required for C&W. In addition, the CWSIT reviews all changes to the class 2/3 procedures after they are placed under configuration control. The integration of C&W event response procedures is ensured across the program by the CWSIT and its constituent MOD, Crew Office, and program sub-system representatives. The situation response and damage control procedures are included in the baselined and configuration managed ISS Mission Rules and Procedures. These flight procedures are integrated into the overall display development and design modification processes currently in work. The Boeing developed Matrix-X C&W simulator has been brought on-line and is providing simulation support to the program as well as providing a data driven display assessment environment. This simulator has already provided much needed integration support to requirements and design development and is now geared towards supporting procedure development and crew training. The simulator has been instrumental in the performance of integrated crew reviews of both flight 2A procedures and display architectures. The use of this simulator in conjunction with the Flight Crew Training Division's Part Task Trainers has contributed to the development of an integrated, productive, and safe C&W system. The ISSP will continue its support of the CWSIT and ensure that increased levels of attention are maintained to provide a safe, integrated, and operationally viable C&W system. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1062 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Computer Hardware-Software/Software |  | The ISS software development schedule is almost impossibly tight. If something else does not cause a further delay in ISS deployment, software development may very well do so. The decision this year to add integrated testing of some modules at KSC is a very positive step for safety. However, there is no room in the schedule for required changes that may be discovered during this testing. | NASA should realistically reevaluate the achievable ISS software development and test schedule and be willing to delay the ISS deployment if necessary rather than potentially sacrificing safety. | HQ | 02/01/1998 | International Space Station (ISS) Software Development Schedule | The Program has established an aggressive activity to integrate developer schedules with need dates (including training as well as test). Schedules are difficult but proving to be achievable. Any disconnect, whether it is schedule or content, is tracked and worked through the Program's formal decision process on a daily basis. Staffing is reviewed weekly and will be sustained to meet commitments. Additional independent verification and validation and software assurance support has been added. The program is firmly committed to our test plans and will make the appropriate schedule adjustments to maintain these plans. The recently approved Revision D to the ISS assembly sequence provides additional schedule flexibility to accomplish all testing and software activities. Finally, the program will not commit to flight until the software has been adequately tested. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/14/2001
1050 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Reusable Solid Rocket Motor (RSRM)/Flight Support Motor (FSM) |  | Obsolescence changes to the RSRM processes, materials, and hardware are continuous because of changing regulations and other issues impacting RSRM suppliers. It is extremely prudent to qualify all changes in timely, large-scale Flight Support Motor (FSM) firings prior to produce/ship/fly. NASA has recently reverted from its planned 12-month FSM firing interval to tests on 18-month intervals. | Potential safety risks outweigh the small amount of money that might be saved by scheduling the FSM motor tests at 18-month intervals rather than 12 months. NASA should realistically reassess the test intervals for FSM static test firings to ensure that they are sufficiently frequent to qualify, prior to motor flight, the continuing large number of materials, process, and hardware changes. | HQ | 02/01/1998 | Flight Support Motor (FSM) Test Intervals | Evaluation of all known reusable solid rocket motor (RSRM) future material, process, and hardware changes (by NASA and Thiokol) has confirmed no safety risk impact resulting from FSM static tests every 18 months, in lieu of every 12 months. The RSRM Project goal to "include all changes in a static test prior to flight incorporation" has not changed, and any exceptions will continue to be approved by the Space Shuttle Program Manager before flight incorporation. If a change is planned in the future wherein an 18-month FSM static test frequency is insufficient to support qualification prior to motor flight, program funding requirements will be considered to accelerate an FSM static test to ensure no increased program flight safety risk. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/13/2001
1048 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/External Tank (ET)/Super Light Weight Tank (SLWT) |  | The Super Light Weight Tank (SLWT) has completed its design certification review, and proof tests on the first tank have been satisfactorily passed. The only remaining test to complete certification on the SLWT is the cryogenic loading test that will be run on the first production tank on the launch pad. The diligent attention that has been given to quality control, particularly to material inspection and weld integrity, has made this program successful. | NASA should ensure that the current manufacturing and quality control procedures continue to be rigidly adhered to and conscientiously followed in production. | HQ | 02/01/1998 | Certification of the Super Light Weight Tank (SLWT) | NASA concurs with this recommendation. MSFC and Lockheed Martin Michoud Space Systems (LMMSS), the External Tank prime contractor, periodically perform a NASA Engineering and Quality Audit (NEQA), which focuses on both the processes and the flight hardware. The audit is conducted by experienced MSFC and LMMSS technical and management personnel and the operators and inspectors that actually utilize those processes. LMMSS also performs internal and supplier audits throughout the year. In addition, on-site MSFC Science and Engineering, Safety and Mission Assurance, and DCMC personnel provide continuous insight and guidance through surveillance and limited oversight activities. Finally, adherence to manufacturing and quality control procedures is one of the primary focuses of the on-site government personnel. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/13/2001
1047 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | The reduction of Government Mandatory Inspection Points (GMIPs) at KSC has significantly lagged the downsizing of NASA quality personnel responsible for processing these GMIPs. This has resulted in an expanded workload among remaining NASA quality inspectors and made it more difficult to conduct analyses needed to identify further GMIP reductions. There has been a similar reduction of NASA safety inspectors and engineers at KSC without a commensurate reduction in over-sight requirements while, at the same time, the addition of new safety audit or insight responsibilities has taken place. | Any downsizing of personnel by both NASA and Shuttle Processing Contract (SPC) should be preceded by the reduction of commensurate workload associated with Space Shuttle processing, such as reduction of GMIPs and NASA safety inspections. | HQ | 02/01/1998 | Reduction of Government Mandatory Inspection Points (GMIPs) | NASA concurs with the recommended approach of reducing the workload in Space Shuttle processing before proceeding with downsizing NASA and SPC personnel; however, we have not been as successful in this area as desired. In the downsizing effort implemented in February 1998, SPC experienced an unexpectedly high level of voluntary attrition in certain critical functions-an outcome that was predicted by ASAP members and others. Although SPC experienced shortages of critical skills and staffing to minimum levels for short periods of time in selected areas, SPC and NASA worked together to overcome these deficits and assure that the scheduled missions through STS-91 were safely executed. This was done by a combination of launch schedule relief, back-filling SPC shortages with NASA expertise, and re-hiring technical expertise to train and certify SPC staff, thus eliminating shortages in critical skills. Evaluation of GMIPs for potential elimination by process engineering and quality engineering staff continues. It is estimated that approximately 6,000 of the original 22,000 GMIPs will remain in place at the end of this effort. This is a level assessed as commensurate with the current NASA quality inspection workforce. NASA Headquarters Office of Safety and Mission Assurance (OSMA) continues to evaluate the situation at KSC regarding NASA and SPC workforce reductions by assessing process efficiencies and workload indicators. Indicators of process effectiveness include overtime rates and first-time quality rates. Although the efforts are not yet complete, OSMA anticipates that as GMIPs are reduced overtime rates for NASA quality inspections will drop. Additionally, if the development of process efficiency initiatives by SPC are effective, then, when implemented, OSMA anticipates that SPC engineering and technician overtime rates will drop and first-time quality rates, based on NASA surveillance sampling, will increase. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/13/2001
1049 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/External Tank (ET)/Super Light Weight Tank (SLWT) |  | The design requirements for the SLWT include operating with a maximum Space Shuttle Main Engine (SSME) power of only 106%, even at abort conditions. The Space Shuttle program has approved a baseline plan to examine the possibility of certifying the Space Shuttle for intact aborts at a 109% SSME power setting. | NASA should complete its evaluation of a 109% power setting for intact aborts as soon as practicable and reevaluate the ability of the SLWT to accommodate this higher power setting. | HQ | 02/01/1998 | Increased Space Shuttle Main Engine (SSME) Power Setting for Intact Aborts | NASA concurs with the ASAP recommendation. Specific evaluations with regards to orbiter and SLWT have already been completed or are near completion. The Block II Space Shuttle main engine (SSME) certification program will provide the capability for intact abort at 109 percent power level. This certification program is planned to be complete by October 1, 1998. A change request to baseline the 109 percent intact abort loads and thermal environments shall be released by the end of 1998 following completion of Block II SSME 109 percent certification. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/13/2001
1044 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Structured Surveillance |  | The Kennedy Space Center (KSC) has been successfully phasing in the structured surveillance process for safety and quality for some time. The development of metrics using structured surveillance information has lagged data collection. | KSC should continue to expand the use of structured surveillance and to focus effort on the development of valid and reliable metrics to assess program performance from structured surveillance results. | HQ | 02/01/1998 | Implementation of Structured Surveillance | We concur. The development of reliable metrics with which to measure performance of the SFOC in all areas including safety and quality is progressing at KSC. There are several examples of this. At KSC, NASA Safety has developed a data base for the Space Shuttle Program, revised its surveillance approach, and developed a method by which proper measurements can be evaluated and analyzed in determining safety program management effectiveness and contractual statement of work compliance. These new metrics will enable NASA Safety to more effectively measure contractor performance. The Quality Surveillance Record data base is currently being modified to clarify the method by which deficiencies and observations are counted and to better define failure codes and other data collected. These changes will increase the reliability of the data used to assess program performance and will be implemented in early July. In the interim, the existing data base has been modified and focuses on surveillance data collection for tasks which GMIP's were deleted through the GMIP reduction efforts. KSC has developed an expanded surveillance system that will provide extensive insight into the contractor's overall operation by process analysis. The process analysis program was initiated in October 1997, and there are presently 11 Quality Process Analysts working the pilot program at KSC. This system will provide added insight into the contractor's processes, procedures, and policies. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/13/2001
1046 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | To compensate for skills deficiencies related to staff departures from KSC, both NASA and SPC are making extensive use of cross-training of personnel, both technicians and engineers. Individuals who have been cross-trained also should have recent "hands-on" experience before they undertake a cross-trained task. | NASA and SPC should develop and use valid and reliable measures of the readiness of personnel to take on tasks for which they have been trained but on which they have only limited or episodic experience. The cross-training program could include a regularly scheduled rotation of duties so that the multiply trained individual has the opportunity to employ all of the acquired skills and knowledge at appropriate intervals. | HQ | 02/01/1998 | Experience Level Before Cross-Training of NASA and Shuttle Processing Contract (SPC) Personnel | NASA is in full agreement with the Panel's position that individuals who have been cross-trained also should have recent hands-on experience before performing tasks. The combined NASA/SPC training and certification plan identifies those skills that require hands-on training as part of the certification process. Personnel selected for cross-training are required to be certified to perform other jobs in the same family of skills (i.e., mechanical systems, avionics systems, electrical distribution systems). With this knowledge base, those identified for cross-training will be required to meet the same training and performance requirements established for the given task. Performance is measured to verify that the individual has obtained the stated objectives of the instructional tool being used. In the case of hands-on training, the employee is required to demonstrate 100% command of the task being performed. The certification process is controlled by the KSC Certification Board, which operates under approved certification procedures. The Certification Board, chaired by the SPC S&MA Director at KSC, approves and implements certification/ recertification requirements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/13/2001
1043 | Artrip, Chris - 0000000000 : NO@ADDRESS.GIVEN | Artrip, Chris - 0000000000 : NO@ADDRESS.GIVEN |  | Construction Site Safety, Electrical Shock |  | Do not allow work to be performed on energized electrical equipment. | Require Activity Hazard Analysis for all tasks. Require Utilities outage request/Permit before working on electrical facilities. Do not allow employees to work on energized equipment. Conduct daily construction-site safety meetings. Ensure proper training of employees. 5. Ensure employees use proper tools and require proper PPE as well as follow NASA safety processes in place for electrical work. | AFRC | 07/26/2001 | A contractor employee was working on an energized electrical sub-panel.(480v) While removing cover from above the busses the employee dropped the cover shorting out the busses. An arch and flash occurred slightly burning the employee's hands. The main breaker tripped causing an uncontrolled shutdown of the equipment. The interior of the panel was damaged requiring replacement of interior parts. |  | N/A |  |  | Public | Not Specified |  | 12/13/2001
1040 | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN |  | Dimensional stability of dissimilar materials in operational and non-operational environments where excessive or unintentional heating may occur |  | The effect of operational and non-operational environments on seal dimensions must be anticipated. This is especially true for dissimilar materials subjected to excessive and unintentional sources of heat, or materials whose physical or mechanical properties may be altered, even reversibly, during service. | Since the coefficients of thermal expansion of plastics and metals differ by an order of magnitude, preventing unwanted seal extrusion entails implementation of appropriate engineering rather than materials approaches. For example, more effective seal entrapment design strategies could be implemented (for example, use grooved or barbed retainer surfaces, or different seal cavity entrapment geometries). Alternatively, the time at temperature during the seal's service lifetime could be minimized. Unwanted seal recession could also be prevented by optimal seal preform geometry and use of lower process temperatures. | WSTF | 08/21/2001 | In order to mitigate pilot seal extrusion-related failures of the Primary Reaction Control System (PRCS) pilot-operated valve (POV), effort were made to develop a redesigned POV (RPOV) pilot seat assembly. The POV controls the flow of hypergolic liquid propellants to the Space Shuttle Orbiter attitude control thrusters. During the redesign, specific factors were found to be essential in fabricating a dimensionally stable pilot seal. Seal Extrusion. Seal extrusion (Figure 1) is caused by thermal expansion mismatch between adjacent PTFE and metal parts in the POV or RPOV, and is potentially aggravated by: excessive internal stress or internal stress gradients in as-fabricated pilot seals low seal exit area relative to entrapped seal volume thermal cycling during seat assembly (e.g., retainer welding) vacuum bake-outs during periodic thruster maintenance heat soak-back after thruster firing, especially multiple sequential burns or long burns any presence of oxidizer vapor close to a fuel pilot seal Data on semi-trapped PTFE specimens simulating a POV seal configuration show that extrusion is: incremental and irreversible increases with the size of the thermal excursion decreases with successive thermal cycling (stress relief) is accompanied by gap formation in the seal cavity The above factors must be considered when developing a viable pilot seal. [D] Figure 1. Impression replica profiles of an extruded Shuttle Orbiter PRCS POV pilot seal (left) and an unextruded, unused POV pilot seal (right) (63 ´ magnification) Seal Recession. Seal recession (Figure 2) is characterized by a loss of seal proud height around the circumference of the seal. Recession deprives the sealing interface of material thus leading to possible leakage. Recession arises from negative internal stress during differential thermal contraction of seal and surrounding metal. Although recession was observed after valve level acceptance testing of RPOVs, it is conceivable that recession could also be caused by overheating during fabrication, or use of too small of a PTFE preform. [D] Figure 2. A sectioned RPOV pilot seat assembly showing seal recession (within boxed region) after initial valve level acceptance testing. The seal has receded into the cavity by approximately 0.050 mm (0.002 in.). PTFE Susceptibility to Oxidizer. When exposed to oxidizer (dinitrogen tetroxide), PTFE undergoes significant yet reversible changes in mass, hardness, density, and crystallinity [1]. The effect of fuel (monomethylhydrazine) on PTFE properties is negligible by comparison (Figure 3). [D] Figure 3. Mass uptake and desorption data for PFTE Teflon 7A exposed to liquid oxidizer (solid symbols) and fuel (open symbols). Reference: Pasternak, R. A., Christensen, M. V., Heller, J., Macromolecules, 3, 366 (1970). |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/12/2001
1042 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | Operations and processing in accordance with the Shuttle Processing Contract (SPC) have been satisfactory. Nevertheless, lingering concerns include: the danger of not keeping foremost the overarching goal of safety before schedule before cost; the tendency in a success-oriented environment to overlook the need for continued fostering of frank and open discussion; the press of budget inhibiting the maintenance of a well-trained NASA presence on the work floor; and the difficulty of a continued cooperative search for the most meaningful measures of operations and processing effectiveness. | 1a. Both NASA and the SPC contractor should reaffirm at frequent intervals the dedication to safety before schedule before cost. 1b. NASA should develop and promulgate training and career paths leading to qualification for senior NASA Space Shuttle management positions. 1c. NASA should continue to ensure that a trained and qualified Government personnel presence is maintained on the work floor. 1d. NASA and SPC should continue to search for, develop, test, and establish the most meaningful measures of operations and processing effectiveness possible. | HQ | 02/01/1998 | Implementation of the Shuttle Processing Contract (SPC) | 1a. The Space Shuttle Program concurs with the ASAP affirmation that safety is our first priority. The potential for safety impacts as a result of restructuring and downsizing are recognized by NASA at every level. From the Administrator down there is the communication of and the commitment to the policy that safety is the most important factor to be considered in our execution of the program and that restructuring and downsizing efforts are to recognize this policy and solicit and support a zero tolerance position for safety impacts. The restructuring efforts across the Program in pursuit of efficiencies which might allow downsizing of the workforce consistently stress that such efficiencies must be enabled by identification and implementation of better ways to accomplish the necessary work, or the unanimous agreement that the work is no longer necessary, but that in either case that the safety of the operations are preserved. In the case of the restructuring and downsizing enabled by the SPC transition of some responsibility and tasks to the contractor, the transition plans for these processes and tasks specifically address the safety implications of the transition. Additionally, the Program has required the NASA Safety and Mission Assurance (S&MA) organizations to review and concur on the transition plans as an added assurance. Other Program downsizing efforts have similar emphasis embedded in the definition and implementation of their restructuring, and the S&MA organizations are similarly committed as a normal function of their institutional and programmatic oversight to assure this focus is not compromised. Additionally, the Program priorities of 1) fly safely, 2) meet the manifest, 3) improve mission supportability, and 4) reduce cost are incorporated into almost every facet of planning and communication within both the NASA and contractor execution of the Program. Besides the continuous presentation of these priorities in employee awareness media, the Program highlights their relative order in the formal consideration of design and/or process changes being considered by the various Program control boards. Additionally, these priorities are the focus point for most of the Program management forums such as the Program Management Reviews and SPC Contract Management Reviews (CMR's). They are specified as the basis for the Program Strategic Plan, as well as the SPC goals and objectives used by the contractor and NASA to manage and monitor the success of the SPC. Finally, these priorities are embedded in the SPC award fee process (which provides for four formal reviews each year). Specifically, the award fee criteria provide for both safety and overall performance gates which, if not met by the contractor, would result in loss of any potential cost reduction share by the contractor. In summary, NASA and all of the contractors supporting the Space Shuttle Program have always been and remain committed to assuring that safety is of the highest priority in every facet of the Program operation. While downsizing does increase the challenge of management to execute a successful Program, process changes, design modifications, employee skills maintenance, and reorganizations are all part of the management challenges to be faced and resolved, and maintenance of the high level of attention to safety in resolving these challenges is recognized by NASA and the contractors alike as not being subject to compromise. 1b. While it is true that the roles for NASA management and technical personnel are being reduced in number and reshaped to focus on the critical areas of anomalies and changes, these roles and the ongoing role of assessing the contractor's performance against the contract and Program requirements should provide a continued source of trained and capable future NASA senior managers. NASA has an active commitment to development of the skills for senior managers for all functional areas of the Agency, and Space Shuttle Program senior managers are generally products of both their in-line experiences as well as these career development programs. It is anticipated at this time that the roles for NASA personnel and the career development programs which have served NASA well to this point will be sufficient to assure a continuation of highly qualified and capable senior managers in the future. Given the nature of the still evolving definition of the NASA and prime contractor roles and responsibilities for the SPC operational model, it is reasonable to provide special attention to this concern, and the Program will ensure that specific consideration is given to this concern in the transition plans being developed and implemented by the functional and institutional organizations across the Program. 1c. NASA/KSC has maintained a physical presence on the work floor since the beginning of the Shuttle Processing Contract and will continue this presence for SPC, Payload Ground Operations Contract, and Base Operations Contract. NASA engineering, operations, safety, and quality personnel maintain a surveillance and audit presence of overall operations for insight purposes and are formally involved for selected tasks being performed. Presence on the floor monitoring hazardous or safety critical operations has been maintained through the transition to performance based contracting and will be maintained in the future. The frequency and depth of the insight and presence may be adjusted as justified by the results of the contractor's performance, but the value of these checks and balances has long been recognized by NASA and will be maintained. To a lesser degree, this same floor presence is executed at production sites through Resident Office presence and periodic audit and surveillance activities by NASA Center personnel. While there is a focused initiative to minimize Government mandatory inspection points (GMIP's) across the Program, it is mutually recognized by NASA that the criticality of some checks and balances in critical processes demands that some small percentage (10-15 percent) will be maintained on the production and processing floors. This presence also supports the desired training and qualification needs for NASA to remain a smart customer. Finally, there are functional roles anticipated for continued NASA participation, such as flight controllers, astronauts, and launch directors which will also provide a significant avenue for NASA skills maintenance in the long-term management model. 1d. NASA recognize the value of meaningful measures of the operational and processing effectiveness for the Program and continually strive to evolve and improve on the measures currently in place. The SPC Performance Measurement System (PMS) has been a significant development project since the beginning of the contract, continues to take shape as the primary repository for the performance metrics, which provide management insight into the cost, and technical performance across the complete contract. Once the system is complete and populated with viable metrics, NASA will validate the system. The goal is to complete the validation by the fall of 1998. Key metrics are reviewed quarterly at the SPC CMR, and individual functional areas such as flight operations and ground processing use these on a continual basis for their management execution and insight. Additional measures are continually developed at the Program level and within individual functional areas to enhance the understanding of performance trends, and when proven to be effective management tools, these metrics roll into the PMS and/or other forums and products used to manage the Program. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/12/2001
1041 | Goss, Robert - 0000000000 : NO@ADDRESS.GIVEN | Goss, Robert - 0000000000 : NO@ADDRESS.GIVEN |  | Gravity Probe-B Nitrogen Contamination Mishap Investigation Final Report |  | All operations and modifications to flight hardware and its interfacing GSE should always have comprehensive and well reviewed written procedures. Schedule pressure can cause even top performers to make mistakes and/or take short cuts. Gas K-bottles or other sources of gases should be readily identifiable in safety critical and contamination critical programs. Gases should be positively verified in safety critical and contamination critical programs. Gases should be segregated by species. Controls should be in place to avoid inadvertently placing a different gas in a rack or storage location designated for another species of gas. All personnel supervising or writing procedures for transportation activities should be trained on DOT HAZMAT regulations. In addition to the need for a positive identification of gases, the traceability and accountability must be maintained to ensure that no changes have occurred. Lessons learned should be widely disseminated and appropriate follow-through on appropriate actions from the lessons must occur. It is important to maintain configuration control on GSE that interfaces with flight hardware and diligently verify its configuration and functions, especially if repairs or modifications are being incorporated. A single integrated procedure should be used when multiple simultaneous operations are occurring in order to establish clear lines of authority. Ensure safety and minimize distractions and concerns of the participants. Contamination plans and control should be thorough and consider all sources of contamination including using the incorrect materials and gases. MIPs should be utilized to ensure success in executing the procedures and not be viewed as hindrances to completing the tasks. All program and project offices should be familiar with the NASA Mishap Notification process and requirements, and also with initial actions necessary to preserve evidence (including independence of witness statements). | The Board's principal findings and recommendations are: DOMINANT ROOT CAUSES: Finding: The GP-B Cryo Team (Stanford University Cryogenics Team) performed the supply connect and disconnect operations on the flight hardware and its interfacing ground support equipment (GSE) without a written procedure or checklist. Recommendation: Train employees on the significance of documented procedures. Require the use of comprehensive and well-reviewed procedures and checklists. Finding: The work schedule pressure caused some individuals to be overworked. Recommendation: Review manpower, work schedules, and limit overtime. Ensure the project schedule is reasonable. CONTRIBUTING CAUSES: Finding: The K-bottles of gases are not color coded for different gases. Recommendation: Develop a method of uniquely identifying K-bottles by gas species and consider using unique fittings for different types of gas systems. Finding: The individual connecting the GN2 K-bottle to the flight hardware exhibited complacency when he failed to look at the label on the K-bottle prior to connection and when he tagged the K-bottle for pick up earlier in the move sequence. Recommendation: Provide training to all Integration and Test (I&T) personnel to verify gas type, inspect for cleanliness, check grade, and document the activity and results during any operation that involves the flight article. Finding: Department of Transportation (DOT) Hazardous Materials (HAZMAT) regulations were not met. Recommendation: Provide training for appropriate individuals on DOT HAZMAT regulations and shipping documents. Finding: SU identification, traceability, and accountability of gas K-bottles are inadequate. Recommendation: Improve the identification of gases and the control and traceability by requiring appropriate identifying paperwork to accompany all fluid supplies and by providing a segregated and labeled storage area for different types of gases. More detailed recommendations may be found in the complete board report which is included with this lesson learned. | MSFC | 10/15/2001 | At approximately 10:30 a.m. on August 26, 2001, gaseous nitrogen (GN2) was erroneously connected to the Gravity Probe-B (GP-B) guard tank vent line as the GP-B Science Payload (Figure 1) was readied for transport from Stanford University (SU) to Lockheed Martin (LM) in Palo Alto, California. At approximately 2:30 p.m. (after the GP-B Science Payload arrived at LM), the error was recognized and the GN2 was disconnected. Gaseous helium (GHe) was the intended gas to be connected instead of GN2. Since the guard tank is at a much lower temperature than the freezing point of GN2, concerns arose over the possible detrimental effects of frozen nitrogen (N2) in the vent line and/or the guard tank itself. The purpose of the move was to transfer the GP-B Science Payload from SU to LM for later integration with the spacecraft. The move was uneventful except for the discovery of the connection of the incorrect gas to the guard tank. The immediate cause of the incident was the inadvertent connection of the GN2 to the guard tank instead of utilizing the required GHe. A procedure to check the guard tank vent line impedance was executed on September 15, 2001. The data showed significant but not total blockage of the vent line with frozen N2. The procedure added heat to the guard tank and flowed gas through the vent line until there was no further indication of N2 in the tank or line. There is no reason to believe that damage to the hardware had occurred since the vent line was only partially blocked. There was an impact on the schedule due to the recovery time, and there will be an associated cost based on the schedule impact. |  | N/A |  | Science | Public | Not Specified |  | 12/12/2001
1039 | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN |  | Limitations of material procurement specifications in polytetrafluoroethylene (PTFE) resin selection |  | The criticality of understanding unique PTFE properties that derive from subtle resin differences can not be underestimated. Additional tests must be performed to distinguish between candidate resins, and to ensure that required properties not covered by available specifications are met. Materials selection criteria must be constantly re-evaluated to ensure that all key properties are addressed in new applications. Proper resin selection also was found to partially compensate for an unoptimized seal design. Given the nature of the hot-forming assembly process used, the material with the highest resistance to compressive fracturing should have been chosen initially. Switching from a free-flowing extrusion grade to a nonfree-flowing compression-molding grade of PTFE allowed fabrication of viable seals suitable for valve level testing. | Perform comprehensive research and testing prior to manufacturing parts for unique operational environments. Develop more informative tests such as a squeeze test to better differentiate between candidate resins. | WSTF | 08/21/2001 | In order to mitigate seal extrusion-related failures in the Primary Reaction Control System (PRCS) pilot-operated valve (POV), an effort was undertaken to develop a redesigned POV (RPOV) pilot seat assembly. The POV controls the flow of hypergolic liquid propellants to the Space Shuttle Orbiter attitude control thrusters. Specifications and selection assistance from suppliers were found to be inadequate for choosing an appropriate grade of PTFE for seal material without further testing. The two PTFE resins under consideration had similar properties per current material procurement specifications. For example, the dimensional stability, tensile strength, and percent elongation requirements were virtually the same. Meaningful properties such as dimensional stability under load (creep), retention of properties at higher operational temperatures, and chemical resistance to propellants were not covered. Resin selection design assistance from commercial resin suppliers for specific applications such as a thruster valve seal was found to be lacking. Resin candidates were also hard to distinguish by most laboratory tests, but each candidate was later found to exhibit unique physical and mechanical properties that made the difference between fabricating a viable versus non-viable seal. Initial RPOV seal fabrication efforts focused on using a pre-sintered, free-flowing extrusion molding PTFE grade per AMS 3658 [1], sold under the trademark of Algoflon(r)-E2 [2]. Seals made from Algoflon-E2 exhibited significant splotchiness, microcracking, and fibrillation after the hot-forming assembly process and seal recession after valve testing. To resolve these issues, an as-sintered, non-free-flowing compression molding PTFE per AMS 3660 [3], sold under the trademark of Teflon(r)-7A [4], was used. [D] Figure 1. Redesigned pilot seal showing overall splotchy appearance and fibrillation around seal id and od after trimming Given the limited utility of material procurement specifications, a squeeze test which allowed the compressive strain to be varied from 15 to 90 percent was devised to better differentiate between resins. Specimens made from the pre-sintered, free-flowing Algoflon-E2 resin produced a lower strength PTFE that was more susceptible to fracturing (Figure 2, bottom). Since Algoflon-E2 consists of coarse, agglomerated particles, fracturing was attributed to adhesive failure along resin particle boundaries. By comparison, a specimen made from the as-sintered, non-free-flowing resin gradually transitioned from fully opaque to translucent material without any evidence of fracturing or splotchiness. [D] Figure 2. Polytetrafluoroethylene squeeze test specimens: Teflon-7A (top, 1 piece) and Algoflon-E2 (bottom, 2 pieces). Notice the fracturing in the Algoflon-E2 specimens. References: Aerospace Material Specification 3658, Revision C. Polytetrafluoroethylene Extrusions, Premium Strength, Sintered and Stress-Relieved Radiographically Inspected. Society of Aerospace Engineers, Warrendale, PA, July 1993. Algoflon(r) is a registered trademark of Ausimont Montedison Group, Milan, Italy. Aerospace Material Specification 3660, Revision C. Polytetrafluoroethylene (PTFE) Moldings, General Purpose Grade, As Sintered. Society of Aerospace Engineers, Warrendale, PA, February 1994. Teflon(r) is a registered trademark of E. I. DuPont and Nemours and Company, Wilmington, DE. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/12/2001
1038 | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN |  | Optimized pre-forming of thermoplastic polymer parts |  | Pre-forming of piece parts made from thermoplastic polymers requires special care. Geometrical design criteria must not take precedence over polymer property limitations. For example, never exceed the elastic limit of a polymer unless some property degradation can be tolerated. Also, preclude fabrication of nonviable parts by anticipating adverse consequences of poorly optimized preform size and shape. | When designing with PTFE, the tendency of PTFE to undergo creep and cold flow must be considered. While a positive interference fit is necessary to avoid gap formation and seal recession in semitrapped seals, the interference fit should remain close to the elastic limit of PTFE so that key mechanical properties are not changed irreversibly. The use of smaller, properly proportioned preforms may benefit long-term seal performance by reducing the magnitude and gradient of internal stress, and thus minimizing the tendency of seals to extrude. Internal stress could be further minimized by a slower strain rate when tightening down on the retainer via the hot-forming fixture during seat assembly, or by post-assembly annealing. | WSTF | 08/21/2001 | The Primary Reaction Control System (PRCS) pilot-operated valve (POV) controls the flow of hypergolic liquid propellants, nitrogen tetroxide (oxidizer) and monomethylhydrazine (fuel), to the Space Shuttle Orbiter attitude control thrusters. The POV has experienced numerous in-flight and ground turnaround failures, including leakage and failure to open upon command. Corrosion in the oxidizer valves and seal extrusion in the fuel valves have been linked to most of these failures. The desire to mitigate corrosion and seal extrusion led to an effort to develop a redesigned POV (RPOV) pilot seat assembly. Preform Size. Semitrapped PTFE seals, such as the PRCS POV pilot seal, will undergo coldflow during service [1]. This phenomenon can help to replenish lost material at a sealing interface or heal seal imperfections [2]. However, if the preform used during fabrication is too small, gaps may form in the seal cavity during fabrication that will cause the seal to recede into the seal cavity during qualification testing or service, causing loss of seal-to-poppet contact and ultimately leakage. Conversely, if the preform is too large, the compressive yield point of the PTFE can be exceeded during interference fitting of adjacent metal and plastic parts, resulting in irreversible plastic deformation and associated property loss. In general, the compressive yield strain of thermoplastic polymers such as PTFE is of the order of several percent. The interference fit used during initial attempts to fabricate a RPOV pilot seal (17 to 26 percent) exceeded the yield point of PTFE by a factor of about 5 to 7, resulting in the formation of translucent PTFE in regions of highest internal stress (Figure 1). [D] Figure 1. Sectioned initial attempt RPOV seal made with Algoflon E-2 polytetrafluoroethylene showing translucent (plastically deformed) and opaque regions (normal appearance). By comparison, the interference fit used in POV and final RPOV pilot seal fabrication (7 percent) exceeded the yield point of PTFE by a factor of about 2. The use of an overly large seal preform can have another adverse consequence. Excessively oversized preforms give rise to higher levels internal stress within semitrapped parts. This frozen-in-stress will relieve over time or during thermal cycling, and could be manifested as unacceptable extrusion during service. Preform Shape. If the preform is shaped incorrectly relative to the metal cavity dimensions (producing non-uniform squeeze within the seal), an internal stress gradient within the semitrapped PTFE seal can result. Depending on the magnitude and direction of the gradient, either recession or extrusion of the seal could result. The use of correctly shaped seal preforms that minimize the squeeze gradient within the seal is recommended. This could be accomplished in the RPOV by maintaining equivalent radial and axial seal squeezes during fabrication. Exit Area/Volume Ratio. A lower seal exit area/entrapped seal volume (A/V) ratio was present in the initial and final RPOV designs (A/V = 0.22 mm-1) compared to original POV design (A/V = 0.35 mm-1). A differential expansion model for an annular, semitrapped seal like that in a POV configuration showed that twofold reduction in the A/V ratio will result in double the extrusion during heating [3]. Therefore, the highest practical A/V ratio should be used in semitrapped seal design. Unoptimized Design Consequences. Evidence of undesirable structural and morphological changes was obtained during initial RPOV seal fabrication. Machined PTFE seals had a mottled, splotchy appearance in areas where the greatest amount of seal squeeze had occurred. This material was especially prone to fracturing and fibrillation during trimming. Subsequent sectioning of the seat assembly revealed PTFE material with a translucent appearance in the region of highest interference fit, while the remaining material in the seal retained a normal opaque appearance (Figure 1). One factor thought to be responsible for the formation of the translucent material was excessive shearing accompanied by irreversible property loss. Evidence of irreversible property loss was supported by decreasing Shore durometer hardness of PTFE test coupons with increasing squeeze (percent strain) (Figure 2). Hardness reductions in semicrystalline thermoplastics such as PTFE are generally regarded as indicative of irreversible deformation modes within crystalline lamellae involving chain slip and tilt at lower strains, followed by lamellar shear and crystal destruction at larger strains [4]. [D] Figure 2. Effect of increasing percent squeeze on the Shore A durometer hardness of polytetrafluoroethylene References: Singleton, K. B., Cold Facts about Cold Flow, The Journal of Teflon Reprint No. 39, DuPont and Nemours and Company, Plastics Department, Wilmington, DE. Wichmann, H., TF E Seat Evolution Report. ISC Report 90201, PO T-92270, NASA Johnson Space Center White Sands Test Facility, Las Cruces, NM, February 1999. Waller, J. M., Factors Contributing to the Extrusion of Monomethylhydrazine Pilot Operated Valve Seals, TR-WSTF-960-001, NASA-JSC White Sands Test Facility, June 1, 2000. Balta-Calleja, F., Martinez-Salazar, J., Rueda, D. R., quotHardness,quot Polymers, An Encyclopaedic Sourcebook of Engineering Properties, J. Kroschwitz, Ed., Wiley & Sons, 415, 1987. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/11/2001
1037 | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN |  | Machining of thermoplastic polymers |  | Machining of polymers such as polytetrafluoroethylene (PTFE) used in the fabrication of small piece-parts made to close tolerances presents special challenges. | Appropriate experience and tooling must be sought, and ample time allocated for practice before viable seal preforms can be machined. For example, machining of PTFE to close tolerances using a conventional lathe required spraying isopropyl alcohol (IPA) directly on the PTFE during preform fabrication and final trimming to create the final seal profile. Implementation of established machining guidelines for PFTE was also found to be essential [1]. Accurate machining of small RPOV piece-parts was further assisted by the use of a video microscope and monitor system with quotin-processquot measurement and inspection capability. Reference: Product Literature. Teflon PTFE Properties Handbook, DuPont and Nemours and Company, Specialty Polymers, Wilmington, DE, November 1992. | WSTF | 08/21/2001 | The Primary Reaction Control System (PRCS) pilot-operated valve (POV) controls the flow of hypergolic liquid propellants nitrogen tetroxide (oxidizer) and monomethylhydrazine (fuel) to the Space Shuttle Orbiter attitude control thrusters. The POV has experienced numerous in-flight and ground turnaround failures, including leakage and failure to open upon command. Corrosion in the oxidizer valves and seal extrusion in the fuel valves have been implicated in most failures. The desire to mitigate corrosion and seal extrusion led to an effort to develop a redesigned POV (RPOV) pilot seat assembly. Machining of polytetrafluoroethylene (PTFE) pre-forms for the RPOV pilot seals was found to be a demanding art requiring special tooling, support equipment, and practice. For example, the need to machine PTFE to close tolerances can be thwarted by slight temperature changes. Given the small size of the machined parts (Figure 1) and the close tolerances required (Figure 2), it was essential to see and accurately measure the article being machined. [D] Figure 1. RPOV seat assembly piece-parts (Left: MP35N seat, Middle: PTFE preform, Right: MP35N retainer) [D] Figure 2. Final RPOV seat assembly design configuration Also, proper cutting tool size, shape, material, cutting angle, nose radius, sharpening technique, cutting speed, and coolant were important considerations in obtaining desired tolerances and surface finish. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/11/2001
1036 | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN | Waller, Jess - 0000000000 : NO@ADDRESS.GIVEN |  | Prototyping does not guarantee success during build-up of flight-configuration hardware |  | Without careful consideration, 'minor' design changes to hardware and associated assembly/test fixtures (for example, material specifications, dimensional tolerances, surface finishes, assembly process variables, etc.) can greatly affect conclusions drawn from the prototype test data and even invalidate the entire prototype effort. Prototype hardware was built as a proof-of-concept and therefore was not flight representative. This approach used existing parts and yielded encouraging initial results, but the reduced level of design rigor contributed to the difficulties in subsequent fabrication. In this regard, prototyping failed to reveal subtleties in critical design features and fabrication parameters that were unique to the build-up of a flight-configuration hardware. | When developing complex hardware, every effort should be made to maximize the likeness of prototype and subsequent design configurations. If the final design configuration is known, prototype hardware should be built to closely approximate this configuration regardless of short-term cost or schedule implications. If the final design configuration is not known, every effort should be made to minimize changes to a well-performing prototype configuration. | WSTF | 08/21/2001 | The Primary Reaction Control System (PRCS) pilot-operated valve (POV) controls the flow of hypergolic liquid propellants, nitrogen tetroxide (oxidizer) and monomethylhydrazine (fuel), to the Space Shuttle Orbiter attitude control thrusters. The POV has experienced numerous in-flight and ground turnaround failures, including leakage and failure to open upon command. Corrosion in the oxidizer valves and seal extrusion in the fuel valves have been linked to most of these failures. The desire to mitigate corrosion and seal extrusion led to an effort to develop a redesigned POV (RPOV) pilot seat assembly. To streamline RPOV seat assembly fabrication, prototype seat assemblies were built using a hot-forming procedure. The hot-forming fixture is shown in Figure 1. [D] Figure 1. Prototype RPOV hot-forming fixture The hot-forming procedure consisted of the following main steps: Fabricating a slightly oversized polytetrafluoroethylene (PTFE) seal preform Installating a loosely assembled preform, retainer, and seat into the hot-forming fixture Heating of the entire assembly to 120-150 °C (250-300 °F) under load Removing the heated assembly from the oven, followed by interference fitting (squeezing) of the PTFE seal while cooling Prototype RPOV pilot seat assemblies were fabricated using scrapped POV metal parts and generic PTFE bar stock. Dimensional tolerances were also relaxed on the seal preform. This approach was thought to minimize fabrication complexity, maximize conformance to the seal cavity shape, and maximize dimensional stability of the seal over the expected thruster operating temperature range, which was well below the seal processing temperature. Success during valve-level testing of prototype RPOV seat assemblies gave early confidence in the RPOV design concept and assembly techniques. Based on this success, flight-configuration RPOV seat assemblies were then fabricated. Unfortunately, seal-related problems not revealed by prototyping hampered attempts to fabricate viable flight-configuration RPOV pilot seat assemblies. There were three instances where reduced level of design rigor during prototyping contributed to the difficulties during fabrication of flight-configuration hardware: It is suspected that the two-piece retainer and tiny screws used for securing the retainer to the seat inadvertently increased the mechanical compliance of the seal cavity. This minimized seal squeeze and mechanical deformation that ultimately produced micro-cracking and recession of the seal in flight-configuration hardware. The convenient use of uncontrolled PTFE bar stock for the prototype seals, instead of using a carefully researched PTFE grade based on consultation with materials and processing experts, delayed optimum material selection. A lack of precise strain rate control during prototype hot-forming trials, along with a design change to the prototype hot-forming fixture to accommodate the planned retainer weld, contributed to a lack of process repeatability. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/06/2001
1035 | Saulsberry, Regor - 0000000000 : NO@ADDRESS.GIVEN | Saulsberry, Regor - 0000000000 : NO@ADDRESS.GIVEN |  | Mars 2001 Risk Reduction Testing, Pyrovalve |  | When focusing on fixing one hardware problem, be careful to identify and eliminate other hardware problems which may be created by the change. Additionally, be careful to fully test every hardware change to qualify the system and ensure something has not been missed. In this scenario, new hardware was used to eliminate a known hazard but it introduced other unanticipated risks. Changing from the previous high blow-by valve to a new low blow-by valve did mitigate the risk of a pyrotechnically induced propellant explosion upon ignition. However, an increased operational reliability risk was introduced because the new valve did not have an extensive operational history. The risks were initially missed, but were ultimately identified through thorough testing and necessary modifications were made. | When focusing on fixing one hardware problem, be careful to identify and eliminate other hardware problems which may be created by the change. Fully test every hardware change to qualify the system and ensure something has not been missed. | WSTF | 08/17/2001 | A new low blow-by pyrovalve was used in place of a high blow-by pyrovalve primarily to avoid the possibility of a pyrotechnic-induced propellant explosion in a newly designed propulsion system. During blow-by testing of the new valves, one valve did not cycle when commanded. Failure analysis indicated that both initiators and the booster had fired, yet the valve did not cycle. Further investigation indicated that the booster charge was expelled from the Primer Chamber Assembly down into the ram bore. This prevented the booster can surface from opening properly (petaling) and some of the booster energy was diverted to expanding the booster can rather than fully transmitting the energy to the ram. As a result, the diminished energy transferred to the ram was inadequate to shear the tube section that opened the valve. The valve manufacturer improved booster retention by increasing an aluminum retention ring diameter to be slightly larger than the ram bore and improved the potting between the booster and housing. This improved valve configuration was then procured by the program and evaluated by typical lot acceptance testing. Subsequent testing and analysis indicated that the potting bond was not consistent, and that the booster retention ring could possibly deform, allowing displacement of the booster into the ram bore. The risk of a flight valve failing was low but still unacceptable to the project because the vehicle did not have redundant pyrovalves. The retention washer material was changed to a high strength stainless steel and the outside diameter was further increased. The potting process was also improved to form a better gas seal. Testing indicated the reliability risk had been successfully mitigated. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/06/2001
1031 | Tryon, Roy - 0000000000 : NO@ADDRESS.GIVEN | Tryon, Roy - 0000000000 : NO@ADDRESS.GIVEN |  | Construction Site Safety, Insulation Impaling Pins |  | Impaling pins present a jobsite hazard. Working around impaling pins requires extra care and proper equipment. Activity hazard analysis for all on-going work must be reviewed with ALL trades on a daily basis. | Use a more stable ladder for high work. Use a safer, more stable, roll-around scaffold when hazardous pins are present. Cut off and trim all impaling pins prior to other adjacent contract operations. Consider using other insulation support methods instead of impaling pins. Modify Specifications to include "prompt nipping, trimming and safing of projecting impaling pins." When pins are present, include impaling pin hazards in daily safety meetings and in activity hazard analysis. | AFRC | 07/20/2001 | DFRC B4822 Incident Report: A workman was on a ladder spray painting alongside a sheet metal panel wall which had previously been insulated with large continuous insulation batts. The insulation was installed on impaling pins about 1/8" x 8" long. The insulation crew had not trimmed or nipped off the excess projecting pins, leaving 2 to 3 inches projecting from the wall. The painter dropped a can or tool and he lunged to catch it. The ladder shifted abruptly. He instinctively put out his hand to steady his situation and impaled his hand on one of the projecting pins. When he pulled his hand off of the pin, he suffered profuse arterial bleeding. The medical team responded quickly, and the painter's wound was treated and bandaged at the site. The area required a blood clean-up. The workman was sent home that afternoon, but returned to work the next morning. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/05/2001
1033 | Lehman, David - 0000000000 : NO@ADDRESS.GIVEN | Lehman, David - 0000000000 : NO@ADDRESS.GIVEN |  | Controlling Risk on Cost-Capped, Schedule-Driven, Technology Validation Projects (1998) | Deep Space 1 (DS1) was a cost-capped, schedule-driven, technology validation project, designed to flight validate 12 advanced technologies that represented major breakthroughs over state-of-the-art systems. DS1 exceeded its mission success criteria, both in terms of technology demonstration and mission duration. The lesson lists 7 recommendations/success criteria for high risk, cost capped missions. | The Formulation process (Phase A/B) for a typical spacecraft project should be at least one year; it might be shorter for smaller projects as determined on a case-by-case basis. It must culminate in a review to ensure that the mission concept is sound, the requirements are well defined and acceptable, and sufficient resources are available to complete the project. Very early in the Formulation phase, define: (1) the funding profile, (2) the date the launch vehicle is needed, (3) the Level 1 requirements and success criteria, (4) the reserves strategy and (5) the partnering approach. Do not proceed with further commitments until an agreement has been reached with NASA. Also very early in the Formulation phase, define the use of new technology and its readiness, and backups for risk mitigation. Create a project team environment that forces problems to be addressed immediately as they are identified. The extensive JPL technical resources should be utilized to assist in early problem resolution. Challenge every quotnewquot or quotcreepingquot requirement. Rigorous technical evaluations of potential industrial partners must be completed. Provide adequate early funding for the chosen partner. Co-location of all project team members is a desired arrangement, but must be implemented very early in the project life cycle to achieve maximum effectiveness. | See Lesson(s) Learned. | JPL | 12/31/2000 | Deep Space 1 (DS1) was a cost-capped, schedule-driven, technology validation project, designed to flight validate 12 advanced technologies that represented major breakthroughs over state-of-the-art systems. An aerospace industry partner was originally selected to provide much of the spacecraft hardware and integration, but ultimately required significant JPL expertise and assistance. JPL was originally responsible for project management and several other elements, but assumed significant additional responsibilities. NASA Lewis (now Glenn) Research Center, through the NSTAR program provided the highest priority technology, the ion propulsion system. DS1 exceeded its mission success criteria, both in terms of technology demonstration and mission duration. In addition, it provided the first close-up spectacular views of a cometary nucleus as part of a very successful extended mission. [D] From the very beginning, the project accepted very high risk in developing and flying the mission. The accepted risk was compounded by what turned out to be insufficient schedule and funding, leading to insufficient review and oversight of several crucial processes: A lack of an early and complete review of the project to (1) assess adequacy of plans, schedule, cost, resource margins, and (2) gain a full understanding of the project's risk posture. Cost and schedule reserves that were inadequate given the many advanced technologies to be demonstrated during the mission. Level 1 requirements and mission success criteria that remained unresolved until very late in development. Accepting a formulation phase that was too short for the team to develop a good plan for implementation. A funding profile that lagged the fast-paced schedule, and caused serious inefficiencies during project start-up. This delayed early and full integration of the industrial partner into the project team. Launch vehicle selection that took too long. External influences caused too many different vehicles to be considered. Some technologies were selected for demonstration that proved too ambitious. A cost cap that was imposed early, before the selection of the payload, launch service, and mission plan was finalized. The project manager was not fully empowered. References: quotDeep Space 1 Lessons Learned,quot JPL internal presentation, David H. Lehman, December 1, 2000. quotPlan Timely Implementation of Backups In Case Breakthrough Technologies Fail to Meet Readiness Gatesquot Additional Key Words: Autonomous Navigation, Flight Qualification, Management and Planning, Technology Plan, Technology Readiness Level | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.2.2.2 (" Management Practices: Planning "), and Paragraph 5.22.1 (" Management Practices: Lessons Learned "), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 12/05/2001
1032 | Tryon, Roy - 0000000000 : NO@ADDRESS.GIVEN | Tryon, Roy - 0000000000 : NO@ADDRESS.GIVEN |  | Construction Site Safety, Sheet Metal Panels Materials Handling |  | Do not handle large materials on open exposed flightline on windy days. Even routine material handling operations can be hazardous when that activity is not well planned. | Materials with large surface areas should be handled INSIDE the shelter of the building--not outside in the wind. When working with large material items, provide a second person to help secure and control the material Include hazard awareness and mitigation measures in the daily safety meeting prior to handling large items. When a NASA safety officer (the project inspector) provides safety advice, listen and follow that advice. | AFRC | 07/20/2001 | DFRC B4823 Incident Report: An iron worker, working alone, was rolling up large sheets (4'x10') of galvanized sheet metal that had been laid down on the slab in front of an addition to a flightline building. While rolling one of the sheets into the wind, a gust of wind picked up one end of the sheet metal causing it to curl up rapidly towards the worker. A corner of the sheet slashed backward, cutting deeply into the worker's left forearm. Medical personnel arrived quickly. The wound was treated and bandaged at the site and the worker was transported to the hospital for stitches. The accident occurred on a Friday, and the ironworker recuperated over the weekend. He returned to work on Monday morning. Just prior to the accident, the project inspector advised the ironworker to roll up the metal sheets in the direction of the wind. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/05/2001
1034 | Tryon, Roy - 0000000000 : NO@ADDRESS.GIVEN | Tryon, Roy - 0000000000 : NO@ADDRESS.GIVEN |  | Construction Site Safety, Demolition Mezzanines |  | Demolition operations, especially elevated ones, present substantial hazards as well as the potential for serious injury. Small "shop" projects should not be exempted from activity hazard analysis and safety planning. | All elevated demolition operations must have thorough activity hazard analysis. Always use buddy system when conducting elevated or hazardous demolition. Never cut off a branch you are sitting if you are beyond the cut line. Provide proper temporary restraints (ropes, scaffolding, etc.) to hold up larger and heavier components until they can be lowered safely to the floor/deck below. | AFRC | 06/20/2001 | Location: DFRC/B4800 Incident Report: A facilities maintenance shop worker, working alone, was disassembling and removing an 8' high mezzanine structure decked with 4'x8' sections of steel bar grating. The support structure consisted of a bolted-up system of uni-strut columns and beams. While kneeling on a section of partially disassembled and cantilevered grating, the worker removed one bolt too many. The remaining structure collapsed. The panel the worker was kneeling on rotated about the remaining beam and then slid backwards and collapsed onto the floor. The end of the grating severely scraped the worker across his chest and forearms. The worker also suffered multiple bruises. Office workers across the hall from the collapse heard the accident and called for medical help. The medical team arrived on the scene quickly. Because of the nature of the fall and the position of the injured worker, the medical response team slowly and carefully loaded the worker onto a stretcher board. He was then transported to the hospital for examination and treatment of what turned out to be numerous painful but not life-threatening injuries. The injured worker did not return to work for several weeks. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 12/05/2001
1045 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce Certification |  | NASA Safety and Mission Assurance (S&MA) auditors at KSC overseeing operations requiring Self-Contained Atmospheric Protective Ensemble (SCAPE) are not certified for SCAPE. | In order to be in a position to conduct valid safety and quality audits of SCAPE operations, NASA should ensure that personnel involved are certified so that, when necessary, they can observe the tasks while they are performed. | HQ | 02/01/1998 | Certification of Self-Contained Atmospheric Protective Ensemble (SCAPE) Auditors | The Space Shuttle Program concurs that safety and quality audits of SCAPE operations be performed. However, KSC's position is that NASA's safety and quality personnel monitoring SCAPE tasks will not be exposed to the additional risk of SCAPE operations as personnel can accomplish monitoring tasks by observing and communicating through the audio and video capabilities of the Operational Intercommunication System and operational television (OTV). All SCAPE tasks are conducted on recorded communications channels that are monitored in the control room, and the majority of tasks are observable on the OTV system. NASA quality and safety personnel have performed those audits for several years without being SCAPE certified. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 12/03/2001
1028 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Aeronautics Research/Aviation Safety/NASA Cooperation with Other Agencies |  | NASA's aeronautics research programs aimed at increasing aviation safety are having and will continue to have a significant positive impact on both military and civil flight operations. Several of these were in cooperation with other Government agencies, such as the Federal Aviation Administration. | NASA should continue to pursue aeronautics research programs, particularly joint efforts with other agencies, that will increase the safety of air operations. | HQ | 02/01/1997 | The Positive Impact of NASA and Other Federal Agency Aeronautics Research Programs Aimed at Increasing Aviation Safety | In direct support of the White House Commission on Aviation Safety and Security, NASA has begun a major safety research initiative in partnership with the FAA, DoD, the National Weather Service, and the aviation industry. NASA will invest up to a half billion dollars over the next 5 years targeted at a strategic goal of reducing aircraft accident rates fivefold within 10 years and tenfold within 20 years. This initiative will include research to reduce human-error-caused accidents and incidents, predict and prevent mechanical and software malfunctions, and eliminate accidents involving hazardous weather and controlled flight into terrain. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/20/2001
1027 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Aeronautics/Research and Development/Wind Tunnel Inspections |  | The fan blades on the 40' x 80' x 120' wind tunnel at the Ames Research Center developed cracks after only 2,000 hours of operation. To preclude shutting down the tunnel for the 1 year required to procure and install a new set of blades, it was decided to repair the old blades while waiting for delivery of the replacements. The repair includes wrapping the root section of the blades, which eliminates the ability to detect crack growth by visual inspection. | NASA should ensure that a suitable inspection program, including frequent checks using nondestructive evaluation methods, is implemented. | HQ | 02/01/1997 | Wind Tunnel Fan Blade Cracking at Ames Research Center | As part of the fan blade repair at the National Full-Scale Aerodynamic Complex (NFAC), quality assurance and inservice inspection procedures are being developed and applied to ensure functionality of the repair. All blades are being visually examined to assess and establish their condition prior to the start of repair. Throughout the repair process, both ultrasonic and acoustic tap testing is being performed to determine adequacy of the crack fill, as well as the wrap lay-up quality and bonding. After placing back in service, periodic inspections using acoustic tap testing and a series of full-scale fatigue tests will be implemented to monitor and characterize void growth. Based on these testing results, criteria for the periodic inspections, including frequency and size of indications, will be developed. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/20/2001
1029 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Ground Processing Operations/Environmental Requirements and Obsolescence Issues |  | The Space Shuttle program has experienced some difficulties when stable work processes were altered to counter obsolescence or meet new environmental requirements. The simultaneous change in pressure sensitive adhesive and cleaning wipe in the RSRMs to meet environmental regulations is one example. | The Space Shuttle program should not alter long-established and stable processes without defining and completing an adequate test program. If changes in stable and well-characterized safety-related hardware and processes are being driven by environmental requirements, NASA should consider seeking waivers of these requirements rather than altering a proven design. | HQ | 02/01/1997 | Materials Obsolescence, Parts Obsolescence and Environmental Regulations Issues Cause Disruptions in Stable Shuttle Ground Operations Processes | The SSP has been and is committed to not altering long-established and stable processes without defining and completing an adequate test program. The program has long had requirements governing the recertification of hardware in the event of either a hardware design change and/or a process change(s) that affect form, fit, function, safety, and/or reliability. However, the program has authorized a recent requirement change (reference PRCB Directive S071024DL) to provide a program-level review of all hardware and/or process changes whose certification is based solely on analysis. This requirement change necessitates a program assessment of the rationale for specifically defined changes whose recertification is based solely on an analysis, as opposed to those where the recertification is based on the performance of an adequate test program. It is felt that compliance with this new requirement will assure that changes to long-established and stable process changes are only implemented with adequate and appropriate recertification. For any safety-related hardware or process change that is being driven by environmental requirements, NASA includes in its initial assessments the appropriateness of seeking a waiver to the requirements that are causing the change. Where such an assessment substantiates the appropriateness of a waiver, then that waiver shall be sought. The SSP adopted a policy that balances flight safety and environmental protection goals in SSP letter MS-96-071, dated September 16, 1996. The SSP manager specified: (1) obtain long-term waivers for materials essential to safe Space Shuttle operations where functionality cannot be verified; (2) obtain long-term waivers for materials where no replacements exist; and (3) continue to pursue identification and certification of replacement materials. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1030 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Emergency Preparedness/Firefighting Preparedness and Training/Resource Inadequacies |  | While firefighting preparedness and training in NASA is generally adequate, further reductions in staffing and funding may compromise the ability to perform this vital safety function. | Continue to review firefighting at all NASA Centers to ensure that funding, personnel, training, and adequacy of equipment are properly addressed. | HQ | 02/01/1997 | Reductions in Staffing and Funding May Compromise the Ability to Perform Firefighting Training | NASA agrees with the assessment that fire protection for NASA facilities could suffer if not properly managed by NASA. In accordance with NMI 1240.3, "Functional Management," the Office of Safety and Mission Assurance (OSMA) has performed functional reviews ("spot checks") at each Center since March 1994. Each of these functional reviews had, as an element, an evaluation of the fire protection program for the Center. In prior years, reviews were conducted as part of a Center survey process, which also included fire protection. These reviews focused principally on whether firefighting preparedness and training within NASA is at the appropriate level for performing this vital safety function. Because of the recommendation made by the Panel, additional attention has been focused on this concern within NASA over the last several months. During the NASA Emergency Preparedness Coordinators meeting held at the Ames Research Center, February 25-28, 1997, all coordinators were given an action to further pursue this specific concern at their individual installations as a "high level of interest." At the May 21-23, 1997, meeting for NASA Fire Protection Coordinators, held at the Jet Propulsion Laboratory, these coordinators provided a "status" briefing on the posture of their fire protection program in light of the stated concerns by the Panel. All NASA Centers and Installations have reported that their fire protection and response capability at this time remains adequate. However, it was a consensus that diminished NASA budgets have fostered a concomitant shifting of each NASA Center's reliance to the community's local fire protection and response capability through memoranda of agreement. Because local community fire departments are feeling the same pressure of downsizing that the Federal establishments are facing, these departments are also reducing capabilities and increasing response times. The OSMA, the Enterprise Institutional Program Officers (IPOs), and the Center Fire Protection Coordinators will need to be increasingly vigilant that any shift of local community fire department's response capability away from Federal facilities will not increase the risk to NASA personnel or property to an unacceptable level. The OSMA will continue to focus attention on fire protection in our scheduled visits to Centers and will keep the Enterprise AAs and IPOs informed. Through proper assessment and advocacy for application of appropriate resources through the IPOs, we will continue to assure that NASA personnel and resources are afforded the highest degree of fire protection. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1026 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Aeronautics Technology Research Center Flight Operations Consolidation/Delay in Implementation/Flight Safety Impacts |  | The well-planned consolidation of NASA flight research aircraft at the Dryden Flight Research Center has been put on hold by congressional mandates. This uncertain situation has prompted low morale and caused the loss of good people, which could well lead to flight safety problems. | The well-planned consolidation of NASA flight research aircraft at the Dryden Flight Research Center has been put on hold by congressional mandates. This uncertain situation has prompted low morale and caused the loss of good people, which could well lead to flight safety problems. | HQ | 02/01/1997 | Consolidation of Flight Operations Research at DFRC was put on Hold by Congressional Mandates and has Caused Workforce/Morale Problems | NASA is continuing to work with both the Administration and Congress on the consolidation of flight research aircraft. As always, safety of flight remains the "number one" priority in all our aircraft operations. We will cancel or postpone missions if staffing attrition or other problems impact operations. Most recently, the Office of Safety and Mission Assurance completed an assessment of aircraft operations at the Ames Research Center, where they found "an extremely talented and dedicated group of professionals who are committed to mission success and safety." Although staff has been declining, a number of aircraft have been decommissioned, thereby allowing a smaller staff to continue effective and safe operations. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/20/2001
1023 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Computer Software/Configuration Control/Verification and Validation (V&V) |  | The use of the Matrix X autocode generator for ISS software can lead to serious problems if the generated code and Matrix X itself are not subjected to effective configuration control or the products are not subjected to unit-level V&V. These problems can be exacerbated if the code generated by Matrix X is modified by hand. | NASA should ensure that thorough IV&V is conducted on all code produced by Matrix X, including any hand-coded modifications made to it, and that there is adequate configuration control on the code generated by Matrix X. | HQ | 02/01/1997 | Possible Lack of Configuration Control and Software Verification and Validation | NASA agrees with the intent of the recommendation. IV&V will be performed on programs in accordance with the approach explained in our response to item 27a above. NASA is aware of the problems and concerns relating to Matrix X. Software changes that are made after auto-code generation, configuration management difficulties with hand-crafted changes after regeneration, code that appears different after auto-generation because of new variable name assignments, and new releases of the auto-coding tool itself are the principal areas of concern. These problems and concerns are considered to be inherent to auto-code generation tools. The NASA IV&V Facility in West Virginia will continue to evaluate the use of auto-code generators and the Matrix X generator tool specifically in order to better characterize these concerns and develop policies and procedures to better govern the use of auto-generated code. Some potential users of Matrix X have already been working closely with the NASA IV&V Facility on the issue of Matrix X and auto-code generation in general. The IV&V Facility will review program plans for programs that plan to incorporate an auto-generation tool and will assist in the development of guidelines to minimize the risks. Regarding the Product Group 1 (PG1) use of Matrix X for developing the ISS Control and Data Handling software, NASA concurs with the concern over the con-figuration change control and the verification of the auto-coded software. The configuration control of all auto-coded software should be both at the model level and at the source code level. The prime contractor will be receiving both the models and the generated source and binary code from the PGs and will regenerate the source and binary code to ensure completeness and accuracy of the delivery. Product Group 1 had problems late last year with unit testing of the flight software produced by Matrix X, but at that time they concluded that it was better to utilize a more modular design. Coincident with this, Product Group 1 also used Matrix X to build unit test drivers without impacting the unit under test. This procedure also includes the capability to test the units on the target hardware. These changes alleviate the NASA IV&V Facility's original concerns with Matrix X and unit testing. The prime contractor is currently negotiating the wording for the PG1 Software Development Plan to implement these changes. The prime contractor has not yet begun looking at the older Product Group 3 (PG3) Software Development Plan to determine any additional changes needed. The NASA IV&V Facility's analysis of PG3's use of Matrix X did not generate any concerns. It should be noted that neither Product Group 2 nor the prime contractor use Matrix X for coding their software. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/20/2001
1024 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Command and Data Handling/Firmware Documentation |  | NASA does not have procedures in place for documenting the firmware that is placed in ISS components, particularly for devices that were grandfathered from Space Station Freedom. | NASA should ensure that all firmware code, particularly that grandfathered from Space Station Freedom, is properly documented and archived for future reference. Further, NASA should ensure that it retains the rights to such software. | HQ | 02/01/1997 | Inadequate Procedures for Documenting Firmware Placed in ISS Components | NASA agrees with the recommendation. Direction to deliver copies of the documentation (requirement, design, test, etc.) of the firmware controller software prepared as part of their software development process is being given to each vendor. A library will be established in the Software Development and Integration Laboratory (SDIL) at the Sonny Carter Training Facility. In addition, as part of the sustaining engineering activity, a plan is being developed to bring the qualification firmware controller units to the IV&V Facility and provide a capability to use these controllers instead of math models when required to support anomaly resolution or testing. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/20/2001
1025 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station Program/Software Development/Improved Processes |  | There has been a marked improvement in the software development process for the ISS. | By no means have all problems been solved, and there is still much to be done. Continue the focused efforts. | HQ | 02/01/1997 | Improvement in the Software Development Process for the International Space Station Program | NASA agrees with the recommendation. A strong management focus on the software development process for the ISS will continue. These include weekly status reports concerning the prime contractor and product group developments and strong interaction at the design and test reviews. To ensure progress does not slip, the prime contractor has initiated several activities, including additional shift work, new hiring, and developer/tester teaming arrangements. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/20/2001
1021 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Computer Software/Software Safety Policy Requirements/Potential Inadequacies |  | NASA's Agencywide software safety policy allows projects latitude to tailor their software safety plan for safety-critical software. It does not, however, require projects to obtain center Safety and Mission Assurance (S&MA) approval of the tailored software safety plans nor does it require Verification and Validation (V&V) per se. While the software assurance standard does mention V&V, it does not require any independence of V&V for safety-critical software. | 27a. NASA should require approval of a project's tailored software safety plan by both the center S&MA organization and by one administrative level higher than that making the request. 27b. NASA's software safety plan should require formal V&V of safety-critical software. Testing alone does not suffice. 27c. NASA should develop an explicit policy that requires independent V&V for safety-critical software. | HQ | 02/01/1997 | Potential Inadequacy of NASA Agencywide Software Safety Policy Requirements | 27a. NASA agrees with the intent of this recommendation but believes the requirements for formal system safety program plans and software management plans exist and, with proper and firm enforcement, fulfill the objective of this recommendation. To be sure that these requirements are perfectly understood, the Office of Safety and Mission Assurance (OSMA) will update NSS 1740.13, "NASA Software Safety Standard," to explicitly state that the program/project manager for programs/projects perform an assessment to determine, based on the level of criticality and risk, the scope and level of Independent Verification and Validation (IV&V) to be planned. The results of the assessment will be formally reviewed by Center Safety and Mission Assurance (SMA). The program/project manager, in consultation with SMA, will tailor an approach to ensure that the appropriate V&V requirements are established and implemented. The OSMA will place more emphasis on the implementation and enforcement of these existing requirements. Process verification, recently established in the OSMA, will be used to evaluate and enforce these existing policy and requirements more aggressively. NASA is committed to assuring that required program management plans and any subordinate plans such as software or safety management plans cover the essential requirements for programs where warranted by cost, size, complexity, lifespan, risk, and consequence of failure. Additional changes are being incorporated into NPG 7120.5, "NASA Program/Project Management Guide" (currently under development), to ensure that necessary and sufficient requirements will be fulfilled for programs having software vulnerabilities. SMA organizations at each level are to be a party to these decisions and are to intervene where necessary to assure that proper and clearly documented decisions are made by the appropriate level of management. The Program Management Councils could play a role in adjudicating any issues with the content of program management plans. 27b. NASA agrees with the intent of this recommendation and is confident that NPD 2820, "NASA Software Policies" (currently under development), will ensure that software management and/or safety plans developed for any NASA program/project will specify the level of V&V and types of testing that should be implemented. NPD 2820 policy relating to software V&V states that NASA will create and/or acquire and maintain software through risk-based management. Risk management products shall be documented or referenced in a management plan. NASA will employ V&V, IV&V, and other trusted verification techniques for appropriate risk mitigation based on the cost, size, complexity, lifespan, risk, and consequence of failure. NSS 1740.13 is not a NASA Software Safety Plan. The level of detailed requirements that the ASAP is recommending be in NSS 1740.13 more appropriately belongs in the documents that the programs and projects will prepare in response to NSS 1740.13. These details need to be documented in the Software Management Plan (SMP), the System Safety Program Plan (SSPP), or the Program Management Plan (PMP). NASA maintains that the requirement stated in NASA-STD-2100-91, "Software Documentation Standard," suffices as a requirement for addressing the issue of V&V for programs. NHB 1700.1, "NASA Safety Policy and Requirements Document," requires NASA program managers to publish and maintain an approved NASA Safety Management Plan (SMP). The program manager is responsible for approval of the NASA SMP and contractor Safety Program Plan (SPP). The system safety manager (SSM), assigned by the program manager (PM) from the Center Safety and Mission Assurance organization, prepares the SMP. The SSM, reviews the contractor's SPP and provides recommendations to the PM. The SSM, upon review of the contractor's SPP, will have the required insight into the approach for software V&V to ensure that a proper balance of analyses, inspections, and testing is planned for the entire life cycle of the program. NASA's SMA organizations at the NASA Centers are currently involved in the review of V&V plans for software and do make recommendations to the PM. 27c. NASA agrees with the premise that safety-critical software is a prime candidate for IV&V; however, it is NASA's position that all software determined to be safety-critical by engineering or safety analyses need not be subjected to IV&V. To be sure that program/project managers plan for the proper level of both V&V and IV&V from the outset, the OSMA will update NSS 1740.13, "NASA Software Safety Standard," to explicitly state that program/project managers perform an assessment to determine the scope and level of IV&V based on the level of criticality and risk. The results of the assessment will be formally reviewed by SMA. This way, the program/project manager, in consultation with SMA, will tailor an approach to ensure that the appropriate V&V requirements are established and implemented. NPD 2820 has incorporated the proper approach for software on NASA programs/projects; the directive requires program managers to employ IV&V, V&V, and other proven verification techniques for risk mitigation, based on cost, complexity, risk, and consequence of failure. NPG 7120.5, "NASA Program/Project Management Guide" (currently under development), will reflect some of the requirements now found in documents that program managers may not normally review for compliance. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/20/2001
1022 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Computer Software/Software Safety Policy Requirements/Potential Inadequacies |  | NASA has put considerable effort into the reorganization of its software activities and has made significant progress. It does not yet, however, have a comprehensive, clear set of roles and responsibilities for various groups within the Agency with respect to software development, safety, V&V, and software process development. | NASA should ensure that there is a clear, universally well-understood, widely promulgated, and enforced NASA Policy Directive on the roles and responsibilities of its various organizations vis-à-vis software development and safety. Moreover, that Policy Directive should specify organizational roles and responsibilities solely on the basis of technical and administrative capability. | HQ | 02/01/1997 | Potential Inadequacy of NASA Agencywide Software Safety Policy Requirements | NASA agrees with the recommendation. The July 1996 (draft) program plan for the Fairmont (IV&V) Facility is the contract between Code Q and the Facility and will be updated for future funding and delegation of the software assurance program. NASA concurs that the draft plan now contains ambiguities but will be clarified in the next update. The IV&V Facility's reporting structure will be finalized in the upcoming proposed Ames Research Center reorganization. It is anticipated that the IV&V Facility will be moved from under the direction of Code I at Ames and installed as the equivalent of a Directorate in the new ARC organization. The IV&V Facility Business Plan currently defines the roles and responsibilities of the IV&V Facility. NASA Headquarters will establish and document at the policy level the roles in the Agency for all software, including embedded and flight system software. The policies document will explain how the roles and responsibilities of the Agencywide software efforts mentioned in the finding (e.g., CIO, COE-IT, IV&V Facility) fit together in a synergistic manner within the Agency. The new NPD 2820 will define Agency policy for program/project utilization of the IV&V Facility. The Chief Information Officer, the Chief Engineer's Office, the Office of Safety and Mission Assurance, and the Software Working Group will be responsible for increasing Agency awareness of all the software-related resources, policies, and existing standards. The newly implemented Code Q process verification activity will validate Agency project managers' awareness of software assurance policy and procedures for compliance in software development efforts. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/20/2001
1020 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/X-38 Project/Crew Return Vehicle (CRV) Development |  | The X-38 research vehicle program is a good approach for developing an ISS CRV. | Any CRV resulting from the X-38 program should be capable of fulfilling the design reference missions that were developed by the Space Station Freedom program for an assured CRV. | HQ | 02/01/1997 | X-38 Research Vehicle Use for Crew Return Vehicle Development | The ISS program and the X-38 project are developing a top-level set of requirements and dependencies between the ISS and the CRV derived from the X-38. This document, the Performance and Support Requirements Document (PSRD), specifies the three basic CRV design reference missions (return of an injured or ill crew person, emergency evacuation of the station, and return of crew in case the ISS cannot be resupplied) as defined in the top-level Station Specification, SSP 41000. These three design reference missions are the same as used for the ACRV during the Space Station Freedom program. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1019 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Communications System/Wireless Capability |  | The ISS design does not include a requirement for a wireless communication system to maintain crew contact throughout the station. The present design requires a crew member to translate to a panel or connect a headset. | The ISS program should establish a requirement for "hands-free" communications with crew members to deal with situations such as injuries or meteorite/debris impacts in which it may be necessary to establish rapid contact. | HQ | 02/01/1997 | Lack of Requirement for Wireless Communication Capability for Expedition Crews | The requirements specification for this capability has been developed and is provided in Attachment 2. The Station Wireless Communications Subsystem (SWCS) will be installed on orbit no earlier than assembly flight 6a. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1018 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Hazardous Materials Containment/Payload Toxic Substance Sensing |  | The ISS has no requirement for sensing a toxic substance spill within a payload rack. The ISS does require that toxic substances in payload racks be multiply contained. | The ISS should require payload providers to include, as part of their system design, detection and annunciation of any toxics they carry or could generate. | HQ | 02/01/1997 | Payload Requirements for Hazardous Materials Containment | NASA concurs. The approach for payloads on the ISS is patterned after the Shuttle approach. The payload design requirements are defined in NSTS 1700.7B, "Safety Policy and Requirements for Payloads Using the Space Transportation System," and the ISS Addendum, which to date make the possibility of having a toxic spill so remote as to be an acceptable risk. Requirements imposed on payloads include containment levels stipulated based on level of toxicity of the substance or use of an approved pressure vessel. The payload provider is required to obtain approval by the Payload Safety Review Panel (PSRP) for the use of any toxic substance, as well as the containment method utilized. Through the safety process defined in NSTS 13830, "Implementation Procedure for STS Payloads System Safety Requirements," all potentially toxic substances are labeled and documented in crew procedures, along with any cleanup instructions. This ensures that needed information on any potentially toxic substance is readily available to the crew. This concept for the handling of toxic substances is based on Shuttle and Mir program experience and has not been changed. When payloads are reviewed by the PSRP, compliance with the above requirements must be demonstrated. Astronaut training and procedures are reviewed and approved to ensure that the crew is adequately educated to avoid inadvertently mixing toxic chemicals. In addition, the payload design must still be able to tolerate the appropriate number of operator errors. These requirements do not impose design solutions on payloads; rather, they require the payload providers to proactively consider their own design solutions to avoid toxic mixing. Enforcing these requirements in the PSRP process by ensuring compliance with the requirements of NSTS 1700.7B will restrict the possibility for toxic mixing to an acceptable risk. Dependent on a case-by-case analysis, the PSRP or the payload provider may request detection and monitoring. The detection will then be provided by the payload provider organization with tie-in to the ISS core systems of C&W (annunciation) provided by core system interfaces at the rack level. This service will then be defined in the appropriate Interface Definition Document (IDD). The crew will be used to enunciate any toxic spills throughout the ISS. This is considered essentially the equivalent of the panic alarm. The crew will also be used to detect any toxic spill. Studies have shown that intermodule ventilation will spread any toxic gases to all elements of the ISS within 20 minutes, which makes station-level detection not practical. This further illustrates the importance of having adequate design requirements imposed on payloads to preclude toxic spills. Crew annunciation and detection have been considered acceptable because of the design requirements imposed on the payloads to maintain appropriate levels of containment. However, should a toxic spill occur, provisions are available to payloads for cleanup. These include a crew contamination protection kit (goggles, chemical resistant bags, chemical resistant gloves, emergency eyewash), a portable breathing apparatus, a combustion products analyzer, a volatile organics analyzer, multiple airborne trace contaminant control equipment, vacuum access, and module depressurization. The JSC Mission Operations Directorate is currently developing procedures to respond to a toxic spill. The procedures will be based on Shuttle experience. The response will depend on the hazard level of the substance, the state of the substance (liquid, gas, or solid), the location of the spill, and the size of the spill. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1015 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Micrometeoroid Debris Protection/Hazard Detection, Assessment and Control |  | The overall design philosophy for meteoroid and orbital debris (M/OD) mitigation has been agreed to, in principle, by the international partners. Much of the U.S. module shielding design is nearing completion. Nevertheless, there remains a finite probability that a penetrating collision will occur during the life of the ISS mission. The emphasis of the M/OD effort is therefore shifting to operations issues, such as caution and warning, damage control, and strategies for reaction to depressurization events. | Agreement with the international partners should be completed. Operational strategies and procedures for handling M/OD events should be developed and incorporated into ISS plans and schedules. Crew training programs to accommodate these strategies and procedures should be established. | HQ | 02/01/1997 | Shift From Design Philosophy for Micrometeoroid Debris Penetration Scenarios to Flight Operations Strategies for Hazard Detection, Assessment, and Control | The Common Depressurization Strategy (CDS) team was formed in May 1995 to coordinate the program approach for responding to a potential depressurization event. The team's charter is to address crew and vehicle operational strategies, immediately identify required hardware modifications to make safe the vehicle and crew, and develop necessary plans for implementation of these items. Baseline crew procedures, repair requirements, assessment methodologies, and identified hardware modifications (to reduce risks of vehicle and crew loss in the event of a penetration) are documented in international protocol agreements. Plans for implementation are being developed. This approach has been independently reviewed and validated in a series of joint meetings led by Lt. Gen. Thomas P. Stafford (USAF, Ret.) of the NASA Advisory Council and Academician Vladimir F. Utkin of the Russia Space Agency Advisory Expert Council. Specific activities have been agreed to and will be completed by December 1997. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1017 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Caution and Warning System/Systems Engineering |  | Design of the Caution and Warning (C&W) system had been lagging behind that of other ISS systems. Priority has now been given to the system engineering effort that is required to resolve conflicting operational concepts and to finalize the design. | Continue to apply high-level system engineering attention to the expeditious resolution of C&W design philosophies and implementations. | HQ | 02/01/1997 | Application of Systems Engineering Methodology to ISS Caution and Warning System | NASA concurs. The ISS Caution and Warning (C&W) system has matured throughout 1996, with improvements in tone commonality, event definition, Personal Computer System (PCS) display development, application code generation, and recognition by all program elements. The C&W System Integration Team's (CWSIT) primary purpose is to ensure that the C&W system is safe, robust, and integrated throughout the vehicle and throughout the lifetime of the program. The team's primary responsibilities include: Providing end-to-end C&W design integration, including display and response concept definition. Developing and leading a forum for resolution of C&W design/operational issues Attachment 1 provides specific responses based on the current design for the examples cited in Section III: Information in Support of Findings and Recommendations, ASAP Annual Report, February 1997. In addition, in response to the ASAP concerns, the International Space Station Program Office (ISSPO) has tasked two independent assessments of caution and warning activities. These efforts are led by the Manager, ISS Independent Assessment, and the ISS Chief Engineer. These assessments were completed in August 1997. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1016 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Real-Time Operations/Collision Avoidance Maneuvers |  | The collision avoidance and maneuver process for evading meteoroids and orbital debris is complicated and not yet completely worked out for many of the scenarios likely to occur during the life of the ISS program. | The collision avoidance and maneuver process must be worked out in detail and documented in interagency memoranda and in agreements among the international partners. | HQ | 02/01/1997 | Collision Avoidance Maneuvers of the ISS Require Close, Real-Time Cooperation Between NASA and US Space Command | NASA has a history of cooperation with the U.S. Air Force Space Command (USSPACECOM). Several Memoranda of Agreement (MOAs) are in place with USSPACECOM for Shuttle collision avoidance procedures. The requirements for the ISS are being worked through an established working group. A Debris Avoidance Operations Plan was drafted in 1996. Required international participation is being and has been worked through hardware specifications, international protocol agreements, and the Station Program Implementation Plan. A Flight Mechanics Working Group has been chartered, which includes Russian and NASA participation. This group meets regularly, and their results are documented in the ISSP Flight Rules Manual. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1011 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/SFOC Contract/Logistics Functions Transition |  | Transition of logistics functions under Phase 1 of the Space Flight Operations Contract (SFOC) appears to be taking place smoothly. Key personnel are maintaining continuity in management techniques and processes. | Continue adherence to established systems, and make maximum use of the inherent capability of the incumbent personnel in the logistics systems. | HQ | 02/01/1997 | Transition to USA Management of Logistics Functions Under Phase 1 of the SFOC Contract | NASA concurs. The established NASA Logistics Operations continues to monitor the established logistics systems and enhance others in order to maintain insight into the logistics activity. Both the SFOC contractor and NASA Logistics Organization have retained incumbent key personnel with critical logistics skills to minimize the transitional risks and continue to support the SSP. Currently, the SFOC contractor is studying the horizontal consolidation of like functions and processes. NASA Logistics Operations will monitor the contractor's progress to assure that the logistics systems resulting from this consolidation will be capable, effective, efficient, and, above all, not adversely impacting the safety of operations. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1012 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Cannibalization Rates, Spares, and Repair Turnaround Times |  | Long-term projections suggest increasing cannibalization rates, component repair turnaround times, and loss of repair capability for the Space Shuttle logistics and support programs. | Take early remedial action to control this potential situation, such as maintaining sufficient spares and extending repair and overhaul capability. | HQ | 02/01/1997 | NASA Budget Situation Impacts on Shuttle Logistics Capabilities | NASA is closely monitoring logistics trends. The areas of emphasis stress long-term logistics support indicators, specifically backlog and repair turnaround. While an increase in repair turnaround time has been noted, vehicle support remains at the same high level. Budget reductions in past years have meant that fewer spares have been produced and less repairs were performed, but NASA and the contractor will continue to manage the process to maintain acceptable levels of support. Presently, logistics performance measurement data do not indicate any adverse trends in cannibalization rates. NASA has directed SFOC management to maintain an emphasis on logistics supportability during the transition of all contract responsibilities. The SFOC contractor has been directed to maintain key personnel with critical logistics skills to minimize transitional risks and provide continuity to Shuttle logistics support. In addition, SFOC is required to develop and submit original equipment manufacturer (OEM) contingency plans for responding to known and potential support issues at effected OEMs. All known supportability threats are tracked and evaluated to determine the associated risk and required actions for resolution. The SFOC has the appropriate processes in place to both monitor and respond to loss of subcontractor capability. The NASA Shuttle Logistics Depot (NSLD) has been certified to make some repairs where there has been a loss of critical supplier capability. The SFOC is also considering consolidating similar work at one vendor so that the NSLD is not the only repair agent. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1014 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | International Space Station (ISS) Program/Ground Processing Schedule/Test and Verification |  | The schedules for ISS buildup are tight, and there is little, if any, schedule slack to accommodate late or unavailable hardware. Schedule and/or budget pressures could lead to deferring work to orbit or curtailing prelaunch testing. | ISS program plans for finishing and testing hardware before launch should not be compromised to meet either launch schedules or budgets. | HQ | 02/01/1997 | Lack of Schedule Slack in ISS Program Causing Potential Decrease in Prelaunch Ground Testing | NASA concurs. Integration testing is in the approved program's current baseline. Prelaunch integrated testing at KSC is based on the degree to which this testing abates program risk, weighed against the hardware damage risk and the cost and schedule impacts. The content for component, subassembly, and element-level testing is the minimum requirement for specification compliance verification. A program-approved change would be required to eliminate this work. In fact, integration and testing are being strengthened as opportunities develop. A proposal to conduct multi-element integration testing is being planned, which would exploit the unique KSC ground processing expertise. This would involve actual flight hardware to conduct end-to-end testing for assembly elements 3A, 4A, 5A, and 6A in the manner that these elements would be assembled on-orbit. ISS program requirements for on-orbit stage and assembly-complete capability reflect a thoroughly reviewed baseline. This baseline generally reflects a minimum required capability, which has incorporated improvements to satisfy an achievable crew workload. There is strong inherent resistance in the program, therefore, to bringing incomplete hardware to be processed at KSC, much less than to orbit, because of the minimum capability constraints and crew workload impacts. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1013 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Logistics/Obsolescence of Parts |  | Obsolescence of components and systems on the Space Shuttle is an increasing problem threatening critical spares availability. | Alternative components must be developed and certified, and, where necessary, systems must be redesigned to use available or adaptable units. | HQ | 02/01/1997 | Parts Obsolescence May be Caused by Several Issues Including Vendors Going Out of Business, Discontinuance of a Part, and Environmental Law Changes | NASA continues to identify and coordinate obsolescence issues concerning hardware, special test equipment, vendor capability, and environmental restrictions with the appropriate design center. Each issue is evaluated for logistics impacts, and this information is communicated to or within the design center so that appropriate action can be taken to initiate any required redesigns, modifications, or enhancements. A Kennedy Space Center (KSC) logistics priority list is maintained to communicate logistics' top concerns to design center management. While obsolescence will continue, a team approach to problem identification, prioritization, and resolution appears to be providing effective problem resolution. Additionally, the Shuttle upgrade program is designed to assure that potential problem areas are addressed so as to preclude disruption in meeting manifest requirements. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/20/2001
1010 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Super Light Weight External Tank/Materials & Test and Verification Changes |  | The 2195 aluminum-lithium alloy used in the tank walls and domes of the new Super Light Weight Tank (SLWT) has a lower fracture toughness at cryogenic temperatures than was anticipated in the design. To compensate for this potentially critical short-coming, NASA has limited the pressure used in the full tank proof test and has recognized that acceptance of each SLWT for flight is highly dependent on far more stringent quality control of the materials and processes used to manufacture the SLWT than is required for the current external tanks. | 16a. Assure that the acceptance tests of the 2195 material and the quality control procedures used in the manufacture of each SLWT continue to be sufficiently stringent, clearly specified, conscientiously adhered to, and their use unambiguously documented. 16b. The criticality of these quality control operations makes it mandatory for NASA to retain buyoff of the results of those fabrication operations and tests that are essential in determining SLWT safety. 16c. As quality control data on the size of flaws detected in 2195 aluminum-lithium material are collected, they should be used in an updated analysis of the SLWT structure, because it may permit the verifiable spread between flight limit stress and proof stress to be raised above that presently reported. | HQ | 02/01/1997 | Lower than Anticipated Fracture Toughness of the 2195 Aluminum-Lithium Alloy Used in the SLWT at Cryogenic Temperatures Causing Changes to Test & Verification Procedures | 16a. The SSP and Marshall Space Flight Center (MSFC) will continue to ensure that material acceptance testing and the quality control procedures used in the manufacturing of SLWT's are of a sufficient quality to validate that each tank is fully in compliance with all program requirements and is safe to fly. 16b. The SSP and MSFC will retain NASA approval of the quality control program and changes to that baseline. 16c. The simulated service database has been developed from data collected on fracture specimens with flaws that are 0.175 inch long. The data verify a 2.9% positive spread between the flight and proof-test conditions. Using the demonstrated flaw detectability level for our nondestructive evaluation dye penetrant process (0.086 inch long) would increase the spread to approximately 14%. Because of uncertainties, it is NASA's standard policy to use a factor of two on our flaw detectability limit. This methodology provides the proper risk allocation between the nondestructive evaluation capability and proof-test levels. The use of a flaw size of 0.175 inch for the simulated service tests is conservative for the SLWT. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/15/2001
1004 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Block II Space Shuttle Main Engine (SSME)/Alternate High Pressure Fuel Turbo pump (ATP HPFTP) Design |  | The Block II SSME development program has proceeded well, except for the Alternate Turbopump Program High Pressure Fuel Turbopump (ATP HPFTP). The HPFTP has suffered significant failures in testing, which were traced to shortcomings in hardware design details. Corrective actions have been implemented on the HPFTP. Block II engine testing has resumed for this major safety improvement. | Continue the development and certification test programs as originally planned. Accumulate the specified test operating times for the modified ATP HPFTP, and employ the number of test pumps as per the original test plan. | HQ | 02/01/1997 | Shortcomings in hardware design details for Alternate High Pressure Fuel Turbo Pump (ATP HPFTP) | The SSME project is committed to meet the original development and certification plan requirements. The schedule for certification has been adjusted to accommodate comprehensive resolution of the development problems. Scheduled completion of certification testing is now February 1998. As originally planned, the total "hot-fire time" for development and certification will exceed 60,000 seconds, utilizing eight HPFTP units. Certification will be based on two units with 22 tests each, and "hot-fire time" of 11,000 seconds per pump or 22,000 seconds total certification time. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1001 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Orbiter/Auxiliary Power Unit (APU) |  | A new gas generator valve module for the Improved Auxiliary Power Unit (IAPU) is currently entering the process of certification. When fully certified, the IAPU with this new valve is planned to be qualified for 75 hours of operation between scheduled teardowns and overhauls (in excess of 10 years at projected use rates). | Once certification is achieved for 75 hours of IAPU operation, NASA should establish a periodic inspection and test program to assure that IAPUs continue to perform in accordance with requirements throughout their service life. | HQ | 02/01/1997 | Improved Auxiliary Power Unit (APU) | An IAPU maintenance plan is being developed by the NASA and contractor technical community. Current activity is focused on developing a maintenance specification, evaluating long-term life of elastomeric components, and organizing a parts tracking/usage database. At the conclusion of this effort in late FY 1997, a long-term maintenance plan will be baselined for implementation. Supplementing this to provide long-term service life information is a fleet leader test program at WSTF. The WSTF program is currently scheduled to conclude in FY 1999 and is to demonstrate 75-hour run time and evaluate 10+ year teardown and overhaul time. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1003 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Orbiter/Avionics Modifications |  | The Multi-Function Electronic Display System (MEDS) in the orbiter is being implemented with display functions and formats that mimic the present electromechanical and cathode ray tube presentations. There are significant potential safety and operational benefits from enhancing the amount, type, and format of information shown on the MEDS displays. | The Space Shuttle program should commit to a significantly enhanced MEDS display as soon as possible. The MEDS advanced display working group or a similar multidisciplinary team should be tasked with identifying specific modifications and an associated timetable so that the opportunities inherent in MEDS can be realized. | HQ | 02/01/1997 | Orbiter Avionics Modifications | The SSP has established an enhanced MEDS program that includes hardware and software enhancements to take full advantage of MEDS capabilities. This includes hardware expansion as well as utilization of inherent MEDS capabilities to provide better displays and improve crew situational awareness. Additionally, an SSP Cockpit Upgrade Team is being formed to develop advanced display and application concepts for future implementation into MEDS/enhanced MEDS/future avionics upgrades capability. The Cockpit Upgrade Team will also participate in avionics upgrades discussions in order to anticipate future hardware and software changes and develop advanced cockpit applications to further improve crew awareness and reduce crew training requirements. Initial testing of new applications for enhanced MEDS will begin in June 1997. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1002 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Orbiter/Avionics Modifications |  | The Space Shuttle is about to receive two major avionics upgrades--a triple redundant Global Positioning System (GPS) installation and the Multi-Function Electronic Display System (MEDS)-both of which require significant changes to the Primary Flight Software (PFS) and Backup Flight Software (BFS) systems. | The Space Shuttle program should ensure that both the GPS and MEDS software changes are thoroughly tested in the Shuttle Avionics Integration Laboratory (SAIL) using the normal and enhanced test protocols that have proved to be robust when testing major modifications. | HQ | 02/01/1997 | Orbiter Avionics Modifications | The SSP concurs that all software and hardware changes need thorough testing, and it recognizes the extremely important role that SAIL testing fulfills in the complement of testing for software certification. All Shuttle software or hardware upgrades are assessed to determine integrated verification test requirements. The SSP and its contractors cooperate to produce integrated hardware and software test implementation plans, test requirements documents, and integrated test schedules to assure that the required resources, including SAIL, are available. All these plans are reviewed and approved by the program. Thorough testing of each new capability is then performed and analyzed. This same rigorous process that is used for flight software Operational Increment (OI) updates will be applied to the MEDS, GPS, other Shuttle upgrades, and future software updates. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1007 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Reusable Solid Rocket Motor (RSRM)/Manufacturing & Process Control and Certification Testing |  | Changes in the Pressure Sensitive Adhesive (PSA) and the cleaning agent for the J-flap of the RSRM were driven by environmental regulations. The certification testing for these changes included a Flight Support Motor (FSM) firing without the application of side loads, a significant condition for RSRM field joints for which the J-flap plays a role. | Employ the application of side loads in all future RSRM FSM firings. | HQ | 02/01/1997 | Environmental Regulations Resulting in Manufacturing Process Changes for RSRM | The SSP and RSRM project agree with this recommendation when aft field joint test objectives warrant inclusion on an FSM test motor. During Space Shuttle return-to-flight RSRM redesign, the assessment of strut loading on the solid rocket motors concluded that the only influence was at the aft field joint. The influence on the aft field joint gap openings was predicted to be less than 0.001 inch, roughly an order of magnitude less than the contribution of the internal motor pressures. Side loads were included on two RSRM static test motors (QM-7 and -8) in a comprehensive effort to include every element of flight loading influencing the aft field joint gap openings. Joint gap openings were not measured directly, but the sealing systems performed as expected. Gap openings were measured on the RSRM structural test article-3, where testing showed side loads influence to be less than 0.0005 inch out of a total of 0.0084 inch for aft field joints only. The consideration to include side loads on all future tests would not come without technical penalty. To accommodate the side load forces, the aft test stand must be locked out, and as such, no thrust measurements are obtained. Also, no thrust vector control (TVC) duty cycling is performed during the side load events, which requires modification to the baseline static test duty cycle; for certain test objectives, this is an important requirement consideration. This baseline TVC duty cycle is utilized to allow direct performance comparisons between static tests, primarily associated with nozzle and aft dome materials or components. Therefore, a generic inclusion of side loads on all future FSM tests would require elimination of other test considerations, which, depending on specific test objectives, might be a qualification necessity. In conclusion, the RSRM static test policy includes side loads on full-scale static test motors where there are test objectives associated with the aft field joints, which could be influenced by side loads. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1006 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Block II Space Shuttle Main Engine (SSME)/Test & Verification to 109% Power Level |  | The Block II engine will be certified for operation at 109% power level only for abort situations. Accordingly, the test program provides only limited cumulative test time at this thrust level. | After completion of the current planned Block II certification test program, conduct a certification extension test program that will demonstrate the highest thrust level for safe continuous operation achievable by the Block II configuration. This program should attempt to achieve at least the 109% power level. | HQ | 02/01/1997 | Certification of Block II SSME Testing at 109% for Intact Abort Scenarios | The Block II program was developed to "improve the safety, reliability, and robustness of the SSME" by providing lower operating temperatures, pressures, shaft speeds, and other critical parameters. An increase in operating power level from 104% to 104.5% will offset some of the weight gain of Block II. The Block II SSME was never intended to increase Space Shuttle ascent performance or increase payload capability to orbit. However, additional performance has been accepted for a few specific missions at the cost of some of the improved safety margin. There is a commitment that the ISS flights will provide 106% engine power level certification to achieve mandatory critical payloads to orbit. The Block II certification will also provide a 109% intact abort capability, which will allow the vehicle system to better optimize abort scenarios. Implementation recommendations for use of 109% throttle for intact aborts will be made by the Shuttle operations element once certification is complete. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1005 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Block II Space Shuttle Main Engine (SSME)/Test Schedule |  | The schedule for the first flight of the Block II engine has slipped, from September 1997 to December 1997. This schedule is optimistic and contains no slack for future development problems. The schedule also requires continued availability of three test stands at the Stennis Space Center (SSC). | Maintain the full scope of the planned test programs. Assure the availability of test stand A-2 at SSC for as long as it is needed for the Block II engine test programs so that three test stands continue to be available. | HQ | 02/01/1997 | Block II SSME Test Schedule Slippage and SSME Test Stand Availability | The development and certification test programs will be maintained as originally planned. Test stand availability has been coordinated with other program test requirements to support completion of Block II HPFTP certification testing in February 1998. Three test stands are required only until July 1997 to support this schedule. A mid-May milestone to initiate construction authorization for the July reconfiguration of Test Stand A-1 for X-33 testing will be reassessed based on fuel pump development status at that time. The other two test stands will remain dedicated to SSME testing. After test stand modification, conversion back to SSME test configuration would take approximately 1 month. The first flight of the Block II configuration has been reassigned to STS-91, currently scheduled for May 1998. Due to the development problems with the ATP HPFTP and the associated schedule slips, the SSP has elected to certify an interim Block II configuration, designated Block IIA. Block IIA will consist of Rocketdyne's current HPFTP in conjunction with the other Block II components and will provide the safety and reliability benefits of the large throat main combustion chamber at the earliest opportunity. This configuration will be certified to fly nominal missions at 104% to 104.5% rated power level (RPL) and will maintain the current 109% RPL contingency abort capability. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
995 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | One consequence of the implementation of the Space Flight Operations Contract (SFOC) is a reduction in opportunities for NASA personnel to maintain detailed, day-to-day work floor interfaces with their contractor counterparts both at space flight centers and major contractor facilities. This could compromise NASA's ability to carry out its assessment function. | In order to carry out its assessment role, NASA must maintain some physical presence on the work floor at the space flight centers and major contractor facilities. NASA must ensure that the people staffing these surveillance positions are and continue to be appropriately skilled, thoroughly knowledgeable about the Space Shuttle, and sufficiently experienced with both the subsystem they oversee and the total Space Shuttle system. | HQ | 02/01/1997 | Implementation of the Space Flight Operations Contract (SFOC) | NASA concurs with the finding and is sensitive to the need to maintain a skilled and capable workforce in both the management and technical functions necessary for Space Shuttle program (SSP) success, and the Agency will work with the contractor in establishing the eventual organizational roles and responsibilities to assure that success. The transition process will be managed at a pace to ensure that necessary skills are maintained within the Government/contractor workforce. The assessment function that NASA will perform in the future Shuttle operations architecture will require the maintenance of a solid skill base within the Agency. NASA will retain the capability to review all anomalies in operations and system performance, as well as all changes to operations and to systems. NASA's role in requirements control will also provide continuous exposure to designs and operations within the program. The participation of NASA engineering and management in the development of Shuttle upgrades will provide further opportunity for the maintenance of an inherent skill base. Finally, there will be functional roles for NASA personnel, such as astronauts, flight controllers, and mission directors that will provide an avenue for skills development and maintenance. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
996 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | It is not clear how NASA Space Shuttle supervisory personnel will be trained and acquire the experience levels necessary to function effectively in senior management positions when the SFOC is fully implemented and the traditional learning ladder positions are staffed by the contractor. | NASA should develop and promulgate training and career paths leading to preparation and qualification as potential senior NASA Space Shuttle management. | HQ | 02/01/1997 | Implementation of the Space Flight Operations Contract (SFOC) | NASA has an active commitment to the development of the skills of senior managers for all functional areas of the Agency. Space Shuttle program senior managers are generally products of both their in-line experiences as well as the NASA career development programs. It is anticipated at this time that the roles for NASA personnel and the career development programs that have served NASA well to this point will be sufficient to assure a continuation of highly qualified and capable senior managers in the future. Given the evolving nature of the NASA and prime contractor roles and responsibilities for the SFOC operational model, it is reasonable to focus special attention on this issue; the program will ensure that specific consideration is given to management development in the transition plans being developed and implemented across the program. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
997 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Workforce |  | No objective measure has yet been developed, or is likely possible, that can shed significant light on the impact of downsizing on the safety of Space Shuttle operations. | In the absence of a valid predictive safety metric, NASA should ensure that all functions affected by downsizing and necessary for safe operations are assigned to people who have the knowledge, skills, and time to carry them out. | HQ | 02/01/1997 | Safety Impact of Downsizing | NASA concurs; all of the contractors supporting the Space Shuttle program remain committed to assuring that safety is the highest priority in every facet of the program. The program recognizes the concerns that downsizing may raise, and it will assure that knowledgeable and skilled individuals are assigned to all critical Shuttle functions, including those being downsized. The plans for the transition of processes and tasks under the SFOC specifically address the safety implications of the transition. As an added assurance, the Shuttle program has required that the NASA Safety and Mission Assurance (SMA) organizations review and concur on the transition plans. Other program downsizing efforts have a similar emphasis on safety embedded in them, and both program management and the SMA management are committed to assure that this focus is not compromised. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
998 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Integrity of Space Shuttle Processing Quality Assurance Procedures |  | Postflight discovery of a wrench and an equipment name plate in the forward skirt of one STS-79 Solid Rocket Booster (SRB) has heightened concern for the overall integrity of Space Shuttle processing quality assurance procedures. | NASA, in concert with the several Space Shuttle contractors, should conduct an in-depth review of Space Shuttle processing quality assurance procedures focused on creating a more formal, documented approach to accounting for tools and other material introduced to and removed from flight hardware work areas. | HQ | 02/01/1997 | Postflight discovery of a wrench and an equipment name plate in the forward skirt of one STS-79 Solid Rocket Booster (SRB) has heightened concern for the overall integrity of Space Shuttle processing quality assurance procedures. | The Space Shuttle program element contractors presented their tool control programs to the Space Shuttle System Safety Review Panel (SSRP) meeting in December 1996. The SSRP reviewed the tool control programs of all the contractors and determined that each of the tool programs was effective for the type of work per-formed. The SSRP recommended that tool accounting audits be maintained or increased, and that metrics be maintained to assure that each tool control program remains effective. In a letter dated March 20, 1997, the Space Shuttle Systems Integration Office confirmed that NSTS 07700, "Space Shuttle Program Definition and Requirements," requires tool control for only the launch and landing project, and recommended that Volume XI of NSTS 0770 be expanded to include tool control at the manufacturing facilities. A change request to NSTS 07700, Volume XI, adding the program requirement to include tool control at the element manufacturing facilities, was approved by the Program Requirements Control Board (PRCB) on July 10, 1997. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1000 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Orbiter/Quality Assurance |  | The orbiter Reaction Control System (RCS) thruster valves continue to leak in flight. NASA has aggressively attacked this problem with some success. Procedural changes have improved thruster reliability, and the incidence of leakage has been reduced but not eliminated. | Continued attention must be focused on the elimination of the root causes of RCS valve leakage/failures. | HQ | 02/01/1997 | Leaking Reaction Control System (RCS) Thruster Valves | Several remedial actions have been and are being implemented as a result of a 1995 tiger team investigation into the causes of RCS valve leakage/failure. This has resulted in many procedural changes and several potential hardware improvement concepts. The procedural changes are reducing the number of in-flight thruster valve failures. Many of the hardware improvements are entering a development testing phase. Examples of procedure and hardware changes include: Preventative maintenance flushing. Water flushing of the RCS pilot operated valves (POV) was developed at the White Sands Test Facility (WSTF) and has been verified to remove iron nitrate contamination from the POV. Manifold thruster preventative change-outs. It is now required to change all thrusters on a manifold when that manifold is drained for any reason. The removed thrusters are sent to WSTF for water flushing and then returned to spares. Hard-filled manifold processing. The POV has demonstrated substantially better sealing capability in a fully wetted, hard-filled condition. KSC procedures have been implemented that provide the ability to maintain a hard-filled manifold configuration when performing work on the RCS pods. Minimization of moisture intrusion. Several additional recommendations have been implemented that specifically address minimizing moisture intrusion into the propellant system. Redesigned POV (RPOV). Another result of the critical examination of the RCS POV failure history was the recommendation that the oxidizer POV be redesigned to improve the ability to withstand nitrate contamination. The resulting RPOV is proceeding through buildup and development testing. The RPOV design addresses the areas in the current valve that are known to be sensitive to nitrate contamination. Minimization of oxidizer moisture and iron content. The presence of iron and water in nitrogen tetroxide greatly increases the potential for precipitation of iron nitrate internal to the POV pilot cavity. Therefore, a molecular sieve is being designed and fabricated to reduce the levels of iron and water in nitrogen tetroxide. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
999 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Operations-Processing/Upgrades |  | NASA plans to operate the Space Shuttle until at least 2012. This will require safety and operational upgrades to hardware, software, and logistics support. | NASA should complete Space Shuttle upgrades as soon as possible to take advantage of opportunities for earliest risk reduction and operational improvement. | HQ | 02/01/1997 | Space Shuttle Safety and Operational Upgrades | The SSP upgrade strategy is founded on the premise that safety, reliability, and supportability improvements must be made to support human space transportation until a suitable replacement is available. To manage and focus these efforts more effectively, the SSP established the Office of SSP Development on January 16, 1997. The Space Shuttle upgrades program is being implemented from a systems perspective. Upgrades will be integrated and prioritized across all flight and ground systems, ensuring that individual upgrades are compatible and that their impact is assessed across the entire program. A phased approach to the SSP upgrades is already under way. Phase I, to be completed by the year 2000, emphasizes safety and performance enhancements for the International Space Station (ISS) assembly and utilization. Ongoing efforts within all SSP elements are also under way to identify Phase II candidate and Phase III/IV studies. Primary emphasis remains on safety and risk reduction by improving reliability and maintainability, eliminating obsolescent components, and improving vehicle performance. As those upgrade candidates are identified by the program elements, the SSP is committed to expediting implementation to maximize safety and reduce overall program risk. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1009 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Reusable Solid Rocket Motor (RSRM)/Manufacturing & Process Control and Certification Testing |  | A substantial program effort is under way to eliminate the asbestos used in RSRM manufacture and replace it with more environmentally acceptable (i.e., "asbestos-free") materials. Although some of the materials tested to date meet specifications, they do not provide as high structural and thermal margins as the asbestos-containing materials. | To maintain flight safety, NASA should not eliminate the use of asbestos in RSRM manufacture. An environmental waiver should be obtained to continue its use in RSRM insulation, liners, inhibitors, and other motor parts in the event of future regulatory threat to the asbestos supplier. | HQ | 02/01/1997 | Environmental Regulations Resulting in Material Changes for RSRM | NASA currently has no plan to introduce nonasbestos-based replacements for asbestos-based components in RSRM production. The RSRM production and flight history are baselined with asbestos-based materials, primarily NBR rubber. Asbestos is also a constituent of liner and adhesives. The production, handling, and disposal processes for these materials are performed in compliance with strict state, Federal, and local controls and regulations regarding asbestos material. There are no currently identified regulations to ban production or use of asbestos materials in the RSRM supply chain. Because there is no existing or pending regulation, pursuit of waivers or exemptions is not applicable at this time. NASA considers it prudent to continue low-level development of possible alternative nonasbestos materials. This reflects NASA's sensitivity to the environment, worker safety and health issues, and the fact that the shelf life of these materials precludes the option to stockpile. This development effort is being carried out to provide limited contingency development at a routine pace. The recommendations by both the ASAP and the RSRM initiatives to find alternative materials are consistent with program policy documented in SSP letter MS 96-071, dated September 16, 1996. The policy seeks to balance flight safety and environmental protection goals. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
1008 | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN | Lengyel, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program/Reusable Solid Rocket Motor (RSRM)/Manufacturing & Process Control and Certification Testing |  | There are many material and process changes in work for the RSRM in response to both environmental regulations and obsolescence issues. A vital part of the certification program for these changes is the demonstration of the acceptability of the changes during an FSM firing. At present, FSM firings are scheduled at 2-year intervals instead of the 1-year or 18-month intervals previously used. | Considering the large number of changes in RSRM materials and processes and the importance of proper simulation of operating conditions in any certification test program, NASA should reevaluate its decision to have 2 years between FSM firings. | HQ | 02/01/1997 | Environmental Regulations Resulting in Manufacturing Process and Test Certification Changes for RSRM | The RSRM project presented an assessment of static test motor frequency to the PRCB on February 27, 1997, and recommended static tests at 1-year intervals. The recommendation was accepted by the PRCB. An initiative is under way to ensure that the maximum possible benefit is obtained from each test. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 11/01/2001
993 | Chesser, Charles - 0000000000 : NO@ADDRESS.GIVEN | Chesser, Charles - 0000000000 : NO@ADDRESS.GIVEN |  | Pressure Testing |  | Warnings and procedural notes do not reliably protect hardware from excessive pressure during test. | Use fail safe methods, such as re-configuring the test setup, to safeguard hardware under test pressure in lieu of warnings. | MSFC | 01/01/2001 | A valve was damaged by being exposed to excess pressure during testing because it was in the wrong configuration. The valve was in the 'closed' position when warnings and procedures stated to only test in the 'open' position. | No evidence is available, since no further valve testing was done due to Project termination, but the revised procedure should have kept the valve from accepting pressure in the closed configuration. | N/A |  |  | Public | Not Specified |  | 10/23/2001
994 | Chesser, Charles - 0000000000 : NO@ADDRESS.GIVEN | Chesser, Charles - 0000000000 : NO@ADDRESS.GIVEN |  | Respiratory problems from the laying up of fiberglass operation |  | Prior to conducting an operation which could generate particles, perform a particle count assessment to assure adequate ventilation/vacuum and filtering of air breathed. Also, train personnel in the proper use of all facility safety devices prior to commencing the operation. | Make assessments of all hazardous operations and adequately train personnel before conducting any hazardous operation. Minimize the exposure to airborne particles whenever possible. | MSFC | 01/01/2001 | Employees inhaled small fiberglass fibers from not using the vacuum system which was available and lack of adequate safety procedures. | None available; the operation was stopped and dismantled due to termination of the PROJECT. | N/A |  |  | Public | Not Specified |  | 10/23/2001
989 | Kolecki, Ron - 0000000000 : NO@ADDRESS.GIVEN | Kolecki, Ron - 0000000000 : NO@ADDRESS.GIVEN |  | ETU Laser Diode Pump Array Failure - Indium gasket short between contacts caused electrical failure |  |  |  | GSFC | 10/02/2001 | The ETU Laser for GLAS started showing signs of failing to lase. Initial failure investigations pointed to the laser Oscillator Diode. A detailed investigation disclosed that the cause of the short was an indium bridge within a screw hole in the pump array. In the diode pump array, the manufacturer uses a thin indium gasket to assure good thermal conductivity from the diode bar to the diode bar mount. The assembly torque used on the screws of this diode and the repeated assembly and disassembly of this particular diode stack caused the indium gasket to bridge/creep (smear across) the insulator. Basically, there were insufficient clearances around the holes in the indium gasket to allow proper alignment of the gasket to hole interface given that the indium will flow under pressure. | As this was an ETU, controls were put into place to prevent recurrence. To date, no flight hardware has been affected by this issue. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 10/15/2001
990 | Le, Suong - 0000000000 : NO@ADDRESS.GIVEN | Le, Suong - 0000000000 : NO@ADDRESS.GIVEN |  | Degradation of Pur-Ester Polyurethane Tubing due to Aging |  | The ester polyurethane is unsuitable for purging when used beyond its recommended shelf life. More critical, however, is the potential contamination problem due to the transfer of ester plasticizer to the instrument while under purge. The ruptured filter resulted in transferring particles from the degraded purge line to the contamination-sensitive SBUV/2 instrument. Subsequent cleaning, realignment of optics, and numerous levels of testing were needed to restore the instrument to specifications. This incident had a significant impact to instrument schedule and, therefore, cost. | Replace the Pur-ester polyurethane tubing with Teflon tubing, which is inert, resistant to moisture, clean, plasticizers-free, and has a shelf life of up to twenty (20) years. Install a more rugged 0.01 micron stainless membrane filter that can filter out smaller particles and withstand higher burst pressure. Install an in-line flow meter to control flow rate and to meet the instrument's flow specifications. Inspect the purge line routinely to ensure proper operation of filters, meters, gauges, and the source of purge gas. | GSFC | 11/24/2000 | White particulate residue from the ester-plasticized polyurethane purge line was flushed from the tubing wall and contaminated the NOAA N' SBUV/2 (Solar Backscatter Ultraviolet Radiometer) Flight Model (FM) 8 while the instrument was under purge. A sudden burst of high pressure and excessive flow through the purge line had possibly resulted in rupturing an in-line membrane filter causing the white platelet particles to pass through the inlet filter of the instrument. At the time, no flow meter was placed in the purge line. Although the MIL-HDBK-695, Rubber Products: Recommended Shelf Life, stipulates a shelf life of three (3) to five (5) years for polyester urethane products, this purge tubing had been in service for the past fifteen (15) years up to the time of the incident. Some polyester urethanes have poor resistance to humidity (MIL-HDBK-695). Urethanes also are not resistant to ultraviolet radiation. Both conditions existed during clean room storage of the SBUV/2 instrument. The material was visibly degraded as it became less flexible and opaque with residue buildup on the inside and outside of the tubing walls. |  | N/A |  | Science | Public | Not Specified |  | 10/15/2001
991 | Greanias, George - 0000000000 : NO@ADDRESS.GIVEN | Greanias, George - 0000000000 : NO@ADDRESS.GIVEN |  | Planning and Conduct of Hazardous Tests Require Extra Precautions (2000-2001) | Two ruptures of burst discs and an over pressurization of the cryostat helium tank occurred on the ground during integration and test of SIRTF. Precautions for planning and conducting hazardous tests should include high quality test procedures, documentation of and pre-test training for known test anomalies, easily understood readouts, test readiness reviews including test procedures confirmation for proper GSE & sensor maintenance, and involvement of quality assurance personnel throughout the pre-test and testing activities. | When planning tests that are potentially hazardous to personnel, flight hardware or facilities (e.g., high/low temperatures or pressures, stored energy, deployables), special measures should be taken to ensure that: Test procedures are especially well written, well organized, and easy to understand by both engineering and quality assurance personnel. Known test anomalies that history has shown to be inherent to the test equipment or conditions (including their likely causes, effects, and remedies) are documented and included in pre-test training. Readouts of safety-critical test control data are provided in an easily understood form (e.g., audible, visible or graphic format). Test readiness reviews are held, and test procedures require confirmation that GSE test equipment and sensors have been properly maintained. Quality assurance personnel are present and involved throughout the test to ensure procedures are properly followed, including prescribed responses to pre-identified potential anomalies. | (See Lessons Learned) | JPL | 12/31/2000 | Three failures occurred on the ground over a three-week period during integration and test of the Space Infrared Telescope Facility (SIRTF) cryostat at a contractor facility: Rupture of a Pressure Release Device (quotBurst Discquot) on Cryostat Fill-Side. During a helium top-off operation performed to place the cryostat in a safe standby configuration, unexpectedly slow helium transfer was noted by test personnel. This was later attributed to a clogged filter on ground support equipment (GSE) that had not been properly maintained. To speed the flow, test personnel intentionally closed the cryostat internal (see V3 in the graphic) and external (V4) fill valves in reverse order, contrary to the formal test procedure. This caused a pressure surge within the plumbing that ruptured the fill-side burst disc. The test crew was not adequately trained and staffed to deal with this test anomaly. Rupture of Burst Disc on Cryostat Vent-Side. A second incident ruptured the burst disc on the vent-side of the cryostat. A fitting on the GSE cryogenic servicing equipment had been removed and reinstalled without proper torqueing or a leak check. The leaky fitting allowed air to enter the flight system over a period of several days. Frozen condensates from the leak blocked the vent side plumbing and caused the failure. The root cause was the lack of a formal procedure for (1) maintaining the GSE, (2) verifying that there were no leaks within the GSE plumbing after connection to the cryostat, or (3) monitoring the GSE for leakage on a continuous basis. Cryostat Helium Tank Overpressurization. The blockage of the vent line described above caused over-pressurization of the helium tank above the maximum design pressure. Due to the blocked flow, the tank pressure increased even as the pressure downstream of the blockage remained stable. The tank temperature sensor readings should have alerted the test crew, but the readings were considered suspect. This lack of response to a safety-critical sensor indication may be attributed to lack of (1) confidence caused by previous sensor calibration and readout problems, (2) red-flag limits in the control software, and (3) careful real time scrutiny of the test data by cryogenic experts outside the core Cryo-Telescope Assembly (CTA) team. Equipment damage was limited to the two ruptured burst discs, but the incident resulted in a significant cost and schedule impact to the SIRTF project, and posed a potentially significant risk to personnel safety. [D] GSE Configuration When Fill-Side Burst Disc Was Ruptured Reference: SIRTF Cryostat Operations Failure Report, contractor internal report, March 27, 2001. Additional Key Words: test facility operations, facility safety, test equipment maintenance, GSE maintenance, QA oversight, test oversight, test plan | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 (quotEngineering Practices: Protection and Security of Flight Hardwarequot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/15/2001
992 | Duxbury, Thomas - 0000000000 : NO@ADDRESS.GIVEN | Duxbury, Thomas - 0000000000 : NO@ADDRESS.GIVEN |  | Spaceborne Imaging Camera Contamination (1999) | Contamination analysis does not always identify contamination sources or complex migration paths. Designs should keep camera systems and thermal control surfaces away from vent paths and/or keep sensitive surfaces covered or sealed. Designs should include mitigation measures, (application of heat) for water vapor contamination and when using structural composite materials consideration should be given to selecting low hygroscopic materials or using non-outgassing coatings. | Theoretical contamination analyses may not always identify all contamination sources and complex migration paths. This may require unanticipated decontamination of optical surfaces during mission operations. | Special attention should be placed on design and operational details when dealing with optical systems that are particularly sensitive to contamination. Develop spacecraft configurations that keep camera system components away from all outgassing sources and vent paths to the greatest extent practical. When using composite materials for primary spacecraft structure or instrument elements, consider the use of low hygroscopic materials. Also consider the use of non-outgassing coatings on composite structures to reduce hygroscopic absorption, which further reduces the possibility of outgassing. During periods of possible contamination, keep space-born camera optical components covered or sealed; or keep them warm to avoid cold surfaces that may attract contaminating molecules. Use heaters or direct sunlight on optical instrument radiators to raise internal temperatures to drive off contaminants. Do not permit sunlight directly on contaminated optical surfaces. If the contaminants are organic, sunlight ultraviolet may cause them to permanently darken and adhere to optical surfaces or thermal control surfaces. Additional key words: Subsystem and Instrument Development | JPL | 08/03/2001 | During first use after launch, the optical surfaces of the imaging camera onboard the NASA Discovery STARDUST spacecraft were found to be contaminated, thereby degrading the image quality. The cold operational temperatures of the camera CCD detector and optics offered a convenient "cold sink" for contamination molecules. This phenomenon occurs when free molecules migrate to the coldest available surface. This contamination may have originated from spacecraft outgassing and/or trapped contaminates within the camera. Such events have happened in the past on U.S. and international cold-biased instruments. Heat from internal heaters (or the sun for inorganic molecules) is commonly used to remove such contaminates, and has been used successfully on this mission to improve imaging quality. Following the successful removal of contaminants through the heating process, a recontamination of the camera optical surfaces occurred as the temperature gradient between the spacecraft and the camera optical components returned to its nominal value (warm contamination sources and cold optical surfaces). Using internal heaters again removed the contaminants. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.5 ("Engineering Practices: Materials, Processes, and Contamination Control"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 10/01/2001
987 | Olivier, Jean - 0000000000 : NO@ADDRESS.GIVEN | Olivier, Jean - 0000000000 : NO@ADDRESS.GIVEN |  | Chandra X-ray Observatory (CXO) Development Program Programmatic "Lessons Learned" |  | Stable Requirements are key to program stability. Do not allow requirements to creep. One step in this process is to involve all stakeholders in developing and finalizing requirements. Stakeholders may include potential development and operations contractors, engineering and other organizations and NASA Headquarters. Plan early in the program for operations considerations, making sure the operations organization is strongly involved in defining requirements and in the early design process to assure systems are user friendly. This is not easy to accomplish for either MSFC or the contractor, particularly in a schedule and funding constrained development environment where design features to enhance operations may result in features not envisioned by the design organization. To the maximum extent possible assure that the operations and verification databases, as well as, command and telemetry pneumonic are common. Often, to reduce cost, a contractor will propose the use of systems level Electrical Ground Support Equipment (EGSE) that was previously used on another program. This can make portability between operations and verification difficult, since Ground Support Equipment (GSE) Interface Control Document (ICD) is often obsolete by the time the program is ready for systems testing. Use of existing GSE may require both hardware and software upgrades. The operations organization should realize from the beginning that the development program may suffer schedule erosion, and should therefore develop contingency planning for operations procedure development in an environment where the operations database is not yet finalized. Spending effort complaining about the development program being late is not productive. Spend the necessary resources to provide for a strong systems engineering organization throughout the program. Assign managers for all interface control documents and layout a schedule for their development through baselining. Make sure the systems engineering manager has direct control of all manpower for systems analyses such as thermal, structural dynamics, error budgets, loads, mass properties, electrical power demand, orbital mechanics, etc. Do not overlook the need for strong systems engineering involvement in requirements and verification traceability. Make sure that one organization is responsible for end-to-end systems engineering for the entire payload including the payload ground operations system. Engineering of the entire system includes penetrating the total system design on both sides of an ICD rather than working just your side of it. When responsible for building a total systems analytical model (thermal, structural, dynamic, electrical, etc.) by assembling a number of analytical inputs from other organizations, systematically check the accuracy of these inputs before using them and perform sanity tests on the total model with simple yet carefully chosen boundary conditions to make sure it is correct. When verifying performance of optical elements or systems always cross check the results using another completely different test method. When required to use gravity off-loaders in the test of optical systems, it is essential that they be rigorously tested and correlated with analytical models under both nominal and off nominal conditions. Maintain a strong engineering involvement with the contractor from the beginning of the program, not just when you get into trouble. Encourage a sense of "ownership" and continuity of responsibility for all individuals involved in the program. In the case of engineering this can be helped greatly by insuring that the same individual remains responsible for a given technical discipline throughout the program. Assure that adequate funding and schedule reserve is budgeted at the beginning of the program, no less than 25% and possibly more depending on assessed technical risk. Before launch of any remotely operated satellite or other equipment, perform end-to-end tests of the flight system with the ground control system using the final flight and ground versions of hardware, software, database and procedures. The flight operations team should perform these tests. To the extent possible, each command type should be sent and verified. Commands that by their nature cannot be tested in this manner should be tested in a high fidelity simulator with the ground system and all hardware commands to the flight system should be verified using the ground system for functionality. Any mission critical verification that requires verification, in whole or in part, by analysis should be double checked or preferably analyzed in parallel by an independent party. This same principle should also apply to any operational commands that are generated based on analytical input. To the extent that resources permit, design the system with reserve capability, including failure tolerance, beyond that stated in the requirements. Never stop looking for undetected failure modes or potential risks throughout the entire program development and operational phases. Hold regular status meetings by telecon with the entire program team so that all parties remain knowledgeable of program status and issues. NASA management's main goal should be to provide help and guidance to their contractors. Monitoring progress is only a by-product of this effort, not its primary objective. Taking shortcuts in box-level testing is a gamble with poor odds. Spend the time to thoroughly verify the flight worthiness of hardware and software at the lowest level. Finding box-level problems during systems-level testing is much more costly and disruptive in the long run. If independent review teams are to be used, get them involved at Preliminary Design Review (PDR) and keep them involved in all major reviews, as well as in the resolution of critical issues as they arise throughout the program. Critically evaluate any hardware or software that a contractor wants to use from another program or verify by similarity. Independently assess its specifications and how it was used in former programs, as compared with your requirements. Be particularly wary if the previous program was classified and details are not available. Insist that the contractor provide all specifications to support your evaluation. Be especially cautious when dealing with highly complex scientific hardware where the developer is "the only one that understands how it works." This system should not be exempt from review by as knowledgeable a team of experts as you can assemble, even if they have to be brought in from another NASA center or independent organizations. For instance, the Advanced Charge-Coupled Device (CCD) Imaging Spectrometer (ACIS) CCD radiation test shortcomings may have been caught by such a team, if one had been assembled one early in the program. | Reiterating major lessons learned: Do not allow requirements to creep. Include operations in requirements definition and early design. Wherever possible, maintain common pneumonics for all components and sub-systems. Develop operational contingency plans to accommodate possible schedule delays. Provide strong systems engineering throughout the program life cycle. Organize to ensure proper analysis of critical interfaces. When verifying performance of optical elements or systems, always cross check the results using another completely different test method. Maintain a strong engineering involvement with the contractor from the beginning of the program, not just when you get into trouble. Assure that adequate funding and schedule reserve is budgeted at the beginning of the program. Before launch of any remotely operated satellite or other equipment, perform end-to-end tests of the flight system with the ground control system using the final flight and ground versions of hardware, software, database and procedures. Provide cross-checks for any mission critical verifications based, in any part, on analysis. To the extent that resources permit, make program decisions that provide the system with reserve capabilities that exceed the requirements. Never stop looking for undetected failure modes or potential risks. Hold regular status meetings with the entire program team so that all parties remain knowledgeable of program status and issues. NASA management's main goal should be to provide help and guidance to their contractors. Spend the time to thoroughly verify the flight worthiness of hardware and software at the lowest level. If independent review teams are to be used, get them involved at Preliminary Design Review (PDR) and keep them involved. Critically evaluate any hardware or software that a contractor wants to use from another program or verify by similarity. No system should be exempt from review by technical experts as you can assemble, even if they have to be brought in from outside. | MSFC | 05/03/2001 | Marshall Space Flight Center (MSFC) was responsible for the development of the Chandra X-ray Observatory, successfully launched in July, 1999. Chandra is the third of NASA's "Great Observatories." This captures program management lessons learned from Chandra's inception through its launch in 1999. |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/20/2001
988 | Glenn, Malcolm - 0000000000 : NO@ADDRESS.GIVEN | Glenn, Malcolm - 0000000000 : NO@ADDRESS.GIVEN |  | Ordinance/Firing Line Misconnect |  | The team did not follow the paper as written. The team did not call a time out and get help, even when they raised a question about proper performance of the task. If you or any team member is unfamiliar with a task, take whatever means necessary to understand the task before starting. The work team did not have much experience on the specific task. | Rigorously and deliberately follow the paper, step by step, every time you do a task. Call a time out if there is any question. Ensure you are familiar with the task and are comfortable doing the task. If you have any doubts, ask for help. Be aware of the task specific experience of people and assign tasks accordingly. Different people can be assigned to the task to balance light experience. When people cannot be balanced based on experience, leadership must recognize and highlight the job as one needing extra attention. Extra attention may include emphasis during briefings, a pre-job walk down or rehearsal, extra on-the-job observations and a post-job walkdown. | KSC | 01/01/2001 | At KSC, during performance of Space Shuttle external tank/solid rocket booster thrust post ordinance installation in the booster forward skirt, the frustrum separation cable was mistakenly connected. The job was to install ordinance components in flight hardware. There were three NASA Standard Initiators (NSI) to install, and cables to connect to two of the NSIs. The work team, consisting of three team members, did this work correctly. Then one of the team members noticed the third NSI did not have the cable connected and asked a question about the connection. The work team then connected, in error, the third cable. A problem report was written and the mistakenly connected cable was disconnected and safed. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 08/20/2001
986 | Winters, John - 0000000000 : NO@ADDRESS.GIVEN | Winters, John - 0000000000 : NO@ADDRESS.GIVEN |  | Tight scheduling and New Unfamiliar Equipment in Hazardous Environments |  | Using new equipment in hazardous environments without full understanding all the capabilities and restrictions can easily cause injury or equipment destruction. Add to this dangerous situation the "hurry up, let's get this job done" attitude, is only adding fuel to an accident waiting to happen. | Be sure training is thorough. All persons who will use the equipment (supervisors and technicians) need to understand the application and restrictions of the new equipment. Do not let tight time constraints take precedence over any activity. Ensure all personnel understand their safety and other performance responsibilities and fully understand the new equipment and tasks. | JSC | 08/01/2001 | High voltage linemen were on very tight time constraints and were attempting to measure the voltage in a 15kV fuse cabinet. They were going to measure the voltage from phase to ground of approximately 7630 volts. The equipment they were using is engineered to contact high power lines or transformers out in the open for direct readings. The linemen had contacted the phase conductor with one probe of the test meter and were attempting to make contact with a ground point in the fuse cabinet of the transformer when an electric flash occurred, indicating a ground fault. The ground fault went through and out of the back of the meter ground faulting to the cabinet enclosure. No one was injured but the fault caused an immediate interruption of power to the site electric feeder. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/07/2001
984 | Greenslade, Linda - 0000000000 : NO@ADDRESS.GIVEN | Greenslade, Linda - 0000000000 : NO@ADDRESS.GIVEN |  | Acquisition Management for In-house Development Efforts |  | In-house development of complex flight hardware systems requires early and sustained attention by a dedicated, experienced procurement/technical management team. With the appropriate balance of procurement and technical personnel, many of these issues could have been avoided. | An integrated, dedicated and experienced procurement/technical management team is essential beginning in the early phases of the Project. Advance procurement planning and effective technical management will ensure development of realistic schedules and will result in the most cost-effective acquisition strategies for the Project. A well-developed acquisition plan should also incorporate: technology readiness and impact on the development cycle; best approach(es) to meet the unique needs of the Project; effective contract structure/contract type/incentive plans; and work-arounds and dual procurement strategies, where appropriate. | GSFC | 10/18/2000 | An in-house instrument build required a significant number of hardware purchases from outside vendors. A one-year acceleration in the development resulted in the need to procure most of these items on an accelerated schedule. While the technical team worked hard to develop the appropriate procurement strategy and schedule for these hardware procurements, some unfortunate technicalities due to their procurement inexperience resulted in delayed procurement schedules, increased cost, and in one case, the need for re-competition. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/07/2001
985 | Dollberg, John - 0000000000 : NO@ADDRESS.GIVEN | Dollberg, John - 0000000000 : NO@ADDRESS.GIVEN |  | Banana Plug Test Leads |  | The exposed banana plug was operating at 120v DC which can cause damage to equipment or injury to personnel. | Modify existing banana plug leads in the inventory and to procure only new banana plug test leads that provide a deadfacing capability. | KSC | 08/01/2001 | During Space Station hardware testing at Kennedy Space Center, a technician was in the process of connecting a current probe banana type plug test lead into a breakout box when he observed an arc. The arc caused the circuit protection to trip which safed the system. The exposed plug had contacted a grounding strap which caused the arc. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/07/2001
981 | Sampson, Mike - 0000000000 : NO@ADDRESS.GIVEN; Brusse, Jay - | Sampson, Mike - 0000000000 : NO@ADDRESS.GIVEN |  | Reverse Polarity Concerns With Tantalum Capacitors |  | By nature of their construction, tantalum capacitors (both wet slug and dry slug styles) are polar devices that are susceptible to performance degradation and/or catastrophic failure if reverse biased. This behavioral characteristic has always been known, but recent experiences have reminded us of the importance of proper installation and circuit design when using this type of component. Historically, reverse polarity failures have been observed that resulted from: Incorrect initial installation (part installed backwards) Incorrect installation during rework (original part installed correctly, but replacement part put in backwards) Correct circuit design, but incorrect artwork on the printed wiring board (part installed correctly according to the artwork, but actually in backwards) Incorrect circuit design (printed wiring board artwork correct per circuit layout, but design error resulted in parts in backwards) The NASA EEE Parts Assurance Group (NEPAG) is currently investigating the reverse polarity behavior of tantalum dry slug chip capacitors because there is little definitive information in the literature on this subject. Preliminary results will be available in the last quarter of 2001. Guidelines Regarding Reverse Bias Application of Tantalum Capacitors Wet Slug (Non-Solid) Tantalum Capacitors Ex.- MIL-PRF-39006 CLR79, CLR81, CLR90 and CLR91 types Capable of handling up to 3 volts of reverse polarity regardless of capacitor voltage rating. Leakage current characteristics will be higher than normal. Exceeding 3 volts reverse bias will cause rapid deterioration of the capacitor leading to catastrophic failure (short circuit) Polarity identification is generally indicated by a "+" or a stripe on the anode termination. Also, hermetically sealed, tubular case, wet slug styles have a crimp towards one end of the case that may be used to identify the anode ("+") end. Exceptions or variations to these conventions may exist. Dry Slug (Solid) Tantalum Capacitors Ex. MIL-PRF-39003 and MIL-PRF-55365 CSR, CSS and CWR types Sensitive to reverse polarity but tend to be much less so than their wet slug counterparts. May fail explosively under reverse bias, even catch fire. May survive "indefinitely" at room temperature with up to 15% of their voltage rating applied in reverse. Capacitors will have a higher leakage current than in the forward direction, but this may be undetectable in the majority of heavily derated circuit applications. The circuit may operate properly for many hours (hundreds or even thousands) before failure. Influential factors in life expectancy are believed to include: manufacturer, style, size, capacitance, moisture content and of course rated voltage. "Chip" styles may be more vulnerable to failure under reverse bias than hermetically sealed styles because moisture may accelerate failure. NEPAG is investigating the effect of moisture. "Chip" styles are more prone to being installed improperly because they may be very small and the polarity identifier can be hard to see. Conformally coated "chip" styles (ex.--CWR06) typically identify the polarity by a small projection "nub" in the center of one termination representing the anode (+) termination Molded case "chip" styles (ex.--CWR09 and CWR11) identify the polarity by a beveled edge in the case and/or a polarity bar marked on the case Polarity identification is generally indicated by a "+" or a stripe adjacent to the anode termination. Exceptions or variations to these conventions may exist. One example of such an exception is the tubular case capacitor made in accordance with MIL-PRF-39003/10 which requires a stripe to identify the cathode "-" termination | Based on the aforementioned concerns with reverse bias application of tantalum capacitors, the following suggestions are provided. Due to possible variations in the conventions used to identify capacitor polarity, careful review of the capacitors marking requirements (per MIL specification or per manufacturer data sheet) must be performed to ensure proper orientation during installation Carefully review circuit designs and printed wiring board artwork for correct polarity of tantalum capacitors Carefully inspect all tantalum capacitors following installation to ensure their polarity matches the artwork (or corrective action instructions if the artwork is faulty) Photograph populated boards at a magnification, fidelity and from a perspective capable of showing the polarity of the tantalum capacitors Carefully review the polarity of all tantalum chip capacitors replaced as a result of rework | GSFC | 06/12/2000 | Most tantalum capacitors are sensitive to the polarity of the applied voltage. Incorrect installation and/or improper circuit application that subjects the capacitors to reverse bias may lead to performance degradation or catastrophic failure (short circuit) of the capacitor. Dry slug tantalum capacitors can survive being installed backwards for long periods of time (thousands of hours) when derated to 15% or less of rated voltage. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/07/2001
982 | Sampson, Mike - 0000000000 : NO@ADDRESS.GIVEN; Brusse, Jay - | Sampson, Mike - 0000000000 : NO@ADDRESS.GIVEN |  | Retention of Traceability Data for EEE Parts |  | Recently, NASA Goddard Space Flight Center (GSFC) has observed that many hardware builders repackage EEE parts during receiving inspection and discard the part manufacturer's original shipping containers. This practice can lead to loss of vital lot traceability information because in many cases, the shipping containers contain unique lot information that may not be provided by the part markings or other shipping documentation (Certificates of Compliance, etc.) that is typically retained by the user. This problem may also occur if the user discards the paperwork and/or packaging when all the parts in the package have been used. Accurate and detailed EEE part lot traceability information may be critical in order to perform risk assessments, circuit performance analysis and failure investigations especially when problems are reported for parts that may already be assembled into hardware or when troubleshooting on-orbit anomalies. The EEE part manufacturer generally establishes lot traceability through a combination of the manufacturer's part number, CAGE code and a unique production Lot Date Code (LDC). Generally speaking, the production LDC identifies a group of parts of the same style and ratings that are manufactured from the same raw material lots and are processed through all critical manufacturing steps and tests as a single group. As such, the production LDC is an invaluable lot identifier. Unfortunately, this production LDC is generally NOT marked directly on the parts (especially for smaller chip style components where there may be insufficient room for any part markings) and is sometimes only provided to the user on labels affixed to the original shipping containers for the parts (i.e., C of C may not contain production LDC info). It is important to note that a production LDC is not the same as the inspection LDC (or marking LDC) which is commonly marked directly on the part and shipping documentation. (For MIL specification products, the LDC marked on the parts is the inspection LDC). The inspection LDC generally represents the year and week when a group of parts is subjected to the manufacturer's final test and inspection (end of production test). It is very probable for a manufacturer to submit many different production lots of the same part type to final inspection during the same week. As such, each inspection lot may be me made up of multiple production lots. When a problem is later discovered that is attributed to a specific production lot, the user may not be able to effectively assess risk if the only traceability data they have on file is the inspection LDC. Figure 1 helps to illustrate a recent example where disposal of the manufacturer's original shipping containers resulted in loss of effective lot traceability. This figure shows the original shipping container of one tantalum chip capacitor manufacturer. A label affixed to the container by the manufacturer provides vital lot traceability information including procurement part number, manufacturer part number, CAGE Code, production LDC and inspection LDC. The other shipping documentation that accompanied this manufacturer's shipment did NOT contain the production LDC. Different users of this manufacturer's parts discarded this container (and label) after performing receiving inspection or stocking or kitting the parts. When problems with this manufacturer's parts were later reported, having only part number and inspection LDC (from part markings and C of C) made traceability back to the manufacturer's original production traveler information exceedingly difficult, if not impossible. Therefore, valuable lot pedigree information could not be obtained to assist in the risk assessment process. [D] | To assist in effective lot traceability it is suggested to require OEMs and their contractors to retain ALL of the EEE part manufacturer's original shipping documentation AND packaging information. If shipping containers cannot be retained, then pertinent labels should be copied or carefully removed for storage along with other pertinent receiving inspection data. In addition, it is suggested to retain this traceability information for the duration of the mission in the event that this data is required to address on-orbit anomalies. | GSFC | 04/16/2001 | Effective, critical traceability of EEE parts may be lost if original shipping containers and documentation are not retained by original equipment manufacturers (OEMs) and their contractors. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/07/2001
983 | Greenslade, Linda - 0000000000 : NO@ADDRESS.GIVEN | Greenslade, Linda - 0000000000 : NO@ADDRESS.GIVEN |  | Fixed Price Spacecraft Contracting |  | Fixed price spacecraft contracting works best when interfaces are well defined. Since the design of the spacecraft (and other mission elements) revolves around the instrument's design and function, it is crucial that the concept, requirements, technology, design and engineering model will result in open-ended support requirements and numerous contract/cost/schedule changes throughout the implementation phase, which reduces the efficiency of the initial bus procurement. | Delay finalization of the spacecraft until interfaces are defined to a reasonable confidence level, so as not to significantly impact spacecraft configuration or the fixed price, OR proceed with a study period with multiple competitors until interfaces are sufficiently defined, with down-selection and final price determination occurring at the end of the study period. Additionally, limit the contribution of government furnished equipment to those items that "make sense." If the contractor can provide the equipment at a reasonable cost and risk, include it in the fixed price contract; this will minimize impacts to the fixed price effort. | GSFC | 10/18/2000 | Procurement of a fixed price spacecraft was a cost effective strategy to reduce total mission cost. However, the impact of undefined interfaces at the start of the contract and the uncertainties related to government-furnished hardware, resulted in some costs, which could have been avoided. Additional cost savings could have been realized if the instrument design and other interfaces were in a more advanced state. |  | N/A |  | Science | Public | Not Specified |  | 08/07/2001
980 | Grady, Kevin - 0000000000 : NO@ADDRESS.GIVEN | Grady, Kevin - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Interface Simulators |  | The approach which the Project undertook was to develop simulators which electrically duplicated the spacecraft side of the interface. These simulators were then shipped to the instruments on a rotating basis. Tests were performed with instrument engineering model hardware and the flight instruments as well. These tests were performed on the flight instruments, after the flight instrument was assembled, but before the lengthy environmental and calibration test phases which complex instruments demand. This gave the instrument developers the confidence that their instrument would be compatible with the spacecraft, when the time came to integrate into the spacecraft. In doing this, it avoided the possibility of having to make a significant instrument modification, as a result of an interface incompatibility, after the instrument had been delivered. This in turn could have resulted in the need for additional regression testing (T/V, EMI/EMC) and the attendant schedule impact. In addition to the benefits of isolating design or workmanship errors in the instrument's spacecraft interface early, it provided an early opportunity for the instrument teams to work in the environment that they would be seeing, after they delivered their instrument to the spacecraft facility. Command and telemetry databases were hosted on the spacecraft interface simulator, and building block procedures, which were to be executed later at spacecraft level, could be debugged at this early opportunity prior to instrument delivery. The planning and information interchange necessitated by the use of this interface simulator hardware caused spacecraft and instrument teams to become cognizant of integration and test issues much sooner than they likely would have. This led to a Terra instrument integration activity which was virtually trouble free. The spacecraft interface simulators deployed during the instrument integration and test phases played an enormous role in the eventual ease of instrument integration. The Terra experience is a strong endorsement for the use of spacecraft simulators at the instrument developers' facility during instrument integration and test. This is particularly true when significant development risk resides on both sides of the interface and the complexity of the instruments is such that a significant amount of time is invested during the instrument environmental test flow. | The spacecraft interface simulators deployed during the instrument integration and test phases played an enormous role in the eventual ease of instrument integration. The Terra experience is a strong endorsement for the use of spacecraft simulators at the instrument developers' facility during instrument integration and test. This is particularly true when significant development risk resides on both sides of the interface and the complexity of the instruments is such that a significant amount of time is invested during the instrument environmental test flow. | GSFC | 06/12/2000 | The Terra spacecraft relied on several state-of-the-art developments, as a result of the demanding resource requirements of the Terra instrument suite. These spacecraft development activities were performed in parallel with five state-of-the-art remote sensing instrument developments. Due to the nature of this extensive development, it was anticipated that difficulties and schedule challenges would arise on both sides of this interface. The challenge, which faced the Project, was how to mitigate the risk of verification of this interface, particularly when that flight interface might not be verified until very late in the systems integration schedule. The challenge was compounded by the fact that two of the Terra instruments were international instruments. |  | N/A |  | Science | Public | Not Specified |  | 08/07/2001
979 | Grady, Kevin - 0000000000 : NO@ADDRESS.GIVEN | Grady, Kevin - 0000000000 : NO@ADDRESS.GIVEN |  | Thruster Plume Impingement |  | Several weeks of investigation proceeded, and a significant amount of analysis and modeling were performed. It was determined that the impingement of the thruster plumes from two of the attitude thrusters were producing a large torque, by impinging on the Terra solar array. The Terra solar array is a very large flexible blanket type array. The location of the array during the maneuver resulted in the worse possible orientation for plume interaction, and it also resulted in the largest possible moment arm between the center-of-pressure and center-of-gravity. The combination of these two factors resulted in the larger than expected disturbance torque, which led to the attitude disturbance and the shutdown of the orbit raising maneuver. Subsequent to numerous analyses and simulations, an optimal orientation for the solar array during the maneuvers was determined, and a modified thruster torque transformation matrix were developed. The torque transformation matrix accounted for the residual disturbance which was still induced, even with the solar array in the optmized orientation. A series of smaller orbit raising maneuvers were performed to verify the software changes. The maneuvers executed without problems. Long duration maneuvers were then performed. These maneuvers were likewise successful. Terra reached its operational orbit and began flying in formation with Landsat 7 in February 2000. Upon reviewing the process on why this error was not detected before launch, it was determined that no direct modeling of the plume impingement phenomena was ever performed. Plume effects were accounted for via a design allocation process; however, the torque that was allocated in the design process was inadequate. The allocation was not verified via a closed-loop simulation simulation. This experience reaffirms the value of performing high fidelity 3-axis simulations prior to launch. This is particularly true as spacecraft grow, and surface areas become larger. The utility of high fidelity 3-axis simulations is unquestionable, and should be performed as a routine and continuous part of the spacecraft design process. | This experience reaffirms the value of performing high fidelity 3-axis simulations prior to launch. This is particularly true as spacecraft grow, and surface areas become larger. The utility of high fidelity 3-axis simulations is unquestionable, and should be performed as a routine and continuous part of the spacecraft design process. | GSFC | 04/23/2000 | On January 11, 2000, while the Terra spacecraft was attempting its first long orbit raising maneuver, the maneuver was prematurely terminated after 11 seconds of the burn. The burn was halted due to the fact that on-board attitude tolerance limit exceedences were detected. The flight computer correctly aborted the maneuver. There was no time critically for executing the maneuver on that particular day nor at that particular orbit, therefore a rigorous investigation ensued. This maneuver had been preceded by a calibration burn, which was analyzed and deemed to be nominal. | All subsequent orbital raising maneuvers were nominal. | N/A |  | Science | Public | Not Specified |  | 08/06/2001
978 | Grady, Kevin - 0000000000 : NO@ADDRESS.GIVEN | Grady, Kevin - 0000000000 : NO@ADDRESS.GIVEN |  | End-to-End Testing |  | The Terra development schedule had always planned to perform end-to-end testing between the spacecraft and the EOS control center as soon as the ground system was capable of such testing. The initial test between the satellite and the ground system was in fact conducted while the spacecraft was in spacecraft-level thermal/vacuum test. The Terra housekeeping command and control links were exercised, just prior to completion of the Terra thermal/vacuum test. Due to unforeseen problems in the launch vehicle and the ground system, this initial test would prove to be almost two years before the launch of Terra. When the decision was made to change the implementation of the Terra ground system, due to the fact that a number of technical problems were not reaching resolution, the resolve to execute rigorous end-to-end testing became even more critical. A decision was made in the fall of 1998 to incorporate a new control center software package. The software was planned for completion in the spring, with the launch of Terra scheduled for the summer. Schedule pressures could have forced a lesser amount of allocated time for end-to-end testing, however the Project adopted the philosophy that no rigor be compromised, and a comprehensive test flow was adopted. Where early testing was possible with preliminary deliveries of the ground software, the philosophy was to always regression test when a subsequent software delivery became available. The spacecraft and ground teams performed tremendously in spite of difficult and challenging circumstances. Both S-band and Ku-band tests were executed, using the NASA Compatibility Test Van (CTV) which had been shipped to the launch site for this very purpose. The early orbit mission activities were tested and retested, validating the hardware, software, and perhaps most importantly the people. The lesson learned from the success of Terra's early communications success, is that there is no substitute for real life end-to-end testing. In Terra's unique circumstances, it placed a tremendous demand on the spacecraft and ground systems personnel who had to complete the software development, launch preparations and end-to-end testing on a compressed schedule. All who were involved with Terra will agree that there should be no compromise when it comes to such critical tests between the flight and ground segments. | The lesson learned from the success of Terra's early communications success, is that there is no substitute for real life end-to-end testing. In Terra's unique circumstances, it placed a tremendous demand on the spacecraft and ground systems personnel who had to complete the software development, launch preparations and end-to-end testing on a compressed schedule. All who were involved with Terra will agree that there should be no compromise when it comes to such critical tests between the flight and ground segments. No compromises should be made when it comes to pre-launch end-to-end testing. | GSFC | 03/25/2000 | The successful early mission on-orbit space-to-ground communications between the Terra spacecraft and the EOS Control Center is a reaffirmation of the value of rigorous pre-launch end-to-end testing. The Terra mission has experienced virtually trouble-free space-to-ground communications from launch and ascent, through the present completion of instrument activation. This success is a direct product of the mandate to perform rigorous end-to-end testing prior to launch. |  | N/A |  | Science | Public | Not Specified |  | 08/06/2001
977 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Shareware/Freeware as Integral Elements of Computer Systems |  | Use of shareware/freeware applications within systems should be carefully considered since many of these applications do not provide long (or short) term user support. If shareware/freeware is used, identify its use as a risk to the system and prepare contingency plans for system use in the case where user support cannot be obtained. | Carefully consider the long-term support issues that are inherent with use of shareware/freeware within systems. | HQ | 07/26/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance (OSMA) began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR) (http://solar.msfc.nasa.gov), currently one of NASA's primary distance learning resources. The intent of the initial development effort was to design and implement a prototype system for the Safety and Mission Assurance discipline. One of the considerations for that development effort was to concentrate development activities on basic system functionality (such as the Learning Management System that managed testing, test results and user account information) and course materials. Many other functions such as website search capabilities were accomplished using "shareware" or "freeware" in order to reduce costs and/or development time. Most of these software packages performed well in the system; however, as other changes were made to the system or external events such as Year 2000 occurred, problems arose. These problems were mostly minor and related to the lack of support from the developers of these shareware/freeware applications. In each case a solution was found for the problem but not without impacting resources that were developing new capabilities or course materials. | Shareware/freeware is being phased out of system use as time and resources permit. | N/A |  |  | Public | Not Specified |  | 07/31/2001
974 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Training Course Development |  | Contract schedules need to be developed based on a clear understanding of the work to be completed, and a realistic assessment of the availability of the people to perform the work. Clearly define the scope, content, duration and magnitude of support that SMEs are expected to provide and obtain an informed consent from the SMEs for their participation prior to initiating the course development process. Because an individual is a Subject Matter Expert (SME) in a topic does not automatically make the individual an expert in developing training/course materials on the subject. These individuals need to be educated to effectively perform their functions. In the absence of other documentation, training materials developed by consensus may serve to informally document standard practices. | Identify the availability of the government resources up front and establish government review cycles based on that availability. If possible, make arrangements for the SMEs to be assigned as a primary assignment for the duration of the course development process rather than as a collateral assignment. Always plan to provide introductory course development training to Subject Matter Experts before they attempt to create training materials. | HQ | 07/26/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance (OSMA) began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR) (http://solar.msfc.nasa.gov), currently one of NASA's primary distance learning resources. Since the intent of the initial development effort was to design and implement a prototype system for the Safety and Mission Assurance discipline a large percentage of the current SOLAR course offerings are Safety and Mission Assurance related. The approximately 70 Safety and Mission Assurance courses available on SOLAR were developed using teams of subject matter experts (SMEs) working in conjunction with the prime contractor (BDM now TRW). After the determination that a SOLAR course needs to be developed a "standard" module development process is followed. The following is a greatly simplified version of that process. Note: To review the detailed process information for course development as contained within the SOLAR Documentation Suite, contact Feedback and Support on the SOLAR website (https://solar.msfc.nasa.gov). The simplified process is as follows: A Lead SME and supporting SME(s) are identified that can provide the technical content to be contained within the course. The SMEs work with the prime contractor to define the scope of the training course and document that scope in a course synopsis and course roadmap. The SMEs provide the prime contractor with appropriate reference materials to develop an initial draft course. The Lead SME coordinates a detailed technical review of the initial draft course by the supporting SME(s) and provides comments back to the prime contractor. The prime contractor responds to the SME comments and prepares a draft course for SME review and acceptance. The Lead SME coordinates a review of the acceptance draft to evaluate how well the initial comments were incorporated into the acceptance draft and to identify and resolve any remaining concerns/corrections. The prime contractor cleans up any corrections and prepares the course for release. The Lead SME performs a final clerical review of the course and then approves the course for review by the Discipline and Agency Training Administrators. This process was developed with several goals in mind. First and foremost we wanted to capture knowledge from subject matter experts and capture that knowledge in a form that was readily shared with others. Second, as much as possible, we wanted all courses to represent NASA practice rather than Center specific practices. So the team of SMEs was required to synthesize information concerning individual Center practices into a single course applicable across all of NASA. Third, all of the course materials were to be comprehensive, clear and concise. The teams of SMEs were very successful in meeting these goals as evidenced by the body of courses that are available on the Safety and Mission Assurance portion of SOLAR. The process of developing courses was not without difficulties. For the most part the SMEs (both Lead SMEs and support SMEs) assigned to support the development of these courses did so on a collateral duty basis. They were assigned to support the course development on a part time or time available basis. This led to problems associated with the contractual schedule for course development. The initial contract task orders were established with very specific schedule milestones for the contractor to meet during the course development process. Since the SMEs were not exclusively assigned to support course development activities it was in many cases difficult, if not impossible, for the teams of SMEs to meet review deadlines. The Project Manager was subsequently required to spend more of her time focusing on shepherding the SMEs through the course development process and less on the overall project. It also became clear that while the SMEs were truly experts in their specific fields, their experience in developing training or course materials (especially web-based training), using the web, and working on this specific contract varied from none to minimal. This necessitated the development of an education process for all SMEs to define their roles and responsibilities, explain the development process and clarify the schedule requirements. This information was provided to the SMEs in a hardcopy package prior to the initial course development teleconference and was then discussed at length during the initial course development teleconference. Making adjustments to the course development process such as establishing the government review periods based on the availability of the SMEs and providing the SMEs with a "formal" education in the contractually specified course development process improved productivity. Of note was one unexpected outcome of the use of SMEs from various Centers to develop consensus course materials. In many cases, there were no documented Agency level standard practices related to the topics covered in the courses. The release of the courses in some cases served to informally document these standard practices. | As new contract task orders were developed, increased time for the SME review cycles was added to the process. Delays attributable to SME availability has been reduced. Detailed SME packages were developed which explain the course development process and responsibilities. Where these packages have been used the SMEs have not needed as much guidance from the Project Manager and have been able to work more independently. | N/A |  |  | Public | Not Specified |  | 07/31/2001
975 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Role of Marketing in System Use |  | A targeted roll out campaign for web based information systems are effective in building an initial user base. | Include a roll out campaign for introduction of web-based information systems. | HQ | 07/25/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance (OSMA) began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR) (http://solar.msfc.nasa.gov), currently one of NASA's primary distance learning resources. The intent of the initial development effort was to design and implement a prototype system for the Safety and Mission Assurance discipline. Since web-based distance learning was an untried technology within NASA, the development team determined that an extensive marketing campaign was needed to inform the potential users and their supervisors of the availability of the web-based training capability. The marketing plan included an extensive roll-out campaign that visited each of the NASA Centers, the Jet Propulsion Laboratory, White Sands Test Facility and NASA Headquarters after the 1997 release of the prototype system for use. As part of the roll out campaign an informational package was developed that included: An information folder that related the web-based distance learning capability to the NASA Strategic Plan and explained the benefits of the system Handout information sheets that included: A message from the Associate Administrator for Safety and Mission Assurance Points of Contact at each of the NASA Centers A list of all of the Safety and Mission Assurance training sources including the web-based distance learning training site A list of all of the available web-based courses A series of instructions for first time users on how to access and use the system 3. A business card with the training site logo and web address 4. A sticker with the training site logo and web address The detailed roll out for each facility was coordinated with each Center's PDI Point of Contact. The basic roll out was intended to include a formal overview session with senior Center and Safety and Mission Assurance management. In addition each sessions with the employees were conducted using formal briefings, hands-on training sessions or both depending on what the Center PDI Point of Contact and management desired. A copy of the information package was provided to each participant of any of the roll out sessions. As a part of the tailoring performed at each Center, the PDI Points of Contact also determined the target audience for the roll-outs (safety and mission assurance only or all disciplines) and prepared and distributed announcements, notices and related articles in local publications as appropriate. In addition to the Center focused roll outs we also provided separate focused presentations to groups such as the Procurement Conference, Program/Project Management Initiative and the Headquarters Code Training Points of Contact. [D] As the graphic indicates, after each of these roll out visits we noted an increase in the number of system users and course completions. The roll outs established the initial user base for the web-based distance learning system and allowed a comprehensive demonstration of the capabilities of the prototype system. The roll outs not only increased the user base, but also established contacts with representatives from other disciplines that attended the roll outs. Several of these contacts wanted to use the system's capability for providing training within their discipline or specialty. In this respect the roll outs also provided the opportunity and impetus to expand the system beyond the safety and mission assurance discipline and into the system now known as SOLAR. |  | N/A |  |  | Public | Not Specified |  | 07/31/2001
976 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | User Feedback (Operational) Testing |  | Use of a User Feedback (or Operational) Test is effective in identification of system weaknesses as well as weaknesses in assumptions applied to the development process. In addition to identifying shortfalls in the system the User Feedback Test can also helps in determining the capability of the users to operate the system. | Conduct a User Feedback (or Operational) Test prior to system release. | HQ | 07/26/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance (OSMA) began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR) (http://solar.msfc.nasa.gov), currently one of NASA's primary distance learning resources. The intent of the initial development effort was to design and implement a prototype system for the Safety and Mission Assurance discipline. Since web-based distance learning was an untried technology within NASA, the development team determined that before initial system release a User Feedback Test was required to exercise the system and identify problems from a user perspective. (Since this test was conducted under expected operating conditions using a portion of the expected user base it could also be considered an operational test). Not surprisingly the test results identified a series of changes that should be made to the system before production release. These included: Adding acronym and test buttons to the system navigation aids frame. Improving the legibility of embedded forms by using Portable Document Format files Providing clear indications of what each hyperlink identified within the course work does (glossary vs. more course material vs. reference, etc.) While identification of changes to features and other improvements of that type were expected outcomes of the User Feedback Test we were not prepared for one of the findings that conflicted with one of the primary assumptions we'd made as we initiated design. We had assumed that even though the Internet and the world-wide-web were relatively new, most of the NASA workforce would have enough familiarity and capability to use the web-based distance learning capability without additional assistance. The test results indicated otherwise, we had a wide spread of web user capability from experienced to novice and if we wanted the web-based distance learning capability to succeed on a wide basis within NASA additional support would be required. (As a note while most new users/potential users now have enough basic internet/web skills to navigate the SOLAR web-site we still experience some difficulties when users are required to perform non-routine web activities, for example downloading and integrating plug-ins required for system use. Therefore the introduction of new capabilities that require non-routine web activities needs to be well thought out and should include arrangements for support of users.) In response to the results of the User Feedback Test an upgrade to the system was provided that included a more extensive tutorial "Web-Workshop" to the user help features. This "Web-Workshop" was oriented to the novice web user and included topics such as Browser Basics, Screen Resolution, Plug-ins and Helper Applications as well as an Explanation of System Features. Examination of the User Feedback Test results also was a factor in including hands-on system demonstrations as a part of the system roll out and marketing campaign. A secondary outcome from the test was the identification that the pace of individual users taking the training varied much more than we had originally anticipated. Our original plan was to identify a "suggested" time to complete each module based upon an "average" user; however, after noting the wide variation in the time required to complete modules we decided to play-down the "suggested" times so as not to stigmatize slower self-paced learners. |  | N/A |  |  | Public | Not Specified |  | 07/31/2001
970 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Planning for Transition of Project Management Responsibilities |  | The time to start transition planning for any transfer of functional responsibility is immediately after the decision is made that a transition will occur, regardless of how far in the future that transition may take place. Early planning allows the project participants the opportunity to coordinate a responsibility transfer concurrent with existing and planned work rather than being controlled by external factors and forced to defer project activities. | Initiate planning for transfer of responsibilities as soon as the decision to make the transfer occurs. If a project is a proof-of-concept activity like the original PDI distance learning project, the development work should include planning to transition to full operating capability. | HQ | 07/26/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance (OSMA) began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR) (http://solar.msfc.nasa.gov), currently one of NASA's primary distance learning resources. The intent of the initial development effort was to design and implement a prototype system for the Safety and Mission Assurance discipline. OSMA managed the project and the Training and Development Division at NASA Headquarters (Hereafter referred to as the Sponsor) provided the funding. The only stipulation that the Sponsor made was that whatever capability was developed it needed to be adaptable for use across all of the Agency's functional disciplines. The prototype distance learning system was successful and did evolve into SOLAR which is a multi-discipline Agencywide distance learning system. As part of the decision to release SOLAR, OSMA and the Sponsor agreed that since the training materials were no longer limited to just the Safety and Mission Assurance discipline, that at some point in time the Sponsor would assume responsibility from OSMA for day-to-day management of the overall system. OSMA and the other functional discipline areas would retain responsibility for their individual discipline segments of the system including their specific course materials. No milestone was established for the transition of responsibility and no planning was conducted to prepare for the transition. Both the OSMA Project Team and the Sponsor assumed that there would be adequate opportunity to plan and prepare for the transition of responsibility. Unfortunately, changing needs within OSMA dictated identification of a transition date with short notice for planing, preparation and implementation. Of course no time is a perfect time for a transition, which was also the case here as several other issues were also consuming both the SOLAR Project Team and the Sponsor's time. Since there had been no transition planning on the part of either the SOLAR Project Team or the Sponsor several issues quickly materialized. The principle one being that the OSMA was not going to transfer any human resources to continue Project management responsibility and the Sponsor did not have any staff with sufficient time available to assume that responsibility. While OSMA and the Sponsor did eventually complete the management transition it did adversely affect SOLAR by essentially stalling all new system development work while the transition team focused on completing the transition and maintaining day-to-day system operational capability. |  | N/A |  |  | Public | Not Specified |  | 07/30/2001
971 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Identification of Market Needs |  | Course development decisions need to be made based on potential market for the course. Just because a course is available doesn't mean that it will be utilized. | Carefully consider the market and priority for each training course before initiating the development process. | HQ | 07/26/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance (OSMA) began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR) (http://solar.msfc.nasa.gov), currently one of NASA's primary distance learning resources. The intent of the initial development effort was to design and implement a prototype system for the Safety and Mission Assurance discipline. Since one of the benefits of a web-based distance learning capability is the ability to provide training to a widely dispersed audience we chose to develop courses targeted to one of our most widely dispersed communities, NASA Safety and Mission Assurance in-plant representatives. (While the courses were targeted to NASA in-plant representatives many of the courses were also suitable for use by other communities outside of in-plant locations). In 1997 after release of the prototype system for use, the development team embarked on an extensive roll out campaign that visited each of the NASA Centers, White Sands Test Facility and Headquarters. After each of these roll out visits we noted an increase in the number of system users and course completions. The data from this time period did demonstrate the capabilities of the prototype system and the ability to provide training to dispersed sites via the Internet. Over the time between 1996 and today (June 2001) the number of course completions has been tracked by the SOLAR system. The results show that there is a wide variation in the number of completions for different courses. For example between the time period of May 1996 to June 2001 the Receiving Inspection course has been completed 18 times. During the much shorter period of January 2000 to June 2001 the Headquarters ISO 9001 Quality System course has been completed 639 times. This data raises the question, was the market for training adequately examined to identify which courses should have been developed? In this case the answer is probably not. While development of the Receiving Inspection class met several needs (capturing knowledge from technical experts that were leaving the Agency, helping demonstrate the web-based training technology, providing training to 18 students) it was developed at the same time the Agency was preparing to implement ISO 9000 across all of the Centers. There was also a need to provide ISO 9000 training to each of the Centers to assist in the implementation process. The number of course completions for Headquarters ISO 9001 Quality System course used in preparation for NASA Headquarters ISO 9001 implementation suggests that a much larger need could have been met by developing a Center specific ISO course rather than the Receiving Inspection course. More careful market selection of courses to be included in the SOLAR predecessor system would probably also have increased the number of users and system utilization earlier in the system's lifecycle. One note concerning the above example: when the Receiving Inspection course was developed it is unlikely that the people who needed to provide Center specific ISO 9000 training would have risked using an unproven web-based training capability to meet their urgent needs. Since Headquarters was one of the later activities to implement ISO 9001, they were able to use what became the proven technology of SOLAR to meet some of their training needs. |  | N/A |  |  | Public | Not Specified |  | 07/30/2001
969 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Project Management Team Composition |  | The composition of the Project Team has a direct impact on the success of projects. Early consideration of the scope of the Project and careful assignment of Project Team members to provide coverage of all the major portions of that scope increases the likelihood of Project success | Careful consideration should be applied to the composition of Project Management Teams. Project teams for distance learning development and implementation should include substantial capability in each of the following areas: Educational theory, Training technology, Discipline content. | HQ | 07/26/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR), (http://solar.msfc.nasa.gov) currently one of NASA's primary distance learning resources. At the initiation of this development, distance learning and use of the Internet were in their infancy. Since this development was a trailblazing effort there was little in the way of guidance to follow and few resources available concerning adaptation of the Internet to education and training. The management team that was assembled for this project was a key element in the ultimate success of the project. The core team members of the project team included the Project Manager and three specialty experts. The Project Manager focused on the big picture activities such as project definition, interface with senior management, budgeting, contracting, scheduling, marketing, and coordination of the efforts of those involved in the project (core team members, Center points of contact, subject matter experts, contractor). The first of the specialty experts provided knowledge of education theory and instructional systems design. The second was familiar with the computer hardware and software systems within the Agency including most desktop configurations. Finally a Safety and Mission Assurance (discipline) professional, familiar at a general level of knowledge of all elements of the technical content of the subject matter and the targeted users, completed the core team (The detailed technical content of individual courses was created using separate teams of subject matter experts). The prime contractor's organization included counterparts to each of the core team members. The Project Manager and the core project team members were able to effectively plan and implement this distance learning program within NASA in large part because their individual knowledge bases covered all of they key aspects of the program. |  | N/A |  |  | Public | Not Specified |  | 07/30/2001
973 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Web-based Training Considerations |  | There are many factors in addition to the number of potential training instances that should be considerations in determining if web-based training is an appropriate method for training delivery. These factors include potential number of training instances; dispersion of students/instructor; delivery period; shelf life of the course materials; instructor based delivery options such as Video-teleconferencing; synchronous vs. asynchronous delivery requirements; portability among training delivery systems. Note: As distance learning technology evolves other factors may need to be considered when determining the training delivery method. Advances in training technology now allow for the easy separation of development of course content and course templates (the operational look and feel of course delivery). For example, the Shared Content Object Reference Model (SCORM) has been recently developed as a standard means for packaging course content. Course content developed in accordance with this standard can be plugged into compliant training delivery systems. SCORM compliant course materials are also packaged in segments that can be used by multiple training courses. The goal being to encourage technologies that enable dynamic learning where content is custom-assembled and delivered to learners according to their own personal pace and need. This enables sharing of course content among different courses or training systems. In comparison the current SOLAR technology relies on static webpages specifically developed for a course/module. (The course content is not independent from the delivery system). Any reuse would require replicating the webpages and assembling them within a new course/module. Reusability of course segments or use in other training systems as in SCORM would allow development costs to be potentially spread over an even larger number of training use instances. | Carefully consider all factors when determining the method of training delivery. | HQ | 07/26/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance (OSMA) began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR) (http://solar.msfc.nasa.gov), currently one of NASA's primary distance learning resources. The intent of the initial development effort was to design and implement a prototype system for the Safety and Mission Assurance discipline. Over the five years since the initial release of SOLAR (or its predecessor) there have been approximately 2500 training instances (completion of a single module by a single person) in the Safety and Mission Assurance discipline's approximately 70 courses. Over this time period some Safety and Mission Assurance courses have as few as 20 training use instances while others have had several hundred training use instances. In other disciplines (such as Information Technology Security) where SOLAR is used for mandatory training there have been thousands of training use instances for a single course. Based on this data, is it reasonable to assume that a potentially large number of training use instances is the only determining factor in the decision to develop a web-based training course? Certainly the need to provide a large number of training use instances suggests web-based training as a candidate for content delivery since per training use instance development and delivery costs are reduced each time an additional student completes a course. In contrast the development costs for instructor based training are reduced each time an additional student completes a course but the delivery costs vary depending on the number of students, their location, etc. If the course content is appropriate for delivery via web-based training, then web-based training can be an effective method for training large numbers of students. If a large number of potential training use instances represents a good potential course for web-based development, does that mean that a small number of training use instances rules out web-based training as an alternative to instructor based training? The answer depends on several factors. Just considering the potential number of students alone is not sufficient to make the determination. The location of the students and the instructors must be considered. The cost to deliver training to 20 students that are collocated with the instructor is quite a bit less than the cost to deliver training to 20 students that are each in a different location, since travel, lodging and meals must be considered. (Note: Other options for providing the training such as the use of Video-teleconferencing may offset some or all of these costs and should be a factor in determining method of delivery). The period over which the training is to be provided and the shelf life of the course material must also be considered. If the course was to be delivered to 5 students a year for 4 years, web-based course delivery might be more cost effective than instructor based delivery. Again location of students and instructor would affect costs. The shelf life of the course material would also be a factor. If the course required no updates over the 4-year period then the development cost is spread over all of the training use instances. If updates were required during the 4-year period then each of those represents an additional development effort; in essence the "single" course would actually look like four courses from a development standpoint. One final consideration concerns the timing of the course. If all of the training instances can be accommodated simultaneously (synchronous) then even in a dispersed student population use of technology such as Video-teleconferencing could make instructor based delivery a consideration. If however the training can not be delivered simultaneously (asynchronous) web based training becomes more attractive. |  | N/A |  |  | Public | Not Specified |  | 07/30/2001
972 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | User IDs and Passwords |  | Proliferation of User IDs and Passwords can frustrate system users, particularly if the User ID and Password combination is not used on a regular basis. For systems with infrequent access, a large amount of resources may be required to provide the capability to reset User IDs and Passwords. | Consider carefully the decision to adopt a unique User ID and Password authentication method. Consider instead using or piggybacking on another system's authentication system so that users have a single User ID and Password to access multiple capabilities. If a unique User ID and Password authentication system is adopted, ensure that sufficient user support is provided to quickly respond to user requests for Password resets. | HQ | 07/26/2001 | In the 1995-1996 timeframe the Office of Safety and Mission Assurance (OSMA) began development of a distance learning capability under the umbrella of the Professional Development Initiative (PDI). This distance learning capability eventually evolved from a Safety and Mission Assurance discipline system into the Site for Online Learning and Resources (SOLAR) (http://solar.msfc.nasa.gov), currently one of NASA's primary distance learning resources. The intent of the initial development effort was to design and implement a prototype system for the Safety and Mission Assurance discipline. Since the system was web-based part of the design considerations involved system security, specifically the use of User IDs and Passwords. The system was going to maintain user sensitive course completion data (completion records and testing scores) so establishing a User ID and Password to generate and access that information became a requirement. In addition, some course materials were going to contain licensed material and finally we wanted to limit access to the courses to the NASA community to ensure availability of courses to our users. To accomplish this the User ID and Password were also required to access course materials. SOLAR was configured to maintain its own User ID and Password protocols and files. The decision to develop a unique User ID and Password system was based on two assumptions. The first assumption was that requiring users to remember another User ID and Password would not be a burden and second that development of a unique capability would be easier than integrating the system into the various security systems resident at the NASA Centers. As use of the SOLAR system grew and some disciplines initiated mandatory training, by far the largest demand for user support involved re-establishing out-of-date or forgotten passwords. This represented a significant expenditure of resources to maintain the user support primarily to reset passwords. An additional system capability was added to automate password revalidation, this capability did reduce the demand for manual update. This did not solve the frustrations of users who had to remember another User ID/Password combination or were delayed even momentarily from taking training which they had allotted time to complete often with a looming deadline for completion. |  | N/A |  |  | Public | Not Specified |  | 07/30/2001
955 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Case Field Joint: Addition of a Pressurizing "J" slot in the Case Insulation |  | An interference fit between the case insulation of adjacent field segments, coupled with a pressurizing "J" slot in the male side of the joint will prevent hot combustion gasses from reaching the sealing "O" rings. | Cast or machine the joining insulation surfaces for an interference fit, and provide a "J" shaped circumferential groove in the insulation on the male side of the joint to allow chamber pressure to help ensure impenetrable sealing of the insulation joint. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through the case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
951 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Nozzle Joint: "O" Ring Compression Increase |  | Greater compression of the primary "O" ring is required to achieve reliable operation of a case-to-nozzle joint. | Increase the diameter of the "O" ring and redimension the "O" ring groove to provide optimum "O" ring squeeze while preventing "O" ring entrapment. (In the Solid Rocket Motor (SRM), the primary "O" ring diameter was increased to 0.290 in and the groove was decreased in width from 0.378 inch to 0.345 inch.) | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through he case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Revised Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
952 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Nozzle Joint: Added Capture Feature |  | A capture feature is required on case-to-case solid rocket motor field joints to prevent joint rotation and subsequent deactivation of primary and secondary sealing "O" rings. | Provide an additional "tang" on the field joint, which is an interference fit with the clevis on the mating segment. This tang contains an additional "O" ring groove and "O" ring which provides a thermal barrier to prevent hot combustion gasses from escaping from the field joint. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through he case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Revised Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
954 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Case Field Joint: Added Joint Heater |  | "O" rings become inflexible and do not properly seal at low temperatures. A heater is needed to raise the "O" ring temperature above that which would cause improper sealing. | Provide a joint heater for all field joints to maintain resiliency of the "O" rings. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through the case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
953 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Case Field Joint: Larger "O" rings and "O" ring grooves |  | Larger "O" rings are needed to increase surface sealing contact area to prevent hot gasses from escaping through the field joint. | Provide larger "O" rings, and provide wider "O" ring grooves to accommodate compression of the "O" rings during assembly and operation. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through the case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
957 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Nozzle Internal Seals: Dual "O" Ring Seals and Leak Check Ports |  | Dual "O" ring seals, with leak check ports in between, are required for nozzle seals in solid propellant rocket motors. | Provide a primary and secondary seal for all internal nozzle joints, with a leak check port in between the two seals to confirm seal integrity. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through the case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
956 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Case Field Joint: Added Leak Check Port |  | A second leak check port is required because of the third "O" ring that was added in the capture feature, and to provide a port to verify and seat the primary "O" ring. | Add a second leak check port in the field joint tang. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through the case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
958 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Joint Protection System |  | External joint insulation and sealing, (coupled with the field joint heater) is required to maintain field joint "O" rings at a 75° F minimum temperature, and to prevent moisture intrusion for both the field joints and the factory joints. | Cork insulation is applied with an adhesive to protect the field joints from cold temperatures and moisture. Ethylene Propylene Diene Monomer is used as a moisture seal over the factory joints. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through the case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | Effectiveness: As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
959 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Factory Joint Insulation: Safety Factors |  | A safety factor of at least 2.00 is required for factory joints in solid rocket motors. | Provide additional insulation plies to provide a safety factor at or above 2.0 for solid rocket motor factory joints. (Three to six extra plies were required to achieve this margin in the Space Shuttle Solid Rocket Motor.) | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through he case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
961 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME) Component Test Facility: Simplicity of Design |  | Avoiding overcomplexity of component test facilities prevents many potential engine component failures. | Provide simple, straightforward, well-designed, component test facilities which themselves are made up of well proven and reliable components. Reduce the number and complexity of components and instrumentation devices to the minimum required to obtain essential engine performance data. | MSFC | 05/15/1995 | The SSME turbobpump test stand had approximately 2,000 valves, two dozen, which were servo-operated. Facility preburner valves weighed as much as 5 tons for the 14,000 psi system. Facility problems were abundant. In one test, for example, a facility rotary flowmeter failed, releasing flowmeter blades into the LOX flow stream, causing a fire. A similar failure also occurred on a fuel facility subsystem. | The Space shuttle Main Engines have operated successfully in over 68 flights. Although many minor changes have been made to improve performance and reliability, this lesson learned or feature described has continued to sustain reliable performance in over 200 flight performances of individual engines. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
962 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME): Computer Models of Transient Performance |  | The use of computer models to depict transient behavior helps to characterize critical startup and operational parameters. | Make maximum use of computer modeling techniques to characterize the start-up and shut-down transient performance of liquid propellant rocket engines. | MSFC | 05/15/1995 | Fuel or oxidizer starvation will cause hazardous conditions due to off-nominal mixture ratios in liquid propellant rocket engines. A safe and repeatable start sequence was developed by making maximum use of the engine mounted computer to control propellant valve positions. The report stated that "Without the precise timing and positioning (of valves) allowed by the Main Engine controller (MEC), it is doubtful that a satisfactory start could have been deve | The Space shuttle Main Engines have operated successfully in over 68 flights. Although many minor changes have been made to improve performance and reliability, this lesson learned or feature described has continued to sustain reliable performance in over 200 flight performances of individual engines. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
960 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME): Integrated Subsystem Test Bed |  | The use of an Integrated Subsystem test Bed and Full Engine Testing in preference to individual component testing speeds up the development process and produces a high reliability engine that takes into account subsystem interactions. A special engineering and management team is required to integrate the components and to plan the test program. | Establish component design through analysis, engineering design, and interface engineering. The build an integrated test bed engine that takes into account all of the environmental, interface, and operational factors. Meticulously plan and conduct integrated engine test bed firings. | MSFC | 05/15/1995 | The SSME components were originally planned to be tested on a "bobtail" engine. To provide integrated testing, which takes into account the component interactions, however it was decided to add a shortened version of the thrust chamber. The shortened version had an area ratio of 35:1 versus the flight configuration requirements of 77.5 to 1. The test engine could throttle to 50% without requiring a vacuum chamber. | The Space shuttle Main Engines have operated successfully in over 68 flights. Although many minor changes have been made to improve performance and reliability, this lesson learned or feature described has continued to sustain reliable performance in over 200 flight performances of individual engines. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
963 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME): Start Sequence Investigations |  | Exploration of engine start sequences in small time increments provides reliable start cycles. | Explore engine start sequences in small time increments. | MSFC | 05/15/1995 | Computer mathematical models had shown the engine to be sensitive to small changes in propellant conditions, and that timing relative to opening the propellant valves was critical. Expecting difficulties, a cautious step-by-step plan was followed to explore the start sequence in small time increments. It took 35 weeks and a series of 37 test, including 13 turbopump replacements to extend reliable performance form the 2-second startup transient to main power level. | The Space shuttle Main Engines have operated successfully in over 68 flights. Although many minor changes have been made to improve performance and reliability, this lesson learned or feature described has continued to sustain reliable performance in over 200 flight performances of individual engines. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
968 | Wilson, Robert - 0000000000 : NO@ADDRESS.GIVEN | Wilson, Robert - 0000000000 : NO@ADDRESS.GIVEN |  | Avoid Test Program Reductions on Lower Cost/Higher Risk Instrument Projects | Project test deficiencies frequently occur in cost/schedule driven flight instrument developments. Cost/schedule driven, high-risk instrument projects should plan for expanded test programs. Should engineering problems arise and reserves become depleted, consideration should be given to reductions in mission scope, instead of reductions in the test program. Allow time for retest after correcting problems discovered during testing. | Cost and schedule constraints affecting the delivery of science instruments may create pressure for a reduced testing program. In fact, the higher level of risk associated with cost-driven development projects may mandate a more rigorous testing program. | Cost/schedule driven, high-risk instrument projects should plan for expanded test programs. Should engineering problems arise and reserves become depleted, reduce the mission scope instead of the test program. Allow time for retest after correcting problems discovered during testing. | JPL | 05/31/2001 | Project test deficiencies frequently occur in cost/schedule driven flight instrument developments. Early cost estimates prepared when a mission's science concept is first proposed are frequently overly optimistic due to lack of full understanding of the science scope and instrument complexity. Budget constraints based upon these early cost estimates normally preclude any funding increases. The instrument project may then be forced to cope with unknown, understated, or perhaps unacceptable risk to comply with the funding cap. Under these conditions, the proposed mission assurance plan/funding is usually inadequate for the actual level of mission risk. Problems typical of complex instrument developments quickly deplete the minimal reserves accepted early in the project. Failure to perform timely risk trade studies of reductions in mission scope versus early depletion of reserves renders contingency plans inadequate. The lack of additional budget, and schedule slips characteristic of complex instrument designs, result in the project having few or no options other than to shrink the overall test program (both functional and environmental). As a result, problems are frequently not discovered until systems integration - or even worse, after launch. Additional Key Words: test planning, mission assurance program, tailoring, integration and test, ATLO, project reserves, risk management | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.2.2.2 ("Management Practices: Planning"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Science | Public | Not Specified |  | 07/23/2001
967 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME): Instrumented Safety Checks During Engine Startup |  | Instrumented "safety checks" at critical points in the startup and operational procedures ensure proper engine system priming. | A safety check of turbopump speed is made at 1.25 seconds in the startup sequence to ensure that the high pressure fuel turbopump speed is high enough to safely proceed through the priming sequence. | MSFC | 05/15/1995 | Turbine speed must be high enough at the time of main combustion chamber priming to be able to pump hydrogen through the downstream system against the back pressure rise created by the chamber priming, or an engine burnout will occur due to the oxygen rich combustion. | The Space Shuttle Main Engines have operated successfully in over 68 flights. Although many minor changes have been made to improve performance and reliability, this lesson learned or feature described has continued to sustain reliable performance in over 200 flight performances of individual engines. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
965 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME): Turbopump Bearing Lubrication |  | Recirculation flows of propellants can be used to pre-chill turbopumps to cryogenic temperatures and to eliminate gas pockets in the propellant feed system. | Use recirculation flows of propellants in liquid rocket engines to pre-chill turbopumps to cryogenic temperatures, which will eliminate gas pockets in the propellant feed system. Maintain these flows for an hour or more prior to attempting an engine start. | MSFC | 05/15/1995 | In the SSME, a small recirculation flow is maintained by flowing the propellant through a bleed valve located at the main fuel valve to an overboard dump line or pumped back into the LH2 inlet. Recirculation flow of LOX is maintained by flowing LOX through a bleed valve located a the fuel preburner oxidizer valve to an overboard dump system. These recirculation flows have successfully eliminated gas pockets in the LH2 and LOX systems. | The Space Shuttle Main Engines have operated successfully in over 68 flights. Although many minor changes have been made to improve performance and reliability, this lesson learned or feature described has continued to sustain reliable performance in over 200 flight performances of individual engines. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
966 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME): Fuel System Oscillations |  | Fuel system oscillations can be reduced during the startup phase by closely controlled engine priming sequence. | Reduce two-cycle-per-second oscillations in the fuel system by issuing a 10% "notch" -closing command to the fuel preburner oxidizer valve at a specified time in the startup sequence. | MSFC | 05/15/1995 | After the main fuel valve starts to open, three oxidizer valves in the SSME are separately subjected to a series of position commands to precisely control oxidizer system priming times for the three combustors. The first oxidizer valve to be commanded is the fuel preburner oxidizer valve (FPOV). After a delay of 0.100 seconds, the FPOV is ramped to 56 percent open at its maximum skew rate. At 0.72 seconds, the FPOV is given a "notch" command to close about 10%. Just prior to the third fuel system oscillation, second "notch" command is given. | The Space Shuttle Main Engines have operated successfully in over 68 flights. Although many minor changes have been made to improve performance and reliability, this lesson learned or feature described has continued to sustain reliable performance in over 200 flight performances of individual engines. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
964 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME): Dry Gaseous Purges |  | Dry gaseous purges in a start preparation phase will aid in obtaining a reliable start sequence. | Use dry gaseous purges in a start preparation phase to aid in obtaining a reliable start sequence for high performance liquid propellant rocket engines. | MSFC | 05/15/1995 | Prior to starting the engine, there is a period of time referred to as the start preparation phase. At the beginning of this time period, the oxidizer side of the engine is purged with dry nitrogen to eliminate moisture and the fuel side is purged with dry helium to eliminate air as well as moisture. This prevents the formation of ice particles in the LOX system or air frozen by the hydrogen. | The Space shuttle Main Engines have operated successfully in over 68 flights. Although many minor changes have been made to improve performance and reliability, this lesson learned or feature described has continued to sustain reliable performance in over 200 flight performances of individual engines. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
946 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Nozzle Joint: Add a Pressurizing Slot in Case Insulation |  | A pressurizing slot was designed and implemented in the case-to-nozzle joints in large solid propellant rocket motors between nozzle and case insulation joints. | Provide a circumferential slot in case insulation near the interface between case and nozzle insulation. A circumferential flow baffle was installed in this slot to prevent insulation erosion, and a stress-relieving radius former is placed at the base of this slot to prevent potential insulation cracking. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through the case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
947 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Nozzle Joint: Interference Fit Bondline Case and Nozzle Insulation |  | An interference fit is required between case and nozzle insulation to prevent hot gas leakage between the insulation that could reach the joint's metal parts. | Provide a compression fit that will force the case and nozzle insulation components together during nozzle assembly. This interference fit is maintained during motor case pressurization due to the pressurizing slot provided in the case insulation. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through he case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
948 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Nozzle Joint: Replace Zinc Chromate Putty with Polysulfide Adhesive |  | A polysulfide adhesive will provide a much more secure and impenetrable insulation joint than the Zinc Chromate Putty used in 51-L and previous solid rocket motors. | Provide a polysulfide adhesive material to bond the carbon phenolic nozzle insulation material to the asbestos/silica filled Acrylonitrile Butadiene Rubber insulation in the rocket motor case. | MSFC | 03/27/1995 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through he case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
949 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Nozzle Joint: Wiper "O" Ring and Vent Slot Addition |  | A wiper "O" ring and wiper vent slots are required in the glass phenolic layer of nozzle insulation to prevent entrapment of air in the case-to-nozzle joint during assembly, and to prevent polysulfide adhesive from contaminating the primary "O" ring. The wiper "O" ring, along with the polysulfide adhesive, provides two thermal barriers before motor combustion gasses could reach the primary seal. | Add an "O" ring groove and "O" ring to the nozzle interface between the nozzle glass phenolic insulation and the case insulation. A wiper vent slot and vent port are also required to vent air that is trapped during assembly. | MSFC | 03/27/2001 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through he case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
950 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Case-to-Nozzle Joint: Addition of Radial Bolts |  | Radial bolts, as well as longitudinal bolts, are required to ensure an impenetrable seal between the nozzle and case metal parts. (In the SRM Application, one hundred Radial Bolts were added.) (Nozzle-to case joint deflections at the primary seal are reduced in the Space Shuttle SRM from 0.053 inches in 0.008 inches.) | Provide radial bolts alternating with the axial bolts that attach the nozzle, to ensure an effective seal between the case and nozzle metal parts. | MSFC | 03/27/2001 | The Challenger (Space Shuttle Flight #51L) accident triggered a detailed review of all of the joints in the Solid Rocket Motor. Analyses showed a potential weakness and potential flow paths for hot gasses through he case-to-nozzle joint that could cause a catastrophic event similar to that encountered in Challenger. | As of this date, eight-six (86) Solid Rocket Motors (RSRM) have flown successfully and ten (10) full-scale RSRM test motors have been tested successfully since Challenger with no failures and no evidence of joint deterioration or burn-through. This successful record indicates that recurrence control has been successful. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 07/23/2001
942 | Winters, John - 0000000000 : NO@ADDRESS.GIVEN | Winters, John - 0000000000 : NO@ADDRESS.GIVEN |  | Improper Use of Hand Tools |  | Sufficient downward pressure on the wrench and high torgue could cause flexing or bending of the shaft, which in combination with the applied torque could cause the forged shaft to break suddenly and without warning. | Take a minute or two, to think about the job you are preparing to do; analyze the risk and danger. Wear proper Personal Protective Equipment (PPE), i.e. eye protection, gloves, etc. Select the right tool for the job. Use the tool as it was designed to be used. Do not modify the tool or use "cheaters" to provide leverage or forces the tool was not designed for. Remember, everything can and probably will break at sometime, especially if misused. | JSC | 05/03/2001 | An individual was using a 10 inch long by 3/16th inch T-handled Allen wrench to extract screws. While attempting to remove the screws the Allen wrench broke in half resulting in the individual's hand to come down on the broken sharp end of the Allen wrench shaft puncturing his hand. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 07/10/2001
945 | Murphy, M - 0000000000 : NO@ADDRESS.GIVEN | Murphy, M - 0000000000 : NO@ADDRESS.GIVEN |  | Unexpected reactions in chemical mixtures during storage |  | Understand the physical characteristics of any chemical mixture and implement appropriate safety measures to preclude undesirable events. | Review the written procedures and the laboratory Chemical Hygiene Plan for the task. Perform job hazard analyses for all laboratory tasks. Wear protective clothing (goggles, gloves, coat) and work in a clean well-ventilated fume hood. Keep the sash down when reactions are in progress. Never take aqua regia out of the hood. Only prepare the amount you need for immediate use and destroy any excess in the hood in which it was prepared. Aqua regia can be destroyed by cautious and careful dilution with water. Use a large waste container and add the aqua regia to the water, which will produce a less hazardous and less reactive waste. Never store aqua regia and never put it in a closed container, since evolved gases will cause a pressure build-up and possible explosion. Label waste container to remind employees of specific waste. Schedule a frequent waste pickup disposal. This will prevent overfilling of the container and will promptly remove the hazard from the work area. Assess the physical characteristics of any mixture through literature searches, professional consultation, or direct test/check out of the mixture both prior to and subsequent to loading the reaction system especially for the first time. Be aware of the limitations of relying on material safety data sheets (MSDS) and other literature to assess the hazardous characteristics of a mixture. MSDS do not traditionally address interactions between a mixture's chemical components except as broad classes (acids versus bases, oxidizers versus reducing agents, or organics, etc.). | JSC | 06/25/2001 | A tightly capped bottle containing dilute aqua regia chemical waste was stored in a fume hood. Evolved gases resulted in a pressure build-up causing the bottle to explode. The contents sprayed across the room onto the floor. The bottle explosion occurred overnight when the laboratory was unoccupied; however, a potential acid burn exists if an employee was in the room at the time of the bottle explosion. A review of available literature indicates that aqua regia, which is a combination of hydrochloric acid and nitric acid, will oxidize with time resulting in the evolution of Nitrous Oxide (NO2). This reaction is ongoing and is subsequent to the intended use of the mixture. This pressure build-up is normal for this type of mixture. |  | N/A |  |  | Public | Not Specified |  | 07/10/2001
944 | Saulsberry, Regor - 0000000000 : NO@ADDRESS.GIVEN | Saulsberry, Regor - 0000000000 : NO@ADDRESS.GIVEN |  | Pyrovalve Anomaly Studies |  | Test pyrovalves the way you will use them on a mission. Regular lot acceptance tests and qualifications tests were accomplished. However, a propellant interaction test was not performed that could have identified this mission hazard. This was a major omission since the hot blow-by from these valves was demonstrated to readily initiate the downstream hydrazine under the specific actuation scenarios tested. Test all corners of the operational box (with some margin of safety). In other words, test the valve/system under all the possible extremes. This may include maximum over and under pyrotechnic energy levels, min and max temperatures, and min and max system pressures. "Operational Margin" testing is another consideration. | Test pyrovalves the way you will use them on a mission. Test all corners of the operational box (with some margin of safety). | WSTF | 12/31/2000 | Starting in 1995, WSTF tested approximately 50 pyrovalves in order to provide insights into the Mars Observer and certain other spacecraft anomalies. The pyrotechnic blow-by past the ram was measured and characterized and overall valve speed and other physical properties were characterized. Pyrotechnic/propellant interaction testing also was accomplished; testing included simulation of the Telstar 402 and LandSat 6 failures, verification that the Mars 98 pyrovalve and actuation scenarios were safe, evaluation of the Interim Control Module actuations, and tests that characterized pyrotechnic induced propellant reaction rates. Some major safety implications are summarized below. Most of the valves with O-ring seals on Telsar 402, Landsat 6, and the Mars Observer produced significant hot pyrotechnic blow-by. (These were manufactured by one company.) Telstar 402: Flight telemetry indicated that the propellant system was breached immediately following initiation of the second parallel pyrovalve. Actuation of the first valve introduced helium-saturated hydrazine into the evacuated downstream manifold. This created a very unfavorable scenario that greatly increased the chances of ignition. The second pyrovalve was liquid locked and some hydrazine foam may have been produced. Both WSTF and Lockheed Martin duplicated the scenario and both encountered explosions that were characteristic of the flight anomaly. LandSat 6: This was very similar to the Telstar 402 anomaly. Significant differences included a small variation in the time between the actuation of the first and second parallel pyrovalve, and the materials from which that the pyrovalves were made. Telstar 402 used titanium valves and the LandSat 6 used stainless steel valves. Both types of valves caused similar explosions in WSTF testing. Interim Control Module: This system used monomethalhydrazine (MMH) and no explosions occurred in WSTF tesing, probably due to the fact that MMH is much less sensitive than hydrazine. Mars 98: These tests were accomplished using separate hydrazine and nitrogen tetroxide systems and used very low blow-by valves (utilizing interference fit rams rather than O-ring seals). No system pressure increases were observed that were above water baseline test data. This indicated that blow-by was below the threshold for ignition of hydrazine, and that this type of valve no reactivity with nitrogen tetroxide (as was observed with some titanium valves from OEA.) Engineers at Langley Research Center developed a test which measures the amount of energy required to actuate a valve by using a weight drop tower and then measures the energy output of the pyrotechnic charge using a volume chamber. Comparing these energies determines if the valve is over or under-powered. It was determined that the Mars Observer and Telstar 402 valves were so over powered that they frequently broke chunks of titanium out of the ram stop at the end of the stroke. |  | N/A |  | Science | Public | Not Specified |  | 07/10/2001
943 | Murphy, M - 0000000000 : NO@ADDRESS.GIVEN | Murphy, M - 0000000000 : NO@ADDRESS.GIVEN |  | Fire Hazards- Linseed Oil |  | Spontaneous heating occurs when a self-ignition combustible reacts with sufficient oxygen from the air. This reaction is known as auto-oxidation, and results in the rapid evolution of heat and may eventually cause ignition. The MSDS for linseed oil and the label information have explicit warnings about the possibility of spontaneous combustion. | Before using any material, read carefully all cautions and directions on product label before use. Since empty containers typically retain residue, follow all label warnings after container is empty. Read your material's safety data sheet and become familiar with its hazardous properties and countermeasures. Oily rags or waste and other oily materials can cause spontaneous combustion fires if not handled properly; therefore, immediately after use, and before disposal or storage, you can, Store rags in a metal container with a tight fitting cover until disposal. Keep container away from other flammable items, OR Spread out all oily rags to dry by flattening them out to their full size in a well-ventilated place, OR Hand wash them thoroughly with water and detergent and rinse (do not use washing machine which may trap vapors), OR Immerse rags in water before disposal in a sealed waste container. | JSC | 05/07/2001 | An employee placed wadded paper towels soaked with linseed oil inside their vehicle on the floorboard pending later disposal. The paper towels ignited and caused a fire in the vehicle. The fire was extinguished before any major damage. Further inspection of the area found wadded paper towels soaked with linseed oil that were disposed in a trash container. The trash container bag was retrieved and the paper towels were disposed properly before a fire could ignite. The paper towels retrieved were extremely warm to the touch, indicating spontaneous combustion had already begun. |  | N/A |  |  | Public | Not Specified |  | 07/10/2001
941 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Involve Project Scientists in Critical Decisions Throughout the Project Lifecycle (1999) | For MCO and MPL, mission scientists were not active participants in making critical decisions throughout the mission design and operations phases. Involvement of scientists throughout the project life cycle as full partners in project development and operations makes a significant contribution to overall mission success. Ensure that a detailed mission science plan, tools, and necessary support are in place, and full operations training of the science team (including contingencies) has been completed, prior to any science data collection activities (e.g., planetary encounters, landings, etc.). | A primary measure of mission success is how well a project achieves its science goals. Involvement of scientists throughout the project life cycle makes a significant contribution to overall mission success. Scientists are best able to assess the impact of project decisions on science objectives and participate in mission/science tradeoffs. Scientists participating in projects should be made full partners in project development and operations. Ensure that a detailed mission science plan, tools, and necessary support are in place, and full operations training of the science team (including contingencies) has been completed, prior to any science data collection activities (e.g., planetary encounters, landings, etc.). Additional Key Words: Principal Investigators, Project Management, Science Return | See Lesson(s) Learned | JPL | 07/03/2001 | Compared to previous projects, the Mars Surveyor Program budgeted significantly less monetary and personnel resources to support the Mars Climate Orbiter (MCO) and Mars Polar Lander (MPL) mission science goals. According to Reference (1), one consequence of this approach was that mission scientists (who had the most knowledge of Mars, the instruments, and the mission science objectives) were not active participants in making critical decisions throughout the mission design and operations phases. Due to the funding constraints, the science teams were not fully prepared for mission operations supporting science data collection at Mars. Had either of these missions successfully arrived at Mars, a significant amount of science data could have been lost. In contrast, the successful Mars Pathfinder project had full involvement of the science team from the beginning. Reference(s): "Report on Project Management in NASA by the Mars Climate Orbiter Mishap Investigation Board (Stephenson Report)," March 13, 2000, page 18. "Scientist Involvement," JPL Corrective Action Notice No. Z69172, May 1, 2000. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.3.3 ("Management Practices: Science"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 07/03/2001
940 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | 12 Foot Pressure Wind Tunnel Fall Mishap Report |  | Fall protection must be used and enforced while working in locations which pose substantial risk of a fall. | Ensure compliance with fall protection and working heights standard. Management to evaluate the need for a specific fall protection retraining interval. Use this incident as a lessons-learned exercise in fall protection training. The observation of blatant or repeated violations of safety requirements must be addressed by managers and supervisors through consistently applied corrective and disciplinary actions. Organization to take steps to ensure that prior to proceeding with any work, every employee has the knowledge, tools, and equipment to complete the job safely. Managers/supervisors must continuously reinforce the safety principle that "whenever there is a conflict between our safety objectives and mission objectives, safety shall be our first consideration". Management shall provide easy access to all safety documentation for employees. When new information is distributed, an overview of the information should be provided through some form of interactive presentation such as branch meetings, toolbox discussions, etc. Maintenance engineering should be incorporated in the requirements for facility design. All facilities that have the potential for fall hazard should be inspected for fall hazards within the next six months. Update AHB 1700.1 to correct errors in fall protection references. The Ames Safety Office should prepare an additional chapter dedicated to this subject matter. The Ames Safety Office should evaluate the existing training records database for effectiveness in informing supervisors of their employees training history and requirements. The Ames Safety Office should provide training or professional assistance to employees and their supervisors on hazard identification for their areas of control. Inspectors who conduct periodic safety inspections should have adequate expertise and training to be able to identify existing hazardous conditions in the workplace. | ARC | 06/18/2001 | An engineering technician was standing on a temporary platform located between the guardrails of the 3rd floor and the exterior surface of the test section plenum. The platform did not inlcude guardrails or other fall restraint devices. The technician was threading a pipe assembly into a blind flange. The pipe assembly was necessary to route test-dependent instrumentation wiring out of the plenum. While tightening the pipe assembly, the open-ended adjustable wrench he was using slipped off the pipe. This caused him to lose his balance and fall onto the curved exterior of the plenum at the 3rd floor level. He slid down the plenum surface approximately 25 feet to a metal obscuration platform located 40 inches below the surface of the 2nd level. The technician sustained a fractured left scapula, a severe laceration of his scalp, and a minor concussion. This injury resulted in several days away from work. Medical assistance was provided in a very timely and effective manner by co-workers and medical personnel. This mishap occurred on December 14th, 2000. A mishap investigation board began it's investigation of this mishap on December 15, 2000. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/26/2001
937 | Glenn, Malcolm - 0000000000 : NO@ADDRESS.GIVEN | Glenn, Malcolm - 0000000000 : NO@ADDRESS.GIVEN |  | Mobile Crane Mishap |  | Follow all procedures/instructions for handling and operation of materials and equipment. Ensure edge protection devices are used. A single person is to be designated as the person in charge for all crane and hoist operations; as such, shall conduct a pre-task briefing, establish a safety zone, ensure all equipment is in safe working order and the load properly rigged, prior to commencing operations. Ensure written procedures are available and used for all crane and hoist operations involving complex configurations and/or requirements. Prior to use, the written procedures shall have been reviewed and approved by appropriate levels of Management, Engineering, Safety and Health, and Quality. Prohibit the use of cranes and hoists for pulling, dragging or any operations that would cause side loading unless the crane or hoist is specifically designed to do so. | Follow all procedures/instructions for handling and operations of materials and equipment. Ensure edge protection devices are used. | KSC | 01/01/2001 | A three-man crane operating crew was assisting a three-man crane overhaul crew to refurbish a 140-ton crew and to refurbish a 110-ton government owned mobile crane on September 15, 2000. On this day, the overhaul crew was to install new boom pendants, requiring the cable bridle and its associated cables to be moved from its temporary stowage location behind the cab of the crane to a point on the boom where it could be attached to the boom pendants. To move the bridle with its associated cables forward along the length of the boom, a second 65-ton government owned mobile crane was used to lift the cable bridle assembly and pull it to the new location. The cable bridle (weighing approximately 1100 pounds) was attached to the hook of the 65-ton crane with a web sling (rated for 10,000 pound capacity in the vertical choker configuration) used in a horizontal choker configuration. The crane operating personnel were performing the following duties: One member operated the 65-ton crane used to lift the cable bridle assembly and pull it to its new location. A second member operated the 140-ton crane in order to play out cable while the bridle assembly was being pulled. The third member was on the ground acting as the signalman for the two crane operators. With the three crane operating crew members in position and the overhaul crew members observing the operations, the cable bridle was lifted and slowly pulled along the boom of the 140-ton crane. During this movement the cable bridle underwent several yawing motions due to the cables binding on the sheaves as the cable unspooled from the take-up drums. The sheaves were binding because the cables were being pulled at an angle and the choker hitch configuration did not keep the bridle straight and level with the direction of pull. The web sling failed allowing the bridle to fall. The bridle assembly impacted the butt section of the boom of the 140-ton crane before it landed on the ground. At the same time, the block of the 65-ton crane swung back striking the stowed jib boom attached to the main boom of the 65-ton crane. The jib boom of the 65-ton crane was a total loss because a portion of the main support section was severely damaged beyond repair. The butt section of the boom of the 140-ton crane was slightly bent and the bridle was damaged in several places. The falling cables cracked the overhead glass on the cab of the 140-ton crane. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 05/17/2001
936 | Drake, Thomas - 0000000000 : NO@ADDRESS.GIVEN | Drake, Thomas - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Commercial/Industry Terminology |  | Use caution when using industry terms in a specification. | In specifications for products ensure that terms used are consistent with the industry that is implementing the specification. Also, do not use an industry term and give it a definition that is contradictory to the understanded industry meaning. | KSC | 03/14/2001 | During the Procurement and Fabrication of the MPLM Support Vehicle, a specification was written for the truck tractor portion of the vehicle. An industry term Gross Combined Weight (GCW) was used and further defined in the specification as the combined weight of the trailer and associated equipment. This is contradictory to the industry term, which is the combined weight of the truck tractor and trailer. During proofload of the equipment it was noted that the proofload weight was not adequate. The vendor picked up on the industry term GCW and assumed a 50,000 lb. GCW. This is a combined tractor weight of 12,000 lb. and trailer weight of 38,000 lb. The intent of the specification was to have a 50,000 lb. trailer and associated equipment weight plus a truck tractor capable of pulling it which is approximately 12,000 lb. This would have resulted in a 24% undersized proofload. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 05/17/2001
938 | Nichols, David - 0000000000 : NO@ADDRESS.GIVEN | Nichols, David - 0000000000 : NO@ADDRESS.GIVEN |  | Probable Scenario for Mars Polar Lander Mission Loss (1998) | Neither the Mars Polar Lander (MPL) software requirements specification nor the software, subsystem or system test plans required verification of immunity to transient signals. MPL touchdown sensors generated known transient signals at leg deployment. Full leg deployment test was not repeated after wiring corrections. Tests should be re-run after test deficiencies are corrected or hardware or software is revised unless clear rationale exists for not doing so. Hardware operational characteristics, including transients and spurious signals must be reflected in software requirements and verified by test. See 4/18/17 note updating these findings. | Project test policy and procedures should specify actions to be taken when a failure occurs during test. When tests are aborted, or known to have had flawed procedures, they must be rerun after the test deficiencies are corrected. When test article hardware or software is changed, the test should be rerun unless there is a clear rationale for omitting the rerun. All known hardware operational characteristics, including transients and spurious signals, must be reflected in the software requirements documents and verified by test. 4/18/17 Update. In designing a mission that has substantial heritage from a previous successful mission, it is imprudent to take the previous success for granted. The 15 failure modes discovered during PHX development suggest that MPF, Spirit, and Opportunity may have narrowly escaped mission failure during EDL, and they support the need for a very critical, skeptical, view of inherited flight systems. | See Lesson(s) Learned | JPL | 02/14/2001 | The MPL flight software did not take into account certain known hardware characteristics. Resulting mission-critical failure modes were not detected during testing of the spacecraft. It was known that the touchdown sensors generated false momentary signals at leg deployment. This transient behavior was not properly accounted for in the software design. It is believed that these momentary signals were recorded as valid touchdown events, resulting in the engines shutting down at an altitude of 40 meters. The resultant free fall to the surface of Mars is viewed as the probable cause of the December 1999 MPL mission loss (References 1 and 2). Neither the software requirements specification nor the software, subsystem or system test plans required verification of transient signal immunity. Therefore it was never verified. Wiring errors in the touchdown sensors prevented registry of the touchdown or detection of the false transient signal during the first system-level leg deployment test. A full leg deployment test was not repeated after the wiring was corrected. However, the footpads were again manually depressed and the sensors successfully registered a touchdown. A rerun of the complete deployment test with the correct wiring would probably have detected the software's inability to disregard the false momentary signal caused by leg rebound. 4/18/17 Update. The conclusions of the Young (Reference (1)) and Casani (Reference (2)) reports have not been invalidated over the past 17 years. However, the development of the Mars Phoenix (PHX) lander, which inherited much of the MPL design and spare hardware and was launched in 2007, revealed another 15 failure modes (Reference (5)) during the Entry, Descent, and Landing (EDL) phase which could have led to the MPL mission failure (and one or two of them could also have threatened (the successful) Mars Pathfinder (MPF), Spirit, and Opportunity rover missions). For example, the breakup analysis performed after the 2003 Columbia Shuttle loss reveals the potential for the MPL cruise stage to have re-contacted the rear of the MPL lander during its descent through the Martian atmosphere. References: Mars Program Independent Assessment Team Summary Report (Young Report), 14 March 2000. Report on the Mars Polar Lander and Deep Space 2 Missions, JPL Special Review Board (Casani Report), JPL Internal Document D-18709, 22 March 2000, Section 7.7. JPL Corrective Action Notice No. Z69163, Mars Program Investigation Results: "Software Design", 4 May 2000. JPL Lesson Learned, Software Error in the MPL Uplink Loss Timer. Rob Manning, “Can failure be a measure of success?,” JPL LEAP Seminar, March 24, 2017. Additional Key Words: Software Test, System Integration and Test, Test Planning | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.5.1 ("Engineering Practices: Design and Verification for Environmental Compatibility - Test Execution"), and Paragraph 6.14.2.4 ("Engineering Practices: Project and System Level Functional Verification and Validation - Verification and Validation"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 05/17/2001
939 | Nichols, David - 0000000000 : NO@ADDRESS.GIVEN | Nichols, David - 0000000000 : NO@ADDRESS.GIVEN |  | MPL Uplink Loss Timer Software/Test Errors (1998) | Prelaunch tests and verification of software and hardware used to switch to a redundant string should include assumed failures in either string during all mission phases. MPL did not verify the ability of the Lander to switch to the redundant uplink string after landing assuming a failure in the primary string had occurred during earlier entry, descent and landing phases. Recognize that transitions to another mission phase are high-risk sequences and that database changes that impact logic decisions should be retested. | Recognize that the transition to another mission phase (e.g. from EDL to the landed phase) is a high risk sequence. Devote extra effort to planning and performing tests of these transitions. Unit and integration testing should, at a minimum, test against the full operational range of parameters. When changes are made to database parameters that affect logic decisions, the logic should be re-tested. | See Lesson(s) Learned | JPL | 02/14/2001 | The Mars Polar Lander (MPL) flight software design contained mission-critical logic errors that were not detected during testing of the spacecraft due to omissions in the pre-launch test program and pre-launch uplink verification process. The failure reviews (References 1 and 2) attributed MPL mission loss to a leg rebound transient that is summarized in Reference 4. The uplink loss timer is software designed to trigger a switch from a failed uplink hardware string to the backup string if the spacecraft has not received a command from mission operations for a selected time period. Because of the significant physical reconfiguration of the spacecraft telecommunications equipment from the cruise to post-landing configuration, this uplink loss software was planned to self-reconfigure after the landing. Post mission testing demonstrated that an undetected logic error prevented the reconfiguration. With this software misconfigured, the detection of a failed uplink string and the required swapping to the backup string could not occur. Inadequate Test of Mission Phase Transition: During software integration testing, there were several tests that crossed the boundary from Entry, Descent and Landing (EDL) to the landed mission phase. After the successful simulated landing, each test issued commands to configure the quotuplink loss faultquot test case (i.e., loss of primary uplink string). This test condition masked the software flaw by inadvertently completing a successful transition to the landed configuration, which would not have occurred had a true hardware fault happened. The test did not verify the ability of the lander to switch to the redundant string if a failure occurred during the earlier EDL sequence. Failure to Test Full Range of Operational Parameters: Unit and integration testing of the uplink loss timer logic did not cover the full operational range of parameters. This resulted in failure to identify a legal parameter value that could cause catastrophic behavior. References: Mars Program Independent Assessment Team Summary Report (Young Report), 14 March 2000. Report on the Mars Polar Lander and Deep Space 2 Missions, JPL Special Review Board (Casani Report), JPL Internal Document D-18709, 22 March 2000, Section 7.7. JPL Corrective Action Notice No. Z69163, Mars Program Investigation Results: quotSoftware Designquot, 4 May 2000. JPL Lesson Learned quotProbable Scenario for Mars Polar Lander Mission Lossquot Additional Key Words: Fault Tolerance, Redundancy Verification, Software Test, System Integration and Test, Test Planning | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.7 (quotEngineering Practices: Project and System Level Functional Verification and Validation - Verification and Validationquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science | Public | Not Specified |  | 05/17/2001
935 | Zimmerman, Frank - 0000000000 : NO@ADDRESS.GIVEN | Zimmerman, Frank - 0000000000 : NO@ADDRESS.GIVEN |  | High Velocity OxyFuel (HVOF) Thermal Spray System Incident |  | The potential exists for kerosene and oxygen to mix outside the combustion chamber of a TAFA model JP5000 HVOF gun. If a mixture of kerosene and oxygen is ignited outside the combustion chamber of the HVOF gun, it will damage the oxygen-regulating circuit of the controller. TAFA, the manufacturer of the JP5000 HVOF system does not notify customers of updated in safe operating procedures. | Mount the HVOF gun at a 5-degree downward orientation. Periodically verify down hill orientation. do not operate by hand. Purge the HVOF gun for at least 20 seconds before ignition to ensure no residual kerosene is present. Request updates and bulletins from the HVOF system manufacturer. Periodically check with manufacturer that all documentation on hand is current. Update procedures as the manufacturer revises them. | MSFC | 02/22/2000 | During routine starting of the HVOF thermal spray gun, an incident occurred that resulted in the unintended mixing and ignition of liquid fuel (kerosene) and oxygen in the HVOF system. By some mechanism, the kerosene fuel was allowed to mix with gaseous oxygen upstream of the oxygen check valve in the combustion chamber of the gun. Upon starting the HVOF spray gun, this fuel ignited outside of the combustion chamber, in which it normally mixes and is burned. The flame front traveled up stream in the oxygen supply line and into the controller console, burning or melting several plastic tubes and lines in the cabinet, and contaminating the oxygen-regulating portion of the system. No personnel were injured and the equipment sustained approximately $7,800 worth of damage. As the manufacturer (TAFA) repaired the equipment, they offered the most likely cause of the mishap and suggested some corrective actions. If the HVOF gun is not mounted in! a slightly (at least 5 degrees) downhill orientation (barrel is lower than the rear of the gun), it is possible for a small amount of residual fuel to seep into the oxygen supply line. This can lead to "hard" starts or, as in this extreme case, damage the equipment. It is suspected that the HVOF gun was mounted level (parallel to the floor), or even slightly uphill, though not enough to be perceived by the operator. While the equipment manufacturer recommends this practice, it was not described or included in the documentation that originally came with the HVOF system. Consequently, the operator had no idea of the potential consequences related to gun orientation. This equipment had been in operation for over 6 years witout incident before this mishap. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 04/30/2001
934 | Hartline, Tom - 0000000000 : NO@ADDRESS.GIVEN | Hartline, Tom - 0000000000 : NO@ADDRESS.GIVEN |  | SSME 0523 Test 902-772 Major Mishap |  | Early on in the investigation there was much concern regarding the lack of damage to the FPB faceplate. Past failures in the FPB injector and OPB injector suggested that faceplate damage was common for fuel flow loss due to contamination. Model analysis performed during this investigation suggests that with a short-duration test and with the fuel cavity contamination type and quantity observed, damage to the FPB faceplate does not necessarily occur. In other words, there exists a substantial range of contamination levels within which it is possible to effectively destroy the HPFTP without melting the FPB faceplate. This conclusion is supported not only by the post-test hardware inspections from this test, but also by mathematical modeling analysis performed by MSFC and Rocketdyne. The Pratt & Whitney HPFTP/AT has shown that it can endure extreme levels of imbalance and damage without engine catastrophic results. | Verify that all systems are free of foreign object debris prior to hot-fire. Limit the opportunity for contamination introduction by minimizing the use of potential contaminants and using permanent closures on joints were applicable. Keep joints closed at all times when access is not required to perform work. Implement an improved method of dealing with loose, non-serialized materials to ensure full accountability. Additional inspections and checkouts should be considered to verify that the engine is contamination free, prior to any hot-fire. The use of reusable joint barriers, which can be controlled and accounted for, should be investigated. Provide clear instructions in processing paperwork and discrepancy paperwork. Use positive identification of engine hardware to ensure that the work is being done on the correct part. Correct electronic paperwork systems, to either prevent changes or provide a clear tracking of change activities. Further ensure that all SSME changes can be tracked. SSME Project should investigate evidence to ensure that SSME 0523 Powerhead structural properties were adequate. Ensure that an unacceptable condition does not exist in the flight fleet. The SSME Project should understand the mechanism causing roller bearing failure and ensure that conditions experienced were outside the designed capability of the roller bearing. The agency and its contractor teams need to avoid schedule practices that create undue risks. | MSFC | 06/16/2000 | Space Shuttle Main Engine (SSME) test 902-772 was conducted Friday, June 16, 2000, on engine 0523 with High Pressure Fuel TurboPump (HPFTP/AT) 8109R1, and High Pressure Oxidizer Turbopump (HPOTP/AT) 8308. The test was prematurely cutoff at 5.2 seconds due a violation of the High Pressure Fuel Turbine (HPFT) temperature limit of 1860 degrees Rankine. The high temperature led to High Pressure Fuel Turbopump turbine damage and the declaration of a type A mishap. The major objective of this test was to characterize the effects of Chamber Coolant Valve (CCV) position on HPFT temperature. Engine 0523 was in the Block Ia configuration (small throat Main Combustion Chamber) with the exception of the Pratt & Whitney High Pressure Fuel Turbopump. It had previously been tested for 119 starts and 59,278 seconds. It was the fleet leader in both starts and seconds. Nominal operation was planned for the first 90 seconds of the test. The first indication of abnormal performance occurred 2.7 seconds into the start transient. High Pressure Fuel Turbine temperature measurements in two of the four locations began increasing beyond predictions. Other two measurements remained normal. All other engine performance parameters indicated normal engine operation at this time. The two high measurements reached the 1860 degree limit at 4.04 seconds. At approximately 4.97 seconds, the High Pressure Fuel TurboPump vibration levels increased sharply and engine performance dropped. The HPFT temperature limit was activated at 5.04 seconds and a failure identification (FID) was issued, accompanied by a major component failure (MCF). The control and data simulator (CADS) commanded shutdown. The turbine temperature measurements continued to increase after shutdown, reaching a high of 2165 degrees Rankine. Post test inspections revealed heat damage to the High Pressure Fuel Turbine. The Fuel Preburner fuel manifold was heavily contaminated with "LOX" tape. During the assembly of SSME 0523, tape was introduced into the fuel system during some "hands on" process (temporary closure, contamination barrier, unintentional introduction, etc.). The tape contamination went unnoticed and was left in the fuel system during the remainder of assembly and pre-test activities. On June 16, 2000, Stennis Space Center conducted test 902-772. SSME 0523 was to be tested for a scheduled duration of 210 seconds. At engine start the tape contamination was forced downstream in the fuel system, eventually coming to rest as debris in both the Fuel Preburner (FPB) injector and Oxidizer Preburner (OPB) injector. The amount of debris in the FPB was sufficient to block the fuel inlet holes to several FPB injector elements in a localized area. This blockage caused a localized high mixture ratio area in the preburner without affecting overall engine system performance. Data analysis indicates a localized temperature increase occurred in the vicinity of HPFT DS T CH A measurement and the HPFT DS T measurement at joint KG2dt beginning at approximately 2.7 seconds. At approximately 4.9 seconds, the localized temperature increase caused melting of the support struts and first stage vanes in the HPFTP/AT. The melting of the turbine stator caused local structural failure. The liberated material continued down the hot gas flow stream, impacting the first stage blades, causing the first stage blades to fail due to impact. This caused significant HPF turbopump imbalance. Data analysis indicates synchronous vibrational level increases of approximately 8 Grms on the pump end and 20 Grms on the turbine end. The levels continue to increase with the increase of imbalance of the turbopump; eventually reaching approximately 16 Grms on the pump end and 83 Grms on the turbine end. At 5.04 seconds, the HPFT DS T Launch Commit Criteria (LCC) was activated. At 5.08 seconds, 2 Failure Identifications (FID's) were issued indicating that HPFT DS T CH A2 and HPFT DS T CH A3 had exceeded the 1860 degree Rankine redline. These FID's were accompanied by a Major Component Failure (MCF) indication. The Facility Command and Data Simulator (CADS) was set to respond to an MCF indication before 6.6 seconds with a command to perform engine shutdown. The CADS unit issued a shutdown command and the engine entered shutdown phase at 5.18 seconds. The engine powered down nominally with the exception of the HPFTP. Its spindown was much faster than nominal. It stopped at approximately 4 seconds after shutdown (expected for a pump with severe imbalance). |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 04/30/2001
932 | Tweed, Daniel - 0000000000 : NO@ADDRESS.GIVEN | Tweed, Daniel - 0000000000 : NO@ADDRESS.GIVEN |  | Configuration Control for Underground Utilities |  | The Mishap Investigation Board learned that thrust blocks at KSC are not documented or identified in a manner which would enable utility locators to locate them, and that modifications to non-configured systems are often performed using engineering sketches that are not typically incorporated into master planning drawings. For underground utilities, this results in some installations that are not adequately documented. | Thrust blocks should be documented as integral components of underground piping systems, and design agencies should update their specifications to provide for positive identification of all new underground thrust blocks from ground level. Excavation control processes should be reviewed and revised as necessary to incorporate the identification of known and probable thrust block locations when utility locators identify underground piping systems. Facility management organizations should review configuration management processes and revise them as necessary to ensure that all underground utility modifications are documented (as-built) and incorporated into appropriate master planning documentation. | KSC | 03/21/2001 | On January 7, 2001, a large washout was discovered in the vicinity of Facility K7-1205F at the Kennedy Space Center Press Site. Water was flowing from the open end of a failed 4" potable water main. The washout undermined portions of the concrete foundation and driveway apron for a garage canopy at K7-1205F and damaged the sewer and electric services to the facility. The dominant root cause of this mishap was the removal of a concrete thrust block from the end of the 4" water main during installation of a power conduit by a KSC support contractor. The thrust block was mistaken for waste concrete material. With the removal of the thrust block, used as the primary constraint for the direct buried slip joint piping system, there was insufficient contact area with the soil to prevent the water main from separating at the joints. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/26/2001
930 | Winters, John - 0000000000 : NO@ADDRESS.GIVEN | Winters, John - 0000000000 : NO@ADDRESS.GIVEN |  | Hidden Hazards Associated With Raised Flooring |  | Raised flooring are susceptible to hidden hazards due to improper design / installation / maintenance | When working under a raised floor or maintaining the raised floor itself; inspect the supporting floor pedestals, pedestal caps, stringers, tiles and cross members for proper assembly, positioning, and any signs of deterioration or damage. When reassembling the flooring, always position the components exactly as they were before removal. Immediately report any safety concerns about raised flooring, such as raised and uneven tiles, to the Facility Managers. | JSC | 03/12/2001 | An employee fell through a section of raised flooring that collapsed, suffering knee and back injuries. The ensuing investigation revealed that the floor tile support cross members were not properly positioned on the floor support stanchions. The floor tile support cross member slipped off of the floor support stringer because the pedestals cap in use was the incorrect type. [D] |  | N/A |  |  | Public | Not Specified |  | 03/23/2001
931 | Manning, Jonathan - 0000000000 : NO@ADDRESS.GIVEN | Manning, Jonathan - 0000000000 : NO@ADDRESS.GIVEN |  | Faulty Chair Mechanism |  | Actively working with manufacturers and/or suppliers to find fault or defects in products will greatly improve safe usage. Purchasing chairs and other equipment with extended warranties provides much needed leverage when correcting defects through the manufacturer. This keeps the warranty intact and ensures equipment that continues to be in good and safe working order and improved. | If you have one of these chairs, do not sit in a full recline position. Identify such chairs to your furniture managers to ensure that your chair is still in good working order and fixed if necessary. | JSC | 11/15/2000 | JSC employees fell out of their office chairs when they broke. One employee was injured; the other was not. These two events were several months apart. The model that broke is an adjustable, high-back, gray chair made by Dauphin North America, product code # SL1939 1995 model. The investigation found fractures in the mechanism that attaches the backrest to the base. The manufacture confirms that the metal in the mechanism is not strong enough to withstand repeated stress and strain. Both failures occurred when the chair was unlocked in the full recline position. The chairs are under warranty. Dauphin North America is manufacturing new mechanisms to replace the ones on the 1995 models. The 1996 models and succeeding have the stronger mechanism. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/23/2001
927 | Connors, Chuck - 0000000000 : NO@ADDRESS.GIVEN | Connors, Chuck - 0000000000 : NO@ADDRESS.GIVEN |  | KAO (Kuiper Airborne Observatory) Gauge Calibration Problem During Aircraft Pressure Test |  | Make sure gauges are calibrated and that there is documentation to substantiate successful calibration prior to the start of the test. | Both NASA and the contractor worked very hard to substantiate that no structural damage had occurred. This task was successful but it took quite an effort at a very busy time in the program. To avoid a similar incident like this one, it is recommended that successful calibration of the gauges be checked and to provide a relief valve in the pressurization system that will protect the aircraft from being overpressurized. | ARC | 02/22/2001 | During the pre-modification pressure test, the contractor had a difficult time in reaching the full pressure test value. The clam shell doors were open and the aft seals around the door were inverted and letting air escape. The contractor was preparing to get additional compressors when it was noticed that the skin of the aircraft appeared to be bowed. The test was immediately halted and NASA requested that the pressure gauges be checked for proper calibration. The contractor discovered that the gauges were out of calibration and were reading a lower pressure and it was determined that they had actually reached the full test pressure value and even exceeded this value. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 03/05/2001
924 | Bodie, C - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - ; Brusse, J - | Bodie, C - 0000000000 : NO@ADDRESS.GIVEN |  | Tin Whiskers Cause Electrical Shorts | Although the phenomenon of tin whisker formation is well known, spacecraft are still suffering failures from them. When tin plating is used on mechanical, electrical or electromechanical components, continuous process monitoring (especially of suppliers) must occur to assure that tin whisker growth is addressed including control of the type and amount of impurities added to plating baths and compliance is maintained. | Although the tin whisker phenomenon has been documented for decades and is reasonably well understood, it remains a reliability hazard that warrants continuous attention to vendor and in-house tin plating processes. Tin whiskers may grow spontaneously to more than 4 mm in length. The filaments can typically carry 25-50 mA of current, or 1 amp for a short period. (Reference #1) | The recommendations documented in the previous military specification MIL-T-10727 and the current industry specification ASTM B545, such as controlling the type and amount of impurities intentionally added to the plating bath, should be implemented to prevent or minimize the occurrence of tin whiskers. When tin plating is used on mechanical, electrical or electromechanical components, continuous process monitoring (especially of suppliers) must occur to assure that tin whisker growth is addressed and compliance maintained. Additional Key Words: Latent Failure, Material Properties, Sneak Circuit | JPL | 11/15/2000 | During the period May-July 1998, one or more of the redundant spacecraft control processors (SCPs) failed in each of three commercial communications satellites. This resulted in one of the satellites being removed from service. Three SCP failures were attributed to intermittent or continuous short circuits caused by the growth of conductive filaments, known as quottin whiskers,quot from the tin-plated surface of an electronic assembly or its cover. Although well known in the past, these recent failures have reminded the space community of the potential risks associated with the use of pure tin-plated finishes on electronic components and assemblies. While pure tin protective coatings are favored by the electronics industry because of their material properties and cost, they are susceptible to the spontaneous growth of single crystal structures -- tin whiskers. Growth occurs with pure tin plating, regardless of the presence of an applied electric field, moisture, or an atmosphere. It may begin soon after plating or may take years to initiate. Tin whiskers are capable of causing electrical failures ranging from parametric deviations to catastrophic short circuits. quotBrightquot pure tin plating has been found to be particularly susceptible to whisker growth, and the U.S. military has discouraged its use. [D] Simulation of Whisker Growth (courtesy of GSFC) [D] Reference(s): NASA Goddard Space Flight Center Tin Whiskers Information Page, http://nepp.NASA.gov/whisker/index.html. quotTin Plating, Whisker Growth,quot GIDEP Alert No. AAN-U-00-11, January 4, 2000. Military specification MIL-T-10727, Tin Plating: Electrodeposited or Hot-Dipped, For Ferrous and Nonferrous Metals (cancelled February 7, 1997) - refer to ASTM B545-1997, Standard Specification for Electrodeposited Coatings of Tin. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.3.6 (quotSafety and Mission Assurance Practices: Quality Assurancequot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/05/2001
925 | Connors, Chuck - 0000000000 : NO@ADDRESS.GIVEN | Connors, Chuck - 0000000000 : NO@ADDRESS.GIVEN |  | KAO (Kuiper Airborne Observatory) Cavity Wall Deflections |  | Perform independent validation of analysis for critical structures. | Use both FEM (Finite Element Modeling) and hand calculations for verification. Monitor the relative deflections between the Telescope Assembly and the aircraft until the pressure reaches a reasonable level. | ARC | 02/20/2001 | During the post modification pressure test, the fore and aft cavity walls deflected inward until it reached the full pressure (8.0 psi) deflection value at only 2psi. The test was stopped because of the large deflections present at only 2psi. An investigation was performed to determine the cause of the large deflection at 2psi. It was determined that the contractor had underestimated the cavity wall stiffness by a factor of 4. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 03/05/2001
926 | Bussiere, Neil - 0000000000 : NO@ADDRESS.GIVEN | Bussiere, Neil - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Program - Process Control Focus Group Machining/Equipment/Machine Maintenance Can Affect Hardware Integrity |  | Any machine which is inoperable should exhibit visible evidence that the machine is out of service. Should the cleaning fluid in the VTL or any other unintended materials come in contact with space flight hardware the integrity of the hardware could be compromised. | Maintenance should have Red-tagged the machine and the power source disengaged to prevent its use until such a time as the machine maintenance was completed and the machine could operate as intended. | MSFC | 02/20/2001 | A machinist preparing to cut a Space Shuttle Main Engine turbopump part on a Vertical Turret Lathe (VTL) noticed that the cutting fluid did not exhibit a white milky appearance as expected. The machinist also detected an unusual odor and consistency to the fluid. The machining operation was immediately terminated and area management was notified. The management team determined that the fluid was actually cleaning fluid introduced into the VTL over the weekend as part of normal routine maintenance. Although the cleaning fluid had not yet been removed there was no evidence of a Red Tag on the VTL to restrict its usage. | Red Tags or Lock-Out tags on or adjacent to a machine's power source prevent any potential operator from starting a machine which is inoperable or could potentially cause damage to hardware. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 03/05/2001
929 | Atkins, K - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Atkins, K - 0000000000 : NO@ADDRESS.GIVEN |  | Planning Effective Project Reviews (1999) | The root cause of the Mars Climate Orbiter (MCO) mission failure was identified as cumulative navigation errors. These errors resulted, in part, from operational procedures and software that were inadequately reviewed, evaluated, and implemented. A high degree of formality, anomaly follow-up and close out, selection of reviewers and penetration of technical issues is essential in the review process, including the design, operational, and peer reviews. | A high degree of formality and penetration of technical issues is essential in the review process, including the design, operational, and peer reviews. | Line organizations should assign appropriate representatives to attend reviews in their respective disciplines. For example, the Navigation line organization should be involved in system design reviews and attend all launch readiness and mission orbit insertion reviews. Review boards should assess the project proposed review agendas as stated in JPL/NASA center policy and guidelines for reviews. (see Reference 7 for JPL review policy) The board chairman should review with the board the criteria for reviews. The review board chair should review the planned implementation of the established guidelines and procedures with the process owner for technical reviews. Review board members should be advised by the board chair to pursue reasons for all anomalies revealed during reviews and ensure that appropriate action items are documented. JPL/NASA center policy and guidelines should be modified as necessary to emphasize the need to conduct, the value of, and the implementation of peer reviews. Additional Keyword: Formal Review | JPL | 11/29/2000 | The root cause of the Mars Climate Orbiter (MCO) mission failure was identified as cumulative navigation errors. These errors resulted, in part, from operational procedures and software that were inadequately reviewed, evaluated, and implemented. During development and operational phases, review board membership frequently did not include the appropriate discipline experts to identify important issues. For example, the Navigation line organization was not represented at the "MOI (Mars orbit insertion) and Aerobraking Readiness Review" during which information on cumulative navigational errors was provided. Contrary to established best practices, requests for action were not generated to address issues identified during this review. Neither the project nor the line organizations utilized peer reviews to their full potential. References: "Management of MCO Risks During Mars Encounter," Lesson Learned No. 0916 "Report on the Loss of the Mars Climate Orbiter Mission," JPL D-18441, JPL Special Review Board, November 11, 1999. "Phase I Report," (NASA) Mars Climate Orbiter Mishap Investigation Board, November 10, 1999 "Mars Climate Orbiter Mishap Investigation Board Phase I Report", Lesson Learned Number 0641, December 1, 1999 Corrective Action Notice No. Z66277, MCO-JPL/SRB Finding #4.11: "Effectiveness of Reviews," November 23, 1999. Corrective Action Notice No. Z69160, Mars Program Investigation Results: Review Process, May 1, 2000. JPL Policy: "Reviews," Rev. 7, JPL Document DMIE-10389, October 18, 2000; JPL Guidelines for Reviews (D-10401), Rev. A, JPL Document DMIE-35163, August 15, 1998. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.16 ("Management Practices: Reviews"), Paragraph 6.1.1 ("Engineering Practices: Mission Design"), Paragraph 6.14.2.3 ("Engineering Practices: Project and System Level Functional Verification and Validation - Verification and Validation"), and Paragraph 6.14.2.5 ("Engineering Practices: Project and System Level Functional Verification and Validation - Verification and Validation"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/05/2001
928 | Connors, Chuck - 0000000000 : NO@ADDRESS.GIVEN | Connors, Chuck - 0000000000 : NO@ADDRESS.GIVEN |  | KAO Aft Bulkhead Installation |  | The design and related interfaces including tooling need to be shown to fit prior to installation. | Use of a mockup to prove out the tooling and related interfaces is recommended. | ARC | 11/06/1972 | The aft cavity bulkhead was built entirely outside the aircraft with no requirements to demonstrate the actual fit inside the aircraft. After manufacturing was complete, it was discovered that the aft bulkhead did not fit inside the aircraft. An investigation of this problem revealed that the dimensions on the drawings were incorrect. The aft bulkhead wall had to be removed and modified. This additional work cost the project a delay of about 3 weeks. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 03/05/2001
923 | Stevenson, Charles - 0000000000 : NO@ADDRESS.GIVEN | Stevenson, Charles - 0000000000 : NO@ADDRESS.GIVEN |  | Quick Release Pin Causes Shuttle Launch Scrub |  | Maintenance practices, for the proper use, stowage, inspection and repair of QRPs and tethers, were not conveyed, monitored, or reinforced. Previously assigned QRP and tether corrective actions were not implemented. The VAB HB-3 quotB Roofquot F-9 platform modification's final acceptance inspection failed to detect the kickplate's tether was not installed per the drawing, nor did the inspection identify the incorrect swage on the end of the tether. The approved procedural task sequencing for inspections and platform retractions set up the conditions that permitted the QRP to fall and remain undetected in the VAB. | Standardize QRP and tether maintenance procedures across processing facilities. Add quotmaintenance practicesquot (in general) and QRPs and tethers (specifically) to first line management's Site Safety Observation Checklists, to ensure QRPs are stowed correctly, as well as to ensure maintenance inspection and repair tasks are effectively completed. Charter a cross-functional team to assess the current status of the facility maintenance program and identify areas of improvement needed to enhance maintenance effectiveness. Develop an Internet Based training course that emphasizes the expectations for achieving a quotLevel of Excellencequot for maintenance practices. As a minimum, course content should address the proper use, stowage, inspection, maintenance and repair of QRPs and tethers. Corrective Action Engineering should review, and correct as needed, their in-house recurrence control identification process. Revise and standardize final inspection acceptance criteria sheets, to verify the as-built configuration matches the released engineering design. Eliminate/minimize the handling risk associated with the current design of the F-9 kickplate. Modify the F-9 kickplate, as needed, in order to attach it permanently to the F-9 flip platform. Identify any other kickplates being used in the processing facilities that present a similar handling risk. Revise the pre-VAB rollout inspection. Procedure should constrain task sequencing to ensure upper level platforms are verified retracted, prior to performing lower level platform inspections. Revise the External Tank Pre-Launch inspection to add more detailed inspection criteria. For more detailed information refer to the Formal Accident Investigation Board Report: Quick Release Pin - Launch Delay STS-92/OV-103/PAD A. | KSC | 11/27/2000 | On 10 October 2000, during the STS-92 launch countdown T-3 hour Final Inspection, a 4-inch long and 3/16-inch diameter quotT-handlequot Quick Release Pin (QRP) and tether were discovered laying between the External Tank (ET) LO2 Feedline and the in-board Feedline Support Bracket. Photo 1 - Quick Release Pin found on inboard side of the ET LO2 Feedline support bracket The inspection team was unable to retrieve the QRP. The launch team was notified and launch was scrubbed at T-20 minutes. Removal of the QRP and tether was completed at 0226 hours on 11 October 2000. The QRP had only caused minor damage to the LO2 Feedline Support Bracket foam insulation. STS-92, the 100th Space Shuttle Mission, was launched successfully at 1917 hours on 11 October 2000. During a follow-up investigative walkdowns of the Vehicle Assembly Building (VAB) and Pad A, a VAB High Bay (HB) 3 quotB Roofquot kickplate attachment for platform F-9 was discovered to be missing a 3/16-inch diameter QRP. The F-9 platform is located 73.6 feet directly above the found QRP's resting location on the LO2 Feedline Support Bracket. Photo 2 - 2VAB HB-3 Integration Cell Platform configuration in relation to pin location The kickplate was routed to the Malfunction Lab on 16 October 2000 and the Lab confirmed a match between the paint over spray found on the QRP's T-handle and the paint on the kickplate. The Investigative Board concluded that the QRP most likely fell just prior to or during the quotB Roofquot Level F-9 platform retraction, which occurred approximately 3 hours after the pre-rollout inspection of the D-2 Level platform. The parallel task sequencing, of the platform inspections and retractions, was not constrained by current procedures. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 01/10/2001
922 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN; Mateer, W - | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Bubble Formation in Dampers May Cause Transient Un-Damped Motion (1998) | Due to the formation of a “hydraulic deadband,” MPL solar panels “flopped” when deployed following thermal vacuum test. Sustained exposure to full or partial vacuum may create bubbles in viscous damping fluids. To varying degrees, all viscous dampers are believed to be subject to bubble formation. Early in-flight deployment may reduce the risk of deadband formation in viscous fluid dampers and of subsequent structural and electrical damage. During hardware design and deployment sequence planning, consider the impact of bubble formation upon damper deadband characteristics and the effect on deployment loads and dynamics. | Sustained exposure to full or partial vacuum may create bubbles in viscous damping fluids, affecting damping mechanism performance. Early in-flight deployment may reduce the risk of deadband formation in viscous fluid dampers and of subsequent structural and electrical damage. | During hardware design and deployment sequence planning, consider the impact of bubble formation upon damper deadband characteristics and the effect on deployment loads and dynamics. | JPL | 11/01/2000 | Viscous fluid dampers commonly used to control deployments may exhibit an initial transient of un-damped motion when actuated after prolonged exposure to vacuum. The Mars Polar Lander (MPL) solar panels quotfloppedquot when deployed following thermal vacuum test. It was determined that small bubbles had risen to the top of the deployment dampers and coalesced, resulting in a region of reduced damping during the damper stroke-- a hydraulic deadband. Although the array was not damaged, a study was undertaken to evaluate the risk to in-flight deployment of the Mars Global Surveyor (MGS) high gain antenna (HGA), which uses a similar damper and is deployed following the cruise phase of the mission. [D] Deployment Hinge Assembly for the MGS HGA The study determined that exposure of a damper to vacuum produces bubbles in the silicone fluid within the vane cavity. It was found that a 20-day exposure of this particular damper to vacuum/low pressure in a gravity field will allow the bubbles to coalesce; this results in a maximum deadband of 55 degrees, insufficient to cause structural damage in this application. To varying degrees, all viscous dampers are believed to be subject to bubble formation. Reference(s): quotMGS High Gain Antenna Deployment Independent Review,quot Jet Propulsion Laboratory IOM No. 3501-WHM-98-001, William H. Mateer II, October 23, 1998. quotViscous Damper, (Sealed Damper Assembly, Non-Temp., Compensated),quot GIDEP Alert No. H6-P-98-01, January 30, 1998. Category: Subsystem and Instrument Development | The referenced GIDEP alert recommends a design approach to minimize bubble formation. This lesson will be evaluated for possible corrective action and practices may be modified as appropriate. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 01/10/2001
921 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN; Jahan, M - | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Acquisition and Oversight of Contracted Software Development (1999) | The loss of MCO was attributed to, among other causes, the lack of a controlled and effective process for acquisition of contractor-developed, mission critical software. NASA Centers should develop and implement acquisition plans for contractor-developed software and this should be described in each Project Implementation Plan. These plans must provide for Software Requirements, Software Management Planning, and Acceptance Testing and assure NASA Center verification of the adequacy of the software design approach and overall contractor implementation throughout the software life cycle. | Tailorable acquisition management and oversight processes for NASA contracted software development are essential to ensure that customers receive a quality product. | NASA Centers should develop and implement acquisition plans for contractor-developed software. The management approach for such software acquisition should be described in each Project Implementation Plan. These plans must provide for Software Requirements, Software Management Planning, and Acceptance Testing. Assure NASA Center verification of the adequacy of the software design approach and overall contractor implementation throughout the software life cycle. | JPL | 10/05/2000 | The loss of Mars Climate Orbiter (MCO) was attributed to, among other causes, the lack of a controlled and effective process for acquisition of contractor-developed, mission critical software. Under the MCO procurement strategy, JPL placed full responsibility for flight software development in the hands of a contractor/industrial partner and did not monitor the quality of the contractor's product. (See References 1 & 2.) Reference(s): "Report on Project Management in NASA by the Mars Climate Orbiter Mishap Investigation Board," NASA, March 13, 2000. Corrective Action Notice No. Z66254, MCO-JPL/SRB Finding #4.2: "Software Development Process" JPL Policy: Design, Build, Assemble, and Test Process, Section 2.4: Software Acquisition, July 7, 2000. ”Deficiencies in Mission Critical Software Development for Mars Climate Orbiter," Lesson Learned Number 0740, April 4, 2000. Additional Key Words: Contract Monitoring, Performance Based Contracting, Software IV&V, Software Quality Assurance (SQA), Software Standards, System Contractor Oversight | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.11.3 ("Engineering Practices: Software Development - Development, Maintenance and Acquisition Practices"), and Paragraph 7.1.5 ("Safety and Mission Assurance Practices: Mission Assurance Management"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.11.5.2 ("Flight Software System Design: Verification - Design for Incremental Verification"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 11/07/2000
919 | Ochs, Bill - 0000000000 : NO@ADDRESS.GIVEN | Ochs, Bill - 0000000000 : NO@ADDRESS.GIVEN |  | Principal Investigator (PI) Mode Contingency Funding |  | The first lesson learned from this event is that having the Mission Manager hold a certain amount of contingency funding at the project level and not by the PI is a definite positive. These contingency funds can be used to mitigate risks that are beyond the control of the project. Examples of these risks include new requirements that are out of scope of the contract with the PI, provide funding for up to a 30 day launch delay if the launch services provider's funds have been expended for other unforeseen circumstances, problems in observatory level Integration and Test (I&T) for which the PI may not be able to support with his/hers contingency, etc. The second lesson learned is that the amount of contingency funding held by the PI of approximately 15% is sufficient, but given the current environment regarding risk, the amount of contingency held by the GSFC Mission Manager is not enough. | First, for future PI Mode missions, the GSFC Mission Manager should hold a certain amount of contingency reserve at GSFC under his/her control. Second, the amount of contingency held at the beginning of the Implementation Phase by the PI should remain at approximately 15%, but the contingency held by the GSFC Mission Manager should be approximately 10%. This will bring the total amount of contingency funding available to the project to 25%. | GSFC | 09/13/2000 | The Solar Radiation and Climate Experiment (SORCE) Project is a PI Mode cost capped mission. During the formation of the SORCE Mission (which is a combination of the Solar/Stellar Irradiance Comparison Experiment (SOLSTICE) and the Total Solar Irradiance Mission (TSIM)), two decisions were made with regards to contingency funding. First, unlike most PI Mode missions in which the PI holds all the contingency funding, it was determined that the GSFC Mission Manager would hold a small amount of contingency. Secondly, as in the past with other PI Mode Missions the total amount of contingency would be approximately 15%. For the SORCE Mission, the PI held approximately 13% and the GSFC Mission Manager held about 5%. During the Implementation Phase of the mission, new requirements have been levied on the project with regards to acceptable risk, risk mitigation, and Software Independent Verification and Validation (IV&V). Additionally, potential changes at KSC with regards to commercialization of payload processing facilities and changes to the payload/launch vehicle integration process (driven by concerns of both GSFC project management and the PI) are also forthcoming. The new requirements and changes are threatening to deplete both the contingency funds being held by the GSFC Mission Manager and the Mission unique funds held at KSC. |  | N/A |  | Science | Public | Not Specified |  | 10/23/2000
913 | Newell, J - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Newell, J - 0000000000 : NO@ADDRESS.GIVEN |  | Space Mechanisms Reliability (2000) | Studies have shown that mechanical failures are more likely to have a significant impact on mission success than the majority of electronic failures. Spaceflight mechanisms are usually unique designs that lack the years of testing and usage common to electrical devices and in general cannot be designed with the same level of block of functional redundancy, or graceful degradation, common with electronic circuit design. The lesson provides a recommended checklist that contains 92 measures for enhancing the reliability, ease of fabrication, testability, maintainability, and robustness of mechanical designs. | Overall reliability, ease of fabrication, testability, maintainability, and robustness of mechanical designs can all be enhanced by early and continuous application of the following checklist. Parts, Materials & Processes Electronics Parts per MIL-STD-1547 Low outgassing materials per NASA JSC SP-R-0022 Limit use of hygroscopic materials Galvanic corrosion control per MIL-STD-889 Stress corrosion cracking control per MIL-STD-1568 Limit use of magnetic materials Insulating materials resistivity less than 10 Mohm-meters Honeycomb panels properly vented Anti corrosion coatings per MIL-F-7179 Deployables Self supporting in 1 g Power sufficient for deployment in 1 g Redundancy for deployment mechanism Redundancy for release mechanism Stress analysis complete Fatigue analysis complete Sliding surfaces lubricated to prevent galling or seizure Sliding surface contact pressure analyzed Pin pullers acting in double shear Pin puller misalignment loads checked Pin puller retraction force margin > 100% Pin puller stroke tolerance analysis conducted Pin puller retraction > 2 mm beyond release point Pyro cartridge devices per DOD-E-83578 Bearings Self aligning bearing used for deployables, hinges and linkages Bearings not used as electrical paths Ferrous materials corrosion resistant Ball bearing tolerances per ABEC 7, 7P or 7T CRES bearings per MIL-B-81793 Environmental loading analysis complete Preload checked under alignment, fit, tolerance, thermal and load induced distortions Fatigue analysis complete Hertzian contact stress < 335 ksi Runout tolerances checked on shafts and housings Lubricants Coefficient of friction measured Property changes in vacuum understood Checked for depletion and wear-out Operating temperatures checked Viscosity vs. temperature understood Outgassing properties known Provides corrosion protection Cleanliness controlled Run-in requirements checked Okay in humidity and salt spray environments Material compatibility understood Dry lubricants sputtered, plated or vacuum deposited Humidity controlled for MoS2 Hard coatings applied by ion implantation or CVD Hydraulic fluids per MIL-H-6083 or MIL-H-5605 Brush and Slip Ring Assemblies Carbon brushes avoided Contact forces checked Wear rate of brushes and rings understood Outgassing properties understood Sealing provisions okay Wear debris controlled or contained Lubrication applied Ring/brush corrosion prevented Lubricant depletion checked under environmental loading Electrical and Electronic Wiring routed to avoid moving interfaces Metal mechanism components well grounded to avoid charge build up Power draw checked under min, max and nominal source conditions Electric Motors A/C motors per MIL-M-13787 DC motors per MIL-M-8609 or MIL-M-13786 Adequate position and rate feedback for closed loop control Motors characterized for: rotor inertia, friction, damping, speed vs. torque, temperature effects, backdrive torque and margin Stepper motors - check detent torque and margin Springs Helical springs per MIL-S-13572 and MIL-STD-29 Fatigue life checked Temperature effects checked Redundant springs used where possible Dry film lubricant used (sans carbon) when low friction needed Dampers Viscous dampers per MIL-STD-1246 Clean fluid fill for viscous dampers (filter fluid and fill in vacuum) Seals tested to ensure no leakage Gears Manufactured per American Gear Manufacturers Assn (AGMA) Proper materials, surface hardness, and lubrication assured Proper load distribution (eg no edge or non-uniform tooth face loads during operation) No tooth pitting, brinelling and bending stresses under operating loads Impact tooth loads understood and checked Service life and duty cycle analyzed Fasteners Fastening systems per MIL-STD-1515 Threaded parts per MIL-S-8879 Minimum 5-thread engagement No screws smaller than #8 Fastener loads and stresses adequately checked Locking devices used on all fasteners (use pin, safety wire, lock thread or plastic insert; avoid compounds, springs or star type lock washers) Structure Load, stress, fatigue and fracture analyses completed Material properties from MIL-HDBK-5 and MIL-HDBK-17 Pressurized components designed per MIL-STD-1522 General Launch and operating environments defined; tests and analyses conducted Clearances checked over temperature and load conditions Failure Mode and Effects Criticality Analysis conducted Minimum integrity check: benchtop performance, followed by vibe and thermal Several of the referenced standards have been withdrawn but still represent an excellent source of guidelines. Additional Key Words: failure mechanism, mechanical faults, design analysis, design margin, mechanical anomaly, gyros, mechanism design | (See quotLessons Learnedquot) | JPL | 08/16/2000 | Studies of NASA robotic spacecraft by JPL reliability engineers have shown that mechanism failures are more likely to have a significant impact on mission success than the majority of electronic failures. Spaceflight mechanisms are usually unique designs that lack the years of testing and usage common to electrical devices. They also generally cannot be designed with the same level of block or functional redundancy, or graceful degradation, common with electronic circuit design. Mechanisms, such as deployables, intended for use after a prolonged or severe exposure to space environments provide a special challenge to designers. [D] 60-meter SRTM mast is an example of increasingly large and mechanically complex space mechanisms. Two resources are available to assist in the design and qualification of flight mechanisms: A NASA Space Mechanisms Lessons Learned Study (Reference 1) identifies common mechanical failure modes and suggests preventive measures. The study, which employed an industry survey and a literature search, covers three major categories of mechanisms-- deployable appendages, rotating systems (gears, motors, bearings, reaction wheels, etc.), and oscillating systems (i.e., gimbal bearings). JPL has prepared a Checklist for Reliable Mechanism Usage. This checklist is provided in the Recommendations. Reference 2 also provides a link to the latest version of this checklist. It provides a list of key measures that can be taken to avoid design and test oversights. Some of these items may appear obvious to the experienced mechanical engineer, but may be overlooked under deadline pressure. The Space Mechanisms Lessons Learned Study is used by JPL as a primary design reference, and the Checklist has recently been used to identify high probability/major impact failure modes subject to risk management. Reference(s): Space Mechanisms Lessons Learned Study, NASA Technical Memorandum 107046, Mechanical Technology Inc., November 1994, at http://www-rel.jpl.nasa.gov/reltec/mechpart/mti95tr4.pdf Checklist for Reliable Mechanism Usage, James Newell, Jet Propulsion Laboratory, May 2000, at http://www-rel.jpl.nasa.gov/reltec/mechpart/ mechlist.htm | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 4.2 (quotFlight System Design: Mechanical Configuration/Systems Designquot), and Paragraph 4.2.3 (quotFlight System Design: Mechanical Configuration/Systems Design - Mechanismsquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 10/20/2000
917 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate Project/Line Interaction Throughout Mars Climate Orbiter's Project Life Cycle (1999) | MCO's emphasis on lean, fast responding, project teams led to less oversight by the technical line organizations that might have detected the omissions and errors that led to mission loss. Early in the formulation phase of each project, appropriate individual project/line organization work agreements should be established and implemented throughout the project life cycle. Appropriate technical expertise external to flight project teams should be available to the projects for problem solving and peer review. Employees should be trained on all aspects of project/line organization interactions. | Lack of a culture that encourages and facilitates the use of appropriate technical expertise/resources to supplement small, cost constrained, tightly scheduled flight project teams can lead to mission failure. | Technical line organization participation in flight project development and operations should be clearly defined and established as institutional policy. Early in the formulation phase of each project, appropriate individual project/line organization work agreements should be established and implemented throughout the project life cycle (see Lesson No. 0641, Recommendation #9). The institution should assure that appropriate technical expertise external to flight project teams are available to the projects for problem solving and peer review. Employees should be trained on all aspects of project/line organization interactions. | JPL | 04/14/2000 | The JPL requirement for concurrent development of many small spaceflight missions has led to the emergence of lean, fast responding project teams. To accommodate these many projects, JPL has created a process called "soft projectization" (Reference 3) which tends to blur the roles and responsibilities of the traditional JPL matrixed project/line organizations. This process can result in far less oversight by the technical line organizations. In addition, constrained project resources and schedule pressures may lead to problems being quickly prioritized and dispositioned without recourse to JPL expertise external to these teams. This lack of interaction with management and technical experts within JPL line organizations increases the risk of omissions and the potential for errors. For the Mars Climate Orbiter (MCO) mission operations, the timely involvement of the highly experienced experts in the JPL navigation line organization would likely have revealed the erroneous delta-Vs generated by the software that compensated for small forces effects. (These errors were identified by the JPL and NASA Review Boards as the direct result of a file incompatibility that was the root cause of the MCO mission failure (References 1 and 2)). Such involvement would at least have recognized the large targeting uncertainty, which could have been corrected prior to Mars Encounter. In addition, the "soft projectization" approach led to the Project perception that line organization involvement would be intrusive, disruptive, and of little value. Similarly, some line managers tended to "wash their hands" of traditional technical responsibilities to the Project. Reference(s): "Report on the Loss of the Mars Climate Orbiter Mission," JPL D-18441, JPL Special Review Board, November 11, 1999 "Phase I Report," (NASA) Mars Climate Orbiter Mishap Investigation Board, November 10, 1999 "Soft Projectization," JPL document D-12547, Rev. 0, January 1, 1998 "Mars Climate Orbiter Mishap Investigation Board - Phase I Report", Lesson Learned Number 0641, December 1, 1999 Corrective Action Notice No. Z66275, MCO-JPL/SRB Finding 4.10: "Project-Line Interaction" Additional Key Words: Faster, Better, Cheaper (FBC) projects; organizational interfaces; communications; industrial partners; technical reviews; design reviews; training; project implementation plan | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.12.1 ("Management Practices: Project Staffing and Destaffing"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 10/20/2000
914 | Welch, Ron - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, David - | Welch, Ron - 0000000000 : NO@ADDRESS.GIVEN |  | Genesis Canister Lift Incident (2000) | Genesis: In 2000 the Genesis canister detached from a lift fixture fitting just prior to system-level thermal vacuum testing. Fabrication or test organizations should inspect all MGSE for fastener engagement and specified torque prior to delivery for use by a project. Where feasible, threaded components that are to be placed under tension should be designed with a positive locking device. Flight projects should conduct and document visual and physical inspections of MGSE prior to use. Personnel safety should be addressed, as appropriate, by all procedures. In addition, all test personnel should constantly remain at a safe distance during operations involving suspended loads. | For mechanical ground support equipment (MGSE), never assume that visual inspections alone will assure both flight equipment and personnel safety. Additional Key Words: Nondestructive Inspection, NDI, Crane, Lift Procedure, Quality Assurance, Test Procedures, Mechanical Integration, System Integration and Test, System Safety, Industrial Safety | The fabrication or test organization should thoroughly inspect all MGSE for fastener engagement and specified torque prior to delivery for use by a project. Where feasible, threaded components that are to be placed under tension should be designed with a positive locking device. Otherwise, fastener heads should be spot bonded or torque-striped, as appropriate, to enhance visual inspection of thread engagement. Flight projects should also conduct thorough visual and physical inspections of MGSE prior to each individual use (Reference 3). These inspections should be documented in appropriate procedures, such as JPL Assembly and Inspection Data Sheets (AIDS) for lifting critical hardware. Personnel safety should be addressed, as appropriate, by all procedures. In addition, all test personnel should constantly remain at a safe distance during operations involving suspended loads. | JPL | 07/19/2000 | JPL has responsibility for the development, integration, and testing of the payload (including the canister and collector arrays) for the Genesis Project, a mission to collect solar wind particles and return them to Earth. While the Genesis canister was being lifted from the transportation dolly at JPL in preparation for system-level thermal vacuum testing on May 3, 2000, the lift fixture detached at one of the three swivel hoist ring tension fittings. [D] Prior to mounting on the test chamber door, one corner of the canister fell ~5 centimeters (~2 inches) back onto the dolly. Nearby personnel cushioned the fall, and there was no damage to the Canister or support equipment, or serious injury to personnel. Post-incident inspection revealed that the threaded fastener had backed out of the fixture and became detached. Additionally, the fasteners at the other tension fittings, and at the upper hoist point, were found only hand-tight. The lift fixture assembly had been proof tested 8 months earlier. The fixture had been reassembled by the vendor following the proof test and dye penetrant inspection of the swivel hoist fittings. The fixture had last been used to lift the Canister two days prior to this incident. The fixture was visually inspected prior to the May 3, 2000 lift incident, but the hoist rings were not checked for tightness. There is no evidence that the hoist ring fasteners had been properly torqued since the proof test. The procedure governing the canister lift operation (Reference 2) did not require adequate checking of all fasteners prior to attaching the fixture to the hoist. Reference(s): Jet Propulsion Laboratory Problem/Failure Report No. Z69149, May 3, 2000 JPL Assembly and Inspection Data Sheet (AIDS) No. 216421, May 2, 2000 JPL QA Procedure QAP 61.5, quotQA Inspections of MGSE Used on JCIs.quot | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraphs 6.12.5.3 (quotEngineering Practices: Protection and Security of Flight Hardwarequot), and Paragraph 7.3.1 (quotSafety and Mission Assurance Practices: Quality Assurancequot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Science | Public | Not Specified |  | 10/20/2000
916 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate MCO Contingency Maneuver Planning (1999) | The MCO project declined further consideration of a fifth trajectory correction maneuver because it had not been adequately tested. Flight projects should review their operational scenarios and mission timelines for consistency with their mission plans and to verify that all planning and testing necessary to support mission risk management decisions has been completed with appropriate management review. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.1.1 (Mission Design) in the Jet Propulsion Laboratory standard ¿Flight Project Practices, Rev. 6,¿ JPL DocID 58032, March 6, 2006, and supporting Paragraph 7.3 (Trajectory Correction Maneuver (TCM) Scenario Design) in the JPL standard ¿Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles),¿ JPL Document D-17868, Rev. 3, December 11, 2006.quot | Flight projects should review their operational scenarios and mission timelines for consistency with their mission plans and to verify that all planning and testing necessary to support mission risk management decisions has been completed with appropriate management review. | JPL | 05/03/2000 | The root cause of the Mars Climate Orbiter (MCO) mission failure was identified by the JPL and NASA Review Boards as navigation errors caused by the software output that provided compensation for small forces effects to the JPL navigation team (References 1 and 2). The mission plan called for execution of the fifth trajectory correction maneuver (TCM-5), if needed, two days prior to Mars Orbit Insertion (MOI). TCM-5 had not been included in the baseline mission operations timeline. As a result, it had never been tested for flight sequence compatibility and for mission safety. Furthermore, TCM-5 was not included in operational readiness testing (ORT). Therefore, when the time came to execute TCM-5, the decision represented a major risk item for the MCO project. Because of this high perceived risk just prior to MOI, and the lack of compelling evidence of the need to perform this maneuver, the project declined further consideration of TCM-5. [D] Reference(s): quotReport on the Loss of the Mars Climate Orbiter Mission,quot JPL D-18441, JPL Special Review Board, November 11, 1999 quotPhase I Report,quot (NASA) Mars Climate Orbiter Mishap Investigation Board, November 10, 1999 quotMars Climate Orbiter Mishap Investigation Board - Phase I Reportquot, Lesson Learned Number 0641, December 1, 1999 Corrective Action Notice No. Z66283, MCO-JPL/SRB Finding #4.13:quotRisk Managementquot Additional Key Words: course correction, trajectory error, navigation uncertainty, configuration control, CM, software testing, compatibility testing, peer review, mission planning, mission design | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.1.1 (quotEngineering Practices: Mission Designquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 7.3 (quotFlight Scenario Design: Trajectory Correction Maneuver (TCM) Scenario Designquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 10/20/2000
918 | Montague, Ronald - 0000000000 : NO@ADDRESS.GIVEN | Montague, Ronald - 0000000000 : NO@ADDRESS.GIVEN |  | Evolution of Mission Requirements for Support Equipment |  | Equipment at all phases of processing and buildup must be used in the manner it was designed and thoroughly re-evaluated as requirements change. | It is imperative that documented procedures accurately reflect defined processes, especially when configurations change, work environments change, or new equipment is introduced. Procedures embarked upon without verification of their adequacy and correctness can lead to a false sense of security that all work is being done safely. Managers and employees at all levels must ensure that complacency is not allowed to creep into the work environment. Hardware must only be used for its intended function. As the need arises to expand that function, it must be accomplished through an appropriate evaluation and review process. Risks inherent in all phases of process execution must be assessed to ensure that appropriate safeguards and controls are clearly specified in training and procedures. | JSC | 10/17/2000 | During installation of the Thermal Micrometeorite Guard (TMG), the Short Extravehicular Mobility Unit (EMU) #3018 fell from the EMU ground test fixture (EGTF) to the floor. The primary cause of the mishap was that the EGTF was not used in a manner for which it was designed or assessed. The EGTF was designed and certified for 4-pin operations. The design of the TMG required a 3-pin operation during installation (one pin had to be removed.) The existing procedure for installation of the TMG on the SEMU did not address how the SEMU is to be handled or positioned, nor was there a procedure for the use of the EGTF. During this particular mishap, the TMG installation was being conducted with the [front] of the SEMU down. With the front of the SEMU facing up, this type of mishap would probably never occur because of the design of the pin receptacles. Proper procedures for installation of the TMG with the SEMU in an EGTF could have prevented this incident. Even thought this potential for mishap has existed since the EGTF was introduced in 1983, its presence was either recognized and not documented in a hazard analysis or not recognized at all. No formal training plan or objectives exist for personnel who handle flight equipment in the EMU laboratory. While OJT apprenticeship was implemented for these operations, there are neither measurable requirements nor documentation to support successful completion of training. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 10/20/2000
915 | Krawczyk, Richard - 0000000000 : NO@ADDRESS.GIVEN | Krawczyk, Richard - 0000000000 : NO@ADDRESS.GIVEN |  | Propellant Management for Geosynchronous Satellite |  | The fuel log had been maintained by bookkeeping method where mission analysis software provides calculation of fuel used by each thruster, based on propulsion/maneuver parameters, to track incremental fuel consumption since launch. Independent supplemental calculation of remaining fuel was done based on telemetry values for tank temperature and pressure relative to initial conditions. The uncertainty in the remaining mass of hydrazine increases with fuel depletion as calculated by both methods. This provided an overestimate of remaining fuel. | Satellite builders and operators should plan for thermal capacitance testing as an additional method of fuel gauging. Since propellant tank system thermal response is defined by mass and heat capacity, the rate of temperature rise due to a known heat input is an indication of remaining fuel in the tank. Careful location of heaters and temperature sensors can allow prelaunch calibraton and on-orbit thermal tests that can provide propellant gauging where the uncertainty decreases with depletion. | GRC | 09/29/2000 | Hydrazine fuel in pressurized tanks is used for satellite stationkeeping. Fuel consumption log indicated sufficient fuel to extend mission beyond date originally planned. During a north-south stationkeeping in July 1998, thruster firing was aborted due to satellite attitude instability caused by uneven thruster firing. This was determined to be caused by two-phase flow of liquid hydrazine and Helium pressurant gas to thrusters in the odd half-system. This only occurs when hydrazine in a tank is nearly depleted. The fuel log indicated that the tanks in both the odd and even half system should have had sufficient fuel for several more stationkeeping maneuvers, contrary to the observed performance. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 10/20/2000
912 | Lapelosa, Mary - 0000000000 : NO@ADDRESS.GIVEN | Lapelosa, Mary - 0000000000 : NO@ADDRESS.GIVEN |  | Launch Services Responsibility Under a Spacecraft Development Fixed Price Contract |  | Having a fixed price contract for a spacecraft delivery and a separate contract for the launch vehicle required the government be inserted as the responsible party between the two contracts. The dual contract environment removed the government's ability to enforce the performance penalties in the event of a launch failure and created a complexity in the spacecraft to ELV interface requirements allocation and verification process. The complexity was demonstrated by unwillingness to directly sign the launch vehicle interface control document (ICD), a joint agreement between NASA/KSC and NASA/GSFC. Instead, the TDRS Project Office at the Goddard Space Flight Center (GSFC) was forced to insert itself between the parties negotiating a launch vehicle agreement. | Future spacecraft development activities using fixed price contracting should either include launch services as part of the overall contract or require the spacecraft contractor to participate as a signature member of the Launch Vehicle Interface Control Document development process. | GSFC | 09/07/2000 | The Tracking and Data Relay Satellite (TDRS) project entered into a firm fixed price contractual agreement to procure three spacecraft as part of the NASA replenishment program of the existing fleet. This contract contains performance penalties based upon any number of failed non-operational services after launch and checkout through years 1 to 8 on orbit. The contract also specifies that NASA is responsible for the provision of the launch vehicle, an Atlas IIA as "government furnished equipment." As a result, the government is responsible for providing the Atlas IIA under a separate contract and thus became responsible for the launch and delivery to orbit. The effect of this dual contract approach was to create a built in ambiguity reducing NASA's ability to make the TDRS contractor accountable for on orbit spacecraft performance and for NASA to enforce the performance penalties. The contract requires that NASA is responsible for the safe delivery of the spacecraft on orbit and failure of the launch represents a total loss of mission to NASA. | Integration of launch services with spacecraft development under a fixed price contract is common commercial practice. | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/18/2000
910 | Tiffany, Dorothy - 0000000000 : NO@ADDRESS.GIVEN | Tiffany, Dorothy - 0000000000 : NO@ADDRESS.GIVEN |  | Corporate Organizational Changes |  | The contract financial systems, including the earned value baseline, require a substantial amount of oversight by the government to ensure the establishment of a credible financial and schedule baseline under the new management scheme. A new baseline must be established after such a major disruption and change of management in order for the new managers to accept responsibility. While Prime Contractor developed and maintained a detailed "transition schedule" to physically transfer equipment, data, personnel, etc. to the west coast, adequate follow-up and management attention at the new location was insufficient. | Appoint a management focal point and a team of subject matter experts for transition issues and actions on the NASA side. This team should be involved in the planning and implementation of any new systems and other changes necessitated by the transition from one organization to another throughout the process. | GSFC | 08/01/2000 | Numerous cost, schedule, technical and programmatic problems due to Prime Contractor's closure of East Coast production facility and program relocation to West Coast. Also, key members of contractor workforce did not relocate with the program resulting in lost program knowledge. Specific problems included: delayed implementation of financial systems, lost data (engineering changes notices, cost "actual" files), lost parts, lost tooling; additional schedule delays ("transition" testing); need for new equipment at contract cost (vertical transports for spacecraft); incompatibility of configuration management systems. Similar problems could also occur after a major reorganization or merger, causing a change in systems, especially the financial systems. | The new cost and schedule baseline has successfully predicted the contract requirements and actual cost and schedule progress has tracked closely to the plan. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/18/2000
908 | Coolidge, Dave - 0000000000 : NO@ADDRESS.GIVEN | Coolidge, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | NOAA-15(K) S-Band Antenna Failure |  | Designers of satellite elements subjected to significant thermal gradients in orbit must carefully consider the coefficients of thermal expansion (CTE) of all components in the design. A detailed thermal model must be constructed that accurately reflects in orbit temperature extremes and gradients that the element will experience. A detailed mechanical model must be constructed that accurately models both mechanical and thermal stresses within the element. For elements subjected to frequent and large thermal excursions, additional qualification testing in the form of thermal cycling should be considered. | Ensure that new flight hardware is subjected to a rigorous and well-documented peer and design review process. | GSFC | 08/01/2000 | The NOAA-15 (K) satellite was launched on May 13 1998. The satellite was the first in the new series of Polar Operational Environmental Satellites (POES) that had design heritage back to Tiros-N launched in 1978. NOAA-15, however, had three S-band antennas operating in the 1700 MHz frequency range that were new to this mission. Approximately 18 days after launch, data quality degradation was noted during tape recorder playbacks on the S-band #2 link. In October science data from the AMSU-B instrument provided by the UK was observed to have contamination toward one side of the scan field of view. The degradation was consistently evident or not depending upon the satellite orbital location. An Anomaly Review Board was established and investigation revealed that the contamination appeared to rotate around the globe as the sun moved from north to south during the annual season change. Further investigation revealed a thermal correlation to the link degradation and science data contamination as the S-band antennas experienced large thermal gradients throughout the orbit. A detailed thermal stress analysis performed for the antenna confirmed stress levels within internal connecting elements that were sufficient to cause breakage. Once broken, changes in antenna gain, axial ratio, and SWR would significantly degrade link performance and antenna patterns. The failure mode was confirmed in a thermal cycling test of a flight antenna. | The antennas were redesigned with materials that matched closely in CTE characteristics. The new antenna successfully completed qualification that included an extensive thermal cycling test. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/18/2000
911 | Berry, Richard - 0000000000 : NO@ADDRESS.GIVEN | Berry, Richard - 0000000000 : NO@ADDRESS.GIVEN |  | Provide Detailed WBS for Flight Software in the RFP |  | This organizational segregation of flight software from the spacecraft subsystems leads to a "lack of ownership" of the subsystem flight software by the Subsystem Manager. Typically, the Subsystem Manager is only concerned that he finalize his requirements and design prior to Spacecraft CDR. This in turn leads to late delivery of flight software ICDs, requirements, design algorithms, data constants, and test cases from the subsystem to the Flight Software Manager. | Force a "Software Team" approach by specifying in the software portion of the WBS that at least one representative from every subsystem organization which has active flight software (typically C&DH, GN&C, Power, maybe Thermal, Instruments) be co-located to the software group. These Subsystem Analysts will report to the Flight Software Manager, not the Subsystem Manager, and be responsible for the software deliverables. | GSFC | 09/06/2000 | The Work Breakdown Structure (WBS) in the Request for Proposal (RFP) will become the basis for the Contractor's Project organizational structure and job order numbers. If not mandated via the WBS, the Contractor may choose to organizationally segregate flight software from the spacecraft subsystems it is controlling. |  | N/A |  | Science | Public | Not Specified |  | 09/18/2000
909 | Coolidge, Dave - 0000000000 : NO@ADDRESS.GIVEN | Coolidge, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | Satellite Deployments |  | The most likely cause of the incomplete deployment of the VRA was inadequate service loops in the wire harness across the hinge of the antenna boom mechanism. Similarly, the most likely cause of the incomplete deployment of the -Y deployable sunshade was an inadequate service loop in the wire harness between the Instrument Mounting Platform (IMP) and the potentiometer in the deployable sunshade hinge assembly. | Review test procedures and hardware for all mechanisms to assure testing is done with the mechanism in the full flight configuration (i.e., test as you fly). Modify procedures and drawings to assure adequate service loops are provided in cross hinge cabling. All ground deployment testing should be conducted with the cross hinge wire harness and any insulation in the flight configuration and not redressed after stowage of the deployment mechanism for flight. If any change/redressing of cabling is necessary after deployment testing, conduct a walkout of that deployable before stowage for flight. Deployments/walkouts should be videotaped and mechanisms should be photo-documented in the deployed and final stowed position. | GSFC | 08/01/2000 | During the launch of the NOAA-K weather satellite there was an anomalous deployment of the Very High Frequency Real Time Antenna (VRA) and an incomplete deployment of the -Y Deployable Sunshade. The VRA is a two-stage deployment. Phase 1 deploys 76 degrees followed by the Phase 2, which deploys through an angle of 166 degrees. The Phase 1 slowly deployed to only approximately 58 degrees instead of its planned 76 degrees. The Phase 2 deployed its full 166 degrees. This left the VRA mispointed by approximately 18 degrees. However, this mispointing does not affect data recovery via the VRA. The telemetry indicated the -Y sunshade had not fully deployed. The incomplete sunshade deployment could not by correlated to other indirect observables, since the -Y deployable sunshade is not required for thermal control in the AM orbit. | Mechanical AGE and all related test procedures were modified to include deployment tiger team recommendations. Subsequent satellite testing was performed in flight configuration. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/18/2000
903 | Kross, Dennis - 0000000000 : NO@ADDRESS.GIVEN | Kross, Dennis - 0000000000 : NO@ADDRESS.GIVEN |  | High Energy Spectroscopic Imager Test Mishap | HESSI: The structural qualification test, a sine-burst test on a shaker table, subjected the HESSI spacecraft to a major overtest condition that resulted in significant structural damage to the spacecraft. Recognize that environmental testing carries inherent risks. Proactively maintain and track the mechanical health of test facilities, and upgrade them as necessary. Employ “canned” tests for trending. Evaluate critical control system response data real-time during vibration testing (but prior to sine-burst). Prior to test, perform a vibration facility validation test for each planned test series that is representative of the actual test conditions. Provide for self-checks. Define test requirements in the test plan for each test, and ensure test operators have adequate data and training. | Lessons Learned/Recommendations: While environmental testing has demonstrated considerable value to spaceflight projects, such testing always carries inherent risks. Test facilities must be maintained, and over time replaced as necessary, such that the test equipment is in good working order. Metrics must be developed and tracked that assess the mechanical health of the systems. "Canned" tests should be developed and periodically utilized to provide a trended database for the test facility system response. Any deviations in the system response should be investigated. Critical control system response data, such as the transfer function or inverse transfer functions and calculated drive voltage, must be evaluated real-time during vibration testing, but before application of the sine-burst to ensure that they are reasonable and do not indicate system maladies. A vibration facility validation test should be done for each planned test series that is representative of the actual test conditions before flight or critical hardware is mounted. Use of a simulated mass consistent with that of the test article is always recommended for spacecraft system level testing. Other flight equipment validation testing should be considered based on mass and criticality. Self-checks should be done that provide a representative response for the forcing range of the planned test. For higher force shock tests, shaker systems and test fixtures often do not respond in a linear fashion. It is also foolhardy to assume that test facilities are always in perfect working order. All test requirements should be defined in the test plan for a particular test. The test operators must have adequate data and training to ensure complete verification testing before testing critical hardware. | See Lessons Learned | JPL | 05/10/2000 | The High Energy Spectroscopic Imager (HESSI) spacecraft primary mission objective is to explore the basic physics of particle acceleration and explosive energy release in solar flares. The HESSI spacecraft was scheduled for a July, 2000, launch on a Pegasus vehicle as part of the Small Explorer Program (SMEX). On March 21, 2000, the HESSI spacecraft was being subjected to a series of vibration tests at JPL as a part of its flight certification program. The structural qualification test, a sine-burst test on a shaker table, subjected the spacecraft to a major overtest condition that resulted in significant structural damage to the spacecraft. The incident has been designated as a Class A mishap since the damage exceeded $1 million. A sine-burst test is a quasi-static load simulation technique. The shaker table in this incident was well over 40 years of age. The fatigue life characteristics of such shaker tables are unknown. The root cause of the overtest condition was the mechanical binding ("stiction" or static friction) between the slip table and the granite mass. It resulted from physical contact between a portion of the slip table and the granite mass caused by a mechanical failure in the shaker's support structure. The stiction caused the shaker system to present highly non-linear gain characteristics to the control system making it impossible for the controller to calculate an appropriate forcing function. This particular sine-burst was leading to a higher level qualification test. The resulting overtest level was about 10x that planned for this test, but only about 2.5X the final qualification level. Contributing Factors Identified by the Review Board: At some facilities, older test equipment may have time-related failure modes unknown to the users. Misalignment caused the slip table to exhibit non-linear behavior in that it would bind at low levels of force input. The test personnel did not have existing knowledge that data were available to assess the quality of the transfer function calculated from the self-check prior to initiating the sine-burst test. Post-test review of the transfer function used to generate the shaker drive signal for the test and examination of the drive voltage indicated that the test setup was not operating as expected and that an overtest could occur. A significant contributing factor to the mishap was the lack of a facility validation test using the sine-burst on the shaker table before the spacecraft was mounted. It is industry best practice to do a facility checkout with a simulated mass mock-up before mounting a piece of critical hardware. Such a validation test effectively calibrates the entire test setup. A further contributing factor to the mishap was a mechanical anomaly that occurred in the exciter system. The shaker appears to have shifted in its support cradle after being coupled to the slip table in preparation for this test. The shift is thought to have been caused by the breakage of the outer race of a main trunion bearing. This resulted in a misalignment that brought one area of the slip plate into contact with the granite reaction mass creating a much larger frictional drag than normal. An additional contributing factor to the mishap was the low amplitude of the pre-test self-check. If a higher amplitude self-check had been used, the control software would have more closely approximated the system transfer function and increased the probability of detecting that stiction existed. References Jet Propulsion Laboratory Problem Failure Report (PFR) No. Z68924, March 24, 2000. Report on High Energy Solar Spectroscopic Imager (HESSI) Test Mishap, HESSI Test Mishap Investigation Board, May 18, 2000. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/18/2000
904 | Chrissotimos, Nick - 0000000000 : NO@ADDRESS.GIVEN | Chrissotimos, Nick - 0000000000 : NO@ADDRESS.GIVEN |  | ESSP VCL Selection and Formulation |  | The initial cost cap category of $60M for the total life cycle cost including the launch service and a 36 month launch readiness was too low for this class of mission. The mission had proposed excellent science with new technology and a streamlined experienced management team. During the formulation phase project management and system engineering had to be changed and enhanced due to inexperience, lack of a significant infrastructure and the restricted budget, this caused a disruption and delay in the formulation phase. In addition, the instrument interfaces were not well defined and the instrument technology proved to be difficult to develop, as well as the management of the instrument definition and proposed development. For PI mode managed missions the PI needs to select an established and experienced flight project management team with the infrastructure to provide the required management functions. | The second ESSP AO was improved, including putting a greater emphasis on mission assurance, management and technology readiness levels. In addition, the cost caps were raised and schedule requirement for launch readiness lengthened. Selections were made not only on science but also on the management capability of the PI's team and the readiness for implementation. | GSFC | 07/21/2000 | Selection of VCL as the first ESSP mission, given the cost cap, schedule and mission assurance requirements as specified in the initial ESSP AO in 1996. The primary focus of the AO was on good science, low cost, short schedule, and PI led missions. The AO had minimal mission assurance requirements and relied on the proposers to utilize their current and best internal management practices with minimal NASA oversight. |  | N/A |  | Science | Public | Not Specified |  | 09/18/2000
905 | Daney, William - 0000000000 : NO@ADDRESS.GIVEN | Daney, William - 0000000000 : NO@ADDRESS.GIVEN |  | NOAA-K AVHRR/HIRS Instrument Louvers Not Connected |  | A critical review of out of flow processes is necessary to insure that no steps are deleted or improperly added. Keep good records of all "non-flight" installations. Discrepancy reports, red tags and/or a configuration log book should be mandated and reviewed at critical milestones. Double check all accessible connector matings before spacecraft shipment. | See Lesson(s) Learned. | GSFC | 08/01/2000 | After launch it was observed that the Advanced Very High Resolution Radiometer (AVHRR) instrument was running hotter than normal. The design calls for active louvers to open to radiate heat and bring the instrument baseplate temperature to within design limits. A review of the procedures used in building the spacecraft indicates the louvers were removed after Thermal Vacuum testing and reinstalled as a "Non-flight / Temporary mechanical installation" for fit check purposes. The connector was not mated at this time. A subsequent decision was made to leave the louvers in place but no notation of the lack of electrical connection was made. There was a procedure run prior to shipment, which is used to verify the mate status of every accessible connector on the spacecraft. This connector was not on the list. The NOAA-K satellite was flown with the thermal louver cable disconnected. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/18/2000
906 | Crosby, Donald - 0000000000 : NO@ADDRESS.GIVEN | Crosby, Donald - 0000000000 : NO@ADDRESS.GIVEN |  | AMSU-B EMI/EMC System Level Testing |  | The key lesson here is not a new one. Ground testing should be done in the same configuration in which you will fly. The normal on-orbit operating mode for AMSU-B is scanning. However, during much of the spacecraft level EMI/EMC testing on the NOAA-K spacecraft, the AMSU-B instrument was tested in a non-scanning mode due to a ground test, antenna bearing operating time restriction. Even though there were restrictions on the ground operating time of the instrument in the scan mode, more time could have been allocated for EMI/EMC system level testing. It is important to test all flight hardware in as near flight conditions as possible to avoid on-orbit surprises. The second lesson here is to carefully and thoroughly review all of your test data. In reviewing the spacecraft level EMI/EMC data again after the flight anomaly was noted, it was discovered that during the times the instrument was scanning, interference was visible in the data. The instrument was also tested by itself before delivery to the spacecraft and interference should have been detected there also. The third lesson is that in the design of space flight hardware, care must be taken to assure that whenever possible, hardware can be adequately tested on the ground before launch. In the case of AMSU-B, the manufacturer of the instrument was concerned that bearing lubricant would degrade through oxidation while operating at ambient pressure. They therefore imposed a ground test operating time limit on the instrument. Other lubricants and/or designs were available that would have eliminated this constraint. | See Lessons Learned. | GSFC | 01/01/2000 | After the launch of the NOAA-15 spacecraft, an EMI/EMC interference affecting science data was noted in the Advanced Microwave Sounding Unit (AMSU)-B data. This interference was subsequently attributed to the SAR and S band transmitters and was due to inadequate AMSU-B shielding. The problem was aggravated by a malfunction in the spacecraft antenna. Fortunately, the AMSU-B data was recoverable on the ground through additional data manipulation and processing. | Fortunately, the AMSU-B NOAA-K data was correctable, through ground data processing, down to the normal noise level limitation. The FM 2 and FM 3 units, which were still on the ground, were physically modified to include more shielding for radiated emissions. Subsequently, they were retested for radiation susceptibility and demonstrated performance nearly at the noise limit. Any remaining noise effects will be correctable through ground processing. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/18/2000
907 | Brumfield, Mark - 0000000000 : NO@ADDRESS.GIVEN | Brumfield, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | Core Competency of Subcontractors |  | If an offer seems too good to be true, it probably is. By extending beyond the core competencies at the subcontractors, major financial and schedule impacts were incurred. In addition, it is imperative that the core competencies be understood at the onset of the procurement activities. | In any instance where a contractor is doing something for the first time, significant oversight is needed. Try not to develop new abilities on flight hardware. This runs the same risks as developing new technologies if significant oversight by persons with acumen of the subject is not provided. | GSFC | 08/01/2000 | The POES Program made a decision to embellish an instrument by incorporating a new scanner design. This new design was to replace a weak motor with a stronger one that would have the same operational performance. In doing this, the motor and the drive electronics had to be replaced. The Prime Instrument contractor always subcontracts out the build of the motors, and this time the decision was made to allow the motor vendor to build the control electronics as well as the motor. The build of the control electronics was a new venue for the motor vendor and made an equitable offer to the Prime for both the motor and the control electronics. The vendor was never able to produce the control electronics and that activity had to be brought back in-house by the Prime. As a consequence, the modification experienced a significant over-run and substantial delays in the delivery of the units. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/18/2000
902 | Thurow, Lori - 0000000000 : NO@ADDRESS.GIVEN | Thurow, Lori - 0000000000 : NO@ADDRESS.GIVEN |  | Hydrazine Cylinder Shipping |  | NASA has an exemption on these cylinders to authorize their transportation, even though they were constructed with material not currently on the material list in the code of regulations and for how they were acceptance tested. These cylinders are just as safe as the general regulation's intent, but allow variances to the general regulation. Exemptions are quite often how new containers enter into the transportation codes. These DOT exemptions may have transportation mode restrictions. When shipping a cylinder with a DOT exemption number on the side of the cylinder, shipping department personnel must recognize the need to review the terms of the exemption before shipping the cylinder. Shipping department personnel may not have copies of the exemption or may not be familiar enough with the code to recognize that they need a copy of the exemption. | The cylinder storage personnel should hand over a copy of the DOT exemption to the shipping department as part of their paperwork to request shipment. The cylinder storage personnel who have these exemption-covered cylinders must have access to and understand the requirements of the exemption. Shipping department personnel must be trained to recognize the need to review the terms of all DOT exemptions and to include the exemptions as part of the shipping documentation. | KSC | 06/28/2000 | A hydrazine cylinder containing 11 liters of Hydrazine was shipped to the Kennedy Space Center (KSC). The shipping paperwork indicated the cylinder contained 1 liter of Hydrazine. The cylinder was transported by cargo air. Although transportation regulations allow cargo air transportation for quantities of this commodity up to 2.5 liters, the cylinder is covered by a Department of Transportation (DOT) exemption that specifically requires either motor vehicle or cargo vessel (boat) transportation regardless of quantity. The exemption takes precedence over the general regulation. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 09/11/2000
901 | Williams, George - 0000000000 : NO@ADDRESS.GIVEN | Williams, George - 0000000000 : NO@ADDRESS.GIVEN |  | Wearing of Proper Undergarments with Fireproof materials such as Nomex Increases Survival Chances from Burn Injuries |  | The second layer of protection prevented burns in the covered area. DuPont has on the label of their manufactured NOMEX garments that only NOMEX or natural fibers silk, wool or cotton be worn as undergarmets with NOMEX outer garmnets. Victims with burns over less than one half of the body have a good chance of survival. Short sleeve and short pants undergarments would provide this about 50% protection. Long undergarments would provide even additional protection. | Wear NOMEX or natural fiber cotton, wool or silk undergarments under NOMEX outer garments. Whenever possible (such as low risk from heat stress during cold weather), wear long undergarmets under the NOMEX. | JSC | 07/12/2000 | Two workers in Donaldson, La Plant Explosion.. Both were wearing NOMEX OVERALLS. One employee was wearing no under garments; burns over most of the body. The second employee was wearing cotton shorts and tee shirt; there were burns only where the undergarments did not cover the body. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 08/28/2000
897 | McGlynn, R - 0000000000 : NO@ADDRESS.GIVEN | McGlynn, R - 0000000000 : NO@ADDRESS.GIVEN |  | Approval Process for Launch Vehicle (LV)/Spacecraft (SC) Interface Control Document (ICD) Changes |  | The formal ICD approval process should include the SC contractor in order to ensure comprehensive review/accountability by all parties. | The SC contractor should be added to the formal LV/SC ICD review/approval process. The IRN document should be changed to include a signature block for the SC contractor. | GSFC | 07/25/2000 | Changes to an approved LV/SC ICD are submitted via an Interface Revision Notice (IRN) document. The existing formal approval process requires the signatures of NASA-GSFC (SC), NASA-KSC (LV), and the LV contractor on all IRN submittals. Noticeably absent from the formal process is the SC contractor. NASA-GSFC and the SC contractor have an informal agreement whereby the change is reviewed and concurrence is documented via e-mail correspondence. During the GOES-L "Red Team" review process the omission of the SC contractor in the formal review/approval process raised the question of legal/liability issues. |  | N/A |  | Science | Public | Not Specified |  | 08/04/2000
898 | Vernacchio, Albert - 0000000000 : NO@ADDRESS.GIVEN | Vernacchio, Albert - 0000000000 : NO@ADDRESS.GIVEN |  | Hubble Space Telescope Servicing Mission Operations Training |  | Include key JSC Shuttle Operations positions in "internal" mission simulations to the extent possible to facilitate early team coordination and improve mission readiness. | Include key JSC Shuttle Operations positions in "internal" mission simulations to the extent possible to facilitate early team coordination and improve mission readiness. | GSFC | 07/27/2000 | During mission operations training for HST Servicing Missions, GSFC conducts "internal" simulations to prepare the operations for Joint Integrated Simulations with the entire Shuttle Operations Team. It was recognized early on that it would be a tremendous benefit to include key JSC positions including the payload officer and his support team in these internal simulations. This facilitated early JSC/GSFC team coordination prior to Joint Integrated Simulations. It also improves the realism of the training by modeling all of the interfaces and to a certain extent modeling some normal work tasks and anomalies external to either center. For SM3A, this type of training was also deemed valuable to the Lead Flight Director who also participated in some "internal" simulations. References Hubble Space Telescope Servicing Mission 3A Evaluation and Lessons Learned Report, LMMS/P056329, Baseline Issue, April 5, 2000. STS-103 Internal Post Flight Report, JSC Memorandum to Distribution from STS-103 Lead Payload Officer |  | N/A |  | Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/04/2000
896 | McGlynn, R - 0000000000 : NO@ADDRESS.GIVEN | McGlynn, R - 0000000000 : NO@ADDRESS.GIVEN |  | Minimizing Impacts Associated with Construction Operations at Mission Critical Facilities |  | Both facility (construction schedule) and Project requirements must be maintained in a fashion that minimizes the impacts to both. Furthermore, any collaborative strategy developed to minimize conflicts must not compromise the ability to meet mission success criteria. | Construction activities should be suspended in mission specific support areas of a mission critical facility (e.g. control center) 30 days prior to launch. This will insure that verified interfaces are preserved in support of mission operations, and mission success criteria. Furthermore, configuration management and safety requirements dictate that cabling exposed during construction should be labeled and signs posted as to potential hazards. | GSFC | 07/18/2000 | Construction operations aimed at improving accommodations or improving the capabilities of a mission critical support facility are required periodically. An extensive construction effort was underway at the Spacecraft Operations Control Center (SOCC) in Suitland, Maryland during the period immediately preceding the launch of the GOES-L spacecraft (5/3/00). Standard operating procedure for the SOCC is to freeze the hardware/software configuration of the facility 30 days prior to launch. On-going construction at the facility made it difficult to satisfy this requirement without impacting the facility construction schedule, which can effect multiple programs. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 08/04/2000
895 | Roth, Don - 0000000000 : NO@ADDRESS.GIVEN | Roth, Don - 0000000000 : NO@ADDRESS.GIVEN |  | Software Simulation |  | Software simulation can aid in 'better, faster, cheaper'. It can be used as a risk management tool where risk in this case is not meeting schedule. | Software simulation can be used in similar situations where software developers are waiting for hardware. | GRC | 07/27/2000 | I was involved in a project in which we were developing a new control and data acquisition system for an instrument to be used to measure radiation absorption in clouds. The instrument was being refitted with electronic hardware that was to be controlled by software I was developing with a peer. Only problem was that the hardware was not ready for 3 months while we were supposed to be developing the software. And the project was on a very tight deadline. What we were able to do was create a software simulator to test and validate many of the features of how our software was supposed to work. Of course, this cannot truly be substituted for the hardware but it can get you 50% or more of the way there (depending on the particular project). This allowed us to complete the project on schedule. Additionally, the simulator drove us to create a truly standalone simulator to be able to demonstrate to others how the instrument and interface will work together. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/04/2000
900 | Lewis, D - 0000000000 : NO@ADDRESS.GIVEN | Lewis, D - 0000000000 : NO@ADDRESS.GIVEN |  | Working with Foreign Contributors to NASA Missions/Flight Assurance |  | In PI-mode missions with a foreign partner making a major hardware contribution, reconciliation during the proposal stage of NASA's and the partner's approaches to setting environmental standards and structuring environmental tests and QA program features may avoid protracted delays later. A good place to start is with definition of terms, e.g., Preliminary Design Review may not mean the same thing to CNES as it does to NASA. | Early agreement on definition of terms & on environmental standards, test, and QA programs; need to avoid policy of not insisting on an appropriate level of insight just because foreign partner has offered a contribution; could be a significant risk to NASA's investment in the mission. | GSFC | 07/31/2000 | Schedules that had been agreed, on closer examination, turned out to mean something different than parties expected; design loads presented to NASA for use in designing a mission payload were wildly conservative & could lead to significant cost increases. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/04/2000
899 | Lewis, D - 0000000000 : NO@ADDRESS.GIVEN | Lewis, D - 0000000000 : NO@ADDRESS.GIVEN |  | Working with Foreign Contributors to NASA Missions/Contributions |  | In PI-mode missions with foreign partners making hardware contributions, misunderstandings may be avoided if these contributions are defined in terms of the items or services to be contributed, rather than as a commitment to a specified resource level. | Agreements between NASA and foreign partners (e.g., MOUs) should describe the hardware to be contributed and be written such that the contributor accepts the development risk rather than NASA. For hardware items, the higher the level of assembly the better, because the interfaces tend to be cleaner. | GSFC | 07/31/2000 | Foreign contributor committed to a dollar value & then found that initial cost estimates for the proposed contribution were grossly understated; consequently partner provided only a partial delivery of their contribution, leaving a shortfall for NASA to make up. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/04/2000
894 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Sinusoidal Vibration | Preferred Practice for Design & Test. Probability of failure is increased in flight due to low frequency transient environment. Some workmanship defects in large structures and full-up systems may go undetected. Subject assemblies and the full up flight system to swept sinusoidal vibration. This practice has been used on Mariner Series, Viking, Voyager, Galileo. | Probability of failure is increased in flight due to low frequency transient environment. Some workmanship defects in large structures and full-up systems may go undetected. | Subject assemblies and the full-up flight system to swept sinusoidal vibration. | JPL | 01/31/1999 | This Lesson Learned is based on Reliability Practice PT-TE-1406 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Certain failures are not normally exposed by random vibration. Sinusoidal vibration permits greater displacement excitation of the test item in the lower frequencies. Apply sinusoidal vibration to the test item by sweeping over a frequency range beginning at approximately 10 Hz (± one octave) up to approximately 100 Hz (± one octave). Sweep the frequency range at a logarithmic rate (i.e. delta f/f is constant). Sinusoidal vibration is performed with the same fixturing and concurrent with random vibration. Sinusoidal vibration is employed to simulate the effects of significant flight environment launch transients. These transients typically produce the dominant loading on primary and secondary structure and many of the larger subsystems and assemblies. Sinusoidal vibration is the only widespread current method of adequately exciting the lower frequency dynamic modes -- particularly those below approximately 40 Hz. Sweeping at a log rate between 1 octave/minute and 6 octaves/minute should avoid application of excessive fatigue cycles. The higher rate is near the upper limit which most control systems can accommodate without experiencing some instability. The use of logarithmic sweep rates has the advantage in that a nearly equal time is spent at resonance for a given Q, independent of frequency. Sinusoidal vibration levels can be derived as in the following example: Step 1. Create analytically derived transient waveforms from various flight events: [D] Step 2. Compute the shock spectra for each of the waveforms in Step 1: [D] Step 3. Take data from previous flight measurements: [D] Step 4. Combine results from steps 2, and 3 and envelope: [D] Step 5. Convert to a sine amplitude equivalent vs. frequency by dividing Shock Response Spectrum envelope in Step 4 by Q: [D] Alternatives to the use of swept sine vibration testing are currently under development which address several of the objections to this method. In particular, the problem of excessive resonance build-up in a sinusoidal vibration sweep relative to the flight transient environment may be alleviated by any of the following tests: Narrow band swept random. Discrete frequency sinusoidal pulses applied at regular frequency intervals. Complex waveform pulses representative of a composite of the various launch transient events. | This practice has been used on Mariner Series, Viking, Voyager, Galileo. | N/A |  |  | Public | Not Specified |  | 07/24/2000
889 | Cramer, Bryant - 0000000000 : NO@ADDRESS.GIVEN | Cramer, Bryant - 0000000000 : NO@ADDRESS.GIVEN |  | Budgetary Reserve Recommendation for Technology Validation Missions |  | A 10% budgetary reserve is inadequate for a technology validation mission. The EO-1 experience suggests that 15% is a minimum and 20% would be preferred. Three characteristics peculiar to technology validation missions require this additional reserve. Accurately assessing the maturity of an advanced technology is very important. Considerable reserve can be quickly expended in maturing a technology to reach flight status consistent with the aggressive schedule typical of such missions. In a related way, using reserve to overcome whatever difficulties may be encountered in the fabrication of "first-time" flight hardware is another activity that can quickly consume considerable reserve. Lastly, the exact performance needed to effectively validate the advanced technology may not be fully understood until rather late in the definition process and this may increase the cost of the spacecraft. | Future technology validation missions should carry a minimum budgetary reserve of 15% at the Confirmation Review. | GSFC | 06/28/2000 | The New Millennium Program's First Earth-Observing Mission (NMP/EO-1) was selected for flight in March 1996 and completed its Confirmation Review in May 1997. At the time of selection, the EO-1 Project had a 10% budgetary reserve. By the end of the Confirmation Review nearly 75% of this reserve was committed to additional mission definition, an overrun in one of the advanced technologies, and implementing four risk mitigation recommendations of the Confirmation Review Board. The Goddard Space Flight Center Program Management Council recommended that the EO-1 budget be augmented by 7.3% to restore the reserve committed during the definition process. After review, the Earth Science Enterprise provided the additional budget. | Subsequent experience with other technology validation missions has indicated that this recommendation is appropriate for this class of missions. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 07/13/2000
887 | Jungewaelter, Jan - 0000000000 : NO@ADDRESS.GIVEN | Jungewaelter, Jan - 0000000000 : NO@ADDRESS.GIVEN |  | Hazards of Providing NASA Hardware for Public Display |  | Spacecraft hardware and test articles used for public display must be thoroughly scrutinized for hazards prior to release to the public. The Lunar Module test article had been stored safely without incident for over 25 years. Personnel should resist the temptation to become complacent with items that are assumed to be safe. Toxic vapor checks of large systems may not indicate the complete status of a contaminated system. Artifacts previously contaminated with a hazardous substance must be fully decontaminated prior to release to the public. This includes flushing of all portions of the system as well as removal of all softgoods. Museum personnel must be fully informed of potential hazards. | Perform a thorough evaluation of all potential hazards prior to releasing artifacts for public display. Artifacts previously contaminated with a hazardous substance must be fully decontaminated prior to release to the public. This includes removal of all softgoods. If inaccessible, secure and mark fluid lines and volumes which may be potentially contaminated. Ensure museum personnel are fully informed of potential hazards. | WSTF | 06/14/2000 | During preparation for public display of a Lunar Module Test Article, museum personnel claimed to be exposed to a small puff of brown/orange vapor, presumably oxidizer. The incident occurred August 23, 1998, when the museum technician was removing portions of lines that were not representative of flight configuration. The test article had been field decontaminated and checked for oxidizer contamination prior to shipment to the museum. It may be possible that some isolated portions of the system and offgassing from the flexhose softgoods may have been overlooked as potential sources of oxidizer. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 07/13/2000
888 | Cramer, Bryant - 0000000000 : NO@ADDRESS.GIVEN | Cramer, Bryant - 0000000000 : NO@ADDRESS.GIVEN |  | Skill Requirements for Technology Validation Missions |  | Due to the risky nature of the advanced technologies to be flight-validated, we determined that our traditional project organization was not well suited to deal with this new kind of mission. More specifically, we identified the following shortfalls in our organization: We needed someone with insight into these new technologies who could devote all of their time to managing their maturation to flight status and to define the best way to validate them once on orbit. We needed additional help for the Mission Systems Engineer to devise a system and subsystem architectures to minimize the interaction between the advanced technologies and thereby maximize the likelihood of flight-validating them while remaining within the mission cost cap. We needed risk management well beyond what we would expect for a small science mission. | Based on the above lessons learned, we make the following recommendations for future technology validation missions: Provide a full-time Mission Technologist to manage the technologies assigned to the mission for flight-validation. Provide sufficient system engineering to develop a cost-effective architecture that minimizes the interaction between the advanced technologies. Provide a Risk Manager to develop a more robust risk management than we typically employ. | GSFC | 06/27/2000 | The New Millennium Program's first Earth-Observing mission (EO-1) is a technology validation mission designed to flight-validate advanced imaging technologies applicable to a Landsat follow-on mission. It includes a pushbroom multispectral imager, a hyperspectral imager, an atmospheric corrector, and several spacecraft technologies applicable to future remote sensing missions. The EO-1 advanced technologies are reflected in Figure 1. | Subsequent experience with other missions within the New Millennium Program has served to reinforce applicability of these recommendations. | N/A |  | Science | Public | Not Specified |  | 07/13/2000
884 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | Lack of Communication Leading to Aircraft Tow Incident |  | Inadequate means for communication during towing can lead to damage to aircraft. Pre-briefing wilth all tow personnel prior to each tow will assist in planning each tow and avoiding potential towing incidents. For this incident, a pre-briefing would have brought to everyone's attention that the scaffolding had been moved off-center and that potential collision with the scaffolding would be likely. Painting of a new alignment centerline would have likely avoided collision of the aircraft with the scaffolding. | A detailed review of the towing incident revealed that the procedures were adequate, all personnel were certified to participate in the towing of the aircraft, and that whistles are provided for use during towing operations. For this particular incident, personnel did not following the towing procedures. Disciplinary actions were taken by company management and emphasis was placed on correctly following towing procedures. | ARC | 05/22/2000 | A ground crew was towing the NASA owned B747SP to the nose docks at Raytheon E-Systems Waco facility. Damage to the aircraft was sustained when the crew was trying to position the aircraft in the nose dock. The aircraft was slightly off center and while it was being moved, it struck one side of the nose dock. The extent of the damage was about 30 square inches located on the left hand side of the aircraft just aft of the flight deck, close to the emergency escape area. Ground handling personnel did not have whistles or any other means to properly communicate with the tug driver. An alignment centering line had been painted on the hangar floor but the scaffolding had since been moved off-center without notifying all ground tow personnel. | An audit was successfully performed to verify compliance with establish procedures. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/14/2000
885 | Menke, R - 0000000000 : NO@ADDRESS.GIVEN; Welch, R - ; Oberhettinger, D - | Menke, R - 0000000000 : NO@ADDRESS.GIVEN |  | Verify Configuration of Flight Hardware Prior to Test (1998) | During a system-level ambient functional test of the MPL spacecraft, the software test sequence commanded the gimbaled medium gain antenna through its full range of motion, striking one of the undeployed solar panels. Confirm that developmental and flight hardware is in a configuration that has been reviewed for hardware and personnel safety prior to beginning any test sequence and that the appropriate procedure for powering down flight hardware in all test configurations under any potential emergency condition has been determined. Hold a thorough Test Readiness Review using the most current checklist that addresses personnel safety, software and hardware safety, test operations and constraints, fault protection actions, kinematics and interference analysis, commandability, emergency shutdown, and restart procedures. | It is necessary to confirm that developmental and flight hardware is in a configuration that has been reviewed for hardware and personnel safety prior to beginning any test sequence. Real and potential structural interferences should be mapped and documented for all deployable/articulated components on the spacecraft. This should be done for all spacecraft test and operational configurations. | Where movement of articulated or deployable mechanism is commanded in any test of developmental and flight hardware: Determine the appropriate method and procedure of powering down flight hardware in all test configurations under any potential emergency condition. Never compromise the ability to command the spacecraft/test article while a test is in progress. Hold a thorough Test Readiness Review using the most current checklist that addresses personnel safety, software and hardware safety, test operations and constraints, fault protection actions, kinematics and interference analysis, commandability, emergency shutdown, and restart procedures. This review should include a vehicle walkdown prior to test and should be attended by subsystem and flight operations specialists to assure that the test remains consistent with constraints. | JPL | 06/07/2000 | Flight hardware was damaged, and personnel safety potentially compromised, during a system-level ambient functional test of the Mars Polar Lander (MPL) spacecraft intended to simulate the mission profile immediately after landing. The software test sequence that was programmed into the vehicle commanded the gimbaled medium gain antenna (MGA) through its full range of motion. This inadvertently drove the MGA into one of the undeployed solar panels, cracking the composite antenna reflector dish and scratching the substrate of that solar panel. [D] MPL in the quotLandedquot Configuration A previous test left the solar array configured on the lander in the stowed position. This undeployed mechanical configuration obstructs a full-range-of-motion test of the MGA. As the impending collision was observed, the test conductor attempted to command a halt to the motion. However, the commands did not execute because the uplink path was then in the process of being reconfigured from hard-line to radio frequency. Furthermore, the emergency power-off switch only governed the ground support equipment and could not shut down the spacecraft since it was in a battery-powered flight configuration. The primary causes of this test incident were: Configuration Control. Failure to confirm, prior to testing, that the lander was in the quotlandedquot configuration with the solar array deployed to allow full motion of the MGA. Flight Design. Omission of a method for emergency removal of battery power to the vehicle. Reference (2) describes a similar omission. Reference: Jet Propulsion Laboratory Problem/Failure Report No. Z47115, September 8, 1998. Inadvertent Powering of the Deep Space 2 Mars Microprobe, JPL Lesson Learned No. 0626, June 21, 1999. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraphs 6.12.5.3 and 6.12.5.7 (quotEngineering Practices: Protection and Security of Flight Hardwarequot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 06/14/2000
886 | Oberhettinger, David - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, David - 0000000000 : NO@ADDRESS.GIVEN |  | Mission Assurance During Mars Climate Orbiter Operations (1999) | Although a mission assurance manager was assigned to MCO during project development, there was no independent mission assurance function established for the work performed at JPL following launch. Require an independent Mission Assurance representative during the operational phase of every flight project. This individual should become familiar with and integrated into the project during the latter phases of development, and possess independent responsibility to verify compliance with design and operational requirements. Require all flight projects to report and track post-launch anomalies on ISAs. Project management should rigidly enforce this requirement and maintain a disciplined disposition, tracking and resolution process. | See Recommendation(s) | Revise JPL mission assurance policies and procedures to require an independent Mission Assurance representative during the operational phase of every flight project. This individual should become familiar with and integrated into the project during the latter phases of development, and possess independent responsibility to verify compliance with design and operational requirements. See Lesson No. 0641, Recommendation #14. Require all flight projects to report and track post-launch anomalies on ISAs. Project management should rigidly enforce this requirement and maintain a disciplined disposition, tracking, and resolution process. See Lesson No. 0641, Recommendation #10. Note: Any project member observing an anomaly is empowered to write an anomaly report. | JPL | 04/27/2000 | Although a mission assurance manager (MAM) was assigned to Mars Climate Orbiter (MCO) during project development, there was no independent mission assurance function established for the work performed at JPL following launch. The decision whether to have a project-level mission assurance function during the operations phase was previously at the discretion of the JPL project manager. The JPL Mission Assurance Management and Independent Assessment process now requires a Mission Assurance representative for all flight mission operational phases. A lack of continuous mission assurance oversight was noted by the JPL MCO review board. Contrary to established practice: The spacecraft was launched without end-to-end testing to validate Angular Momentum Desaturation (AMD) file compatibility with the ground-data system navigation software. The JPL MCO review board identified file incompatibility as the root cause of the MCO mission loss. Discrepancies between the delta-Vs expected by the Navigation Team and those produced by the AMD file were observed during mission operations. However, no Incident/Surprise/Anomaly report (ISA) or Problem/Failure Report (PFR) was ever written on this issue. The Navigation Team documented the issue in an e-mail and attempted to resolve it informally. The investigation was dropped prior to resolution as it was considered to be low priority subsequent trajectory correction maneuvers (TCMs) were expected to resolve these discrepancies. Reference: Report on the Loss of the Mars Climate Orbiter Mission, JPL D-18441, JPL Special Review Board, November 11, 1999. Phase I Report, (NASA) Mars Climate Orbiter Mishap Investigation Board, November 10, 1999 "Mars Climate Orbiter Mishap Investigation Board - Phase I Report", Lesson Learned Number 0641, December 1, 1999. Corrective Action Notice No. Z66257, MCO-JPL/SRB Finding 4.4:"Mission Assurance," November 23, 1999. Corrective Action Notice No. Z66268, MCO-JPL/SRB Finding 4.5: "Problem Reporting, Tracking, and Closeout," November 23,1999. Additional Key Words: FRACAS, Failure Reporting and Corrective Action System, Product Assurance, Software Test, SQA, Software Quality Assurance, Documentation, Management Oversight | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.6.1 ("Safety and Mission Assurance Practices: Problem Reporting"), Paragraph 7.7.1 ("Safety and Mission Assurance Practices: Mission Operations Assurance"), Paragraph 7.1.1 ("Safety and Mission Assurance Practices: Mission Assurance Management Practices"), Paragraph 7.6.14 ("Safety and Mission Assurance Practices: Problem Reporting"), and Paragraph 7.7.1 ("Safety and Mission Assurance Practices: Mission Operation Assurance"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/14/2000
862 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | 3.5-Foot Hypersonic Wind Tunnel Ceramic Bed Matrix Heater Mishap |  | The ceramic bed heater is especially vulnerable to excess differential pressure across the bed. Location of the lower pressure port created a single point failure that allowed the differential pressure to develop uncontrolled. Steps which could have been taken to prevent this mishap from occurring could have been more rigorous reviews, identifying the pressure ports in the vessel as safety critical features, listing them as such on the fabrication drawings and in failure modes analyses, and assuring that inspection during construction was accomplished. Formal configuration management should commence immediately following design completion. This configuration management may be tailored to the size and scope of the project. In cases of contracting for hardware or software systems, NASA should participate in or thoroughly audit the Contractors systems to assure adequate configuration controls. The Systems Engineering process, functioning in a project to define and understand all system interfaces, is extremely important. It is even more important for rehabilitation type projects where interfaces between the old and the new systems can become critical. The Trial Run approach of IST for establishing differential pressure settings for safety limits offered no provision for detecting system faults such as the incorrectly located pressure port. It could only have succeeded with a correctly functioning system. The test plan should have provided predicted (calculated) values of differential pressure across the orificed grate as a function of header pressure and valve position. Lines of authority and responsibility must be defined and functioning for a safe and successful ISH process. Project responsibility should extend through the IST process and until the facility is recertified operational and returned to the operating organization. With known high incidence of errors in developmental software, a methodology should be implemented for simulation modeling of systems for software testing prior to putting research facilities at risk. Commercial software systems are available for these purposes. Real time recording and storage of run data for review and diagnostic use is very important whenever attempting the final validation of a control system and its associated software. It is extremely important when using actual system hardware to support the validation process. The more dynamic the system's response to input, the greater the consequences of control system failure. Investigation of unexpected behavior of high energy or otherwise potentially dangerous systems should include support analyses or other positive causal verification which cannot result in detriment to the system, before proceeding with full system operation. | Inspect, repair and verify integrity of all internal heater vessel structures. Correct and relocate lower pressure port in the heater vessel to assure its location is well below the grate and any influence on the flow by the flow diverters. Perform another review of engineering and hazards analyses on all facility interfaces, with specific emphasis on interfaces between the old and the new. Identify the function of the pressure ports as having potential for a single point failure causing a critical mishap. Correct and recertify the software, followed by institution of a higher level of configuration management requiring NASA review and approval of changes. Inspect and correct malfunctions in the hardwire trip circuit system. Verify the reliability and independence of the hardwire trip system. Develop predicted performance differential pressure characteristic values, based on planned test parameters. Use these expected values to set tolerance bands to be flagged as limits for IST. Establish procedures for review of test values falling outside the flagged limits, and for clearing the flags. Provide a high speed data acquisition system for use during IST for recording of run data that might be required for diagnostic purposes. | ARC | 05/22/2000 | Test personnel from the 3.5-foot Hypersonic Wind Tunnel facility, supported by personnel from the project phase 3 contractor, were conducting blowdown tests as a part of the Integrated Systems Testing (IST). The tests were being done to certify the operational status of the facility following a construction of facilities project for rehabilitation of the facility. The mishap occurred seconds after the start of the 5th run of the day, at approximately 10:00 a.m. Four previous blowdown tests had been completed on that day without incident. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/06/2000
863 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | Modular Building Fire |  | Require detailed inspections for all new trailers and modulars. Assure that these inspections include all electrical and mechanical systems with special emphasis on potential ignition sources such as heating coils. When alarms tests are conducted, verify that the fire department dispatch office (duty office at Ames) receives the proper building number. | Survey existing buildings and be responsible to see that all buildings have correctly posted and clearly visible building numbers. The Center's maps should be updated periodically and distributed to all emergency organizations. Replace the back-up fire alarm receivers with models that can correctly report the building number consistent with the main receiver. Alarms to the duty office, during periodic testing, should verify the building number. Assure adequate fire truck access when determining site for a facility. Do not locate modular buildings in places that do not have access directly to streets. The trailer/modular building standard, which NASA is currently developing, should require more detailed inspections of such facilities with special emphasis given to the building mechanical and electrical systems. Construction inspectors should conduct periodic inspection of modular buildings under construction on site. Specify that all furnaces with electric re-heat or auxiliary heating coils be provided with access panels at the electric coils. This would allow for initial and periodic inspection of the coils for dust and debris accumulation. The new NASA trailer/modular guide specification should include access panels at electric furnace heating coils. Also, the same should be included in the Ames local trailer guide specification. | ARC | 05/22/2000 | A fire occurred in a modular building, #T-046, at the NASA Ames Research Center at Moffett Field (Mountain View), California. The building was about three months old, purchased and assembled on site by American Modular Systems, Inc. The building was occupied by code OFX, Range Systems Branch. In the area that the fire occurred, research in microwave landing systems was being conducted. The fire was first reported by a building janitorial worker, who noticed the fire at the rear of the structure at or near one of the four wall-mounted heat pumps. The alarm was received at the Moffett Field Fire Department at 0100 hrs. The first engine company arrived at 0103 hrs. and the fire reported extinguished at 0143 hrs. Most of the fire damage occurred above the suspended ceiling with some heat and water damage below, and some damage throughout the building. Various test equipment and computers located on work benches were damaged. The building was subsequently closed. The fire started at the mouth of one of the heat pump units located at the discharge duct connector. At the discharge flange of the heat pump there are electric resistance heating coils that operate under various conditions in which the unit is unable to produce sufficient heat. Six manufacturing deficiencies were discovered at these duct connectors. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/06/2000
864 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | Table Saw Injury to NSI Technology Services Corporation Employee |  | The contractor's Safety and Health Plan should be reviewed and revised to include a training/certification program for individuals on the safe operation of major (table saw, lathe, automatic punch/press, drill press, etc.) shop equipment. Periodic refresher courses should be considered as part of this plan. Specific written procedures should be developed for the proper and safe operation of major shop equipment. This should include both basic and critical recommendations. A table saw should never be used for cutting small pieces of wood if a push stick cannot be employed or if the stock being cut makes it necessary for the operator's hand to be within six inches of the saw blade. Insure that safety meetings are held on a regular monthly basis in accordance with the NSI Health and Safety Plan. These meetings should involve a free flow of safety information between management and the workers. Management should provide support for all reasonable safety requests. This forum should also be used to conduct updates/reviews of good safety practices of the operation of different major equipment each time. All major shop equipment should be on a scheduled preventive maintenance program. The program should not only check for the condition of the equipment, but also evaluate and advise on the condition of the cutting tools and other peripheral items associated with the safe operation of the equipment. In the future, it is imperative that after a serious accident nothing at the accident scene be altered. Preserving the accident scene will allow the investigators the chance to review and study the actual conditions and allow photographs to be taken for the record. Regular meetings should be held between the Contracting Officer (CO), Contracting Officer's Technical Representative (COTR), Sub-COTR and contractor to insure that work performed is within the scope of the contract. First aid supplies are available through the ARC Stores Stock Catalog. This information needs to be conveyed to the ARC Staff and supplies need to be distributed to the appropriate areas. During operating hours, the Ames Health Unit should respond to all 911 emergency calls of a medical nature. Even if their presence is not needed, it could have a calming/stabilizing effect at the accident scene. | See lesson(s) learned. | ARC | 05/22/2000 | An employee of NSI Technology Services Corporation (NSI) injured his right hand in a table saw accident. The injury occurred when the employee was modifying conference room chairs. Two fingers were severed and a third was severely damaged. The employee was taken to the hospital for emergency treatment and was released. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/06/2000
866 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | High Altitude Missions Branch Fatal Mishap |  | Government and industry need to increase their efforts to educate and heighten the awareness of users regarding the lethality of nitrogen and other inert gases and the rapid onset of asphyxia when these gases are inspired. New safety provision and requirements should be documented in existing organizational safety plans required by AHB 1700-1. It is the responsibility of management to insure awareness of these plans with periodic safety review staff meetings for both Government and contract personnel. Consideration should be given to amplification of management responsibility for dealing with emergencies and mishaps, and to dissemination of this information by means of an appropriate memorandum to all management at reasonable intervals. NASA should require training and/or certification procedures for personnel working with inert gases under circumstances such that they can become asphyxiants. Thorough training and checkout should be given to all new personal equipment technicians in the High Altitude Missions Branch notwithstanding their previous knowledge of and experience with the equipment. The nitrogen regulator and outlet to the portable testing kit in the personal equipment maintenance room should be placarded. A warning placard near or over any testing console or workbench utilizing nitrogen or other inert gas should make reference to the hazards of asphyxia. Consideration should be given to the use of breathing air instead of nitrogen as the gas supply for personal equipment testing in this facility. A number of contractor and/or NASA personnel in the High Altitude Missions Branch should receive cardiopulmonary resuscitation training. At this time, the nearest CPR-trained staff members are in Building 240A, too far away to be of much help in the event of a serious problem in Building 240. | See Lesson(s) Learned. | ARC | 05/22/2000 | A personal equipment technician employed by a California Company in support of the operations of the High Altitude Missions Branch, was fatally injured by inhalation of nitrogen while conducting a periodic inspection on a pressure helmet. It is presumed that the technician donned the helmet in the course of his inspection; he then closed and secured the face seal. The helmet was connected to a source of nitrogen, the gas used in the facility for bench-testing and maintenance of this equipment. The technician lost consciousness within 20-35 seconds after beginning to breathe nitrogen; he was found by a coworker at 3:15 p.m., deeply cyanotic and unresponsive. Cardiopulmonary resuscitation efforts were unsuccessful; the technician was pronounced dead at the hospital upon arrival there by ambulance. A post-mortem examination was conducted by the Office of the Coroner-Medical Examiner, County of Santa Clara. The cause of death was stated to be asphyxia due to inhalation of nitrogen gas. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/06/2000
865 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | Ames VTOL Test Pad Personnel Injury Accident |  | Clarify the crew leader's role and responsibility in relationship to the truck driver's role and responsibility. Require a more critical inspection by the crew leader of all loads prior to moving any loads. Place more emphasis on center-of-gravity problems/considerations in current crane operating safety courses. Since we will probably have to handle this same load again, determine and incorporate a safe means for future handling. Continue to furnish, or supplement, advanced training to maintain a high level of safety awareness on the part of all riggers. Consult private industry rigging firms to determine new methods. Insist upon the proper utilization of hand signals between the crane operator and the load spotter. In the future, attach a tether line to all loads. | See Lesson(s) Learned. | ARC | 05/22/2000 | One of two truck driver employees of Contractor's Cargo Company, was lifted or hurled, from the top of a flatbed trailer parked on the NASA-Ames Vertical Takeoff and Landing (VTOL) Test Pad. This mishap occurred while the employee was positioning a load suspended in slings on the flatbed. The towbar of the load, which was the flatbed front wheel assembly, rotated from a vertical to horizontal position upon being touched or moved by the employee. In the course of being lifted or hurled from the truck by the towbar, the employee sustained serious head injuries and was transported, unconscious, to a hospital. He remained at the hospital for about a month, then was transferred to Southern California. He was still in a coma when he was transferred. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/06/2000
868 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | Mishap At The Underground Air Storage Facility |  | The underground casings of the UASF have experienced anodic corrosion at their exterior surface resulting in a loss of wall thickness of up to 50 percent with localized areas being even greater. The cathodic protection applied to the UASF has been grossly inadequate. Based on these findings, it is only a matter of time before another failure occurs. The most recent failure could have caused personnel injury (The spouting of water and air and the throwing of mud). Therefore, it is the recommendation of the Investigation Panel that the UASF be abandoned and another high pressure air storage facility, if needed, be constructed. The idea of an underground facility should not be rejected because of the recent experience. An underground facility seems attractive from a safety standpoint and, with a properly designed protection system, should be considered with other alternatives in an engineering study. The Investigation Panel recognizes that the missions and goals of the Center may require the continued use of the existing field in the interim. The Investigation Panel has given consideration to this possibility and offers the following guidelines: Convert the existing manual isolation valves, on each cluster, to remote actuation to allow isolation of an individual cluster and limit the release of energy. Install a venting system, to vent a cluster in case of emergency, to further reduce the release of energy. This vent could be a simple rupture disk that is punctured by a remotely actuated knife. Install an adequate cathodic protection system to slow or arrest the anodic corrosion. The possibility exists of using the test well as the sacrificial anode. Inspect the remaining casings to determine their condition. The maximum operating pressure should be based on engineering analysis of the condition of the field and the required additional life. | See Lesson(s) Learned. | ARC | 05/22/2000 | A casing in Cluster #1 of the Underground Air Storage Facility (UASF) ruptured releasing high pressure air (3000 psig) into the substrate at about 500 ft below the surface. Although, quick action by the crew isolated the UASF from the rest of the distribution system, the entire 5x106 SCF of air, stored in the UASF, was released through the rupture. The released air created a crater around the affected cluster and sprayed mud onto the surrounding area for a radius of approximately 150 feet. Damage was localized to the one cluster. However, personnel that had entered the area to attempt to isolate the individual clusters from the manifold were exposed to streams of water and mud when evacuating the area. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/06/2000
869 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | Prop-Rotor Mishap in 40'x80' Wind Tunnel |  | Ensure that adequate design and stress analysis have been done and documented for all critical components in models and test hardware. Insure that all components have sufficient load capacity. Perform comprehensive design review and instrument accordingly for health monitoring. An important goal is to do a comprehensive FMECA by knowledgeable systems engineers or designers, prioritize potential failures based on probability, look at consequences of failure in priority order, and then develop instrumentation and emergency procedures on this basis. This is a difficult task, but when there are many potential single-point failures and the consequences of failure is high, it is worth significant effort. Bearings and fasteners are notorious failure points (even if not highly loaded). They must be monitored, maintained, and replaced accordingly. During design reviews, do not overlook parts designed by contractors even though this may be difficult for proprietary reasons. Because some parts have high safety factors does not mean they all do. In fact, hardware that has been used and modified several times is very likely to have a large variation in safety factors. If control systems are designed to lock up to preclude further inputs, Wind Tunnel Emergency Stop should be the only course of action when lock up occurs. Minimize voice directions during emergencies. When open loop control systems are difficult to control, they should be automated (loop closed). When doing research in which control rates are sensitive, human factor considerations become important and must be considered. There should be inspections or verification during assembly and maintenance procedures at critical points. It should not be up to one person to be responsible for the entire assembly or maintenance. Documentation must be comprehensive. | Select an appropriate sized bearing set and redesign the housings as required. Based on an updated analysis decide on components that should be monitored during testing and add appropriate instrumentation such as thermocouples or resistance temperature detectors. The adequacy of all components must be carefully checked using appropriate loads; documentation must be completed. Modify procedures so that if emergency conditions are encountered when the rotor torque is negative the Emergency Stop is initiated. Realistic limits should be set up, and then if they are encountered a Wind Tunnel Emergency Stop should be activated. Give the monitor for the Bar Chart Monitor an Emergency Stop button. Develop a closed-loop control for E/F and RPM that provides accurate control and relieves the operator of the workload associated with control of these variables. Consideration should be given to human engineering the control consoles. Special consideration should be given to emergencies. Assembly procedures should be well documented, and there should be mandatory in-process inspection points. It is not fair nor prudent to place full responsibility for accurate assembly on one person. Improve maintenance documentation; for example, records of bearing changeout should be maintained. When an incident occurs and actions are taken there should be sign-offs by the Branch and Division Chiefs approving actions taken or intended. Insist that each manager from section head on up through the NFAC organization be totally accountable to the process of configuration management. NFAC has the written process in place. Management must make sure it does what it's supposed to do; i.e., control all potential hazards. Critical components such as fasteners and bearings must be accurately described. Add blade angle (or collective actuator position) to the PCM tape, and incorporate means of ensuring the azimuth position on the tape is reliable before testing. Consider adding Wind Tunnel dynamic pressure to the tape as well. Use dual tape machines that overlap tapes so that tapes do not have to be changed during a run, or shorten the runs. Modify the Data Acquisition System (DAS) so the data on the PCM tape are not interrupted, or change the procedure to not record data on the DAS during emergencies. The outer race retaining nut should be modified (i.e., by extending it and adding a shoulder) to stop the inner race slider from moving very far in the event of a bearing failure. Consider locating a collective blade angle transducer closer to the blades as a safety monitor. Because the signal would have to go through the slip rings and would therefore be less reliable, it is recommended that this be a safety monitor only and not replacement for the present system. Reinforce the bottom rails of the first fence, and double the height of the second fence. A quick verification is to do a hardness test, and hardness testers are not very expensive. Therefore, it would be worthwhile to sensitize the Wind Tunnel operators and mechanics to fastener problems and for them to have their own hardness tester for quickly and conveniently checking all fasteners they have doubts about. When doing armor plate/fragmentation calculation it is usual to assume the maximum impact velocity is at the maximum normal tip speed. Because of the over-speed encountered, this assumption should be reconsidered. | ARC | 05/22/2000 | A mishap occurred with the Propeller Test Rig (PTR) in the 40'x80' Wind Tunnel at an airspeed of about 200 knots. The model was a 25' diameter, three bladed prop rotor, and it was rotating at a speed of about 500 rpm before the mishap. The mishap was caused by failure of a bearing set in the collective pitch control system during a run in which several data points had been taken and new conditions were being set up. The rotor torque went from about 10,000 ft-lb to ñ2,000 ft-lb (model motors went from acting as motors to generators), and the rotor control system locked up as it was designed to do at ñ2,000 ft-lb of torque to prevent actuator failures from causing damage to the PTR. At this time it was recognized that there was a problem, and the designated procedure was followed which was to open the breaker to the model motors. Opening the breaker (although it had happened automatically) had been successful during an incident that occurred on March 21, 1991, and it was thought that this was a similar event. As soon as the breaker was opened the rotor began to accelerate. Because the rotor blades had gone to a lower blade angle (unknown at the time) the rotor accelerated to a very high speed. Redlines were rapidly indicated on the Bar Chart Monitor, and as soon as this occurred the Wind Tunnel Emergency Stop was initiated. However, the failure had progressed too far, and the rotor continued to speed up until it self-destructed due to overspeed. The rotor reached a speed of close to 1000 rpm; the safe operating limit was 630 rpm, and the structural limit for the blade tension straps was 930 rpm. At overspeed, one blade tore loose and lodged in the top of the test section. The remaining rotor and mast assembly tore loose from the model drive system due to the imbalance. The mast landed on top of the Rig, and the rotor assembly went down the tunnel coming to rest against the safety fence. Some of the debris went past the first fence, but most was collected against the fence attached to vane set 5 which is the last vane set ahead of the Wind Tunnel drive fans. The only damage to the Wind Tunnel drive was a small gouge in one of the blades. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/06/2000
856 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | SOFIA B747 Aircraft Upper Rudder Incident |  | Perform adequate planing prior to performing the task.Verify that adequate resources are available. | Implement procedures to require identification of critical tasks where human error can result in pesonnel death/injury and/or substantial damage to equipment. Implement procedures to require adequate planing including verification that required resources (personnel experience, procedures, and tooling) are available. Require management signature on a critical task planing checklist to indicate adequate planing of resouces has been accomplished. Perform periodic audit to verify implementation of the procedure. | ARC | 02/04/2000 | The SOFIA B747 upper rudder was dropped after it was removed from the tail of the aircraft and was in the process of being placed on a flat bed trailer. Maintenance personnel attempted to rotate the removed rudder from the vertical to the horizontal position. This task was performed without the use of a holding/transport fixture as defined within the specific task job card and utilizing only two of the four attach points called out in the written procedures. Prior to removal, the procedures were reviewed and found adequate to perform this task. While the procedures addressed the equipment and the process for removal of the rudder, they did not address the process beyond installation of the vertical rudder on a dolly. Though telephone calls were made in an attempt to locate equipment required by the procedures, there was none available when the decision was made to proceed with the rudder removal. The production supervisor admitted responsibility for the decision to proceed without all of the equipment required by the procedures and he proceeded to transition the rudder from a vertical to a horizontal position. The transition was attempted by unfastening the two harness support brackets on one side of the rudder. As the crew began the transition, the loading was multiplied by approximately 800 lbs. of counterweights on the rudder's leading edge, a condition for which the sling assembly and attach points were not designed to carry. Of the three bolts at the point of failure, one bolt stripped the threads on exit, another pulled the attachement receptacle through and out, and the third bolt pulled the attachment receptacle and surrounding structure loose from the rudder. | Audit was performed by NASA to verify adequacy of corrective action. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/05/2000
859 | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN |  | Facilities, Complete Contract Specs. Requirements |  | There is more to filling up a hole that just throwing the dirt back into it. Compaction is very important and if it is not done properly, the dirt will settle and you will be left with a big sinkhole. | There is more to filling up a hole that just throwing the dirt back into it. Compaction is very important and if it is not done properly, the dirt will settle and you will be left with a big sinkhole. | GRC | 08/23/1999 | A water line coming into a building was being increased in size to accommodate a new building sprinkler system. The excavation was done, but the compaction that should have been done was not. The specification of backfilling was not part of the contract documents. |  | N/A |  |  | Public | Not Specified |  | 06/05/2000
858 | Leiffer, James - 0000000000 : NO@ADDRESS.GIVEN | Leiffer, James - 0000000000 : NO@ADDRESS.GIVEN |  | F-18 Drop Model Battery Box Problem |  | That all components located in the battery compartment be inspected prior to sealing the box to ensure no loose clips or any other material is present. | Conduct final inspection prior to sealing boxes. | LaRC | 02/11/2000 | A loose metal clip inside of a sealed battery box appeared to cause a short that caused excessive heat to build in the NiCd batteries and in turn cause additional shorts between the individual cells. These secondary shorts caused a runaway condition that could not be stopped until the battery voltage was drained. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/05/2000
857 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | SOFIA B747 Aircraft Towing Incident |  | Supervisor must assure adequate resources in terms of equipment and safety briefing are performed prior to initiating aircraft tow activities. | Provide training to supervisor and tow operators on the importance of safety briefing and having adequate resources prior to performing towing activities. | ARC | 02/07/2000 | The SOFIA B747 aircraft was being towed into the large maintenance nosedock inside the 7500 hangar building at the Raytheon, Waco facility. As the aircraft approached the nose dock it made contact with the upper support structure of the nosedock. Labor and material costs were identified as less than $10,000. There were no personel injury associated with the incident. The damage is located at FS 480, stringer 2A, exterior top left side of fuselage. The exterior skin deformation is approximately 18" in lenght and 14" in width, with approximately .250 indentation of skin on either side of the frame. No fracturing of external skin is visible. The cause of this incident was attributed to the following: Insufficient clearance between top of the aircraft and nosedock support structure. Lack of clear communication means between the aircraft/nosedock clearance observer and the tow task supervisor. Supervisor failure to ensure tow team members were pre-briefed on specific duties and resposnsibilities prior to performance of the task. Supervisor failure to properly plan aircraft tow operations prior to task performance. Supervisor failure to ensure tow team personnel possessed required support equipment (Not all task assigned personnel possessed alert whistles/horns). | Government representative performed audit of towing opeations to verify adequate corrective actions were implemented. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/05/2000
861 | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN | Briceno, Anthony - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate Holding/Transport Fixtures Leading to B747SP Rudder Damage |  | Failure to use appropriate holding/transport fixtures as defined within the specific task job card can result in damage to the rudder. Inadequate procedures to achieve safe removal of the rudder from the crane/sling can result in damage to the rudder. | Critical tasks such as rudder removal have been defined and a checklist has to be prepared to determine process, skill, tooling, training, and procedures requirements. During planning, if an area of the requirements is insufficient or a special circumstance exists, the checklist and documentation will be routed to engineering. Upon completion of the critical task planning function, the disciplines involved will approve the plan. Production will write a work instruction for each critical task, attach a pre-task checklistform, and coordinate with personnel involved in performint the task. Upon issuing instructions to the floor, the task supervisor will verify requirements, review and sign the checklist, and make sure each individual has the proper knowledge and skill. | ARC | 05/18/2000 | The upper rudder of the 747SP aircraft was removed from the aircraft tail. The rudder was lowered lengthwise in the vertical position to a flat bed. The rudder was rotated to a position above the flat bed. The rudder was next rotated to a hinged up horizontal position. The two right hand fittngs were removed and the rudder was rotated over towards the right side. The lower left hand fitting pulled the screws and some surrounding structure from the rudder. This allowed the rudder to fall on the flat bed and then approximately 30 inches to the concrete floor. One area 8 inches by 5 inches of the rudder frame and skin was pulled loose. One threaded lock was pulled loose and one threaded lock was stripped. Several rivets were popped on one of the counter weight attachments and minor bending on the lower end of the rudder. | An audit was performed to collect objective evidence that adequate controls have been implemented and are working satisfactorily. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/05/2000
860 | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN |  | Facilities, Mod & Rehab, Added Team Member |  | It becomes a logistics nightmare for a Project Manager to coordinate people moves in a Mod and Rehab project. | Include in the Project Team a Move Coordinator. This person would work along with the Project Manager to ensure a smooth transition for the inconvenienced building occupants. | GRC | 08/23/1999 | The Mod and Rehab projects are typically requiring that people be moved out of offices while the construction activity is taking place. As a result, there is an extra burden on the Project Manager to coordinate people moves. Along with the moves come the issues of telephone and computer moves, because different organizations handle these moves. In addition, there is also the issue of where are the people going to be temporarily moved to. During the planning phases of moves, it becomes a full-time job to coordinate all the above activities. |  | N/A |  |  | Public | Not Specified |  | 06/05/2000
867 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Use of GN2 for Valve Corrosion Control |  | When a pneumatically actuated valve is deactivated and the valve changes position, the valve diaphragm returns to the normal position and provides a vacuum at the actuator breather. This results in the outside air being drawn into the actuator chamber, along with any contaminants in the air. At the Space Shuttle launch pads the contaminants that are in the air include salt spray, SRB exhaust, possible N2O4 vapors, and water from high humidity. The contaminants cause corrosion in the actuator chamber affecting the operation of the valve. Providing GN2 to the actuator breather eliminates the possibility of drawing contaminants into the chamber. | GN2 is provided to the actuator breather of pneumatically actuated valves used in hostile environments (salt spray, high humidity, SRB exhaust). | KSC | 05/21/2000 | This Lesson Learned is based on Maintainability Technique number OPS-16 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Attaching a source of GN2 to the actuator breather provides an atmosphere in the actuator chamber of pneumatically actuated valves that prevents corrosion thus lengthening the life of the valves. GN2 is provided to the actuator breather of the pneumatically actuated valves. The source may be a dedicated GN2 source or a more efficient means would be to tap off a nearby panel that uses GN2 for an environmental or hazard proofing purge. A line connected from the panel to the actuator breather port would allow access to the GN2 for filling the valve actuator chamber when the valve is deactivated (see Figure 1). [D] When designing the system, caution should be used to prevent or minimize back pressure on the actuator which would reduce actuator performance. | This practice has been used on the Space Shuttle Program and the KSC Launch Operations Area Hypergolic Servicing System. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/24/2000
882 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Computer-Aided Laser Shaft Alignment of Rotating Machinery |  | Rotating equipment (i.e., pumps, motors, compressors) are sensitive to the alignment to each other and to the smallest of changes due to operating conditions. Proper alignment is the largest factor in determining the life of bearings, seals and couplings. Even quotflexiblequot couplings fail to completely absorb the additional stresses caused by misalignment. Misalignment causes these crucial components to become overloaded and break down prematurely, especially when operating at high speed. More conventional methods, such as using feeler gages and dial indicators are too inaccurate and require a complicated, time consuming alignment process. | The use of laser methodology for the critical shaft alignment of rotating machinery. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number OPS-14 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Reduction in the failure rate of rotational equipment due to induced failures resulting from improper or inadequate installation, providing more efficient operation as well as reduced operating and maintenance costs. This practice identifies the use of a laser alignment system for installation of machinery with rotating shafts (i.e., pumps, motors) to obtain optimum alignment coupling, resulting in less wear and increased reliability. The laser system is a low power, pulsed semiconductor laser. The detector is a biaxial, analog photoelectric semiconductor position detector with a resolution of 1 micron. The linearization characteristics of each laser detector are unique and are stored in the systems computer, thus only the detector and computer specifically matched to each other may be used together. The laser transmitter is attached to the shaft of the stationary machine and the reflector is attached to the shaft of the machine to be moved. The prism reflects the beam in a plane parallel to that in which it receives the beam. As the prism shifts along the radial axis during rotation, the spacing between the beams is altered, and from this difference the offset of the shafts are determined. In the perpendicular plane, the prism acts as an ordinary mirror. As the prism is rotated about its vertical axis, the angle between the entering and reflected beams changes, permitting angular misalignment to be computed. The computer receives its input data directly from the detector through a connecting cable and calculates the alignment correction values for the feet of the machine to be moved. The computer can also detect the presence of quotsoftfootquot on the shaft alignment. Softfoot results from the mounting base not providing a level and even surface for securing the equipment, resulting in an unstable installation and misalignment leading to premature failure. The system can be used for gauging the amount and effect of softfoot, but cannot determine the cause or corrective action. The objective of alignment is to ensure that the rotating shaft centerlines of different machines are aligned. It is important to understand that alignment refers to the positions of 2 centerlines of rotation. Shaft alignment means quotPositioning two or more machines so that their rotational centerlines are collinear at the coupling point under operating conditions.quot Collinear means 2 lines that are positioned as one line or 2 lines in exactly the same place. As used in alignment it means quotTwo or more lines with no offset or angularity between them.quot The phrase quotcoupling pointquot acknowledges that vibration due to misalignment originates at the point of power transmission, the coupling. It does not mean that the couplings are being aligned. The shafts are being aligned, the coupling center is just the measuring point. quotUnder operating conditionsquot is taking into account that the machines often move after startup due to wear, thermal growth, dynamic loads or support structure shifts. The term quotshaft alignmentquot implies that the bearings and shafts are free from preloads. In properly installed equipment, there are no outside forces or strains on the bearings or shafts. A laser alignment system eliminates the effects of irregular shaft or coupling surfaces, eccentricity, bent shafts, etc. Unlike conventional methods using dials and gages where a spanner bar is used, there is no sag in the laser beam. The effects of vibration on the alignment process is insignificant, as the laser beam travels at the speed of light. The laser system is a 25 to 1 improvement over the dial measurement system, with a 0.00004quot resolution. Simplified Version of How the Optics Work [D] A side view of laser and prism. When the prism is moved up or down, the return beam moves up or down twice the distance the prism moved. Thus measurement offsets between two points can be determined. The offset measured is the offset of the prism relative to the laser. [D] Offset measurement The detector can not only sense up and down motion of the return beam, but side to side as well, However, if we slide the prism side to side, the beam does not move. The beam will move side to side only if we rotate the prism in the horizontal plane. Prism moved side to side; beam does not move. [D] Horizontal rotation moves beam. [D] Note that the angle the return beam moves is twice the angle the prism moves. If the beam is zeroed at the 12:00 position and then read at the 6:00 position, the X reading (or horizontal beam movement) is one leg of a 90 deg. triangle. The distance from laser to prism is the other leg. The angle defined by these two legs is two times the actual angular misalignment between the shafts. The position detector is an analog biaxial photoelectric cell with a repeatable resolution of 1 micron (or approx. 0.00004quot). Because beam movement is twice prism movement, system repeatability is 0.5 micron or (approx.) 0.00002quot. Devices such as position detectors are highly nonlinear and subject to many manufacturing variables. To compensate for nonlinearity, the electronics contain sophisticated linearizing algorithms that linearize the output of a given position detector with 2% of beam displacement. Thus, overall measuring error is less than 2% of displayed value, rounded off to 0.5 mil. Reference: The OPTALIGN Training Book (catalog No. 01-705-01) Ludeca, Inc. 1527 N. W. 89th Court Miami, FL 33172 FAX (305) 591-8935 | This practice has been used on the Hypergol Maintenance Facility (HMF) at the Kennedy Space which uses a stainless steel pump for pumping hypergolic fuels. This pump needed replacement approximately every 3 months at a cost of about $30,000. The need for replacement was due to seal and bearing failure caused by misalignment. New equipment was installed using the laser alignment system and based upon vibration measurements of the operating machinery, noticeable improvement in operation was achieved. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/24/2000
883 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Facility Chilled Water for Thermal Conditioning Unit (TCU) |  | An existing FCW system is tapped into to provide the heat exchange medium used for conditioning the hypergolic propellants to the acceptable limits for loading the Space Shuttle tanks. This eliminated a Freon conditioning unit that was previously installed at each propellant storage area thereby eliminating the associated operating and maintenance expenses. | Use of the Facility Chilled Water (FCW) System to provide the heat exchange medium for the hypergolic propellant Thermal Conditioning Units (TCU). | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number OPS-15 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Incorporating this technique eliminates the need and cost of a separate cooling system to be designed, installed and maintained at each propellant storage area. Maintainability and reliability of the TCU is greatly enhanced since the individual cooling systems have been removed in lieu of connections to the existing Facility Chilled Water (FCW) System. While at the launch pad the Space Shuttle Orbital Maneuvering System (OMS) and Reaction Control System (RCS) propellant tanks are filled with hypergolic propellant; Monomethylhydrazine (MMH) and Nitrogen Tetroxide (N2O4). The OMS/RCS is used for altitude and attitude changes required by the Shuttle during orbital flight. Loading of the tanks takes place about two weeks prior to launch. A temperature requirement is imposed on the propellant for loading to assure proper operation of the Ground Support Equipment (GSE) and to assure proper weight measurement of the loaded propellant. The temperature requirement is met by raising or lowering the propellant temperature as required by flowing through the Thermal Conditioning Unit (TCU). If the propellant temperature is below that required, the facility chilled water is heated in the TCU heater before flowing through the heat exchanger where the propellant is brought up to the required temperature (see figure 1). [D] If the propellant temperature is above that required, the heater is not operated and the FCW provides the heat sink needed to lower the temperature. Each MMH and N2O4 storage area has a TCU. The FCW is piped to the propellant storage areas through insulated tubing from the launch pad FCW system. Filters are provided in the pad FCW system to prevent contaminants from damaging or clogging downstream components. Using the FCW System to provide the heat exchange medium eliminates the need for a separate conditioning unit at each TCU. The previous TCUs used a Freon conditioning unit for temperature control of the propellant. Eliminating those units eliminates the high operating and maintenance costs and environmental concerns associated with each Freon heat exchanger. Reference: KSC Drawing 79K05081 - Hypergol System Schematic Pad 39A. | This practice has been used on the Space Shuttle Program and the KSC Hypergolic Propellant Loading System. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/24/2000
849 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Predictive Maintenance Program |  | Predictive maintenance is a technique which checks the "health" of an item while it is operating using one or more sophisticated tools. The capabilities for predictive maintenance exists because of the availability of desktop computers, and the increased sophistication of equipment monitoring instruments. Too much or too little maintenance is avoided because the equipment is monitored on a regular basis providing trend data that can be used to project probable machine alarm dates. According to the Electric Power Research Institute (EPRI), the annual maintenance cost of such a program is reduced by 50% or more to between $7 and $9 per horsepower. | Predictive maintenance is a technique that allows for a systematic method of monitoring and trending of equipment condition. This activity takes place while equipment is on-line and provides early warning of equipment operation approaching out of limit conditions. | KSC | 12/01/1994 | This Lesson Learned is based on Maintainability Technique number OPS-13 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Predictive maintenance allows for scheduling of maintenance when it is required and when it will have the least effect on scheduled activities requiring support of the equipment in question. Unexpected equipment breakdowns and scheduled maintenance downtime for periodic disassembly and inspection to determine equipment condition are virtually eliminated. Additional discussion of the benefits of predictive maintenance is provided in the following pages. Predictive maintenance is a technique which checks the "health" of an item while it is operating using one or more sophisticated tools. The capabilities for predictive maintenance exist because of the availability of desktop computers, and the increased sophistication of equipment monitoring instruments. Too much or too little maintenance is avoided because the equipment is monitored on a regular basis providing trend data that can be used to project probable machine alarm dates. According to the Electric Power Research Institute (EPRI), the annual maintenance cost of such a program is reduced by 50% or more to between $7 and $9 per horsepower. Predictive maintenance has received a great deal of attention in the past five years or more. U. S. industry spent $200 billion in 1985 alone, to maintain plants and equipment. Studies by the EPRI show that the annual maintenance cost of repairing machinery when it breaks down (corrective maintenance) is $17 to $18 per horsepower. Contrasted to that is preventive maintenance, which uses statistics to determine the probable health of equipment. However, in the real world, machines do not follow averages. The result is usually "over maintenance" or "under maintenance." The EPRI Studies show that the annual maintenance cost per horsepower using preventive maintenance is between $11 and $13. As was stated earlier, the EPRI study shows that predictive maintenance reduces manual maintenance costs to between $7 and $9 per horsepower. Benefits from implementing a Predictive Maintenance Program include: Condition of equipment under a predictive maintenance program is known, permitting repairs to be planned and carried out without interrupting scheduled support activities. Reduced maintenance costs are realized through the use of predictive maintenance. Maintenance needs can be anticipated and planned. Maintenance activities are more efficiently planned from a standpoint of manpower, parts, and tools. Catastrophic failures, which impose secondary, expensive damage, are also avoided. Improved equipment performance is achieved through the use of predictive maintenance. Predictive maintenance measures equipment condition so that corrections can be made before performance is compromised. Predictive maintenance provides several potential areas for energy savings. Elimination of high energy vibration sources such as misalignment and imbalance will reduce machine power consumption. Motor phase imbalance, which increases power consumption can be corrected resulting in savings in power and increased motor life. Technical Description Predictive (or condition-based) maintenance is an outgrowth of a preventive maintenance program. Today's state of the art technologies, readily available user friendly desk top computers, and increased sophistication of equipment monitoring instruments, now make it possible to have a reliable and cost effective predictive maintenance program. The first step in developing an effective predictive maintenance program is to determine the cost of the maintenance program such as cost for maintenance personnel, repairs, spares and cost associated with losses incurred due to equipment being down. The next step is to identify the number of man-hours required to monitor the equipment. Simple machinery (motors, pumps, or fans) will require fewer points to accurately detect developing problems than more complex equipment, such as turbines or generators. By counting the pieces of equipment and the number of measurement points, you can estimate the level of manpower required. More critical equipment may require more frequent monitoring, which will increase manpower requirements. The monitoring frequency is a function of the critical nature of the equipment; so the next step is to set up an equipment classification system. For example: Class 1 - essential equipment - includes equipment that must be on-line to continue all or a major part of a process. Loss of this equipment would have a major impact on safety, productivity and availability. Also included in this group would be equipment that has a high repair cost, or a long lead time for ordering repair parts. Class 2 - critical equipment - includes equipment that would limit a major part of a process, and equipment with high initial replacement costs, or chronic maintenance problems. Class 3- serious equipment - includes equipment that is not critical to process, but require monitoring to ensure acceptable process performance. Class 4 - other equipment - includes high speed or high load machinery that is prone to premature failure because of its severe operating mode, but is not considered critical to the process. Once equipment has been properly grouped, the data acquisition schedules and routes can be established; and projected manpower levels determined. If sufficient staff is not available, the potential savings from the program must justify additional personnel. Besides salaries, costs should include the cost of diagnostic and analytical equipment, office space, and any overhead costs that will be charged to the group. Costs should also include training and additional skill development. Training costs can range from a few hundred to a few thousand dollars in the first year; depending on the level of experience and the size of the staff. A typical predictive maintenance system contains four main components: a microprocessor based data collector, a host computer, software and transducers. Each is an important element and it is important that they function well as a total system. Some important characteristics of the integrated system to consider are: User friendly software and hardware. The predictive maintenance program will often be staffed with technicians and engineers that understand the mechanics of machine operation but not necessarily computers. Hardware and software must be designed for simple, straightforward operation. Error correction should be simple, but it should not allow the free form modification of data. Automated data acquisition management and trending. The object of using a microprocessor based data collector and a host computer is to remove the possibility of human error during data input, minimize manpower requirements, and automate as much of the data handling as possible. Flexibility. The system should be capable of collecting, storing and presenting data such as vibration data in a variety of formats (displacement, frequency, velocity, acceleration, cpm) and providing accurate data analysis. The system should accurately accept any commercially available transducer input. Reliability. The hardware and software should have proven field experience. Ask for a users' list and find out strengths or weaknesses from people who have experience with the system. Accuracy. Data must be accurate and repeatable since decisions on equipment condition will be made based on the information that is collected and analyzed. Technical support. Training and technical support is a very important consideration. A properly configured predictive maintenance system should provide valuable information with a minimum level of manpower, and only a limited knowledge of the theory behind the predictive maintenance techniques used. Each system will, however, require some training in the basics of data base development and diagnostics. Report generation. Maximum flexibility in format and content is important and the system should be able to generate reports at several levels of detail. Examples of the types of reports the system should be able to produce are: Exception report. This report consists of listing equipment that have exceeded one or more alarm or alert limits, missing data points, notepad observations, or equipment with a predicted failure before the next scheduled measurement date. Last measurement report. This report is a listing of components, notepad observations, project failure time, and missed measurement points. The report would include information shown on the exception report and a complete review of all equipment. A machine history report recapping total equipment history including all components. If the system does not automatically generate these reports the manpower requirements can increase substantially. If a limiting factor is staff levels or experience; or if the cost-benefit analysis is inconclusive, a pilot program may be the best solution. Equipment vendors will help establish a program and phase out their support as the in-house staff becomes proficient. This option allows the development of financial benefits, provides hands-on training for the in-house staff, and develops a data base. Another option is to contract with an outside company to run the program. With this option, the need for additional in-house staff is eliminated, as is the need for an investment in data acquisition and analysis equipment. One should avoid vendors who quote fixed price per measurement point regardless of the type of equipment. Because of the type of equipment being measured complexity of the measurements will vary and also their cost. A price based on equipment type (motors, pumps vs turbines, generators) should be requested. There are numerous techniques available for implementing a Predictive Maintenance Program. Techniques that may be found in various predictive maintenance programs include: Vibration analysis which is performed on mechanical equipment to evaluate the online condition of its mechanical parts, and effect on related pieces of equipment. Effectiveness of vibration mounts, shafts, bearings, coupling alignment and impeller balance are measured and monitored to determine if equipment is functioning properly and within specifications. Ferrography Analysis, a wear particle analysis being diagnostic and predictive techniques to evaluate the on-line condition of interacting lubricated or fluid powered parts. Lubricants or fluids are analyzed for condition, level and type of contamination. A wide array of problems with equipment, the lubricants/fluids and maintenance methods can be determined by use of ferrography. Utilization of oil analysis has and will continue to expand the existing life of critical equipment. Thermography is used to analyze equipment that exhibits over-heating and heat links when not operating properly. This includes equipment as varied as circuit breaker panels, electronic circuit boards, cryogenic piping, GN2 heaters and many others. Laser Alignment is used to detect misalignment in mechanical equipment components that can lead to accelerated wear or possible catastrophic failure. It is used to verify proper installation and even fabrication of mechanical equipment before operation. It is also used for online monitoring to ensure proper alignment is maintained during equipment operation. Correct alignment will reduce power consumption. Motor Analysis is used to determine the level of degradation in electrical motor circuits, such as individual phase resistance from power bus disconnect through the motor windings, phase to ground resistance, inductance of motor coils and capacitance of each phase to ground. Detecting and correcting phase imbalance saves in power consumption and prevents motor core reduction. Ultrasonics is that technology used to detect hidden flaws in materials, especially metals. This technology has advanced into a completely digital and portable microprocessor-controlled ultrasonic flaw detector. It is safe and faster than using X-Ray technology to detect flaws. Visual inspection where plant or maintenance engineers, on a regular basis, visually inspect each critical system. A comprehensive predictive maintenance program is composed of several techniques which, when combined, can predict most mechanical and electrical problems found in equipment. References Lockheed Space Operations Company Predictive Engineering Technology Program Implementation Plan, 10/94. EG&G Florida, KSC Predictive Maintenance Plan, EGG-4061130, 11/20/92. P/PM Technology Publications (issues from 1986 or present). Maintenance Technology Publications (issues from 1993 to present). | This practice has been used by the Kennedy Space Center Shuttle Processing Contractor and Base Operations Contractor Predictive Maintenance Programs for Ground Support and Facilities Equipment, U. S. Industry (Utility, Manufacturing, Processing, etc.). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/24/2000
878 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter S-Band Uplink Monitoring System |  | During the Space Shuttle launch countdown, various computers and multilogic Command Control Units (CCUs) aboard the Orbiter await data feeds from Control Centers at both Kennedy and Johnson Space Centers. These CCUs activate Orbiter sensors that provide the launch team with vital data such as temperature and pressure readings. In addition to data, voice communications from JSC are transmitted directly to the Orbiter Flight Crew. The S-Band Monitoring System provides verification that these signals arrive at the launch pad error-free. It also provides the means to pinpoint the source of any errors, should they occur. | The S-Band Uplink Monitoring System provides the means to verify the voice and data communications received by the Orbiter while at the launch pad are complete and error-free. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number OPS-18 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Maintainability of the S-Band Uplink Monitoring System is enhanced by providing a means to pinpoint faults should they occur. Reliability is also enhanced by ensuring the communication signals are transmitted as intended. The Goddard Unified S-Band (GUSB) system transmits voice and data signals via free space to two antennas at the launch pad; the Orbiter S-Band Antenna and the Monitor S-Band Antenna on the Fixed Service Structure (FSS). Both antennas receive the same signal. The signal from the Monitor Antenna is retransmitted over an optional link, demodulated at the Orbiter Processing Facility (OPF) and compared to the signal being sent from GUSB (See Figure 1). [D] Figure 1. S-Band Uplink Monitoring System Block Diagram The GUSB voice and data communications are critical, particularly during launch countdown. However, transmissions can be distorted because of a transmission frame error, a discontinuity in Radio Frequency (RF) signal level, or a response to harmonics. Concerns arise about the information reaching the Orbiter: Is it error free? Is it identical to that which was transmitted? The S-Band Uplink Monitor System answers these questions continuously throughout launch countdown. This system detects such problems; furthermore, it provides a frame of reference whereby engineers can troubleshoot and pinpoint the errors to the following areas: The GUSB transmitter The receiver on-board the Orbiter The Orbiter's on-board sensor The monitoring receiver in the OPF This capability enhances the maintainability of the monitoring system, as well as the GUSB transmission system, by providing this pinpointing capability. RF Transmission The GUSB antenna transmits the modulated S-Band signal (2106 or 2041 MHZ, payload dependant) at several levels during the countdown: 10KW, 1KW, 200 W, 16 µW. The Uplink Monitor S-Band Antenna receives the incoming S-Band Signal at the 295-foot level of the FSS. The antenna was designed to be located as close as possible to the Orbiter S-Band Antenna in order to receive the same signal in terms of strength and noise content. The signal is then split at half power between two channels. The channel selected depends on the GUSB signal power. The channels are identical except for their variable attenuator settings. The high power channel has high attenuation so the optical transmitter does not saturate; the low power channel has low attenuation so the signal has considerable strength when it reaches the optical transmitter input. After the signal passes through the directional coupler, the RF amplifier in each channel boosts the signal with a +52dB gain to acquire optimum signal strength through the optical link. This assures an adequate signal strength at the receiver in the OPF after passing through the final directional coupler. Fiber-Optic Link The signal is now transmitted to the OPF through an optical link. The use of fiber over a long distance minimizes both attenuation and noise interference. In addition, electromagnetic interference is non-existent when transmitting over fiber optics. For these reasons, the fiber-optical link covers a sizable distance of the system's total transmission range (up to 8 KM for Pad B). The optical power at the transmitter is set to allow for losses in the optical link and still be above the sensitivity of the optical receiver in the OPF. The number of patch panels and fiber optic connectors are kept to a minimum to minimize losses during the routing of the signal to the OPF. Two fiber optic couplers are used because the system is required to transmit the signal from either launch pad to OPF-1, 2 or OPF-3. The first coupler is a single-mode 2X2 which allows two inputs such as the low-power channels from Pads A and B to transmit to OPF 1, 2 on output 1 and to OPF-3 on output 2. The second coupler is configured similarly, except that the high power channels feed the inputs. The fiber optical receivers in the OPF communications and Tracking Laboratory receive the modulated optical signal. At this point the signal is demodulated off the light wave and coupled to the S-Band receiver in the OPF where it is compared with that coming off an S-band receiver that is monitoring the GUSB. Information is demodulated from the carrier and recorded by a frame-check computer that indicates the bit-error count. It is at this point that engineers can determine if the S-Band signal received at the Orbiter is accurate and detectable. Reference: KSC Drawing 80K54080. | This practice has been used on the Space Shuttle Program. | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 04/24/2000
881 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Fiber Optic Systems |  | Fiber optics can enhance the transmission quality, capacity, and safety environment of the system. The system designer should carefully weight the pros and cons of fiber optics vs. copper, microwave, or satellite for the transmission medium. Optical fiber, if cabled and installed properly, will last for years without any preventive maintenance. Reliability of optical cable is very good, and will enhance system availability, minimize downtime for maintenance, and reduce repair costs. | During new design or upgrades to existing transmission systems, consider the use of fiber optic systems in place of metallic cable systems. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number OPS-08 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Properly designed fiber optic transmission systems will last for long periods of time without any preventive maintenance and can offer reduced maintenance downtime and repair costs. Well-built optical transmission lines and couplers are relatively immune to electromagnetic interference, adverse temperature, and moisture conditions and can be used for underwater cable. An optic fiber can be 20 times lighter and five times smaller than copper wire and still carry far more energy. Using fiber optic control circuits provides electrical isolation for safety in hazardous environments. Because optical cables carry no current they are safe to use in explosive environments and eliminate the hazards of short circuits in metal wires and cables. Components and Operation The basic elements found in fiber optic systems are a transmitter, fiber optic cable, receiver, and connectors. Figure 1 illustrates the main parts of a fiber optic system. The following is a brief description of these elements and their function: The Transmitter converts an electrical signal to a light signal. The transmitter consists of a driver and a source. The input to the driver is the signal from the equipment being served. The driver circuit changes the input signal into a form required to operate the source. The source, either a light-emitting diode (LED) or laser diode, does the actual conversion. The Fiber Optic Cable is the medium for carrying the light signal. The main parts of a fiber cable are the optical fiber, cladding, buffer jacket, buffer, strength members, and jacket. Figure 2 illustrates the main parts of a single fiber cable. The optical fiber contains two concentric layers called the core and the cladding. The inner core is the light-carrying part. The surrounding cladding provides the difference in refractive index that allows total internal reflection of light through the core. The buffer is the plastic coating applied to the cladding. [D] [D] Cable buffers are one of two types, loose or tight. The loose buffer uses a hard plastic tube having an inside diameter several times that of the fiber. One or more fibers lie within the buffer tube. The tube isolates the fiber from the rest of the cable and the mechanical forces acting on it. The buffer becomes the load bearing member. As the cable expands and shrinks with changes in temperature, it does not affect the fiber as much. A fiber has a lower temperature coefficient than most cable elements, meaning that it expands and contracts less. The tight buffer has a plastic directly applied over the fiber coating. This construction provides better crush and impact resistance; however, it does not protect the fiber as well from stresses of temperature variations. Because the plastic expands and contracts at a different rate than the fiber, contractions caused by variations in temperature can result in loss-producing microbends. Tight buffers are more flexible and allow tighter turn radii. Therefore; tight tube buffers are useful for indoor applications where temperature variations are minimal and the capability to make tight turns inside walls is desired. Strength members add mechanical strength to the fiber cable. The most common strength members are Kevlar Aramid yarn, steel, and fiberglass epoxy rods. During and after installation, the strength members handle the tensile stresses applied to the cable so that the fiber is not damaged. Kevlar is most commonly used when individual fibers are placed within their own jackets. Steel and fiberglass members find use in multi-fiber cables. Steel offers better strength than fiberglass, but may not be the best choice for maintaining an all dielectric cable. Steel also attracts lighting, whereas insulation provides protection from the fiber does not. The jacket-like wire insulation provides protection from the effects of abrasion, oil, ozone, acids, alkali, solvents, etc. The choice of jacket material depends on the degree of resistance required for different influences and costs. The Receiver accepts the light signal and converts it back to an electrical signal. The receiver contains a detector, amplifier, and an output section. The amplifier enhances the attenuated signal from the detector. The output section performs many functions such as: separation of the clock and data, pulse reshaping and timing, level shifting to ensure compatibility (TTL, ECL, etc.) and gain control. Connectors and splices, which link the various components of a fiber optic system, are vital to system performance. A connector is defined as a disconnectable device used to connect a fiber to a source, detector, or another fiber. It is designed to be easily connected and disconnected many times. A splice is a device used to connect one fiber to another permanently. Connection by splices and connectors couples light from one component to another with as little loss of optical power as possible. The key to a fiber optic connection is precise alignment of the mated fiber cores (or spots in single-mode fibers) so that nearly all the light is coupled from one fiber across the junction to the other fiber. Contact between the fibers is not required. However, the demands of precise alignment on small fibers create a challenge to the designer of the connector or splice. Maintainability design features that should be addressed in the design for fiber optic systems should provide for fault localization and isolation, modular replacement, and built-in test and check-out capability. Improvements Fiber optics systems offer many benefits. In sensing systems, sensitive electronics can be isolated from shock, vibration, and harsh environments, resulting in more economical packaging. The number of repeaters required for low attenuation cable is less than with conventional systems and for short hauls of less than 10 km, no repeaters are necessary. In the absence of electrical current, the life of a fiber optic system's components equals the useful life of the control system, the light source, and the electronics. Maintenance and repair costs are reduced dramatically. Installation costs of fiber optic cables are lower than metal cables because the shipping and handling costs are about one-fourth and labor costs one-half that of current metal cables. Reference: RADC-TR-88-124, Impact of Fiber Optics on System Reliability and Maintainability, June 1988. RADC-TR-80-322, Failure Rates for Fiber Optic Assemblies, October 1980. AWP, Technician's Guide for Fiber Optics, 1987. | This practice has been used on the Kennedy Space Center Ground Support Systems (e.g., Launch Processing System, Ground Communications System). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/24/2000
879 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Equipment Protection From Liquid Intrusion |  | This technique is included in the Space Shuttle Ground Support Equipment General Design Requirements. Utilization of this technique can help prevent failures to other equipment and unnecessary downtime. | This practice will increase equipment reliability and decrease maintenance by preventing unnecessary repairs to equipment, personnel time loss, and schedule impact due to liquid intrusion. Facilities that contain electrical and electronic equipment (e.g., motor control centers, power supplies, programmable logic controllers, etc.) should be designed with adequate protection from overhead oil or water sources. Oil sources can come from an overhead crane gearbox that may leak and water intrusion from an overhead pipe or valve. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number OPS-17 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Water leaks or ruptures can also spill onto sensitive flight hardware or other equipment. This technique will prevent additional repairs if overhead oil or water leaks occur from facility systems. Most importantly, this technique will decrease the electrical hazard potential to maintenance personnel by restricting the entry of water that can cause short circuits. During hoisting operations, oil can drip onto sensitive flight hardware or other equipment. If a drip pan is used, the pan can catch the oil and it can be inspected to monitor the gearbox for oil loss. Significant oil loss can cause damage to the gearbox assembly. To protect against water intrusion, design facilities with drip pans above electronic equipment as shown in Figure 1. Water sources can come from fluid condensation, firex water, or ruptured fluid lines. [D] Use of this technique could have prevented the loss of air conditioning at the KSC Vehicle Assembly Building, Orbiter Processing Facility, and the Launch Control Center when a water line, located above a main power substation, ruptured and shorted the main buses. This mishap interrupted Shuttle processing and cost considerable resources. Hoists contain gearbox assemblies that are filled with oil for lubrication and gear cooling. Gaskets that seal the gearbox housing parts or shaft seals can deteriorate over time and cause oil to leak out. Startup and vibration can cause bolts that connect the gearbox assembly together to become loose and cause oil to leak out. To capture the oil, pans can be constructed from sheet metal. Metal straps are placed on each end of the pan and loop around the front and rear of the gearbox shown in Figure 2. The oil pan should be deep enough to hold all the oil in the gearbox. However, because of space constraints a shallower pan may be used. The pan area should cover the bottom area of the gearbox. [D] For example, Bridge Buckets, located in each of the Orbiter Processing Facilities, are used by personnel to travel along the length of the Orbiter Cargo Bay for inspections. There are gearbox assemblies at various locations such as the hoisting system and the bridge drive assembly. The bucket hoisting system contains a gearbox assembly on each end of the hoist drum. Each gearbox contains a shallow pan with two straps, one on each end, that loop around the front and rear of the gearbox. This prevents any oil that may drip into the Orbiter Cargo Bay. The 250 Ton Bridge Crane, located in the Vehicle Assembly Building, contains an oil drip pan inside the hook load assembly. This prevents oil that could drip onto Solid Rocket Booster Segments or the Orbiter. Reference: SW-E-0002, Space Shuttle Ground Support Equipment General Design Requirements, section 3.4.3.1.ff | This practice has been used at various KSC Facilites. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/24/2000
880 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | AC - Variable Frequency Drive Systems |  | Variable frequency drive systems are installed at the Shuttle launch pads at KSC. The system allows for a direct coupling between the main propulsion system liquid oxygen pump and drive motor. This eliminates the motor clutch system, a high maintenance item, and gaseous nitrogen lines used to purge the clutch system. | During the design of new or modifications to existing systems requiring motor speed control, consider the use of alternating current (AC) variable frequency drive systems for motor control. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number OPS-07 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. AC variable frequency drive systems for motor speed control offer several advantages over systems that use DC or AC motors coupled with mechanical devices (clutches and pulleys) to achieve motor speed control. These advantages enhance system maintainability resulting in: Improved system maintainability, reliability, and performance. Reduction of preventive and corrective maintenance (manhours and materials) by elimination of mechanical devices. Increased system availability. Self-contained diagnostic test capability. Reduced size and mechanical complexity. Reduced life cycle costs. The use of A/C variable frequency drive systems provides greater efficiency for motor speed control than mechanical devices with DC or AC motors. AC variable frequency drive systems allow for direct coupling and eliminates the need for mechanical devices such as clutches and pulleys. Elimination of these mechanical devices results in decreased maintenance downtime and repair costs. Adjustable speed AC drives also offer many advantages over DC drives because of simplicity, high-speed capability, and low maintenance requirements of induction motors. These motors are suitable for adverse conditions such as dirty air, explosive atmospheres, and inaccessible locations. Components Typically, an adjustable frequency drive system for an AC induction motor will consist of a converter module, DC link module, and inverter module. The following is a description of an adjustable frequency drive system. The configuration shown and the type of control scheme used classify the drive as a current source inverter type. Figure 1 illustrates three fundamental steps used in converting the AC input into a variable AC output. [D] The converter module can be thought of as a programmable DC voltage source where the three AC input lines are rectified by silicon controlled rectifiers (SCR's) to provide a variable DC output. An SCR can be thought of as a controlled rectifier or switch that lets current flow in the forward direction when gated or opened. Then it cannot shut off again until the flow reverses or ceases. At this point the SCR regains its forward blocking capability until gated again. The control circuitry in the drive turns the SCR's on 60 times per second to obtain the desired current flow. Each time a new SCR is gated, it then forces a previous one to shut off. If it is necessary to turn off all the SCR's, all gate signals are removed and the SCR's then turned off naturally when the AC input voltage is reversed. The DC link module is so called because it is a device that connects the inverter and converter modules. Electronically it is an inductor or choke that filters the output of the converter module and provides a more uniform flow of current to the inverter module. Since the inductor tries to maintain a constant flow of current through it, this allows the voltage source converter to function as a current source to the inverter module. The inverter module takes the filtered DC from the DC link module and converts it back to AC. Here the SCR's are gated, one after the other, steering this DC into and out of each of three input lines to the motor. The faster the SCR's are fired, the faster the motor turns. Since the AC line is not present here, external commutating capacitors are used to ensure that each time a new SCR is fired, an old or previously conducting one is shut off. Drive Operation The following paragraphs briefly discuss some of the characteristics of the drive: Output voltage and current normally delivered to a motor from the AC input line are both sinusoidal. This is not true when operating the motor from a current source inverter (see Figure 1). The voltage waveform is closely sinusoidal with disturbances called commutation spikes. The output current is a high quality quasi-square waveform. The current source inverter makes no attempt to define the shape of the output motor voltage. The output voltage is simply a result of the current and rotation of the motor. The shape of the current waveform is defined and its level is increased or decreased to obtain the required voltage. Stated more simply, the control circuitry contains an inner current regulator loop with an outer voltage regulator loop that ensures that the proper current and voltage are supplied to the motor. Crowbar: Since during normal operating conditions the DC link or choke is carrying a large current, which implies a large amount of stored energy, it is worth discussing what happens should the input or output to the drive be suddenly disconnected. The inductor would normally develop whatever voltage is needed to maintain the constant flow of DC. To mitigate the danger of these damaging voltage levels, protective circuits are incorporated within the drive to provide a path for this DC. The protective schemes are based on the capability of both the inverter and converter modules to provide a path for this current by firing two series SCR's in the converter and inverter modules, thus generating a direct short circuit path through which the current trapped in the inductor may flow. The process of firing these SCR's to provide a current path is called quotcrowbar.quot Output clamp: With an abrupt loss of load, the protective mechanism operates as follows. The inverter output leads to the motor are equipped with a device called an quotoutput clamp.quot If the motor is abruptly disconnected, the output current from the inverter will transfer to this clamp circuit until its level hits 950 volts DC. At this point, the control circuitry will force a quotcrowbarquot and shut off the converter module. This prevents any further increase in output voltage; an orderly shutdown is performed. Commutation: Commutation is a process by which an SCR is forced out of a conducting state by reverse biasing. Two types of commutation normally occur in the power circuit, natural and forced. Regeneration: The SCR converter is a two-quadrant device capable of accepting power from the DC bus and returning it to the line when the DC bus potential is negative. This capability makes the current source inverter one of the few inverter types that are inherently regenerative without excessive circuit complication. Low speed cogging: Each commutation in the inverter module causes the current flow to the motor to be abruptly stopped in one phase and started in another. This action forces the motor to turn one-sixth of a rotation on a 2-pole machine, one-half on a 4-pole machine, etc. This explains why, at very low speeds, the motor appears to move in discrete steps rather than smoothly rotate. At a frequency of 1 Hertz, for example, a two-pole machine would perform one complete rotation in six distinct steps at a rate of six steps per second. This effect is reduced depending on the inertia of the connected load. The visual effect completely disappears at speeds above a few Hertz. Reference: KSC Electrical Advanced Schematic Drawing 79K06382. KSC Electrical Advanced Schematic Drawing 79K40029. | This practice has been used on Launch Complex 39A & B, Main Propulsion System, Liquid Oxygen Subsystem. | N/A |  |  | Public | Not Specified |  | 04/24/2000
842 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Common Charge Points for Lubrication Systems for Mechanical Ground Support Equipment |  | Maintenance effort and system downtime will be reduced by the implementation of common charge points for lubrication systems on mechnical ground support equipment. | Use junction boxes and hardlines to provide common charge points for grease lubrication of mechanical systems. | KSC | 11/29/1994 | This Lesson Learned is based on Maintainability Technique number DFE-3 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: This practice reduces the amount of time spent during maintenance by reducing the number of locations to access for grease lubrication. This practice will also eliminate the need to access difficult to reach locations and make maintenance safer by eliminating the need to access hazardous locations. Implementation Method: Required maintenance time is reduced by use of junction boxes and hardlines to lubricate bearing surfaces on mechanical equipment. This practice is most beneficial on large mechanical systems such as bridge cranes. Overhead bridge cranes require periodic lubrication of pivot bearings, wheel bearings, shafts, and other bearing surfaces. This servicing requires the maintenance technician to access a large number of locations on the equipment. The junction boxes are used to create locations from which many bearing surfaces can be lubricated at the same time. This reduces the number of locations that maintenance personnel must access. The junction boxes are machined metal blocks with internal passageways for the grease or oil. There are two banks of hardline connection points along the bottom of the block. The blocks are available in various sizes allowing 2-12 hardlines to be connected. Each hardline that connects to the junction box is coupled to an internal chamber with a double acting piston. A pin indicator on top of each piston controls the volume (.012 - .072 cu. in.) of lubricant delivered and provides positive indication of discharge to each bank. There is a lever at one end of the block which directs the flow of grease from the grease fitting to one of the two banks of hardlines. With the lever in the vertical position, the maintenance technician applies grease through a grease fitting (Figure A). This directs lubricant to the top of the double acting piston in each chamber driving them downward thereby forcing lubricant under each piston to be discharged into the bank one hardlines. This continues until all of the pin indicators are fully retracted. This indicates that the proper volume of lubricant has been applied to each hardline in bank one and bank two and is ready for discharge. [D] Figure A [D] Figure B Rotary Valve Handle Rotary Valve Measuring Pistons Bank 2 Discharge Lines Indicator Stems Bank 1 Discharge Lines Volume Discharge Adjustment Screws The technician then rotates the lever and again applies grease through the grease fitting (Figure B). This applies lubricant under the piston in each chamber driving them upward. Lubricant is forced into each bank two hardline and the chamber is replenished to service bank one. When all the pin indicators are fully extended, the proper volume of grease has been applied to each hardline in bank two. The lever is then returned to the original position, ready for the next lubrication cycle. The primary benefit of this practice is minimizing maintenance time (20 - 40%) by consolidating a large number of locations requiring maintenance action into only a few. This practice further reduces maintenance time by placing the lubrication junction boxes on easy to access locations such as personnel walkways. Placing the lubrication junction boxes on personnel walkways will also reduce safety hazards during maintenance. Some locations requiring lubrication may not only be difficult to access but may be hazardous, requiring special safety equipment such as safety harnesses and temporary work platforms. Special access requirements can be reduced or eliminated by the implementation of the practice. | This practice has been used on Space Transportation System (STS), Facilities and Ground Support Equipment such as the Vehicle Assembly Building (VAB) 325 Ton Bridge Cranes. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
843 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Digital Potentiometers in Electrically Powered Systems |  | Digital potentiometers should be considered in new design or major redesign of electronic systems where comprehensive system control, monitoring, configuration and calibration functions are desired (both locally and remotely). Standard devices (electromechanical potentiometers) are limited to manual control. System analysis will reveal strategic points for the inclusion of digital potentiometers to maximize utilization of their remote capabilities and superior noise characteristics. Substitution of standard variable resistance devices with digital potentiometer based circuits will result in enhanced capabilities while yielding reduced maintenance resource impact. | Enhancement maintainability through the use of digital potentiometers to provide accurate and reliable remote control of electronic hardware. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number DFE-4 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Digital potentiometers are Dual Inline Package (DIP) devices capable of supporting variable resistance functions currently accomplished by standard electromechanical potentiometers. However, they can be equipped to handle a wide spectrum of specialty tasks not technically possible with standard devices. For example; remote process control, remote calibration, analog to digital conversions, digital to analog conversions, variable gain amplification and variable oscillation. Implementation Method: Digital potentiometers should be installed in electronic systems as a replacement for standard potentiometers. However, designs should be enhanced to utilize the digital potentiometers' extended functionality. Digital potentiometers are suitable in both facility power and battery driven applications. These devices should be appropriately selected to match system operating parameters and affixed to printed circuit cards as necessary. In contrast to standard potentiometers, digital potentiometers are remotely accessible and can be driven to specific resistance values directly via a 17 bit serial shift register. An application diagram is attached which illustrates a generic implementation methodology. [D] The digital potentiometer, although not an infinitely variable device, has either 64 or 256 resistive increments (based on model). In the event that finer control is necessary, digital potentiometers can be cascaded to provide high resolution trim functions. The digital potentiometers' architecture is designed to simulate that of a standard variable resistance device. Three pinpoints provide signal in, signal out and wiper. However, unlike discrete devices, wiper position can be incrementally changed or directly accessed through inputting desired position into the onboard register. Upon power loss, latest wiper position is saved in nonvolatile memory. As an added improvement over discrete devices, noise has been minimized such that signal to noise ratios are greater than or equal to 120db. Installation of digital potentiometers will provide accurate and reliable remote control of electronic hardware. Digital potentiometers will provide cost savings in the following key areas: Reduced equipment downtime (standard Potentiometers are prone to failures/instability due to contamination). Reduced maintenance and calibration costs on equipment due to superior resistance to drift, remote configuration capability, and remote reporting not available in standard devices. Provides preventive maintenance function and reduces corrective maintenance costs as digital potentiometers do not typically require replacement and can be remotely monitored and configured. Additionally, performance of low level signal processing devices will be greatly enhanced due to superior signal/noise ratios. References: quotDon't Touch That Dialquot; An Overview of Digital Potentiometers and Applications by Dallas Semiconductor Corporation. | Although these devices are not currently in use at Kennedy Space Center (KSC), they represent emerging new technologies with known implementation in commercial industry that are applicable to aerospace systems. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
841 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Availability Prediction and Analysis |  | Availability estimation is a valuable design aid and assessment tool for any system whose operating profile allows for repair of failed units or components. These systems include those that operate on earth such as control centers, system test facilities, or flight simulation systems/facilities. Applying availability prediction and analysis techniques is also an extremely valuable process for guiding the development of maintenance concepts and requirements. | Estimate or predict the future availability of a system, function, or unit where availability is defined as the probability that the system, function, or unit will be in an operable state at a random time. Availability may be assessed for a single component, a repairable unit, a replaceable unit, a system of many replaceable units, or a function performed by multiple systems. | JSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number AT-3 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Availability prediction and assessment methods can provide quantitative performance measures that may be used in assessing a given design or to compare system alternatives to reduce life cycle costs. This technique increases the probability of mission success by ensuring operational readiness. Analyses based on availability predictions will help assess design options and can lead to definition of maintenance support concepts that will increase future system availability, anticipate logistics and maintenance resource needs, and provide long term savings in operations and maintenance costs based on optimization of logistics support. Implementation Method: Availability can be predicted or estimated using various methods and measures. Availability is a characteristic of repairable or restorable items or systems, and assumes that a failed item can be restored to operation through maintenance, reconfiguration, or reset. It is a function of how often a unit fails (reliability) and how fast the unit can be restored after failure (maintainability). A foundation to support both the establishment of reliability and maintainability (R&M) parameters and trade-offs between these parameters is created by availability prediction before analyses. Availability can be estimated for components, items, or units, but overall spacecraft system or ground system availability estimation is based on the combinations and connectivity of the units within the system that perform the functions, i.e., the series and redundant operations paths. Availability Measures One basic measure of availability, called inherent availability, is useful during the design process to assess design characteristics. The measure involves only the as-designed reliability and maintainability characteristics and can be calculated using the estimated mean-time-between-failure (MTBF) and mean-time-to repair (MTTR) parameters. The predicted or estimated measure of inherent availability is calculated as: [D] The MTTR time in the inherent availability calculation does not include such times as administrative or logistic delay time, which generally are beyond the control of the designer, and does not include preventive maintenance time. However, effective trade-offs using the basic times and parameters are possible. Trade-off techniques and some sample uses are included in Reference 1, Section 5.5. Another measure of availability, achieved availability or Aa, can be expressed as: [D] where OT is the total time spent in an operating state, TCM is the total corrective maintenance time that does not include before-and-after maintenance checks, supply, or administrative waiting periods; and TPM is the total time spent performing preventive maintenance. Aa is more specifically directed toward the hardware characteristics than the operational availability measure, which considers the operating and logistics policies. A third basic measure of availability, operational availability, considers all repair time: corrective and preventive maintenance time, administrative delay time, and logistic support time. This is a more realistic definition of availability in terms providing a measure to assess alternative maintenance and logistics support concepts associated with the operation of a system or function. It is usually defined by the equation: [D] where Uptime is the total time a system is in an operable state, and Downtime is the total time the system is in an inoperable state. The sum of Uptime and Downtime, or Total Time, is usually known, specified as a requisite operating time, or is a given time to perform a critical function. Downtime often is broken down into a variety of subcategories such as detection and diagnosis time, time waiting for repair parts, actual unit repair or replacement time, test and checkout time, etc. Table 1 shows the basic difference between the availability measures defined above. [D] Table 1: Commonly Used Availability Measures System or Function Availability Estimation System/function availability estimates may be derived in a limited fashion by algebraically combining mean value estimates of the system units, or more rigorously by using computer- aided simulation methods. Mean Value Estimation Mean value estimation of system availability is usually performed by algebraically combining component, LRU, and ORU availabilities calculated using equation (1). When the system is composed of a number of components, LRU's, or ORU's, the failure of any one of which results in the system being down, the system availability is calculated from the product of these units' availability. When the system involves item redundancy, redundant block availability estimates can be calculated using simple Boolean mathematical decomposition procedures similar to reliability block diagram solution methods. See Reference 1, Section 10.4. Computer-Aided Simulation Availability prediction using computer-aided simulation modeling may use either a stochastic simulation or a Markov model approach. Stochastic simulation modeling uses statistical distributions for the system's reliability, maintainability, and other maintenance and delay time parameters. These distributions are used as mathematical models for estimating individual failure and restoration times and can include failure effects and other operational conditions. A computer program generates random draws from these distributions to simulate when the system is up and down, maintains tables of failures, repairs, failure effects, etc., and tracks system or function capability over time. These data may then be used to calculate and output system operational availability estimates using equation (2). Stochastic Simulation Methods Discrete event stochastic simulation programs are recommended to perform operational availability predictions and analyses for large, repairable systems such as the space station or large ground systems and facilities. These methods simulate and monitor the availability status of defined systems or functions that are composed of a collection of Replaceable Units (RUs). The following process is generally used: Generate simulated future failure times for each designated RU based on predicted RU reliability distributions and parameters. Step through simulated operating time, and when failure events are encountered, evaluate the failure impact or function status given the specific failures encountered. Repair or replace the failed RU using a maintenance policy and procedure based on the availability of required maintenance resources, priority or criticality of the failure, or the current system or function status. Once an RU is repaired or replaced, the system or function status is reset appropriately, and a future failure time for the RU is again generated. Generation of simulated failures and maintenance actions for RUs requires as input the estimated RU time-to-failure distribution model parameters and factors that define the frequency of other scheduled or unscheduled maintenance. The maintenance actions can include equipment failures, preventive maintenance tasks, and environmentally or human-induced failures. To evaluate the effect of a simulated failure on the function's operational capability at a particular point in time, minimal cut sets of failure events that define the system or function failure conditions can be used. Minimal cut sets of failure events can be generated from reliability block diagrams or fault tree analysis of the functions, and then used during a simulation run to dynamically determine queuing priorities based upon functional criticality and the current level of remaining redundancy after the simulated failure occurs. Maintenance is simulated by allocating available maintenance resources and spare parts to the awaiting maintenance action (or waiting for resources to become available). Groups of maintenance actions may also be packaged into shifts of work. If the system under consideration is in a space environment, both external (extravehicular activity or EVA) or internal (intravehicular activity or IVA) can be considered. When the stochastic simulation method is used, each run of the simulation model (called an iteration) will yield a single value of the availability measure that depends on the chance component or unit failures and repairs that happened during that iteration. Therefore, many iterations are required to cover as many potential failure situations as possible, and to give the analyst a better understanding of the variation in the resulting availability as a function of the variations in the random failure and repair process. The number of iterations required for accurate availability measure results will depend on the iteration to iteration variation in the output measure. Experience has shown that in system availability simulations with a large iteration-o-iteration variation, 200 to 1000 iterations or more may be required to obtain a statistically accurate estimate of the average system availability. For example, the Reliability and Maintainability Assessment Tool (RMAT) is a stochastic computer-aided simulation method like that described that has been used at Johnson Space Center for assessing the maintainability and availability characteristics of the Space Station. The output of the RMAT includes the percent of total (or specified mission) time each defined space station function spends in a quotdownquot state as well as the percent of time each defined function is one failure away from functional outage (is zero failure tolerant). Using RMAT, analysts at JSC have been able to perform trade studies that quantify the differences between alternative Space Station configurations in terms of their respective operational availability and maintainability measure estimates. The same simulation methods (such as RMAT) that provide for operational availability measures will also provide maintenance resource usage measures such as maintenance manpower needs and spare part requirements. With this capability, JSC has been able to estimate the maintenance manpower needs, including EVA requirements, of various Space Station alternative configurations. Markov Model Approach A Markov process, or state-space analysis is a mathematical tool particularly well suited to computer simulation of the availability of complex systems when the necessary assumptions are valid. This analysis technique also is well adapted to use in conjunction with Fault Tree Analysis or Reliability Block Diagram Analysis (RBDA). Examples of the use of Markov process analysis may be found in Reference 1 or in such standard reliability textbooks as Reference 2. Failure to use availability predictions and analysis during the design process may lead to costly sub-optimization of the as-designed system reliability and maintainability characteristics. Where operations and support costs are a major portion of the life cycle costs, availability prediction and analysis are critical to understanding the impact of insufficiently defined maintenance resources (personnel, spare parts, test equipment, facilities, etc.), and maintenance concepts on overall system operational availability and mission success probabilities. These analyses can therefore greatly reduce the life cycle costs associated with deploying and supporting a space or ground system. References: MIL-HDBK-338; Electronic Reliability Design Handbook, Reliability Analysis Center, Rome, NY, 1989. O'Connor, P.D.T.; Practical Reliability Engineering, John Wiley & Sons Ltd., Chichester, 1991. | This practice has been used on the International Space Station Program. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
844 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Ground Piping Systems Color Coding and Identification |  | Color coding of the piping systems provides accurate and immediate visual and written identification of the contents within the pipe. This will provide greater safety and lessen the chances of confusion when working within an area with numerous piping systems. The markings on the outside of the pipe show content in color code, the flow direction, pressures and name of contents (See Figure 1). | Use color coding and identification on piping systems to identify the content and pressure of the contents. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number DFE-5 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Easy and ready identification of piping systems contents. Such identification can aid in: Reduced time in researching a particular system location that is to be modified. Knowing the system that is to be modified, visual identification of that system eliminates a large amount of research time reviewing the pipe location drawings. Safely traversing an area knowing which systems can be dangerous to physical contact. Examples of such systems are high temperature steam lines, low temperature LOX and LH2 lines. Tracing systems in search of leaks or in search of a shutoff valve to stop a leak. Locating a fire box in case of fire (all fire lines are painted red). Each example has beneficial aspects from saving time to saving lives and equipment. Implementation Method: This practice establishes, defines, and assigns a color for recognition to each of six classes of material. Five classes represent universally recognized types of hazards involved in the handling of dangerous gases/liquids. A sixth is assigned for exclusive use of fire protection for materials and equipment. The practice requires the application of color warnings in a distinctive manner, as a visual aid and supplement to written identification. Further details can be found in KSC-STD-SF-0004B. This practice is not applicable to electrical conduits, ventilation units, or pipelines installed in missiles, spacecraft airborne equipment, or storage vessels. Identification methods for bulk petroleum product system is covered in MIL-STD-161. The identification of pipelines for aircraft, missiles, and space vehicles is covered in MIL-STD-1247, and color coding for containers of liquid propellants is covered in MIL-STD-172. Piping systems are described as any pipe line used to transport gases, liquids or semiliquids, but not those for carrying solids in gas or air. Valves, fittings, operating accessories, pipe coverings and tie-in points at storage facilities are considered piping systems. Piping identification is broken down into 4 types of markings on the outside of the pipe. The primary set of markings identifies the content which is shown by a color band taped around the pipe. All contents are broken down into 8 colors. The colors used conform to requirements identified in Federal Standard No. 595, Colors and are: Yellow, No. 13655 - Flammable Materials known ordinarily as flammables or combustibles. Brown, No. 10080 - Toxic and Poisonous Materials. All materials extremely hazardous to life or health under normal conditions as toxics or poisons. Blue, No. 15102 - Anesthetics and Harmful Materials. All materials productive of anesthetic vapors and all liquid chemicals and compounds hazardous to life and property but not normally productive of dangerous quantities of fumes or vapors. Green, No. 14110 - Oxidizing Materials which readily furnish oxygen for combustion and fire producers which react explosively or with the evolution of heat in contact with many other materials. Gray, No. 16187 - Physically Dangerous Materials. All materials, not dangerous in themselves, which are asphyxiating in confined areas or which are generally handled in a dangerous physical state of pressure or temperature. Red, No. 11105 - Fire Protection Materials. All materials provided in piping systems or in compressed gas cylinders exclusively for use in fire protection. Black, No. 17038 and White, No. 17875. These colors are assigned for general use where specified in KSC-STD-SF-0004B, Safety Standard for Ground Piping Systems Color Coding and Identification except as follows. Water Piping Systems containing water suitable for human consumption and installed for this purpose shall be painted white, No. 17875 throughout or shall be painted to match surroundings when not in conflict with color designations in referenced standard. The second set of markings is shown as the color used in the flow arrow which is taped to the outside of the pipe. The secondary color marking is used to identify a second characteristic associated with the content. If a second characteristic does not exist, the flow arrow is black and white. The flow arrow indicates the direction of flow, if the content can flow in either direction a double headed arrow is shown. The third set of markings is the title. The title identifies the contents by name or recognized abbreviations. The titles may be taped, glued or stenciled onto the sides of the pipe. The fourth set is the pressure rating which is shown by a numerical number taped on the outside of the pipe. The pressure will be given immediately below the title using the same sizes and color. Piping systems may not need a pressure rating shown if it is below 60 psig. [D] Figure 1. Piping Systems, Color Warnings References: KSC-STD-SF-0004B MIL-STD-161 MIL-STD-1247 MIL-STD-172 FED-STD-595 | This practice applies to all Ground Based Piping Systems installed in areas under the jurisdiction of KSC, including the systems located in floor trenches and above suspended ceilings. Sections of piping that are concealed underground, in floor slabs, or in walls or partitions are not subject to the requirements of this practice. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
846 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Wear Particle Analysis Using Ferrography |  | Ferrography is a wear particle analysis utilizing diagnostic and predictive techniques to evaluate the on-line condition of interacting lubricated or fluid powered parts or components. The use of Ferrography to evaluate a system's condition is to avoid time-consuming and potentially damaging hardware teardown and other destructive or interfering inspections. Ferrography can analyze a system's fluid to determine the type of wear it is experiencing; and, hence, predict the type of system failure and when the failure may occur. Ferrography can provide an established and easily performed inspection method for determining the health of a system and providing an early failure detection method. | Use Ferrography to diagnose equipment problems and predict equipment failure before it occurs. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number AT-6 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Ferrography provides early detection of abnormal wear of the lubricated critical internal components of mechanical systems. Analyzes the debris in system lubricants. Shows particle size, shape and color as well as quantity. Reveals which system component is wearing, and to what degree, and pinpoints the cause of the wear. Implementation Method: Ferrography is a very useful and comprehensive analysis for trending and reporting. At a minimum, the user can obtain an analytical means of monitoring the wear condition; and, at the same time, accrue the necessary sample points required to establish a wear particle concentration baseline and retain the presence of non-magnetic particles for visual inspection and evaluation. The advantage of Ferrography over other preventive maintenance systems is its capacity to detect a broader range of types and sizes (0.1-500 microns) of wear particles. A micron is one millionth of a meter. Ferrographic analysis encompasses wear (metallic and non-metallic), contaminant (crystals, water, and organic and inorganic compounds), and lubricant (friction polymers) monitoring. Typical wear problems identified by Ferrography; gear teeth wear through excessive load or speed, misalignments, fractures, rolling contact failure, water in the oil or poor lubricant condition, oil additive depletion, outside contaminants such as sand or dust, cam shaft and cylinder wall failure, oil filter failure. There are many others. Industrial application of Ferrography entails the non-interruptive machine condition monitoring of heavily used lubricated mechanical systems. Hence, an operational baseline can easily be established by sampling every 50-500 hours of operation (approximately every one to three months, depending on system criticality), and used for quantitative trending analysis. Any anomalies in the wear particle concentration, especially in the generation rate of large particles (>20 microns), is symptomatic of the onset of failure. For consistent results and accurate trending, lubricant samples are taken from the same places in the system each time. The method of sample extraction assures that the lubricant samples contain a representative selection of wear particles. The samples are then ferrographically analyzed both quantitatively and qualitatively. The Direct Reading Ferrograph (DRIII) classifies metallic wear particles as either large (>20 microns) or small (<20 microns) and calculates the large to small wear concentration. These values are entered into the personal computer based Ferrotrend database, which compiles the data points for wear trending analysis. This process determines the existence of a malfunctioning component in the system. The Dual Ferrograph Analyzer prepares the ferrogram (slide) for analysis through the Ferroscope IV Microscope. The qualitative analysis is documented in the Ferrogram Analysis Report Sheet which documents the severity concentration of specific normal and abnormal wear particles. The ferromagnetic particles are sorted by gravity according to relative size, with larger particles appearing at the leading entry of the ferrogram. Non-magnetic particles (including contaminants and friction polymers) are distributed throughout the ferrogram. This process indicates the presence of contaminants, the condition of the lubricant, and the material composition of the abnormal wear particles being generated, from which the source of the wear may be deduced. Ferrography is just one of the methods used at KSC. Ferrographic, viscosity, total acid number and vibration analysis are cooperative elements of the predictive maintenance program. [D] References: GSE Health Trend Analysis - RT-ENG-2/ 90-218 P/PM Technology - March/April - 1991 Standard Oil Engineered Materials -Technical Bulletin 101 Predictive Maintenance Engineering Lab, USA/KSC. | This practice has been used on KSC Payload Facility Crane Gear Reducers. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
845 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Vibration Analysis of Rotating Ground Support Machinery |  | Predictive maintenance is a condition driven preventive maintenance program. Instead of relying on industrial average-life statistics to schedule maintenance activities, predictive maintenance uses direct monitoring of the mechanical condition, system efficiency, and other indicators to determine the most efficient time to service a piece of machinery. Since mechanical systems or machines account for the majority of equipment, vibration monitoring is generally the key component of most predictive maintenance programs because it can provide the greatest benefits. Also, equipment down time is not required for vibration analysis to occur. | Use the noise or vibration created by mechanical equipment to determine the actual condition of the equipment. Vibration analysis can be used as a nondestructive method for detecting incipient problems in rotating machinery such as imbalance, misalignment, and damaged or worn components and thereby prevent catastrophic failures from occurring. Vibration analysis also can be used for determining what maintenance actions are necessary for a piece of rotating machinery and the frequency of those actions. | KSC | 12/01/1994 | This Lesson Learned is based on Maintainability Technique number AT-8 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Vibration analysis allows the maximum interval between repairs to be realized through monitoring the actual mechanical condition of a piece of rotating machinery. Equipment down time is not required for monitoring activities to occur. The monitoring, in turn, directly minimizes the number and cost of unscheduled machine outages created by component failures. Hence, optimum equipment availability may be obtained. Implementation Method: Vibration Analysis is predicated on two basic facts: All common failure modes have distinct vibration frequency components that can be isolated and identified. The amplitude of each distinct vibration component will remain constant unless there is a change in the operating dynamics of the machinery. Monitoring the vibration from machinery can provide a direct correlation between the mechanical condition and recorded vibration data of each machine. Vibration analysis can be used to identify specific degrading machine components or failure modes of machinery before serious damage occurs. Typically, 80% of the machinery problems experienced can often be classified as either imbalance or misalignment. Imbalance and misalignment can lead to premature bearing, coupling, shaft seal, and gear wear. Most of the problems can be rectified by simply improving maintenance standards and procedures and by eliminating careless or sloppy work. Also, imbalance and misalignment do not only occur in established equipment over a period of time, they can be present after initial installation of a new piece of machinery. Vibration analysis can be used to validate that the new equipment has been properly installed. This would prevent the introduction of failure causes which would have a detrimental effect on the life of the equipment and the process which the equipment supports. Recent advancements in microprocessor technology and the development of PC based software have simplified data acquisition, automated data management, and minimized the need to have professional vibration consultants available to interpret the data. Commercially available systems are capable of routinely monitoring, trending, evaluating, and reporting the mechanical condition of all mechanical equipment. Vibration analysis was started in 1988 by the Shuttle Processing Contractor (SPC) in an effort to reduce the high failure rates experienced by the rotating machinery associated with Environmental Control System (ECS) located in the Orbiter Processing Facility (OPF) at the Kennedy Space Center (KSC). The vibration analysis program initially monitored 66 pieces of equipment associated with the ECS and the Orbiter Portable Purge Units used at the OPF and the two launch pads of Launch Complex 39. The information gathered was used to effectively reduce the failure rate and down time of the ECS equipment. Because of the success achieved with the ECS equipment, the SPC expanded the vibration analysis program to include all other Space Shuttle Program ground system equipment for which it had maintenance responsibility at KSC. The equipment considered was machine-train components. Machine-train components consist of a primary driver or drivers (i.e., electric motor, turbine), all intermediate drives (i.e., couplings, belts, gear box), and all driven machine components (i.e., fans, pumps, drums). All the SPC equipment was assessed. A list of equipment that would lend itself to vibration analysis was created. Due to the number of items identified, the SPC categorized the equipment into a priority listing of equipment that would be of benefit to the Space Shuttle Program. Once the equipment to be monitored was identified, a process was established to routinely obtain vibration data from specific locations on the equipment. Preparation for data collection involved determining what type of data equipment was necessary, what type of data to collect, where to take the measurements (i.e., shaft, bearing, housing, mount, coupling, gears, or fan), how many degrees of freedom for each component were to be measured (i.e., x-axis, y-axis, z-axis, radial), and should the measurement devices be of a permanent or temporary type attachment. All of the data is collected via a portable handheld microprocessor-based instrument. This removes the potential for human error, reduces manpower requirements, and automates the acquisition of vibration data. Due to the massive amount of data that is collected, a reliable PC based automated data management system was selected that enables the vibration data to be stored, trended, and recalled for use in developing long-term trends. It is important to note that the bearings in a machine-train are the primary limiting factor for operating life. The first indication of machinery problems often develops in the vibration signature of the machine's bearings. However, the bearings are typically not the cause of the problem. But since they are the weakest link in most machinery, the bearings are usually the first to fail. Vibration checks at points other than the bearings are also taken to check for structural problems. Experience has proven that on new or refurbished equipment, vibration data should be collected once a week for four consecutive weeks. This will enable a trend to be established for future comparison. The frequency of monitoring a piece of equipment after establishing an initial baseline is based on the following considerations: The machine's operating modes (i.e., intermittent or continuous speeds/loads). The machine's operating environment. The importance of the machine's function. Data derived from comparison of the initial baseline. Availability of spare parts. To regularly acquire enough data for complete diagnosis of a machine's potential failure would be "overkill" and unduly burden the data collection process. The periodic collection of vibration data on a prescribed route for trending purposes should be treated as a tool to indicate pending problems. Industry standards are utilized to determine a problem condition unless specific pieces of equipment dictate more stringent or lax alarm limits. Once a possible problem is identified, more data is collected from the equipment in order to aid the vibration analyst in determining the exact cause of the anomaly. In order to resolve the anomaly in an efficient manner, "if" and "what type" of information is needed. The questions asked are: What is the problem? What is the machine's history? What has the operator observed? When did the problem start? Was it sudden or gradual? Did the machine ever run properly? Have any changes been made recently? Modifications? Realignments? Changes in machine speed? Other NASA centers utilize vibration analysis for their own purposes as shown by Reference 4. References: Lockheed Space Operations Company Predictive Engineering Technology Program Implementation Plan. Mobley, R. Keith: "An Introduction to Predictive Maintenance," Van Nostrand Reinhold, 1990. P/PM Technology, Volume 5, Issue 3 -May/ June 1992. "Absolute Ball Bearing Wear Measurements From SSME Turbopump Dynamic Signals," by J. M. Hine. Proceedings of the 59th Shock and Vibration Symposium, Volume III, pp. 45- 55, October 1988. | This practice has been used on the following KSC equipment. Cooling Fans for 2000 KW Generators on the Crawler/Transporter. Environmental Control System at the Orbiter Processing Facility and the launch pads of Launch Complex 39. Liquid Oxygen Pumps at the launch pads of Launch Complex 39. Orbiter Dock Seal Blowers at the Payload Changeout Room on the launch pads of Launch Complex 39. Payload Bay Area Access Bridge/Bucket at the Orbiter Processing Facility | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
848 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Maintenance & Test Criteria for Circuit Breakers |  | While this practice may seem to be one that would routinely be found in a maintenance program, in reality that's not so. All too often it is assumed that a new part is not only serviceable, but that it also meets the specification requirements as advertised. However, due to process variables, inspection techniques, and even fraud, this is not always the case. Example: in February 1992 KSC was alerted by NASA HQ/Code QR that the Nuclear Regulatory Commission working with the Inspector General was issuing a GIDEP/Alert on suspect circuit breakers. The situation described that a particular vendor took used circuit breakers from various manufacturers, refurbished the exterior only, falsified circuit breaker data and sold them as new components. These breakers had experienced premature trip, failure to trip (some breakers were not of proper amperage, i.e., mislabeled), and some had exploded. Had KSC not had practice GP-1002, quotMaintenance and Test Criteria for Circuit Breakers,quot in place, suspect circuit breakers could have easily been introduced into KSC's GSE and Facility equipment supporting the Space Shuttle Program. A maintenance program that provides for testing of circuit breakers prior to or upon installation will eliminate these types of failures. | Enhance the Ground Support Equipment (GSE) and Facility Equipment Maintenance Program by adoption of a maintenance practice that provides maintenance and test criteria for electrical circuit breakers. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number AT-7 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Proper maintenance and testing of electrical circuit breakers will enhance system/equipment performance, reliability, and overall availability. Cost savings are realized through testing of circuit breakers prior to or during installation by eliminating damage to other equipment/components caused by defective circuit breakers. Testing will also alert maintenance and logistics to examine existing inventories for other defective circuit breakers. Proper maintenance of circuit breakers will enhance circuit breaker life expectancy as well as the system/equipment it supports. Downtime for unscheduled maintenance is also minimized through proper maintenance and testing of circuit breakers. Implementation Method: In developing a maintenance practice for circuit breakers one should first identify what type of circuit breakers are used (examples; molded-case, draw-out, high-voltage, etc.). Once the circuit breaker types are identified, one can start to identify the criterion for circuit breaker inspection, test, and maintenance. There are many sources of information available to assist one in defining this criterion (example: Federal & Military Specifications/Standards, Air Force Manuals/Regulations, American National Standards Institute (ANSI), National Electrical Manufacturers' Association (NEMA), etc.). The practice should address safety. Safety should be a prime consideration to all concerned in the planning, scheduling, and accomplishment of the work. Supervisors should brief all personnel, prior to the start of each operation, concerning the hazards that may be encountered and the appropriate safety practices to be observed. Supervisors should ensure that only properly trained and qualified personnel participate and that all personnel are equipped with the tools and equipment necessary to do the job safety. Specific safety hazards that may be encountered while working with circuit breakers should be identified. For example; electric shock and secondary injuries caused by contact with energized circuits or devices that are electrostatically charged after removal of test potential. Also physical damage resulting from short circuits, insulation failures, or faulty equipment. Identification of safety equipment that is required when working on circuit breakers should be provided. This equipment may consist of nonmetallic hardhats with chin straps, safety goggles, rubber gloves, sleeves, blankets/mats as required, area barricades and signs. Safety precautions that personnel should be aware of should be identified. For example; turn off power, look out, and disconnect sources of electrical energy before working on equipment. Use of insulated hand tools designed for specific work. Use of protective equipment such as safety approved rubber-insulated gloves with protectors, insulating blankets/mats, and non-metallic hardhats. Wear safety eye protection glasses if there is a possibility of arcing or sparking. Ensure that non-current carrying metallic parts of equipment are grounded. Inspect visually or conduct tests to determine the adequacy of grounds. The following is extracted from KSC GP-1002 and illustrates how that practice addressed one of the types of circuit breakers found at KSC. Molded-Case Circuit Breakers Application. Molded-case circuit breakers are used to interrupt fault currents, to provide overload protection, and to switch the electrical circuit. Construction. Molded-case circuit breakers contain two elements: a switch consisting of a set of contacts with suitable mechanical linkage to operate the contacts; and a trip unit which is an overload and fault sensing device. Operation. When the thermal or magnetic trip senses an overload condition in the electrical circuits, a spring-loaded latch is tripped. The released spring mechanism rapidly opens the breaker contacts and de-energizes the faulted circuit. Most molded-case circuit breakers are equipped with a thermal element composed of a bimetallic strip to provide a time delay and establish the tripping characteristics. The instantaneous-trip device is magnetic. High current flow through the breaker picks up the armature of the magnetic trip device. Movement of the armature releases the latch and opens the breaker contacts. Some breakers are available with an adjustable instantaneous trip. The pickup of this trip may be changed in the field from approximately 5 to 10 times the continuous rating of the breaker. Breakers labeled quotnon-automatic' have no trip unit and are used as load interrupting switches only. Maintenance. (1) Preventive Maintenance. Circuit breakers shall be exercised at intervals recommended in Table 1. If the circuit breaker is equipped with a trip indicator, exercise it to verify that it also operates properly. During routine maintenance, check molded-case circuit breakers for improper terminal connection at the time of installation, distorted plug-in tabs or sockets, poorly cleaned or corroded conductors, improper conductors for the lugs in use, and loose terminations. All of the above are fault conditions which may cause heating and deterioration of the circuit breaker and its response characteristics. [D] Table 1. Recommended Maintenance/Test Intervals for Molded-Case Circuit Breakers Note: The above are minimum recommended maintenance/test intervals. Additional tests may be made when the operating agency has experience to indicate need for concern. If overheating of connections is evident through discoloration or arcing, the breaker should be removed from service and all conducting surfaces cleaned. The breaker should then pass operations tests and the installation megger test before reinstallation. Those breakers with adjustable instantaneous magnetic trip devices should be set at the highest setting unless otherwise directed. (2) Corrective Maintenance. Perform corrective maintenance on molded-case circuit breakers after fault conditions occur. Follow the procedures given in paragraph 4.(1) and perform the tests required in Table 1 (see paragraph 5). If a molded-case circuit breaker interrupts a fault current whose magnitude is equal to its interrupting rating, the breaker may not be operable. Tests. (1) Insulation Megger Tests. Perform insulation megger tests at the intervals indicated in Table 1 and the following instructions. De-energize and, if necessary, remove the breaker from the panel for test. Do not place the megger on large masses of iron nor near strong magnetic fields. Set the megger scale range selector switch in a position that gives a reading in midscale or above. Observe megger readings after a minimum of one minute or when the pointer has reached an apparent stabilized value; record the readings. After completion of the test, apply temporary grounds to all test materials and disconnect all leads. This procedure tests one phase to ground with all other phases grounded and is equivalent to a phase-to-phase test besides the phase-to-ground test. Each phase must be tested individually. Table 2 provides voltage values for insulation megger tests. If a megger reading of 1 megohm minimum is not obtained for each voltage value replace the circuit breaker. [D] Table 2. Voltage Values for Insulation Megger Tests-Molded-Case Circuit Breakers (2) Operations Tests. Perform operations tests at the intervals suggested in Table 1 and with the following instructions. These tests include overcurrent testing for both time-delay and instantaneous trip. Molded-case circuit breakers use two basic methods, sometimes combined, to achieve overload protection: thermallic strip and electromagnetic. Check the circuit breaker manufacturer's instruction book to determine the type of overload device, the method of adjustment, and the proper breaker connections. Use a low-voltage high-current source such as Multi-Amp Model MSA for small breakers of ratings up to 100A and Multi-AMP Model CB-225 for larger breakers. Consult the Multi-Amp Tester instruction book to set up tester controls. De-energize and remove the breaker from the panel for test. Record all data obtained by these tests. Individually test each pole that is equipped with an overload device. Operate (open and close) the breaker two or three times before applying the overcurrent. Connect the Multi-Amp tester across one pole of the breaker with the breaker closed. If the overload protective device of the breaker under test is the thermal bimetallic strip type, allow sufficient time for the heater element to cool to near ambient temperature before starting a second test. No waiting period between tests is necessary for the electromagnetic type of overload protective device. (3) Time Current Trip Test. If the breaker is electrically operated, connect temporary power to the breaker control circuits. Check for proper voltage and if alternating or direct current. The tests currents provided in Table 3 should be used. If the breaker being tested is not listed in Table 3, the test currents should be approximately 3 times the normal trip rating of the breaker. Perform the time current trip test in accordance with Multi-Amp instructions. Observe and record the time shown on the timer as the operating time of the breaker at that percent of rated overload. Compare this test time with times given in Table 3. If the operating time of the breaker does not agree with the curve or Table 3, replace the breaker. If the breaker is not listed in Table 3, check the manufacturer's time current curves for the appropriate trip time. [D] [D] [D] [D] [D] [D] [D] [D] Table 3. Trip Characteristics for Molded-Case Circuit Breaker (4) Instantaneous Trip Test. Connect the breakers to the Multi-Amp tester and select the proper ammeter range (about 10 times the normal trip current rating of the test breaker). Do not rotate the main control while large currents are flowing. Alternately increase the output current and jog the tester until the breaker trips or until the maximum test current is reached. If the breaker does not trip at the desired current value, replace the breaker. The above is only an example of one type of circuit breaker. The criteria should address all circuit breakers that an organization supports. References: Kennedy Space Center (KSC) General Practice (GP) 1002, quotMaintenance and Test Criteria for Circuit Breakers.quot | This practice has been used by the Kennedy Space Center Shuttle Processing contractor. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
847 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Ultrasound Testing |  | The testing provides cost savings thru detection of leaks in air/fluid systems that are not normally audible. Compressors and fluid pumps may run at above normal requirements to make up for the loss caused by leaks creating unnecessary costs to power the equipment. Bearing problems can be evaluated over a period of time to detect progressive wear by changes in the ultrasound intensity level, thus protecting the bearing from sudden failure. Testing of electrical systems for sounds of arcing is easily accomplished enabling loose connections and openings to be found. Ultrasound testing is one of the least complex and less expensive maintenance detection methods, requiring a hand held detector and associated meter. | Use ultrasound as a technique for detection of air/fluid leaks, electrical shorts and bearing wear in Ground Support Equipment (GSE). Ultrasound is a technique of listening for audible frequencies outside the normal range of human hearing. This differs from ultrasonics, which is the technique of inducing sound frequencies into a medium to measure distance or thickness. | KSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number AT-10 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Timely detection and elimination of air/fluid leaks, electrical shorts, and bearing wear will result in substantial cost savings in equipment operation and maintenance. Examples: Elimination of air/fluid leaks would produce savings in power consumption, and equipment wear and tear. Detection and elimination of conditions causing arcing in electrical systems would result in increased system availability and repair time associated with downtime and damage that would have resulted from electrical shorts. Implementation Method: Ultrasounds, by definition, are beyond the limits of normal human hearing, an operator using a sophisticated detector translates ultrasound signals to the range of human hearing. Ultrasound detection is the number of times a sound wave cycles from trough to crest. This is expressed in cycles per second and measured in hertz. One kilohertz is 1000 cycles per second. The best human ears can generally hear noises in the range of 20 to about 20,000 Hz (20 kHz). Many ultrasound detectors start at approximately 20 kHz and can work upward to sounds as high as 100 kHz. Operators using the ultrasound instrument can tune to and quothearquot what is going on in operating machinery (figure 1). [D] Figure 1. Use of Ultrasound Gun to Detect Leaks in Pipe Flanges Fluid and gas systems and other working machinery have constant ultrasound patterns. When a leak occurs, fluid passing through an opening produces turbulence with strong ultrasound frequencies. Changes in the quotsound signaturesquot can readily be recognized as wear in components. An ultrasound detector senses subtle shifts in the signature of a component and pinpoints potential sources of failure before they cause costly damage. The longer wavelengths of lower-pitched sounds easily penetrate solid; yet they slip through minute openings. Ultrasound detectors are used for isolating such leaks. Operators use lightweight, battery-powered pistol-shaped instruments which can easily be moved from machine to machine. The instrument circuitry translates the high-pitched ultrasounds to those in the human hearing range. Some instruments feature a frequency-adjust dial to provide tuning capability, enabling operators to hear the ultrasounds through headphones and determine their intensity by the definitions registered on an analog meter. The instrument is used to establish sound patterns, which compared at a later date become useful in locating and diagnosing bearing failure, vacuum and pressure leaks, valve blowby and faulty electrical circuits. References: Plant Engineering, June 18, 1987. Maintenance Technology, January 1994 P/PM Technology, March/April 1991. P/PM Technology, Reprint 1986-1988. Predictive Engineering, LSOC/KSC.May 3, 1996. | This practice has been used on Automobiles, Power Industry, Hospitals, Aircraft. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
855 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Pneumatic System Contamination Protection |  | System gas must be conditioned before it is allowed to enter a new system. Installing filters immediately upstream of interfaces achieves this objective and also reduces dirt and water contamination that can interfere with component and system operation. | Install filters immediately upstream of all interfaces in pneumatic systems to control dirt and water contamination. | KSC | 12/01/1994 | This Lesson Learned is based on Maintainability Technique number OPS-11 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Proper use of filters, prevents contaminated gas from interfacing with component and system operation, provides the following benefits: Decreased component failure caused by contamination. Efficient and effective means of servicing system/equipment by filter cleaning or replacement. Increased system availability due to reduction in system maintenance. No matter how well a system is designed or how expensive, particulate-contaminated gas interferes with component and system operation. System gas must be conditioned; it must be decontaminated before it is allowed to enter a pneumatic system. The KSC design standard for pneumatic systems defines the following requirements for filters: Filters shall be installed immediately upstream of all interfaces where control of particulate matter is critical and at other appropriate points as required to control particulate migration. Selection of filters shall be made only after analysis of overall system performance requirements. This ensures maximum protection of critical components and minimal performance penalty (pressure drop). Filter housings and elements shall be constructed of 300 series stainless steel to reduce particulate contamination due to corrosion. Seal materials shall conform to manufacturer's recommendations and the requirements specified herein. The element construction should be welded instead of soldered whenever possible to simplify cleaning. Where 300 series stainless steel is specified, type 303 and other austenitic stainless steels should be avoided whenever possible because of susceptibility to stress corrosion cracking. However, overall cost should be the deciding factor. Filter elements shall maintain filtering quality and not be damaged in any way when subjected to worst-case system conditions (i.e., maximum design flow rate and element clogged to its maximum design capability). Providing unconditioned gas in a pneumatic system will have the following effects: Degraded system performance because of contamination. Increased maintenance cost and downtime to recover from problems induced by contamination. Decreased system availability. References KSC-SD-Z-0005A, Standard for Design of Pneumatic Ground Support Equipment. Parker-Hannifin Corp., Bulletin 0225-B1, Fluid Power. | This practice has been used on the Apollo, National Space Transportation System, and Pneumatic Ground Support Systems. | N/A |  |  | Public | Not Specified |  | 04/20/2000
837 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | False Alarm Mitigation Techniques |  | The reliability of a system's BIT can be determined in part by the number of false alarms it experiences. If the BIT can not accurately identify and report the occurrence of failures then the test has failed its mission. Testability must be treated with the same level of importance as other design disciplines. BIT reliability must be considered just as critical as any other performance requirement. A system cannot perform its mission if its components are constantly being removed for false maintenance. | Minimize the occurrence and effect of Built In Test (BIT) false alarms by applying principles and techniques that are intended to reduce the probability of false alarms and increase the reliability of BIT in avionics and other electronic equipment. | JSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number DFE-2 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Effectively implementing Built-in-Test (BIT) techniques automatically reduces the number of BIT false alarms. Decreasing the number of BIT false alarms increases a system's availability and decreases the maintenance man-hours required. The overall result is a reduction of the system's life cycle cost. Implementation Method: To mitigate false alarms, a system's BIT circuitry must be able to cope with a limited amount of anomalous performance. NASA Handbook 5300.4 (1E) defines a false alarm as an indicated fault where no fault exists. Based on this definition, this technique is concerned only with BIT indications of system malfunction which cause unnecessary maintenance actions. The inability of a system to detect or report the occurrence of a failure, a fails to alarm condition, is not a false alarm and is not addressed. BIT should be designed to distinguish between actual failures and anomalies which must be tolerated due to adverse operating conditions or that are normal anomalies within acceptable limits. To accomplish this, the following principles and techniques must be mandated in the system specifications, requirement documents, and design policies and implemented in the system design. Voting Scheme One technique is called the Voting Scheme. With the voting scheme, all test data are analyzed by three or more different computers. A failure is declared only when a majority of the computers detect the same failure. An example of this type of architecture is the Space Shuttle Orbiter Avionics System. The five General Purpose Computers (GPCs) are all interconnected to the same 28 serial data channels. The GPCs perform all system-level processing and require a majority agreement on all test signals. This technique requires an extensive use of resources but is extremely effective at mitigating false alarms. A less complicated version of this is the use of double or triple redundant monitors. Having two or more sensors in series increases the reliability of the test data reported while only requiring a single computer or processor. Continuous Monitoring Continuous monitoring with BIT filtering can be used in place of the voting scheme. With this technique, BIT results are based on a integration of successive measurements of a signal over a period of time instead of a single check of the signal. The monitoring of the signal does not have to be continuous but only sampled over the time period. The filtering involves comparing the current reading of a signal with past and future readings of the same signal. This filtering allows for the disregarding of sporadic out-of-limit measurements. Only when a signal is out-of-limits for a predefined time limit or a sequence of tests identify the same failure, should the BIT flag be set. To maximize the effectiveness of continuous monitoring, the BIT data must be recorded. Once recorded, the data need to be summarized and evaluated so that trends can be tracked and weaknesses identified. Controls should be implemented to help manage all of this data. The number of signals monitored and the maximum sample rate can be limited. The time span over which data are collected should be set at a reasonable period, and the type of data accumulated should be restricted. Finally, computing techniques can be used that do not require the storage of old data. Once the information is gathered, a failure log should be created. This failure log is the basis for future modifications to the system's BIT. To improve the BIT, every instant of anomalous performance not related to an identified failure mode should be analyzed and the root causes identified. Some form of corrective action must be taken to avoid recurrence. If a design change cannot be made, then the BIT must be modified to accommodate the non-failure causing anomaly. The need for modification requires BIT to be flexible. Test parameters and limits must be easily changed. The operator should be able to control or even change the test sequence. This flexibility allows the necessary changes in the BIT to be made if false alarms start occurring. For example, the Space Station's Command and Data Handling System uses programmable Deadman Timers in the multiplexer/demultiplexer (MDM's) and standard data processor (SDP's). The response intervals of the timers can be adjusted by the system controller to accommodate changes in system configuration or mode of operation. However, the BIT software must be changed without disturbing the system operation. For this to be possible, the BIT software must be independent of the operating software. Decentralized Architecture Another technique for mitigating false alarms is the use of a distributed or decentralized BIT architecture. With this approach the BIT is implemented so that a NO GO on a given test directly isolates the implied failure to a replaceable unit. Locating most of the BIT internal to a unit greatly reduces the possibility of incorrect isolation of a failure. Although the decentralized BIT concept consists primarily of unit level tests, some system level testing is still required. An excellent technology for combining unit level testing with system level testing is boundary scan. Boundary scan is the application of a partitioning scan ring at the boundary of integrated circuit (IC) designs to provide controllability and observability access via scan operations. In Figure 1, an IC is shown with an application logic section, related input and output, and a boundary scan path consisting of a series of boundary scan cells (BSC), one BSC per IC function pin. The BSCs are interconnected to form a scan path between the host IC's Test Data Input (TDI) pin and Test Data Output (TDO) pin, for serial access. [D] Figure 1. Integrated Circuit with Boundary Scan Paths During normal IC operation, input and output signals pass freely through each BSC, from the Normal Data Input (NDI) to the Normal Data Output (NDO). However, when the boundary test mode is entered, the IC's boundary is partitioned in such a way that test stimulus can be shifted in and applied from each BSC output (NDO). The test response can then be captured at each BSC input (NDI) and shifted out for inspection. Internal testing of the application logic is accomplished by applying test stimulus from the input BSCs and capturing test response at the output BSCs. External testing of wiring interconnects and neighboring ICs on a board assembly is accomplished by applying test stimulus from the output BSCs and capturing test response at the input BSCs. This application of a scan path at the boundary of IC designs provides an embedded testing capability that can overcome test access problems. The unit level tests can also be combined for a subsystem or system level verification (Figure 2). More details on applying these techniques are in IEEE Standards 1149.1 Boundary Scan and 1149.5 System and Maintenance Bus. [D] Figure 2: Typical Test Regimen for Space Systems Finally, high-reliability components should be used in the design. The reliability of the BIT hardware should at least equal or exceed that of the hardware it is testing. The BIT software also needs to be thoroughly tested and verified to ensure that it will not be a source of false alarms. Accordingly, adequate amounts of effort and resources must be allocated during the design phase. The designer should not be unduly limited by memory size, component count, or any other allocated resource. These guidelines are not all inclusive. The false alarm problem is very complex. Each system is unique and must be approached differently. The best approach is simply to eliminate each factor as it is identified. References: Coppola, Anthony, A Design Guide for Built-In-Test (BIT), RADC-TR-78-224, April 1979. Malcolm, John G., Highland, Richard W., Analysis of Built-In-Test False Alarm Conditions, RADC-TR-81-220, August 1981. NASA Handbook 5300.4 (1E), Maintainability Program Requirements for Space Systems, March 10, 1987. Texas Instruments Inc., TESTABILITY, Test and Emulation Primer, 1989. | This practice has been used on International Space Station Program and the National Space Transportation System. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
870 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Fault Isolation Using Terminal Blocks |  | Maintenance effort and system downtime will be reduced by the implementation of this practice. | Utilize terminal blocks (strips) in control cabinets and junction boxes to provide common test points for fault isolation. | KSC | 12/01/1994 | This Lesson Learned is based on Maintainability Technique number OPS-12 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. This practice reduces the amount of time spent during troubleshooting and maintenance of ground support and facility equipment by: Centralizing test point locations for electrical circuits. Clearly labeling wire/terminals for ease of locating a particular circuit. Making spare wires available for wire replacement or system modifications. Fault Isolation is simplified by utilizing terminal blocks in the circuitry of ground support and facility equipment. The terminal blocks are used to modularize the equipments circuits at locations that are convenient to personnel access. Examples of convenient locations are control panels and junction boxes. Each wire at the terminal blocks is labeled clearly. The label is the wire number listed on the electrical schematic. Clear, meaningful labels and a centralized location will reduce the time required for maintenance personnel to locate and identify circuits necessary to troubleshoot. The centralized location makes component isolation easier. Only a screwdriver is usually required to disconnect wires during troubleshooting. Consideration must be given to the design of the terminal block. The screw terminals should be recessed into the block or separated by non-conductive dividers so that tools and probes cannot create a short across adjacent terminals during troubleshooting or accidental contact. Consideration must also be given to wiring layout. Signal wiring should be separated from power and control wiring to reduce the chance of electrical interference. Any high voltage wiring should be separated and a cover placed over the terminal block to reduce the danger to personnel. If required, covers should be placed over all terminal blocks if there is a concern regarding debris and foreign objects causing electrical short circuits. Other benefits are realized from this practice. Control panels and junction boxes are located in areas that are safe for personnel access, reducing the need to expose personnel to dangerous conditions. Spare wires between control cabinets and junction boxes are included in the original design. The spare wires can be used to replace existing wires if they are damaged or to add new components during system modifications. A systematic approach to wiring is necessary to implement this practice which reduces wiring errors at startup. | This practice has been used on the following KSC systems: Space Transportation System (STS), Facilities and Ground Support Equipment, Examples: Vehicle Assembly Building (VAB) 325 Ton Bridge Cranes, Orbiter Processing Facility Three (OPF-3) 30 Ton Bridge Cranes. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
839 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Fault-Detection, Fault-Isolation and Recovery (FDIR) Techniques |  | Operating in such a critical environment as outer space, astronauts' lives and mission success are dependent on the integrity of a system. Since time and resources are limited, the sooner failures can be accurately detected and a failed system repaired and recovered, the more likely crew survival rate and mission success are to be improved. | Apply techniques such as Built in Test (BIT), strategic placing of sensors, centralized architecture, and fault isolation and recovery to optimize system availability. | JSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number DFE-7 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: The main goal of fault detection and isolation is to effectively detect faults and accurately isolate them to a failed component in the shortest time possible. This capability leads to reduction in diagnostic time or downtime in general and, therefore, increased system availability. A good inherent diagnostic of a system also enhances the crewmembers' confidence in operating the system, the main driver of mission success. Effective FDIR can keep a difficult to maintain system up and running where normal methods would lead to system downtime. FDIR is especially beneficial to an on-orbit system where maintenance may be impossible. Implementation Method: The growth of electronic technology challenges the use of electronic systems in several respects. One of these is the complexity of testing the systems to determine functional status and to permit efficient fault detection and fault isolation. The term quotdiagnostic capabilitiesquot refers to the abilities of a system to detect a failure and to isolate it to a failed maintainable unit. In the past, diagnostics were considered only as a design afterthought and, as a result, many programs are faced with higher mean time to repair (MTTR) and higher work-hour and false alarm rates. This reduces system availability and operational readiness while increasing life cycle costs. Diagnostics are a significant key to achieving system performance and cost effectiveness goals. In such a critical system as the International Space Station, on which human life is dependent, a system recovery concept is also an important aspect that needs to be considered early in the system's design phase. This technique consists of sections on fault-detection, fault-isolation, and recovery techniques. Since they are all related under the integrated diagnostics concept, techniques of one section may be referenced in other sections. Fault-Detection Techniques A system fault can be detected manually or automatically, depending on operating modes and how quickly the system needs to be restored. For a system that requires human interfaces, system failures can be detected quickly by human visual and/or auditory senses. If, for example, a light is switched on and there is no illumination, one can visually detect that there is a problem with either the light switch, light bulb, power source, or circuitry. The obvious advantages of manual fault detection are that it incurs no costs associated with complex system designs. Another common methodology, built-in testing (BIT), is employed to detect and isolate faults without using external test equipment. BIT ranges in complexity from a lamp that lights when equipment fails, to a resident computer that generates test signals and evaluates system responses. BIT can be continuously operated, interleaved with other operations, or initiated on command. During power-on self-testing, for example, the system runs a self-diagnostic test after the power is applied and includes hardware sensors and software error correcting codes. Its particular mechanization and utilization in a system are, of course, determined by the designer. BIT often means additional hardware above that required for the primary function. Reliability and cost are affected and tradeoffs leading to a balanced solution must be made. BIT protective circuitry, moreover, should be designed to be fail-safe. This means that failure in the BIT circuitry should not affect system performance. Whenever feasible, the BIT input and output should be sufficiently isolated from the normal channels so that any failure in the BIT will not cause impairment of the function being tested. Also, it should be recognized that BIT can fail, and additional measures should be taken to avoid utilization of possibly erroneous BIT output in recovery measures. In addition to BIT circuitry which actuates visual status indicators, BIT features may also include test points and self-test meters. The goal of BIT design is to decrease MTTR by steering a technician to the faulty component as quickly as possible. BIT designers attempt to attain this goal through various means, including the use of innovative circuitry and rearrangement of circuits to perform dual functions with a single circuit, if possible; e.g., driving a visual indicator and tying into various AND gates with a single driver. The BIT designer also standardizes BIT circuitry as much as possible, thus driving down the cost of implementing BIT. Other important general considerations in designing hardware BIT are: The reliability of the BIT hardware should exceed that of the hardware being tested. If this is not the case, the probability of failure of the BIT may be almost as great as the probability of failure of the unit being tested. The BIT should be kept simple but effective in meeting operational needs. The type of circuitry used for BIT should be, if feasible, of the same type used in the normal system to minimize the number of different types of components used in any particular system. As a part of the BIT design process, the overall system architecture must also be considered for the most effective implementation. Generally, there are two common approaches: centralization and decentralization. Centralization is regarded as a highly integrated approach in which a centralized unit acts as a quotwatch dogquot in detecting and reporting system out-of-tolerance conditions. The centralized unit determines if a failure actually occurred based on the data and information queried from the lower level, and annunciates or reports faults (see figure 1). [D] Figure 1. Centralized Architecture The type of information acquired by the central unit is an example of passive BIT. Passive BIT monitors system performance on line without the use of a test pattern generator; therefore, it may not be able to completely monitor the system. Active BIT, a more comprehensive type of testing, can also be used. In active BIT, a test pattern is written to a unit and compared to an expected pattern. The system operation must be interrupted for this type of test if the module is operating. Not all modules are operated continuously, however, and a computer-controlled BIT system can take advantage of times when a module is not needed to run a test sequence. This is referred to as interleaving BIT, which can be a powerful means for maintaining confidence in a system without disrupting its mission to run tests. On the other hand, decentralized architecture places detection capabilities at the maintainable unit level. Each maintainable unit has the means to detect all the identified failures within the unit. Once a failure occurs, the unit reports to a higher level for record and fault annunciation (see figure 2). Both passive and active BIT can be used in this case. [D] Figure 2. Decentralization With decentralized BIT, each module will have its own circuitry to monitor such out-of-tolerance conditions as voltage, current, or parity word at a particular node or memory location. Failure condition of a module can be notified to a central display unit via a data distribution network such as a 1553 bus network. One advantage of decentralized architecture is that a subsystem or a module can be taken off line for a comprehensive test using active BIT (generated test pattern). In general, the decentralized control must have the following characteristics: Self-test capability. Isolation from other system data. Some type of synchronization with system functions. A voting scheme is another effective technique to detect failure. With this technique, on-line data are processed by three or more redundant computers. A failure is declared when one unit's output is different from the other two or three units. Decentralized architecture is commonly used in this application. The inertial measurement system on the Orbiter exemplifies this type of architecture, in that three redundant inertial measurement units process real-time data and compare the outputs for majority agreement. This method requires additional resources but is highly effective in fault detection. Fault-Isolation Technique Once a failure is detected, the next step is to locate the cause of that failure. The complexity of a system, quick-turn around time demand, repair location, and human skill level are some important factors which must be considered in planning the fault isolation strategy of a system. Faults can be isolated manually by visually inspecting for burned-out components or by using an external test set for system diagnostics. For a more complex system and time-critical mission, the faults can also be isolated automatically. BIT, as mentioned in the fault-detection section, contains an inherent fault-isolation mechanism, since signals generated by a failed module can be identified by the control unit, thereby allowing a test pattern to be injected to that particular unit to confirm its failure. Sometimes BIT can isolate failures down to a certain system level or to a region of a system that has components connected in a series. In this situation, it is rather difficult to determine exactly which component has actually failed. In contrast, voting scheme will accurately pinpoint the failed unit, because the redundant connections of the system dictate the ease of fault isolation. However, in situations where the remaining two units indicate a fault has occurred, a failed unit will not be easily identified because there is no quotmajorityquot reference data for comparison. A more recent approach to isolating a failure in the integrated circuit (IC) industry is called the boundary scan. The IC is divided into regions which are accessible via scan operations. A boundary scan path consists of a series of boundary scan cells (BSC's), one BSC per IC function pin. The BSC's are interconnected with the host IC's test data input pin and test data output pin, for serial access. During normal IC operation, input and output signals pass through each BSC without interference. When the boundary test mode is selected, however, the test stimulus is applied through a series of BSC's, and test results are captured at the end of the scan path. This technique overcomes the test access problems that can cause difficulty in fault isolation. The unit level tests can also be combined for a system-level verification. Recovery Technique In order for a system to recover manually or automatically from a failure, modes of operation which depend on types of failures must be defined and planned ahead. During the design phase, the system's critical functions, levels of redundancy, and functional paths are usually identified so its recovery functions can be realized. In general, there are three categories of recovery: (a) 100 percent functional recovery using redundant system components, (b) functional recovery using an alternative path, and (c) degraded functional recovery. For category (a), the system is designed so that when a component fails, its failure is reported and the component's redundant or backup unit can be turned on manually or automatically. In such systems as satellites, interplanetary probes, and the Space Station, which require autonomous operations, automatic recovery is likely to be provided. Resources are almost always limited in any situation; therefore, instead of having a redundant string or unit, an alternative path, category (b), may be taken to recover the lost function. The alternative path usually does not achieve the full capabilities of the original function because of limiting space and design constraints, including costs. For reasons stated above, many redundant critical functions of the Space Station have been designed using the method of functional recovery. If, for example, the cooling loop of the thermal control system failed and was unable to cool the electronics equipment mounted on the cold plates, cool air from the environmental control and life support system may be redirected in order to keep the equipment from overheating. The equipment may also be required to operate at a minimal level to lessen the heat generated. As a worst case, redundant strings are out or not available; in which case, operating a system at some minimal capacity must be considered to protect crews or vehicles. In these cases, the critical functions of a system must be looked at to decide which of its components or units may be turned off without losing the ability to control the spacecraft until repairs are made. If, for example, some of the solar array panels were damaged, insufficient electrical power would be generated to support all the Space Station functions. In this case, power allotted to less critical functions would have to be curtailed or eliminated and even critical systems may have to be operated at some compromised level. Summary FDIR is becoming an increasingly important factor in designing today's complicated systems and in today's competitive edges for operating an efficient plant or space system with minimal downtime. In any business, downtime or delays may cost millions of dollars a year in addition to operating costs, simply because FDIR was a design afterthought. By implementing FDIR's design features, one can be assured that the final product will be a safe, efficient, and maintainable system. References: Air Force Design Handbook 1-9, quotMaintainability (for Ground Electronic Systems),quot Second Edition, Revision 7, February 25, 1988, United States Air Force Aeronautical Systems Division. Architecture Design Document (ADD) D684-10504, quotFailure Detection, Isolation, and Recovery (FDIR),quot February 22, 1994, International Space Station Alpha Program, National Aeronautics and Space Administration. Anthony Coppola, quotA Design Guide for Built-In Test (BIT),quot April 1979, Rome Air Development Center, Air Force Systems Command. | This practice has been used on International Space Station Program. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
838 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Software Design for Maintainability |  | Because of increases in the size and complexity of software products, software maintenance tasks have become increasingly more difficult. Software maintenance should not be a design afterthought; it should be possible for software maintainers to enhance the product without tearing down and rebuilding the majority of code. | Apply maintainability concepts to development of software in the early phases of the lifecycle. | JSC | 12/01/1994 | This Lesson Learned is based on Maintainability Technique number DFE-6 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: By designing software products that are maintainable we can update and enhance fielded software much faster and at lower cost. Software can be reused, thus alleviating costly update time. Also, any faults found in the software can be easily diagnosed and corrected, reducing downtime and meeting delivery schedules. Software maintainability ensures system availability by reducing system downtime. Implementation Method: Introduction Recently, software products have exhibited a dramatic growth in size, complexity, and life cycle cost (LCC). In a large system, software LCC typically exceeds that of hardware, with 80-90 percent of the total system cost going into software maintenance to modify the delivered program to meet the changing and growing needs of users. The total system cost includes hardware, software, acquisition, development, and deployment costs. Changes over the life of a program are inevitable, even if the program has met all its design requirements. Software changes are needed to adapt to increased functional requirements and different system configurations brought about by these changes. One of the most urgent concerns in the computer industry is the need to maintain and enhance the software product at faster rates and at lower costs. To meet this objective, better, more maintainable software must be designed. Maintainable Software Maintainable software, which facilitates the correction of errors and deficiencies, can be expanded or contracted to satisfy new or changing requirements, which may include enhancing existing functions, modifying for hardware upgrades, and correcting code errors. The means of achieving this goal depends on not only one technique, but a combination of many tools and techniques, including the following: Early planning: anticipating what and how programs might be modified at a later stage. Modular design: defining subsets and simplifying functionality (i.e., one module performs only one function). Object-oriented design: encapsulating both methods and data structures to achieve a higher level of independence than that of modular design. Uniform conventions: facilitating error detection and debugging. Naming conventions: providing understandable codes. Coding standards, comments, and style: enhancing readability of the program. Documentation standards. Common tool sets. Configuration Management It should be noted that topics d through h can all come under the classification of configuration management, which as a subject in and of itself is very important to maintainability, but is listed by itself to show importance. Early Planning As with anything else, early planning puts design problems into perspective, provides good strategy, and is the most cost-effective way for modifying or adding features to software products at some later time. Early in the definition phase, expected changes should be identified and prioritized so that their considerations can result in an architecture receptive to change. The system functionality should be decomposed into manageable segments for which software modules may be built. The format of these modules should be standardized so that code can be added, deleted, or modified to incorporate expected as well as unexpected changes. This helps to ensure that minimum interface alterations will be required to implement a change. Also, some particularly volatile areas should have their parametric values stored in databases to facilitate their change. Identifying expected changes early in the definition phase, and making allowances for unexpected changes, makes for a more maintainable software product. Configuration Management Configuration management of software is probably the single most important management and maintainability concept utilized in software development. Utilization of coding standards, documentation standards, release standards, common languages and other methods will provide for good configuration management. A plan should be developed very early in the development cycle for managing the configuration of the software under development, and that plan should be followed rigorously. If configuration management breaks down, the code under development is doomed to be extremely troublesome when released for operations. Modular Design Modularized software is best structured so that high probability changes do not affect the interface of widely used modules. However, one of the most commonly encountered errors is when two or more simple functions are combined into one module because the functions seem too simple to separate. For example, one might be tempted to combine synchronization and message sending and acknowledgment in building an operating system. The two functions seem closely related and for the sake of reliability one may insist on a "handshake" with each exchange of synchronization signals. If later an application is encountered in which synchronization is needed more frequently, it may be found that there is no simple way to strip the message sending routine away from he synchronization routines. The irony of such a situation is that the mechanism could have been built effectively and separately from a simpler mechanism. Modular design also provides reusable code and reduces redundant coding that might occur in many similar functions. For example, a generic input/output routine will save coding time and make it convenient for users to retrieve and use the module. Moreover, the modules can be saved in a software repository; e.g., FORTRAN Mat-Lib, and made available to the public. Identifying potentially desirable modules, however, is a demanding intellectual exercise in which the software designer first searches for the minimal module that might conceivably perform a useful service and then searches for a set of minimal increments to the systems. Each increment is small-sometimes so small that it seems trivial. The minimalist approach seeks to avoid a module that performs more than one function as discussed above. Identifying minimal modules is difficult, however, because minimal system programs are not usually requested. Minimal modules are useful if the software family is going to be developed but are not usually worth building by themselves. Similarly, maximum flexibility is obtained by looking for the smallest possible increments in capability. Use of ADA Programming Language The Department of Defense (DoD) undertook an effort some years back to develop a standard language that would provide for many things, including software maintainability. ADA programming language, the result of this effort, will provide software maintainability, as a rule, if utilized properly with other concepts listed here. Other languages can be maintainable as well, but much research and planning must go into the language chosen for development, and ADA is always a good place to start, especially in the development of government applications. Object-Oriented Design Object-Oriented Design is a more recent approach in restructuring programs. It is intended to make program tasks more independent of each other and therefore easier to maintain. Normally, as taught in most computer courses, structured programming helps in dealing with the complexities and reduction of "spaghetti" in the code; however, structured programming is still based on the expected sequence of executing instructions. Attempting to design and debug programs by thinking through the order in which the computer does things ultimately leads to software that nobody can fully understand. With object-oriented techniques, a designer generates code based on objects and their behaviors. Objects, which might be real or abstract, could include an invoice, organization, order-filling process, or icon on a screen that a user points to and opens. An object's behaviors are expressed by its contained data structures and operations, which are also called "methods." Most systems can be built without having to think about loops, branches, and program-control structures, because the object-oriented technique is an event-driven programming approach in which events cause changes in the state of objects. Each state change is usually simple to program by itself, so the program is divided into relatively simple pieces. Each object, in effect, performs a specific function independent of other objects. It responds to messages, not knowing why the message was sent or what the consequences of its actions will be. Because objects act individually, each class which is made up of these objects can be changed largely independent of other classes. This makes the class relatively easy to test and modify. Object-oriented systems are much easier to maintain than conventional systems. Space and other considerations make it impossible to discuss the object-oriented concept here. Readers to whom this concept is new are encouraged to pursue it further in object-oriented programming. Uniform Conventions Software coding standards and naming conventions are also important in producing maintainable code; therefore, they must be established during the development process. All production of new code should be done according to these standards, along with all program extension and repair work, during both the development and maintenance phases. All software development processes should be documented, consistent and repeatable. The benefit to the maintenance programmer is that by learning the formal aspects and naming conventions of one segment of the system software, he or she will know these aspects and conventions for the other segments. Error detection and debugging are facilitated with more effort concentrated on understanding the logic of the program, even when working with a new segment. Naming Conventions The naming standards should encompass the systematic assignment of mnemonic terms chosen to suggest their own interpretation by carrying as much information about their respective variables as possible. It would be desirable, from a maintenance programmer's point of view, if there were a one-to-one correspondence between variable names throughout the program system. Global variables should be defined in a common glossary with their names the same in all routines. Local model variables are those having a meaning in the model or system specification but appear only in one routine; names of these may duplicate other local variable names, but not global names. Coding Standards, Comments and Style Since easy-to-read code is a definite plus to the software maintainer, one set of coding standards should be used to develop the documentation, flowchart construction, input/output processing, error processing, module interfacing, and naming of modules and variables. This consistency, which promotes general understanding, has prompted the Government to stipulate in software programming contracts the inclusion of the following software coding: Presentation style: describes the rules and conventions for the format of the source code that may include paper listings, listings stored on electronic media, or both: Indentation and spacing. Use of capitalization. Uniform presentation of information throughout the source code; the grouping of all data declarations. Use of headers. Layout of source code listings. Conditions under which comments are provided and format to be used. Size of code aggregates (100-200 executable, nonexpandable statements). Naming: defines rules and conventions governing the selection of identifiers used in the source code listing. Documentation Standards The reasoning for documentation standards is nearly identical to that for coding standards. Standardized document formats are necessary for good maintainability. Consistently formatted documentation simplifies the process of familiarization with any given project and assists the effort to make any given information easier to locate. It also promotes understanding of what the current status of a project is, what changes have been made, and the reasoning behind various activities during the development process. Common Toolsets A uniform environment and a standardized set of development tools adds several points important to increasing the maintainability of software. First, is the ability to reuse validated code. If changes must be made to the software, and the changes are similar to something that has been used previously, it is very convenient to be able to use code that has already been proven with the development tools being utilized. Secondly, a common toolset and environment allow for program and code portability between stations. As the environment is common, no conversions are necessary, and program compilation differences are negated. A standardized environment also reduces time necessary for training. Much less time is necessary to train people on one system than to train them for multiple toolsets. This also has the advantage of raising the average level of knowledge for that one toolset, thereby increasing efficiency. When one toolset is used for development, only one set of software resource libraries is necessary. All of this combines to decrease necessary resources needed to develop and maintain any given piece of software. Conclusion Software maintenance is a major cost contributor to software LCC. Maintenance is incurred to both correct faults and enhance capability. Therefore, designing code that minimizes maintenance costs will effectively reduce the LCC of operational software References: Capers Jones, "Programming Productivity: Issues for The Eighties," ITT Programming Technology Center, Stratford, Connecticut. Tsun S. Chow, "Software Quality Assurance: A Practical Approach," IEEE Computer Society, Worldway Postal Center, Los Angeles, California. J. Martin and J. J. Odell, "Object-Oriented Analysis and Design," Prentice Hall, Englewood Cliffs, New Jersey. Parish Girish, "Handbook of Software Maintenance," John Wiley & Sons, New York. "Third International Conference on Software Engineering," May 10-12, 1978, Atlanta, Georgia. "Annual Reliability and Maintainability Symposium," January 26-28, 1993, Atlanta, Georgia. | This practice has been used on International Space Station Program. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
840 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Mean Time To Repair Predictions |  | This MTTR prediction technique is a fast, simple, accurate and effective approach for providing a design baseline for repair times. Design and product assurance engineers can use the MTTR data to effectively define sparing, logistics and maintenance programs for a pending design. | Predict the mean time to repair (MTTR) of avionics and ground electronics systems at any level of maintenance (on orbit, intermediate or depot level) using analytical methods . This technique assumes a constant failure rate, and should be used accordingly. | JSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number AT-2 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: The Mean Time To Repair (MTTR) predictions can be used to highlight those areas of a system that exhibit poor maintainability in order to justify improvement, modification, or a change of design. They also permit the user to make an early assessment of whether the system predicted downtime and logistic requirements are adequate and consistent with the system operational requirements and allocations. Implementation Method: In general, the MTTR of a system is an estimated average elapsed time required to perform corrective maintenance, which consists of fault isolation and correction. For analysis purposes, fault correction is divided into disassembly, interchange, re-assembly, alignment and checkout tasks. The repair time of a maintainable unit generally consists of both a large number of relatively short-time repair periods and a small number of long-time repair periods. The former would correspond to the more usual case where the failed unit is replaced by a spare at the operational site on detection of a failure. The long downtimes would occur when diagnosis is difficult or removing a defective part is complicated due to, for instance, rusted/stripped mounted nuts. Having a collection of such field data provides the design engineer an opportunity to assess the Mean Time To Repair (MTTR) of the current system as it matures, or to predict the MTTR of a new system according to its features with the current system. MTTR is a useful parameter that should be used early in planning and designing stages of a system. The parameter is used in assessing the accessibility/locations of system components; for example, a component that often fails should be located where it can easily be removed and replaced. The estimated MTTR may also dictate changes in system designs in order to meet the turn-around time criteria for critical systems, such as communication and life support systems on the Space Station. In addition, the parameter helps in calculating the life cycle cost of a system, which includes cost of the average time technicians spend on a repair task, or how much Extravehicular Activity (EVA) time is required for astronauts to repair a system. MTTR is defined as the average time necessary to troubleshoot, remove, repair, and replace a failed system component. An interval estimator for MTTR can be developed from the mean of the sample data, within a lower and a upper limit with a confidence bound. For example, from a sample data set, one can find with 90-percent confidence that the range 3.2 to 4.2 will contain the population mean. Unfortunately, the exact MTTR of a system can never be found due to data uncertainties. Log-Normal Distribution The distribution most commonly used to describe the actual frequencies of occurrence of system repair time is the log normal because it reflects short duration repair-time, a large number of observations closely grouped about some modal value, and long repair-time data points. The general shape of log normal distribution is shown in Figure 1. [D] Figure 1: Lognormal Distribution Without getting involved in the derivation of the distribution equations which can be found in any statistical textbook, the following example will illustrate how MTTR of a replaceable unit may be calculated from a finite observed set of data. Example 1: The repair times ti for an orbital replaceable unit (ORU) are observed to be 1.3, 1.5, 1.7, 1.8, 2.2, 2.6, 3.0, 3.1, and 3.9 hours. Using log normal distribution to estimate the MTTR of the unit. Solution: [D] Utilizing statistical methods, the Maximum Likelihood Estimator (MLE), or the best estimated value of the mean is: [D] The Maximum Likelihood Estimator of the variance is: [D] Therefore, the mean of the log normal distribution of this example is: [D] and its variability of time to repair is: [D] How to Implement the MTTR Process Accurately estimating the MTTR of a new system is more than applying the derived formulas on field data of any existing systems. The designer must know the overall maintenance concept and operating conditions of the new system; for example, how and where the system is going to be operated and how its failed units will be swapped out. With this background, the designer can proceed to approximate the maintenance procedure of the new system, then select an existing system that has been exposed to similar operating conditions and that has a mature set of operating data. After the similarity between the two systems is assessed, the designer then can determine certain conversion factors needed to make the existing system data more applicable to the new system. Once this is done, the predictions for the new system are more meaningful and accurate. Elements of MTTR The MTTR prediction of a system begins at the replaceable unit level (RUL) where a defective unit is removed and replaced in order to restore the system to its original condition. Then the system MTTR predictions are accomplished by integrating the MTTR's of maintainable units. The following defines the elements used in the MTTR prediction of a system: Fault Isolation: Time associated with those tasks required to isolate the fault to the item. Disassembly: Time associated with gaining access to the replaceable item or items identified during the fault correction process. Interchange: Time associated with the removal and replacement of a faulty replaceable item or suspected faulty item. Reassembly: Time associated with closing up the equipment after interchange is performed. Alignment: Time associated with aligning the system or replaceable item after a fault has been corrected. Checkout: Time associated with the verification that a fault has been corrected and the system is operational. Constant failure rates: The rate of failures that result from strictly random or chance causes. This type of failure occurs predominantly in the useful life period of a unit. K factor: For on-orbit tasks, a conversion factor may be applied to convert elemental task times performed in 1-g environment to Micro-gravity environment. The conversion factor may be derived from data of past similar programs or from the neutral buoyancy testing. Ground Rules and Assumptions In the prediction, certain ground rules and assumptions apply: Mean Time To Repair (MTTR) does not include the maintenance overhead, which is generally non-related task time such as time to fill out a requisition, time to go get tools, break-time, time waiting for parts, etc. Worksite time is the only variable considered. All equipment experiences a constant failure rate. All tasks are performed sequentially by one crew member unless otherwise noted. Maintenance is performed in accordance with established maintenance procedures and appropriately trained personnel. The prediction depends upon the use of recorded reliability and maintainability data and experience that have been obtained from comparable systems and components under similar conditions of use and operation. System Level Prediction At the system level, MTTR is calculated by summing the product of the replaceable items' MTTR's and their corresponding failure rates; the result is then divided into the sum of all replaceable items' failure rates. Mathematically, it can be expressed as: [D] As an example, assume the three ORUs of a system have the following MTTR'S, Variance (V), and failure rates L: [D] Table 1: ORU / MTTR Apply the above formula to calculate the system MTTR: The results of the above example indicate that the most often failed unit will essentially drive the MTTR and variance of a system. [D] Overall, the prediction is a straight forward process and is useful in estimating a system's MTTR. Even with a limited set of data, if the prediction is used early in the design phase, the derived value should help in shaping a preliminary design guideline for the system. In addition, the prediction can also verify logistics and maintainability requirements at some later stage. References: Lamarre, B. G., Mathematical Modeling, Reliability and Maintainability of Electronic Systems, Edited by: J.E. Arsenault and J.A. Roberts, Computer Science Press, p372 - 373. Miller, Irwin, Probability and Statistics for Engineers, Prentice Hall Inc., Englewood Cliffs, p116. MIL-HDBK-338-1A, Electronic Reliability Design Handbook, Department of Defense. | This practice has been used on International Space Station Program. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/20/2000
827 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Quantitative Reliability Requirements Used as Performance-Based Requirements for Space Systems |  | Program teams and/or contractors will not be obligated and/or held accountable to design for reliability, and reliability issues may be overlooked. Also, operational design goals may not be met due to less than expected vehicle availability because of failed critical items. Program cost as well as risk will probably increase. | Develop performance-based reliability requirements by considering elements of system performance in terms of specific missions and events and by determining the requisite system reliability needed to achieve those missions and events. Specify the requisite reliability in the system specifications in quantitative terms, along with recommended approaches to verify the requirements are met. Require the system provider to demonstrate adherence to the reliability requirements via analysis and test. | JSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-ED-1273, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Quantitative reliability requirements provide specific design goals and criteria for assuring that the system will meet the intended durability and life. Early in the design process, the system developer will be required to consider how the design will provide the requisite reliability characteristics and must provide analyses to verify that the delivered hardware will meet the requirements. Assessment of the early design's ability to meet quantitative reliability requirements will support design trades, component selection, and maintainability design, and help assure that appropriate material strengths are used as well as the appropriate levels and types of redundancy. Implementation Method: The missions and scientific objectives of the subject space system are used to define quantitative reliability goals and objectives. In general, the quantitative reliability goals and objectives are stated as requisite probabilities of achieving specific missions or scientific objectives under stated operating conditions and environments. The probability values specified as being required are established through a process of trading off a desire for very high value against the cost and design constraints of achieving that value. The specified level will also determine an accepted level of risk or likelihood that the mission objective will not be met. Very often, the acceptable level may be negotiated between the science community or user, the contractor, and the various responsible NASA organizations. The use of quantitative performance-based reliability requirements does not supersede or negate the need for specifying fault tolerance or other classical reliability requirements. Fault tolerance requirements and reliability design criteria should also be levied to ensure the proper separation of redundancy, and the avoidance of failure propagation. Quantitative requirements are levied to ensure that the operational performance and missions can be met with an accepted probability level or likelihood. Table 1 shows examples of several different types of quantitative reliability requirements that can be levied on a space hardware program. The importance of using both types of requirements lies in the need to ensure that the system design is as robust as necessary and that it meets the verifiable performance goal. These types of requirements, if utilized correctly, will work hand in hand to provide the contractor direction on developing a more reliable product. The quantitative requirements are levied to ensure that operational needs can be met based on pre-set conditions. [D] Table 1: Examples of Quantitative Reliability Requirements A quantitative reliability requirement by definition means that the reliability is expressed in a measurable quantity. Performance-based reliability requirements are generally stated in terms of the probability of properly performing a mission phase or objective without a failure (or sequence of failures) that will terminate the mission phase. An example is the International Space Station reliability requirement in SSP 41000, quotSystem Specification for the International Space Station (ISS).quot The reliability requirement in SSP 41000 states that the Space Station shall provide an operational capability to provide a microgravity environment for 50 percent of the internal payload locations for at least 180 days per year in continuous periods of no less than 30 days with a reliability of 0.80 or better. This requirement holds the ISS prime contractor responsible for providing a vehicle design that will operate continuously for 30 days without suffering a system failure that would exceed the conditions necessary for microgravity science, and do so at least 4 out of 5 of the periods. The system reliability, given its associated components and redundancy configuration, can be measured against that quantitative requirement. Also, during design reviews, consideration must be given to reliability assessments of the design because of such requirements, thus heightening the awareness of program risks that may otherwise go uncovered. Other requirement statements might relate to the launch phase of a space system or simply to the normal operation phase. However, the specific elements of the requirement statement include the description of the desired performance, usually a direct or indirect reference to the amount of time involved, and the probability value needed. The mission/objective specified in a reliability requirement may deal with a major portion of the entire mission or may be a very specific portion of the mission. For instance, a reliability requirement may be specified for the ability to maintain attitude or perform a significant mission event. The specification values used for the reliability requirement depends on the criticality of the mission or objective and the consequences of failure. In the Space Station case, loss of the microgravity capability is not inherently catastrophic, and a repair capability is available. Four successful 30-day periods out of five was considered to be reasonably achievable, and was deemed to be acceptable to the scientific user community. In man-rated vehicles, determining an acceptable value for the likelihood of mission success (hence loss of mission) may be more difficult. However, specifications for the reliability may then address the probability of avoiding mission aborts or loss of function. An example might be quotthe item shall perform its functions during the launch phase without losing any of the defined capabilities or functions with a probability of 0.98.quot The Federal Aviation Administration relates the consequence of failure and the probability of its occurrence in its consideration of risk, and is shown in Figure 1. By defining quantitative reliability requirements as those involving failure events throughout a flight leading to emergency procedures or immediate landings (mission aborts), the quantitative values for commercial vehicles would be specified in the 0.999 to 0.99999 range, (or conversely 1 out of a thousand to 1 out of 100 thousand). [D] Figure 1: An Illustration of the Relationship Between Consequence of Failure and the Probability of Its Occurrence (FAA, Updated) In non-man rated vehicles or systems, the emphasis is on specifying a requirement that is sufficient to ensure a high likelihood of mission success, but not so high as to drive cost and weight beyond reasonable bounds. The use of function and item redundancy for increasing the likelihood of mission success will likely be necessary to meet high quantitative reliability specifications, but redundancy can also add significant program costs. Again, trade studies may be necessary to balance requirements for the likelihood of meeting a mission objective against the reliability achieved with current manufacturing technologies and against various design options. For instance, it would be extremely difficult at current technology levels to meet a 0.999 reliability on a lengthy mission of high complexity without the use of functional redundancy. For quick-development, highly cost-restrictive programs with limited objectives, a performance-based reliability requirement of 0.9 or less may be appropriate to keep the acquisition costs within bounds. To verify the fulfillment of a quantitative requirement, reliability analysis such as reliability block diagram analysis (RBDA) is used. The attribute of reliability, by definition, lies in the probabilistic realm while most performance attributes or parameters such as temperature, speed, thrust, voltage, or material strength contain more deterministic characteristics. Within the accuracy of the measuring devices, one can directly measure performance attributes in the deterministic realm to verify compliance with requirements. No such measuring device exists for probabilistic parameters like reliability; it is usually estimated through comparison to similar components or systems through inference, analysis, and the use of statistics. Verification that quantitative requirements have been met also provides answers to questions such as quothow reliable is this system?quot [D] Table 2: Quantitative Reliability Requirement Verification Techniques A reliability requirement specified without a probability value such as quotthe vehicle shall perform xyz mission on-orbit without failure for 5 yearsquot is impossible to verify during qualification or acceptance testing. The likelihood, or probability, that the requirement will be met is assessable, and this activity is inherently equivalent to assessing the reliability. Without quantitative requirements, it is left to the certification assessor to evaluate an estimate of the probability of success and to decide if that is sufficient, which places the risk on the program. A great deal of preliminary analysis may be necessary in the requirement specification process that considers the capability of the technology to various levels of reliability. This preliminary analysis helps avoid setting quantitative requirements too high or too low. Development of quantitative reliability requirements must represent a balance between the operational performance requirements of the system and the ability to restore and maintain the system through maintenance and sparing. Establishment of quantitative requirements as high as possible is necessary to maximize the probability that the system will complete the mission without failure. However, achieving high reliability or probability of mission success increases cost by generally requiring redundant equipment and fail-safe devices as well as high margins of safety in the material properties used. Thus, meeting unrealistic and unnecessary reliability requirements can lead to program weight and volume problems as well as cost inflation Based on the stress-strength concept of failure, perfect reliability could be achieved by building a system whose strength is greater than any conceivable stress put on the system. In reality, weight, volume, and cost constraints usually limit the strength of the design. Although perfect reliability from space systems cannot be expected, consideration of the needs of the operational community as well as the budget of the program will help in determining a requirement level. Also, if reliability goals are not met, it may be necessary to initiate a reliability growth scenario in which failure modes are analyzed and designed out of the system. This may or may not cost the program extra money, as reliability growth testing may not have been part of the original life cycle plan. As mentioned above, the International Space Station Program has levied a quantitative performance requirement on the Prime Contractor. Arrival at that requirement came through rigorous coordination with operational elements of the program, including the Mission Operations Directorate and the Science and Utilization community. The actual benchmark of 0.8 was derived from analysis of the operational needs of the program, the number of failures that could be tolerated, and an early analysis of what the space station design concept could provide. This number was a mutual agreement between the product assurance community and the operations community. As a result of this requirement, the prime is undergoing an effort as part of itís reliability group to maintain a running tally of the overall station reliability via reliability block diagram analysis. Every design change, program change, or other input is reflected in the running tally to ensure that the design meets the requirement. Technical Rationale: Many previous NASA program development efforts have relied on specific design requirements such as redundancy to minimize risk and the likelihood of failure. Quantitative reliability requirements augment qualitative reliability analysis such as failure tolerance, but more importantly, gives teeth to a requirement that may otherwise slip from the design. Designers and contractors are held responsible for designing systems and to demonstrate analytically that the system or function will have a sufficient likelihood of failure-free mission operations. References: SSP 41000, quotSystem Specification for the International Space Station (ISS),quot November 1, 1994, Contract NAS15-10000. NASA Risk Management Program Tools and Techniques Handbook, Draft, July 1988, NASA Headquarters, Code QS. NASA Safety Risk Management Program Plan, Sections 1-5, NASA Headquarters, Code QS. Reliability Preferred Practice PD-AP-1313, quotSystem Reliability Assessment Using Block Diagramming Methods.quot | This practice has been used on the International Space Station Program. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
826 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Manned Space Vehicle Battery Safety |  | Failures can result in battery-operated equipment if safety precautions are not implemented correctly during operation of the flight equipment. | This practice is for use by designers of battery-operated equipment flown on space vehicles. It provides such people with information on the design of battery-operated equipment to result in a design which is safe. Safe, in this practice, means safe for ground personnel and crew to handle and use; safe for use in the enclosed environment of a manned space vehicle and safe to be mounted in adjacent un-pressurized spaces. | JSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-ED-1272, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: There have been many requests by the Space Shuttle Payload customers for a practice which describes all the hazards associated with the use of batteries in and on manned space flight vehicles. This practice is prepared for designers of battery-operated equipment so that designs can accommodate these hazard controls. This practice describes the process that a design engineer should consider in order to verify control of hazards to personnel and the equipment. Hazards to ground personnel who must handle battery-operated equipment are considered, as well as hazards to space crew and vehicles. Implementation Method: The purpose of this practice is primarily to cover battery safety, not performance. Inquiries are frequently received from payload customers as to a listing of batteries quotapprovedquotfor use onboard the Space Shuttle. There is no such list. Any battery which can be made safe to fly in the manned spacecraft environments can be used. There are some kinds of batteries however, that are not practical to make safe for in-cabin use. For example, a battery with large amounts of free electrolyte presents huge problems in a zero quotgquot environment when trying to prevent electrolyte escape. Another example is lithium-sulfur dioxide cells, which have built-in overpressure relief which releases SO2 and other electrolyte components whenever internal cell pressure is high enough. Batteries that contain these chararacteristics are unacceptable in the close environment of the Orbiter cabin. The following is a listing of the types of cells which have already flown in the Orbiter (cabin or payload bay). These include: (1) silver oxide-zinc primary (one shot) and secondary (rechargeable); (2) nickel-cadmium secondary; (3) nickel-hydrogen secondary; (4) nickel-metal hydride, (5) alkaline-manganese primary; (6) LeClanche (carbon-zinc) primary; (7) zinc-air primary; (8) lead-acid secondary pressure relieved cells or cells having immobilized electrolyte; (9) mercuric oxide-zinc primary and (10) lithium primary cells having the following cathodic (positive) active materials consisting of: (a) Thionyl chloride; (b) Thionyl chloride with bromine chloride complexing additive (Li-BCX); (c) Sulfur dioxide; (external to habitable area); (d) Polycarbon monofluoride; (e) Manganese dioxide; (f) Iodine; and (g) Silver chromate. It must be noted that lithium-based cells are subject to extremely close review and are required to have seemingly excessive hazard controls incorporated in their usage. They can yield extremely high energies per unit weight and volume relative to other cell types. They have uniquely hazardous failure modes. For many types of lithium batteries, there is little comprehensive data which characterizes either performance or response to abusive or off-nominal exposure. The chemicals contained in them are usually either highly flammable, corrosive and/or toxic. In their various failure modes, they are subject to leakage, venting, or violent explosions accompanied by scattered shrapnel and toxic materials. Hence, no effort is spared in providing the utmost assurance that every known or suspected failure mode is prevented by effective hazard controls. Use of other types of cells is strongly encouraged wherever feasible. Weight and volume differences alone are not necessarily sufficient justification for use of lithium based cells. Use of batteries of any chemistry, including those listed above, may require extensive testing, evaluation and use of source controls. Certification prior to flight is always required. Many of the hazard controls associated with the batteries, enhance performance reliability, since the battery is designed to prevent hazards which are the result of failures. For example, the prevention of electrolyte leakage and grounding in a battery case which may cause a battery explosion also prevents aborted battery operation. The content of this practice is not intended to consider every conceivable contingency. There is no attempt herein to provide knowledge on the theory and electrochemistry of batteries, except as necessary to dictate a hazard or its control. General Battery Hazards Sources and Controls Battery hazards can generally be broken into seven categories. These are: (1) short circuits; (2) electrolyte leakage; (3) battery gases; (4) high temperature exposure; (5) circulating currents; (6) structural; and (7) charging. Practice No. 1. Flight batteries should not be subjected to short circuits. Rationale. Shorts can occur in the loads served by the battery through conductive electrolyte leaks between cells within a battery or by careless contact with cell and battery terminals. Internal shorts in cells of batteries which have been prepared for flight by effective procedures are rare. A sustained short can result in extremely high temperature increases. Table I shows effects of shorting relatively benign alkaline-manganese cells and batteries through about 30 milliohms. Peak currents are reached in less than one second. [D] Table 1: Effects of Shorting Through 30 Milliohms High temperatures can result in surfaces which burn crewmen (118 degrees F is the specification limit for touchable surfaces), meltdown of protective plastic structure surrounding the battery, release of noxious or explosive substances (hydrogen for example) or initiation of a fire. In addition to heating, a short circuit through an electrolyte leak can decompose water in the electrolyte to hydrogen and oxygen, then provide the minuscule ignition energy (1-2 micro joules) to explode the hydrogen-oxygen mixture when the short circuit current terminates with a small arc at last contact. This type of failure is considered to have caused a momentary LM descent battery short circuit during the cis-lunar leg of the aborted Apollo 13 mission. Some obvious hazard controls had been omitted to save weight because such an event was considered unlikely. Apollo 14 and later LM batteries incorporated the controls. Special Considerations Batteries must have circuit interrupters which are physically and electrically close to the battery terminals and are rated well below the battery's short circuit current capability. Interrupters may be fuses, circuit breakers, thermal switches or any other effective device. The interrupter should be in the ground leg of batteries with metal cases so that battery grounds inside the battery case (usually grounded to structure) may be sensed and interrupted. All inner surfaces of metal battery cases must be coated with an insulating paint known to be resistant to the battery electrolyte. This procedure aids in preventing battery grounds to the case through electrolyte leakage. Cell terminals must also be protected from contact with other conductive surfaces by potting or by non-conductive barrier (e.g., plastic sheets). The parts of battery terminals extending inside the battery case must be insulated from unintentional contact with other conductors and bridging by electrolyte leaks. The battery terminals which pass through metal battery cases must be insulated from the case by an insulating collar or other effective means. The parts of battery terminals on the outside of the battery case must be positively protected from accidental bridging. This may be accomplished by using female connector, recessing stud-type terminals, installation of effective insulating barriers, etc. Wire lengths inside the battery case must be insulated, restrained from contact with the cell terminals and physically constrained from movement due to vibration or bumping. Practice No. 2. Preventive measures must be implemented to prevent electrolyte leakage. Rationale. Electrolyte leakage can be caused by excessive free electrolyte in vented (pressure relieved) cells. Inadequate design of electrolyte trapping or baffling provisions under covers of vented cells or leakage through cracked cell containers is a major cause for electrolyte leakage. Another cause for electrolyte leakage is faulty seals on sealed cells, and leakage of electrolyte forced through seals by cells overheating or over discharging. Special Considerations Excessive free electrolyte in vented cells should be corrected by performing cell tests in which the quantity of free electrolyte is reduced until the cell capacity begins to be reduced. These tests must be conducted on cells whose age and cycle-life exposure is nearly identical to that proposed for flight cells. This type of test applies mainly to silver oxide-zinc rectangular cells. The cell manufacturer generally specifies a slight excess of electrolyte be used because his cells are generally recharged several times by most customers. With increasing cycles for use, the excess free electrolyte is generally depleted by both water electrolysis and absorption in gradually expanding zinc negative. Cells used in space applications are generally used on their first to fifth cycle and do not require excess free electrolyte. Cell covers can also be designed to have a cylindrical quotstand-pipequot extend downward from the underside of the cell cover toward the cell plates, from the cell vent opening in the cover. When the cell is inverted in a gravity environment, the electrolyte level collecting on the inside of the cell cover is optimized not to rise above the opening of the quotstand-pipequot. This represents the worst case. All other cell positions, including the zero quotgquot are better. Cells having free electrolyte, must be fitted with relief values in their vent ports, not just an opening and/or absorbent material. Relief valve opening pressures having a range from 3 to 35 psid and are a function of the ability of the cell case to withstand internal pressure without cracking. Some steel-case rectangular NiCd cells are considered quotsealedquot because they use relief valves set to open at 100 to 200 psid. These are not the hermetically sealed, space-type NiCd cells which may also be used. If inputs are feasible at the cell design level, micro porous teflon plugs or sheets may be installed on the vent opening on the underside of the cell cover. Such material, if not covered over the electrolyte, will permit gas to escape but will prevent electrolyte escape due to its small pores and non-wetting property. If it is not possible to use the above controls, absorbent material, such as non-woven polypropylene or cotton wadding, should be used to fill the void spaces in a battery container or is placed directly over the cell vents. This is a less satisfactory control since electrolyte may be trapped against conductive parts by the absorbent material which may also be flammable. Internal surfaces of metal battery cases must be coated with an electrolyte resistant paint as well. The required prelaunch stowage of batteries in any space vehicle, has to be oriented in an quotuprightquot position relative to gravity so that any free electrolyte is forced by earth gravity and the launch acceleration into the cell plates and separators and away from the cells seals or vents. This configuration decreases the chance of an in-flight leakage from occurring. If electrolyte is added at the initial design level of vented cells having free electrolyte, extension of the separator material beyond the cell electrolyte is required. This extension provides additional volume for capillary capture of the electrolyte, which then may require acceleration forces larger than 1g for dislodgment. In-flight maneuvers nearly always provide significantly less g's of force. Practice No. 3. Flight batteries utilizing aqueous-based electrolytes should not be stored in enclosed spaces. Rationale. Hydrogen gas, mixed with air or oxygen is flammable or explosive over a wide range of concentrations (e.g., 3.8 percent to 94 percent in air). Accumulation of hydrogen in enclosed spaces containing oxygen must always be prevented. Aqueous electrolyte cells subjected to charging, will generate oxygen as the charge nears completion, thus providing oxygen where none may have existed before (due to nitrogen purging). Whenever a flammable/explosive mixture of hydrogen and oxygen exist, an ignition source is presumed to exist although one may not be obviously identifiable. This condition can occur because energy required for ignition is on the order of 1 or 2 micro joules.Special Considerations The traditional means of avoiding hydrogen accumulation is to provide continuous air ventilation at a rate sufficient to continuously dilute evolved hydrogen below the 3.8 percent flammability level. For example, a lead-acid or silver oxide-zinc battery on over-charge is considered to evolve hydrogen at the rate expressed by the following equation: Q = 0.016 NI Where: Q = cu. ft. H2/hr. at 1 atm. and 77 deg F N = no. of cells in battery I = charging current in amperes Thus, a battery of 20 cells on charge at 3 amps evolves: Q = .016 x 20 x 3 = 0.96 cfh H 2 To dilute the hydrogen to about 2 percent concentration in the ventilating air, the air flow must be: 0.96 / .02 = 48 cfh The value Q may be corrected for temperature and pressure by multiplying it by the value: K = { 1.415(T+460) } / P Where: P = actual pressure in mm Hg T = actual temperature in degrees F In practice, it is rarely feasible to ventilate hydrogen in normal Orbiter battery applications. Hence one or more of the following controls must be exercised whether or not charging is performed on board the Orbiter. Avoid charging the battery in the habitable spaces of the Orbiter. Do not seal battery cases or provide low pressure relief valves (3 to 15 psid) on the case. Minimize the volume of void spaces inside the battery case by design or by adding electrolyte-resistant, non-flammable filler such as potting material. Prohibit any component inside the battery case which may provide an ignition source, such as arching between relay contacts. Purge the battery completely with dry nitrogen (or any other inert gas) as soon as the battery is installed in the Orbiter. Minimize the exposure of the battery to high temperatures. Practice No. 4. Do not expose flight batteries to high temperatures. Rationale. High temperatures is construed to mean temperatures higher than 120 degrees F. Some batteries can safely and successfully operate at temperatures well above 120 degrees F. Some cells, notably silver oxide-zinc, are subject to thermal runaway. At high temperatures, silver oxide decomposes, yielding oxygen. The release of oxygen oxidizes zinc in the negative plates, resulting in heat evolution and an increase in cell temperatures which increases the silver oxide decomposition rate. This is different from the mechanism of thermal runaway which can occur during constant potential charging of NiCd cells. Special Considerations Perform a thermal analysis on the battery and its surroundings to verify probable battery temperatures under load and non-load conditions. This practice is particularly necessary for high energy, high power batteries that are installed with equipment stowed in the Orbiter payload bays. Do not operate cells at loads above those set as maximum by the battery manufacturers. Provide adequate short circuit protection (See practice no.1, Short Circuits). If the thermal analysis conducted on the battery shows that it will become cold enough to require heat inputs, electrical heaters must have redundant thermostatic over temperature controls. If the thermal analysis shows that any combination of internal and external heating may result in over temperature, the following precautions must be considered: Provision for heat sinking, heat shunts or active cooling. Provisions for barriers from insulation or other convective, radiative or conductive heat sources. Provisions for thermally actuated circuit breakers to interrupt the load current near hazardous temperatures. Thermally optimized on-board location (move battery to cooler location). Practice No. 5. Batteries should be protected from circulating currents. Rationale. Circulating currents are unintended current flow, generally between cells or cell stacks connected in parallel. They can also occur between standby batteries and the prime power they support, or through electrolyte leakage paths between cells. They result in parasitic discharging and/or unintended charging of cells in the circulating current loop. Circulating currents between parallel-connected cells stacks can result from lowered voltage in one or more stacks due to cell degradation, followed by current flow from adjacent electrically sound stacks due to the resulting difference in stack potentials. Hazards associated with currents circulating through electrolyte leakage paths are described under practice no. 2, Electrolyte Leakage. The hazard due to current flow between parallel stacks of cells or between a standby battery and a prime power source, results from unintended charge and/or discharge. In adequate electrolyte batteries, charging can result in water electrolysis with consequent hydrogen generation (See practice no. 3, Enclosed Spaces) charging of lithium primary batteries is hazardous and is covered under charge prevention. Unregulated discharging can result in overheating of the hazard which are covered under practice number 4, High Temperatures. Special Considerations Circulating currents between parallel cells or cell stacks must be prevented by a blocking diode in the parallel legs. Small, conservatively current-rated Schottky barrier rectifiers have been used for this purpose to minimize voltage drops. Another alternative is to use larger capacity cells instead of many smaller cells in parallel. In the case of secondary batteries, severe charging current distribution problems can arise with parallel cell strings, requiring special charge current controls. Currents circulating from a prime power source to its back-up battery, must also be prevented with a blocking diode. Depending on the circuit power requirements, redundant controls such as a high resistance or a fuse in series with the battery may be installed. Another option is to put a relay in series with the battery which is held open by the prime power source. Practice No. 6. Flight batteries should not be subjected to mechanical, chemical and thermal stresses which reduce the integrity or functional capability of the cell cases and the battery case. Rationale. Breakage of mounting provisions, permits unconstrained movement of the batteries. Breakage of cell cases, permits uncontrolled release of electrolyte and gases within the battery case. Breakage or other failures of the battery case seals, can also permit the release of the electrolyte and gases to the enclosed battery environment. Fractures of the internal current-carrying members, can also result in arching and explosions. Special Considerations Battery cases are often made of lightweight materials such as aluminum alloy, magnesium alloy, plastics, etc. In such instances, a materials compatibility and stress analysis should be made to ensure maintenance of the cell and the battery case material strength and function after exposure to the electrolyte, potting materials and their solvents or to any material to which the battery may be exposed. Battery cases should not be sealed (in the hermetical sense) but rather should have relief valves or low pressure venting provisions installed. If a design is made which results in a gas-tight seal in spite of this constraint, the case must then meet the requirements of Paragraph 208.4 of NHB 1700.7A, quotSafety Policy and Requirements for Payloads Using the Space Transportation System,quot regarding pressure vessel safety. If the battery case closure contains provisions for low pressure venting and is otherwise sealed, it must meet the requirements of paragraph 208.7 of NHB 1700.7A, regarding sealed containers. Silver oxide-zinc cells swell in the direction normal to the plane of their plates (electrodes). Zinc-air button cells swell axially; e.g., a Duracell 1200HP cell will lengthen axially about 0.015 inches during discharge. Battery development testing must include determinations of such dimensional changes. Battery case structural design must provide the strength to withstand or negate the stresses that are encountered. If it is known that significantly low or high temperatures will be experienced by the battery, whether from external or internal sources, consideration must be given to the effects of the differential thermal expansion and contraction between dissimilar materials; e.g., plastic cell cases and metal battery cases. Plastic cell cases must not be quotpinnedquot to a metal battery case by cement, hard potting or mechanical means. Resilient filler may also be required to absorb dimensional changes due to large temperature changes. Verify the vibration resistance of the battery assembly to the vibration spectrum listed below by conducting battery certification tests or by analysis. [D] Table 2: quotFreq vs Rangequot Vibration should be for fifteen minutes in each of the three axes of the assembly. Verify shock resistance of the battery assembly to shock inputs of the below test by certification test or analysis. Subject the assembly to test in accordance with MIL-STD-810, Method 516.4. Apply a sawtooth shock pulse, 20g peak, 11+ l millisecond rise and 1+ millisecond decay, once in each direction along each of the three orthogonal axes, for a total of 6 shock pulses. This procedure is from the obsolete MIL-STD-810C. Practice No. 7. Prevent overcharging of flight batteries to preclude excessive build up of heat and/or explosive gas mixtures or expulsion of electrolyte fluids. Rationale. The charging referred to in this practice is that which may be applied on secondary batteries used in the Orbiter while in flight or awaiting launch on the pad. This condition rarely exists at the Cape due to the inaccessibility of the batteries or lack of necessity to charge. If a charge is required, most of the charges are trickle charges to quottop-offquot losses due to self discharge on the pad. Special Considerations Use a battery design which does not require freshening or quottrickle chargesquot. This is equivalent to saying do not use nickel-cadmium cells, since they have poor charged shelf-life. Nearly any other kind of cell has adequate shelf-life for shuttle missions. However, it may be necessary to use nickel-cadmium cells in applications requiring high power and low energy. Note that sealed nickel-cadmium cells on overcharge at or less than the manufacturerís recommended current and voltage are capable of recombining the generated oxygen within the cell. Therefore they will not vent any gas under these conditions nor experience significant internal pressure rise. Ground service or onboard chargers must be designed with all the performance precision and reliability of other space equipment. The voltage and current controls must follow output requirements determined during development testing or specified by the battery manufacturer to prevent excessive overcharging. Temperature adjustments of voltage and current may have to be included in the charger as well. Lithium-ion batteries require special consideration for charging, since charge control must be implemented on the individual cells. Vented or pressure-relieved batteries requiring-charging while in or on the shuttle on the launch pad should be mounted upright (tops of cells up, relative to the earthís gravity) so that any evolved gas is less likely to entrain the electrolyte. Charging instructions must include a safety warning which bans the presence of any ignition source (smoking, welding, hammering, electrical relays or switches opening and closing, etc.) near batteries undergoing charge. If battery cells are truly hermetically sealed, as in the case of certain nickel-cadmium rectangular-cell satellite batteries, gas evolution presents no problem if charge voltage and current controls are adequately implemented. Charging instructions and instrumentation must provide for a ground check between the battery terminals (disconnected from external circuitry) and the battery case after charging. Minimum resistance should be greater than 1 megohm. Where equipment batteries must be charged in flight, this procedure must be addressed in the equipment safety analysis report. | This practice has been used on the Space Shuttle Program, Orbiter, Apollo Command & Service Module (CSM) , Lunar Entry Module (LEM), International Space Station and Shuttle Payloads programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
825 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | System Reliabilty Assessment Using Block Diagraming Methods |  | In cases where computer-aided RBD analyses are not performed, personnel may evaluate the reliability merits of the design using a more qualitative approach or pursuing a hand calculation method. The qualitative or manual methods may require more time than is available to influence the program's design decision processes. Rigorous hand calculations also leave room for error or incompleteness. In either of these cases, reliability and maintainability disciplines could prove to be relatively ineffective. | Use reliability predictions derived from block diagram analyses during the design phase of the hardware development life cycle to analyze design reliability; perform sensitivity analyses; investigate design trade-offs; verify compliance with system-level requirements; and make design and operations decisions based on reliability analysis outputs, ground rules, and assumptions. | JSC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1313, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Reliability block diagram (RBD) analyses enable design and product assurance engineers to (1) quantify the reliability of a system or function, (2) assess the level of failure tolerance achieved, (3) identify intersystem disconnects as well as areas of incomplete design definition, and (4) perform trade-off studies to optimize reliability and cost within a program. Commercially available software tools can be used to automate the RBD assessment process, especially for reliability sensitivity analyses, thus allowing analyses to be performed more effectively and timely. These assessment methods can also pinpoint areas of concern within a system that might not be obvious otherwise and can aid the design activity in improving overall system performance. Implementation Method: Analysis methods described below make use of RBD analyses and commercially available software tools to analyze NASA space system designs. They are equally useful for analyzing mechanical and electrical systems and identifying potential deficiencies in system redundancy and/or reliability performance based on RBD assessments derived from drawings, schematics, and system specifications and documentation. A detailed understanding of system architecture and functionality is necessary to assess system reliability using these types of quantitative analyses. The output of this analysis is valuable to the design and engineering functions on a program. It is more useful if a concurrent relationship exists between the product assurance team activity performing the analysis and the engineering design team, since design alterations and improvements can be made in near real time. These methods combine research, drawing review, reliability analyses, and the use of software automation. When this approach is taken, it is recommended that a team of individuals be involved to bring the necessary skills to the analysis, to share the workload, and to ensure that all technical areas of the analysis are covered. The RBD Technique: The RBD process involves developing block diagrams of a system or of a systemís function (tasks for which hardware/software systems were designed). JSC analysis personnel have developed both system and system function models. Experience shows that more benefits are realized from the system function models. When a function is represented as a block diagram, the models should include all operational components of the systems that are involved in the function and reflect component redundancy and subsystem-to-subsystem connectivity. The models are developed with a commercially available software tool and, with the proper inputs, are assessed for overall system reliability and design reliability concerns. Software analysis tools are an essential part of the JSC RBD analysis process. For these analyses, JSC personnel use commercially developed software for a personal computer. As with any analysis, it is critical that all involved parties understand (1) what items were used for input and what assumptions were made, (2) what calculations were performed, and (3) what interpretations can be made from the outputs. Inputs. To create an RBD, it is necessary to collect three types of information about the system being studied: functional systems architecture data, component reliability data, and mission times. Architecture defines the redundancy interrelationships between items within a system or function. These relationships are used by the RBD process in determining serial, parallel, and m of n relationships (out of n components, m are required for success). The architecture of the RBD is attained from a study of the schematics and other diagrams of the hardware, as well as the ground rules and survival assumptions that dictate which subset of that hardware is to be used. This information is entered into the block diagram editor of the software and is linked to the failure rate data base (into which data must also be hand entered). The second type of essential information includes failure rates of the equipment of interest to the lowest modeled level of detail (i.e., piece part, etc.). The third type of essential data is the mission time of each modeled component. The last two pieces of data are used to calculate the reliability for each item in the RBD over the mission time specified and is part of the overall function probability of success. Numeric Operations. The core of the RBD analysis is the calculation of the model reliability, usually done with a software tool. The functional relationships, failure data, and mission times are input to the tool and, using user-defined methods, the reliability of the model is calculated. Any number of probability distributions can be used for calculation, with the most common method being the constant failure rate assumption using the exponential distribution. Other distributions can be used, and currently JSC is working to understand early failure phenomena and how an early failure model can be used in the reliability calculations. The software calculates reliability (or unreliability) using the block relationships of the block diagram (interdependencies), the failure rates provided by the user, the mission time, and the user-defined calculation method. Probabilities are output in tabular form by a block, higher level function or nested block for the entire model, allowing the analyst to visualize where the reliability is being affected. There are other outputs as well, and they are described below. Outputs. Using the software tools for evaluating the RBD model, a point estimate or numerical calculation for the unreliability of the system or function being studied for the mission time specified will be provided in the form of the tables described above. The RBD analysis tools will also provide a cutset "min-cut upper bound" approximation, which is a list of the failure events ordered in descending probability of occurrence. A failure event is the minimum combination of failures that would result in loss of the modeled function. The most useful features of the cutsets are their ability to conspicuously display the most unreliable characteristics of the design (weak links), areas of incomplete design, and interfaces between two systems within the design which might exhibit low reliability. These concerns are easily identified within a cutset at the top of the listing. The cutset listings are helpful in assessing the failure tolerance of a system and can be used as an indicator of where further study is warranted. Typically, those components, which appear in the top cutsets, are investigated further by changing the failure rates of these components and observing the effects on the overall reliability number. This is known as a sensitivity analysis. If failure rate changes in one component have a significant effect on the overall result, then it is worthwhile to study the possibility of changing this component so that its actual failure rate becomes lower. Other sensitivity analyses are often performed as well, including changes in mission times and actual architectural variations. Utilization of Output: Interpretation and use of the output data are probably the most important parts of the analysis process. The data have been used for verifying quantitative reliability requirements when maintenance of a certain reliability level over a certain mission time is contractually required and this type of prediction is necessary for the verification. The results of RBD analyses can lead to further studies of functional availability, maintenance actions, maintenance times, fault tolerance, spares necessity, etc. The cutsets can be formatted for use by other software tools as input data to a much larger realm of functional simulation. Another type of analysis known as a trade-off study can easily be done with RBD analyses. Trade-off studies are performed by "trading" different system architectures for the architecture of the baseline design of the system and noting the results. This method allows the results of adding redundancy or removing hardware from the system to be quickly identified. To facilitate the analysis process, JSC Safety, Reliability, and Quality Assurance (SR&QA) developed several programs that interface with the software tools and enhance their performance. These programs provide the capability to do sensitivity studies through global modification of key parameters in the data base (e.g., mission duration), an area in which the commercial tool was somewhat lacking. Other such capabilities are needed when several runs of the model are being conducted in a batch fashion. A sensitivity study, for example, would require an incremental modification of the failure rate for the given component on every iteration of the model. To do this, one of the programs mentioned above will provide for access to the data base and modification of the component failure rates before every run in the batch file. As a sidenote, the commercial tool JSC uses provides a user interface that is somewhat difficult to use and, until improvements are made, some difficulties will exist in developing and manipulating RBD models and their corresponding data bases. Technical Rationale: The assessment techniques described above, which have been applied on several JSC programs, have provided valuable data on proposed designs. RBD models have been built and studied for the early design of the Space Station attitude control function (ACF), on both the Space Station baseline and all the proposed redesign options. The ACF is one of the most critical Space Station functions, because loss of attitude control in orbit could quickly result in the loss of the Space Station. RBD analysis was used to point out weak links in the baseline subsystem design and to assist in improving the design by pinpointing where reliability could be improved. Models were also built for the redesign options, comparing the reliability of the ACF of each and providing data that helped in the decision to choose the MSFC Option A. RBD models have also been developed for the latest Space Station configurations to assist the program in verifying quantitative reliability requirements set forth in SSP 41000, "System Specification for the International Space Station (ISS)." SSP 41000 states that the Space Station shall provide for 50 percent of the internal payload locations to perform at least 180 days of microgravity science per year in continuous time intervals of no less than 30 days at a reliability of 0.8 or better. To verify that the current Space Station design will meet that requirement, JSC personnel have developed an RBD model that includes all Space Station functionality required to provide for a microgravity environment. This model has been instrumental in showing that several design changes were necessary to provide for that reliability. Models have been built in the past and will be built in the near future to be used as inputs to functional simulations of Space Station operations. These simulations will provide input to designers in areas where more fault tolerance is necessary; e.g., critical spares list development, maintenance times and mean number of actions, and expected systems availability on a stage-by-stage basis. This type of analysis has been and will continue to be very useful to program management in defining and managing program risk factors. RBD analyses have also been performed on the Orbiter Project. The Orbiter autoland function was assessed to discern the reliability of the associated hardware/software configuration over a long-duration Orbiter (LDO) mission. The autoland function was to be a requirement for LDO because of ill effects on the Orbiter crew during extended stays in zerogravity. The analysis showed a high reliability during the 90-minute mission time window in which the autoland equipment was used. Over a 30-day LDO mission, however, reliability decreased substantially, possibly requiring future on-orbit maintenance of Orbiter systems. Other Orbiter Project analyses have proved the reliability assessments to be a valuable design and management decision-making tool. JSC's RBD analysis process has repeatedly identified weak design points that were not identified during qualitative reviews of the Space Station design. Results of computer-aided RBD analyses performed by JSC SR&QA were used by the Station Redesign Team (SRT) to make recommendations to the President about the merit of different redesign options. The SRT requested that JSC SR&QA investigate the reliability of the Lockheed Bus-1 attitude control system using computer-aided RBD analyses. The results of that effort weighed heavily in the early decision to use the Bus-1 on the "Alpha" Option in place of the "Freedom" baseline propulsion modules (Bus-1 is no longer in the design, since the Russian segment is providing that functionality). Such quantitative approaches as RBD analyses lend a heightened completeness, efficiency, and accuracy to any reliability design analysis. References: RBD Analysis User's Manual (Los Altos California: Science Applications International Corporation, 1992), p. 3-11. | This practice has been used on the Orbiter Project and Space Station Program | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 04/19/2000
829 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Availability, Cost and Resource Allocation (ACARA) Model to Support Maintenance Requirements |  | The development of the Space Station and other space systems (i.e., Space Station payloads and experiments) requiring long-term maintenance support dictates maintenance planning with emphasis on an understanding of the level of support required over a given period of time. The program is written specifically for analyzing availability, life cycle cost, and resource scheduling. A combination of exponential and Weibull probability distribution functions are used to model component failures, and ACARA schedules component replacement to achieve optimum system performance. The scheduling will comply with any constraints on component production, resupply vehicle capacity, on-site spares, crew manpower and equipment. | Employ statistical Monte Carlo methods to analyze availability, life cycle cost, and resource scheduling by using the Availability Cost and Resource Allocation (ACARA) program, which is a software tool developed at Lewis Research Center. | GRC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number AT-4 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: The ACARA program is an inexpensive tool for conducting maintainability, reliability and availability simulations to assess a system's maintenance requirements over a prescribed time interval. Also, availability parameters such as equivalent availability, state availability (percentage of time at a particular output state capability), and number of state occurrences can be computed. Implementation Method: The ACARA program models systems represented by reliability block diagrams comprising series, parallel, and M-of-N parallel redundancy blocks. A hierarchical description of the system is needed to identify the subsystems and blocks contained in the system. Given a reliability block diagram (RBD) representation of a system, the program simulates the behavior of the system over a specified period of time using Monte Carlo techniques to generate block failure and repair intervals as a function of exponential and/or Weibull distributions. ACARA interprets the results of a simulation and displays tables and charts for the following: Performance, i.e., availability and reliability of capacity states Frequency of failure and repair. Lifecycle cost, including hardware, transportation, and maintenance. Usage of available resources, including maintenance man-hours. ACARA Inputs A RBD must be prepared for ACARA to simulate a system's availability. The RBD depicts a system, and the arrangement of the blocks depicts a performed function. RBD does not necessarily depict physical connections in the actual system, but rather shows the role of each block in contributing to the system's function. The blocks are sequentially numbered as B1, B2, B3, etc. and subsystems are numbered as S1, S2, etc, which are defined from the inside out. Figure 1 shows an example of a system with its corresponding blocks and subsystems. [D] Figure 1: Diagram of Blocks and Subsystems Beginning with the innermost set of blocks, each parallel or series set of blocks is partitioned into a subsystem which in turn may combined with other blocks or subsystems. The system shown in Figure 1 contains 6 subsystems: Subsystems 1 and 2 are both variable M-of-N parallel arrangement of batteries. These subsystems respectively contain Blocks 6 through 8 and Blocks 9 through 11. Subsystem 3 consists of Subsystems 1 and 2 in parallel. Subsystem 4 is a binary M-of-N parallel arrangement of diodes, Blocks 3 through 5. Subsystem 5 is a parallel arrangement of two turbines, Blocks 1 and 13. Subsystem 6 comprises the entire system and is a series arrangement of Subsystems 3 through 5 and Blocks 2 and 12. Modeling Time-to-Failure The ACARA program uses the Weibull distribution function to model the time-to-failure for the system. The shape and scale factors are adjusted to modify the form of the distribution. Uniform random numbers from 0 to 1 are generated and substituted for the reliability, R. ACARA uses the early failure (i.e., infant mortality), random failure, and wearout failure (life-limiting failure) models. These models are adjusted by user-defined parameters to approximate the failure characteristics of each block. Random failure is modeled by the Weibull distribution function where the shape factor is equal to 1 (equivalent to the exponential distribution) and the scale parameter is equal to the Mean Time Between Failure (MTBF). Wear out failure is also modeled by the Weibull function. The shape factor must be 1 or more. If the block with an initial age (i.e., it is not brand new) is installed, its initial age is subtracted from its first time-to-failure due to wear out. Likewise, if it undergoes a failure-free period, this period is added to its first time-to-failure. ACARA generates time-to-failure events using one or a combination of these models and assigns the minimum resulting time for each block as its next failure event. The early failure model is canceled by assigning to the block type an early failure probability of zero; random failure, by an excessively large MTBF; and wearout failure, by an excessively large mean life. ACARA also simulates redundant pairs of active and standby blocks. A standby block is installed as dormant and its time-to-failure is initially modeled by random failure, in which the MTBF is multiplied by its characteristic Dormant MTBF Factor. Then, the corresponding active time-to-failure is modeled by early, random, and wearout failure until the active block is replaced. Modeling Down Time The downtime for a failed block depends in part upon the availability of spares and resources. These spares may be local spares, i.e., initially located at the site. If a local spare is available when the block fails, the block is immediately replaced and downtime will depend only on the mean-time-to-repair (MTTR). If no local spares are available, ACARA will schedule a replacement according to the schedule production quantities for that block type, the constraints on mass, volume, and delay associated with the manifesting and loading spares to the resupply vehicle. ACARA also checks the constraints on the maintenance agents to determine when the block can be replaced. Once all the above conditions are met to allow the block to be replaced, ACARA then estimates the time required to replace it. The time-to-repair depends upon the MTTR's for that block type. MTTR's may be specified for up to three separate maintenance agents. Examples of maintenance agents are crew, equipment, and robotics. ACARA assumes that the maintenance actions occur simultaneously, so that the block's repair time is determined by the maintenance agent having the maximum MTTR. During the simulation, the time-to-repair may either be set equal to the maximum defined MTTR or to be determined stochastically. Refer to Reference 1 for a complete guide on the use of ACARA and the explanation for entering data and the output of graphs and information. ACARA may be obtained from the Computer Software Management and Information Center (COSMIC) at the University of Georgia, (706) 542-3265. References: Stalnaker, Dale K., ACARA User's Manual, NASA-TM-103751, February 1991. Hines, W.W. and Montgomery, D.C., Probability and Statistics in Engineering and Management Science, 2nd Ed., John Wiley & Sons, 1980 | This practice has been used on the International Space Station Program and LeRC Micro-gravity Experiments. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
830 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Rocket Engine Failure Prediction Using an Average Signal Power Technique |  | Detection of anomalous behavior is critical during the operation of the Space Shuttle Main Engine (SSME). Increasing the detectability of failures during the steady-state operation of the SSME will minimize the likelihood of costly engine damage and maintenance. The average power signal algorithm is superior to the time series algorithm because more parameters contribute to the first simultaneous failure indication times. This increases the agreement between several parameters, thus increasing the likelihood that an engine anomaly has occurred. This method also reduces the number of false failure indications that can prematurely shut down the engine during testing or operation. | Apply a univariate failure prediction algorithm using a signal processing technique to rocket engine test firing data to provide an early failure indication. The predictive maintenance technique involves tracking the variations in the average signal power over time. | GRC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number AT-5 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: This technique will reduce unnecessary failures attributed to the traditionally used redline-based system. The average signal power algorithm can be used with engine test firing data to provide significantly earlier failure indication times than the present method of using redline limits. Limit monitoring techniques are not capable of detecting certain modes of failures with sufficient warning to avoid major hardware and facility damage. Implementation Method: For discrete random processes, probabilistic functions are used to describe the behavior of the rocket engine system. The Power Spectral Density (PSD) is computed to describe how the variation of the random process is distributed with frequency. For stationary signals, the PSD is bandlimited to ±1/(2T), where T is the sampling interval in seconds. Average Signal Power Calculations The PSD is defined as the discrete-time Fourier transform of an autocorrelation function. (The derivation of the autocorrelation function is shown in Reference 1.) When the autocorrelation function is evaluated at zero lag, then an expression for the average signal power (ASP) of a random stationary process results: [D] where: P xxf ) = discrete-time Fourier Transform r xx [0] = inverse discrete-time Fourier transform The average signal power for several SSME parameters is determined by calculating the autocorrelation at zero lag for the parameters provided in Table 1. The assumption is made that the signal is stationary over the computation interval. The average signal power calculations are performed over 2-second, 50-percent overlapping window for nominal test firings at both 104- and a 109-percent-rated power levels. A smaller time increment must be used to improve the failure the algorithm. [D] Table 1: Signal Threshold and Safety Factor for SSMEs The average plus three standard deviations of the average signal power are computed for all the nominal firings at both engine power levels. These values are combined to calculate the thresholds (see Reference 1). A safety factor ranging from 1.5 to 3.5 is needed to ensure no false failure indications are computed for the nominal firings. The range of safety factors reflected signal behavior variations that occurred over seven nominal A2 firings. When used in the failure detection mode, failure of the average signal power of a parameter to fall outside its threshold results in a failure indication. Also shown in Table 1 are the thresholds calculated from the SSME nominal test firings based on the average signal power algorithm along with the associated safety factors. Algorithm Implementation A system identification and signal processing software package on a RISC workstation provides the average signal power algorithm. Command and Data Simulator (CADS) data from a predetermined number of SSME test firings are used to establish the failure indication thresholds. Several system conditions must be considered to ensure that the algorithm does not erroneously indicate an engine fault. These conditions include sensor failure, propellant tank venting and pressurization, and propellant transfer. Sensor failure detection techniques must be exercised before, or concurrently, with safety monitoring algorithms in order to eliminate the possibility of a sensor failure being interpreted as an engine problem. Typically, all parameters exhibiting sensor problems are removed prior to the application of the algorithm. Failure indication thresholds are established by applying the average signal power algorithm to a set number of nominal tests. For the SSME four anomalous firings and one nominal firing were tested using the thresholds shown in Table 1. An example of the application of the average signal power algorithm to a SSME anomalous test firing is shown in Figures 1 and 2. Figure 1 illustrates the interval over which the average signal power was computed for a single parameter, HPFP discharge pressure and one test firing. [D] Figure 1: Application of the Average Signal Power Algorithm to the HPFP Discharge Pressure Figure 2 displays the resulting average signal power, as a function of time. As shown, the threshold for the average signal power algorithm has been exceeded. [D] Figure 2: Average Signal Power for that Interval with the Failure Indication Threshold Nomenclature: HPFP high pressure fuel pump HPFT high pressure fuel turbine HPFTP high pressure fuel turbopump HPOP high pressure oxidizer pump HPOT high pressure oxidizer turbine LPFP low pressure fuel pump MCC main combustion chamber PID parameter identification SSME space shuttle main engine References: Meyer, C.M., Zakrajsek, J.F., Rocket Engine Failure Detection Using System Identification Techniques, AIAA Paper 90-1993, July 1990. | This practice has been used on the Space Transportation System (STS). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
833 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Neutral Buoyancy Simulation of On-Orbit Maintenance |  | Equipment and crew interface testing in a simulated weightless environment at an early development stage in NASA programs is an accurate means of assessing hardware and tool design features and determining crew capabilities and requirements. While other forms of weightlessness simulations (e.g., parabolic flight, motion base, and computer models) have proven effective in specific applications, underwater simulations have proven particularly beneficial in hardware development, crew/hardware interface design, and operations planning, since they can accommodate a large worksite volume and extended test times. | Simulate on-orbit space maintenance activities by using a neutral buoyancy facility to assist in making design decisions that will ensure optimum on-orbit maintainability of space hardware. | MSFC | 12/01/1994 | This Lesson Learned is based on Maintainability Technique number AT-1 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Neutral buoyancy simulation can provide valuable information for designing-in accessibility, modularity, simplicity, and standardization. It can also provide cost-effective, specific design information on the effectiveness of crew stability aids, crew maneuvering aids, specialized tools, and operational timelines. Maintainability criteria that can be established by utilizing this process include: component accessibility; fasteners accessibility, systems installation; and the configuration and operation of crew stability aids and tools. Implementation Method: The neutral buoyancy facility at MSFC has been used since 1968 to effectively simulate the weightlessness of space, and has assisted in the establishment of maintainability design criteria, particularly in extravehicular activity (EVA). Use of full-scale neutral buoyancy simulations has also allowed for direct human participation in test operations, as well as for access to the large body mock-up hardware developed for EVA simulations. These methods are a very effective way of simulating on-orbit environments for the purpose of verifying and solidifying operations and maintenance procedures. Other neutral buoyancy facilities used for NASA hardware development and test and crew training are the Weightless Environment Test Facility (WETF) at Johnson Space Center, the Neutral Buoyancy Research Facility at the University of Maryland, College Park, Maryland and the neutral buoyancy facility at McDonnell Douglas, Huntington Beach, California. Neutral Buoyancy Characteristics The MSFC neutral buoyancy facility has the following overall characteristics: Six-console control room. Three-person, double-lock hyperbaric chamber. Floating crane for underwater movement of hardware (one 2000-pound hoist, one 500- pound hoist). Removable roof section to accommodate large hardware. T.V. monitors, communications with test subjects, audio/video taping capability, pressure and depth displays of test subjects, and lightning warning systems. Support of up to four Shuttle space suited crew members. Umbilical-supplied underwater primary life support systems. Operational Remote Manipulator Systems (RMS). Air-lock for emergency test subject evacuation. The neutral buoyancy tank within the facility is a 1.3 million-gallon water tank that measures 40 ft. deep and 75 ft. in diameter. The water temperature is maintained at a range of 88 to 92 degrees Fahrenheit and a pH of 7.50. Cathodic protection systems are used to inhibit corrosion. The tank accommodates up to four pressure-suited test subjects simultaneously. Extravehicular Mobility Units are available for four test subjects. The tank can accommodate test durations of up to 6 hours. HST Simulations Underwater simulations in the neutral buoyancy facility strongly influenced the maintainability design criteria for the Hubble Space Telescope (HST) and its components; particularly with regard to visibility, accessibility, and simplicity. One of the primary considerations in maintainability of space hardware is the accessibility of components and systems by crew members during EVA. To be maintained in space, the components of a hardware item must be seen and reached by a pressure-suited astronaut or be within range of the appropriate tools. Altogether, some 70 Orbital Replacement Units (ORUs) on the HST can be replaced on-orbit. Some of the largest ORUs are batteries, computers, reaction wheel assemblies, science instruments, fine guidance sensors, and wide field planetary cameras. One of the telephone-booth-sized science experiments weighs over 700 pounds. These items are mounted in equipment bays around the perimeter of the spacecraft. The bays open with large doors so components can be readily inspected and handled. Using neutral buoyancy simulations, design features of these components were validated, verified, and refined to ensure that the ORU features of modularity, accessibility, and simplicity were inherent in the design. Other features included a series of crew stability aids; including handrails, portable handles, tether attachments, and foot restraints. Neutral buoyancy simulation studies also determined the placement of foot restraints on both the HST and the RMS arm for maximum accessibility. These design features give the crew mobility and stability during unstowing, transporting, and stowing ORUs. Door latch design criteria were also addressed in neutral buoyancy simulations involving the HST. All internally stowed ORUs except the Radial Science Instrument are concealed by doors that must be opened and closed by a crew member before ORUs are installed or removed. Simulations and Design Influence A design criterion that has become increasingly important in on-orbit maintenance and which has been studied using neutral buoyancy simulation is standardization of the EVA interface to ORUs. The practice of standardization became a key issue in HST development with the decision to mount ORUs with 7/16-inch double height hex head bolts in three types of fittings: J-hooks, captive fasteners, and keyhole fasteners. Neutral buoyancy simulations have proven that the use of standardized bolt heads, clearances, and torque limits reduces the complexity of ORU maintenance in space. To achieve electrical connector standardization, neutral buoyancy simulation studies have evaluated such criteria as connector geometry (wing-tab presence, length, and diameter) and surface texture (knurls, ridges, and irregular shapes). Response variables studied included ease of alignment, firmness of grip, and level of torque required to lock the connectors. Studies of this type led to the development of a standard for blind-mate, scoop-proof, low-and force, and subminiature connectors. If accepted as a standard, these connectors would be used in the Upper Atmosphere Research Satellite, Explorer Platform, International Space Station, and in robotic manipulators. Human factors studies have been a significant part of neutral buoyancy simulation tests with large space structures. For example, experiments have been conducted to determine the effect of fatigue on productivity during lengthy EVA structural assembly operations. An experienced test subject assembled a 36 element tetrahedral truss structure repeatedly for 4 hours, while the subject's heart rate and general conditions were monitored. These neutral buoyancy simulations demonstrated EVA productivity to be significantly higher in space than in comparable conditions simulated in ground tests. Assembly time for structural assembly tasks was approximately 20 percent less in actual flight. The Experimental Assembly of Structures in EVA (EASE) project, an experiment flown on Space Shuttle mission STS 61-B, revealed that a flexible structure can be assembled in underwater conditions with a learning curve of 78 percent. It was determined that learning rate is independent of the strength, coordination, or size of the test subject; or the fit of the pressure suit. Structural configurations have been used at the MSFC neutral buoyancy simulator to obtain human factors data. In one experiment, six-element tetrahedrons were used to obtain data on learning and on the relative value of a variety of assembly aids. The structural elements in these tetrahedrons were 11-foot-long tubes of PVC plastic, 4 inches in diameter. Sleeve-locking connectors were used to join the beams at the nodes of the structure, or "joint cluster." Much more complex structures were used to collect information on fatigue, and on crew members' ability to deal with complicated configurations and hardware. A single 36-element tetrahedral truss served as a baseline structure for comparing single-person assembly with two-person assembly, for quantifying productivity changes due to the use of various assembly aids, and for evaluating other structural configurations. Results of structural assembly experiments have shown that test subject learning rate is much higher in the weightless conditions of neutral buoyancy than in conditions on dry land. The most time-consuming task during assembly operations is aligning the beams. This large time consumption is due to the kinematics of water drag. Fatigue is not a significant factor in the assembly process if the subjects pace themselves. None the less, the following considerations must be taken when running a simulation to avoid problems: Assign two safety divers per test subject to manage the umbilical and monitor the test subjects performance. When possible, conduct paper computer simulations, and one-g dry run simulations prior to neutral buoyancy simulations. Principal Limitations The principal limitations of neutral buoyancy simulations include: (1) the need to design hardware to accommodate the effects of water corrosion, (2) varying water pressure with depth, and (3) frictional resistance of the water to body and equipment movement. The impact of not taking full advantage of the neutral buoyancy simulation capabilities at MSFC and other locations could mean entering a space mission without full knowledge of the effects of weightlessness on mission tasks, particularly in EVA's. Maximum emphasis should be placed on conducting simulations with the highest fidelity possible to ensure mission success. Failure to do so results in a greater probability of incurring safety hazards, anomalies, increased maintenance resources (man-hours), and hardware damage. References: Akin, David L. and Howard, Russell D.: Neutral Buoyancy Simulation for Space Telerobotics Operations, In SPIE, Cooperative Intelligence Robotics in Space, Vol. II, pp. 414-420, 1991. Akin, David L. and Bowden, Mary L.: "EVA Capabilities for the Assembly of Large Space Structures," IAF-82-393, Massachusetts Institute of Technology, October 1, 1982. Akin, David L.: A Design Methodology for Neutral Buoyancy Simulation of Space Operations, 88-4628-CP, Massachusetts Institute of Technology, September 1988. Barnby, Mary E. and Griffin, Thomas J.: Neutral Buoyancy Methodology for Studying Satellite Servicing EVA Crewmember Interfaces, Proceedings of the Human Factors Society 33rd Annual Meeting, pp. 149-153, 1989. Designing an Observatory for Maintenance in Orbit: The Hubble Space Telescope Experience, NASA/MSFC, April 1987. EIA Standard for Connector, Electrical, Rectangular, Blind-Mate, Scoop-Proof, Low-Force, Subminiature, AN/SI/EIA S-XXX-1991 (draft), American National Standards Institute, Inc., November 18, 1991. Griffin, B.N.: Zero-G Simulation Verifies EVA Servicing of Space Station Modules, AIAA-86-2312, AIAA, Space Station in the Twenty-First Century, Reno, Nevada, September 3-5, 1986. Neutral Buoyancy Simulator Test and Checkout Procedures for NBS Test Operations, NBS-TCP-90, NASA/MSFC, April 17, 1992. Sanders, Fred G.: Space Telescope Neutral Buoyancy Simulations - The First Two Years, NASA-TM-82485, NASA/MSFC, June 1982. The Design and Development of the Hubble Space Telescope Neutral Buoyancy Trainer, Final Report for Contract NAS8-35318, Essex Corporation, December 31, 1990. Lessons Learned Document from Neutral Buoyancy Simulation Testing Activities, MDC H34111, McDonnell Douglas Astronautics Company, Huntington Beach, CA, October 1987. Sexton, J.D.: Report for Neutral Buoyancy Simulations of Transfer Orbit Stage Contingency Extravehicular Activities, NASA-TM-103583, NASA/MSFC, June 1992. Sexton, J.D.: Test Report for Neutral Buoyancy Simulations of Hubble Space Telescope Maintenance and Refurbishment Operations: Simulations of HST Maintenance and Refurbishment Mission and New Block II ORU Access Study, NASA/MSFC, May 1989. | This practice has been used on Skylab, Hubble Space Telescope, Space Shuttle Orbiter, International Space Station, Apollo. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
832 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Robotic Removal and Application of SRB Thermal Systems |  | SRB refurbishment operations at KSC have resulted in the successful robotic insulation removal and application of 68 SRB aft skirts and other SRB elements. The facility schematic depicted in the description shows the SRB aft skirt in its most environmentally critical operation, insulation removal. This facility has been in operation for 5 years and, under routine maintenance, has been operational since its inception. Similar reliable operation has been experienced in the robotic application of insulation. | When designing robotic systems for removal and application of thermal protection materials, pay close attention to support fixture indexing, precision positioning, optimum sequencing, and protection against robotic cell environmental conditions. By integrating proven hardware and software practices with equipment and facility design and operation, the effectiveness of robotic systems is ensured. | MSFC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number OPS-03 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Adherence to proven robot cell design and operational practices will result in improved consistency, speed, safety, precision, and reliability and increased cost-effectiveness of robotic systems over manual or semi-automated processes. Implementation Method: When the SRB is recovered from the ocean, disassembled for refurbishment, and reused on subsequent Space Shuttle flights, several layers of insulating materials and protective coatings must be removed and then re-applied. Experience has shown that the use of robotic systems for insulation removal and application will improve productivity in most operations by a factor in excess of 10 to 1. Originally, the application of the SRB insulation was a semi-automatic operation. The nine ingredients (see Table 1) were measured by hand, placed in a large blender and mixer, and mixed to a uniform consistency required for spraying. This mixture was pressurized and delivered to the spray gun, which was attached to a pedestal mounted robot in the spray cell. The SRB structures were prepared by hand, i.e., sanded, cleaned, inspected, and areas masked that did not require insulation. The SRB structure was mounted on a portable turntable, which was coordinated with the operation of the robot and spray gun. Then the SRB structure and the turntable were positioned into the spray cell. A technician (with breathing air and protective equipment) was required in the spray cell during actual spraying to take thickness measurements, assist in unplugging the spray gun, and remove the wet insulation, if it did not meet specifications. The cured insulation had to meet a flatwire tensile test of 50 to 100 pounds and a toleranced thickness requirement. Adjustments were made to the delivery system and the insulation reapplied until it met specifications. Preparation of the structure for spraying and insulation required many man-hours. 2215 Adhesive parts A & B* Ground Cork Glass Ecco Spheres Phenolic Micro Balloons Chopped Glass Fibers 1/4 inch long Milled Glass Fibers 1/8 inch long Bentone 27 Ethyl Alcohol Methylene Chloride/per Chloroethylene * The original adhesive that contained shell z Catalyst was a carcinogenic Table 1. Ingredients in the SRB Insulation After automating and robotizing the application of the insulation, the insulation ingredients are automatically measured, blended, mixed, pressurized and delivered to the spray gun, which is mounted on a gantry robot. The gantry robot allows spraying inside the structures without the need to rotate the structure for access. The robot is programmed to automatically attach an end-effector to perform the following operations: sanding, cleaning, inspection, masking, spraying, and thickness measurements. Automating and robotizing the application of insulation eliminated the need for a technician in the spray cell and eliminated many of man-hours of hand work. At the start of the SRB refurbishment program, the insulation was removed manually. This required a technician to manually hold a hydrolaser pressurized to 8,000 to 10,000 psi. This created a backwash of 72 pounds force that the technician had to overcome using two 2-men crews rotated every 15 minutes. Any insulation left after this operation was removed by hand using nonmetallic chisels and mallets. Manual removal of the insulation from the two aft skirts required approximately 400 man-hours. [D] Figure 1. Example Robot Facility: SRB Insulation Removal Procedures for Robotic Removal Robotizing the removal of the insulation reduced the man-hours for two aft skirts to approximately 64 man-hours. The hydrolaser is mounted on a gantry robot which is located in the removal cell. The pressure to the hydrolaser has been increased to 12,000 to 15,000 psi. Technicians have been eliminated from the hazardous environment. The robot is controlled by computer. A turntable (also controlled by computers) is mounted flush with the floor. After removal of the insulation, the robot is programmed to clean the hydrolaser cell. Table 2 lists typical reasons for using automated robot cell to apply and remove SRB insulation. Table 3 is a list of the 13 best practices in the design of robotic systems for removal and application of insulation. The most predominant consideration was the high pressure water spray and debris environment encountered in the hydrolaser insulation removal process. Operational maintenance, as well as design, is important in maintaining a safe and efficient operation. Potable water is used to reduce corrosion in the pumps, valves, and lines. The use of de-ionized water should be considered in areas where the water has a high mineral content. Since the water used in the insulation removal process is recycled, the water must be filtered prior to reuse to prevent erosion and corrosion of pumping and spray equipment. Man out-of-the-loop for hazardous and toxic environments Efficient; robot does not get tired. Will do whatever it is programmed to do and will do it repeatedly. Will handle various end effectors for sanding, cleaning, inspection, spraying, and thickness measurements. Table 2. Typical Reasons for Using Robots For the SRB insulation system removal, the water is filtered to contain particles no greater than 5 microns. On a quarterly basis, or every 100 operating hours, high pressure water pumps are inspected and overhauled if necessary to repair or replace the pump head, pistons, or brass sleeves. Preventive maintenance is performed regularly. Gear Specifications to the environment and the application (i.e., adaption to a solvent or water spray and debris-laden environment). Pay close attention to the ergonomics for operators (i.e., convenience of controls, visibility, amnual override, and teaching procedures). Provide sufficient space in robotic facilities for support equipment, mechanisms, personnel, and operational control stations. Design-in automated shutdown to be activated in the event of excessive flow, pressures, temperatures, or inadvertent ingress of personnel. Consider the use of vision systems for alignment, completion status, inspection, and thickness measurements. Provide overload sensing and tactile feedback for delicate operations. Retain manual capability for emergency and backup operations Establish precise automatic indexing of fixtures with workpiece and robot to minimize setup time. Provide electrical grounding of all system elements Purchase over-rated equipment. Use only 75% or less of the capacity in the initial design to provide growth potential and operational/maintenance margins. Protect robot elements from solvents in the enviroment to ensure continued robot lubrication. Train and use dedicated personnel for robotic operations Establish preventive maintenance requirements during the design phase based on designed-in ease of maintenance features (i.e., proper panel access, calibration test ports, equipment clearances, etc.). Table 3. Best Practices for Robotic Systems Facility Requirements A robotic facility of the type used for SRB insulation removal and application must allow operator visibility of the process and careful design for personnel safety and access provisions. During the noisy removal process, personnel within a 50 ft. radius are required to wear ear protection. Operators entering the area during or immediately after spray operations are required to wear protective suits with self-contained breathing apparatus to prevent inhalation or contact with toxic fumes. Facility design must be carefully coordinated with robot design and robotic operations planning. A concurrent engineering approach is desirable in the design of robotic systems to ensure use of the correct robot, operating in an optimally designed facility, for the target application. A team of engineers and technicians representing all applicable disciplines should be assigned full time to the project throughout design and operations. Three levels of drawings of the robot/facility complex representing: (1) components, (2) subsystems, and (3) the integrated system should proceed through 30, 60, and 90 percent design reviews. Three-dimensional solid modeling simulations using computer-aided design techniques will dramatically speed up the design process. (See the MSFC Guideline titled, quotConcurrent Engineering Guideline for Aerospace Systems,quot in NASA TM 4322A, quotNASA Preferred Reliability Practices for Design and Testquot). The facility must contain support equipment, pumping systems, material storage, control stations, and personnel dressing and clean-up. Particular attention should be paid to debris handling. Sloped concrete subfloors provide for easy debris collection and clean-up. Automated cell clean-up techniques should be considered for material removal operations. Special Design Considerations Robotic systems lend themselves to the effective application of automated emergency shutdown, automatic end-effector changeout, overload sensing, tactile feedback, and manual override. These features should be designed into the robotic system at the outset with participation of the robot vendor. Setup time can be minimized by providing pre-engineered or automatic indexing and relative positioning between the work piece, support tooling or equipment, and robot. While mechanical systems should be over-designed for extra margins of safety against wear and malfunctions, care should be taken not to grossly overdesign control system memory, particularly if a bubble memory is used. This could result in slower robot control system operation. References: Rice, Robert: Process Report on the Automated Hydro Removal of TPS, Report # USB-ATG-003, USBI Booster Production Company, Inc., NASA/MSFC contract # NAS8-36300, January 1986. Loshe, Thomas: Hydrolyzing Operations in High Pressure Wash Facilities, Maintenance Manual # B8598, USBI Document Prepared for Kennedy Space Center, October 4, 1991. Loshe, Thomas: Solid Rocket Booster Thermal Protection Removal System Software Users Guide, Document # 10MNL-0044, United Technologies, USBI, April 2, 1990. Babai, Majid: Robot Simulation and Manufacturing, Aerospace Engineering, SAE, October 1992, pp 11-13. Fertig, Alan R. and Tony S. Humble: Robots Refurbish Space Shuttle Hardware, TABES Conference Proceedings, Huntsville Association of Technical Societies (HATS), Huntsville, AL, 1987. Special Government Publications: MM B8601, Preventive Maintenance Gantry Robot and Controller MM B8604, Preventive Maintenance/Validation Robot End Effectors MM B8611, SRB Insulation Manufacturing Manual (Forward Assembly) MM B8616, SRB Aft Skirt Assembly-MSA-2 TPS Operations Manual MM B8630, MSA-2 Tunnel Cover Assembly Operations Manual STP 513, Cleaning Sprayable MSA-2 Insulation Spray STP 621, MSA Control Room Operation STP 622, Installation and Removal of Robot End Effector Adapters STP 634, Sprayable MSA-2 Insulation Control Room and Mix Operations TP 741, MSA-2 Spray System Preparation -ARF SESP (Safety Engineering Standard Procedure) 23405, Safety Requirements for Robot Systems | This practice has been used on the Space Shuttle Solid Rocket Booster (SRB). | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
831 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Maintainability Program Management Considerations |  | Decisions by program management to establish maintainability requirements early in the program will provide design impetus towards a system with higher operational availability at lower operational costs. Lower downtime and less complicated maintenance actions will be needed when maintenance is required. | Identify program management considerations necessary when implementing maintainability principles for NASA space flight, atmospheric, or ground support programs. | HQ | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number PM-2 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Early and effective planning and implementation of a maintainability program can significantly lower the risk of reduced system operational effectiveness resulting from maintainability design shortfalls. This reduces maintenance time/support, which directly relates to reduced operating costs and increased system operational time. Implementation Method: This technique outlines management considerations to observe when applying the principles of maintainability on a program at NASA. It also provides information on how to realize cost savings and reduced system downtime. This information complements PM-1, quotBenefits of Implementing Maintainability on NASA Programs,quot by providing guidelines for establishing a maintainability program once the benefits have been understood. Program management is responsible for establishing proper integration of maintainability early in program development and ensuring adequate control of the application of the maintainability discipline throughout the development program. Figure 1 provides flow diagram for an effective Maintainability program beginning with development of its goals and objectives , followed by development of the program/system maintenance concept and the Maintainability Program Plan, and establishment of program control and evaluation during design, production (manufacturing) and operations. The order of these program development elements is important, as each affects the next step in the process. [D] Figure 1: Maintainability Program Development (1) ESTABLISH MAINTAINABILITY AS PART OF THE OVERALL SYSTEMS ENGINEERING AND OPERATION PLANNING PROCESS. Set Goals and Objectives One of the missions of the maintainability program is to measure the ability of an item to be retained or restored to a specified condition when maintenance is performed. The degree of maintainability designed into a system should reflect the function (mission) of the system/subsystem and the impact on operational objectives of the program if the system is non-operational for any length of time. System availability (the ability of the system to operate whenever called upon to do so) is very important, and maximum availability should be a goal of the program. Program maintainability goals and objectives must be developed with cost and schedule in mind; however, careful consideration must also be given to the technical and operational goals of the program. These qualitative goals and objectives are developed by analyzing the system operating cycle, the physical and maintenance support environments, and other equipment characteristics consistent with mission and cost objectives. Attention must also be given to existing support programs to avoid needless duplication during development of new support systems. Development of the maintainability goals and objectives will lead to derivation of the maintenance concept, maintainability plan, and definition of maintainability requirements discussed in the following paragraphs. Establish Interfaces with Other Engineering Disciplines Maintainability engineering is a system engineering discipline that combines system analysis and equipment design with a knowledge of safety, reliability, human factors, and life-cycle costing to optimize the maintenance characteristics of system design and to provide an awareness of interface problems. Its goal is to optimize the combination of design features, repair policies, and maintenance resources to the desired level of maintainability at acceptable life-cycle costs. The many interfaces and feedback paths between maintainability engineering and other product development and operational disciplines are shown in Figure 2. [D] Figure 2: System Reliability, Maintainability and Support Relationships (typical) While maintainability personnel must be intimately involved in the product development process and provide inputs to design through design techniques and analysis, it is program management's responsibility to develop and support the relationship between maintainability and the rest of the system engineering disciplines. This support is key to establishment of a concurrent engineering process. These relationships must be mirrored in the Maintainability Program Plan. (2) DEVELOP MAINTENANCE AND LOGISTICS CONCEPTS EARLY IN THE CONCEPTUAL PHASE OF THE PROGRAM. The program maintenance concept provides the basis for establishing overall maintainability design requirements on the program, and contains detailed planning on maintenance policy. It defines overall repair policy, organizational and depot maintenance, system availability, repair vs. replacement policy, level of replacement, skill level requirements, sparing philosophy, diagnostic/testing principles and concepts, contractor maintenance responsibilities, payload maintenance responsibilities, and crew time allocations for maintenance (Maintainability Technique PM-3 provides details on each of these elements). Development of the maintenance concept is based on initial maintainability analysis and program inputs such as mission profile, system availability and reliability requirements, system mass properties constraints, and personnel considerations. The maintenance concept may be developed from the ground up, or may come from a similar successful program, tailored to meet the needs of the new program. New technology may also dictate the maintenance concept, e.g. maintainable items may be scrapped instead of repaired because the cost of repair outweighs the replacement cost. Definition of logistics and support concepts is a function of the maintenance concept. The operational environment of the system, the level of support personnel defined by the maintenance concept, and cost and schedule are important drivers for the logistics/support programs. These elements are also important contributors to system maintainability in that logistics planning can define how much system down time is required during maintenance operations. For example, downtime can be held to a minimum if spares are co-located with the system during operations. It is important that Program management closely monitor all logistics development to ensure inclusion of maintenance and logistics concepts early in the program. Both concepts drive the development of lower-level requirements. Assess Existing Resources Another important aspect of planning for a new program is assessment of the existing logistic and support infrastructure. As an example, the infrastructure of the NSTS system at KSC comprises the launch pad, numerous assembly and support buildings, and support personnel and equipment. These are important factors to consider when planning for new programs that will use KSC as the central operations base. If some of the existing structures and equipment can be used by the new program, then the developmental and operational costs of the program will be reduced. During early planning stages, management should also look at how the new program can adapt to the existing support infrastructure, and what equipment and personnel may be used to eliminate unnecessary costs. Establish a Maintainability Program Plan The maintainability program plan is the master planning and control document for the maintainability program. It provides detailed activities and resources necessary to attain the goals and objectives of the maintainability program. It must be developed with the program contractor(s) if they exist, or if the program is in-house, all developmental and operational disciplines must be represented. The plan must be consistent with the type and complexity of the system or equipment and must be integrated with the systems engineering process. It identifies how the contractor/program office will tailor the maintainability program to meet requirements throughout the three major program phases: Development, Production, and Operations/ Support. Typically it contains the following elements shown in Table 1: Duties of each organizational element involved in the accomplishment of the maintainability tasks cited in the product specification or statement of work. Interfaces between maintainability and other project organizations, such as design engineering, software, reliability, safety, maintenance, and logistics. Identification of each maintainability task, narrative task descriptions, schedules, and supporting documentation of plans for task exectuation and management. Description of the nature and extent that the maintainability function participates in formal and informal design reviews, and authority of maintainability personnel in approval for drawing release. Table 1. Elements of the Maintainability Program Plan (3) PROVIDE UNIFORM QUALITATIVE AND QUANTITATIVE MAINTAINABILITY REQUIREMENTS. Maintainability design requirements are established from the Maintainability Program Plan and the derived maintenance concept. These requirements are intended as rules system designers follow to meet overall program goals and objectives. They include mission, operational environment, and system concepts. They must be baselined early and not changed unless absolutely necessary. The requirements can include both quantitative and qualitative values of maintainability parameters. Quantitative maintainability requirements are usually the result of maintainability allocations based on system availability and operational timing requirements, with allocations made at each level down to the replaceable module, assembly or component level as needed. Examples of quantitative requirements are shown in Table 2: Maintenance manhours per operating hour (MMH/OH) Mean-Time-To-Repair (MTTR) Mean-Time-To-Restore-System (MTTRS) Fault detection and isolation of sub-systems task times End item change out time Unit removal/installation times Availability Table 2. Examples of Quantitative Requirements They may be established at any, or all, levels of maintenance and can help define maintenance criticalities and reduction of necessary system components. Qualitative requirements are used to accomplish two purposes. First, they address maintainability design features which are vital in achieving the maintainability goals, but cannot be measured. For example, elimination of safetywire/lockwire, standardization of fasteners, use of captive fasteners, and color-coding of electrical wiring are some basic qualitative maintainability requirements used on orbital programs. Second, qualitative requirements are used to meet customer/program requirements and enhance the maintainability characteristics of the system. Examples include specification of common handtools only for organizational and intermediate levels of maintenance, and designing so that only one skill level is required for all organizational level maintenance personnel. (4) EXERCISE PROGRAM CONTROL AND EVALUATION. The maintainability program must be an integral part of the systems engineering process and all design and development activities. Activities include design reviews, development and implementation of methods for assessing maintainability effectiveness, dissemination of maintainability data, and proper implementation of program test and evaluation. Subcontractor/supplier control is also a key area for program evaluation and monitoring. Summary Program management's participation in the development and implementation of sound maintainability practices on NASA programs is extremely important. Whether the program contains ground based systems, or is orbital and beyond, maintainability plays a key role in system operations, providing for increased system effectiveness and availability, and lower life cycle costs. The steps outlined above are guidelines towards success, and can be tailored depending on the type of program. However, the importance of a concurrent engineering approach and the existence of intimate professional relationships between maintainability personnel and other systems engineering disciplines can not be overstated, and existence of these examples will enhance the chance of program success (based on historical experience). References: NASA Handbook 5300.4(1E), quotMaintainability Program Requirements for Space Systems,quot March 10, 1987, NASA Headquarters. Air Force Design Handbook 1-9, quotMaintainability (for Ground Electronic Systems),quot Second Edition, Revision 7, February 25, 1988, United States Air Force Aeronautical Systems Division. quotMaintainability Engineering Design and Cost of Maintainability,quot Revision II, January, 1975, Rome Air Development Center. Reliability, Maintainability, and Supportability (RMS) Guidebook, Second Edition, 1992, Society of Automotive Engineers G-11 International RMS Committee. Maintainability Technique PM-1, quotBenefits of Implementing Maintainability on NASA Programsquot Maintainability Technique PM-3: quotMaintenance Concept for Space Systems.quot | This practice has been used on Hubble Space Telescope, SRB's, Shuttle GSE, and Space Acceleration Measurement System. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
834 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Maintainability Considerations in Extravehicular Activities (EVA) Design: An Astronaut's Perspective |  | Proper EVA design consists of working early and closely with the astronaut(s). Tasks and operations that are desired by the payload/system need to be reviewed early by the crew to ensure that the design is directed toward ease of EVA operability and maintainability. This will increase the probability of EVA mission success. | Extravehicular Activities (EVAs) are very demanding and specialized space flight activities. With the substantial costs from any unsuccessful EVA and the limited opportunities for work-arounds, careful maintainability design of payloads/systems and their operations are essential for complete mission success. | JSC | 12/01/1994 | This Lesson Learned is based on Maintainability Technique number OPS-19 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: A well thought out and properly designed EVA incorporating ease of crew maintainability leads to mission success. Failure to properly address crew maintainability in the EVA design can lead to time-consuming "work-arounds," the inability of the crew to fully complete the desired and/or required tasks, and may expose the crew to unnecessary safety hazards. Implementation Method: Background Astronaut Jerry Ross has participated in the development of almost all of the EVA hardware and procedures for the Space program since 1981. This includes being the support crewman and EVA Capsule Communicator (CAPCOM) for the first manned maneuvering unit (MMU) flight (STS-41B), the Solar Max repair mission (STS-41C), the WESTAR and PALAPA retrievals (STS-51A), and the attempted "flyswatter" activation of the SYNCOM satellite. He has also performed four EVAs on STS-61B and STS-37 to investigate space construction techniques and prototype Space Station EVA equipment and to repair the Gamma Ray Observatory. In addition, he has participated in the testing of advanced space suits since 1984 and in the design of Space Station EVA systems since 1985. Primary Crew Considerations First and foremost, a human being can do almost anything during a space walk that can be done on the Earth's surface. However, working in zero gravity and in a spacesuit necessitates certain design compromises to facilitate the productivity of the spacewalker and to enhance the probable success of the EVA. Two factors that must always be considered when designing EVAs are: (1) that the spacesuit is stiff, restricts visibility and movement, is fatiguing to work in, and all work is done with gloves that significantly reduce tactility and dexterity; and (2) that all things must be tethered (including the crew persons) to preclude them from drifting away and becoming lost. EVA Design Considerations There are several design considerations that must be kept in mind when developing an EVA. Compatibility - EVA equipment and tasks should be designed to be EVA compatible. This will maximize the probability of success, minimize the expense, eliminate EVA hazards, and prevent the need for inefficient, time-consuming operational workarounds due to bad design concepts. Task Design - Tasks should be designed, when possible, so that tools are not required. For example, a doorknob should be used instead of bolts to provide access behind a panel. If tools are required, standard tools and interfaces should be used. This minimizes the number of tools that need to be flown and training required, and enhances the probability of success. Tools should be stowed at work sites when possible to minimize the movement of tools and equipment. Power tools should be used for tasks that are repetitive. This increases productivity and will reduce crew fatigue. For the most part, tasks should be designed so that only one hand is required. This is due to considerations of working in the spacesuit and the frequent requirement to stabilize oneself with the other hand. The maximum force to perform a task should be designed to < 113 N (25 lbs.) and the task should be designed to use large muscle groups whenever possible to reduce crew fatigue. Proven Design Concepts - Proven design concepts should be standardized and used; e.g., double high bolt heads, electrical wing tab connections, and ganged connectors. Designs should also minimize the number of loose parts by using self-retaining fasteners and panel hinges. Good Visual Indicators - Good markings, feedback's, and indicators need to be provided so the EVA crewperson can visually verify that the proper condition has been achieved, such as closed, locked, open, or over-center. Restraints - The right types of restraints, foot restraints, hand-holds, tether points, and translation aids need to be provided in the right locations. Their placement, type, and number must be determined through suited zero-gravity simulations in an underwater facility. Involvement of Safety and Quality Assurance - The Quality Assurance and Safety organizations should be involved in the design process at an early stage. This will help to ensure a good and safe design and help minimize the need for costly redesign. EVA Simulation Water tanks provide an excellent analog simulation capability. They should be used early in the design process with mock-ups of the flight hardware and tasks to be performed. Astronaut participation in these early water tank evaluations is essential to a cost-effective and efficient design process. The mock-up should be upgraded as the design matures and the fidelity of the mock-up to the flight hardware can be critical to the success of an EVA. Functional Testing and Fit Checks Functional tests of EVA hardware and tools in a thermal/vacuum chamber have proven to be mandatory. Many design changes have resulted from such tests. Fit checks of all flight hardware to all flight (and flight spares) hardware and tools are mandatory. Develop a matrix of all interfaces and perform physical fit checks. Numerous on-orbit problems have been avoided through this process. Space Shuttle EVA Operations For the Space Shuttle, EVA is at least a three person task (two EVA crew members and a third crewman on the aft flight deck to observe and act as an EVA activity manager). This third crewperson or activity manager serves as a time line prompter, procedure reader, picture taker, and keeps track of all of the loose hardware items. Crew coordination is essential when EVA operations are combined with remote manipulator system operations and Orbiter operations. Use conservative EVA timelines so that there will be time to deal with any unanticipated problems or delays. Convenient break points should be developed so that hardware can be left in a safe and stable configuration between EVAs. Backup procedures should be developed to overcome significant problems should they occur on orbit. Such preflight work saved the Solar Max repair mission and the WESTAR and PALAPA satellite retrievals. Develop and maintain good documentation of flight hardware configurations. Closeout (prelaunch) photographs are important to the EVA design and development process. The lack of good closeout photos and other detailed information on the "as flown" hardware configuration almost caused the failure of both the Solar Max and WESTAR/PALAPA EVA missions. | This practice has been used on Shuttle Orbiter Missions with EVA's. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
835 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Benefits of Implementing Maintainability on NASA Programs |  | Maintainability requirements for programs that require ground and/or in-space maintenance and anomaly resolution have to be established early in the program to be cost effective. Lack of management support to properly fund maintainability activities up-front can result in increased program risk. Including maintainability in the design process will greatly reduce the number of operational problems associated with system maintenance, improve the availability of the system, and reduce program costs. | Programmatic provisions for ease of maintenance greatly enhance hardware and software system operational effectiveness for both in-space and ground support systems. | JSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number PM-1 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Benefit: Implementation of maintainability principles can reduce risk by increasing operational availability and reducing lifecycle costs. Provisions for system maintainability also yields long term benefits that include decreased maintenance times, less wear and tear on project personnel, and extended useful life of ground and in-space assets. Implementation Method: Over the years, NASA has successfully launched manned spacecraft to the moon, sent unmanned probes into the outer reaches of the solar system, and developed reusable space systems for earth orbitable missions. NASA also performs valuable atmospheric research and development of ground systems, all of which contain complex hardware and software that must be maintained during all phases of operations and in multiple environments. However, in this age of shrinking budgets, doing more with less is becoming the overall programmatic theme. NASA space flight programs are being driven towards more automated, compact designs in which fewer support resources will be available than in past programs. This technique will outline the benefits of implementing well-defined and user-friendly principles of maintainability on all NASA programs, regardless of the operational scenario. Emphasis is placed on how and why a maintainability program can enhance the effectiveness of a system and its overall operation. It must be noted, however, that maintainability of unmanned deep space systems provides a different set of challenges. Maintainability is defined in NASA Handbook 5300.4(1E), quotMaintainability Program Requirements for Space Systems,quot as: quotA measure of the ease and rapidity with which a system or equipment can be restored to operational status following a failure,quot and is consistent with NHB 7120.5, quotManagement of Major Systems and Projects.quot It is a characteristic of equipment and installation, personnel availability in the required skill levels, adequacy of maintenance procedures and test equipment, and the physical environment under which maintenance is performed. Applying maintainability principles will enhance the systems readiness/availability through factors such as visibility, accessibility, testability, simplicity, and interchangeability of the systems being maintained. Using maintainability prediction techniques and other quantitative maintainability analyses can greatly enhance the confidence in operational capabilities of a design. These predictions can also aid in design decisions and trade studies where several design options are being considered. Also, cost savings and fewer schedule impacts in the operational phase of the program will result due to decreased maintenance time, minimization of support equipment, and increased system availability. Another benefit is a decrease in management overhead later on in the life cycle as a result of including maintainability planning as a full partner in early maintenance/logistics concept planning and development. PROGRAMMATIC BENEFITS Maintainability Program Implementation Project management is responsible for implementing maintainability on a program via development of specific requirements for cost effective system maintenance in the early phases of the life cycle. Trade studies of the impacts of maintainability design on life cycle costs are used to evaluate the balance between cost of designing to minimize maintenance times and the associated increase in system availability resulting from the decrease in maintenance times. Usually, the up-front cost of designing in maintainability is much less than the cost savings realized over the operational portion of the life cycle. Several programs have opted to accept the short-term cost savings by deleting maintainability requirements in the design phase, but the associated increase in maintenance and support costs incurred during operations would have been significant. An example of this is the Space Station Program, which had deleted requirements for on-orbit automated fault detection, isolation and recovery (FDIR), saving the program up-front money. However, the alternative concept was to increase the mission control center manpower during operations for ground based FDIR, but this presented a significant cost increase when averaged over the life cycle. Another positive example is the Hubble Space Telescope Program. Maintainability concepts were included early in the life cycle, where maintenance planning and optimum ORU usage in design saved the program significant costs when on-orbit repairs became necessary. Figure 1 accentuates the cost tradeoffs between introducing maintainability concepts into a program and the time at which they are introduced. These tradeoffs can mean the difference between a successful maintainability program and a costly, less effective one. [D] Figure 1. Effect of Implementing Maintainability Program vs Phase The NASA systems engineering process should require that the system be designed for ease of maintenance within it's specified operating environment(s), and should ensure that the proper personnel (design and operations maintainability experts) and funds are committed to development of the process to achieve maximum program benefit. Program schedule will be affected by lack of system maintainability because necessary ground support will increase, maintenance times will be higher, necessary maintenance actions will increase, EVA will be at a premium, and system availability will be lower. Table 1 highlights key program benefits. Enhanced System Readiness/Availability Reduced Downtime Supportable Systems Ease of Troubleshooting and Repair System Growth Oppertunities Hardware/Software Modifications Interchangeability Modular Designs Decreased Storage Considerations Reduced Maintenance Manpower Reduced Operational Costs Compatibility with other Programs Reduced Management Overhead Table 1: Maintainability Programmatic Benefits Maintenance/Logistics Concept Development Development of the maintenance and logistics concepts for a program early in the life cycle must include the maintainability characteristics of the design. The maintenance concept is a plan for maintenance and support of end-items on a program once it is operational. It provides the basis for design of the operational support system and also defines the logistics support program, which will determine the application of spares and tools necessary for maintenance. The use of other logistic resources, such as tools and test equipment, facilities and spare parts, will be optimized through including maintainability planning as a key operational element. Derivation of these plans early on in the life cycle solidifies many operational aspects of the program, thus allowing for integrated design and support planning development. MAINTAINABILITY DESIGN BENEFITS Visibility Visibility is an element of maintainability design that provides the system maintainer visual access to a system component for maintenance action(s). Even short duration tasks such as NASA space shuttle orbiter component inspection can increase downtime if the component is blocked from view. Designing for visibility greatly reduces maintenance times. Accessibility Accessibility is the ease of which an item can be accessed during maintenance and can greatly impact maintenance times if not inherent in the design, especially on systems where on-orbit maintenance will be required. When accessibility is poor, other failures are often caused by removal/disconnection and incorrect re-installation of other items that hamper access, causing rework. Accessibility of all replaceable, maintainable items will provide key time and energy savings to the system maintainer. Testability Testability is a measure of the ability to detect system faults and to isolate them at the lowest replaceable component(s). The speed with which faults are diagnosed can greatly influence downtime and maintenance costs. For example, deficiencies in Space Shuttle Orbiter testability design have caused launch delays, which translate to higher program costs. As technology advances continue to increase the capability and complexity of systems, use of automatic diagnostics as a means of FDIR substantially reduces the need for highly trained maintenance personnel and can decrease maintenance costs by reducing the erroneous replacement of non-faulty equipment. FDIR systems include both internal diagnostic systems, referred to as built-in-test (BIT) or built-in-test-equipment (BITE), and external diagnostic systems, referred to as automatic test equipment (ATE), test sets or off-line test equipment used as part of a reduced ground support system, all of which will minimize down-time and cost over the operational life cycle. Simplicity System simplicity relates to the number of subsystems that are within the system, the number of parts in a system, and whether parts are standard or special purpose. System simplification reduces spares investment, the enhances the effectiveness of maintenance troubleshooting, and reduces the overall cost of the system while increasing the reliability. For example, the International Space Station Alpha program has simplified the design and potentially increased the on-orbit maintainability of the space station, thus avoiding many operational problems that might have flown with the Freedom Program. One example is the Command and Data Handling Subsystem, which is the data processing backbone for the space station. Formerly, the system consisted of several different central processing units, multiple level architecture, and several different network standards. The new design comprises only one network standard, one standard CPU, and a greatly reduced number of orbital replaceable units (ORU's). Maintainability design criteria were definite factors in the design changes to this space station subsystem. Reduced training costs can also be a direct result of design simplification. Maintenance requires skilled personnel in quantities and skill levels commensurate with the complexity of the maintenance characteristics of the system. An easily maintainable system can be quickly restored to service by the skills of available maintenance personnel, thus increasing the availability of the system. Interchangeability Interchangeability refers to a component's ability to be replaced with a similar component without a requirement for recalibration. This flexibility in design reduces the number of maintenance procedures and consequently reduces maintenance costs. Interchangeability also allows for system growth with minimum associated costs, due to the use of standard or common end-items. Human Factors Human factors design requirements also should be applied to ensure proper design consideration. The human factors discipline identifies structure and equipment features that impede task performance by inhibiting or prohibiting maintainer body movement, and also identifies requirements necessary to provide an efficient workspace for maintainers. Normally, the system design must be well specified and represented in drawings or sketches before detailed anthropometric evaluation can be effective. However, early evaluation during concept development can assure early application of anthropometric considerations. Use of these evaluation results leads to improved designs largely in the areas of system provisions for equipment access, arrangement, assembly, storage, and maintenance task procedures. The benefits of the evaluation include less time to effect repairs, lower maintenance costs, improved supportability systems, and improved safety. Summary Implementation of maintainability features in a design can bring about operational cost savings for both manned and unmanned systems. The programmatic benefits of designing system hardware and software for ease and reduction of maintenance are numerous, and can save a program, as seen with NASA's Hubble Space Telescope. Maintenance in a hostile, micro-gravity environment is a difficult and undesirable task for humans. Minimal exposure time to this environment can be achieved by implementing maintainability features in the design. The most successful NASA programs have been those which included maintainability features in all facets of the life cycle. Remote system restoration by redundancy management and contingency planning is particularly essential to assuring mission success on projects manned intervention is either undesireable or impractical. References: NASA Handbook 5300.4(1E) quotMaintainability Program Requirements for Space Systems,quot March 10, 1987, NASA Headquarters. NASA Handbook 7120.5, quotManagement of Major Systems and Projects,quot November 1993, NASA Headquarters Air Force Design Handbook 1-9 quotMaintainability (for Ground Electronic Systems),quot Second Edition, Revision 7, February 25, 1988, United States Air Force Aeronautical Systems Division. quotMaintainability Engineering Design and Cost of Maintainability,quot Revision II, January 1975, Rome Air Development Center. Reliability, Maintainability, and Supportability (RMS) Guidebook, Second Edition, 1992, Society of Automotive Engineers G-11 International RMS Committee. MIL-STD-470B quotMaintainability Program for Systems and Equipment,quot May 30, 1989, Department of Defense | This practice has been used on International Space Station Program, Hubble Space Telescope, SRB's, Shuttle GSE, Space Acceleration Measurement System, and others. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/19/2000
836 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Booster (SRB) Refurbishment Practices |  | Through the past decade of maintaining the SRB by refurbishing the structures and components, MSFC and its contractors have developed and implemented successful refurbishment specifications and procedures that have proven their effectiveness. For example, failure to adhere to the proven practice of refurbishing recovered hardware from salt water impact can result in unacceptable performance, scrapping of otherwise usable hardware, expenditure of unnecessary resources, and possible schedule delays. | Engage in refurbishment activities to rebuild and prepare for reuse of the Solid Rocket Boosters (SRB's) after each Space Shuttle Orbiter launch. These refurbishment activities include: (1) inspection, (2) reworking of anomalies to specification, (3) material review board (MRB) acceptance or scrapping, (4) cleaning, (5) corrosion protection and prevention, (6) scheduled part replacement, (7) test and checkout, and (8) preparation for storage or return to flight buildup. | MSFC | 11/30/1994 | Benefit: This Lesson Learned is based on Maintainability Technique number OPS-01 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Implementation Method: Refurbishment of SRB components is cost effective and conserves resources. This allows for reuse of SRB's, thus saving money for the program versus building new SRB's for each launch. Solid Rocket Booster (SRB) Refurbishment encompasses the activities required to return the reusable SRB component to a flightworthy condition after SRB ignition, liftoff, and flight; separation from the external tank; descent (free fall and parachute); ocean impact; and retrieval. When the decision was made to recover and reuse the SRB hardware, a design team was organized to formulate the maintainability criteria for a reusable booster. The SRB Flow Chart for Maintainability is shown in Figure 1. The maintainability design team produced the Solid Rocket Booster Maintainability Design Criteria Document (reference 1), a document that was used by designers as they conceived each design feature, performed the necessary tradeoffs of the design parameters, and made other design and product engineering decisions. The design team included maintainability as a design goal and incorporated the desired maintainability features into components of the end item throughout the design process. Maintainability factors that were considered during the design of the SRB are shown in Table 1. [D] Figure 1. SRB Flow Chart for Maintainability Accessibility Commonality of Fasteners Electrical Subsystem Installation and Removal Thrust Vector Control (TVC) Subsystem Installation and Removal Markings and Color Coding Unitization of Subsystems Irreversibility of Connectors Tool and Equipment Design Spares Provisioning Table 1. SRB Maintainability Factors Design Process Considerations Table 2 lists typical maintenance actions that were considered during the design process. The SRB was designed to withstand launch, water impact, and towback environments, incorporating the capability of 10 flights for the parachutes; 20 flights for electrical/electronic components, Thrust Vector Control (TVC) components, and SRM components; and 40 flights for the structures. SRB structures are typically welded and/or mechanically fastened aluminum except for the external tank attach ring, which is mechanically fastened steel. All aluminum structural assemblies are first painted and then coated with an ablative insulation. The SRM segments are forged D6AC steel. All structural components are cleaned and/or alodined as appropriate, before being primed and top coated with paint. The mechanically fastened aluminum and steel structural components are designed to be protected from salt water intrusion by applying sealant between adjoining surfaces, installing the fasteners with sealant, torquing the fasteners, and applying a fillet of sealant along the edge of brackets where they join the main structure. The electronic/electrical components exposed to salt water are sealed, and the external surfaces of these components are painted. The TVC hydraulic system is a closed-loop system that does not permit the intrusion of sea water. The SRM segments' external surfaces are protected with an epoxy paint finish, and the internal surfaces are protected by the propellant insulator that is bonded to the inside surfaces of the SRM segments. Areas not protected with paint or bonded-on insulation are protected with a water-repellent grease. Inspection Troubleshooting Calibration and Adjustment Repair Verification Table 2. Maintenance Actions Specific Improvements Typical areas of the SRB that have been redesigned or modified as a result of trouble areas found during recovery and refurbishment are discussed below: Galvanic corrosion occurred in the aft skirt of the first few SRB's recovered. To prevent this from recurring the design team added a zinc coating to selected metal components, and bolted anodes (Zinc bars) to some components of the TVC system. The aft skirts of the first few SRB's experienced water impact damage. The corrective action included the addition of gusset reinforcements to the structural rings. Foam was sprayed on the interior of the aft skirt to protect the reinforcement rings and the TVC components. Impact force with the water was reduced by increasing the diameter of the main parachutes from 115 feet to 136 feet. The larger parachutes decreased the SRB's water impact velocity from 88 ft/sec to 75.5 ft/sec (60 mph to 51.5 mph, respectively). During initial teardown and inspection, water and corrosion were found between the mating surfaces of structural members. To correct this problem, the sealant application specifications were modified to require the sealant to be applied to both surfaces before joining. To eliminate potential water entry into the forward skirt, the following areas were modified or redesigned: The aft seal on the forward skirt was changed from a rectangular to a quotDquot configuration to allow better contact between the forward skirt and the forward dome of the SRM. A fillet of sealant was added between the access door and the surrounding structure after final close-out of the forward skirt. Sealant was added to the mating surfaces and the installation bolts of the separation nut housing for the main parachute attach fittings. The following practices improved maintainability, parachute deployment, and parachute inflation: To avoid abrasive damage that occurred during main parachute deployment, foam and ablative material were added to portions of the frustum and the main parachute support structure. To avoid damage to the parachutes during deployment, the parachutes are now packed in a circular pattern rather than the previous zig-zag pattern. The opening at the top of the main parachute canopy was decreased in diameter to allow quicker inflation of the parachute. After every flight electronic components were being returned to the vendor for refurbishment. After refurbishment, acceptance test procedures (ATP) were performed, including vibration and thermal testing. The vibration level of these tests caused the remaining life of the component to be reduced. To prevent the excessive expenditure of components' lifetime (except for the range safety system components) vibration and thermal testing has been eliminated during normal turnaround. The constant improvement of electronic parts by the manufacturer presents a unique problem to the SRB refurbishment effort because the improved parts are often not interchangeable with their predecessors. A sufficient quantity of spare parts must be procured to meet logistics requirements until the components are redesigned to use the improved parts. Typical Refurbishment Procedures Figure 2 depicts the SRB flight configuration. After approximately 125 seconds into the Shuttle flight, the SRB's are jettisoned from the external tank. During reentry, the nose cap is jettisoned (it is not recovered), deploying the drogue parachute. After the SRB is stabilized in a vertical position, the frustum is jettisoned and descends into the ocean. Its descent is held to a safe velocity by the drogue parachute. In the meantime, the jettisoning of the frustum deploys the three main parachutes, lowering the remaining portion of the SRB into the ocean. Once in the ocean, the parachutes (which are jettisoned at water impact) and the frustum are removed by the recovery team and positioned onto the recovery vessel. A plug is inserted into the SRM nozzle throat and the SRB is dewatered. Removal of the water from the SRB allows the SRB to be positioned from a vertical position to a horizontal position. The SRB is then towed to the disassembly area dock. [D] Figure 2. SRB Flight Configuration At dockside, the SRB is lifted from the water and placed on dollies. The SRB pyrotechnics are disarmed, the TVC fuel system is depressurized, and an assessment team inspects and documents anomalies that may have occurred during flight. Then the SRB is washed with a detergent solution in a semiautomated wash facility. The aft skirt is removed and routed to the TVC disassembly facility. Table 3 lists a typical flow sequence for major structure refurbishment. After the aft skirt is removed, the remainder of the SRB is routed to the disassembly facility. Tow SRB from water impact area to dock Remove SRB from ocean, Rinse with potable water. Place SRB on transporter. Safe SRB Ordnance and Hydrazine Systems. Assessment Team Inspection. Wash SRB with detergent solution and rinse. Remove aft skirt assembly. TVC refurbishement facility. Remove TVC Components. Disassembly area; remove components. Critical dimension check. Thermal protection system removal, robotic hydrolaser. Inspect, Visual and NDE (XRAY and Ultrasonics). Rework, Touch-up paint (repaint every fifth use.) Inspect and identify. Preflight storage. Table 3. Typical Structure Refurbishment Flow As the SRB components are removed, they are identified by attaching a metal tag with their part number and dispositioned per the Predisposition List for SRB Flight Hardware (reference 2). The SRB component is then routed to the refurbishment area where a prepared refurbishment procedure document is attached to the part. The part is reworked to conform to the Refurbishment Engineering Specification. This specification lists the requirements for refurbishing each component to flightworthy condition before it is returned to storage. The SRM segments are disassembled in the disassembly facility at dockside, placed on rail cars, and transported to the SRM contractor located in Utah. At the contractor's plant, the segments are off-loaded and routed to refurbishment areas. All segments that are to be reused must meet the requirements of specification STW7-2744 (reference 3). If segment dimensions fall outside the acceptable requirements of this specification, an individual analysis is required to determine the effect on the structural and sealing capability before reusability is determined. All documented nonconformances are reviewed to determine if the condition of the hardware has changed. The most critical areas to be reviewed are case membrane thickness, vent port and leak port threaded areas and sealing surfaces, and aft segment stiffener stubs. No surface defects (corrosion, pitting, scratches, noncrack-like flaws, etc.) deeper than 0.010 inch are permitted. All segments are hydrotested to 1.125 times the Maximum Expected Operating Pressure and magnetic-particle inspected. Major Structures (Frustrum, Forward Skirt, Aft Skirt, External Tank Attach (ETA) Ring, Solid Rocket Motor (SRM) Segments, etc. Electronic Components: Integrated Electronic Assembly (IEA), Integrated Receiver Decoder (IRD), etc. Electrical Cables. TVD Components Auxiliary Power Unit (APU), Hydraulic Pump, Hydraulic Reservoir, Fuel Service Module (FSM), etc. Parachutes Table 4. Types of Hardware That Have Been Successfully Refurbished References: NASA/MSFC: Solid Rocket Booster Maintainability Design Criteria Document, SE-019-022-2H, NASA/Marshall Space Flight Center, AL. USBI: Predisposition List for SRB Flight Hardware, 10PLN-0027, USBI, United Technologies, Huntsville, AL. Thiokol: Space Shuttle SRM Refurbished Case Acceptance Criteria, STW7-2744, Thiokol Corporation, Space Operations, Brigham City, Utah. NASA/MSFC: Sealing of Faying Surfaces Subject to Sea Water Exposure on the SRB Excluding the SRM, 10A00526, NASA/Marshall Space Flight Center, AL. NASA/MSFC: Sealing of Fasteners Subject to Sea Water Exposure on the SRB Excluding the SRM, 10A00527, NASA/Marshall Space Flight Center, AL. NASA/MSFC: Protective Finishes for Aluminum and Steel Alloys Subject to Seawater Exposure on the SRB Excluding the SRM, 10A00528, NASA/Marshall Space Flight Center, AL. NASA/MSFC: Solid Rocket Booster Flight Hardware Ground Operations Plan, SE-019-040-2H, NASA/Marshall Space Flight Center, AL. NASA/MSFC: Solid Rocket Booster Flight Hardware Refurbishment Requirements, SE-019-050-2H, NASA/Marshall Space Flight Center, AL, Systems Analysis and Integration. Thiokol: Space Shuttle SRM, Requirements and Acceptance for Refurbishment Nozzle Metal Components, STW7-2863, Thiokol Corporation, Space Operations, Brigham City, Utah. Thiokol: Space Shuttle SRM, Process Finalization Requirements for Nozzle Metal Hardware, STW7-3450, Thiokol Corporation, Space Operations, Brigham City, Utah. Thiokol: Space Shuttle SRM, Acceptance Criteria, New and Modified Case, STW7-3489, Thiokol Corporation, Space Operations, Brigham City, Utah. Thiokol: Space Shuttle SRM, Acceptance Criteria for Refurbished Igniter Chambers and Igniter Adapter, STW7-3861, Thiokol Corporation, Space Operations, Brigham City, Utah. Thiokol: Refurbishment and Acceptance Criteria for Redesigned Barrier-Booster Assembly, STW7-3888, Thiokol Corporation, Space Operations, Brigham City, Utah. Thiokol: Manufacturing Plan for Space Shuttle Redesigned Solid Rocket Motor (RSRM) Project, TWR-10341(CD), Prepared for NASA by Thiokol Corporation. Brigham City, Utah. USBI: 10MNL-0028, Solid Rocket Booster Pictorial Representations Handbook, USBI, United Technologies, Huntsville, AL. USBI: Frustum/Aft Skirt Disassembly Requirements, 10REG-0032, USBI, United Technologies, Huntsville, AL. USBI: Refurbishment Engineering Specifications For Space Shuttle Solid Rocket Booster Assembly Project, 10SPC-0131, USBI, United Technologies, Huntsville, AL. | This practice has been used on Space Shuttle Solid Rocket Booster (SRB), Space Shuttle Solid Rocket Motor (SRM). | N/A |  |  | Public | Not Specified |  | 04/19/2000
823 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Modal Testing: Measuring Dynamic Structural Characteristics |  | Modal testing is used to verify analytical models or FEMs of a structure or payload. Failure to perform this testing could cause much greater errors and uncertainty in these analytical models. This could lead to failure in a structure or payload. | Modal testing is a structural testing practice that provides low levels of mechanical excitation to a test structure and measures its response to that excitation. This response is then analyzed to experimentally determine the dynamic structural characteristics of the test subject. Modal testing may be performed on all suitable space structures including those associated with the Orbiter and the Space Station. | JSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1440 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Specifically, when used in the analysis of Orbiter payloads, the dynamic structural characteristics of a payload created by modal testing can be correlated with finite element models (FEM's) to predict the payloadís responses to launch and landing environments as well as any other conditions the spacecraft may encounter. This correlation analysis can also be used to perform coupled loads analyses to ensure that the payload will not have any adverse dynamic effects on the Orbiter. Similar benefits are also derived through modal testing of other space structures. Implementation Method: I. Introduction Modal testing is an experimental means of determining the dynamic characteristics of a structure through mechanical excitation, created either by vibrational or impact methods. This excitation is done to create the mode shapes of the test article which are measured by accelerometers. The data from these accelerometers is then analyzed to develop the dynamic structural characteristics of the test article. The results from the modal testing can then be used to verify the FEM's of the structure being studied. Once the FEM's have been correlated to the modal tests, the results can be used to predict the responses of the structure to any future loads that may be encountered. For Orbiter payload analysis, this correlation can also be used to perform coupled loads analyses to ensure that a payload will not have any adverse dynamic effects on the Orbiter. II. Types of Modal Testing There are three types of Modal testing accomplished at JSC. These are (1) resonant frequency checks, (2) quotminiquot modal survey tests, and (3) full modal survey test. Resonant Frequency Checks. The resonant frequency check is the modal test lab's version of the General Vibration Laboratory's (GVL's) sine sweep test and is the simplest of the tests. As with the sine sweep, the only purpose of this test is to determine the frequencies at which resonances occur. Normally, not enough data is taken to develop either modal shapes or damping values. The benefit of this check over the sine sweep is that all axes can be excited at once, and the modal test lab data acquisition system is capable of taking many more channels of data than the data acquisition system in the GVL. This test requires little laboratory time (less than 1 week) to perform (including test article setup, instrumentation, and data reduction) and can also be used to screen a structure to determine if a full modal survey is needed. Excitation is usually done with a quotsmartquot hammer. quotMiniquot Modal Survey Test. The quotminiquot modal survey test is called this because it is not as extensive as the full modal survey test. The data taken is usually quotexploratoryquot in nature and leads to development of mode indicator functions which determine the frequencies at which mode shapes are generated. Less data is normally taken, curve fitting is not performed, and damping values are not developed as compared to the full modal survey testing. The data generated is useful in verifying existing FEM's, but not enough data is taken to perform FEM correlation. Excitation is generally by a quotsmartquot hammer. This test requires little laboratory time (approximately 1 week) to perform (including test article setup, instrumentation, and data reduction). Full Modal Survey Test. The full modal survey test develops the most data and is the most accurate and detailed of the three types of tests. Frequencies, mode shapes, and damping values are developed. Curve fits are performed on the frequency response functions. Electro-dynamic shakers are generally used; however, quotsmartquot hammers may be used in the preliminary phases of testing. The complete tests may take as long as 7 weeks to perform (including test article setup, instrumentation, data reduction, presentation of results, and final report preparation). The final data can be correlated to FEMs. III.Methods of Excitation Excitation of the test subject can be created either by an electro-dynamic shaker or a quotsmartquot hammer. The electro-dynamic shaker can be controlled to transfer random vibration or sinusoidal vibration to the test subject. The electro-dynamic shaker is preferred over the quotsmartquot hammer in the full modal survey tests because it can be more precisely controlled in regard to input force level and input frequency range. Excitation is transferred from the electro-dynamic shaker to the test article by means of a stinger which is designed to be very stiff axially, but very flexible laterally. A force transducer is included in the stinger to measure the input force, and reference accelerometer is placed on the test article next to the stinger. The quotsmartquot hammer is an instrumented hammer used to provide impact excitation to a test article. A hammer requires less set-up time than a shaker and is good for minimum testing. It can also provide quick preliminary testing of many different locations on the test article in order to identify the location of the best shaker placement. IV.Procedures in Modal Survey Testing In full modal testing surveys at JSC, an excitation is applied to a structure and the input excitation and responses in the form of time histories are measured. These responses are then processed by a data acquisition computer to produce the functions from which modal functions are developed. The block diagram of a full modal survey system as shown in Figure 1 consists of (1) an excitation mechanism, (2) a transduction system to measure the various responses (i.e., accelerometers, force transducers), and analyzer. The input and response output from the test article go through the signal conditioning amplifiers to the analyzer which measures the various signals developed by the transducers which consist of force time histories from the input force transducer(s) and acceleration time histories from the output accelerometer(s). The first stage in analyzing the data, after the raw data has gone through the anti-biasing filters, is the conversion of the time histories from analog to digital signals. The data acquisition computer performs a fast Fourier transform (FFT) on the time histories to convert them from a time to a frequency domain. The data acquisition computer also calculates the discrete Fourier transform (DFT) for a full set of spectral lines. The result of this transform is then used to produce modal survey testing output products such as frequencies, mode shapes, and damping values associated with the test article. [D] Figure 1. Block Diagram of a Full Modal Survey System --- Here V. Modal Survey Non-Linear Testing Occasionally, test articles are found to be non-linear, i.e., their responses change with the level of excitation input. In order to test these structures, drive levels must be selected for excitation which encompass the non-linear response range of the test subject or if this range is too large, to encompass the range of anticipated flight environments of the test subject. Technical Rationale: Modal testing is an experimental technique for determining dynamic characteristics of a structure. Testing is performed by providing an excitation to the structure and measuring the responses which are then used to develop the dynamic characteristics of the structure through testing and comparison to FEM's. Unlike environmental vibration testing which is an end unto itself, modal testing is a means to an end; i.e., modal testing is used to verify the FEMs of a structure which can be used as predictors of the structure's dynamic characteristics over a wide range of environmental conditions. The use of modal testing for verifying FEMs produces much greater confidence in the FEMs as ultimate predictors of structural characteristics. References: Ewins, D. J., Modal Testing: Theory and Practice, John Wiley & Sons, Inc., 1984. Bendat, J. S., Piersol, A.G., Random Data Analysis and Measurement Procedures, 2nd Edition, John Wiley & Sons, Inc., 1986. Halpin, Dennis B., Modal Testing Special Topics, JSC 27161, July 1995. Reliability Preferred Practice PT-TE-1406 Sinusoidal Vibration Reliability Preferred Practice PT-TE-1407 Assembly Acoustic Tests Reliability Preferred Practice PT-TE-1413 Random Vibration Testing Reliability Preferred Practice PT-TE-1419 Vibroacoustic Qualification Testing of Payloads, Subsystems, and Components Reliability Preferred Practice PT-TE-1420 Sine-Burst Load Test | This practice has been used on Orbiter, Orbiter payloads, Space Station and other space structures. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
822 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Design of a Small Apparatus for Improved Vibration/Thermal Testing |  | The impact of non-practice is that the larger environmental chamber could be used which would increase costs and time to perform vibration/thermal testing. This would expose the shaker armature to more weight and cold soak temperature extremes. The additional weight can cause armature failure while the lower temperatures can cause armature brittleness and subsequent failure and the higher temperatures can cause vibration shaker shutdown. | A small test fixture has been specifically designed for conducting vibration/thermal tests on small test specimens such as ignitors and detonators. This test fixture creates much smaller loads and less hostile thermal environments for the vibrator table armature thus creating a more reliable test set up. In addition, this small test fixture provides much more rapid and accurate thermal transfer to a test specimen which results in more data points for the same test times and more accuracy and reliability in the test data. | JSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1442 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: This new environmental fixture is much smaller than other larger, bulky environmental fixtures that require long soaking times for even temperature stability over the entire fixture and sample. The smaller fixture has less weight and requires little temperature soaking time for obtaining fixture and specimen temperature stability. This improves the reliability of the test set up as low, long term soaking temperatures can cause armature brittleness and subsequent failure while long term heat soaking of the armature can cause vibrator shaker shutdown. In addition, more data points can be obtained in a shorter period of time with better thermal resolution. Implementation Method: Two small thermal control and conditioning test apparatus' have been developed and utilized in vibration/thermal testing at JSC for NASA Standard Initiator (NSI) and NASA Standard Detonator (NSD) explosive components. These devices are applicable to all fixturing designs which utilize a flow through manifold for the thermal medium. Although these fixtures were designed specifically for vibrating explosive components under extreme conditions the application could be altered by fabricating fixture(s) to incorporate any type device to be thermally conditioned and/or vibrated. Photographs of these apparatus' are shown in Figures 1 and 2. Each are fabricated out of aluminum and differ in several ways. Each is fabricated for its appropriate thread type, mounting hole pattern and thermal medium flow manifold. In addition, the NSI fixture has a cover plate where the NSD fixture does not. The reason for this is to minimize the amount of mass the armature has to move during the NSD vibration profile. One main difference between the two fixtures is the transition of the explosive components from one axis to another. [D] Figure 1. Fixture for NSI Thermal/Vibration Testing [D] Figure 2. Fixture for NSD Thermal/Vibration Testing In each apparatus, liquid nitrogen is used for cold conditioning the explosive component during vibration testing and is controlled as shown in a block diagram in Figure 3. The system is capable of establishing thermal fixture temperatures as low as -310 degrees F with a temperature gradient across the fixture not exceeding 5 degrees F. A glycol/water solution is used for hot temperature conditioning. The solution is circulated through the fixture(s) with a Neslab high temperature bath and control circuit with system capabilities of up to 400 degrees F and thermal gradients not exceeding 3 degrees F. Both apparatus' utilize a phenolic insulator plate to minimize thermal soaking to the armature and an armaflex cap to minimize thermal losses. This prevents soak-out and shutdown problems associated with the armature. [D] Figure 3. Block Diagram of Thermal Control of Cooling and Heating Medium Because of the dynamics of the NSI vibration profile a secondary fixture was used to transition from one axis to another. This fixture allows the transition of the thermal fixture from a horizontal plane to a vertical one. This secondary transition fixture is pictured in Figures 4 and 5 with the NSI thermal/vibration fixture attached in the X and Y vibration planes, respectively. Because of the dynamics of the NSD vibration profile on the other hand, the amount of mass resting on top of the armature is critical, since the profile is demanding close to full power output of the vibration amplifier system. Thus the fixture was designed to have a transition from one axis to another of the explosive components without any extra fixturing. This is done by utilizing both the top and side of the fixture to accomplish the X and Y axes. A 0.018 inch thick shim is used to offset the explosive devices 90 degrees to accomplish the Z axis. [D] Figure 4. Secondary Transition Fixture with NSI Thermal/Vibration Fixture Attached in X Vibration Plane [D] Figure 5. Secondary Transition Fixture with NSI Thermal/Vibration Fixture Attached in Y Vibration Plane Technical Rationale: A thermal environmental chamber has been previously used at JSC to thermally condition explosive components that could be mounted to a shaker head and vibrated in three axes (X, Y, & Z). These prior set-ups had utilized a bulky and heavy environmental chamber which required structural supports and bracing to hold it over the shaker head. Liquid nitrogen was used as a cold temperature conditioning media and electric heaters were used for hot temperature conditioning. The environmental chamber had a large air space which created temperature gradients throughout the chamber. Therefore, obtaining a stable thermal condition for the test subject required a great deal of thermal quotsoakingquot time.The time requirement for conditioning the test subject was also increased at cold temperatures because of the need for more thermal accuracy and stability in this test range. This thermal quotsoakingquot acted as a detriment to the shaker armature components which also quotsoaked outquot to the required temperature causing them to become brittle and more susceptible to damage and/or breakage during the vibration process. Also, when conditioning the test component to a hot condition, the armature ran hotter. If the cooling capacity of the shaker system couldn't keep up with the influx of heat to the armature during the quothotquot test, then the system over-temperature protect circuit shut the vibration test down. All these limitations and inconveniences of the larger environmental chamber led to the development of the smaller, controllable, environmental fixture for vibration/thermal testing which is the subject of this practice. References: Reliability Preferred Practice PT-TE-1402, Thermal Cycling Reliability Preferred Practice PT-TE-1405, Powered-On Vibration Reliability Preferred Practice PT-TE-1406, Sinusoidal Vibration Reliability Preferred Practice PT-TE-1413, Random Vibration Testing | This practice has been used on Vibration/Thermal Testing of the NASA Standard Initiator (NSI) and the NASA Standard Detonator (NSD). [NOTE: Testing of armed NASA Standard Initiators or NASA Standard Detonators is a highly dangerous undertaking and proper safety precautions should always be observed. For more safety information on testing these devices, please contact the Johnson Space Center (JSC)]. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
821 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Automatic Transfer Switches (ATS) In Critical Applications |  | The consequences of non-practice can lead ultimately to loss of life, and secondarily property. The very nature of the critical systems which drive the requirement to use ATS to guard against loss of power demand maximum reliability. | This practice provides proven techniques for enhancing the reliability of Automatic Transfer Switches (ATS) used in critical applications. Systems which require the use of ATS may be optimized for fail-safe operation using worst-case design techniques and good maintainability/preventive maintenance practices. The probability of internal ATS failures which could result in loss of power to the load can be minimized by giving particular attention to the ATS transfer methods, power-switch types used, and regular attention to the health of the equipment. | KSC | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1256; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The major benefit of these design considerations is the greater assurance that loss of power to critical loads and the resulting consequences will not occur. Achieving optimum reliability is of paramount importance in systems that protect life and property. Along with the increase in the reliability of the ATS that is achieved, usually little or no additional design cost is required. Implementation Method: The implementation of these techniques has resulted in the elimination of critical failure modes in Automatic Transfer Switches used in the KSC Shuttle Landing Facility 60 Hertz Power System supporting critical landing aids. Increased system reliability and reduced maintainability costs are inherent features of these practices. Technical Rationale: For critical 60 Hertz Power applications which must use Automatic Transfer Switches (ATS) to provide redundant power sources, it is important to examine the following three design considerations which serve to minimize the probability of ATS failures that could result in loss of power to the load. The first of the three considerations involves the use of ATS's which are designed such that either molded-case circuit-breakers or molded-case switches can be used interchangeably as the switching devices. Only the latter should be used to avoid the possibility of a premature-trip of the circuit-breaker causing total loss of power to the critical load, or depending on the conditions used to cause the ATS to switch, the ATS could transfer prematurely. Whereas a premature transfer is not a critical failure-mode, any unnecessary transfer of an ATS supporting a critical load is undesirable because of the possibility of a system malfunction occurring due to transients or glitches caused by the switch-over. The potential for loss of power to the critical load caused by an open switching device in the ATS brings about the necessity to investigate the second consideration. The second consideration pertains to the technique used to cause the ATS to transfer to its alternate power source. Many ATS's employ a voltage-sensor circuit(s) to detect the loss of preferred input power. When the voltage sensor detects the absence of preferred input power, the transfer is initiated and the ATS switches the load to the alternate power source. In the event that the ATS switching device fails "open" as described in the previous paragraph, no transfer would occur because the voltage-sensor at the preferred input would not have detected any loss of input power. The result would again be loss of power to the load. Hence, the only sure way to guard against this failure-mode is to configure the ATS to sense loss of voltage at the "load" terminals of the ATS instead of at the "preferred" power input terminals. Thus, any internal ATS failure which would otherwise cause loss of power to the load will be neutralized. The intent of providing an ATS in critical power circuits is to eliminate single failures that would cause loss of power to the load. Eliminating the potential for these two types of internal ATS failure-modes significantly reduces the chances of the ATS itself becoming a single-fail point. The third consideration is maintaining the good working order of the ATS, i.e. maintainability and preventative maintenance. Because the ATS is used only for emergency transfer of power, and since maintenance could require taking down the system, regular maintenance may be repeatedly postponed or ignored until a real-time catastrophe reveals that the ATS will not transfer because of a maintenance related failure. Adequate preventative maintenance should not be substituted for convenience. Where possible, scheduled down-time should be used to complete an appropriate maintenance plan. In systems where down-time is not a convenient option, a hardware method of bypassing the ATS to facilitate maintenance should be installed. Designing the system for maintainability allows the required preventative maintenance to be performed without interfering with normal system operation. With the appropriate hardware configuration and preventative maintenance plan in place, optimum reliability can be achieved without any substantial increase in installation or operating cost. Any cost incurred, if any at all, to implement these safeguards is assuredly returned by the avoidance of a single failure of the ATS under worst-case conditions. | This practice has been used on Kennedy Space Center Shuttle Landing Facility 60 Hertz Power System supporting critical landing aids. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
824 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Space Radiation Effects on Electronic Components in Low-Earth Orbit |  | Failures of components encountered in space due to the use of non-rad-hard devices can lead to catastrophic results, which may lead to loss of spacecraft and possibly loss of life. Disregard for these guidelines can cost a program significant resources and make the difference between success and failure of a space mission. | During system design, choose electronic components/devices which will provide maximum failure tolerance from Space Radiation Effects. The information above provides guidance in selection of radiation hardened (rad-hard) solid state devices and microcircuits for use in space vehicles which operate in low-earth orbits. | JSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1258; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: This practice provides enhanced reliability and availability as well as improved chances for mission success. Failure rates due to space radiation effects will be significantly lower, and thus system down time will be much lower, saving program cost and resources. Implementation Method: Space Radiation Environment, Essential Basics: Radiation in space is generated by particles emitted from a variety of sources both within and beyond our solar system. Radiation effects from these particles can not only cause degradation, but can also cause failure of the electronic and electrical systems in space vehicles or satellites. Even high altitude commercial airliners flying polar routes have shown documented cases of avionics malfunctions due to radiation events. Primary Cosmic rays interact with gaseous and other matter at high altitudes and produce secondary radiation. The combination of both contributes to the Space Radiation environment. The fusion process on the Sun's interior produces electrons and protons in great abundance along with helium and other heavier nuclei, which travel towards earth as the solar wind. This solar wind radiates out from the sun in all directions; but the flux of these particles varies with sunspot activity and solar flares. In addition to the particles originating from the sun are particles from other stars and heavy ion sources such as novas and supernovas in our galaxy and beyond. In interplanetary space these ionizing particles constitute the major radiation threat. These particles are influenced by planetary or earth's magnetic field to form radiation belts, which in earth's case are known as Van Allen Radiation belts, containing trapped electrons in the outer belt and protons in the inner belt. The composition and intensity of the radiation varies significantly with the trajectory of a space vehicle. Experience with many spacecraft since Explorer I shows that higher electron concentrations are observed between 45 degrees and 85 degrees latitude in both the northern and southern hemi-spheres, indicating that the belts descend to a lower altitude in these regions. For low inclination orbits, less than 30 degrees, the electron concentrations are relatively low. Due to the earth's asymmetric magnetic field, a region in the Atlantic near Argentina and Brazil, known as South Atlantic Anomaly (SAA), has relatively high concentrations of electrons. The SAA is known to cause problems such as: single event upsets (SEU) in altimeter electronics gate arrays, and quothardquot SEU's in the Space Shuttle Orbiter's Star Tracker's Analog-to-Digital converter. The March 1991 solar storms significantly increased the charged particle distributions in the Van Allen belts, also creating a third belt. In addition to the trapped charged particles in Van Allen radiation belts (electrons and protons), the spacecraft experience radiation threats from high energy heavy ions in space called Galactic Cosmic rays, and secondary X-Rays or Bremstrahlung generated by particles penetrating the skin of the space-craft while they lose energy. This type of electromagnetic radiation is a significant percentage of the total component producing total dose effects. The usual (Centimeter Gram Second) unit used to specify radiation dose or deposited energy is the quotrad,quot which is defined as 100 ergs/gm of material. The material is always specified in parentheses, e.g., rad(Si). But the International system of units (SI) defines an essentially Meter Kilogram Second (MKS) units for absorbed dose called the quotgrayquot (GY). One GY is defined as the deposition of 1 joule per kilogram of radiation energy, i.e 1GY = 100 rads. Solar Flares also contribute varying quantities of electrons, protons, and lower energy heavy ions. Solar flares occur randomly at different times, and during times of high solar activity may contribute very high fluxes of particles over periods of hours or days. Heavy ions of various energies cause single event effects (SEE). A convenient way to express the transient charge generated by these heavy ions or charged particles is in charge per unit length, e.g. pC/micron. However a more frequently used term (but less intuitive) to express the same thing is called, quotLinear Energy Transfer or LETquot, which is expressed in MeV.cm2 /mg. In bit-storage devices the high energy heavy-ions cause bits to change, and are expressed in terms of bit error rates or SEU Error Probability. The SEU Error Probability is a number generated by computer from three data inputs: (a) the expected distribution of particles vs. LET, (b) the device cross-section for upset or latch up as function of LET, usually obtained from laboratory measurements, and (c) a calculation of expected error rate that combines the first two relationships with a calculation of the effect of the omni-directional particle flux on the charge produced in the device by the incident particles. Computer programs are available that perform this calculation. The net result is a fixed number for the upset or latch up probability. The following rules must be observed for estimating total dose environments: Criteria for Selection of Parts for Enhanced Reliability: For Space vehicles or satellites in low inclination (< 28 degrees) Low Earth Orbit ((LEO), < 500 km or 270 nmi) in both northern and southern hemispheres, typical dose rates due to trapped Van Allen electrons and protons are 100-1000 rad(Si)/year. For Space vehicles or satellites in higher inclinations (20 < I > 85 degrees) LEO in both northern and southern hemispheres, typical dose rates due to increased number of trapped electrons are 1000-10,000 rad(Si)/year. There are three categories of components having the following characteristics: Commercial: Process and Design limit the radiation hardness No lot radiation controls Hardness levels: Total Dose: 2 to 10 krad (typical) SEU Threshold LET: 5 Mev/mg/cm2 SEU Error Rate: 10-5 errors/bit-day (typical) Customer performs rad testing, and assumes all risk Customer evaluation and risk Rad Tolerant: Design assures rad hardness up to a certain level No lot radiation controls Hardness levels: Total Dose: 20 to 50 krad (typical) SEU Threshold LET: 20 MeV/mg/cm2 SEU Error Rate: 10-7 - 10-8 errors/bit-day Usually tested for functional fail only, risky Customer evaluation and risk Rad Hard: Designed and processed for particular hardness level Wafer lot radiation tested Hardness levels: Total Dose: > 200 krad to >1 Mrad SEU Threshold LET: 80-150 MeV/mg/cm2 SEU Error Rate: 10-10 - to 10-12 errors/bit-day Latch up: None present in Silicon-on-Insulator/Silicon on Sapphire (SOI/SOS) Complimentary Metal Oxide Semiconductor (CMOS)- technologies Exhibit Low SEU sensitivity for SEE's NOTE: Although Class S does not guarantee that the parts are rad-hard, the design process does dictate whether a part is rad-tolerant or not. Using rad-soft components does not significantly reduce cost, but greatly increases risk. There are no components that are ideal for all parameters. IC design requires many tradeoffs in performance (cost included as performance parameter). Commercial components are useful only for commercial applications, where low cost, latest technology (even if it is immature), and high speed takes precedence over extreme temperatures and voltage ranges. Shielding these devices in Space Applications is a futile effort, especially for Single Event Effects such as SEU and Single Event Latch up (SEL). Total Dose Hardness Levels of Various Technologies: It should be noted that Bipolar device operation depends upon minority carrier current levels flowing through the substrate, while Metal Oxide Semiconductor (MOS) technologies operate upon majority carrier current flows at the surface of the substrate. (Junction Field Effect Transistors depend upon majority carrier currents through the substrate). This is what makes their interaction with radiation different . Table 1 shows a comparison of Bipolar to MOS devices and radiation hardness. [D] Table 1: Radiation Hardness Comparison NOTE: Achieving total dose hardness in CMOS-SOS is more difficult than in bulk CMOS, but SOS does appear to offer advantages relative to dose rate, with respect to SEE. Silicon BIPOLAR technology is also heavily utilized in Linear devices, but analog devices require different transistor design characteristics from logic devices whose operation involves simple switching of logic states. Linear devices are affected by radiation in two ways. Low current transistor betas (current-gains) are degraded by surface effects similar to those which degrade MOS devices. Collector current (i.e. base current minus base-emitter leakage current times the beta of the transistor), is thus affected as a result of radiation exposure. When the leakage current (base-to-emitter) increases significantly as a result of radiation, the transistor will not function properly at low current levels, causing problems with input impedance, input offset and open loop gains. Bipolar devices (Integrated Circuits) often contain parasitic MOS devices, which present no problem in logic devices. Bipolar logic circuits typically operate at 5V with logic thresholds below 2V also helps. The parasitics typically have turn-on voltages in excess of 30V. Bipolar linear devices, however, typically operate at higher voltages (with positive- to-negative supply differentials of from 30V to 40V, making them more susceptible to even small radiation induced shifts in the turn-on voltages of parasitics). The problem is partially solved by design layout changes. Other processing characteristics such as the difference between silicon dioxide and silicon nitride (used for surface passivation) can also change the radiation tolerance characteristics of bipolar linear devices. With improvements in current technology, most such devices are rad-hard to one mega-Rad(si) level. One method to compensate for the transistor-to-transistor leakage current effects due to radiation is corrected by using dielectric isolation technique in bipolar devices. Total Ionizing Dose (TID) Effects in CMOS Devices: CMOS-Bulk Devices (IC's) experience quotlatch upquot due to a parasitic four-layer PNPN path, inherent in most unhardened devices. These parasitic four-layer devices act like a Silicon Control Rectifier (SCR), which once latched cannot be turned off without shutting off the power. Radiation hardening for total dose of such devices can be achieved by choice of technology and design changes to minimize the formation of such paths within an Integrated circuit. CMOS-SOS or CMOS-SOI devices do not have such paths and are inherently rad-hard up to one megaRad(Si), but are comparatively more expensive. CMOS-Bulk devices can be made rad-hard by introducing epitaxial layers to reduce the formation of PNPN paths, thus reducing the chances for latch up to one mega-Rad (Si). Single Event Effects (SEE): High energy protons or heavy ions lose their energy mainly through ionization, i.e create electron-hole pairs as they traverse through p-n junctions or the depth of penetration in the semiconductor material. Some of the deposited charge recombines, and some is collected at the junction contacts. The net effect is a very short duration pulse of current that induces transient at internal circuit nodes. The magnitude of the charge, which is generally much larger for ions with high atomic numbers, depends on the energy and ion type, as well as the path length over which the charge is collected. The effect of these random charges on the circuit depends on a number of factors, including the minimum charge required to switch a digital circuit state, called SEU's. Single bit upsets are easy to correct by Error Correction Codes but multiple bit corrections may lead to problems, and can be corrected by redundancy, etc. Also, memory devices are hardened by design to minimize single event upsets. CMOS Static Random Access Memory (SRAM) cells can be hardened by adding capacitors, resistors, transistors or combination of these devices to the circuit, at the cost of circuit parameter degradation especially the speed. If the CMOS-bulk process creates parasitic SCR's or PNPN structures, the excessive charge may cause a Latch up, leading to a SEL, which can sometimes lead to the destruction of the device. It can be minimized by choice of rad-hard process or technologies. CMOS-SOS/CMOS-SOI, Bipolar and GaAs devices are not prone to latch up or SEL. Latch-up in rad-hard devices is minimized through design and process using (a) numerous, regularly spaced well and substrate contacts in design, (b) thin-epi/shallow well CMOS processes, and (c) butting of the source-to-substrate and source-to-well contacts. The only certain way to eliminate latch up is to use CMOS-SOS or CMOS-SOI process that eliminates one of the parasitic transistors, thereby removing the possibility of latch up. The problems resulting from SEL's are either immediate or latent damage which may reduce functional performance. Non rad-hard circuits or devices can incur damage from excessively high currents within a few microseconds. Once latch-up occurs, a device would remain in a high current, latched condition until power is turned off. Power cycling will be required each time latch up occurs, which will temporarily shutdown sections of the subsystem that share power supplies. Along with power cycling, circuits and subsystems affected by any component will have to be reinitialized. Another potentially catastrophic SEE phenomenon called quotSnapbackquot exhibits many of the characteristics of latch up and can occur in single MOS transistors structure. It can occur in SOS and SOI technologies that do not contain four-layer parasitic structures. A single high energy particle may trigger snapback if the field across the drain region is sufficiently high. Snapback is due to the prospect of a parasitic bipolar transistor existing between the drain and source region of a MOS transistor which amplifies avalanche current that results from the transversal of the heavy ion Cosmic ray particle. This results in a very high current between the drain and source region of the transistor, with subsequent localized heating. Technical Rationale: To ensure dependable and reliable electronic circuit designs, the radiation environment for Total Ionizing Dose (TID) and Single Event Effects (SEE) encountered at a specific height and orbital orientation during the space-craft mission must be determined. Such data is available from NASA documentation such as SSP 30512, quotSpace Station Ionizing Radiation Design Environmentquot and SSP 30513, quotSpace Station Program Natural Environment Effects Test and Analysis Techniquesquot, applicable to the International Space Station Alpha. Goddard Space Flight Center documentation also provides this information. All electronic devices/components will experience two radiation-related effects in space. The first, the TID effect is time dependent, and the second, SEE, depends on many factors and is independent of time. The two effects must be addressed separately in design, and as such, this guideline will define basic ground rules for selection of rad-hard devices (radiation tolerant up to a certain specified dose) which can tolerate the effects produced by space radiation, within specified safe limits. If the power is not turned off when latch up occurs in a power Metal Oxide Semiconductor Field Effect Transistor (MOSFET), the avalanche current within the parasitic SCR structure increases indefinitely to cause heating in the gate channel due to I2 R effect and leads to burn-out by a very high energy cosmic ray particle going through the transistor. Another phenomenon associated with the power-MOSFET's is the gate-oxide damage called single-event-Gate-rupture due to the presence of an extremely large electric field, which causes a force on a trapped charge given by [D] where q is the presence of a charge trapped within oxide, v is the potential or voltage across the gate, and d is the thickness of the gate oxide. Both of the mechanisms are fatal to the power transistors. References: David. M Long, quotHardness of MOS & Bipolar Integrated Circuits,quot IEEE Transactions on Nuclear Science, Vol. NS-27, No 6, December 1980 E.G. Stassinopoulos, quotRadiation Environment in Space,quotIEEE NSPEC Short Course, July, 1990 George C. Messenger, and Milton S. Ash, quotThe Effects of Radiation on Electronic Systems,quot Van Nostrand Reinhold Company, New York, NY, 1986 | This practice has been used on Space Shuttle Orbiter. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
814 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical, Electronic, and Electromechnical (EEE) Parts Screening |  | Without screening, there could be latent failure mechanisms that could cause flight delays and/or failures. For example, two circuits on the Solar Maximum Mission (SMM) spacecraft failed. The failed parts were analyzed upon return from the repair mission and found to contain defects that would have been revealed through screening. In one case, the microcircuit had a metallization flaw; in the second, the CMOS microcircuit had contamination on the die. In another example, screening tests performed on microcircuits resulted in an 85% failure rate. Subsequent failure analysis revealed that improper parts had been used. | Implement a 100% nondestructive screening test on EEE parts prior to assembly, which would prevent early-life failures (generally referred to as infant mortality). | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1401, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: EEE Parts Screening provides a lower rework cost during manufacturing and lower incident of component failures during flight. Implementation Method: Screening for each part can be established as follows: Refer to NASA's compilation of screening criteria for use with various EEE part types. An example may be found in Appendix C of the GSFC Preferred Parts List. If Class S parts are purchased, the screening tests shown in Table 1 have already been conducted. When Class S parts are not available, the screens of Table 1 should be used. Failure criteria during screening should specify Percent Defectives Allowable (PDA) and allowable parameter drift. Typical PDA criterion is 5%. A sample listing of failure mechanisms, the associated distribution of failures, and related screening tests are provided in Table 2. [D] Table 1. 100% Parts Screening Matrix [D] Table 2. Failure Mechanisms/Screening Methods Technical Rationale: The EEE parts manufacturing is controlled by military specification requirements covering a variety of areas such as: starting materials, process controls, electrical or electromechanical performance characteristics, and periodic inspections of some characteristics of finished product. Despite these requirements, defects that cause early-life failures can be randomly built into a product. The screening tests are designed to be destructive to parts with particular defects but nondestructive to good parts. As an example, integrated circuits such as CMOS are highly susceptible to electrical performance failures caused by ionic contamination on the die surface. The contamination can be introduced by any of several uncontrollable avenues during manufacture and cannot be ruled out as an occurrence in any given lot of parts. To avoid early-life failures at higher assembly levels, the lot of parts is subjected to a 100% static burn-in. The burn-in is designed to drive contamination into the die areas where it will interfere with proper circuit operation and cause electrical failures before parts are installed on boards. References: NASA GSFC Preferred Parts List (NPPL) 18/19. Seidl, Raymond H., Garry, William J., quotPi Factors Revisited,quot Proceedings of the Annual Reliability and Maintainability Symposium, 1990. | This practice has been used on all Goddard Space Flight Center (GSFC) flight programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
815 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Loads Anaylysis as a Spacecraft Design Tool |  | The non-use of coupled vehicle/spacecraft calculations can lead to a poorly designed structure, that is, substantially above minimum weight, but not necessarily above dynamic stiffness requirements. Structural and operational reliability of the mission will have been undermined. Unless alternative methods which bound loads have been used, predicted responses, stresses and deformations will be inaccurate. | The determination of accurate spacecraft loads via coupled flight loads analysis is used throughout the entire spacecraft development cycle, from conceptual design to final verification loads calculations. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1317, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Flight loads analysis, when used throughout the spacecraft development cycle, will 1) provide a mission specific set of loads, 2) provide a balanced structural design, 3) reduce conservatism inherent in bounding quasi-static design load calculations, 4) provide early problem definition, and 5) reduce surprises at the final verification loads cycle. Implementation Method: The accurate determination of structural loads during all phases of STS (Space Transportation System) and/or ELV (Expendable Launch Vehicle) flight environments is crucial to spacecraft development. The procedure to calculate these loads involves 1) creation of an accurate spacecraft loads model and its corresponding validation by test, and 2) using this model in conjunction with vehicle/spacecraft coupled flight forcing functions during the development process. The model is linear and cannot be accurate unless the structure it represents is essentially linear. Finite Element Model Creation: The development of an accurate finite element model (FEM) is crucial to the successful structural design of a spacecraft. It can be used to predict nodal and relative accelerations, member loads and stresses, critical displacements, mechanically transmitted random loads, and thermal distortion loads. In addition, it can be used to perform weight saving studies, deployment studies, static test loads calculations, and control and stability studies. The creation of a FEM should begin early in the design phase of a spacecraft. Even a simple model made from sketches can be useful for preliminary predictions of mass properties, frequency calculations, and primary structure design. As the design matures, more details become available (i.e., mass properties, materials, section properties). At this point, it is essential to understand the analyses for which the model is intended, since this determines the complexity required and the assumptions made in modeling. With the recent advent of very high speed computers (Work-stations, RISC machines, etc.) which are available to today's engineers, the temptation is to create large models which in effect when displayed, look almost like a photograph of the structure. This is often not necessary or efficient, and many times incorrect, especially in the interpretation of results. The engineer should have a clear understanding of the structural load paths, including knowledge about how the actual structure will behave under static and dynamic loading. This is the only way he/she will be capable to later interpret transient events in the structure. Finite Element Model Checks Model validity must be validated both mathematically and structurally. Throughout the design cycle some of the checks will directly indicate modeling problems, many requiring engineering insight and judgment to assess model validity. The following checks should be performed: Line-by-line check of input data to ensure input accuracy. Static run with fixed boundary conditions and 1G loads applied separately in each primary structural direction, reviewing resultant displacements, forces and stresses for reasonableness, and symmetry (if possible), etc. Fixed base modal run to calculate resultant structural shapes and frequency modes. Results should be consistent with the structural design. Hand calculations should be made to verify simple characteristics such as panel modes. Modal effective weights and participation factors should be tabulated and studied along with animated mode shape displays to gain insight and ensure consistency with design expectations. Modal strain and kinetic energy calculations also yield insight into structural characteristics. The sum of the effective weights for the modes considered should account for almost the total weight in each direction. Free-free modal run to calculate rigid body modes. These modes should be two orders of magnitude less than the first flexible modes, generally less than .001 Hz, to ensure that there is no inadvertent grounding of the structure. Equilibrium checks of the model are calculated by multiplying the free-free stiffness matrix by geometrically derived rigid body modes. Nodes at which the structure is grounded should be displayed in a tabular form. For those models which will be used to predict thermally induced loads and deflections, a thermal equilibrium check is performed in which a bulk temperature change is imposed in a kinematically constrained model which has all thermal expansion coefficients changed to a single value. Negligible element forces should be generated for this case. All rigid elements must be replaced with stiff elastic elements to facilitate proper temperature calculations. Plot element rotations to assure conformity (if applicable). Also generate a boundary plot to verify proper element locations. It is also strongly recommended that extensive verification using a preprocessor with graphic output be used to verify proper load orientation, model construction, etc. Inspection of all FEM software message and warnings which might indicate among other things, improperly shaped elements, ill-conditioning, mechanisms, massless degrees of freedom, and so forth. Mass properties should be compared to current spacecraft weight statements. Comments relative to automatically imposed restraints, in particular, must be verified to be appropriate. Dynamic models reduced by the Guyan reduction technique to facilitate manageable normal modes calculations should be checked with a full-size matrix eigenvalue extraction technique such as Lanczos to assess the validity of the Guyan reduced eigenvalues and mode shapes. An improperly chosen Guyan reduction set may miss modes and result in frequency error. Model Validation: The finite element model is verified via a series of mechanical tests. Instrumentation data acquired during these tests are then compared to the FEM predicted behavior in order to assess the accuracy of the model. Subsequent adjustments are typically made to improve the model correlation to the test data before the model is considered test verified. The static and dynamic response results and the corresponding strength assessment of the structure are solely dependent on the accuracy of the FEM used to calculate these responses. A model uncertainty factor (MUF) is applied to early loads results when coupled loads analysis is used for structural design. The magnitude of this factor may be reduced to 1.0 as confidence in the model is increased through the verification program. Mass Properties Verification: The initial step in the model correlation should be the measurement and correlation of the rigid body mass properties. At the very least, this should include the structural weight. The center of gravity location and rotary inertia values should also be verified to the greatest extent practicable. In specific instances, where the structure has an axis of symmetry or a simple geometry it may be permissible to rely on analytical values at the discretion of the project management. Typically, the mass property adjustments are made by accounting for non-structural mass items such as harnessing, thermal blanketing, or attachment hardware. This adjustment can be included in the model via the use of the non-structural mass parameter on the element property designation or by distributing concentrated mass elements in the region associated with these items. The mass property adjustments will affect both the static and the dynamic characteristics of the structural model making it essential to perform this correlation first. Accurate representation of the mass properties will have the greatest influence on the rigid body component of response which can be the dominant contributor to the total response. Further, for small components or very stiff structures which can be considered rigid bodies, the mass properties correlation is the only verification necessary. Structural Dynamic Verification The modal survey test is the primary test for verifying the ability of the FEM to represent the dynamic behavior of the structure. The goal of this test is to measure the significant natural modes of the structure within a frequency range defined by the frequency content of the loading environment as transmitted by the launch vehicle. If no modes are predicted within this frequency range, a limited modal survey or shaker based sine sweep test should still be performed in order to verify that no modes exist. A pre-test analysis should be conducted in order to predict the natural frequencies and mode shapes and to determine appropriate locations for accelerometers. To assess the choice of a set of potential accelerometer locations, a Guyan reduction, consisting only of the instrumentation locations, should be performed and mode shapes and frequencies calculated. These results should then be compared to the previously calculated modal quantities, for the full model, to assess the adequacy of the test instrumentation set. The principal method of quantifying the similarity of mode shapes is the cross orthogonality matrix. This method of comparison should be used to make the previously discussed assessment of instrumentation and finally used to evaluate the correlation to the measured test data. If the model correlation is perfect, this matrix should be equal to the identity matrix. The correlation is considered adequate when the diagonal and off-diagonal elements of the matrix are within specified values. Once the mass properties are verified, adjustments to the FEM for modal correlation are usually made by the introduction or removal of local flexibilities which may have been based on poor assumptions. These errors can be detected through visual comparison of the test and analysis mode shapes as well as a combination of strain energy or modal effective weight analysis. Spring elements are often included to represent local flexibilities at joints which have originally been assumed rigid. Conversely, rigid elements may be used in instances where electronic boxes or other equipment appear to stiffen an area in which no stiffness contribution was originally assumed. The correct values for these local changes are typically found by iteration and determination of the cross orthogonality matrix. The changes should be demonstrated to be realistic by local detail analysis and not just chosen to match the sparse test values. Automated methods based on sensitivity and optimization techniques are useful to identify areas of likely error. Within this context, all changes should reflect physical reality. Static Verification: Although the purpose of the static test is to demonstrate the strength of the structure, it may also be used as a secondary model verification test. This is usually not possible if the strength test is performed via the sine burst method, but may be appropriate if actual static pulls are used. A pre-test analysis is always performed in order to determine the appropriate test levels and therefore member loads and stress predictions should be available. The actual member loads as experienced in the test are then acquired through strain gage measurements. The locations of this instrumentation should be chosen in order to characterize the primary load paths and are necessary to prove that the qualification levels were attained. Assuming that the measured levels are not in accordance with pre-test predictions, adjustments to the FEM for correlation to the static test data may be applied in a similar manner as discussed pertaining to the modal survey test. It should be recognized that the need for implementation of a significant model change indicated by the static test data could result in an invalidation of the modal test correlation. This situation rarely occurs because the modal test should adequately exercise the structure and the static test correlation should only indicate minor adjustments. Both the modal and static correlation must be based on the model after all changes are made. Coupled Models: The NASA centers have the luxury of having available for themselves and their contractors use, a library of government and commercial launch vehicle FEMs with the appropriate forcing functions to simulate liftoff, staging, on-orbit and in the case of STS, landing events. These models and their forcing functions, when used in conjunction with the spacecraft model, can be used to determine all spacecraft transient responses. This leads to the most accurate prediction of spacecraft loads possible. In addition, time-phased responses can be used to reduce the conservatism resulting from the application of simultaneous bounding quasi-static design loads. The creation of system level models for coupled loads analysis almost always requires the techniques of modal synthesis. This is due to both the size and complexity of the individual instrument, spacecraft, and launch, landing or stage models. Modal synthesis involves 1) reduction of the individual models to manageable and yet dynamically accurate sizes, and 2) coupling of these reduced models to form the overall system level model, ready for forced response calculations. Modal synthesis requires matrix manipulations and transformations, eigenvalue analysis, and extensive bookkeeping to track the structural parameters through the transformations. Typically, a Craig-Bampton modal model of the spacecraft is made which has as its major characteristics, the physical boundary points and cantilever modes defining the vehicle flexibility with respect to that fixed boundary. This form of characterizing the payload not only greatly reduces the model size, but also permits the analyst to check the mass properties, displacements, and accelerations as a rigid body. All parameters of the vehicle are available for later data recovery via the creation of LTMs (Loads Transformation Matrices) in which structural variables are defined with respect to unit boundary and modal acceleration applications. Note that the formulation of the vehicle model may actually require a series of Craig-Bampton reductions for large instruments, antennas, solar arrays, etc. Careful bookkeeping and many checks -- rigid body, 1-G, equilibrium, effective modal weights, mass properties -- are required at each step to ensure accuracy. If rigid body motions are imposed on the physical degrees of freedom of the models there should be zero resulting forces. Adjustments should be made until this requirement is met. The STS or ELV models are delivered in many different formats, but all currently have the attachment portion of the model defined in physical coordinates, which allows for the direct coupling using matrix techniques (i.e., constraint equations , elastic, or rigid elements, direct matrix addition). Any of the current model deliveries, including discrete mass and stiffness matrices, Craig-Bampton models, or residual stiffness models, can be easily handled with these techniques. The coupling procedure should be checked by independent analysis. This is usually done at a NASA center and is initiated by a loads working group consisting of members representing the payload and launch vehicle (including upper stage) contractors. Loads Analysis: The coupled system level model is run through an eigenvalue analysis routine (i.e., Givens, Modified Givens, generalized dynamic reduction, Lanczos) to calculate uncoupled modes and frequencies. These uncoupled modes and frequencies form the basis for the second order differential equations which are integrated to calculate the forced response due to the application of the forcing functions which are delivered with the launch, landing or stage models. In the case of STS, modal damping is incorporated at this point. System level time response accelerations and displacements are transformed back to local vehicle level modal response via the system level mode shapes. A few non-linear degrees of freedom such as for trunnion friction can be incorporated at this level. LTMs and Data Recovery: The methodology used to recover specific data on the vehicle model involves the use of LTMs. LTMs are simply linear transformations which yield physical quantities from modal responses. During the Craig-Bampton model formulation, LTMs are set up at the vehicle coordinate level in which all vehicle parameters including accelerations, displacements, member forces and stresses, and relative displacements are defined with respect to individually applied boundary and modal accelerations. Then, at the system level, the system level mode shapes are used to transform the generalized displacements and accelerations back to the local modal level. The multiplication of these local modal time responses by the LTMs will yield the desired vehicle physical responses. Data recovery is the all important phase of the coupled loads analysis. The engineer must view responses, study min/max loads, investigate frequency content, etc. until fully convinced that the transient calculations have been accurately carried out. Outputs should include min/max tables, time response plots, shock spectra plots, finite element plots, animated mode shape plots, timed phased stress calculations, etc. All of these facilitate accuracy studies and final report quality for the end user. Technical Rationale: STS and ELV models are available to NASA centers and their subcontractors. Coupled flight loads analyses using these models with their intended spacecraft complement can be performed in a timely manner and at a reasonable cost. Thus, throughout the development cycle of a spacecraft, from conceptual design to final verification loads analysis, flight loads analyses can be used as a design tool. This process yields a high degree of confidence in spacecraft structural integrity, and the spacecraft models' use in weight reduction studies, control and stability studies, thermal distortion loads calculations, deployment studies, and calculation of random loads, etc. References: 1. Shimizu, M. W., Dattilo, D. O., and Kosick, L. J., "STS Dynamic Math Models (M6.OZA) for Payloads Analysis", Rockwell International, STS81l-064F, July 1988 Shimizu, M. W., and Sullivan, A. J., "Landing Forcing Function 7000 Series Data Base", Rockwell International, STS86-0020A, February 1988 Haugen, E. A., "Liftoff Forcing Functions (LR2000 Series) for Payload Loads analysis", Rockwell International, STS89-0609, April 1988 Frederick, D. H., "National Space Transportation System Models and Loads Analysis Configuration Management/Control", Rockwell International, SD77-SH-0214C, December 1989 "Proceedings of the Shuttle Payload Dynamic Environments and Loads Prediction Workshop", JPL D-1347, January 24-26,1984 "General Environmental Verification Specification for STS and ELV Payloads, Subsystems, and Components," GSFC, GEVS-SE, January 1990 Sinusoidal Vibration, Reliability Preferred Practice PT-TE-1406. Assembly Acoustic Tests, Reliability Preferred Practice PT-TE-1407. Random Vibration Testing, Reliability Preferred Practice PT-TE-1413. | This practice has been used on the Hubble Space Telescope, Gamma Ray Observatory, Superfluid Helium On-Orbit Transfer and Get Away Special (GAS) programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
817 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Vibroacoustic Qualification Testing of Payloads, Subsystems, and Components |  | Failure to perform vibroacoustic testing could result in payload failures when subjected to the vibroacoustic environments of the mission, particularly the severe acoustic environment of launch. In addition, the simultaneous occurrence of low-frequency random vibration with high-intensity, low-frequency acoustics can cause failure of load-carrying elements. Examples of components that are susceptible to failure due to random vibration excitation are thin films, filaments, electronic circuit boards, and optical elements. | Perform acoustic and random vibration testing supplemented with additional sine vibration testing as appropriate to qualify payload hardware to the vibroacoustic environments of the mission, particularly the launch environment and to demonstrate acceptable workmanship. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1419 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Adherence to the practice alleviates vibroacoustic-induced failures of structural stress and fatigue, unacceptable workmanship, and performance degradation of sensitive subsystems including instruments and components. Implementation of this practice assures that minimal degradation of quotdesign reliabilityquot has occurred during prior fabrication, integration and test activities. Implementation Method: The GSFC vibroacoustic qualification program for flight hardware requires an acoustics test at the payload level of assembly and random vibration tests on all components. In addition, a random vibration test is required on the payload when practical to better simulate the structure borne inputs. For small payloads, such as those launched by the Scout class launch vehicle, random vibration tests are required and the need for an acoustic test must be assessed. Subsystem level random vibration tests and component level acoustic tests are required when the payload configuration indicates that these exposures are likely to induce significant stress during the mission. In addition, subsystem level acoustic tests may be required. GSFC uses protoflight hardware for verification testing and the basic provisions of this method apply to protoflight hardware but are in general applicable to prototype. Protoflight hardware is flight hardware of a new design and is subjected to a test program that combines elements of prototype and flight acceptance verification; that is, the application of design qualification test levels and flight acceptance test durations. Prototype hardware is hardware of a new design that is not intended for flight and is subjected to a design qualification test program. Vibroacoustic test level limits for protoflight qualification are defined as the maximum expected flight levels (limit levels) plus 3 dB (reference 2). Random vibration levels are determined by responses to the acoustic inputs plus the effects of vibration transmitted through the structure. As a minimum, payload and component vibroacoustic test limits must be sufficient as determined on a case by case basis to demonstrate acceptable workmanship. The acoustic environment at launch is usually the primary source of vibration; however, other transients and sources of vibration must be considered. These sources include possible torsional oscillation imparted by the launch vehicle, vibrations produced by retro/apogee motors on the payload, and sustained oscillations due to Main Engine CutOff (MECO) and pogo effects. Additional vibration tests (such as sine vibration) are required to qualify payload and payload hardware for these inputs if they are expected to occur during the mission. Payload Vibroacoustic Tests: a. Payload acoustic testing - Protoflight payloads must be subjected to an acoustic test to verify their ability to survive the launch acoustic environment and to provide final workmanship acoustic tests. The test specification is dependent on the payload-launch vehicle configuration and must be determined on a case-by-case basis; however, guideline specifications are given in appendix A of reference 2. Facilities and test control - Acoustic tests must be conducted in a reverberant chamber large enough to maintain a uniform sound field at all points surrounding the test item and to produce reverberant acoustic modes in the lowest third octave band specified. The sound pressure level must be controlled at one-third octave band resolution. The preferred method of control is to average four or more microphones with a real-time device that effectively averages the sound pressure level in each filter band. When real-time averaging is not practical, a survey of the chamber must be performed to determine the single point that is most suitable for control of the acoustic test. Additional information on the test facility, the test control methods, and the test setup are contained in paragraph 2.4.2 of reference 2. b. Payload vibration tests - Random vibration tests must be performed on the protoflight payloads subject to any limitations of the available test facilities to verify the ability of the payloads to survive the launch environments and to provide a final assessment of workmanship. The test is required for small payloads (<1000 lb) and must be assessed for larger payloads on a case-by-case basis. Appendix A of reference 2 provides the maximum expected random vibration levels at the spacecraft interface for various expendable launch vehicles (ELV) and other information and guidance on vibration testing. Additional qualification tests must be performed if expected environments are not enveloped by this test. Sine vibration tests must be added to the verification program if sustained oscillations are expected to occur, or to satisfy other load requirements. Launch random vibration: Protoflight as well as prototype payloads must be subjected to a random vibration test to verify flight worthiness and workmanship. The qualification test limits are the maximum flight levels plus 3 dB. The test is intended for payloads of low (<1000 pounds) to moderate (1000 to 5000 pounds) weight and size such as Scout launched spacecraft, small attached STS payloads, etc. The test covers the full 20 - 20,000 Hz frequency range. For moderate-sized payloads, the test is intended to verify the hardware in the frequency band below 200 Hz where acoustic tests do not excite the payload to the levels it will encounter during launch. The payload in its launch configuration is attached to a vibration fixture by use of a flight-type launch-vehicle adapter and attachment hardware. Vibration is applied sequentially at the base of the adapter in each of three orthogonal axes, one of which is parallel to the thrust axis. The excitation spectrum as measured by a control accelerometer(s) equalized such that the acceleration spectral density is maintained within ± 3 dB of the specified level at all frequencies within the test range and the overall RMS level is within ± 10% of the specified level. If the random vibration test is not performed at the payload level, the feasibility of performing the test at the next lower level of assembly must be assessed. Additional Vibration Tests - If additional vibration tests are required to qualify its performance, the payload is tested in a configuration representative of the time the stress occurs during flight with appropriate flight type hardware used for attachment. Subsystem Vibroacoustic Tests: Subsystem vibroacoustic testing - Subsystems must be exposed to random vibration testing unless analyses show that the test exposures are not needed. Specific test levels are determined on a case-by-case basis. The test levels must be equal to the qualification level (highest predicted flight level +3 dB) predicted at the location where the input is controlled. Subsystem acoustic tests must also be performed if the subsystem is judged to be sensitive to this environment. Additional vibration tests to simulate expected mission environments such as sustained periodic oscillations must be performed if applicable. For very large payloads, the random vibration tests may be impractical because of test facility limitations. In these cases, testing at the subsystem or instrument level must be considered. Component Vibroacoustic Test: Component Vibroacoustic Testing - For qualification as well as screening for design and workmanship defects, components must be subjected to a random vibration test along each of three mutually perpendicular axes. In addition, an acoustic test must be considered when components are particularly sensitive to the acoustic environment. Random vibration testing - Components must be subjected to random vibration along each of three mutually perpendicular axes for one minute each. When possible, the component random vibration spectrum is based on levels measured at the component mounting locations during previous subsystem or payload testing. When such measurements are not available, the levels must be based on statistically estimated responses of similar components on similar structures or on analysis of the payload. In the absence of any knowledge of the expected level, the generalized vibration test specification given in Table 1 must be used. If the hardware contains delicate optics, detectors, sensors, etc., that could be damaged by the levels of the workmanship test in certain frequency bands, the test levels may be reduced in those frequency bands after appropriate management review. [D] Table 1. Generalized Vibration Test Levels Protoflight Components (STS or ELV) (50lb or Less) If possible the hardware, less the sensitive items, should be subjected to the full test levels. As a minimum, all components are subjected to the levels of Table 2, which represent a workmanship screening test. [D] Table 2. Component Minimum Workmanship Random Vibration Levels (50 lb or Less) Refer to Reference 2 for requirements on the mounting of components to test fixtures and other test setup requirements. For very large components, the random vibration tests may have to be supplemented or replaced by an acoustic test if the vibration test levels are insufficient to excite internal hardware. If neither the acoustic nor vibration excitation is sufficient to provide an adequate workmanship test, a screening program should be initiated at lower levels of assembly; down to the board level, if necessary. 2. Acoustic Test - If a component level acoustic test is required, the test set-up and control are in accordance with the requirements for payload testing. 3. Additional Vibration Tests - Additional vibration tests may have to be performed to qualify the hardware for other vibrational inputs expected during the mission; such as a sine sweep to simulate periodic oscillations. Fatigue Life Considerations - The nature of the protoflight test program prevents a demonstration of hardware lifetime because the same hardware is both tested and flown. When hardware reliability considerations demand the demonstration of a specific hardware lifetime, a prototype verification program must be employed, the test durations modified accordingly. Specifically, the duration of the vibroacoustic exposures is extended to account for the life that the flight hardware will experience during the mission . In order to account for the scatter factor associated with the demonstration of fatigue, the duration of prototype exposures are at least four times the intended life of the flight hardware. Acceptance Testing - Vibroacoustic and other vibration testing for the acceptance of previously qualified hardware are conducted at the maximum expected flight levels using the same duration (1 min.) as used for protoflight hardware. The payload is subjected to an acoustic test, and the payload (when practical) and components levels are subjected to random vibration tests in the three axes. As a minimum, the random vibration levels shall represent the workmanship test levels. In addition, subsystems receive vibroacoustic testing as required by project specific requirements. Retest of reflight hardware - The amount of retest that is needed is determined by considering the amount of rework done after flight and by comparing the stresses of the upcoming flight with those of the previous flight. The principle objective is to verify the workmanship and to ensure that structural degradation has not occurred. If no disassembly and rework was done, retests may not be required. The effects of storage and elapsed time since last exposure are considered in determining the need for retest. Subsystems that have been taken apart and reassembled must be subjected ,as a minimum, to an acoustic test (levels are equal to the limit levels) and a random vibration test in at least one axis. More comprehensive exposures must be considered if the rework has been extensive. Performance Monitoring: Before and after each vibroacoustic test, the test item must be examined and functionally tested. During the test, power is applied when appropriate and the performance of the test item is monitored. Technical Rationale: Payloads can be sensitive to the vibroacoustic environment depending upon the degree of coupling between the acoustic excitation and the payload structure. Lightly stiffened, thin-panel type payload structures with large surface areas and low-mass loading are most susceptible to direct acoustic excitation. Truss-type structures are less susceptible to direct acoustic excitation because they have relatively high stiffness and small surface areas; however, the response of truss-type structures to acoustically induced random interface motions may be severe if the truss structure is mechanically coupled to the acoustically sensitive panel-type structures. The acoustic environment at launch is usually the primary source of vibration; however, other transients and sources of vibration can cause hardware problems. These sources include possible torsional oscillations imparted by the launch vehicle, vibrations produced by retro/apogee motors on the payload, and sustained oscillations due to MECO and pogo effects. References: SPAR-3, Guidelines For Standard Payload Assurance Requirements (SPAR) For Goddard Orbital Projects, March 1990 GEVS-SE, General Environmental Verification Specification For STS And ELV Payloads, Subsystems, And Components, January 1990 D-EH-1, Engineering Handbook For STS Payloads, Part 1: Loads And Structures, September 1982 Space Vehicle Design, Michael D. Griffin and James R. French, 1991 Design of Geosynchronous Spacecraft, Brin N. Agrawal, 1986 quotPowered-On Vibrationquot, Reliability Preferred Practice PT-TE-1405 quotSinusoidal Vibrationquot, Reliability Preferred Practice PT-TE-1406 quotAssembly Acoustic Testsquot, Reliability Preferred Practice PT-TE-1407. | This practice has been used on All Flight Programs Managed By GSFC including GOES, HST, COBE, etc. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
816 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Design of an Improved Gas Transfer Valve for Leak Tight Testing |  | The use of the redesigned tube-piercing valve in place of the commercial valve provided one with no leakage and more robust and reliable operational characteristics. Re-use of the commercial valve would give less than satisfactory results in OAFGSS testing. | A needle-point penetration gas transfer valve has been developed at JSC that is leak tight and gives very reliable results in transferring low or high pressure gases from sample containers to laboratory measuring devices such as chromatographs. | JSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1441 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The reliability benefits of this new valve are that it can be used to transfer gas without risking the loss of the sample or the sampleís purity. This improved reliability is in comparision to normal refrigeration gas transfer valves which are not leak tight and are not suitable for gas transfer where limited and unique gas samples are available and absolute gas measurements are required. Implementation Method: The purpose of this gas transfer valve was to provide a leak tight method of delivering gases from an Orbiter Aft Fuselage Gas Sampling System (OAFGSS) bottle assembly to a laboratory chromatograph. A commercial gas transfer system was modified to accomplish this task. A tube piercing valve was redesigned to replace the dynamic shaft seal with a compressible hermetically-sealed metal bellows. The redesigned valve and the component parts are illustrated in Figure 1. [D] Figure 1. Valve Assembly and Gas Transfer Set-up The redesigned valve incorporates existing technologies into a compact and most importantly leak-tight device. The metal bellows assembly was obtained from an off-the-shelf valve which was readily available. The body of the valve had to be fabricated; however, the basic idea was obtained from commercial valves. A high vacuum fitting was used as the outlet fitting of the valve due to its excellent ability to provide a leak-tight connection. The redesigned valve also has an adjustable stem travel which allows the stem tip penetration to be set to the desired level without excessive deformation of the tube which could lead to valve leakage. Helium leak checks were made on the valve after its development to determine leak rates and are shown in Table 1. The leak detector was configured to detect helium leaks as low as 1x10-8 standard cubic centimeters per second (sccs) during valve functioning. The values shown in Table 1 indicate that the valve is leak tight. [D] Table 1. Leak Tests on the Gas Sampling Valve Technical Rationale: It was desired by the Space Shuttle Program to determine if and at what levels explosive exhaust gasses were being collected in the Orbiter Aft Fuselage during ascent of the Orbiter. For this purpose, several gas transfer assemblies were developed and flown on the Orbiter. Each of the assemblies were programmed to sample exhaust gasses at several locations and altitudes along the Orbiter ascent trajectory. After a mission, these assemblies were downloaded and taken to a laboratory for gas analysis. Commercial tube piercing gas transfer systems were first used to penetrate the assembliesí access tube for chromatography testing. This technique was not suitable in some cases because of valve leakage and not reliable in others because of sample contamination, i.e., smaller samples were sometimes completely lost while other samples became contaminated with atmospheric constituents that rendered the test results meaningless. For this reason, a new gas transfer valve was developed for use that was leak tight and preserved the sample and its integrity during testing. | This practice has been used on the Space Shuttle Program | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
819 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Structural Stress Analysis |  | Not performing a complete and comprehensive stress analysis on the spacecraft structural components may lead to an inadequate design with unsafe or inefficient load paths. Without proper stress analysis, the objectives of minimum weight and a balanced design will not be met. Structural testing may also be misguided in that some components may be inadequately tested while others may be over-stressed. | This paper describes the general methodology for performing stress analysis for structures used in space applications. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1318, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Reliability of spacecraft structural components is greatly increased, and their cost and weight reduced by the systematic and rigorous application of sound stress analysis principles as an integral part of the design process. Implementation Method: Objectives: Structural stress analysis is performed in order to ensure that a structure will fulfill its intended function in a given loads environment. It is important to anticipate all the possible failure modes and design against them. For a space structure, the most common modes of failure are as follows: Ultimate failure, rupture, and collapse due to stresses exceeding material ultimate strength, Detrimental yielding that undermines structural integrity or performance due to stresses exceeding material yield strength, Instability (buckling) under a combination of loads, deformations, and part geometry such that the structure faces collapse before material strength is reached, Fatigue of material due to crack initiation and propagation under cyclic loads and fracture due to unstable crack propagation, quotExcessivequot elastic static or dynamic deformations causing loss of function, preload or alignment, interference, and undesirable vibrational noise, Other time dependent material failure modes including stress corrosion, creep, stress rupture, and thermal fatigue. A spacecraft (S/C) structure is usually classified as primary or secondary. The primary structure consists of those elements which react to the overall S/C bending, axial, shear, and torsional loads. Secondary structure comprises those elements which do not appreciably contribute to overall S/C stiffness. Non-flight components are referred to as mechanical ground support equipment (MGSE). Structural stress analysis should define and address all the loads acting on the S/C primary and secondary structures. Table 1 summarizes the most common loads encountered in the space applications. [D] Table 1. Summary of Spacecraft Loads Structural loads are specified at the maximum expected level and referred to as the design or limit loads. Usually, two or more of these loads act simultaneously and their combined effect needs to be considered. Note that the loads environment applied to the structure during the verification testing may be more significant than the loads experienced during flight. Many structural failures have occurred during testing in the past. Therefore, these loads must be considered very carefully in the strength and fatigue calculations. It should be noted that this practice does not address all the possible loads a structure may encounter, such as impact with orbital debris. Analysis Philosophy: The structural analysis should guide the design of the S/C and sizing of the components and provide a high degree of confidence. The analysis should be an integral part of the design process, thus minimizing design effort and time by eliminating redesign caused by failure during structural verification testing. An important benefit of performing stress analyses is the ability to determine design sensitivities and to conduct trade studies. Thus, effective optimization of the structure can be achieved, enhancing reliability while reducing cost and weight. It is essential for the analysis to be conservative, i.e., the failure load predicted should be less than the actual load the structure can withstand. This is necessary in view of the uncertainties in the analysis assumptions and the variations in the applied loads and material properties within normal bounds. The concept of an overall safety factor (SF) is introduced to account for various uncertainties and the limit loads are increased in proportion to the SF (Ultimate Load = SF x Limit Load). A typical SF value used for the ultimate failure of flight structures is 1.4. In addition, a yield SF typically equal to 1.25 is selected to prevent structural damage or detrimental yielding during structural testing or flight. Additional safety factors may be used for fittings, castings, etc. to account for related uncertainties. The SF requirements may change depending on the responsible NASA center, the sponsoring agency, and the project. In addition to applying a SF, care should be given to conduct a conservative analysis using lower bounds for estimating the structure's load carrying capacity. This will lead to a more reliable design; however, there will be a weight penalty. It should also be noted that the analysis effort decreases with increasing conservatism. Therefore, at the start of the analysis, factors such as weight criticality of the structure, uncertainties in data, and available time for analysis should be considered. Analysis Overview: Stress analysis activities vary depending on the function and maturity of the phase, namely: (a) the Conceptual and Preliminary Design, (b) the Detail Design, and (c) the Verification phases.For the conceptual and the preliminary design activities, the design loads and the safety factors are considered to evaluate the feasibility and adequacy of the load paths and to size the major structural elements. Most of the trade/optimization studies are conducted in this phase. In the detail design phase, the bulk of the stress analysis activities takes place. Sizing and checking of the load paths is carried out in detail and the design is finalized. In the verification phase, stress analysis is used to analytically show that the structural testing will create the required minimum response (usually 1.25 times the limit loads) and the maximum response will not cause structural damage or detrimental yielding. Analysis Methods: The general method and techniques used in structural stress analysis are outlined in Table 2. A description of each of these activities is given below. [D] Table 2. Stress/Failure Analysis Outline 1. Determination of the Structural Requirements and Loads: The first step of the analysis is the establishment of the requirements concerning strength, loads, displacements, service (cyclic) life, and verification (reference 1). In addition to strength, the design and sizing is sometimes dictated by maximum displacement requirements. The service life requirements may also dictate design and are to be clearly defined in every structural design and stress analysis activity. A S/C structure is subjected to a dynamic loads environment due to time varying accelerations, pressures, temperatures, and structurally or acoustically transmitted vibratory disturbances. The time history of loads seen by a specific component will be determined by its relative location as well as its stiffness and thermal paths to the rest of the S/C. This is determined by means of a dynamic structural analysis of the overall S/C referred to as quotCoupled Loads Analysis.quot This is usually performed by the quotLoads Groupquot and is out of the scope of this paper. The quotLoads Groupquot provides the stress analyst with given equivalent static loads which envelope the dynamic loads. It is important to make sure that the component does not see higher mechanical forces and this can usually be accomplished by means of checking the resonant frequencies of the structure as discussed under activity 4 below. Coupled loads transient analysis is repeated and refined as the design progresses to provide more realistic and less conservative load levels. Dynamic or time-phased stresses can also be calculated for a structure to determine the actual stress history and peaks. This requires calculation of stresses in conjunction with the coupled loads transient analysis. 2. Material Characterization: Selection of proper materials for a given structure is based on various considerations such as strength to weight (specific strength) and stiffness to weight (specific stiffness) ratios, ductility, resistance to corrosion (reference 2), thermal characteristics, cost, and ease of manufacturability. These and other structurally important material parameters are summarized in Table 3. [D] Table 3. Structural Goals Versus Material Parameters The stress analyst must understand the pros and cons of stock type, material temper, and fabrication processes, since these may significantly affect material characteristics. (reference 3). Certain types of materials, for example, graphite bonded joints, require special consideration and development testing may be necessary for each specific application. For structural model development and stress analysis, the selected material can be classified as follows: Homogeneity - Characterizes the dependence of structural properties on location within the material. Isotropy - A measure of directional dependence of properties. Conventional metals can be classified as homogeneous, isotropic. A composite lamina is homogeneous (macroscopically), transversely isotropic; whereas a laminate is in general nonhomogeneous and anisotropic. Ductility - A ductile material can undergo a significant amount of plastic deformation before ultimate failure as opposed to a brittle material, which fails without any appreciable yield or warning. A ductile material is less sensitive to cracks and flaws since it can yield locally and redistribute the excessive stresses. Reasonable fracture criterion will quantitatively screen out many non-ductile material applications. The classification of materials determines the type and the number of structural properties required in modeling the structure, which is discussed next. 3. Structural Modeling: A mathematical model of the structure is developed in order to predict deformations, internal forces, and stresses. It is based on an idealization of the actual structure using simplifying assumptions on geometry, loads, and boundary conditions. There are basically two different kinds of structural modeling the stress analyst can resort to: Computer model based on a numerical solution of the elasticity equations and boundary conditions that govern structural response. The part is represented using a finite number of degrees of freedom, by approximating the geometry using discretization. The most common numerical method used in structural analysis is the Finite Element (FE) Method. (Reference 4). There are several commercially available FE analysis computer programs. The one most widely used in the industry is NASTRAN. (Reference 5). The structure is represented by a collection of quotelementsquot connected at quotnodal points,quot or nodes, to each other. The governing equilibrium and compatibility equations are satisfied at each of the modal points and solved numerically. Results in the form of modal displacements, element internal forces, and stresses are output. Different kinds of structural analyses (e.g., stress, normal modes, forced dynamic response) that need to be performed should be identified so that the model can be built with necessary and sufficient detail. Analytical or hand calculations based on closed form solutions or empirical data given in various sources for different geometries and loading conditions (References 6 and 7). The concept of a quotfreebody diagramquot is used to isolate and identify the internal forces or reactions acting on the part. For a quotstatically determinatequot case these reactions are calculated based on the equations of static equilibrium. For quotstatically indeterminatequot reactions, additional simplifying assumptions and analyses need to be made regarding structure deformations and load paths. Structure stresses and deformations are determined using the applied loads and the calculated reactions, and based on the solutions or data available in the literature. The analyst can also utilize specialized and proven computer programs such as for the analysis of composites, pressure vessels, and truss structures. It is recommended that both approaches to structural modeling be used. The FE model should contain sufficient detail to represent the overall geometry and the important load paths.However, including quottoo muchquot detail such as fillets, joints, and fasteners may increase the modeling (pre-processing), computing (processing), and results (post-processing) times significantly and sometimes without any appreciable advantage. Including too much detail also compounds the difficulty of the model and the results assessment. Therefore, it is recommended that these structural details be analyzed using the internal forces obtained from the quotcoarsequot FE model and hand calculations. Hand calculations should also be used for the overall structure to approximately verify FE analysis results. 4. Determination of Structural Response: The structural model(s) developed, material properties, and loading conditions are used to calculate the structural response, which consists of displacement, internal force, and stress distributions. An important consideration in the determination of structure's response is whether or not it is linear. For a linear system the response is proportional to applied loads, and the principle of superposition applies, that is, the response due to the application of many loads is equal to the sum of individual responses to each one of the loads. This is not the case for a nonlinear system, e.g., a structure undergoing quotlargequot strain (material nonlinearity). The determination of response for a nonlinear system is much more involved and time consuming than that of a linear system. It also needs to be repeated for different magnitudes of the applied forces and cannot simply be obtained using the principle of superposition as for a linear system. The FE model should be designed to output the internal forces at various critical points of the structure. Corresponding stresses can then be calculated analytically using hand calculations. These calculations can be based on the basic strength of materials equations (References 8 and 9) as well as on solutions given for more complicated geometries in the literature. Some of the most common cases are listed here: bending of beams, torsion of bars, flat plates, shells of revolution and pressure vessels (References 6 and 7), direct bearing and shear stress (lugs and shear pins) (Reference 6), joints and fasteners (Reference 7), and honeycomb sandwich panels (References 10 and 11). For ductile materials under cyclic loading and for brittle materials, stress concentration factors given in the literature (Reference 12) should be used to predict the local stress peaks around geometry/loading discontinuities. It is necessary to ensure that the equivalent static loads used in the stress analysis conservatively represent the effect of the actual dynamic forces the structure will experience. In the early phases of design (i.e., conceptual and preliminary), this can be verified by determining the resonant frequencies of the structure and making sure they fall within the acceptable ranges determined by the coupled loads analysis. Note that natural frequencies and mode shapes of a structure are defined only for a linear system. They can be determined using the FEM and running an eigenvalue analysis on the structural model, which must possess the correct mass properties. For a nonlinear system, resonance conditions are determined not only by the frequency but also the magnitude of load fluctuations. A forced dynamic response simulation of the structure may be run using the FE model to investigate the resonances of a nonlinear structure. 5. Failure Modes Check: Adequacy of the structure to withstand the calculated forces and stresses is checked by calculating a margin of safety (MS) which is defined as MS = Structure Strength (Force or Stress) - 1 SF x Applied Force or Stress Structure Strength Failure is predicted for MS < 0. Failure stress or force is determined by means of failure theories (References 13 and 14). Some of the most commonly used ones are summarized below: Maximum Normal Stress Theory is used to predict ultimate failure withMS = Ftu /(SFx smax ) - 1. Here Ftu is the ultimate tensile strength of the material and smax is the maximum normal stress due to the external loading. In general, this theory is more applicable to brittle materials. Maximum Shear Stress (Tresca) Theory is used to conservatively predict ultimate failure for ductile materials. MS = Fsu /(SF x tmax ) - 1,where Fsu is the ultimate shear strength of the material and tmax is the predicted maximum shear stress. This theory can also be used to predict the onset of yield by replacing Fsu by Fsy, the shear yield strength of the material. Distortion Energy Theory is used for predicting the initiation of yield in a structure and gives more accurate results than the maximum shear stress theory. The margin of safety is given byMS = Fty /(SF x sVM) - 1, where Fty is the tensile yield strength, and sVM is the so called Von Mises stress. A similar criterion used for the failure prediction of laminated composite materials is the Tsai-Hill Theory (Reference 15). Structural Instability is predicted by first determining the critical buckling load of a structure Pcr. The margin of safety is given byMS = Pcr /(SF x Pa) - 1,where Pa is the load (compressive, shear) acting on the structure. Pcr for common shapes and loading can be found in the literature, e.g.; buckling strength of columns, flat and curved sheet panels with and without stiffeners, composite shapes, cylinders, crippling References 6 and 10). It is recommended that a conservative approach be taken in the modeling of boundary conditions because they significantly affect the critical buckling load. In certain weight critical cases, a post buckling analysis may be performed to access the remaining load carrying capacity of the structure. It is unconservative to use the quotlowquot stress modulus of elasticity (Young's Modulus) at quothighquot stresses. The value of Pcr depends on the modulus of elasticity which in turn depends on the stress level. Fracture Control Requirements of S/C parts are outlined in detail in related NASA documents (References 16 and 17). Parts are classified as contained, fail-safe, safe-life or low-release mass and analyzed accordingly. A part is considered contained if it can be shown that even if it broke and became loose, is contained within an enclosure and does not endanger the S/C (Reference 18). A fail-safe structure is a component with redundant load paths such that failure of one does not lead to the failure of the overall structure. A safe-life part must be inspected for cracks. Also, a crack propagation analysis needs to be performed to ensure adequate service life (Reference 19). A scatter factor typically equal to 4.0 and analogous to SF is used in this analysis. A low release-mass part weighs less than a specified threshold value and is considered non-fracture critical. The effect of simultaneously applied loads on certain structural components is assessed by means of interaction equations. These are empirically based relations used especially for stability (Reference 10) and fastener integrity (Reference 3). Strength of various mechanical components such as springs, bearings, and gears can be assessed based on machine design equations (Reference 14) or load ratings and specifications given by the manufacturer. 6. Optimization and Redesign (if Necessary): Several iterations may be made on the material, configuration, and the dimensions of a component before its design is finalized. Major trade studies and design modifications are considered in the preliminary design phase. Finer details are tuned in the later stages of the design using a similar iterative approach. 7. Documentation: All stress analysis results need to be properly documented with correct references to the models used in analysis, flight and test loads cases, and the safety factors. Proper documentation is essential to a successful stress analysis activity during design, fabrication, and verification testing. Technical Rationale: Systematic application of the stress analysis techniques outlined in the previous section enables the design engineer to establish accurate relationships between structural configuration, size, loading, and strength margins thus leading to more reliable and efficient structural designs. References: quotGeneral Environmental Verification for STS & ELV Payloads, Subsystems, and Components,quot GEVS-SE, NASA Goddard Space Flight Center, Jan. 1990. quotDesign Criteria for Controlling Stress Corrosion Cracking,quot MSFC-SPEC-522B, July 1, 1987. quotMilitary Handbook - Metallic Materials and Elements for Aerospace Vehicle Structures,quot MIL-HDBK-5F, Vol. 1&2, 1 Nov. 1990. quotConcepts and Applications of Finite Element Analysis,quot R. D. Cook, 2nd ed., John Wiley & Sons, 1981. quotUSERS MANUAL - MSC/NASTRAN VERSION 66,quot The MacNeal-Schwendler Corporation, Vol. 1 & 2, Nov. 1988. quotRoark's Formulas for Stress and Strain,quot W. C. Young, 6 ed., 1989. quotAeronautic Structures Manual,quot NASA Technical Memorandum, NASA TM X-73305, Vol.1-3, Marshall Space Flight Center, Aug. 1975. quotStrength of Materials/Elementary Theory and Problems,quot S. Timoshenko, 3nd ed., Robert E. Krieger Pub. Co., 1976. quotAircraft Structures,quot D. J. Peery and J. J. Azar, McGraw Hill, 1982. quotAnalysis and Design of Flight Vehicle Structures,quot E. F. Bruhn, S. R. Jacobs and Assoc., Inc., 1973. quotDesign Handbook for Honeycomb Sandwich Structures,quot Hexcel Corporation, 1988. quotStress Concentration Design Factors,quot R. E. Peterson, John Wiley & Sons, 1953. quotFailure of Materials in Mechanical Design - Analysis/Prediction/Prevention,quot J. A. Collins, John Wiley & Sons, 1981. quotMechanical Engineering Design,quot J. E. Shigley and L. D. Mitchell, McGraw Hill, 1983. quotMechanics of Composite Materials,quot R. M. Jones, McGraw Hill, 1975. quotFracture Control Requirements for Payloads using the National Space Transportation System,quot NHB 8071.1, NASA, Washington, D. C., 1988. quotGeneral Fracture Control Plan for Payloads using the Space Transportation System,quot NASA Goddard Space Flight Center, 1988. quotContainment Analysis for Fracture Control of STS Payloads,quot Swales and Associates, Inc., 1985. quotFatigue Crack Growth Computer Program - NASA/FLAGRO,quot Version 2.0, NASA Lyndon B. Johnson Space Flight Center, 1992. Assembly Acoustic Tests, Reliability Preferred Practice PT-TE-1407. Fiber Reinforced Polymer Composite Material Selection, Reliability Preferred Practice GD-DE-2210. Guidelines for Using Flight Loads Analysis as a Spacecraft Design Tool, Reliability Preferred PracticePD-AP-1317. Meteoroids/Space Debris, Reliability Preferred Practice PD-EC-1102. Pyrotechnic Shock, Reliability Preferred Practice PT-TE-1408. Random Vibration Testing, Reliability Preferred Practice PT-TE-1413. Sinusoidal Vibration, Reliability Preferred Practice PT-TE-1406. Structural Laminate Composites for Space Applications, Reliability Preferred Practice PD-ED-1217. | This practice has been used on theHubble Space Telescope, Gamma Ray Observatory, Superfluid Helium On-Orbit Transfer and Get Away Special (GAS) programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
818 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Qualification of Nonstandard Electrical, Electronic, and Electromechanical (EEE) Parts in Spaceflight Applications |  | Noncompliance with the use of NASA qualified parts would result in the use of unqualified and untested parts in spaceflight hardware. These unqualified parts could result in marginal performance and failure to perform in or survive the environmental exposure of space. | The source for selection of acceptable flight quality EEE parts for use on Goddard projects is the GSFC Preferred Parts List (PPL-20) (Reference 2). PPL-20 complements NASA Standard Electrical, Electronic, and Electromechanical (EEE) Parts List (NSPL) (MIL-STD-975) (Reference 1) by listing additional part types and part categories not included in MIL-STD-975. Recognizing that it is neither possible nor desirable to include all parts in the GSFC PPL and in the NSPL, the GSFC parts requirements make provision that limited numbers of parts not included in the PPL or the NSPL may be used if it is demonstrated that the parts are acceptable (Reference 5, section 5). The acceptability of nonstandard parts is enhanced by use of the part procurement specifications provided in Appendix E of PPL-20. The acceptability of these nonstandard parts must be demonstrated prior to commitment to design or use. Requests for approval to use nonstandard parts with supporting documentation are forwarded to the appropriate GSFC Project Office for review and approval. The practice described herein is used for demonstrating and documenting the acceptability of nonstandard parts for space flight use. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1418 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The practice of using approved nonstandard parts that have been appropriately demonstrated to be acceptable for the applications provides for a wider range of parts selection than are available with standard parts. These parts are at a quality level equal to that of Grades 1 or 2 standard parts. Implementation Method: Any EEE part that does not meet the criteria of a NASA Standard Part by being listed in the NASA Standard Parts List (NSPL) or the Preferred Parts List (PPL) is a nonstandard part that must be reviewed and accepted prior to use. It is the responsibility of the activity selecting the nonstandard part to demonstrate acceptability of the part prior to committing it to a design. Contractors document and approve their selection, application, evaluation, and acceptance criteria for nonstandard parts on a GSFC Form 4-15 (see Figures 1 & 2), Nonstandard Parts Approval Request (NSPAR)(Reference 5). The NSPAR forms are forwarded to the GSFC Project Office for review and GSFC approval. Figure 3 depicts the process flow of the nonstandard parts approval process. [D] Figure 1: Nonstandard Part Approval Request (NSPAR)/GSFC Form 4-15 [D] Figure 2: Nonstandard Part Approval Request/ GSFC Form 4-15 (Second Page) [D] Figure 3: Nonstandard Part Approval Process Flow Nonstandard Parts Specifications: Nonstandard parts must be at a quality level equal to that of Grade 1 or 2 standard parts and are procured in accordance with military, NASA, or contractor controlled specifications prepared in accordance with MIL-STD-490. Specifications for nonstandard parts are equal to the requirements of the nearest applicable standard part. Specifications and drawings fully identify the item being procured and include the physical, electrical, and environmental test requirements and quality assurance provisions including parts screening necessary to control manufacturing and acceptance. Specifications also describe marking, handling, packaging, storage of parts and the criteria for testing of parts taken from storage, and address environmental controls for temperature, humidity, particulate contamination, and controls for electrostatic discharge (ESD) for parts which are susceptible to ESD damage. Parts Qualification and Quality Conformance Inspection: Nonstandard parts have qualification bases traceable to test and inspection data at the part level in a manner consistent with the specification requirements of the nearest standard parts. The qualification is based on parts which have been produced by the same manufacturer using the same manufacturing technology as the nonstandard parts for which approval is being sought. Nonstandard parts undergo quality conformance inspection consistent with the specification requirements of the nearest standard parts. Hybrid Microcircuits: Hybrid microcircuits that are not included in the NSPL or the PPL are subject to nonstandard parts control. Their selection and approval is consistent with the requirements of MIL-H-38534B, General Specification for Microcircuits. Additional Parts Requirements Applicable to Nonstandard Parts: The following additional requirements pertain to nonstandard parts as applicable: Derating, Radiation Hardness, Screening Verification Tests, Destructive Physical Analyses, and Parts Identification List (Reference 5). Technical Rationale: The competent selection and acceptance of the proper EEE Parts for spaceflight use is an essential part of design of spacecraft hardware. With the rapidly growing availability of EEE parts that perform major system functions, the selection of parts has become a mainstream activity of electronic design. Further, the assurance that the selected part will perform reliably in the application, whether it be a small component with a limited mission life or an entire spacecraft with a long expected lifetime, continues to be a primary engineering responsibility. References: NASA Standard Electrical, Electronic, and Electromechanical Parts List, MIL-STD-975 (NSPL) GSFC Preferred Parts List (PPL) MIL-STD-490, Specification Practices MIL-H-38534B, General Specification for Hybrid Microcircuits Guidelines for Standard Payload Assurance Requirements (SPAR) for GSFC Orbital Projects | GFSC spaceflight projects approve the use of nonstandard parts on a per case basis. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
820 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Global Positioning System (GPS) Timing System |  | The use of an older, less accurate timing system would not provide the reliability, accuracy and the monitor and feedback capabilities that may be required or desired for timing of some present-day systems. | Use of the Global Positioning System (GPS) to provide a timing system with improved reliability and accuracy over the previous system. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1234; from NASA Technical Memorandum 4322A, NASA Reliability Practices. Benefit: In addition to improving the timing system's overall reliability by utilizing multiple timing sources, the upgrade from the previous Apollo-era designed system (using LORAN and WWV) provides improvements in the accuracy, monitoring and feedback capabilities. The timing system is used to provide timing commonality between instrumentation systems so data can be referenced with respect to time. Improving the reliability and accuracy of this system improves the time reference capabilities. Implementation Method: The primary time sources of the GPS Timing System are two GPS receivers and an Eastern Test Range UHF timing receiver. Each receiver's output feeds a Time Code Generator whose output feeds an Error Detection and Switching System. The inputs from different receivers are compared for bit error and phase error. Switching to a secondary input is performed if a fault is detected. The output is fed to Distribution Amplifiers for distribution throughout the KSC launch area (see Figure 1). [D] Figure 1. GPS Timing Block Diagram The GPS Timing System is equipped with a computer system that allows the operator to monitor all timing outputs including the signal source, signal level, distribution communication circuit number and end user. The timing signal is also displayed on an oscilloscope. This allows operators to quickly identify any distribution problems. On a daily basis, operators can page through every timing signal distributed from the LCC, checking the code and level of each signal. After checking all signals, the operator places the computer in auto mode, and the computer automatically checks the time difference between a cesium clock and all other timing units (two GPS receivers, the Eastern Test Range UHF timing receiver, two LORAN receivers, the Communication Instrumentation Facility time, ETR time and a portable clock time). The time differences are logged on a printer along with the following information from each GPS receiver: Greenwich Mean Time Satellites being tracked Oscillator control voltage Satellites selected Satellites deselected Antenna status The printout can then be reviewed by the operator and filed as part of the station log for historical purposes. The computer system is also equipped with a program that monitors the Timing Station at night and during other unmanned periods. The program pages through each time unit every 10 minutes, checking the time difference between the units and the Cesium clock. The time difference is logged on disk for use during the next work period when it is imported to a software application that can generate graphs for system analysis. Technical Rationale: Engineers at Kennedy Space Center require timing commonality between instrumentation systems so data can be referenced with respect to time. The development of the GPS allowed for the development of a timing system that is more accurate, more reliable and provides greater monitoring and feedback capabilities than the Apollo-era design it replaces. That system, using LORAN and WWV, resolved time to an accuracy of +\- 1 microsecond. The GPS system is accurate to within +\- 200 nanoseconds. Another advantage is that unlike LORAN, GPS satellites are capable of supplying the time and need not be used in conjunction with any other system. References: KSC Drawing - G79K20503, quotKSC Timing System Diagramquot KSC Drawing - 80K54337, quotLCC, Rm 2P22, Timing Systemquot | This practice has been used on Space Shuttle Program Kennedy Space Center (KSC) Launch Control Center (LCC) Timing System | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/18/2000
792 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Radiation Design Margin Requirement | Preferred Practice for Design & Test. The RDM requirement provides a systematic approach to managing the mission risk posed by uncertainties in both the radiation model and hardware susceptibility to radiation. The failure to apply a radiation factor to part selection and shielding design represents a significant risk that a critical subsystem or assembly will prove vulnerable to the radiation environment encountered during the mission. Design spacecraft hardware assemblies with the required radiation design margin (RDM) to assure that they can withstand ionization effects and displacement damage resulting from the flight radiation environment. The term “margin” does not imply a known factor of safety but rather accommodates the uncertainty in the radiation susceptibility predictions. The reliability requirement to survive for a period of time in the anticipated mission radiation environment is a spacecraft design driver. | The RDM requirement provides a systematic approach to managing the mission risk posed by uncertainties in both the radiation model and hardware susceptibility to radiation. The failure to apply a radiation factor to part selection and shielding design represents a significant risk that a critical subsystem or assembly will prove vulnerable to the radiation environment encountered during the mission. | Design spacecraft hardware assemblies with the required radiation design margin (RDM) to assure that they can withstand ionization effects and displacement damage resulting from the flight radiation environment. The term quotmarginquot does not imply a known factor of safety but rather accommodates the uncertainty in the radiation susceptibility predictions. The reliability requirement to survive for a period of time in the anticipated mission radiation environment is a spacecraft design driver. | JPL | 01/29/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1260; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The Radiation Design Margin (RDM) requirement is imposed on assemblies or subsystems to assure reliable operation and to minimize the risk, especially in mission critical applications. The general use of an RDM connotes action to overcome the inevitable uncertainties in environmental calculations and part radiation hardness determinations. Implementation Method: RDM is defined as the ratio of the part or component radiation capability in the given application to the expected radiation environment at the part or component location during the mission. The part/component radiation capability is defined to be the fluence (or dose), flux (or dose rate) of charged particles, or nuclear radiation which will produce enough change (degradation or radiation induced interference) in the part characteristics to cause the part to operate outside of specification for the particular circuit application. An RDM value of 2, for example, would mean that the hardware is designed to withstand twice the radiation predicted by the radiation model. Based on flight experiences, it is standard practice at JPL for most applications to require an RDM of 2 if only the inadvertent shielding of the surrounding spacecraft or instrument enclosure materials are considered in the radiation/shielding analysis. However it is required to invoke an RDM of 3 when the local shielding, such as component/part packaging or spot shielding, is taken into account. The RDM requirement does not apply directly to single event effects (SEE) such as single event upset (SEU), single event latchup (SEL), etc. However, SEE margins are derived by placing limits on minimum SEE sensitivity and by using design-case mission environments that account for the statistical probabilities of solar flares. Radiation Effects (1) Long-Term Ionization Effects Damage to electronics and materials may arise from the long-term effects of ionizing radiation. Ionization occurs when charged particles (or electrons from gamma-ray interactions) transfer small amounts of energy to electrons in the target material. The unit of ionization is the rad (material must be specified), which is defined as 100 erg/g of material. In semiconductor devices, ionization produces electron-hole pairs within the semiconductor and insulators (such as oxides). Some of this charge will be trapped at the semiconductor/insulator surface. In MOS structures, the trapped charge will cause a shift in the gate threshold voltage. Mobility (which affects switching speed and drive current) is also degraded. In addition to the gate oxide, ionization also affects the field oxide, which is used for isolation in MOS integrated circuits. This will result in extremely large leakage currents if the threshold shifts are large enough to cause inversion. Field oxide failure is an important failure mode for many commercial CMOS devices. In bipolar devices, trapped charges at oxide layers cause two effects. The traps increase surface recombination, decreasing the gain of bipolar transistors. If the trap density is high enough, an inversion layer can be created in p-doped regions that increases the surface area of the junction. This also affects transistor gain, and may cause substantial increases in leakage current. In optical materials, long-term ionization effects appear primarily as an increase in optical absorption. These usually are manifestations of charge trapping at a pre-existing defect, so the absorption rate is a strong function of the initial material properties. For example, fused quartz generally colors less than alkali glasses from a given ionizing dose. In quartz crystal used for precision oscillators or filters, long-term ionization effects can produce significant resonant frequency shifts. Again, there is a strong dependence upon the type of material used. Natural quartz shows the largest frequency shift for a given ionizing dose; synthetic quartz shows less, and swept synthetic quartz even less. In these cases, selection of the quartz crystal growth method can minimize the potential effect. The devices and materials of concern and the most serious radiation induced effects are: MOS devices (threshold voltage shift, decrease in drive current and switching speed, increase in leakage current). Bipolar transistors (hFE degradation, especially at low collector current; leakage current), and junction field effects transistors (JFETs) (enhanced source-drain leakage current). Analog microcircuits (offset voltage, offset current and bias-current changes, gain degradation). Digital microcircuits (enhanced transistor leakage, or logic failure due to decrease in gain (bipolar devices) or changes in threshold voltage and switching speed (CMOS)). Quartz resonant crystals (frequency shifts). Optical materials (increased absorption). External polymeric surfaces (mechanical degradation). (2) Transient Ionization Effects (Interference) Interference is defined as transient ionization effects that persist only while the electronics are being irradiated, and whose severity is generally proportional to the dose rate. Interference effects depend primarily on the rate of ionization energy deposition, i.e., the dose rate measured in rads (material)/sec. There are four types of interference in electronic devices and optical materials: Primary photocurrents in low current input stages to the electronics. Electron emission from cathodes of electron multiplier-type detectors. Ionization-induced conductivity in photo-sensitive materials, such as those in detector surfaces. Ionization-induced fluorescence in optical materials such as detector windows and lenses (fluorescence efficiencies vary strongly with the material). (3) Displacement Effects Displacement of atoms in crystal lattices cause permanent changes in material properties. The expected proton and electron fluences usually do not represent as severe an environment for displacement effects as for long-term ionization effects. Therefore, only the most sensitive devices will be affected significantly by displacement effects. Displacement effects can impact the following electronic devices and properties: Bipolar transistors (gain, saturation voltage) PN junction diodes (forward voltage, leakage current). Light emitting diodes (LED) (light emitting efficiency). Semiconductor photodetectors (sensitivity). Linear integrated circuits incorporating lateral p-n-p transistors. RDM Factor Determination (1) Radiation Hardness Determination There are at least five quantities that can contribute to uncertainty in part radiation susceptibility: Statistical variations in parts from a specific manufacturing line, Part type, Manufacturing process, Circuit design, and Circuit application. There are many different part types, many circuit designs and applications and perhaps several different manufacturing processes. Consequently, the uncertainty in the capability of the part to withstand radiation has to be sufficiently large to account for the large variations from part to part. Most of these part variations are difficult to quantify. Testing is the only method for determining the radiation capability to be expected in a given flight lot, but this typically is done with only a small sample of devices. Testing conditions may also affect results. For some linear integrated circuit devices, the total ionizing dose (TID) capability could drop dramatically if tested with a low dose rate instead of a high dose rate. For example, OP42 was formerly rated a radiation-hard device (> 100 Krads), but was recently found very soft (~ 15 Krads or lower) when tested with the low dose rate more typical of a flight environment. As modern electronic parts have higher capacity and smaller volume compared to those used on Voyager and other older spacecraft, they may be more delicate and vulnerable to deposited charges. (See quotRadiation Effects.quot) It will be prudent to carefully examine RDMs of higher magnitude on future spacecraft programs or to refine the part radiation hardness determination technique if an RDM of 2 or lower is demanded. Part radiation hardness testing is considered a cost driver because more accurate testing requires more samples, more realistic radiation sources and conditions simulating spaceflight, and longer test time. (2) Radiation Environment Calculation Definition of the local ambient radiation environment is dependent on the mission design, the environmental radiation models, the radiation transport code, and the spacecraft mass model. The calculated radiation environment might be the total ionizing dose (TID), the 20 MeV equivalent proton fluence for displacement damage, or the flux for detector interference effects. The uncertainty in the radiation model depends on the modeled environment and on the mission design. Uncertainties in the mission design are difficult to quantify. Parameters include the trajectory (heliocentric distance, mission length, altitude, inclination, etc.) and launch date. The uncertainty in the radiation environment depends on the environment in question. For example, prediction of the proton fluences from solar flares is treated probabilistically, and the discrepancy between predictions for the 10 MeV fluence between two different solar flare models is a factor of 2 (at the 95 percent confidence level) (Ref. 1). Similarly, the uncertainties in the Jovian trapped electron environment and the Earthís trapped radiation proton model AP8 are estimated to be also a factor of 2. The uncertainties resulting from the use of different radiation transport codes and different spacecraft mass models are generally less than a factor of 2 (Ref. 1). Typically, once the mission design is confirmed, the TID as a function of shielding thickness (dose-depth data) are generated for a simplified geometric mass model such as a spherical shell model. Figure 1 is an example for a flight mission at 1 AU from the sun during the solar max period. It is standard practice to apply the dose-depth curve of 95 percent confidence level for the flight assembly design. This radiation dose curve can be used to obtain conservative quotfirst-lookquot shielded dose values without hardware configuration modeling. These dose plots should only be used to obtain dose value by using the minimum shield thickness applicable to a given hardware location. Since these plots do not represent the flight hardware configurations, they should be used for design assessment only if they are applied in a conservative manner (minimum shield thickness used). If a part does not meet the RDM value of 2 requirement based on this conservative TID level, a three-dimensional mass model simulating the flight assembly is then constructed for the radiation transport code. The resulting TID level will be lower than the TID data from the spherical shell model, and therefore the part is more likely to meet the RDM requirement. However, when the part/component package has to be included in the 3D mass model or a spot shield has to be added, the RDM is increased from 2 to 3 as explained earlier. The more extensive radiation/shielding calculations tend to be a cost driver, but it relieves the shielding requirement and saves more mass. [D] Figure 1. Radiation Dose from Solar Flare Protons for 1 Year at 1 AU Technical Rationale: The uncertainties in radiation environment estimates and the part or component radiation capability determinations lead to RDM values between 3.5 to 11.5 (Ref. 1). Historically, the introduction of an RDM value of 2 stems from the Voyager project and was established based solely on available mass. An RDM much greater than 2, perhaps as high as 10, would have been selected to cover all uncertainties were there sufficient mass available (Ref. 1). The RDM of 3 is imposed when the local shielding such as component/part packaging or spot shielding is taken into account. There is an implied greater risk associated with taking the local shielding into consideration because this is done in cases where soft parts must be used; one is dependent on local shielding and its calculated effectiveness rather than on an inherently hard part. The selection of an RDM may be somewhat arbitrary and will tend to be driven by mass limitations, acceptable risk versus cost, and the overall radiation hardness program. Resource and mass limitations which preclude usage of conservative RDMs are typically imposed on flight projects. Based on the ìbestî radiation model at the time, the part radiation hardness test data, and the expected mass and other resource limitations, a radiation design factor of 2 (3 if local shielding is considered) is required for spacecraft elements intended to operate during a flight mission. The term used to describe this radiation design factor, radiation design margin or RDM, may be a misnomer. quotDesign marginquot suggests a known factor of safety, which translates as a high degree of certainty of survival in the radiation environment. Instead, the RDM arises from significant uncertainties in all the elements of the radiation susceptibility calculations. It may be more appropriate to refer to a radiation design factor instead of implying the existence of a conservative margin. An RDM value of 2 should not be interpreted as a 100 percent margin as it is sometimes misconstrued. Although an RDM of 2 does not cover the uncertainties, it proved affordable and effective on the Voyager mission. As defined earlier, the RDM is the ratio of the part or component radiation capability, in the given application, to withstand the expected radiation environment at the part or component location for a flight mission. The use of RDM as a spacecraft design tool acknowledges that there are uncertainties in environmental calculations and part radiation hardness determinations. References: JPL IOM 5217-88-39, quotRadiation Design Margins,quot S. B. Gabriel to Distribution, September 22, 1988. JPL IOM 5217-91-208, quotRadiation Design Margin for CRAF/Cassini Missions,quot G. Murphy and R. Kemski to Distribution, February 14, 1992. JPL IOM 5137-87-233, quotComparison of Predicted and Observed Radiation Levels for Voyager Outer Planet Flybys,quot N. Divine and R. Ridenoure to C.E. Kohlhase, August 5, 1987. quotTotal Dose Hardness Assurance Design Guidelines,quot Defense Nuclear Agency Report No. DNA5909F, February, 1982. Environmental Factors, Reliability Preferred Practice No. PD-ED-1101 Design and Analysis of Electronic Circuits for Worst Case Environments and Part Variations, Reliability Preferred Practice No. PD-ED-1212. | JPL has applied an RDM requirement to Voyager and all subsequent flight projects. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
791 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Risk Rating of Problem/Failure Reports | The identification of project/task risk just prior to launch/delivery becomes a costly and time-consuming activity. Early and continuous risk ratings enable management to focus on the issues with the highest probability of impacting mission success. Project management is provided with visibility to a concise subset (<5 percent) of a large information base focusing on the key problematic areas in a timely fashion. | The identification of Project/Task risk just prior to launch/delivery becomes a costly and time-consuming activity. Even with a protracted, intensive study, some key issues may be missed. | Problem/failure (P/F) reports are assigned a two-factor set of ratings: a failure effect rating and a failure cause/corrective action rating. The composite rating is used to assess the hardware/software residual launch and mission risk. The high risk P/F reports are labeled quotRed Flagquot. | JPL | 01/29/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1305, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Risk rating enables management to focus on the issues with the highest probability of impacting mission success. Project management is provided with visibility to a concise subset (< 5 percent) of a large information base focusing on the key problematic areas in a timely fashion. Implementation Method: A two-factored rating is assigned to each Problem/Failure (P/F) report. Figure 1 is a graphical outline of the rating system and indicates the basis of the quotRed Flagquot risk determination. All closed P/F reports having a potentially significant or major failure effect (Failure Effect Rating of 2 or 3), coupled with uncertain corrective action effectiveness (Failure Cause/Corrective Action rating of 3 or 4), are defined as quotRed Flagquot P/F reports. [D] Figure 1. P/FR Rating Chart quotRed Flagquot Classification: Each Red Flag P/F report has an attached statement that summarizes the symptom, cause, effect, potential mission impact, and corrective action for the P/F report, as well as the rationale for accepting the residual risk. The Project/Task Manager and the Contractor Project Manager (if applicable) review, approve, and sign all Red Flag P/F report closures to acknowledge understanding and acceptance of the defined residual mission risk. 3. All Red Flag P/F reports are discussed at subsequent formal reviews and reported in Monthly Project/Task Management Reports. Each individual Red Flag P/F report is evaluated for its contribution to the overall mission risk. The total set of Red Flag P/F reports must be evaluated for any presentation of mission risk. The Red Flag P/F report contribution to mission risk is a topic for discussion at the preship and the prelaunch reviews. In addition, any unrated P/F report open for 60 days or longer is reviewed and assigned a two-factored rating to determine if there are potential Red Flag issues. As indicated in Figure 1, the two numerically indicated components of the P/F report rating system are the Failure Effect Rating and the composite Failure Cause/Corrective Action Rating. Failure Effect Rating: The first factor, the quotFailure Effect Rating,quot is an assessment of the consequence or impact of the P/F if it had occurred in flight. It is not an assessment of the adequacy of the corrective action. Redundancy is not considered in making the assessment. The assessment is either 1, 2, or 3 based on the following criteria: Rating 1: Negligible effect on mission performance. No appreciable change in functional capability. Minor degradation of engineering/science data. Support equipment or test equipment P/Fs. Support equipment, test equipment, or operator-induced P/Fs. Workmanship failures found at initial test. Drawing errors found at initial test. Note: For items c, d, e, and f, after correction of the underlying P/F cause, the hardware/software must be certified to be in flightworthy condition and the failed test must be successfully completed. Rating 2: Significant degradation to mission performance. Appreciable change in functional capability. Appreciable degradation of engineering/science data. Significant operational difficulties or constraints. Reduction in lifetime. Significant impact on system safety. Rating 3: Major degradation to mission performance or catastrophic impact on system safety. Failure Cause/Corrective Action Rating: The second factor, the quotFailure Cause/Corrective Action Rating,quot is an assessment, with confidence, that the failure cause has been understood correctly, and the confidence that the corrective action is effective and will preclude recurrence of the P/F. The assessment is either 1, 2, 3, or 4 based on the following criteria: Rating 1: The cause of the P/F has been determined with confidence by analysis and/or test. An effective corrective action has been determined, implemented, and verified. Residual risk is considered minimum. Rating 2: The cause of P/F has not been determined with confidence. However, corrective action is considered effective in precluding the observed P/F symptom. Residual risk is considered minimum. Rating 3: The cause is considered to be quotknownquot and quotunderstoodquot with confidence. The correction accomplished within constraints (e.g., time, resources, test capability) does not satisfy with confidence all doubts or concerns regarding the corrective action and its effectiveness for precluding recurrence; or, the correction is considered to be a symptomatic treatment without ensuring an effective overall correction of the basic cause. There is residual risk. Rating 4: The cause has not been defined with confidence. The correction of the P/F is considered to have an uncertain effectiveness for precluding recurrence. There is a residual risk. Technical Rationale: The P/F report risk rating system is a time-proven technique that permits a Project/Task to close all P/F incidents in a timely and efficient manner and yet retain the critical information relating to mission risk in a highly visible and specific format. References: quotProblem/Failure Report Independent Review/Approval,quot Reliability Preferred Practice PD-AP-1304 | This practice has been used on Mariners, Seasat, IRAS, VGR, VIK, GLL and MGN programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
790 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Problem/Failure Report Independent Review/Approval | Preferred Practice for Design & Test. The utilization of a P/F reporting system that has an independent P/F closure process is a major factor in the elimination of in-flight hardware/software failures attributed to preflight P/F that were not resolved adequately prior to launch. Problem/Failure (P/F) Reports are reviewed independently and approved by reliability engineering specialists to ensure objectivity and integrity in the closure process. | The utilization of a P/F reporting system that has an effective independent P/F closure process is a major factor in the elimination of in-flight hardware/software failures attributed to preflight P/F that were not resolved adequately prior to launch. | Problem/Failure (P/F) Reports are reviewed independently and approved by reliability engineering specialists to ensure objectivity and integrity in the closure process. This practice assures that the analysis realistically bounds the extent of the P/F, and the corrective action and its verification are successfully accomplished. The key elements are: Analysis must address the problem. Corrective action must address the analysis and the problem. Analysis must address the effect on other items. Corrective action must have been implemented. Item must have passed the gate that caused the P/F - the hardware/software must be successfully retested. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1304, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Any independent review process increases the level of compliance of the subject process. It also broadens the scope and depth of experience available for each individual issue without the need for a large supporting staff at each supplier organization. Also, an in-place independent review structure improves the rate of data flow for a given level of effort. Implementation Method: There are several levels of independent review in a sequential review process. A Problem/Failure (P/F) not only affects the subject hardware/software but other elements of the system as well. At the first level of independent review, the project/task system engineering organization reviews all identified system related P/F reports, all unknown cause P/F reports, all design related P/F reports, and all critical concern P/F reports that are identified as "Red Flag." At any level of the independent review process, specialists in the area of the P/F can be consulted for their expertise. As a subset of the system level review all project/task systems test or ground operations P/F reports are routed to the test and operations manager for verification of closure adequacy. All P/F reports not initially sent to systems, as well as those P/F reports that have been approved by systems, are sent to the project/task reliability engineering organization. Reliability engineering reviews each P/F report for adherence to the P/F reporting requirements, for completeness and lucidity of the technical contents, for uniformity of rating standards, and for identification of generic P/F or broad issue-related P/F. At this point in the P/F review process, issue-specific specialists can be consulted on issues requiring their field of expertise (safety, environmental factors, etc.) or to explore broader issues raised by an examination of the P/F that were not apparent at the internal P/F reporting level. P/F reports can be recycled back up the review chain if conditions are uncovered in the review process that warrant such an occurrence. The final step in the independent P/F closure process is the Project Management review and approval cycle. In the optimum review process, the status of closed, nonrisk P/F reports is provided by periodic P/F reporting status reports. The critical P/F reports, classified by the "Red Flag" rating, are routed through the appropriate Project Management officials to determine the P/F impact on schedule and future funding, and to identify an element of residual mission risk. Technical Rationale: Independent P/F reporting closure is a key to reducing mission risk. On a recent mission, 25 percent of the contractor-submitted Problem/Failure Reports (P/FRs) had risk rating changes as a result of independent review by Reliability Engineering. Of the 25 percent changed, 1/4 were significant or red flag P/FRs (i.e., 1/16 or 6 percent were major issues). This process results in fewer schedule delays and attendant funding problems late in the Project/Task, by providing the earliest isolation and documentation of P/F that can pose serious mission consequences. Generic P/F can be detected and consolidated in an efficient manner, with attendant cost savings. The P/F reporting system is a resource for providing visibility to all levels of management in near real-time. References: "Risk Rating of Problem/Failure Reports," Reliability Preferred Practice PD-AP-1305. | This practice has been used on the Mariners, Seasat, IRAS, VGR, VIK, GLL and MGN programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
794 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Thermal Analysis of Electronic Assemblies to the Piece Part Level | Preferred Practice for Design & Test. If a Piece Part thermal Analysis (PPTA) is not performed, more than 75 percent of the overstressed piece parts could go undetected. If a PPTA is performed, but only on significant power dissipators, then approximately 70 percent of the thermally overstressed piece parts could go undetected. Quantification of the thermal fatigue design life requirements and performance evaluation of thermal fatigue sensitive elements (solder joints, bondlines, etc.) can only be accomplished by incorporating results of a PPTA. Perform a piece part thermal analysis that includes all piece parts in support of the part stress analysis. Also include fatigue sensitive elements of the assembly such as interconnects (solder joints, bondlines, wirebonds, etc.). | If a PPTA is not performed, more than 75 percent of the overstressed piece parts could go undetected. If a PPTA is performed, but only on significant power dissipators, then approximately 70 percent of the thermally overstressed piece parts could go undetected. Quantification of the thermal fatigue design life requirements and performance evaluation of thermal fatigue sensitive elements (solder joints, bondlines, etc.) can only be accomplished by incorporating results of a PPTA. | Perform a piece part thermal analysis that includes all piece parts in support of the part stress analysis. Also include fatigue sensitive elements of the assembly such as interconnects (solder joints, bondlines, wirebonds, etc.). | JPL | 01/30/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1306, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Allows the thermally overstressed parts to be identified and assessed for risk (instead of just the electrically overstressed parts). Allows the design life requirements of the thermal fatigue sensitive elements (solder joints, bondlines, wirebonds, etc.) to be quantified. Implementation Method: On Class A and B programs, piece part thermal analysis (PPTA) is performed on all electronic assembly designs, including all engineering change requests in support of the part stress analysis (PSA). A policy is established mandating that the required design life of all thermal fatigue sensitive elements be quantified via a PPTA and a life cycle analysis. Moreover, it should be the policy of the contracting agency that this analysis be a deliverable and be independently reviewed by the contracting agency. Technical Rationale: Reliability engineering is the discipline of identifying, risk rating, and eliminating the quottall polesquot or quotweak linksquot in a design. Two of the most significant reliability concerns for spaceflight hardware are reductions in the mission life of the electronic designs due to excessive junction temperatures or thermal fatigue. A proper PPTA can be used to verify that the temperature derating requirements specified in the PSA have been satisfied. The PPTA is also one of the key tools for quantifying the required design life of fatigue sensitive elements. Several reliability practices case studies were performed on the Magellan (MGN) synthetic aperture radar (SAR). The results and conclusions of these studies are summarized below: Case Study Background: The MGN SAR consists of 9 prime and 9 redundant units totaling 40 slices. In all, there are more than 15,000 piece parts in this payload. The MGN SAR was chosen for a series of reliability practice case studies because its design was typical of industry for an electronic payload. More specifically, the electrical design, mechanical packaging, and quotblack boxquot thermal design techniques were very typical of those employed by industry. Role of PPTA In Part Stress Analysis: All of the waivers issued as a result of the MGN SAR PSA effort were reviewed to quantify the number of electrical overstresses versus thermal overstresses. Note that the PSAs and PPTAs did identify many overstresses for which design changes were made. There were 38 waivers issued for part stress reasons covering 211 piece parts. It was found that more than 75 percent of the 211 parts required waiving due to thermal overstresses. The remaining overstresses were for either voltage, current, or power. Thus, if the PPTA had not been performed, only 25 percent (or less) of the waived overstresses would have been identified and understood. Analyzing All Piece Parts Versus Significant Power Dissipators: This case study evaluated the feasibility of only analyzing the key or quotsignificantquot power dissipators. The MGN radar contractor used the MIL-STD-1540 philosophy of box level design temperature margins/levels (not JPL's higher levels). The contractor also used parts derating guidelines very similar to MIL-STD-975G, except that they derated junction temperatures to 105 degrees C instead of the 110 degrees C called out in 975G. One PPTA was performed on each slice. The PPTA's analyzed all piece parts in a slice, even the nondissipating ones. The thermally overstressed piece parts identified in the PPTAs were tabulated according to three different definitions of key or quotsignificantquot power dissipation. They were to analyze only parts with over 100 milliwatts dissipation, over 50 milliwatts dissipation, and no power dissipation. All parts that would have been identified by these three definitions are shown in Table 1. Table 1. Tabulation of thermally overstressed piece parts [D] In fact, the study showed that 10 percent of the thermally overstressed parts dissipated no power. It is quite obvious that the temperature of a piece part is a function of many more variables than just the part's power dissipation. Therefore, all pieceparts should be analyzed when performing a PPTA. Also note that realistic circuit worst-case power dissipation is a key assumption, not just maximum part power capability. Thermal Fatigue Versus Design Life: A study was performed (Reference 1) to define the thermal fatigue design life requirements for various lead attachment arrangements. The PPTA was found to be a key analytical tool in quantifying the design life requirements of the solder joints. References: JPL Publication 89-35, quotMagellan/Galileo Solder Joint Failure Analysis and Recommendations,quot September 15, 1989. quotPart Electrical Stress Analysis,quot Reliability Preferred Practice No. PD-AP-1303 quotEnvironmental Factors,quot Reliability Preferred Practice No. PD-EC-1101. quotThermal Vacuum versus Thermal Atmospheric Testing of Electronic Assemblies,quot Reliability Preferred Practice No. PT-TE-1409. quotThermographic Mapping,quot Reliability Preferred Practice No. PT-TE-1403. | This practice has been used on the Magellan program. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
793 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Characterization of RF Subsystem Susceptibility to Spurious Signals | Preferred Practice for Design & Test. If these reliability analysis and test activities are not performed, transmitters may generate spurious signals at the levels and in the frequency bands that adversely affect receiver or transmitter performance. Reliable design of spacecraft radios requires the analysis and test of hardware responses to spurious emissions that may degrade communications performance. Prior to hardware integration on the spacecraft, receivers and transmitters are tested to verify their compatibility with respect to emissions of conducted radio frequency (RF) signals and susceptibility to these signals. This reliability practice is applied to receivers and transmitters located in the same subsystem and to those installed in different subsystems on the same spacecraft. | If these reliability analysis and test activities are not performed: Transmitters may generate spurious signals at the levels and in the frequency bands which adversely affect receiver performance. Receivers may generate signals at the levels and in the frequency bands which adversely affect transmitter performance. | Reliable design of spacecraft radios requires the analysis and test of hardware responses to spurious emissions which may degrade communications performance. Prior to hardware integration on the spacecraft, receivers and transmitters are tested to verify their compatibility with respect to emissions of conducted radio frequency (RF) signals and susceptibility to these signals. This reliability practice is applied to receivers and transmitters located in the same subsystem and to those installed in different subsystems on the same spacecraft. This early test to identify and resolve radio compatibility problems reduces the risk of uplink/downlink degradation which might threaten mission objectives. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1261; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: This practice validates the compatibility of spacecraft receivers and transmitters. If electromagnetic compatibility problems are identified early in radio design, solutions can be developed, implemented, and verified prior to the integration of the hardware on the spacecraft. Implementation Method: The test configuration should simulate the interconnection of the receivers and transmitters in the system, including simulation of the estimated isolation vs. frequency. The tests are also designed to exercise the full tuning range and the full input signal dynamic range specified for the receiver. Performance criteria which are verified include: Absence of "self-lock," where the receiver does not lock to the output signal from its interconnected transmitter. Absence of "false-lock," where the receiver does not lock to a signal other than its receive frequency applied to the receiver input. Absence of frequency "pushing," where the signal input to the receiver changes the frequency of the receiver's voltage-controlled local oscillators. Absence of dynamic range degradation, both at minimum signal (i.e., receiver threshold) and at maximum signal (i.e., receiver saturation), over the entire receive frequency band. The following RF design components are defined prior to testing: Receiver architecture. Transmitter architecture. Subsystem configuration. System configuration. Receiver/transmitter isolation vs. frequency estimates. Characterization and verification of spurious responses and spurious emissions is performed as a set of phased activities: Step 1: Characterize the spurious responses at the input port to the subsystem. The result of this effort will be a plot of response levels in dBmWatts vs. frequency. Note: dBmWatt is defined as: 10 log10 (PIN/1 mW) Step 2: Characterize the spurious emissions at the output port of the subsystem. The result of this effort will be a plot of the emission levels in dB vs. frequency. Step 3: Compare the subsystem spurious response levels with the subsystem spurious emission levels. The emission levels must be substantially lower (a minimum of 9 dB) than the response levels at all frequencies to demonstrate self-compatibility of the RF subsystem. This comparison will produce a plot of the emission vs. response margin in units of dB vs. frequency. Step 4: Translate the emissions of other RF subsystems on the spacecraft as received by the input port of the subsystem being evaluated using the available information on the antenna port-to-port isolation vs. frequency. These translated emissions are then to be compared to the subsystem spurious response characteristics. Again, these translated emission levels must be substantially lower (a minimum of 9 dB) than the subsystem response levels at all frequencies to demonstrate system compatibility. The result of this step will be another plot of the margin in units of dB vs. frequency. Step 5: Translate the susceptibilities of other RF subsystems on the spacecraft to the output port of the subsystem being evaluated using the available information on the antenna port-to-port isolation vs. frequency. These translated susceptibilities are then compared to the subsystem spurious emissions characteristics. These translated response levels must be substantially higher (a minimum of 9dB) than the subsystem emission levels at all frequencies to demonstrate system compatibility. The result of this effort will be yet another plot of the margin in dB vs. frequency. Step 6: The final step is to solve identified problems by filtering the spurious emissions output of each RF subsystem as necessary to restore dB of positive margin below the spurious susceptibility levels. Technical Rationale: Design and development of receivers and transmitters, particularly those located in different subsystems, are often pursued independently. Early identification and resolution of radio compatibility problems requires that the developer: Examine the frequency scheme of each receiver and transmitter on the spacecraft, and identify the known spurious responses and emissions for each. Based on the planned interconnection of each subsystem via the antenna(s), and on the isolation provided between each of the interconnected subsystems, quantify the margin for each subsystem at the input and output ports as a function of frequency. The scheduling of these two activities should be planned to provide time to implement corrective action, such as the addition of RF filters, prior to spacecraft integration. After this time, such solutions become very expensive and pose risks to the spacecraft launch schedule. Related Practices: Spurious Radiated Interference Awareness, Reliability Preferred Practice No. PD-AP-1310 Radiated Susceptibility System Verification, Reliability Preferred Practice No. PD-TE-1416 | This practice has been used on Voyager, Galileo, Cassini. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
795 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Failure Modes, Effects and Criticality Analysis (FMECA) | Preferred Practice for Design & Test. Without a formal FMECA process, the system design integrity would be determined by the experience and rigor of a large number of individual design engineers. There would be no means of verifying that design risk has been minimized to a degree which yields a high confidence in achieving the mission goals. Analyze all systems to identify potential failure modes by using a systematic study starting at the piece part or circuit functional block level and working up through assemblies and subsystems. Require formal project acceptance of any residual system risk identified by this process. | Without a formal FMECA process, the system design integrity would be determined by the experience and rigor of a large number of individual design engineers. There would be no means of verifying that design risk has been minimized to a degree which yields a high confidence in achieving the mission goals. | Analyze all systems to identify potential failure modes by using a systematic study starting at the piece part or circuit functional block level and working up through assemblies and subsystems. Require formal project acceptance of any residual system risk identified by this process. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1307, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: The FMECA process identifies mission critical failure modes and thereby precipitates formal acknowledgment of the risk to the project and provides an impetus for design alteration. Implementation Method: Through the use of formal spread sheets, each potential failure within an assembly is recorded together with its resultant assembly, subsystem, and system effect. The severity of the system failure effect is assigned from a pre-defined list ranging from "negligible effect" to "mission catastrophic." Design alterations can be made at the circuit level (thereby modifying the assembly level) to eliminate a failure mode or to reduce its severity. The remaining failures are evaluated as potential subsystem failures by accounting for possible redundancy or work-arounds. Again design alterations may be invoked. Those remaining up to the system level are reported as single points of failure (SPFs), and the project makes a conscious decision to either retain them or to initiate corrective action. Technical Rationale: Every technical mission carries with it a degree of risk. A mechanism is needed to identify and quantify the risk to permit decisions to be made which will ultimately reduce the risk to the minimum permissible level within the project cost, schedule, and performance constraints. Because most spacecraft systems are extremely complex, a method of risk identification must be used which has total visibility into the system. The FMECA has been recognized as such an approach and, if implemented rigorously, will provide the necessary visibility. The process requires the assumption of a failure of each part of each unit. The credible failure modes are identified for each part (e.g., capacitors can short or open). If a piece part level FMECA is required by project definition, a line item must be entered for each identified mode of each part, e.g., "C23 shorts". If a project employs a high degree of redundancy, the complexity of a part level FMECA is unnecessary because a presumably redundant element will perform the function. Thus a functional level FMECA is adequate, e.g., "the amplifier chain formed by Q14, Q15, and Q16 and their associated parts has very low gain". This failure may have many root part failure causes but if all possible failure modes of the block are identified, e.g., "low gain, oscillation, high gain, high harmonic distortion", there is no value in recording the individual part causes. The most essential analysis in a design which uses redundancy is that of the cross-strapping networks. For this reason, a parts level FMECA is considered mandatory for all cross-strapped redundant elements, either inside an assembly or at an external interface. | This practice has been used on the Viking, Voyager, Magellan and Galileo programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
797 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Analysis of Radiated EMI From ESD Events Caused by Space Charging | Preferred Practice for Design & Test. EMI problems resulting from ESD events can degrade the performance of spacecraft in flight, when it is too late to implement design fixes. Modeling is utilized for the analysis of conducted and radiated electromagnetic interference (EMI) caused by an electrostatic discharge (ESD) event. The modeling requires the combined use of a SPICE (Ref. 1), or other circuit analysis code and a wire antenna code based on the method of moments, and is primarily applicable to wires, cables, and connectors. | EMI problems resulting from ESD events can degrade the performance of spacecraft in flight, when it is too late to implement design fixes. | Modeling is utilized for the analysis of conducted and radiated electromagnetic interference (EMI) caused by an electrostatic discharge (ESD) event. The modeling requires the combined use of a SPICE (Ref. 1), or other circuit analysis code and a wire antenna code based on the method of moments, and is primarily applicable to wires, cables, and connectors. | JPL | 01/30/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1309, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: The use of a combined SPICE circuit analysis code and a method of moments code for the study of possible conducted and radiated Electromagnetic Interference (EMI) resulting from an Electrostatic Discharge (ESD) event, allow the assessment of EMI noise coupling onto electronic circuit interfaces (Ref. 2). Implementation Method: Background: Surface charging can develop on satellite exterior surfaces as a result of the interactions between the surfaces and the space plasma environment. Considerable research has been done in assessing charging mechanisms that are present when the dielectric surfaces of a spacecraft are exposed to the space plasma environment (at GEO and POLAR orbit primarily). Furthermore, software tools have been developed and utilized for modeling the charging potentials that might be present at several spacecraft locations for a given charging plasma environment. These analysis tools have been useful in the design and configuration of thermal blankets, and other dielectric surfaces on spacecraft. No conclusive theory has yet been developed, but some work has been done in the analysis of the discharge process itself, which occurs when the released charge goes from one surface to another. Nevertheless it is widely accepted that an ESD can occur under vacuum (pressure <105 torr) when either: (a) dielectric surface voltage is greater than 500 V or (b) the electric field between a dielectric surface and a conductor is greater than 105 volts/cm. Finally, when an electrostatic discharge occurs, the release of stored charge creates a discharge current that can generate conducted emissions and radiated emissions. Conducted emissions occur as a result of the replacement current that originates when charge is blown off the dielectric surface inducing a replacement current to flow from the satellite structure. Radiated emissions are generated by the ESD current pulse. The rapid surface potential change induces noise in circuits through capacitive coupling. The discharge current can also induce an inductively coupled signal into the victim circuit. Furthermore, radiated emissions can cause diverse forms of field-to-circuit coupling. Capacitive, inductive and field-to-circuit coupling scenarios are manifestations of conducted and radiated EMI, and are characterized by electrical noise on a victim electronic component or circuit. This induced electrical noise, which is transient by nature, can interfere with nominal current and voltage levels of electronic components causing transient data or command interruptions or, even worse, permanent component damage. Analysis Steps: I. ESD-EMI Topology: This is the first step in EMI analysis from ESD events. A study is performed of spacecraft assemblies and sub-assemblies to identify: a) the most likely locations for spacecraft charging and ESD to occur, b) the most likely location and types of conductive path(s) which will be followed by the induced current after an ESD event, and c) the most likely susceptible circuits within a spacecraft that can be affected by an ESD event. This preliminary work is needed to characterize the topology under which ESD events occur. Figure 1 illustrates a simple example of an ESD event on a shielded cable from the solar array. [D] Figure 1. ESD Events Due To Spacecraft Charging II. EMI Coupling Phase: This is the second step in EMI analysis from ESD. Because of the complex physics involved in conducted and radiated EMI coupling, an approximation technique consists of the use of L,R,C (inductive, resistive, capacitive) network representations between surface charging and possible ESD paths. This technique provides acceptable results for low frequency, typically less than 50 mHz (l >> l,l being the size of the device affected by ESD and l being the wavelength) EMI analysis. The coupling phase task involves the development of an electronic network representation to model the coupling parameters between a charging surface and a susceptible device or conductive path. The network representation will be useful in the evaluation of several characteristic parameters of ESD events such as current and voltages at desired locations. Figure 2 describes a very simple EMI coupling scenario between a solar array (the charging surface) and a spacecraft shielded cable component. The ESD topology phase previously described is a prerequisite for the development of the coupling phase. [D] Figure 2. Lumped Element Parameters For ESD Event Between Solar Array And Cable III. ESD Event Phase: This phase involves the use of Simulator Program with Integrated Circuit Emphasis (SPICE) or another circuit analysis code to calculate currents and voltages at discharge locations. Figure 3 describes a simplified LRC network representation of the ESD event for the example in Figure 2. [D] Figure 3. Circuit Representation of Solar Array to Spacecraft ESD IV. Induced Current Propagation Phase: This final step involves the usage of method-of-moments in computational electromagnetics to model the conducted path(s) and the lumped-network representations of circuits and devices connected to such paths. The method-of-moments will calculate the noise current distribution at any location on the conducted path(s) or circuits. From an assumed current waveform the conducted noise emissions in the frequency domain can then be obtained. The calculated noise current spectrum is also used for evaluating the radiated EMI noise by using simple radiator models. Figure 5 describes method of moments modeling for evaluating the induced noise current on the shielded cable of Figure 4. [D] Figure 4. Physical Representation of Shielded Cable Inside Spacecraft Structure [D] Figure 5. Method Of Moment Modeling of Shielded Cable Technical Rationale: The emphasis on ESD through the years has been on minimizing the occurrence of such events through: (a) a better understanding of the charging processes that occur on different types of dielectric materials used in a spacecraft, (b) a better understanding of the space plasma environment, and (c) following several EMI rules concerning shielding, grounding and bonding. However, there is a need to analyze the EMI effects of actual electrostatic discharge processes because it is usually not possible to eliminate all sources of ESD. References: 1. IEEE International Symposium On EMC, 1988; quotA Simple SPICE Model For Coupled Transmission Linesquot, Clayton R. Paul Perez, R., quotAnalysis of Electromagnetic Interference Effects in Spacecraft Generated by Electrostatic Discharges using the Method of Momentsquot, 6th Annual Review of Progress in Applied Computational Electromagnetics, Monterey, March 19-22, 1990 Design and Analysis of Electronic Circuits for Worst Case Environments and Part Variations, Reliability Preferred Practice No. PD-ED-1212 | This practice has been used on TOPEX (Topographic Oceanographic Experiment). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
796 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Electromagnetic Interference Analysis of Circuit Transients | Preferred Practice for Design & Test. The neglect of EMI noise from transient circuits can cause interference problems and/or degraded performance in electronic devices. Network circuit analysis programs are valuable tools in the analysis of switching circuit transients which are capable of generating conducted and radiated electromagnetic interference (EMI). The analysis is performed to insure that disruptions or degradations due to EMI do not occur. EMI is capable of disrupting the normal operating environment of an electronic circuit or degrading the performance of such a circuit. | The neglect of EMI noise from transient circuits can cause interference problems and/or degraded performance in electronic devices. | Network circuit analysis programs are valuable tools in the analysis of switching circuit transients which are capable of generating conducted and radiated electromagnetic interference (EMI). The analysis is performed to insure that disruptions or degradations due to EMI do not occur. EMI is capable of disrupting the normal operating environment of an electronic circuit or degrading the performance of such a circuit. | JPL | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1308, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Circuit analysis for the purpose of evaluating the conducted and radiated EMI from a switching circuit has resulted in the proper design of switching circuit electronics. The devices connected to electronic switching circuits will not be adversely affected by transient currents and associated radiated fields generated by such currents. Implementation Method: Transient circuits are found on many types of analog electronic devices, e.g., thermostats and relays, where the current needs to be switched quotONquot and quotOFFquot at required intervals. Transient currents in these devices can generate a significant amount of conducted EMI. The magnitude of conducted EMI can be expressed in decibels relative to 1.0 microampere m vs frequency after a Fourier Transform from the time domain to the frequency domain. Furthermore, the transient current, when it flows through a wire or conducting line, can make the conductor behave as a radiating antenna. The fields generated by such an antenna (normally expressed in decibels relative to 1 microvolt per meter m vs frequency) can couple to nearby electronic devices, hence degrading their performance. The EMI analysis of switching transients can be divided into three tasks. As noted in the referenced paper, SPICE (Simulator Program with Integrated Circuit Emphasis), one of the most widely used modeling tools for circuit analysis, can be adapted to this type of problem. The switching circuit and all the electronic devices connected to it directly are modeled using the SPICE code. In this process it is important to realize that the switching parameters (e.g. quotON/OFFquot time, RON & ROFF resistances) must be modeled as accurately as possible. The objective in SPICE modeling is to obtain the quotmagnitude vs timequot profile of the transient current at a location of interest (e.g. across an L, or R, or C component) which would be indicative of the propagation path followed by the transient current that would affect directly other electronic circuits. Once the transient current time-domain profile is known, the Fourier Transform can be calculated. The Fourier Transform is indicative of the magnitude of conducted EMI, at a particular location, as a function of frequency (most conducted emissions are usually in the frequency range of KHz through MHZ). The magnitude of conducted EMI can then be compared with pre-established maximum allowed levels of conducted noise to assess the magnitude of exposure by a susceptible device. If the transient current can be calculated at a location on a conductive line (e.g. wire, cable), it is possible to estimate the amount of radiated EMI emitted by the conducting line as it temporarily behaves as an antenna. From the Fourier Transform previously calculated, the quotmagnitudequot vs quotfrequencyquot component terms are used as driving current sources for the antenna(s) under consideration. A Method of Moments (Ref. 1) code is then used to model the conducting line as a wire antenna and calculate the magnitude of the electric fields as a function of frequency. Figure 1 shows an example of a heater circuit for a battery. The heater circuit consists of two quotON/OFFquot switching thermostats connected to the heater filament (load) inside the battery. Figure 2 shows a SPICE model of the heater circuits. The transient current due to quotON/OFFquot switching can be calculated across several of the parameters illustrated in Figure 2. However, since the battery which supplies the thermostats' current also feeds other electronic devices, it is important to evaluate the conducted noise across the battery (V1 in Figure 2). The conducted and radiated emission can be evaluated by following steps 2 and 3 above. [D] Figure 1. Battery Thermostats & Heating Elements [D] Figure 2. SPICE Thermostats Switching Modeling Technical Rationale: It is important to assess the amount of conducted and radiated EMI being emitted from transient circuits to determine if changes are needed to suppress the EMI. References: IEEE International Symposium on EMC, 1988; quotA Simple SPICE Model for Coupled Transmission Linesquot, Clayton R. Paul Analysis of Radiated EMI From ESD Events Caused By Space Charging, Reliability Preferred Practice No. PD-AP-1309 | This practice has been used on the LPX - Liquid Plume Experiment (SDIO) and Centaur Battery Thermostats Design programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
798 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Spurious Radiated Interference Awareness | Preferred Practice for Design & Test. Interference may be encountered during system test or count-down which could impact the schedule. If it is encountered after launch, the result could be unpredicted or uncontrollable performance. Unexpected interference in receivers can be avoided in a complex system of transmitters and receivers by performing an intermodulation analysis to identify and solve potential problems. Various emitters may be encountered during test, launch, boost, separation and flight. There are a large number of these harmonics and intermodulation products from which potential sources of spurious radiated interferences are identified by a computer aided analysis and corrective measures evaluated. | Interference may be encountered during system test or count-down which could impact the schedule. If it is encountered after launch, the result could be unpredicted or uncontrollable performance. | Unexpected interference in receivers can be avoided in a complex system of transmitters and receivers by performing an intermodulation analysis to identify and solve potential problems. Various emitters may be encountered during system test, launch, boost, separation and flight. There are a large number of these harmonics and intermodulation products from which potential sources of spurious radiated interferences are identified by a computer aided analysis and corrective measures evaluated. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1310, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Spurious radiated interference can be identified and evaluated during the design phase of the project. Solutions can be proposed and implemented in the design phase with far less impact on cost and schedule than when changes are required later. Implementation Method: To perform an intermodulation analysis requires two lists to be prepared. The first list includes the center frequencies and bandwidths of all strong radiators in the vicinity and the frequency of all internal oscillators. The second list includes the frequencies and bandwidths of all receivers and intermediate frequency amplifiers. The number of possible interference frequencies can be a very large number when there are more than a few emitters. Interference results from the sums and differences of all the emitter frequencies and their harmonics taken two at a time. A computer program is utilized to identify potential interference frequencies. Two computer programs are listed under References. The first referenced computer program solves the equation below for up to 200 emitter and receiver frequencies. (F0-BW/2) < [(n x Ft)±(m x Ft)] < (F0 + BW/2) where: F0 = receiver center frequency of each receiver BW = bandwidth of the receiver Ft = list of all emitter frequencies n = harmonic number of each emitter frequency, integers from 1 to h m = harmonic number of 2nd emitter, integers from 0 to h. h = highest harmonic to be selected When potential interference frequencies have been identified, the possibility of their occurrence is evaluated. After positive identification, alternate approaches to eliminating the problem are examined. Alternate approaches include eliminating the non-linearity which causes intermodulation or reducing the amplitude of either of the two emitted signals at the non-linear component. The second referenced computer program is more comprehensive and includes amplitude analysis. Technical Rationale: In an environment of strong field intensities from nearby emitters and complex equipment, surface currents are known to intercept non-linearities in components or conductors. These may be mixer diodes closely coupled to antennas, or contaminated joints between dissimilar metals. These conditions result in rectification of the current which produces odd harmonics of single frequencies and intermodulation products where multiple frequencies occur simultaneously. These spurious signals couple to receiving antennas, producing interference. With multiple frequencies, a large number of harmonics and sums and differences of all possible combinations of the frequencies will occur. Harmonics of local transmitters often cause interference up to their 5th harmonic when they are fairly well filtered, or much higher harmonics when they are not well filtered. The number of intermodulation products to be tested for interference can be large, therefore a computer program is useful in finding the sources of potential interference for each receive frequency and for a number of different bandwidths. References: Paul Rosales, "Intermod", Lockheed Advanced Development Co., Palmdale, California, January 1987 - Updated by T. Larter, JPL, May 1991 Jerry Stafford, "Electromagnetic Compatibility Frequency Analysis, EMCFA", IBM, Huntsville, Alabama, March 1969 - Updated for the Space Shuttle Program by Arthur Reubens and John Roth, April 1975 | This practice has been used on the Earth Observing Satellite (EOS), Ocean Topography Experiment (TOPEX), Advanced Mechanically Scanned Radiometer (AMSR), and the NASA Scatterometer (NSCAT) programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
799 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Redundancy Switching Analysis | Preferred Practice for Design & Test. The long-term survival of complex systems is usually achieved through the practice of design redundancy. There are often unforeseen deficiencies in the redundancy switching which result in non-independence, thereby defeating the intent. Failure to use this practice will very probably result in several instances of defective switching in a complex system such as a spacecraft. To verify that the failure of one of two redundant functions does not impair the ability to transfer to the second function, a rigorous failure modes, effects, and criticality analysis (FMECA) at the piece part-level is performed for all interfacing circuits. | The long-term survival of complex systems is usually achieved through the practice of design redundancy. There are often unforeseen deficiencies in the redundancy switching which result in non-independence, thereby defeating the intent. Failure to use this practice will very probably result in several instances of defective switching in a complex system such as a spacecraft. Experience has shown that initial designs have about a 10 percent chance of non-independence. Just one such defect reduces a presumed redundant system to a single channel system with its inherently shorter life expectancy. | To verify that the failure of one of two redundant functions does not impair the ability to transfer to the second function, a rigorous failure modes, effects, and criticality analysis (FMECA) at the piece part-level is performed for all interfacing circuits. | JPL | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1315, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: By using a systematic method to assure the switching functionality of designed-in redundancy, the long-term performance of complex systems can be assured. Implementation Method: Redundancy switching analysis (RSA) is a subset of the general FMECA process, but it is performed in greater detail because of its criticality. RSA includes the following steps: Identify and diagram all functional blocks which involve the two redundant elements. Expand the functional blocks to show the interface circuitry at the piece part level. Postulate all credible part failures (viz, shorts, opens, saturated high or low, etc.) and determine the effect on the functional redundant path. Verify design compliance with the following objectives: Hardware failures do not propagate across inter-unit interfaces to produce hardware failures in other units. There is sufficient isolation that the postulated failure does not produce a functional failure capable of disturbing the transfer to, or operation of, the redundant function. Technical Rationale: There have been numerous instances of presumably redundant systems which have failed to successfully transfer to the backup path when the primary path is non-functional. A rigorous, systematic search could have foretold the failure and, through design change, averted the problem. The first objective-- preventing failure propagation-- is of most value in a repairable system. Non-propagation minimizes the number of units requiring repair. In spacecraft, this would correspond to the preflight phases of either subsystem or system testing. The key to this investigation is a complete diagram of the involved interface circuits which penetrates each unit to a circuit depth sufficient to prove that no possible failures in Unit 1 can propagate to become irreversible hardware failures in Unit 2. The second key ingredient is a complete list of part or assembly failure modes for hypothesis. The second objective-- guaranteeing successful transfer (or equivalently independence of the primary and back-up functions)-- is a necessity for either repairable or non-repairable systems and requires the same complete interface diagram and complete list of failure modes. The list includes such items as: Part failure (viz, opens, shorts, stuck-ats), Single event effects (viz, latch-up, transfer), and EMI (viz, latch-up, transfer, overvoltage). These last two items are critical since they can effect both sides of a redundant pair. Figures 1 and 2 are illustrations of the process of a redundancy switching analysis for several typical interface Observation: If the postulated short exists and source A is unpowered, its quotoffquot-state load resistance must be high compared to the quotonquot-state source resistance of source B to assure that adequate VA voltage will be received at LOAD A. If not, the diodes must be made series redundant. [D] Figure 1: Example of Passive Redundancy Switching for Cross-Strapped Dual Sources and Dual Loads Observation: If the postulated short exists, the isolation resistor R1 must be large compared to the output source resistance of amplifier A1 to assure that adequate VB voltage is received at LOAD B. [D] Figure 2: Example of Passive Redundancy Switching for Single Source and Dual Load References: Polovko, A.M. (1968). Fundamentals of Reliability Theory, (Chapter 5-4). New York: Academic Press, Inc. Feduccia, A.J. (1993). Reliability Engineerís Toolkit. Griffiss Air Force Base, New York: Rome Laboratory. | This practice has been used on the Voyager, Galileo and Magellan programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
800 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Thick Dielectric Charging/Internal Electrostatic Discharge (IESD) | Preferred Practice for Design & Test. Dielectric compositions used in such spacecraft materials as circuit boards, cable insulation and thermal blankets will build up an imbedded charge when exposed to a natural space environment featuring energetic electrons. If the electric field resulting from the imbedded charge exceeds the breakdown threshold for the dielectric, an arc will occur, damaging the dielectric and producing an electromagnetic pulse which can couple into subsystem electronics. Enhance hardware reliability in an energetic electron environment by conducting a materials inventory, resistivity analysis, and shielding assessment. Ascertain material susceptibility to deep dielectric charging and explosive discharge when the material: 1. Is exposed to an energetic electron flux exceeding 2x10^5 electrons/(cm^2 -s), and 2. Achieves an imbedded charge density greater than a threshold of 10^11 electrons/cm^2. | Non-compliance with the IESD practice will result in increased risk of deep dielectric charging when energetic electrons are encountered. Internal discharges result from severe electron environments; they produce electromagnetic pulses that can couple into subsystem electronics, resulting in anomalous spacecraft behavior. Dielectric breakdown and material failure also occurs. | Dielectric compositions used in such spacecraft materials as circuit boards, cable insulation and thermal blankets will build up an imbedded charge when exposed to a natural space environment featuring energetic electrons. If the electric field resulting from the imbedded charge exceeds the breakdown threshold for the dielectric, an arc will occur, damaging the dielectric and producing an electromagnetic pulse which can couple into subsystem electronics. Enhance hardware reliability in an energetic electron environment by conducting a materials inventory, resistivity analysis, and shielding assessment. Ascertain material susceptibility to deep dielectric charging and explosive discharge when the material: Is exposed to an energetic electron flux exceeding 2x105 electrons/(cm2 -s), and Achieves an imbedded charge density greater than a threshold of 1011 electrons/cm2. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1316, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Materials and design structures which represent possible internal electrostatic discharge (IESD) sources can be identified early in the program. Risk to hardware may be reduced through design changes which substitute materials having sufficient conductivity to permit charge bleed-off. Sensitive cable runs may be rerouted or shielded to reduce exposure to energetic electrons. Grounding schemes may be changed to ensure that otherwise isolated conductors are grounded and that grounds are designed to maximize the opportunity to bleed-off the charge from dielectric materials. Implementation Method: Utilize the electron environment specified for the mission and a transport code (such as NOVICE) to estimate the electron flux at interior locations where dielectric materials pose an IESD problem. When the electron flux exceeds the guideline values, apply ameliorating strategies: Replace dielectric with a more conductive material, Relocate the dielectric structure to a more suitable location within the spacecraft, and Review the grounding scheme to maximize charge bleed-off. Good design practices can minimize IESD risk by optimizing the spacecraft structure to provide shielding for otherwise exposed cable runs and highly resistive materials. Shielding reduces the ability of incident energetic electrons to cause IESD by shifting the flux spectra to lower energies, resulting in fewer high energy particles. Providing a shield thickness of 400 mg/cm2 has been found sufficient to reduce most electron environments below the IESD threshold. Technical Rationale: IESD is caused by electron flux present in the earth's magnetosphere which is sufficiently energetic to penetrate the spacecraft skin and imbed in cable insulation, thermal blankets, circuit boards, and other non-conductors. Ungrounded islands of metalization can also develop a charge. When the charge build-up results in an electric field sufficient to break down the dielectric, an arc to an adjacent material at a lower potential will occur. Material damage (burn-out) and an electromagnetic pulse occurs which can couple into the subsystem electronics with the possibility of undesirable anomalous subsystem behavior. Electrons responsible for bulk dielectric charging are more energetic than those responsible for surface charging. The IESD threshold current density is approximately 2x105 electrons/(cm2-s) for integral electron flux above approximately 100keV. The frequency of IESD increases as the electron flux increases above threshold. Dielectric breakdown begins to occur when the concentration of electrons exceeds approximately 1011 electrons/cm2. References: Vampola, A.L. (1987), "Thick Dielectric Charging on High-Altitude Spacecraft", Journal of Electrostatics, 20, pp 21-30. Fredericks,A.R., Holeman, E.G, Mullem, E.G. (Dec. 1992)," Characteristics of Spontaneous Electrical Discharging of Various Insulators in Space Radiations", IEEE Trans. on Nucl. Sci., 39, 6. Purvis, C.K., Garrett, H.B., Whittlesey, A., Stevens, N.J. (Sept. 1984), "Handbook of Design Guidelines for Assessing and Controlling Spacecraft Charging Effects", NASA Technical Paper 2361. Mizera, P.F., Fennell, J.F., Hall, D.F., Koons, H.C., and Vampola, A.L., "Spacecraft Charging Handbook", SD-TR-85- 26, 1985. Rudie, N.J., "Electron Caused Electromagnetic Pulse", DS&E Magazine, pp 58-59, June 1987. Design Practice to Control Interference From Electrostatic Discharge (ESD), Reliability Preferred Practice No. PD-ED-1244 Surface Charging/ESD Analysis, Reliability Preferred Practice No. PD-AP-1301 | This practice has been used on the Voyager, Galileo, Spacecraft Charging at High Altitudes (SCATHA) and Chemical Release & Radiation Effects Satellite (CRRES) programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
811 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Radiographic Testing of Aerospace Materials |  | Failure to detect defects and flaws internal to materials could result in failure of components and possible loss of mission and life. | Radiographic testing can be used as a nondestructive method for detecting internal defects in thick and complex shapes in metallic and nonmetallic materials, structures, and assemblies. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1423 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Unlike most other nondestructive testing methods, radiographic testing provides a permanent visual record of the defects for possible future use. It can also be used to determine crack growth for use in fracture mechanics to determine critical flaw size in a particular component. Implementation Method: Radiography is an effective method of nondestructively detecting internal flaws in materials and structures. The radiation source emits energy that travels in straight lines and penetrates the test piece. As the radiation energy passes through the test piece, an image, is received on the recording medium opposite the x-ray source. This image is used to evaluate the condition of the part being tested. Film is most frequently used as the recording medium for the image, but there are other techniques that may be used such as fluoroscopic screens, and digitized systems coupled with video monitors. The three basic elements are: 1) a radiation source, 2) the test piece being evaluated, and 3) a recording medium are combined to produce a radiograph as shown schematically in Figure 1. An x-ray is radiation produced from a manmade x-ray tube. Table 1 compares the penetration range of high energy x-ray sources with conventional x-rays. Radiographic film is classified according to speed, contrast, and graininess as depicted in ANSI/ASTM E94. [D] Figure 1. Layout for Flaw Inspection [D] Table 1. Comparison of Penetration Range of Conventional X-Ray Tube vs. High Energy Source Table 2 lists the ASTM film type, relative speed of the film type. Manufacturer-furnished x-ray film exposure charts show the relationships between thickness, kilovolts and exposure time, but only apply to a specific set of conditions. The manufacturer's furnished charts are only accurate to within ±10 percent, since no two x-ray machines are identical. [D] Table 2. Film Description and Applications Radiographics constitutes a health hazard that requires special radiation training for personnel concerned with its use. Also, adequate safety devices should be built into the x-ray facility including those listed below: Safety interlock switches Keylock system Radiation monitoring device Warning system Adequate facility shielding At least one qualified operator plus a Radiation Protection Supervisor or designated alternate must be present at all times during any x-ray operation. The personnel requiring access to the x-ray area must be monitored to ensure that no one absorbs excessive amounts of radiation. The normal means for monitoring radiation is by wearing pocket dosimeters and film badges. The dosimeter is read and recorded daily and usually the film badge is developed and read at least quarterly. Both devices are compared and should check within 20 percent of each other. The allowable dose of radiation is 1 1/4 Roentgen equivalent man (rem) per quarter year. For added safety, each time the x-ray area is entered a survey meter should be used to ensure that the area is safe to enter. Interpretation of radiographs requires highly trained and qualified technicians who must (a) define the quality of the radiographic image, which requires a critical analysis of the radiographic procedure and the image developing procedure; (b) analyze the image to determine the nature and extent of any abnormal condition in the test piece; (c) evaluate the test piece by comparing interpreted information with standards or specifications; and (d) report inspection results accurately and clearly. The major advantages and disadvantages of radiographic testing are listed in Table 3. [D] Table 3. Advantages and Disadvantages of Radiographic Testing Technical Rationale: Radiographic testing has been used successfully at MSFC for years to identify and characterize cracks, voids, inclusions, porosity, lack of weld penetration, lack of fusion in welds, and many other types of defects. Radiographic testing is an accurate and reliable nondestructive testing method for determining defects and flaws internal to materials, structure, and assemblies. It is also used to detect defects and flaws in both metallic and nonmetallic materials. References: MIL-HDBK-728/5: quotMilitary Handbook: Radiographic Inspection,quot December 1985. MIL-STD-410E: quotNondestructive Testing Personnel Qualification and Certification,quot Military Standard, January 1991. MM 1860.2D: quotRadiation Safety Manual,quot NASA, Marshall Space Flight Center, Marshall Space Flight Center, AL 35812, December 1991. MM 1700.4C: quotSafety and Environmental Health Standards,quot NASA, Marshall Space Flight Center, Marshall Space Flight Center, AL, December 1983. Metals Handbook, Volume 17: quotNondestructive Inspection and Quality Control,quot pp. 295-357, ASM International, Metals Park, OH, 1989. MIL-STD-453C: quotRadiographic Inspection,quot Military Standard, December 1984. Ultrasonic Testing of Aerospace Materials: Reliability Preferred Practice PT-TE-1422 Eddy Current Testing of Aerospace Materials: Reliability Preferred Practice PT-TE-1421 | This practice has been used on Saturn I, IB & V Vehicles, Space Shuttle External Tank (ET), Space Shuttle Solid Rocket Booster (SRB), Space Shuttle Main Engine (SSME), and many other MSFC projects. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
813 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Power System Corona Testing |  | Insulation breakdown due to undetected corona discharge can cause power system components to degrade and fail in time. High voltage power supplies that are not tested for corona could experience failures that disrupt mission objectives due to corona-caused shorts. | Test power system components for corona to ensure that their insulation system will meet the design requirements imposed on the equipment and to verify that the gas discharges are not deteriorating the insulation system. The acceptable corona levels are verified in power system components. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1415 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Knowledge of the presence or absence of corona discharge will help in controlling the reliability of high voltage components/systems. Corona testing can reveal potential and unaccounted-for corona discharges that may shorten the service-life of electrical insulating systems, seriously interfere with high voltage system operation and communication links, and result in failure and loss of mission objectives. Implementation Method: Corona current pulses can be detected using electrical measuring instruments. Numerous corona tests performed at LeRC concluded that the corona discharge acceptable limit should be less than 5 picocoulombs. Paschen's curve defines the regions of breakdown as a function of the dielectric media and the product of the pressure times the spacing between the conducting surfaces. The minimum voltage for a common dielectric medium is approximately 300 volts; therefore, testing should be considered for power systems operating at 300 volts and greater. Generally, the corona inception voltage tends to decrease with increasing frequency of the alternating voltage under the influence of which corona takes place. It is reported that the inception voltage decreases somewhat at frequencies above approximately 20 kilohertz and more rapidly at frequencies in the megahertz range (Ref. 9). Several variations of corona test apparatus and circuits are available and can be utilized to generate typical corona environments for the specific power system component type and operating conditions. The basic components of any corona test set consist of a detector, power separation filter and calibration signal coupler. A more general test apparatus that has been used to test corona (partial discharge) is shown in Figure 1. This set up consists of a 40 kilovolt AC and DC partial discharge test set that includes a buffer-isolation amplifier circuit which couples output pulses to a multichannel pulse height analyzer or an oscilloscope. The same partial discharge system of Figure 1 can be connected to a thermal vacuum chamber for testing space power system components to determine corona threshold level. In this test setup, the following modifications are necessary to convert a vacuum pumping test station into a corona threshold test facility: 1) Each O-ring sealed surface is clamped to withstand a maximum test pressure of 1.69X105 newton per square meter (1270 Torr); 2) A 1/2-inch diameter high-voltage transmission line (of copper tubing) is run from the corona tester to the test sample; 3) The tubing from the corona tester to the vacuum chamber is shielded with a 6-inch galvanized pipe; 4) The 1/2 inch tubing is supported with polystyrene standoffs; 5) All directional changes are guarded with 1-inch corona balls; and the vacuum feedthrough is guarded with 1/2 inch radius cover rings. Detailed test setup, procedures and test equipment manuals should be obtained from the test equipment manufacturers. Also, military standards and specifications listed in the References section of this document provide a test apparatus/circuit guide for the different types of components used in high voltage systems. Reference to these standards and specification should be made whenever possible to ensure that the proper component screening procedures and requirements are observed. [D] Figure 1: Typical Partial Discharge Test Setup In general, all measurements should be carried out in an electrically shielded room with its own isolated and filtered power lines. Care should be taken to see that cabling and vacuum feedthroughs are corona free (Ref. 15). With the help of the information contained in the publications referenced herein, detailed procedures should be developed for the various required tests and evaluation of corona. Technical Rationale: The term quotcoronaquot is used as a generic name for any electrical discharges which take place in an energized electrical insulation as the result of accelerated ionization under the influence of the electric field in the insulation (Ref. 9). The reliability of high voltage power systems is related to an electrical discharge (corona) parameter on a component level. Corona causes insulation deterioration, therefore, failure of components becomes more probable as the component degrades. All power system components should be tested to verify that this parameter can be held to a specified minimum for extended periods to ensure system reliability through corona testing (Ref. 1). Corona is sometimes visible in the form of an arc, but visual inspection for presence of corona is grossly inadequate. The voltage at which visible corona can be observed is at a threshold well above the actual corona inception. Although corona-caused arcing is damaging to power systems, the greater concern is the internal invisible corona within a device. Corona originating within an enclosed item is also damaging and can degrade dielectrics. Corona discharges in insulation systems cause momentary changes of potential and consequently current pulses. These current pulses are superimposed on the test voltage signals and may be detected at the terminals of the device under test. Corona testing should be a part of the design tests to verify that the components meet the less than 5 picocoulombs requirement. Components (any electrical devices, such as transformers, cables, connectors, terminations, etc., which incorporate conductors with suitable insulated regions) that have potential for degradation inherent in their insulation system can be identified. This degradation is due to small voids, fractures, separations, delaminations and other defects that are not detectable by visual inspection, and can be detected in insulating systems by corona testing. The presence of corona, because of these defects, subjects a material to ozone, acid, ultra-violet light and bombardment by electrons and ions. An ionization process takes place as a result of gas in a void located within a dielectric or adjacent to the surface of a dielectric that separates two conductors with electric field. Corona discharge, due to electron or ion bombardment in an ionized region, initiates and can erode almost all dielectrics. This erosion is permanent and cumulative. The cumulative effects of corona will cause failure, without warning at a later date, when the dielectric strength becomes less than the applied stresses. This can occur after installation of high voltage components within a system of assumed high reliability. Corona deteriorates insulation in the vicinity of the discharge, reduces distribution efficiency, and disassociates some gases creating noxious gases and odors. Corona within an electric power system generates spurious high-frequency voltages that produce interference in communication links and malfunctions in sensitive electronic circuits. The current pulses it produces in the circuits of high voltage equipment may have very short rise time, high recurrence frequency and sufficient amplitude for simulating, falsifying, distorting or masking signals which are used in electrical communication, control and measurements. At the development and design of the SERT's Power Conditioner, an arcing problem (due to corona discharge) occurred in the ion thruster and caused power source interruption and overload conditions. Using high voltage components that are screened for corona, and elimination of sharp corners on terminals and connectors, reduced the amount of corona-caused arcing in the high voltage system. An example of an early flight failure caused by corona discharge was a short that developed between two pins of a high voltage connector. The gas trapped inside connector voids gradually decreased in pressure until corona discharge began to decompose the insulating system and caused leakage and a short. The failure disabled the experiment. Definitions of Corona terms discussed in this document are provided in Table 1. Corona (partial discarge) A type of localized discharge resulting from transient gaseous ionization in an insulation system when the voltage stress exceeds a critical value. The ionization is usually localized over a portion of the distance between the electrodes of the system. Corona inception voltage (CIV) The lowest voltage at which continuous corona of specified pulse amplitude occurs as the applied voltage is gradually increased. Current pulse A pulse which occurs at some location in a device as a result of a corona discharge. Ionization Any process by which neutral molecules or atoms dissociate to form positively and negatively charged particles Table 1. Corona Related Terms References: Lalli, Vincent R., Mueller, Lawrence A., and Koutnik, Ernest A.: quotSystem Reliability Analysis Through Corona Testing,quot NASA TM X-3287, Lewis Research Center, Ohio, 1975. Klima, Stanley J., and Riley, Thomas J.: quotUltrasonic Evaluation of High Voltage Circuit Boards,quot NASA TM X-73432, Lewis Research Center, Ohio, 1976. Bagwell, James W., Hoffman, Anthony C., Leser, Robert J., Reader, Karl F., Stover, John B., and Vasicek, Richard W.: quotReview of SERT II Power Conditioning,quot NASA TM X-52858, Lewis Research Center, Ohio, 1970. quotNavy Power Supply Reliability, Design and Manufacturing Guidelines,quot Department of the Navy, NAVMAT P-4855-1A, 1989. quotMilitary Handbook, NASA Parts Application Handbook,quot NASA, MIL-HDBK-978-B (NASA), 1989. quotMilitary Specification, Transformers and Inductors,quot Department of Defense, Washington DC, MIL-T-27E, 1985. quotMilitary Specification, Connectors, Coaxial, Radio Frequency,quot Department of Defense, Washington DC, MIL-C-39012C, 1991. quotMilitary Specification, Cables, Radio Frequency, Flexible and Semirigid,quot Department of Defense, Washington DC, MIL-T-17F, 1984. Heinrich, Oswald X.: quotCorona Measuring Techniques and Their Use in Insulation System Evaluation,quot James G. Biddle Co., Plymouth Meeting, Pennsylvania 19462, Technical Bulletin 66T1, May 1964. Instruction Manual 66J , quotPartial Discharge (Corona) Test Equipment,quot Biddle Instruments, James G. Biddle Co. Plymouth Meeting, Pennsylvania 19462. Galambos, Louis G., P.E.: quotCorona: What it is; Damage it causes; How to Avoid It,quot James G. Biddle Co., Plymouth Meeting, Pennsylvania 19462, Printed from Electronic Products Magazine, April 1965 Issue. The Institute of Electrical and Electronics Engineers, Inc., quotIEEE Guide for Making Corona (Discharge) Measurements on Electronics Transformers,quot IEEE Std. 436-1977, December 15, 1977. Bartnikas, R.:, Institut de Recherche, Hydro-Quebec, Varennes, Quebec, Canada and McMahon, E. J., E. I. duPont de Nemours & Co., Inc., Wilmington, Delaware, U.S.A., quotEngineering Dielectrics, Volume I, Corona Measurement and Interpretation,quot American Society for Testing and Materials (ASTM) STP 669, February 1979. Bever, Renate S., and Westron, John L.: quotPartial Discharge Testing Under Direct Voltage Conditions,quot IEEE Transactions on Aerospace and Electronic Systems, Vol. AES-18 No.1, January 1982. Bever, Renate S.: quotRamp Technique for DC Partial Discharge Testing,quot IEEE Transactions on Electrical Insulation, Vol. EI-20 No.1, February 1985. Kreuger, Frederick Hendrik: quotPartial Discharge Detection in High Voltage Equipment,quot Stoneham, Massachusetts, Butterworth-Heinemann Pub. Co., 1989. quotHigh Voltage Power Supply Design and Manufacturing Practicesquot, Reliability Preferred Practice PD-ED-1202. | This practice has been used on Communications Technology Satellite (CTS), Space Plasma High Voltage Interaction Experiment (SPHINX), Space Electronic Rocket (SERT) Tests I and II, and 30 cm Thruster Bi-module. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
812 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Leak Testing of Liquid Hydrogen and Liquid Oxygen Propellant Systems |  | Nonpractice could result in an unacceptable leakages of the cryogenic fuels from the LO2 and LH2 tanks and the propulsion system lines. Excessive leakage could ignite in the presence of an ignition source and could result in catastrophic loss of vehicle and crew. Excessive leakage could cause launch delays and result in excessive program cost. | Leak testing is a nondestructive test method that provides the capability to detect and measure the amount of liquid or gas escaping from a sealed pressure system and to locate the individual leaks for possible repair. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1424 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Leak testing of a Liquid Hydrogen (LH2) and a Liquid Oxygen (LO2) propellant system prior to flight insures that the flight leakage rate does not exceed allowable leakage established for flight. Leak testing also insures the quality and reliability of a Space Shuttle Element and reduces the probability of system failure. Leak checks also prove that seals and sealing surfaces at joints are defect free and seals are seated correctly. Implementation Method: A leak is the result of cracks, holes, porosity, permeability, surface aspirates or scratches in a pressurized container or joint that allows the escape of liquid or gas. Leak test methods and procedures are designed for detecting, locating leaks, and ensuring the quality, serviceability and safety of components, structures and the entire propellant system. Leak testing can be a time consuming and expensive task but should be implemented when necessary to protect product integrity or personnel safety. One of the most important steps in leak test development is to establish the specification for acceptable and unacceptable leak rates. Choosing the most effective and reliable leak testing method is also important. Leak testing methods and sensors include the following: Acoustical - escaping gas that is audible or can be detected using acoustical instrumentation. Odor - from tracer gas. Leak test solution - bubbles form when applied over escaping gas. Pressure decay - pressure loss over time. Pressurized liquid - normally water, leakage can be seen. Trace gas - color/radiation/odor. Gas chromatography. Halogen leak detection - requires use of alcohol torch (blue flame) with a sniffer tube when small amounts of fluorine, chlorine bromine, etc. enter the tube then the blue flame turns to a different color. Helium leak detectors - detects leakage of small amounts of helium. Flow meter - detects the volume of gas escaping over a specified time. Bubble gauge - monitors inter seal leakage between primary/secondary when primary pressurized. Light refraction. Mass spectrometer. Hydrogen sensors. Oxygen sensors. Electronic detectors. Liquid sensitive electrical aluminum tape. This reliability Practice covers MSFCís experience for ensuring that the External Tank, as an element of the Space Shuttle Transportation System, has developed an acceptable leak detection system and leakage verification program for the cryogenic propulsion oxidizer and fuel systems, Liquid Oxygen (LO2) and the Liquid Hydrogen (LH2) tanks. EXTERNAL TANK Extra effort is devoted to the procurement of defect-free raw material. Aluminum plate has been ultrasonic tested at the mill. The skin panels are placed into a weld fixture and welded using the variable polarity plasma arc (VPPA) or TIG welding method. After welding, the welds are x-rayed and penetrant inspected (defects are repaired as required). When the LO2 tank has been assembled, the welds are wrapped with an aluminum tape which has an adhesive that is soluble in water. The LO2 tank is then hydrostatically tested. If a leak is encountered during hydrostatic testing, the water will dissolve the adhesive and provide electrical continuity through the aluminum foil tape. A leak could then be isolated and repaired. After the LH2 tank has been assembled, it is pneumatically proof tested with gaseous nitrogen (GN2). Leakage is checked with bubble solution at a reduced pressure after proof test. After the LO2 tank/intertank assembly is joined to the LH2 tank, the propulsion delivery systems are installed on the tanks. The propulsion delivery systems consist of the LO2 and LH2 feed lines, recirculation line and pressurization lines. The propulsion delivery system lines are joined with bolted flanges containing Naflex or Raco/Creavey seals to control leakage. The Raco®/CreaveyTM seal consists of a primary and secondary seal set. The primary seal is a Raco® seal that is a pressure activated seal consisting of a Teflon jacket over an Inconel 718 spring. The secondary seal is a CreaveyTM seal, which is a tubular Teflon cover with a stainless steel spring core that forms an quotOquot ring type seal. For Raco®/CreaveyTM seal arrangement, see Figure 1. This two-seal arrangement provides for means for leak checking the primary seal or the total leak rate of the primary and secondary seals. For the Naflex seal arrangement, see Figure 2. The bolted flanges for both types of seals have a leak test port that has been proved to be blockage free. The allowable leakage rate for the Raco®/CreaveyTM seals is 0.183 SCIM of helium at 50 ± 5.0 PSIG and ambient temperature. The propulsion line mechanical joints are leak checked in final assembly by pressurizing the leak check port to either 6 or 50 PSIG through a flow meter. The LH2 & LO2 tank and propulsion lines are pressurized to 6 PSIG with GN2 and the leakage rate of ìbî nuts and K seals are checked using the leak test solution bubble test (no bubbles in three minutes). [D] Figure 1. Raco ®/Creavey TM Seal Configuration (not to Scale) [D] Figure 2. Naflex Pressure Assisted Seal (Not to Scale) The LO2 and LH2 tanks remain pressurized to 6 PSIG during storage and could stay pressurized for several years. The tank pressure is monitored and if it decays too rapidly action will be taken to find the leak. During the entire ET program, no repairs have been required for flight hardware. Technical Rationale: The rigorous leak check and nondestructive testing on the External Tank program have contributed to more than fifty successful flights of the Space Shuttle. Leak testing methods performed on the ET including bubble solution, water soluble adhesive on aluminum tape, flow meter testing and pressure decay testing. These techniques have proven to be effective in maintaining 100 percent mission success. References: MMC-ET-SE 25-0: quotSystem Definition Handbook, Space Shuttle External,quot Volume I & II, National Aeronautics and Space Administration, Martin Marietta, August 1987. Bray, Don E. and Don McBride: quotNondestructive Testing Techniques,quot John Wiley & Sons, Inc., 1992. Metals Handbook, Volume 17: quotNondestructive Inspection and Quality Control,quot ASM International, Metals Park, OH, 1989. quotIntroduction to Helium Mass Spectrometer Leak detection,quot Varian Associates, Inc., Palo Alto, CA 94303, 1980. McMaster, Robert C.: quotNondestructive Testing Handbook, Leak Testing,quot Volume 1, American Society for Nondestructive Testing, Inc., 1985. Hammock, W. R. Jr., P.E. Cota, Jr., B.J. Rosenbaum, and M. J. Barrett: quotInvestigative Techniques Used to Locate the Liquid Hydrogen Leakage on the Space Shuttle Main Propulsion System,quot NASA, Johnson Space Center, AIAA SAE/ASME 27th Joint Propulsion Conference, Sacramento, CA, June 24-26, 1991. Szemenyei, B., R. Delcher, M. Randall, E. Schmidlin, and S. Barkhoudarian: quotGround-Based and In-flight Leak Detection for Rocket Engines,quot X91-10319 Rockwell International/Rocketdyne Division, Canoga Park, CA. Barile, Ronald G.: quotHazardous Gas Leak Analysis in the Space Shuttle,quot N92-19308, 1991 NASA/ASEE Summer Faculty Fellowship Program, Kennedy Space Center, University of Central Florida, August 22, 1991. Barile, Ronald and William Helms: H2 Leak Detection Technical Interchange Meeting at KSC, Proceedings, April 29, 1992. S-69-117: quotLeakage Testing Handbook,quot JPL/GE NTIS N-69-38843, July 1969. Reliability Preferred Practice PD-ED-1208, Static Cryogenic Seals for Launch Vehicles. Reliability Preferred Practice PD-ED-1205, Weld Practices for 2219 Aluminum and Inconel 718. | This practice has been used on Saturn I, IB II, IV, IVB, V, and Space Shuttle External Tank (ET). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
828 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Thermographic Mapping of PC Boards |  | Allowing undetected hot spots to exist in flight hardware can be very expensive since the later a problem is detected in a flight program, the more it costs to repair. Using thermography to verify system engineering models is a fast, low-cost technique. | Use thermographic mapping methods to locate hot spots on operating PC boards. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1403, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Quick find of electronic components operating at or above recommended temperatures. Also, this technique can validate the derating factors and thermal design via low cost testing versus analysis. Implementation Method: Using an infrared camera and the flight PC board, make thermographic pictures of the prototype PC boards in operation. Verify the thermograph and determine the delta T to the actual use environment with thermocouples. Shut down the equipment and prepare it for a vacuum test. The board to be tested is placed in a mother board with the appropriate +5 V and ±12 V power supplies. Power is applied to the board, and after a short period, a video recording of the board is made with an infrared camera. Technical Rationale: The following procedure is used to determine the temperature of each component: Junction temperature: T J = T A + T JA Where: TJ = Junction Temperature TA = Ambient Temperature TJA = Junction to Ambient Temperature Rise TJ = 40o C for this example The case temperature, TC, which is measured on the bench at room ambient is given by Equation(2): T C = T J - Q CAP Where: TC = case temperature QCA = case to ambient thermal resistance P = Power dissipated For reliability purposes, it is necessary to keep junction temperatures for CMOS devices at or below 49 degrees C. The case temperature to be measured on the bench comes out to be TC= 34 degrees C for this application. Infrared pictures are made of the PCB mounted outside the package on extended connectors while the equipment is operating on the bench. The logic IC temperature is determined from the infrared picture. If less than or equal to 34 degrees C, the junctions are at the desired operatingtemperature. If greater than 34 degrees C, the reason for the higher temperature is determined.Corrective action is worked out and approved by the Engineering Review Board. Figure 1 is a drawing of the component layout of the SCSI card, and Figure 2 is a thermographic photograph of the board. Thermographic pictures are usually in color, but in this monochrome reproduction, the cross hairs are at the hottest location (128 degrees F), black represents 108 degrees F, white is 98 degrees F, dark grey is 88 degrees F, and light grey is 78 degrees F. [D] Figure 1. SCSI Card [D] Figure 2. Thermograph The operating temperature with the board back in the case is checked by several thermocouples attached to the hottest observed components. This is done in a simulated use environment, perhaps during the thermal environment tests. The resultant delta-T is added to the measured case temperature as a final check of the junction temperature, TJ, in the end-use environment. For sample logic IC, the delta-T was 5 degrees C so the resultant junction temperature is 45 degrees C in the package. This is below the guideline of 49 degrees C. References: Crall, R. F., quotThermal Imaging Benchtop Analysis for Reliability,quot Evaluation Engineering, December 1989. Masi, C. G., quotWhat Can Thermal Imaging Do for You?, quot Test & Measurement World, May 1988. MIL-HDBK-217E, quotReliability Prediction of Electronic Equipment,quot Rome Air Defense Center, October 27, 1986. Foster, W. M., quotThermal Test Report for the Space Acceleration Measurement System Circuit Boardsquot, NASA LeRC Code 6730 Internal Report, November 1987. | This practice has been used on Space Acceleration Measurement System (SAMS), Isothermal Dendritic Growth experiment (IDGE), and STDCE | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
803 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Identification, Control, and Management of Critical Items Lists |  | Failure to adhere to these guidelines could create operational schedule delays, increase operational costs, decrease the effectiveness of failure management, and could result in loss of the mission, loss of a vehicle, or loss of life. | Initiate the preparation of Critical Items Lists (CILs) early in programs to identify and potentially eliminate critical items before the design is frozen and as an input to hardware and software design, testing, and inspection planning activities. Utilize CILs during the operational portion of the life cycle to manage failures and ensure mission success. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1240; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Early identification, tracking, and control of critical items through the preparation, implementation, and maintenance of CILs will provide valuable inputs to a design, development, and production program. From the CIL activity, critical design features, tests, inspection points, and procedures can be identified and implemented that will minimize the probability of failure of a mission or loss of life. Implementation Method: I. Background The Failure Mode and Effects Analysis (FMEA) is performed to identify failure modes. As part of this process, critical failure modes that could lead to loss of life or loss of mission are also identified. These critical failure modes are then placed into a CIL, which is carefully examined for programmatic control by implementing inspection requirements, test requirements and/or special design features or changes which would minimize the failure mode occurrence. Failure Mode and Effects Analyses and resulting CILs can be used not only as a check of the design of systems for reliability, but also as main design drivers for the product or service. Reliability management is the activity involved in coordinating the reliability analyses of design, development, manufacturing, testing, and operations to obtain the proper performance of a given product under specified environmental conditions. Reliability management interfaces with the program management function, the design function, the manufacturing function, the test and inspection function, and the quality function. Reliability management is approached through the formulation and preparation of reliability plans, the performance of specific product design analysis, the support of classical reliability analysis activities, and project/product team participation using concurrent engineering methodologies (see NASA Reliability Design Practice GD-ED-2204). The FMEA/CIL Process (shown on Figure 1) plays a key role in reliability management. Principal outputs of the FMEA/CIL process are CILs (shown on the lower right-hand corner of Figure 1). [D] Figure 1. FMEA/CIL Analysis Process II. Critical Items Lists and Retention Rationale Specific lessons have been learned that will change the value of preparing and maintaining (CILs) early in high-technology, multi-disciplinary aerospace programs and projects. Critical Items Lists are identified through the conduct of a Failure Mode and Effect Analysis (FMEA). The FMEA Process (see Reliability Preferred Practice No. PD-AP-1307) involves a bottom-up analysis of each hardware or software element in a complex system for each possible failure mode. The determination of the ìworst caseî effect of that failure on the system is then determined. If the item can fail in a mode which could result in the loss of life or vehicle or in loss of the mission, the item is placed on a Critical Items List. The FMEA, and resulting CIL, is most effective when it is performed concurrently with the design process and maintained throughout the life of a program or project. The FMEA results in the identification of single failure points (SFPs) and critical redundant items. A typical SFP is defined as a single item of hardware (usually at the component level) the failure of which could result in the loss of life, vehicle, mission, or damage to a vehicle system. It is the general policy of NASA not to permit the retention of single failure points in design unless special conditions prohibit designing it out, such as technology, operations or cost. Retention of a single failure point requires that a justification or rationale be prepared which describes actions taken, safety margins, failure prevention measures, tests, or inspections that will ensure that the critical item of hardware will not fail in the mode indicated in the FMEA. Typical rationale for retention of hardware or software items on a projectís Critical Items List includes information on design, testing, inspection, failure history, and operational use as described below: Design Rationale: Design rationale identifies design features and/or margins that have been provided in the design of the hardware or software element which minimize or eliminate the probability of occurrence of the failure mode and/or reduction or elimination of the potential causes of the failure mode. Test Rationale: Test rationale includes a description of specific tests that have been completed to detect potential failure causes during acceptance and certification tests. Inspection Rationale: Inspection rationale addresses specific inspection methods, procedures, tools, and techniques that are used in the hardware or software manufacturing, assembly, and integration process to detect susceptibility to failure modes or to detect and assess the probability of encountering failure modes and their potential causes. Failure History: Failure history and corrective actions are included as a part of single failure point critical items retention rationale to indicate that the reason for previous failures has been removed or reduced as a potential hazard, and to provide trend analysis. Operational Use: Special operational techniques that would either prevent the particular failure mode or mitigate its effect once it has occurred are included as part of the retention rationale. This rationale includes such factors as flight rules, crew procedures, such as emergency stop features or special crew training. It also includes contingency actions such as extravehicular activity and unplanned in-flight maintenance procedures. The flow of these facets of retention rationale are shown on Figure 2. [D] Figure 2. CIL Retention Rationale Process III. Suggestions for Effective CIL Implementation Correlation of FMEA Results with Fault-Tree Analyses and Hazards Analyses: The FMEA/CIL data can serve as an input to the hazard analysis process. The hazards analysis uses fault trees and is basically a top down approach. It focuses on human errors and considers multiple unrelated failure modes which the FMEA/CIL ground rules out. The Use of Probabilistic Risk Assessments: Probabilistic risk assessments have proven to be useful procedures in providing product development teams with an insight into factors of safety and to strengthen critical item or single failure point retention rationale. Margins of safety have a strong influence on the acceptability of retaining potential failure modes or critical items if it can be proven that risk of failure is reduced to an acceptably low level. Process, Equipment, and Facility Critical Items Analyses: Failures in manufacturing, assembly, and test processes, equipment, and facilities have only an indirect effect on the freedom of flight hardware and software from mission or life-threatening occurrences. Nevertheless, the conduct of process, equipment, and manufacturing facility FMEAs can provide valuable assistance in identifying critical items whose failure could impact system performance or availability. Statistical process control methods, if used prudently in the manufacture of hardware can assist in the detection of conditions which could lead to impending failures affecting performance or schedule. Computer-Aided Management of Critical Items: Common numbering systems coupled with the use of electronic data processing techniques, can speed up the CIL implementation and management process. Where failure modes or causes are identical or related for various system elements, these failure modes or causes can be referenced rather than repeated, reducing the volume of text in retention rationale. Critical item listings can be more easily referenced to corresponding information derived from fault-tree analyses and hazards analyses if there is a common numbering system. CIL Retention Rationale as a Road-Map: Critical Item List retention rationale that is developed very early in hardware or software programs can be used as a road-map for development plans, tests, and inspections. Development program content, then, can be tailored specifically to prevent loss of mission, vehicle, and human life. This road-map could be used to identify inspection points and to help avoid too many series inspections of the same hardware. Critical Items List should be worked in a way that would not impact important program milestones or create unnecessary work-around in the areas of cost, schedules, or performance. For example, processing methods are needed to quickly disposition discrepancies in critical items. IV. Example Uses of Critical Items Lists The uses of CILs are many. Among the more important uses are: (1) analysis of a product, process or project for reliability and failure avoidance before, during, and after the design process; (2) evaluation of the impact of design, material, or fabrication changes on reliability; (3) assessment of failures experienced during testing; (4) recommendation of design changes that will avoid failure recurrences; and (5) determination of the risk of retaining mission critical or life endangering single failure points or redundant failure modes. Some specific examples of typical applications of the FMEA/CIL methodology as an aid to design follow: Spacelab Recertification after the Challenger Incident During the Spacelab recertification effort after the Challenger accident, the FMEA revealed a potential single failure point in the jettison circuitry of the Inertial Pointing System (IPS). A condition existed in which a short in the emergency arming switch could cause the firing of all four NASA Standard Initiators (NSIs). The analysis also revealed that the harness separator would not fire under these conditions. The detailed FMEA analysis of the wiring harnesses also revealed several mission critical wiring anomalies that had to be corrected. Additionally, the payload retention latch assembly was found to be in need of a redundant operational mode. As a result, redundant end switches were added. Redesigned Solid Rocket Motor (RSRM) Project During routine review and assessment of the CILs for the RSRM, it was observed that the specifications for the finish of the secondary sealing surfaces for nozzle joints three and four (inlet to throat joints) were inadequate to retain a 1R criticality ranking (which is a criticality 1 failure mode but with a second or redundant system). Defects of up to 50-mil depth were permitted on the secondary sealing surface while defects of only 3-mil depth had to be reworked for blending if they occurred in the primary seals. A CIL analysis indicated that actually a criticality 1 (potential loss of life) criticality ranking existed. Space Shuttle Main Engine (SSME) Independent Risk Assessment Team When contamination was discovered in the bearing cage of SSME No. 1209, a special independent risk assessment team was established to assess the problem and to determine if the engine was safe to fly. The team relied heavily on the FMEA/CIL analyses that had already been performed by NASA/MSFC and the SSME contractor personnel in order to understand the potential for failure and possible safety hazards. The team identified rationale for retention of the condition that caused the contamination, and the engine was judged safe to fly. This engine subsequently flew (many missions) successfully with no indication of potential failure. Technical Rationale: Extensive analytical work on existing and emerging programs relative to failure identification, management, and control has resulted in well documented, rigorous procedures for the treatment of critical items. Concurrent engineering approaches to program engineering and management have included attention to more details earlier in the design process and at a much lower level than previously attained. Assurance of success means the elimination or reduction of potential failure modes. Elimination or reduction of potential failure modes can only be achieved through the conscientious application of failure mode and effect analysis, critical item identification early in the concept/design phase, and prudent engineering management. The advantages of the FMEA/CIL process are that it: (1) Systematically identifies all credible failure modes and causes; (2) permits a focus on critical single failure points and levels of redundancy; (3) provides risk acceptance rationale for critical failure modes/causes; (4) provides management control of critical items, associated procedures, specifications, and processes; and (5) provides a single, agreed-to listing of all critical items associated with a given project. References: Requirements for Preparation and Approval of Failure Modes and Effects Analysis (FMEA) and Critical Items List (CIL), NSTS 22206, Revision D, Lyndon B. Johnson Space Center, Houston, TX, December 10, 1993. MSFC Shuttle Elements Lessons Learned for the ASRM Project, George C. Marshall Space Flight Center, September 14, 1993. Space Shuttle Failure Modes and Effects Analysis (FMEA) and Critical Items List (CIL) Groundrules, George C. Marshall Space Flight Center, November 5, 1986. Payload and Experiments FMEA/CIL Groundrules: Marshall Space Flight Center, Report #CR5320.9, MSFC, Alabama. Reliability Preferred Practice No. PD-AP-1307, Failure Modes, Effects, and Criticality Analysis, Jet Propulsion Laboratory. | This practice has been used on Rocket Solid Motor Booster (RSMB), Space Shuttle Main Engine (SSME), Solid Rocket Booster (SRB), and External Tank (ET). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
804 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Contamination Budgeting for Space Optical Systems |  | Nonpractice could result in unacceptable degradation of the optical system with unacceptable scientific results and considerable loss of resources. | Use preplanned contamination budgeting for each manufacturing/assembly, testing, shipping, launch, and flight operation and meticulously test optical systems using witness samples throughout the process to track actual contamination against total and incremental allocations. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1241; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Budgeting of a specific amount of the established allowable contamination to the major elements and operations during fabrication, assembly, testing, transportation launch support, and launch and on orbit operations of space optical systems will preclude jeopardizing the scientific objectives of the mission. Budgeting of contamination to major elements will ensure that the cleanliness of the optics and instruments will remain within designated optical requirements for operations in space. Reliability of the scientific objectives are increased by limiting the contamination allowed to the optical systems during each operation, which ensures that contamination during orbital operations is within specification. Implementation Method: 1. Introduction Contamination budgeting allocations for optical systems should be developed by the chief scientist, systems engineer, and the contamination control engineer using information generated from requirements documents, interface control documents, science working groups, contamination control working groups, contamination control review panels, contamination effects analyses, contamination testing programs, and direct customer involvement. The experience gained from other programs to budget and control contamination is also an input to the determination of a contamination budget. Another factor that should be considered is the cost of controlling contamination versus the scientific payback. The effective control of contamination may require: (1) investments in clean room facilities, (2) training of personnel in clean room operations, (3) monitoring of clean room activities and air quality, (4) acceptance of inefficiencies in working conditions caused by special clothing, restricted space and contamination avoidance provisions, and (5) potential performance tradeoff (i.e., use of cleanable or conductive coatings, modified thermal controls, and use of windows). 2. Budgeting for Contamination The two principal types of contamination sources for optical systems are particulate contamination and molecular contamination. Particulate contamination can consist of airborne particles, insulation shreds, clothing fibers, other human induced substances, and trapped particles in interstitial spaces, such as joints and crevices. When these particles settle on the optical surfaces, they cause degradation by obscuration and light scattering. To avoid jeopardizing the scientific objectives of the HST, the maximum percentage area coverage due to particulate contamination for the primary and secondary mirror was set at 5 percent. [D] Figure 1. HST Particle Contamination Budget Allocation Molecular contamination results from depositing outgassed products on optical surfaces, which may cause performance degradation at most wavelengths by absorbing the wave energy and/or modify polarization characteristics. Examples of molecular contaminants are lubricants, exposed organics, and volatile condensible materials. The allowed (per scientific objectives of HST) degradation due to molecular contamination dictates that the reflectance at 1216 Angstroms shall not decrease by more than 10 percent between the time of coating and five years in orbit. The operations that have the greatest potential for contamination have been allocated the larger budgets. 3. Reallocation The requirement that limits the primary and secondary mirror area coverage total contamination budget cannot be changed. However, changes may occur in the schedule where the operational budget may have to be re-allocated. For example, in the particulate contamination budget for the HST, the original allocation of 1.35 percent assigned to pre-acoustic fallout and the chimney effect and the 1.35 percent assigned to the acoustic testing were changed to 1.30 percent. The 0.6 percent assigned to the fallout and chimney effect after acoustic testing was changed to 0.5 percent. The total of 0.2 percent obtained from these operations was assigned to the unplanned rework and storage operation. [D] Figure 2. HST Molecular Contamination Budget Allocation Technical Rationale: For an optical system to achieve its desired goal of returning adequate scientific results, contamination of the optical system must be kept to a minimum. Establishing a contamination budget and controlling the contaminates within this budget ensures that the optical system will produce satisfactory scientific results. References: LMSC 4176437D: quotHubble Space Telescope Contamination Control Plan,quot Lockheed Missiles and Space Co., Inc., (LMSC) January 30, 1987. LMSC 4176594A: quotContamination Degradation Budget Allocation,quot ST/SE-26 Appendix A, Lockheed Missiles and Space Co., Inc., June 4, 1984. LMSC 4176595C: quotHST Environment Definition and Traceability,quot ST/SE-26 Appendix B, Lockheed Missiles and Space Co., Inc., July 13, 1990. LMSC 4176596A: quotHST Contamination Control Training,quot ST/SE-26 Appendix C, Lockheed Missiles and Space Co., Inc., November 15, 1984. LMSC 4176597A: quotST Contamination Control Violation Reports,quot ST/SE-26 Appendix D, Lockheed Missiles and Space Co., Inc., October 30, 1984. LMSC 4176598A: quotST Thermal Vacuum Bake Out,quot ST/SE-26 Appendix E, Lockheed Missiles and Space Co., Inc., March 31, 1988. LMSC 4176599B: quotHST Cleanliness Status,quot ST/SE-26 Appendix F, Lockheed Missiles and Space Co., Inc., August 30, 1990. LMSC/F157834: quotContamination Control Implementation Plan for HST Rework and Storage,quot Lockheed Missiles and Space Co., Inc., November 1, 1986. LMSC/D975220D: quotHubble Space Telescope, Maintenance and Refurbishment Contamination Control Master Plan,quot Lockheed Missiles and Space Co., Inc., June 30, 1988. NASA SP-5076: quotContamination Control Handbook,quot National Aeronautics and Space Administration, 1969. | This practice has been used on Apollo Telescope Mount (ATM), High Energy Astronomy Observatory (HEAO), Hubble Space Telescope (HST), Advanced X-Ray Astrophysics Facility (AXAF). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
802 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Battery Verification Through Long-Term Simulation |  | Failure to perform long term mission simulations will result in inadequate knowledge of long duration performance characteristics and could result in the retention of undesirable battery characteristics or failure modes that would result in mission failure. | Conduct highly instrumented real-time long term tests and accelerated testing of space flight batteries using automated systems that simulate prelaunch, launch, mission, and post mission environments to verify suitability for the mission, to confirm the acceptability of design configurations, to resolve mission anomalies, and to improve reliability. | MSFC | 01/30/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1434 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Since the operational readiness and future performance of space flight batteries at any point in a mission are strongly dependent upon past power cycles and environments, thoroughly instrumented and analyzed ground testing of space flight batteries identical to flight configurations will ensure predictable performance and high reliability of flight batteries. Implementation Method: Real-time, long term mission, power cycle simulations of space flight batteries in ground facility test beds provide an excellent indication of expected performance in flight. Complete verification of a full real-time mission is not possible with long-term missions due to the test lead time. Instead of accelerating the test, the test engineers should quotleadquot the actual mission by a year or two (as long a lead-time as possible while still being able to use flight designs and configurations). This verification is in addition to qualification steps for the designs. Accelerated testing is not common for low earth orbit (LEO) missions but is used for non-LEO missions. The cells are interconnected in the anticipated flight condition and are housed in a thermally controlled chamber which is purged with an inert gas. Preprogramed, computer controlled power supplies and load banks cycle the batteries through the same dormant, power drain, and charging cycles that they would encounter in the space operation. Shading of solar arrays during eclipse periods is simulated by absence of charging current, and charge cycles are simulated during exposure to the sun. Table 1 lists the principal purposes and features of long-term battery simulations. [D] Table 1. Principal Purposes and Features of Long-Term Battery Simulation All cells are instrumented at various locations for current, voltage, temperature, and pressure. Ambient temperature in the chamber is constantly monitored. Voltage and current values are available in real time through digital readouts. Voltage, current, pressure, and temperature are recorded constantly on strip charts. Data are sampled by computer programs which compute and analyze ongoing performance. Table 2 shows the parameters usually recorded and/or computed for each battery cell from sampled data. Ground testing of batteries and their associated power systems has proven to be a valuable asset for the resolution of in-flight anomalies. Limits testing can be safely simulated on the ground to verify or explore variations in flight performance. [D] Table 2. Recorded and Computed Data Parameters for Each Cell Safety precautions are important in testing of all battery systems because leakage of electrolytes or effluents can be hazardous. Typical precautions and safeguards for nickel-hydrogen (Ni-H2) batteries are shown in Table 3. [D] Table 3. Typical Precautions/Safeguards for Ni-H 2Battery Testing An important action that will help to ensure a successful test effort is the preparation of a comprehensive test plan before the test begins. The test plan should describe the overall scope and approach to the test operation, and provide a detailed test sequence including the test set up parameters, data handling requirements, and test procedures. The test setup description should include the cell specifications and method of packaging into the battery configuration, the data acquisition and control procedures, and the thermal control system requirements. Test procedures should include cell characterization testing procedures (assuming that the cells have already passed through acceptance testing prior to receipt at the test site), launch scenario simulation procedures, mission simulation procedures, and mission capacity test and reconditioning procedures if required. Technical Rationale: MSFC has conducted multi-year testing of silver-zinc, nickel-cadmium, and nickel-hydrogen batteries since 1986. Some tests that were started in 1986 are still underway at this writing. Test durations are over eight years and counting. MSFC is conducting 8 to 10 tests simultaneously, with up to 400 channels of instrumentation on some tests. To support the Hubble Space Telescope, diode bypass relays on two batteries were opened to simulate an in-flight anomaly. The HST ground tests indicated that strong performance should continue from the HST flight batteries despite the in-flight anomaly. References: Whitt, Thomas and Lorna Jackson: quotBattery and Cell Testing at Marshall Space Flight Center,quot (a presentation), NASA/MSFC, EB12, Huntsville, AL, 1988. Brewer, Jeffrey, John Pajak, and Lorna Jackson: quotTest Plan for AXAF-I Ni-H2 Battery Mission Simulation Testing,quot NASA/MSFC, EB71, Huntsville, AL, March 30, 1994. Brewer, Jeffrey, and Thomas Whitt: quotHST Ni-H2 Flight Spare Battery Test,quot NASA/MSFC, EB12, Huntsville, AL, Huntsville, AL, October 6, 1989. Whitt, Thomas, and Charles Hall: quotHST Ni-H2 Six Battery Mission Simulation Test,quot NASA/MSFC, EB12, Huntsville, AL, November 2, 1989. Whitt, Thomas, and Jeffrey Brewer: quotFifth Semi-Annual Report on HST Ni-H2 Six Battery and Flight Spare Battery Test,quot NASA/MSFC, Huntsville, AL, August 8, 1993. | This practice has been used on Hubble Space Telescope (HST), Advanced x-ray Astrophysics Facility (AXAF), External Tank (ET), Solid Rocket Booster (SRB), Inertial Upper Stage (IUS), and Combined Release and Radiation Effects Satellite (CRRES). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
801 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Advanced Computed X-Ray Tomography |  | Failure to apply computed X-ray tomography methods for investigations of appropriate hardware may lead to the use of flawed structures. Further, failure to implement safety precautions may result in injury to exposed personnel. | Use advanced computed X-ray tomography as a precision method of materials characterization and defect location to ensure high reliability of aerospace hardware and conformance to design requirements. Employ this sophisticated and proven technology for nondestructive evaluation (NDE) of materials and structures. Assure the adherence to established precautionary measures during tomography operations. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1436 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Advanced computed X-ray tomography can be used to produce both two-dimensional and three-dimensional images of structures, materials, parts, and components. These images are providing information that is useful for inspection, evaluation, and diagnostics of complex hardware. Implementation Method: 1. General Description of the Process: Advanced computed X-ray tomography uses high intensity X-ray sources, sensitive electronic detectors, sophisticated computer control and analysis techniques, and automated manipulation systems capable of translating and rotating test objects, to produce cross-sectional images of precision aerospace components. A system block diagram is shown on Figure 1. This test method can be used to verify tolerances, to determine relative material densities, to locate inclusions or defects, and to measure the extent of erosion and ablation in composite materials. The equipment and procedure is applicable to metals (up to 10 inches thick) composites, or combination metal/composite structures varying from 2 inches to 50 inches in diameter (depending on the material density) and weighing up to 3700 pounds. [D] Figure 1: Advanced Computed X-ray Tomography Basic System Block Diagram Cross-sectional images, generated by rotating and translating test objects slowly in an X-ray source, produce accurate representations of thin slices of the test object. It takes 20 minutes to produce an image of a thin slice for a typical SRM nozzle. To form a three-dimensional image of the internal structure of the nozzle, 150 to 250 slice images are acquired and stacked. The entire process is controlled remotely by computer. Operational personnel are located external to the test cell. To prevent personnel contact with harmful X-radiation sources or environment, there are safety precautions that include constant dosage monitoring of stray/exposure radiation. A principal use of advanced computed X-ray tomography at MSFC has been evaluation of solid propellant rocket motor nozzles. The technique has been used for verification of nozzle integrity, thermocouple location determination, and post-fire char depth evaluation. The procedure can locate high or low density inclusions, delaminations, or debonds, and profound material density variations. The images can be observed in near real time as they are generated, and are archived for future detailed analysis and evaluation. 2. Safety Precautions: To ensure maximum safety to personnel, equipment, test objects, and the environment, safety precautions for tomography facilities should be established and enforced. Flammable or explosive materials are not permitted in the facility. The minimum personnel required for operation of X-ray sources should be a radiation protection supervisor and an operator. Both should be trained in the principles of radiation protection and safety. Personnel are not permitted in the exposure bay during the activation of the X-ray sources. A key-lock system is installed to prevent activation by unauthorized persons. An electronically controlled safety interlock switch is located on the exposure bay doors to shut down system operation when the doors are opened. Further, manual emergency shutdown switches are located at operator consoles and inside the exposure bay. Radiation meters are used to monitor the control room and adjacent work areas. These switches and meters should be tested and calibrated on a periodic basis. Thermoluminescent dosimeter badges and pocket dosimeters are used to monitor exposure to radiation of the personnel. Detailed operating schedules, access control, and sign-in logs should be used to prevent or limit unauthorized persons from entering the facility during operation and to record those who visit during non-operation periods. Warning lights are used to warn personnel of impending or ongoing operations. Video surveillance cameras are used to monitor critical areas to prevent access by unauthorized personnel. Technical Rationale: The MSFC has operated its computed X-ray tomography facility since 1988 with significant benefit to product reliability and with no injury to the personnel or facility. X-ray sources used include a two million electron volts (ev) accelerator, and 420, 320, and 150 Kev X-ray tubes. Computer control of high energy X-ray sources with remote video viewing along with the proper precautions and warnings have been proved to provide a safe and effective inspection procedure. References: Hediger Lisa: quotReliability Improvement for the Advanced Computed Tomography Inspection System (ACTIS),quot Marshall Space Flight Center, AL, August 1992. Lawson, Seth et. al.: quotModified NASA Motor Process Procedure,quot M&P-M-NASA-027, Marshall Space Flight Center, July 1993. Hediger, Lisa et. al: quotStandard Operating and Safety Procedures for the Advanced Computed Tomography Inspection System (ACTIS) Facility,quot EH13P-88-01-Revision A, Marshall Space Flight Center, AL, February 1988. Lee, T.J.: quotRadiation Safety Manual,quot MM 1860.2D, Marshall Space Flight Center, AL, December 26, 1991. Reliability Preferred Practice PT-TE-1423, quotRadiographic Testing of x-ray Materials.quot | This practice has been used on Solid Rocket Motor (SRM), Space Shuttle Main Engine (SSME), Solid Propulsion Integrity Program (SPIP), Modified NASA Motor Program, Sub-Scale Solid Rocket Combustion Simulator, other aerospace and aerospace-related applications. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
806 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Rocket Engine Technology Test Bed Practice |  | Failure to conduct technology testing could result in the absence of reliability enhancing improvements in the engine configuration and could cause subtle failure modes or performance limits to be unnoticed until critical points in the engine development or flight schedule. | Conduct highly instrumented tests of O2/H2rocket engine systems to: (1) evaluate and verify new propulsion technologies; (2) validate or modify analytical models; (3) more fully understand the operation of rocket engine systems under varying performance conditions, and (4) ensure engine reliability and operability. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1427 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Highly instrumented engine system tests of varying configurations under varying conditions provides engine system level validation of advanced propulsion technology concepts prior to incorporation of these concepts into development or production units; provides an opportunity for greater understanding and fine-tuning of analytical tools that characterize engine performance; results in the development and improvement of diagnostic methods; and increases the depth of available knowledge about the inner workings, sensitivities, and detailed performance characteristics of liquid rocket engine systems. The overall benefit are the validation of technology, improved system performance, high system reliability, and mission safety. Implementation Method: Experience in the planning and conduct of propulsion technology tests using the Space Shuttle Main Engine (SSME) has resulted in a systematic and methodical procedure for planning, testing, data analysis, and reporting the results of test bed activities. As seen in Table 1, the testing has ranged from evaluation of new engine components and features, to advanced diagnostic and sensor techniques, to the development of systems for anomaly and failure detection. A key to the continued success of this program has been a technology integration process that places emphasis on integration requirements and costs at an early point in the process. Figure 1 is a flow diagram that depicts the technology integration process. Once an engine technology item has proceeded through the concept evaluation process to a point where a decision is made to pursue test bed evaluation, it is presented by the principal investigator to the Test Bed project manager for prescreening review and then a technology item screening review. [D] Table 1. Typical Types of Technology Test Bed Testing [D] Fig. 1. Technology Test Bed Technology Integration Process In the screening review, an engine technology candidate is judged by its technical merit and potential benefit, the risk of testing the item on the Technology Test Bed engine, and the cost of integrating the item into the engine or facility. Key milestones in the process are Technology Item Screening, the Technology Item Final Design Review, the Integration Design Review, and Hot Fire Testing. Technology Item Final Design Review: Once the technology item is accepted as an output of Technology Item Screening, technology item development proceeds with the conduct of analytical studies, component testing, and the incorporation of design revisions, if required. Then a Technology Item Final Design Review is conducted in which four subject areas are presented and discussed: (1) Technology Item Design Description; (2) Technology Item Design Verification; (3) System Issues; and (4) Safety/Quality Issues. The Technology Item Design Description includes the design configuration and characteristics; the design intent or function; the design requirements; materials and processes, drawings and an integrated design configuration. The Technology Item Design Verification consists of the qualification approach, test and verification plans and results, supporting analysis and assurance that the design and performance meets the intent of the requirements. System Issues include system requirements, system compatibility issues, integration plans and issues, constraints, and Technology Test Bed test operational requirements. Safety/Quality Issues include quality assurance provisions such as fabrication processes and controls, traceability, vendor qualification, and nondestructive evaluation techniques; technology item life; risk assessment; hazards analysis; failure modes and effects analysis; risk mitigation; materials certification; and supporting analyses. When the technology item final design review is successfully completed, fabrication can proceed and readiness certified upon acceptance. Technology Item Integration Design Review: The integration review is conducted to verify that the technology item can be accommodated safely and effectively into the TTB. It consists of: (1) an Integration Design Description; (2) Integrated Design Verification; (3) System Issues, and (4) Safety/Quality Issues. The subject areas covered in the Technology Item Integration Design Review are similar to those for the Technology Item Final Design Review except that all factors are viewed from the standpoint of interaction of the technology item with the Test Bed and its related subsystems, facilities, instrumentation, software and data. Hot Fire Testing and Results: A test plan is prepared for each test series, and it is reviewed at a pretest readiness review before each test. Instrumentation is configured in accordance with an Instrumentation Program and Command List (IP&CL). A test results review is held after each test and a test report is prepared. When two or more tests are combined into a test series, a test series report is prepared. Examples of these documents are included in the list of References for this practice. Technical Rationale: In the conduct and analysis of over fifty tests conducted in the Technology Test Bed program by MSFC since September 1988, the SSME TTB program has proven to be an indispensable tool in the validation of propulsion technology advances for large liquid oxygen/liquid hydrogen rocket engines. The program has also yielded numerous advances in measurement and diagnostic methods that are continuing to be used in the TTB program and are applicable to other similar test and evaluation scenarios. The TTB's highly instrumented engine employs over five times the number of measurements used for an acceptance test of a flight engine. This in-depth instrumentation using flow meters, steady state pressure transducers, high frequency pressure measurements, thermocouples, strain gauges, accelerometers, and sophisticated laser and optics techniques has provided an unprecedented amount of detailed knowledge of the performance subtleties of large O2/H2 engines under widely varying conditions. The program has yielded results that have permitted the incorporation of state-of-the-art technology advances without compromising engine reliability. References: quotSSME Improved Characterization Using Highly Instrumented Engine Test Data,quot B. Piekarski and J. Leahy, Martin Marietta, AIAA/SAE/ASME/ASEE 28th Joint Propulsion Conference, July 6-8, 1992, Nashville, TN, AIAA # 92-3451. quotSpace Shuttle Main Engine Technology Test Bed overview,quot H.V. McConnaughey, Advanced Earth-to-Orbit Propulsion Technology Conference, 1992, Huntsville, AL. quotTechnology Test Bed Program: Engine 3001 with Instrumented Turbopumps,quot NASA/MSFC Test Series Report No. TTB-DEV-EP93-001, January 15, 1993, Huntsville, AL. quotTechnology Test Bed Test Report: Engine #3001,quot NASA/MSFC Report # EP52(92TR-033), August 1992, Huntsville, AL. quotTechnology Test Bed Program: Instrumentation Program and Command List,quot NASA/MSFC Document 1618, November 1989, Huntsville, AL. | This practice has been used on Space Shuttle Main Engine (SSME), and Technology Test Bed (TTB) Program. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
805 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Practice of Reporting Parts, Materials, and Safety Problems (Alerts) |  | Failure to issue or properly designate or to review for program/project impact ALERTS and Problem Advisories or SAFE-ALERTS could cause duplication of testing, possible schedule delays, loss of mission, and, in extreme circumstances, loss of life. | Ensure that potentially significant problems involving parts, materials, and safety discovered during receiving inspection, manufacturing, post-manufacturing inspection, or testing do not affect the safety or the performance of NASA hardware by reporting all anomalies via ALERT systems. ALERTS and SAFE ALERTS pertaining to these problems are quickly disseminated for impact assessment and, if required, corrective action taken or a rationale developed for flying as is. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1428 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The benefit of the ALERTS system is the reduction or elimination of duplicate expenditures of time and money by exchanging information of general concern regarding parts, materials, and safety problems within MSFC, between MSFC and other NASA centers, between NASA and other government organizations, and between government and industry to assist in preventing similar occurrences. The use of the ALERTS system avoids future failures, rules out fraudulent hardware, helps enhance reliability, and ensures mission success. Implementation Method: The Government-Industry Data Exchange Program (GIDEP) is an on-line service that fosters cooperative data interchange between government and industry seeking to reduce or eliminate duplicate expenditures of time and money by making use of existing knowledge. The program provides a means to exchange technical data essential in the research, design, development, production, and operational phases of the cycle of systems and equipment. The primary objectives are to improve reliability, quality, productivity, safety and logistics support. A GIDEP participant may be either a government or industry activity engaged in the design, development, test, production, or support of equipment and systems. Universities and consultant firms who qualify may also participate. GIDEP participants may have access to any of the following four data interchanges 1) Engineering Data Interchange, 2) Failure Experience Data Interchange, 3) Reliability-Maintainability Data Interchange and 4) Metrology Data Interchange. The Failure Experience Data Interchange (FEDI) is the GIDEP data interchange relative to ALERTS, SAFE-ALERTS, and Problem Advisories. The FEDI contains objective failure information generated when significant problems are identified on parts, components, processes, equipment, materials, specifications, or safety hazards. This data includes ALERTS and SAFE-ALERTS, failure analysis, problem information data and manufacturing sources data. The initiator of an ALERT coordinates the ALERT with the manufacturer (vendor) when applicable then forwards the ALERT to the GIDEP Operations Center for electronic distribution to all participants. SAFE-ALERTS describe problems usually related to finished products which could have an impact on the safety of personnel or risk damage to facilities or equipment. FEDI Report definitions follow: ALERT - An ALERT reports a problem with parts, components, materials, specifications, manufacturing processes, or test equipment that can cause a functional failure. SAFE-ALERT - A SAFE-ALERT reports a problem that relates to the safety of personnel or equipment. PROBLEM ADVISORY - A Problem Advisory reports 1) preliminary information on a suspected problem, or 2) a problem with parts, components, materials, manufacturing processes, specifications or test equipment that has an unknown or a low probability of causing a functional failure. Problem advisories that report preliminary information must be followed by updated reports at not less than 30 day intervals until resolved or canceled. MSFC prime contractors are required to participate in GIDEP when their participation is considered advantageous to the program. However, the contractor must obtain MSFC approval for ALERTS which they propose on MSFC hardware. Nonparticipating subcontractors may propose ALERTS for submission to GIDEP via the MSFC System. Approximately 250 to 300 GIDEP ALERTS, SAFE-ALERTS, and Problem Advisories are received and processed each year. Approximately 10 to15 preliminary ALERTS or SAFE-ALERTS are generated within NASA; of those approximately 2 to 4 originate at MSFC. The MSFC ALERT system is comprised of the GIDEP ALERTS, SAFE-ALERTS, and Problem Advisories and internal NASA ALERTS, SAFE-ALERTS, and Problem Advisories. These are processed at MSFC using MSFCís tailored system as shown in Figure 1, MSFC ALERT/SAFE-ALERT System Flow Chart. The left portion of Figure 1 depicts processing ALERTS that originate outside MSFC (includes other NASA centers and GIDEP). The ALERTS are received by the ALERT coordinator, logged in and forwarded to the appropriate MSFC Laboratory for technical evaluation. This evaluator determines whether the alert should be considered a FULL ALERT, Information ALERT, or No Action Required, which is entered onto an evaluation form. These three categories are defined as follows: A FULL ALERT is a serious problem which involves a high probability of causing a failure in quality sensitive equipment. The FULL ALERT should be disseminated immediately for investigation and a required response. An Information ALERT reports a minor problem with low risk of affecting quality sensitive equipment. It will be disseminated for information and will require a response only if it results in an impact. No Action Required is a classification that is applied to conditions which do not represent valid problems or have no impact on quality sensitive equipment. These conditions should not be classified by NASA as an ALERT and it will receive no further dissemination. [D] Figure 1: MSFC ALERT/SAFE-ALERT System Flow Chart The completed evaluation form is returned to the MSFC ALERT Coordinator and filed if classified as ìNo Action Required.î If the ALERT is classified as an Information ALERT or FULL ALERT, it is transmitted to MSFC contractors, laboratories, project offices, and the safety office. When a response is received from a MSFC contractor it is routed through applicable MSFC project offices for coordination with MSFC laboratories and transmitted to the MSFC ALERT coordinator for action and closeout. Responses from MSFC laboratories and safety offices are forwarded to the MSFC ALERT coordinator for action and close out. The response to an ALERT indicates whether the item is included in the system and, if so, what corrective action is required. Further use of the problem part, material, equipment, or process does not take place until the corrective action is implemented. The right portion of Figure 1 depicts proposed ALERTS originating within MSFC and MSFC contractors. The proposed ALERT is forwarded to the MSFC ALERT coordinator, logged in and forwarded to the appropriate MSFC laboratory or safety office for technical evaluation and recommendation. The MSFC ALERT coordinator forwards comments to the affected manufacturer (vendor) for their evaluation and comments. The manufacturer returns their comments to the MSFC ALERT coordinator who transmits information ALERT or FULL ALERT to MSFC contractors, laboratories and project office and safety office with copies to NASA Headquarters, other NASA centers and GIDEP. Responses received from MSFC contractors, laboratories, and safety offices are routed and closed out as stated earlier. An ALERT is considered to be a NASA-wide concern if it is a potential source of unreliability, performance degradation, personnel hazard, or if it may result in a significant schedule delay. Technical Rationale: As technical rationale, two specific situations in which ALERTS or SAFE-ALERTS have been vital to mission success are described below: ALERT No. H1-A-88-01 dated 3-15-88 This ALERT started out as a MSFC TWX ALERT 5210A dated 2-17-88 by memorandum from the MSFC ALERT coordinator. The TWX, and later the GIDEP ALERT, stated that a quality assurance product audit was performed on NAS bolts fabricated from A-286 steel and disclosed they were not properly tested to the requirements of the NAS specification by the manufacturer. This ALERT affected shuttle elements, payloads and satellites. Considerable effort was made to identify and determine the extent of prior use of NAS bolts from the same manufacturer. Testing was performed on the fasteners to determine shear and tensile strengths. Stress analysis was performed using the test results. In all cases, positive margins of safety were depicted. To ensure that the fasteners would be acceptable for 40 usages, a fatigue analysis was performed. An inspection plan was implemented for future procurement of these fasteners. SAFE-ALERT No. M7-S-93-01A A Battery case is part of the Alinco Igniter Circuit Tester, Model 101-5CFG. Embedded in the battery case is a resistor that limits the amount of current to 5 milliamps. This current is low enough to prevent activation of the igniter but sufficient to determine if the igniter is functional through a continuity test. In 1989, a tester was returned for battery replacement and calibration. The presence of the current limiting resistor in the battery case was unknown to the repair technician, who discarded the case because new, larger batteries were required. Use of the tester resulted in premature ignition of a test rocket flare. Fortunately, no injuries occurred. A SAFE-ALERT was issued in 1989, but was not incorporated correctly into the GIDEP data base because an improper document number of M7-F-89-01 was assigned. (The F should have been an S, which would have designated the document as a SAFE-ALERT). As a result of this improper designation, all of the users of this circuit tester model were not alerted to this hazardous situation, and, in an incident in Sweden in 1993, the same model tester caused the ignition of a rocket motor which resulted in one death, three injuries, and two damaged buildings. This incident underscores the need to accurately and promptly designate and disseminate ALERTS and SAFE-ALERTS. However, since Canada is the only other country that is a member of GIDEP, it is doubtful that Sweden would have been alerted. With proper designation, membership in GIDEP would have been another essential element in avoiding the problem. References: MMI 5310.2D: ALERTS and SAFE-ALERTS Reporting of NASA Parts, Materials, and Safety Problems, Marshall Management Instruction, Marshall Space Flight Center, AL 35812, February 4, 1986. NMI-5310.2C: Participation in The Government-Industry Data Exchange Program (GIDEP), NASA Management Instruction, National Aeronautics and Space Administration, Washington, D.C., July 9, 1991. NHB 5310.3: Procedures for NASA ALERT Reporting of Parts, Materials, and Safety Problems, NASA, Office of Safety and Mission Quality Publication, April 1993. NMI 5310.1D: NASA Alert Reporting of Parts, Materials, and Safety Problems, NASA Management Instruction. Government-Industry Data Exchange Program (GIDEP), Program Summary, GIDEP Operations Center, Corona, CA 91720, September 1987. | This practice has been used on Space Shuttle External Tank, Space Shuttle Main Engine, Space Shuttle Solid Rocket Booster, and Space Shuttle Experiments/Payloads. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
809 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Heat Sinks for Parts Operated in Vacuum |  | Hot parts increase failure rate and reduce life. High part failure rates lower the reliability of flight hardware. Low reliability can cause early mission failures that can be very expensive and lower agency prestige. | Perform a thermal analysis of each electronic assembly to the piece-part level. Provide a heat conduction path for all parts whose junction temperature rise exceeds 35oC above the cold plate. | GRC | 01/27/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1411 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Controlling the operating temperature of parts in a vacuum flight environment will lower the failure rate, improve reliability and extend the life of the parts. Implementation Method: Thermal design is used to control the temperatures of the parts in equipment so that they will not exceed specific maximum safe temperatures and to minimize the parts temperature variations under all environmental conditions in which the equipment will operate. The maximum safe temperatures must be calculated based on a parts stress analysis and must be consistent with the required equipment reliability. It is usually necessary to maximize the heat transferred by only a single mode in order to obtain adequately low thermal resistances within equipment. Even though a complete cooling system may include three modes of heat transfer, each particular heat path will usually emphasize a single mode. Where a single mode dominates, other modes can often be ignored. For example, with conduction as the predominant mode for parts operated in a vacuum, the conductive thermal resistance can be made low by the use of thermal shunts. The heat transferred by radiation and convection is almost negligible. That is, in the electro-thermal analogue, the shunt thermal resistances due to radiation and convection are so large that they are insignificant for design purposes. Figure 1 shows an electrical analog of a thermal system of a typical part. Figure 1: Equivalent Thermal Circuit of a Part [D] For example, consider a linear integrated circuit, Part Number 9716 being used in an A/D Converter in a vacuum environment. Without a heat shunt, the case to board temperature rise can be about 15oC for the part when dissipating 300 milliWatts. With a metal clad heat shunt, the case to board temperature rise can be reduced to about 5oC for the same conditions. Figure 2 shows the electrical analog of the thermal system with the shunt. Figure 2: Equivalent Thermal Circuit with Heat Sink [D] Additional enhancement can be obtained through the use of printed circuit boards with metal planes for heat conduction and heat straps for other hot spots. This has been found to be an effective method for conducting heat to the spacecraft cold plate. The effect of this design is to reduce the temperature of the board by minimizing the temperature rise from the cold plate to the board. A reduction in board temperature will allow for an increase in thermal shunting capacity for the applicable heat conduction path. Technical Rationale: The failure rates of parts increase with loading or stress level, whether it be thermal, electrical, or mechanical. Stresses below the intensity which causes catastrophic failure result in progressive deterioration of material. The effect of temperature cycling is believed to be extremely significant. Thermal failure of parts is caused by deterioration, due to temperature, of the materials of which the part is made. An old rule of chemistry (the Arrhenius Rate Law) states that the speed of chemical reactions doubles for every 10oC increase in temperature. Parts failure rates are known to increase exponentially with temperature as evidenced in published data. A thermal failure may occur so rapidly as to be considered catastrophic. However, there is always a slow, progressive deterioration of dielectrics, cathode coatings, transistor junctions and many other materials which accelerates with temperature, leading eventually to failure. These effects are cumulative so that failure rate depends to some extent on the entire ground test/mission thermal history, the temperature-time integral. Thermal failure is, therefore insidious since it is usually impossible to determine the percentage of life remaining in a part. This has a direct bearing on the effects of temperature cycling, which is specified in nearly all specifications for testing parts and equipment, and which may occur during the normal operation of equipment in space, especially if the equipment is power cycled. There are indications that temperature cycling has a very adverse effect on reliability but there exist little quantitative data and no adequate theory by which the effect can be accurately estimated. The true thermal stress is usually at the internal junctions of the part. Since this is internal to the part, it is difficult to measure. The temperature of the accessible outer surface is the most practical index of the thermal condition of the part. Surface or body temperature is a function of the heat dissipation within the part and of its thermal environment, which is a complex function of: (1) coolant type, temperature, pressure and velocity; (2) the configuration, emittances and temperatures of neighboring surfaces; and (3) all conductive heat flow paths surrounding the part. This becomes evident from Figures 1 and 2. References: Electronic Reliability Design Handbook, MIL-HDBK-338-1A, October 1988. Glover, Daniel, Design Considerations for Space Flight Hardware, NASA TM-102300, January 1990. Reliability/Design Thermal Applications, MIL-HDBK-251, January 1978. Reliability Prediction of Electronic Equipment, MIL-HDBK-217E Notice 1, January 1990. EEE Parts Derating, Reliability Preferred Practice PD-ED-1201 Part Junction Temperature, Reliability Preferred Practice PD-ED-1204 Thermal Test Levels/Durations, Reliability Preferred Practice PT-TE-1404 Thermal Analysis of Electronic Assemblies to the Piece Part Level, Reliability Preferred Practice PD-AP-1306 | This practice has been used on SERT II, SAMS, CTS, Atlas/Centaur, and Titan | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
807 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Penetrant Testing of Aerospace Materials |  | Failure to locate surface flaws in critical stressed areas of parts and structures could result in loss of part or structure, loss of mission, and in extreme cases loss of life. | Penetrant testing improves hardware reliability by detecting surface flaws and defects in solid materials and structures. The discontinuities must be open to the material surface. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1426 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Penetrant Testing is a cost effective, nondestructive method for determining cracks, porosity, gouges, laps, seams, and other flaws that are open to the surface of metallics and selected non-metallics. Implementation Method: Liquid penetrant testing is a nondestructive method of detecting surface flaws in solid material and structures. Cracks, porosity, gouges, laps, seams, and other types of flaws can be found using this technique. Penetrant testing is a process in which the liquid penetrant is drawn into small openings by capillary action when it is applied to a surface. After a specified time, excess penetrant is removed from the surface and developer is applied to the surface. The developer absorbs residual penetrant drawn from the flaw leaving a bright-colored penetrant ìbleedingî through the developerís white background giving a clear visual indication of cracks, porosity, and other flaws. There are numerous types and sensitivities of penetrants. The penetrant systems, consisting of penetrant, developer, and cleaner, must be selected for component compatibility and be suitable for use on the test article. In addition to the specific requirements for actual penetrant test, initial surface preparation and final cleaning often requires detailed procedures. Table 1 shows five sensitivity levels for penetrants. Penetrants have been developed for specific applications for ferrous metals, nonferrous metals, glass, polymers and ceramics. The penetrant must also be compatible with the test article to avoid material degradation and possible explosion. For example, the chemical combination of incompatible penetrant materials, the container material, and liquid oxygen, combined with impact or shock, can cause an explosion. Common properties and characteristics of suitable penetrants are listed in Table 2. [D] Table 1. Sensitivity Levels for Penetrants [D] Table 2. Properties and Characteristics of Penetrants There are six basic steps required to perform a penetrant test. These six basic steps are shown in the flow diagram on Figure 1. [D] Figure 1. Penetrant Test Flow Diagram The most common cleaning methods are application of solvents, vapor degreasing, detergent cleaning, steam cleaning and ultrasonic cleaning. Mechanical cleaning using wire brushes, abrasives, emery cloths, or metal scraping are not recommended. However, if mechanical cleaning must be used, light chemical etching is required to reopen any closed flaws. Penetrant testing should be accomplished before any paint or metallic coating is applied since these coatings will close any flaws. The success of penetrant testing depends upon the visibility of flaw indications. To ensure visibility, the penetrant contains either a colored dye easily seen in white light, or a fluorescent dye visible under black (ultraviolet) light. A list of penetrants typically used is listed in reference 4. The penetrant is applied by either dipping, spraying, brushing, or flowing. After penetrant application, a sufficient time (dwell time) is provided to permit the penetrant to permeate the flaw. The manufacturers of penetrants provide the minimum dwell times charts. A typical dwell time chart is shown in Table 3. The penetrant must not be allowed to dry during the dwell time, and must remain wet until the excess penetrant is removed. If penetrant has dried, then the process must be repeated. [D] Table 3. Typical Dwell Time Chart Removal of the penetrant depends upon the type used. The most common methods used are water washable, post emulsified, and solvent removed. Care must be exercised to ensure that the specimen is not over cleaned, thereby removing the penetrant from the flaw. Generally, a developer is required, although some penetrants are formulated for use without a developer. A whitish powder in the developer is very absorbent and acts as a blotter. This blotting action carries the penetrant from the flaw into the powder, forming a flaw pattern. Inspection of the specimen consists of analysis of the patterns on the developer and determining their cause. Inspection may reveal patterns that are either true indications or false indications of a flaw. The true indications are those caused by penetrant bleeding from the actual flaws. Improper cleaning in the initial cleaning step and incomplete removal of the excess penetrant are common causes of false indications. False indications sometimes look like and may hide true indications. If there is doubt about the source of a pattern on the developer, the test should be repeated and the patterns carefully analyzed as they develop. The ability to identify true indications requires much practice. For example, cracks, cold shunts, seams, and forging laps all show up as a continuous line. The same flaws may show up as an intermittent line indicating that the flaw may be partially closed at the surface. Small dots and round indications generally indicate porosity, small inclusions, or blow holes. If the defect is located below the surface, the sensitivity of this method diminishes rapidly with depth. Penetrant inspectors should be qualified and certified in accordance with MIL-STD-410E or SNT-TC-1A. To provide permanent records, photographs of the specimen should be taken prior to post cleaning. Post cleaning is only required of those specimens that are found free of defects. Defects are described by engineering or as specified in MIL-STD-1907. Post inspection cleaning is necessary since the penetrant and developer residue tend to attract moisture, which can cause corrosion or can interfere with subsequent processing or usage. The cleaning methods for post inspection cleaning are generally the same as those recommended for precleaning. Advantages and disadvantages of the penetrant testing method are shown in Table 4. [D] Table 4. Advantages and Disadvantages of Penetrant Testing Method The hazardous properties that should always be considered when using a dye penetrant are liquid flashpoint and toxicity. The flashpoint of penetrant processes can be as low as 40oF to as high as 200oF. The penetrants should be used per manufacturer's instructions. Most penetrants are not actually toxic and do not present a particular hazard in normal use. However, there are precautions that should be followed. Practically all liquid materials used in penetrant, cleaner, and developer have good wetting and detergent properties. Therefore, they exhibit excellent solvent power for fats and oils. These materials, when allowed to contact the skin for an extended period, will dry out the natural oils from the skin, causing it to become rough, red, and if left untreated to eventually crack open, which could cause a severe secondary infection. This is preventable by wearing neoprene-type gloves and aprons, face shield, and protective clothing. If exposed to this skin drying, replenishing the oils on the exposed skin should prevent any cracking. Another hazard with penetrants is the using of dry developers which could be inhaled and become a health hazard. The use of any of the penetrant processes should be performed in a well-ventilated area. If working in a confined area such as a tank, the inspector should have an individual air supply with a full helmet over the head. The black light used when inspecting fluorescent penetrants can cause severe sunburn and damage to the eyes. The blacklight source should always be checked for missing, cracked, or broken filters and repaired before use. Store penetrants in an approved fire container. Technical Rationale: Marshall Space Flight Center has successfully used the penetrant testing method for years. It is a proven method for locating flaws in surface areas of highly stressed areas of components and structures. In addition, it is an effective method for both metallic and nonmetallic materials. References: Bray, Don E. and Don McBride: quotNondestructive Testing Techniques,quot John Wiley & Sons, Inc., New York, NY, 1992. Metals Handbook, Vol. 17: quotNondestructive Inspection and Quality Control,quot pp. 71-88 ASM International, Metals Park, OH 1989. CT-6-2: quotNondestructive Testing Liquid Penetrant,quot Fourth Edition, Class Room Training Handbook, General Dynamics, Convair Division, 1977. P1-4-2: quotNondestructive Testing, Liquid Penetrant,quot Fourth Edition, Programmed Instruction Handbook, General Dynamics, Convair Division, 1977. MIL-STD-410E: quotNondestructive Testing Personnel Qualification and Certification,quot Military Standard, January 1991. MIL-STD-6866: quotLiquid Penetrant Inspection,quot Military Standard, 1989. MIL-I-25135: quotPenetrant Inspection Materials,quot Military Specification, 1989. MIL-STD-1907: quotPenetrant and Magnetic Particle Inspection, Soundness Requirements for Materials, Parts and Weldments,quot Military Standard, 1990. SNT-TC-1A, quotRecommended Practice, Personnel Qualification and Certification in Nondestructive Testing,quot American Society for Nondestructive Testing, Columbus, OH, 1988. | This practice has been used on Saturn I, IB&V, Apollo, Skylab, Space Shuttle External Tank (ET), Space Shuttle Solid Rocket Motor (SRM), Space Shuttle Main Engine (SSME), Space Shuttle Solid Rocket Booster (SRB), and other Marshall Space Flight Center programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
808 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Magnetic Particle Testing of Aerospace Materials |  | Failure to detect defects in surface and subsurface areas of components could result in failure of the components, failure of mission and in extreme cases loss of life. | Magnetic Particle Testing can be used on all ferromagnetic materials to locate surface and subsurface discontinuities such as cracks, laps, seams, and inclusions. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1425 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Magnetic particle testing is a cost effective and expedient nondestructive Testing (NDT) method for determining discontinuities in ferromagnetic material. This NDT method can be performed in both the longitudinal and transverse directions. Implementation Method: Magnetic particle testing (MPT) is a nondestructive method for locating cracks, laps, seams, inclusions and other discontinuities on or near the surface of ferromagnetic materials. MPT is based on the principle that the magnetic flux near the surface of a magnetized material is distorted locally by the presence of discontinuities. This distortion of the field pattern, or quotflux leakage,quot as illustrated in Figure 1, is capable of attracting and holding an inspection medium of finely divided magnetic particles. Depending upon the type particles used, they will be visible under the proper lighting condition. [D] Figure 1. Leakage Field at a Crack in a Bar Magnet Direct current (DC) and alternating current are both suitable for magnetizing parts for MPT. The primary difference between the two currents is: the fields generated by DC penetrate the cross section of the part, and the field generated by the AC are confined to the metal at or near the surface of the part. Therefore, AC should not be used for subsurface discontinuities. The most common magnetization processes are circular and longitudinal. Circular magnetization is when electric current is passed through a straight conductor creating a circular magnetic field around the conductor (see Figure 2a). Longitudinal magnetization is when electric current is passed through a coil of one or more turns a magnetic field is established within the coil (see Figure 2b). To form an indication, the magnetic field must approach a discontinuity at an angle great enough to cause the magnetic field to leave the part and return after bridging the discontinuity. Best results occur when the intersection is 45 degrees to 90 degrees to the magnetic field lines. [D] Figure 2. Magnetized bars showing directions of magnetic field: (a) circular and (b) longitudinal Magnetic particles may be applied to surfaces in a dry form or they may be suspended in a water or oil carriers. The particles are usually coated with a fluorescent material for easy visualization using a black light. When using MPT make sure the induced current is strong enough to produce the magnetic field required to show the flaws being tested for. One fast method to insure adequate current is the use of a quotfield indicator.quot The field indicator consist of a metal disk with cross hatch lines with a thin metal cover attached over the cross hatch disk mounted on a yoke handle. This field indicator is placed in the magnetic field and the current increased while adding magnetic particles until the magnetic particles form a well-distinguished cross on the metal cover. There are also formulas in the references that can be used to determine the starting current. The current can be adjusted as necessary to obtain the desired magnetic field. The advantages of using Magnetic Particle Testing are: Complex shapes can be tested. Cracks filled with paint or other foreign material can be detected. Large numbers of similar parts can be rapidly tested/automated. Small fine cracks can be detected. Subsurface discontinuities can be located. Cracks can be located through thin nonmetallic coatings. Estimate crack depth. Easily learned. Relatively low cost. The disadvantages of magnetic particle testing are: Only ferromagnetic materials can be tested. High electric current required to magnetize. Demagnetization required in some instances. Extreme care to avoid burn spots. Difficult to detect small defects below the surface. Cleaning required after test. Complex shapes may require more than two magnetizations. All personnel performing MPT should be qualified and certified in accordance with MIL-STD-410E. Detecting discontinuities is relatively simple, but adequate interpretation of the indication requires experience and judgement. The safe handling of the magnetic particles are governed by the suppliers Material Safety Data Sheet (MSDS). The suppliers MSDS should certify that the flash point of the oil carriers meet the requirements of DOD-F-87935. The MSDS should also detail personnel hazards such as inhalation, skin contact and eye exposure. Magnetizing equipment should be properly maintained to avoid personnel hazards from electrical shorts. Care should also be taken to avoid electrical arcing and possible ignition of the oil carriers. Any broken ultraviolet filters or bulbs should be replaced immediately. Personnel entering a darkened area to perform fluorescent testing should wait at least one minute for their eyes to adjust to the darkened area. Technical Rationale: MPT is a fast and cost-effective method for determining surface and subsurface defects in ferromagnetic materials. The MPT techniques may be used for in-process inspection and control, final inspection, receiving inspection, and periodic maintenance of machines, structures and handling equipment. References: Bray, Don E. and Don McBride: quotNondestructive Testing Techniques,quot John Wiley & Sons, Inc., 1992. McMaster, Robert C.: quotNondestructive Testing Handbook,quot Volume II, The Ronald Press Company, New York 1963. Metals Handbook, Volume 17: quotNondestructive Inspection and Quality Control,quot pp. 89-128, ASM International, Metals Park, OH, 1989. MIL-STD-1949A: quotMilitary Standard, Magnetic Particle Inspection,quot May 1989. MIL-STD-1907: quotMilitary Standard, Inspection, Liquid Penetrant and Magnetic Particle, Soundness Requirements for Materials, Parts and Weldments,quot March 1990. MIL-I-83387: quotMilitary Specification, Magnetic Rubber Inspection Process,quot July 1987. ASTM E 1444-93: quotStandard Practice for Magnetic Particle Examination,quot American Society for Testing and Materials, 1916 Race St. Philadelphia, PA 18103. MSFC-STD-1249: quotStandard NDE Guidelines and Requirements for Fracture Control Programs,quot Marshall Space Flight Center, AL 35812, September 1985. CT-6-3: quotNondestructive Testing Magnetic Particles,quot Class Room Training Handbook, Second Edition, Convair Division of General Dynamics, San Diego, CA 1977. P1-4-3: quotNondestructive Testing, Magnetic Particle,quot Programmed Instruction Handbook, Fourth Edition, Convair Division of General Dynamics, 1977. MIL-STD-410E: quotMilitary Standard, Nondestructive Testing Personnel Qualification and Certification,quot January 1991. | This practice has been used on Saturn I, IB, V, Apollo, Skylab, Space Shuttle Solid Rocket Booster (SRB), Space Shuttle Main Engine (SSME), and other MSFC projects. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
810 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Thermal Cycling |  | Design and manufacturing defects that could have been detected during ground testing manifest themselves during flight. | As a minimum, run eight thermal cycles over the approximate temperature range for hardware that cycles in flight over ranges greater than 20oC. The last three thermal cycles should be failure free. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1402, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Demonstrates readiness of the hardware to operate in the intended cyclic environment. Precipitates defects from design or manufacturing processes that could result in flight failures. Implementation Method: As part of ATP, run at least eight thermal cycles over the temperature range experienced by the hardware during storage, shipping, launch, flight, and reentry. The maximum and minimum temperatures anticipated should be exceeded by 10 degrees C. The last three thermal cycles should be failure-free. Equipment must stabilize at these limits before cycling to the opposing limit. Equipment generally should be operated within the anticipated thermal range rather than at the thermal limits. Thermal cycling should be conducted in a vacuum if the test item is designed to operate in a vacuum. Technical Rationale: Thermal cycle modeling has shown that the general form of the thermal cycling test math model is given by Equation (1). [D]: Where: TE = Test Effectiveness F = Fraction of total failures that can be recipitated by a thermal cycle Pd = Probability of detection lO = Failure rate at TO N = Number of thermal cycles K = A constant DT = T - TO T = Operating temperature for l TO = Operating temperature for lO Fig. 1 shows that the failures available are the sum of three parts: Failures detected by thermal cycle tests Undetected failures Failures not precipitated [D] Figure 1: General Form of TC Test Model For single temperature range of 50oC, the test effectiveness equation reduces to Equation (2). [D] Figure 2 shows a plot of Equation (2) based on a probability of detection, Pd, of 0.9. The equation is based on values of lO and K that were found by solving two simultaneous equations. [D] Figure 2. Test Effectiveness Plot for lT = 50 oC Printed circuit boards (PCBs) are especially prone to solder joint cracking. The design is required to minimize the mechanical forces, as generated by thermal mismatch of materials or vibration, in the solder joints. References: GDCD BNZ 69-007, Curssell, G. M., Atlas and Centaur Component Acceptance Test Plan, 1984. NASA TMX-53731, Van Orden, R. E., Mounting of Components to Printed Wiring Boards, 1968. Laube, R. B., Space Vehicle Thermal Cycling Test Parameters, Proceeding of the Institute of Environmental Sciences, 1983. Nelson, C. E., System Level Reliability Thermal Cycling, Proceeding of the Institute of Environment Sciences, 1983. | This practice has been used on ATLAS, CENTAUR, Space Electronic Rocket Tests (SERTs) 1 and 2, Communication Technology Satellite (CTS), GOES, COBE, NOAA, LANDSAT, Solar Maximum Mission. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
789 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Subsystem Inheritance Review (SIR) | Preferred Practice for Design & Test. In the absence of inheritance review, one or more potential problems adversely impacting the system, subsystem, or project may not be identified in a timely manner. Conduct a formal design inheritance review at the system, subsystem, or assembly level prior to, or in conjunction with, the corresponding subsystem Preliminary Design Review (PDR). The purpose of the inheritance review is to identify those actions which will be required to establish the compatibility of the proposed inherited design, and any inherited hardware or software, with the subsystem functional and design requirements. | In the absence of inheritance review, one or more potential problems adversely impacting the system, subsystem, or project may not be identified in a timely manner. This oversight may later result in a condition having a significant adverse effect on quality, reliability, capability, schedule, or cost, accompanied by an increased risk of diminished performance or mission failure. | Conduct a formal design inheritance review at the system, subsystem, or assembly level prior to, or in conjunction with, the corresponding subsystem Preliminary Design Review (PDR). The purpose of the inheritance review is to identify those actions which will be required to establish the compatibility of the proposed inherited design, and any inherited hardware or software, with the subsystem functional and design requirements. | JPL | 01/28/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1262; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Use of inherited flight hardware or software may reduce cost and allow a spacecraft designer to avoid the risk of launching unproven equipment. However, the designer often lacks full information on the many design decisions made during development, including some which may cause incompatibility with current spacecraft requirements. Subsystem inheritance review (SIR) probes inheritance issues to help assure that the proposed inherited item will result in an acceptable and reliable product with minimal mission risk. The inheritance review evaluates the compatibility of the inherited or commercial-off-the-shelf (COTS) item with project requirements. It assesses potential risk associated with item use and the need for modification or additional testing. It is held at the earliest possible time prior to the equivalent level PDR. For complex and critical items or where the preponderance of the hardware or software is inherited, the SIR may replace a PDR or critical design review (CDR) for the inherited item. In other cases, discussion of inherited items can be included in another review-- typically, the preliminary requirements review or the PDR. For smaller projects or tasks, the inheritance review and the PDR may be combined into a single review to obtain the benefit at minimum expense. The higher the level of inherited item criticality, technical complexity, and technical risk, the more likely the inheritance review will be held at the subsystem level, or even the assembly level. Responsibilities: The responsible task manager identifies the need for a formal review and initiates the action by contacting the convening authority, usually the next higher management level. The convening authority, in consultation with the responsible task manager, appoints the review board and a chair, and defines the board charter and schedule. The review board, under the direction of the chair, conducts the review and prepares a written report to the responsible manager stating the findings and recommendations. The board may elect to use the JPL Recommendation for Action (RFA) form to document recommendations. All such recommendations are advisory only. The responsible manager prepares a written response to the convening authority addressing the disposition of the review board findings and recommendations for action. The convening authority reviews and approves these dispositions. Inheritance Review Agenda: The SIR agenda items to be addressed match the subsystem PDR agenda items. The PDR agenda is described in the NASA Preferred Reliability Practice, Preliminary Design Review, Practice No. PD-ED-1215.1. If an existing hardware, software, or design element is being inherited, then the subsystem CDR agenda items also need to be considered. The CDR agenda is described in the NASA Preferred Reliability Practice, Critical Design Review, Practice No. PD-ED-1215.3. In addition to these common review agenda items, the SIR may address the topics listed in Table 1. Selection of topics from this list should be tailored in accordance with product complexity and project needs. [D] SIR Tools: Typical tools which may be effective in support of a productive SIR include: Compliance Matrix. Typically, the specifications of an inherited design or configured item do not precisely match current requirements. A compliance matrix is a very useful SIR tool for matching the requirements of the inherited design against the requirements of the target subsystem. Each requirement line item in the current project is checked off against the corresponding inherited item requirement, permitting visual identification of requirement deltas. The product of this analysis is a proposed plan for achieving inherited item compliance with current requirements. Detailed Technical Review. Agenda items and issues which have a potentially significant impact on the cost, performance, and reliability of the inherited design or equipment merit special emphasis. A detailed technical review (DTR) of a single product may be held to make use of specialized expertise; it permits a more in-depth, detailed, technical review of the compatibility, simplicity, and testability of interfaces than is feasible at the SIR. The DTR is organized as an informal, but structured, mini-review held prior to the formal inheritance review to discuss significant issues such as: A comparison of the functional and design requirements for the inherited items with those for the current project, including single point failure policy (and any exceptions), design margins, operating life, and mission flight profile. Environmental design requirements, including margin requirements and their justification, and the associated qualification (or protoflight) and acceptance test requirements for the target application. Comparison of piece part standards for the current and prior projects. This issue must be addressed early in the inheritance review process in consideration of the long lead time for procurement of piece parts. Design assessment or reliability analyses, such as failure modes, effects, and criticality analyses (FMECAs), worst case analyses, and part stress analyses, including the method of determining and combining variables. Also of importance are the requirements for dispositioning analysis discrepancies, and the history of such activity on the prior project. Problem/failure history associated with the hardware or software during ground test and flight operations on the prior project, and the applicability of the problems/failures and their resolution to the requirements of the current project. SIR allows for an assessment of the proposed inherited design and, if applicable, the inherited hardware, software, or firmware by a group of knowledgeable persons not directly involved in the activity under review. A formal review can focus many years of experience on inheritance issues which may affect product reliability. Inheritance review aids the responsible manager in early identification of potential inheritance problems and in developing optimal solutions. References: JPL Standard Practice Instruction (SPI) 4-16-1. Guidelines for Planning and Conducting Formal Reviews, JPL D-10401 (Office of Engineering and Mission Assurance). quotTOPEX Modular Power Subsystem (MPS) Inheritance Review,quot Jet Propulsion Laboratory Memorandum 5131-87-636 (J. Quinn to E. Costogue), December 15, 1987. Preliminary Design Review, Reliability Preferred Practice No. PD-ED-1215.1. Critical Design Review, Reliability Preferred Practice No. PD-ED-1215.3. | This practice has been used on many JPL-managed projects, including Galileo, Magellan, and Mars Observer. In addition, the Topex/Poseidon project made extensive use of inherited items, and SIR was performed on all Topex/Poseidon subsystems | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
788 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Surface Charging/Electrostatic Discharge Analysis | Preferred Practice for Design & Test. Unpredictable operational anomalies and electronic parts failure could be caused by in-flight ESD events. The consequences could be catastrophic. Considering the natural environment, perform spacecraft charging analyses to determine that the energy that can be stored by each nonconductive surface is less than 3 mJ. Determine the feasibility of occurrence of electrostatic discharges (ESD). ESD should not be allowed to occur on surfaces near receivers/antenna operating at less than 8 GHz or on surfaces near sensitive circuits. For this practice to be effective, a test program to demonstrate the spacecraft's immunity to a 3 mJ ESD is required. | Unpredictable operational anomalies and electronic parts failure could be caused by in-flight ESD events. The consequences could be catastrophic. | Considering the natural environment, perform spacecraft charging analyses to determine that the energy that can be stored by each nonconductive surface is less than 3 mJ. Determine the feasibility of occurrence of electrostatic discharges (ESD). ESD should not be allowed to occur on surfaces near receivers/antenna operating at less than 8 GHz or on surfaces near sensitive circuits. For this practice to be effective, a test program to demonstrate the spacecraft's immunity to a 3 mJ ESD is required. | JPL | 01/29/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1301, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Surfaces that are conceivable electrostatic discharge (ESD) sources can be identified early in the program. Design changes such as application of a conductive coating and use of alternate materials can be implemented to eliminate or reduce the ESD risk. Preventive measures such as the installation of RC filters on sensitive circuits also can be implemented to control the adverse ESD effects. Use a validated computer code (NASCAP or other appropriate computer code) to determine the maximum differential charging (V) of each nonconductive surface. When differential charging occurs, an electric field is developed within the dielectric material. The magnitude of the electric field (E) is given by: E = V/d where d is the thickness of the dielectric material. Usually, when this electric field is greater than 2x105 V/cm, ESD is likely to occur. To determine the charging level, electrical properties of the nonconductive material must be known. These properties include (but are not limited to) surface resistivity, bulk resistivity, secondary and backscatter electron emission coefficient, and photoelectron yield. For materials with unknown electrical properties, the charging level must be determined by a ground test. In the ground test, the nonconductive surface is exposed to simulated charging environments (mission-dependent) and the resulting charging levels are measured. ESD must not be allowed to occur on surfaces near sensitive radio frequency (RF) receivers and on surfaces near sensitive circuits. For other surfaces, the energy of an ESD should be limited to 3 mJ. The ESD energy can be determined with the following equation: W = 1/2CV 2 where C is the capacitance of the nonconductive surface with respect to spacecraft ground. The value C depends on the geometry (area and thickness) of the nonconductive surface. The ESD energy as a function of capacitance and charging level is displayed in Figure 1. Usually, the best way to reduce the ESD energy is to limit the value of V. This usually implies the use of a more conductive material. Since the charging current available in the space environment is relatively low, material with resistivity of 109 Ohm-cm is considered adequate for effective charge control. [D] Figure 1: ESD Energy as a Function of Capacitance and Voltage In an environment of energetic electrons, spacecraft surface charging can occur. Due to their high resistivities, dielectric surfaces can be charged to different potentials than the metallic surfaces (which should be at spacecraft ground potential). When the electric field that results from differential charging is sufficiently high, an ESD would occur. ESD is an intense source of electromagnetic interference (EMI). The EMI energies that can be capacitively and inductively coupled to electronic circuits are proportional to both the magnitude and rate of increase (dI/dt) of the discharge current, respectively. Under most conditions, the discharge current (I) is directly related to the energy (W) of a discharge. By minimizing the ESD energy, the magnitude of discharge current and the magnitude of ESD-induced EMI on circuits can be reduced. The typical energy required to damage a sensitive IC is an order of several µJ. The energy required to upset a circuit is approximately 10 times less. In a typical discharge, only a fraction of the stored electrostatic energy can be coupled to a circuit. The coupling efficiency is dependent on the shielding and geometry of the spacecraft. Restricting the energy of an ESD minimizes the amount of energy available for IC damage and circuit upset, resulting in a more reliable spacecraft. In the Voyager ESD system test program, a 30 mJ discharge did not disturb spacecraft operation. However, differences in spacecraft configurations and circuit protection devices (e.g., RC filters in sensitive circuits) means that the quotsafequot (maximum allowable) energy could be different for different spacecraft configurations. Thus, 3 mJ was chosen as the maximum allowable energy. | This practice has been used on the Voyager and Galileo programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/17/2000
786 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Independent Review of Reliability Analyses | Preferred Practice for Design & Test. The absence of independent review of reliability analyses results in the very real possibility of not detecting a design defect. Establish a mandatory closed-loop system for detailed, independent, and timely technical reviews of all analyses performed in support of the reliability/design process. | The absence of independent review of reliability analyses results in the very real possibility of not detecting a design defect. The process rapidly degenerates if the design analyst feels that the analysis task is performed simply to satisfy a project milestone. The depth and accuracy of the analysis suffers, and because of the lack of feedback (positive or negative), there is no increase in technical competence. An independent review with no closed-loop correction system is of little value because experience has shown that condoned apathy will replace corrective action in many cases. Also, there will be no accurate technical and historical record of the design process to aid the troubleshooting required by test or mission failures; and there will be no inheritance record to forward with hardware that is used on more than one project. | Establish a mandatory closed-loop system for detailed, independent, and timely technical reviews of all analyses performed in support of the reliability/design process. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1302, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: This process of peer review serves to validate both the accuracy and the thoroughness of analyses. If performed in a timely fashion, it can correct design errors with minimal program impact. Technical Rationale: The creation of a well-functioning, highly reliable design requires the rigorous application of numerous design tools. Among these are Part Stress, Worst-Case Circuit Performance, Failure Modes and Effects and Criticality, Fault Trees, and Single Event Effects on Electronics. Each of these is a highly specialized field. The design or analysis engineer who performs these is usually the judge of the attributes to be examined and their exact depth of examination. The analyst also selects the analytical approach. All of these decisions are a function of the analyst's experience, wisdom, and perception of the program constraints and needs. For these reasons, it is very possible that omissions or inadvertent errors are occasionally made. Experience on the above noted programs as well as numerous other projects has shown that approximately 40 percent of all analyses contain significant shortcomings when they are performed for the first time. Approximately half of these are defects or omissions in the analysis alone and are not design defects. The remaining 20 percent actually represent design defects, the severity of which ranges from minor to mission catastrophic. Experience has shown that about 5 percent of all released manufacturing designs contain potential mission jeopardizing defects. The only proven method for detection of these defects is an independent review of the design details by an impartial, objective, competent peer in the appropriate technical field. To be effective this process should be a closed-loop system, which clearly identifies the design defect and enters it into a tracking system that requires resolution by either a design change or a program waiver. The process should also clearly differentiate between analysis omissions or defects and design deficiencies. Analysis deficiencies also should be tracked in a similar closed-loop system to assure timely updates, which may ferret out additional design deficiencies and will serve as an accurate historical record of the design. It is essential that the independent review process be based on purely technical grounds that avoid any connotation of being personal or punitive in nature. The reviewers should maintain an objective, constructive, and professional dialogue with the analysts to aid the resolution process. Experience on numerous projects has shown that this independent review process does work and the resultant quality of both the analyses and the designs is enhanced. | This practice has been used on the Viking, Voyager and Magellan programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/14/2000
785 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Assembly Acoustic Tests | Preferred Practice for Design & Test. Unless performed at the assembly level, the probability of failure during systems acoustic testing, or during flight due to the acoustic environment, is increased. Subject selected (large surface area, low mass) assemblies, in addition to the full-up flight system, to acoustic noise. It is imperative on missions with fixed launch windows that acoustic problems on assemblies not be deferred to system level tests. | The probability of failure during systems acoustic testing, or during flight due to the acoustic environment, is increased. | Subject selected (large surface area, low mass) assemblies, in addition to the full-up flight system, to acoustic noise. It is imperative on missions with fixed launch windows that acoustic problems on assemblies not be deferred to system level tests. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1407, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Acoustic noise tests subject potentially susceptible hardware to a significant launch environment, revealing design and workmanship inadequacies which might cause problems in flight. Implementation Method: Apply broadband random acoustic noise (~ 25 to 5000 Hz) to the test item in a reverberant chamber. Control the noise level in one-third octave frequency bands with microphones (generally four or more) distributed around the test item at least one foot from test item surfaces. Technical Rationale: Random-incidence, broadband, random acoustic noise is employed to simulate the effects of the launch acoustic environment. The noise generated by launch vehicle engine exhaust during liftoff and by boundary layer turbulence during transonic and high dynamic pressure events is indeed broadband and random in nature. The acoustic environment that a payload is exposed to within a launch vehicle shroud does tend to be reverberant (random-incidence) in nature. In fact, the reverberant acoustic noise test is one of the most realistic environmental tests employed for payloads. Acoustic noise external to a launch vehicle is not random-incident; however, the actual acoustic wave angle of incidence distribution is seldom known. In practice, employing a random-incidence acoustic test envelops the effects of the flight environment. Acoustic noise is usually the most severe dynamic environment for a launch vehicle or payload in the mid to high frequency range (~ 50 to 2000 Hz). The acoustic pressure fluctuations will induce severe vibrations in relatively large lightweight structures, such as solar panels and reflectors, potentially causing failures of the structure or attached electrical components. These structures should be acoustically tested at the assembly level to avoid potential cost and schedule impacts of a failure during system level testing. The full up spacecraft acoustic test provides verification of the integrated system for the vibroacoustic environment, including verification of the adequacy of assembly random vibration requirements. The acoustic test also qualifies spacecraft elements, such as blankets, cable harnesses, plumbing lines, and secondary structure not tested at the assembly level. | This practice has been used on the Mariner Series, Viking, Voyager and Galileo spacecraft. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/14/2000
746 | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN |  | Facilities, Mod & Rehab Projects |  | It becomes a logistics nightmare for a Project Manager to coordinate; locating free space, managing the moving process, telephone and computer drop relocations. The Project Manager can and does lose contact with the Mod/Rehab work. Some Mods & Rehabs have not had the proper cosmetic work and the offices and corridors present a shoddy, unfinished appearance. | Create the role of a Move Coordinator within the Project Team. When project requirements are being created, include specifications for any and all necessary cosmetic repairs to the facilities. | GRC | 01/01/2000 | During Mod & Rehab projects, typically people are moved out of the offices. This brings about two situations. First , extra workload on the Project Manager to coordinate the moves, i.e. finding temporary office areas, the moving of the furniture, relocation of telephone numbers and computer drops. This can be a full time task in itself. Since the people are out of the office it is the perfect time to paint the offices and corridors. This has previously been accomplished with continual maintenance funds. The reality of budget cuts has eliminated this type of effort. |  | N/A |  |  | Public | Not Specified |  | 04/14/2000
747 | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN |  | Facilities, Costing Of Contracts |  | Changes to a project can be very costly and project contingency can be used early on to rectify items that should have been costed as part of the contract. | Include all work in the bid package. Even if you think you will not be able to afford it, include it as an option or and additive to the package. | GRC | 02/28/2000 | The construction cost estimate for the project was equivalent to the project authority and as a result some work that was suspect of needing to be replaced was not included in the bid documents. The actual scenario was that electrical lighting was in the documents to be replaced in a Mod and Rehab project, however, the existing conduit and wire was planned to be reused. After the project was competitively bid, the actual contract price was less than the project authority. If the electrical work had been included as an option to the contract the cost would have be a more competitive price. The electrical work was not included in an option and as a result the change order to replace the conduit and wiring was an expensive change. |  | N/A |  |  | Public | Not Specified |  | 04/14/2000
748 | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN |  | Facilities, Sprinkler Heads |  | There must be written specifications for compaction of excavation sites to reduce the risk of the ground settling below grade. On site inspections of critical hardware must be preformed prior to installation and/or during the installation. | Review of the contracts to make sure all specifications are included no matter what the size of the scope of work. And if specific hardware is critical, than a sample of the actual hardware to be installed shall be part of the submittal package and so stated in the RFB. | GRC | 08/23/1999 | An excavation was done to facilitate the installation of a larger water line to service a buildings fire sprinkler system. Shortly after the excavation was filled a large sinkhole developed. During the installation of the sprinkler heads, it was noticed the heads installed were not the ones the in the requirements of the contract. |  | N/A |  |  | Public | Not Specified |  | 04/14/2000
787 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Acoustic Noise Requirement | Preferred Practice for Design & Test. In the absence of an acoustic noise requirement for spacecraft design and test, critical hardware that would likely survive other mission phases may fail when exposed to the mechanical stresses of launch. Since the primary vibroacoustic environment occurs at the very beginning of a mission, such failures are likely to have a greater mission impact than failures induced by other space environments over time. Impose an acoustic noise requirement on spacecraft hardware design to ensure the structural integrity of the vehicle and its components in the vibroacoustic launch environment. During the launch of a rocket, such noise is generated by the release of high velocity engine exhaust gases, by the resonant motion of internal engine components, and by the aerodynamic flow field associated with high speed vehicle movement through the atmosphere. This environment places severe stress on flight hardware and has been shown to severely impact subsystem reliability. | In the absence of an acoustic noise requirement for spacecraft design and test, critical hardware which would likely survive other mission phases may fail when exposed to the mechanical stresses of launch. Since the primary vibroacoustic environment occurs at the very beginning of a mission, such failures are likely to have a greater mission impact than failures induced by other space environments over time. | Impose an acoustic noise requirement on spacecraft hardware design to ensure the structural integrity of the vehicle and its components in the vibroacoustic launch environment. Acoustic noise results from the propagation of sound pressure waves through air or other media. During the launch of a rocket, such noise is generated by the release of high velocity engine exhaust gases, by the resonant motion of internal engine components, and by the aerodynamic flow field associated with high speed vehicle movement through the atmosphere. This environment places severe stress on flight hardware and has been shown to severely impact subsystem reliability. | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1259; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The fluctuating pressures associated with acoustic energy during launch can cause vibration of structural components over a broad frequency band, ranging from about 20 Hz to 10,000 Hz and above. Such high frequency vibration can lead to rapid structural fatigue. The acoustic noise requirement assures that flight hardware-- particularly structures with a high ratio of surface area to mass-- is designed with sufficient margin to withstand the launch environment. Definition of an aggressive acoustic noise specification is intended to mitigate the effects of the launch environment on spacecraft reliability. It would not apply to the Space Station nor to the normal operational environment of a spacecraft. Implementation Method: The failure modes produced by acoustic noise excitation are similar to those associated with other types of vibratory structural fatigue. These include failures due to excessive displacement, in which one deflecting component makes contact with another, as well as fractured structural members and loose fasteners. Broken solder joints and cracked circuit boards and wave guides can also occur. Electronic components whose function depends on the motion of structural parts, such as relays and pressure switches, are particularly susceptible. Large flat panels are most susceptible to damage by acoustic energy as they can undergo large displacements while oscillating at low frequency. For a typical spacecraft, this means that a fixed, high gain antenna must be carefully designed and stiffened to avoid bending failures, debonding of composite members, and related problems. In general, any structure with a high ratio of surface area to mass can be expected to experience potential problems in the acoustic noise environment of spacecraft launch. For small payloads, however, random vibration testing is commonly preferred over acoustic noise testing. A typical acoustic noise requirement is illustrated in Figure 1. [D] Figure 1: Typical Acoustic Noise Requirement Such a figure specifies the level of input sound pressure over the spectrum of frequencies at which the pressure can fluctuate. The pressure is expressed in units of decibels (dB), defined as [D] where P is measured in Pascals (Pa) and P ref is ostensibly the audible limit of the human ear, with a value defined as 2 x 10 -5 Pa. The decibel pressure levels in acoustic noise spectra are not generally provided at each and every frequency. Instead, they are often specified over bands of width D f, which span 1/3 of a frequency octave. With this method, 3 sound pressure levels will be provided over any interval in which the frequency doubles. Table 1 is an example of such a 1/3 octave band specification for the curve data of Figure 1. [D] Table 1: 1/3 Octave Band Specification When pressure levels are defined with these methods, it is convenient to provide a measure of the overall acoustic noise intensity. The overall sound pressure level (OASPL) provides just such a measure and, for 1/3 octave band specifications, can be calculated as the decibel equivalent of the root sum square (RSS) pressure. Table 2 illustrates such a calculation for the data of Table 1, and shows that the OASPL is 144.9 dB. It should be noted that this figure is greater than any individual sound pressure level in the specification, because it represents an intensity of the spectrum as a whole. [D] Table 2: Calculation of Overall Sound Pressure Level To quantify the acoustic environment during launch, launch vehicles are often instrumented with internal microphones, which measure noise levels within the rocket fairing. This data is telemetered to the ground for processing and ultimately plotted in the form of a sound pressure level versus frequency spectrum. Since the acoustic forcing function is stochastic, depending on many atmospheric and other variables, data from a number of such flights are generally gathered, and an envelope, such as that of Figure 1, is developed to encompass the historical record of microphone data. This process can be extended and applied to data from a number of launch vehicles. If a launch platform has not yet been manifested for a particular payload, acoustic profiles from a number of candidate rockets can be enveloped, producing an aggressive specification which will ensure design adequacy for the spacecraft. Figure 2 reflects such a process, providing an envelope which encompasses the acoustic environments from three launch vehicles. [D] Figure 2: Envelope of Acoustic Flight Data Technical Rationale: The rationale for acoustic noise testing is straightforward, as acoustic energy is the primary source of vibration input to a space launch vehicle. During the initial phases of a rocket launch, high velocity gases are ejected from motor nozzles and reflected from the ground, creating turbulence in the surrounding air and inducing a vibratory response of the rocket structure. During the subsequent ascent phase of a launch, as the vehicle accelerates through the atmosphere to high velocity, aerodynamic turbulence induces pressure fluctuations which again cause structural vibration. These pressure fluctuations increase in severity as the vehicle approaches and passes through the speed of sound, due to the development and instability of local shock waves. The high-level acoustic noise environment continues during supersonic flight, generally until the maximum dynamic pressure or quotmax Qquot condition is reached. Acoustic energy is transmitted to the mission payload in two ways. First, fluctuating pressures within the payload fairing impinge directly on exposed spacecraft surfaces, inducing vibration in high gain antennae, solar panels and other components having a large ratio of area-to-mass. Secondarily, the fluctuating external pressure field causes an oscillatory response of the rocket structure, which is ultimately transmitted through the spacecraft attachment ring in the form of random vibration. From the spacecraft perspective, this random input is generally lowest at the launch vehicle attachment plane, and increases upward along the payload axis. At the integrated spacecraft level, then, acoustic noise is a primary source of vibration excitation. It is a ìreal worldî environment, should be reflected in spacecraft design requirements, and should be included in virtually any space vehicle test program. These requirements relate specifically to the launch environment and do not apply to the normal operational environment of a spacecraft. References: MIL-STD-1540C, Test Requirements for Launch, Upper-Stage and Space Vehicles, United States Air Force Military Standard, 1994. Steinberg, D. S., Vibration Analysis for Electronic Equipment, New York: John Wiley & Sons, 1986. Himelblau, H., Fuller, C. and Scharton, T., quotAssessment of Space Vehicle Aeroacoustic Vibration Prediction, Design and Testing,quot NASA CR-1596, July, 1970. NASA STD XXXX-94, Standard for Payload Vibroacoustic Test Criteria, National Aeronautics and Space Administration, 1994 (Unreleased). Combination Methods for Deriving Structural Design Loads Considering Vibro-Acoustic, etc., Responses, Reliability Preferred Practice No. PD-ED-1211. Powered-On Vibration, Reliability Preferred Practice No. PT-TE-1405. Sinusoidal Vibration, Reliability Preferred Practice No. PT-TE-1406. Assembly Acoustic Tests, Reliability Preferred Practice No. PT-TE-1407. Environmental Test Sequencing, Reliability Preferred Practice No. PT-TE-1412. Random Vibration Testing, Reliability Preferred Practice No. PT-TE-1413. Vibroacoustic Qualification Testing of Payloads, Subsystems, and Components, Reliability Preferred Practice No. PT-TE-1419 | This practice has been used on Voyager and all subsequent JPL flight projects. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/14/2000
749 | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN | Morris, Joe - 0000000000 : NO@ADDRESS.GIVEN |  | Facilities, Mod/Rehab Projects, Construction Mtgs. |  | It is hard to get complete attendance at the weekly construction meetings. | In the specification section 01200 Project Meetings, specifically require attendance of the weekly construction meetings by the Contractor's job superintendent. | GRC | 08/23/1999 | Building Rehab projects are typically done on the second shift (4:00 p.m.-12:00 a.m.) and construction meetings are held every week to discuss the progress of the job. These meeting times and dates are left up to the participants to determine. The contract requires the meeting, but does not dictate a specific time. The Contractor's job superintendent doesn't start work until 4:00 p.m. and when construction meetings start at 3:00 p.m. some valuable input from the field is missing. The Contractor's Project Manager is always in attendance, however the field representation is also required. If the meetings were moved until 4:00 p.m., many of the Government's representatives would not be in attendance due to their work schedule. |  | N/A |  |  | Public | Not Specified |  | 04/14/2000
780 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Pyrotechnic Shock Testing | Preferred Practice for Design & Test. Non-practice poses a higher risk of flight failure, particularly for small components near the explosive source. Subject potentially sensitive flight assemblies that contain electronic equipment or mechanical devices, as well as entire flight systems, to pyrotechnic shock (pyroshock) as part of a development, acceptance, protoflight, or qualification test program. Perform visual inspection and functional verification testing before and after each pyroshock exposure. Where feasible, perform assembly-level and system-level pyroshock tests with the test article powered and operational to better detect intermittent failures. | Nonpractice poses a higher risk of flight failure, particularly for small components near the explosive source. | Subject potentially sensitive flight assemblies that contain electronic equipment or mechanical devices, as well as entire flight systems, to pyrotechnic shock (pyroshock) as part of a development, acceptance, protoflight, or qualification test program. Perform visual inspection and functional verification testing before and after each pyroshock exposure. Where feasible, perform assembly-level and system-level pyroshock tests with the test article powered and operational to better detect intermittent failures. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1408A, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Early assembly-level pyroshock testing can often reduce the impacts of design and manufacturing/assembly deficiencies upon program cost and schedule prior to system-level test. Such testing can provide a test margin over flight pyroshock conditions which cannot be achieved in system testing. Conversely, system-level shock testing can be used to verify system performance under pyroshock exposure, thus providing increased confidence in mission success and verifying the adequacy of the assembly-level tests. Implementation Method: Pyroshock testing of assemblies may be achieved by using one of the following types of sources: An explosive device [Ref. 1,2], Impact of one structural member (e.g., a hammer) upon another (e.g., a beam, plate, shell, or combinations thereof) [Ref. 2-5], or A vibration exciter or shaker programmed to generate short duration transient motion [Ref. 2,3,6,7]. JPL has historically used a shaker, or a beam or plate excited by an explosive device or by hammer-type impact. The test magnitude should include a margin over maximum predicted flight conditions, which at JPL is commonly selected to be equal to 1.5 times the maximum expected flight environment over a frequency range anticipated to encompass the critical resonant frequencies of the test article. This test condition is monitored by accelerometers located at the facility/test article interface. Usually three shocks are specified for qualification testing, or one shock for protoflight, in each of three orthogonal directions. In most cases, the test article is electrically powered and operational, even when no power is to be applied to the hardware during the flight event. For system-level acceptance testing, the actual pyrotechnic or explosive device(s) are commonly used, with multiple firings (three at JPL) of the devices that generate the dominant shock environment(s) applied to account for firing-to-firing variations. Power-on testing is normally utilized, with the operational mode applicable to the flight pyro event monitored. Pyroshock tests nearly always utilize instrumentation for the purpose of environmental evaluation or test control. Pyroshock measurements are normally made with accelerometers despite some potentially serious deficiencies. Often in the near-field (within 6 in. or 15 cm) and sometimes in the mid-field (within 2 ft or 60 cm) of the source, improperly selected accelerometers may break, hard-bottom, or saturate under pyroshock loading, or incorrectly-set signal conditioners may saturate if accelerometer resonances are sufficiently excited [Ref. 8-10]. Such nonlinear responses will usually make the resulting data invalid over the entire spectrum. Once valid signals are acquired, routine data analysis is performed to provide the desired acceleration time histories and shock response spectrum (SRS) [Ref. 11]. The SRS is utilized with natural frequencies usually selected to correspond to either 1/3 or 1/6 octave band center frequencies and a constant quality factor selected as Q=10. Assembly-level test control is usually specified to match the desired SRS, with additional limits placed on total shock duration. With impacting and explosive shock simulation, this SRS matching is usually performed iteratively with a dynamically similar model. With shaker shock simulation, the SRS matching is performed automatically at low levels, checked at intermediate levels, and then applied at full level. Pyrotechnic shock or pyroshock is the transient motion of structural elements, assemblies, subsystems, or systems due to explosive loading induced by the detonation of ordnance devices incorporated into or attached to the structure. Pyroshock is often characterized by its high peak acceleration (300 g- to 300 kg), high frequency content (100 Hz to 1 MHZ) and short duration (10 µsec to 20 msec), which is largely dependent on the source type and strength, structural type and configuration, and especially the distance from the source to the response point of interest. For aerospace applications, explosive devices are generally used to separate structural subsystems (e.g., payloads from launch vehicles), deploy appendages (e.g., solar panels), or activate on-board operational subsystems (e.g., propellant valves) [Ref. 1,2]. In certain cases, the explosive loading may be accompanied by the release of stored energy due to structural preload. Current spacecraft design often utilizes numerous explosive devices over the course of a mission. JPL has historically utilized most of the available pyrotechnic or explosive devices, which can be divided into two general categories: point sources and line sources. Point sources include explosive bolts, separation nuts, pin pullers and pushers, bolt and cable cutters, and certain combinations of point sources and operational hardware (e.g., pyrovalves). Line sources include flexible linear shaped charges (FLSCs), mild detonating fuses (MDFs), primer cords, and certain commercially-available products intended to capture explosive and structural debris after separation (e.g., Super-ZipTM). Point and line sources have also been combined: V-band (Marmon) clamps use point explosive sources which may then allow the rapid release of stored strain energy from a structural preload acting along a line of contact between the two structures being separated. Because of the high frequency content, many small elements resistant to random vibration are susceptible to pyroshock induced failure. Numerous flight equipment failures have been attributed to pyroshock exposure, some resulting in catastrophic mission loss [Ref. 12-13]. Particular examples of pyroshock induced failures include cracks and fracture in crystals, ceramics, epoxies, glass envelopes, solder joints and wire leads, seal failure, migration of contaminating particles, relay and switch chatter and transfer, and deformation of very small lightweight structural elements. On the other hand, deformation or failure of major structural elements is rare except in those regions close to the source where structural failure is intended. If feasible, assembly-level pyroshock testing should be performed with the test article powered and operational, even when no power is to be applied to the hardware during the flight event, to improve the detection of intermittent failures which might not otherwise be detected until much later in the test program or in flight. Certain hardware can be expected to malfunction during pyroshock exposure but will resume operation within tolerance after the event. Analytical methods and computational procedures have historically been inapplicable to pyroshock prediction. Thus, pyroshock is considered to be an experimental art [Ref. 4,5,7]. References: Kalbfleisch, K.C., "Review of Pyro-Shock Generating Devices and Source Levels", IES Pyrotechnic Shock Tutorial Program, 31st ATM, Institute of Environmental Sciences, Apr.-May 1985. Powers, D.R., "Pyro Shock Test Simulation Methods", IES Pyrotechnic Shock Tutorial Program, 31st ATM, Institute of Environmental Sciences, April-May 1985. Powers, D.R., "Summary of Testing Techniques", Shock and Vibration Bulletin, No. 56, Pt. 3, pp 135-142, August 1986. Davie, N.T., and Bateman, V.I., "Pyroshock Testing", Shock and Vibration Handbook (C.M. Harris, Ed.), 4th ed., Ch. 26, Pt II, McGraw-Hill, NY, 1996 Bateman, V.I., and Davie, N.T., "Recommended Practice for Pyroschock", Proceedings of the 41st ATM, Institute of Environmental Sciences, pp 208-216, April-May 1995. Luhrs, H.N., "Equipment Sensitivity to Pyrotechnic Shock", Proceedings of the 22nd ATM, Institute of Environmental Sciences, pp 3-4, April 1976. Zimmerman, R.M., "Pyroshock Bibliography", Proc. 39th ATM, Institute of Environmental Sciences, Vol.2, pp 471-479, May 1993. Himelblau, H., Piersol, A.G., Wise, J.H., and Grundvig, M.R., "Handbook for Dynamic Data Acquisition and Analysis", IES-RP-DTE012.1, App. A, Institute of Environmental Sciences, Mt. Prospect, IL, March 1994. Piersol, A.G., "Recommendations for the Acquisition and Analysis of Pryoshock Data", Sound and Vibration, Vol. 26, No.4, pp 18-21, April 1992 Piersol, A.G., "Pyroshock Recommendations in Proposed MIL-HDBK on Guidelines for Dynamic Data Acquisition and Analysis", Journal of the Institute of Environmental Sciences, Vol. XXXV, No. 5, pp21-26, Sept-Oct. 1992. Ref. 8, Sec. 5. Moening, C.J., "Pryotechnic Shock Flight Failures", IES Pryotechnic Shock Tutorial Program, 31st ATM, Institute of Environmental Sciences, April-May 1985. Moening, C.J., "Views of the World of Pyrotechnic Shock", Shock and Vibration Bulletin, No. 56, Pt. 3, pp 3-28, August 1986. "Powered-On Vibration," Reliability Preferred Practice No. PT-TE-1405. | This practice has been used on the Mariner series, Viking, Voyager, Galileo and Magellan spacecraft. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/14/2000
782 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Part Electrical Stress Analysis | Preferred Practice for Design & Test. The failure to perform part stress analysis likely will result in several overstressed parts in the design. These will become the life limiting items of the design and produce unacceptably short-lived hardware. If the analysis is performed at nominal temperature and operating points, without derating, or without a detailed thermal analysis, there will be no margin for contingencies and the nominal life expectancy also will be degraded. Every part in an electrical design is subjected to a worst-case part stress analysis performed at the anticipated part temperature experienced during the assembly qualification test (typically 75 degrees C). Every part must meet the project stress derating requirements or be accepted by a formal project waiver. | The failure to perform part stress analysis likely will result in several overstressed parts in the design. These will become the life limiting items of the design and produce unacceptably short-lived hardware. If the analysis is performed at nominal temperature and operating points, without derating, or without a detailed thermal analysis, there will be no margin for contingencies and the nominal life expectancy also will be degraded. | Every part in an electrical design is subjected to a worst-case part stress analysis performed at the anticipated part temperature experienced during the assembly qualification test (typically 75 degrees C). Every part must meet the project stress derating requirements or be accepted by a formal project waiver. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-AP-1303, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Part failure rates are proportional to their applied electrical and thermal stresses. By predicting the stress through analysis, and applying conservative stresses, the probability of mission success can be greatly enhanced. Electrical circuits are analyzed to determine the maximum stress on each part when all applied voltages or currents are maximized and when all variations of other parts in the circuit are set to that combination of minimum and maximum values that produce worst-case maximum stress. This requires a new choice of "other" part combinations in the circuit each time the stress on a new part is determined. The stresses are aggravated by imposing maximum operating temperature when comparing the part stress to its required derating. The initial analysis usually is made without benefit of a detailed part level thermal analysis; therefore, a conservative temperature assumption is made. Highly stressed parts are identified for possible replacement with more robust parts or for possible circuit changes. The final design is confirmed by analysis, with part temperatures based on a part level thermal analysis, and with voltages and currents derived from either specification limits or the results of worst-case circuit analysis. Numerous life tests have been performed on electrical parts that establish the relationship of part life to applied stresses. There is a very strong dependence. The life expectancy typically can be doubled or tripled by operating at half the manufacturers full rated (100 percent) stresses, which typically are commensurate with a 10,000-hour life expectancy. Complex, multiple year missions must achieve very low part failure rates to achieve mission goals; therefore, operation at derated conditions is mandatory. Although typical reliability predictions are based on nominal stresses, circuit nonlinearities and part and voltage variations can cause large operating point variations. Therefore, it is essential that the conservative approach of using worst-case stresses be implemented as standard practice. Although average temperatures during a mission may be nominal, typical qualification test philosophy results in test temperatures that stress the design to assure margin against possible flight contingencies (typically 75 degrees C). It is essential that negligible aging of the parts be introduced during protoflight testing to assure mission reserve life. For this reason, it is prudent to show that the deratings are met while operating in the worst qualification or protoflight test environment. Historical evidence has shown that significant (>40 degree C) temperature rises can exist between the thermal mounting surface of an assembly and the part body if good thermal design of the assembly is not rigorously pursued. For this reason, the results of a part level detailed thermal analysis must be an input to the part stress analysis. In summary, the stress derating requirements of every part at worst-case circuit conditions and contingency temperatures must be met. This will ensure a design that will function with a high degree of confidence at these extremes. It also will force a conservative thermal design (small temperature rises), which will produce even greater mission life margins under the expected nominal flight conditions. References Part Junction Temperature, Reliability Preferred Practice No. PD-ED-1204. | This practice has been used on the Voyager, Magellan and Galileo programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/14/2000
781 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Thermal-Vacuum Versus Thermal-Atmospheric Tests of Electronic Assemblies | Preferred Practice for Design & Test. Performing an atmospheric pressure thermal (T/A) test in lieu of thermal/vacuum (T/V) test reduces the hot temperature margin, screening strength, and test demonstrated reliability. Hot temperature margins can be compromised to the point where there is a zero or negative margin between environmental test levels and the allowable flight level (e.g., a test with only a planned 10 deg C margin and a T/A reduction effect of 15 to 20 deg C would result in a negative test margin). Screening strengths can be reduced by factors of 2 to 4 or more. Test demonstrated reliability can be reduced by factors of 2 to 10 or more. Perform all thermal environmental tests on electronic spaceflight hardware in a flight-like thermal vacuum environment (i.e., do not substitute an atmospheric pressure thermal test for the thermal/vacuum test). Moreover, if a compromise is thought to be necessary for non-technical reasons, then an analysis is required to quantify the reduction in test demonstrated reliability. | Performing an atmospheric pressure thermal (T/A) test in lieu of thermal/vacuum (T/V) test reduces the hot temperature margin, screening strength, and test demonstrated reliability. Hot temperature margins can be compromised to the point where there is a zero or negative margin between environmental test levels and the allowable flight level (e.g., a test with only a planned 10 deg C margin and a T/A reduction effect of 15 to 20 deg C would result in a negative test margin). Screening strengths can be reduced by factors of 2 to 4 or more. Test demonstrated reliability can be reduced by factors of 2 to 10 or more. | Perform all thermal environmental tests on electronic spaceflight hardware in a flight-like thermal vacuum environment (i.e., do not substitute an atmospheric pressure thermal test for the thermal/vacuum test). Moreover, if a compromise is thought to be necessary for nontechnical reasons, then an analysis is required to quantify the reduction in test demonstrated reliability. | JPL | 01/28/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1409, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Assembly-level thermal vacuum testing is the most perceptive test for uncovering design deficiencies and workmanship flaws in spaceflight hardware. The margin beyond flight conditions is demonstrated, as is reliability. However, substituting an atmospheric pressure thermal test for the thermal/vacuum test can effectively reduce electronic piece part temperatures by 20 deg. C or more, even for low power density designs. The net result of this is that the effective test temperatures may be reduced to the point where there is zero or negative margin over the flight thermal environment. Implementation Method: Establish a policy for spaceflight electronic hardware that requires all assembly-level thermal testing to be performed in a thermal/vacuum environment. Moreover, deviation from this policy should require a waiver, supported by quantitative analysis that considers the effect on test demonstrated reliability. Technical Rationale: Vacuum effects: A thermal/vacuum (T/V) test simulates the flight condition. Two different physical phenomena occur when a thermal/atmospheric pressure (T/A) test is performed in lieu of a T/V test. They are quotpure vacuumquot effects and temperature level/gradient effects. The quotpure vacuumquot phenomena include corona and multipacting. Corona is of concern in the pressure region from about 0.1 to 0.001 torr. Multipacting can occur starting from the middle of the corona region all the way to near hard vacuum conditions. Pure vacuum problems most often are associated with radio frequency (RF) or high voltage circuits and devices. The addition of an ambient pressure gas alters key temperature levels and gradients. For a unit that is designed to be conductively coupled to the spacecraft structure (shear plate), the prime thermal path from the piece parts to the shear plate is via the boards and the housing. The introduction of a gas into the quotsimulatedquot flight environment results in two significant thermal alterations. First, the dominant thermal paths from key elements of the assembly (piece parts and solder joints, etc.) are altered because the gas creates a parallel path from these elements to the chamber ambient via the total housing skin. Secondly, artificial parallel paths between the key elements to the flight heat sinking surface are added. These additional parallel paths short out any of the high thermal resistance paths that may be present in the design. The net result of this is a reduction in the temperature of the key elements at both test temperature extremes. This test temperature reduction is referred to as the DT effect. A reduction in gradients between circuit elements also occurs, which can lead to circuit performance that is not typical of flight. For example, a timing circuit may show adequate performance due to the reduced gradients, whereas the performance in a flight-like vacuum condition could be unacceptable. JPL Study Results: Analyses and testing have been specifically performed at JPL since 1985 to quantify the effects of performing T/A testing in lieu of T/V testing. The results of these efforts are summarized in Table 1. Performing T/A testing in lieu of T/V testing reduces the temperature rise from the thermal control surface to key elements (boards, solder joints, parts, etc.) internal to the assembly. Note that this effect reduces the operating temperatures of the key elements over the whole temperature range (i.e., hot testing becomes less severe, while quotcoldquot testing becomes colder). Reductions in the temperature rises can be on the order of 15 deg C to 20 deg C or more. Commonly, T/A testing reduces temperature rises by a factor of 2 to 4. Table 1: Summary of Analysis and Test Results for the DT Effect Associated with Performing T/A Testing in Lieu of T/V Testing [D] Notes: Unit not blanketed during initial T/V test. Estimates for the effect of this indicated that the load on the heat exchanger was approximately twice that dissipated by the unit. Test performed for the DT effect part case-to-housing. Full DT effect shown is a combination of test and analysis. Such reductions lead to margin demonstrations dramatically lower than desired, and can easily cause negative test margin demonstrations. An electronic assembly is manufactured by a series of chemical and mechanical processes. Design and workmanship failures related to the chemical processes are best described by the Arrhenius reaction rate equation. Mechanical design and workmanship failures are most often a result of thermal fatigue and, to a lesser degree, vibration. Both the chemical and thermal fatigue failure mechanisms are a function of temperature. Tables 2 and 3 quantify the temperature influence on these failure mechanisms. Table 2: Arrhenius Reaction Rate Reduction Factors for Various DT Effects and Activation Energies [D] *Assuming a 75 deg C shear plate plus a 35 deg C rise shear plate-to-part junction. Lower test levels lead to greater reduction ratios. Table 3: Screening Strength Reduction Factor (quotXquot Factors) for Various DT Effects and Shear Plate Temperatures [D] *For compliant solder joints and cold test temperatures above the glass transition temperature for all materials involved. Also presented in Table 1 are various rationales generally in use in industry today for choosing a T/A test in lieu of a T/V test. The most common of these rationales are either based on the power density of the unit or type of hardware (i.e. power supply, digital, RF, etc.) undergoing testing. The JPL study results clearly show that these two rationales are not valid. The current rationale in use at JPL today is that if analysis shows that the DT effect is less than 5 deg C on all piece parts, solder joints, etc., and there are no known pure vacuum effects, then performing a T/A test in lieu of a T/V test might be allowed depending of the criticality of the unit under test. The safest and simplest course of action is to T/V test everything. References: 1. Mark Gibbel, quotThermal/Vacuum Versus Thermal Atmospheric Testing of Space Flight Electronic Assemblies,quot NASA Conference Publication 3096, from the 16th Space Simulation conference, Albuquerque, New Mexico, November 5-8, 1990. quotPart Electrical Stress Analysis,quot Reliability Preferred Practice PD-AP-1303. quotEnvironmental Factors,quot Reliability Preferred Practice PT-EC-1101. quotThermal Analysis of Electronic Assemblies to the Piece Part Level,quot Reliability Preferred Practice PD-AP-1306. | This practice has been used on the Ranger, Mariners, Viking, Voyage and Magellen spacecraft. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/14/2000
783 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Thermal Test Levels & Durations | Preferred Practice for Design & Test. Demonstrated design adequacy and its implications to long-term reliability are affected. For example, testing at 50°C instead of 75°C and for about 20 hours instead of 144 hours reduces a test's demonstrated reliability by a factor on the order of 50. Perform thermal dwell test on protoflight hardware over the temperature range of +75°C/-20°C (applied at the thermal control/mounting surface or shearplate) for 24 hours at the cold end and 144 to 288 hours at the hot end. Note: Thermal dwell testing is the standard practice at JPL for systems and components that do not thermally cycle during flight. For systems and components that do thermally cycle (generally over a range > 20°C) in flight, the JPL practice is to cycle over a conservative range for three times the number of flight cycles. | Demonstrated design adequacy and its implications to long term reliability are affected. For example, testing at 50°C instead of 75°C and for about 20 hours instead of 144 hours reduces test demonstrated reliability by a factor on the order of 50. | Perform thermal dwell test on protoflight hardware over the temperature range of +75°C/-20°C (applied at the thermal control/mounting surface or shearplate) for 24 hours at the cold end and 144 to 288 hours at the hot end. Note: Thermal dwell testing is the standard practice at JPL for systems and components which do not thermally cycle during flight. For systems and components that do thermally cycle (generally over a range > 20°C) in flight, the JPL practice is to cycle over a conservative range for three times the number of flight cycles. | JPL | 01/30/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1404, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. This test, coupled with rigorous design practices, provides high confidence that the hardware design is not marginal during its intended long life high reliability mission. Establish a minimum hardware test temperature level range of -20°C / +75°C and specify that a single cycle thermal dwell test be performed for the appropriate durations (24 hours cold and 144 to 288 hours hot). In the early 1960s, JPL adopted a conservative set of thermal design and test temperature levels to demonstrate hardware design adequacy. As a starting point, a reasonable short term flight temperature excursion (+5°C to +50°C) was established for thermal control surfaces (shearplates). The +5°C lower level is a few degrees Celsius above the freezing point of hydrazine, thus integrated thermal control of bus electronics and propulsion systems is possible. The 50°C upper limit is the approximate level reached by a louvered bus electronics bay after about one hour of full (perpendicular) solar irradiance at one A.U. (astronomical unit) and accommodates near earth maneuvers. The long term desired thermal control range is typically 25±5°C, but this range may be broader depending on the tradeoffs of long term reliability and thermal control costs. This original approach reduced the overall complexity of the system thermal control design process: the wide range reduced the sensitivity to louver/radiator size, heater size, power variations, etc. A margin of ±25°C was then applied to the allowable flight range for qualification and protoflight test levels of assemblies mounted to such thermal control surfaces. These levels accommodate thermal compromises in the design where the short term extremes may be approached during steady state operation; they also have been demonstrated to provide an effective screen of assemblies. This resulted in the JPL standard minimum test range of -20°C to +75°C (for electronic assemblies in particular). These conservative test level ranges lead to several desirable features. The conservative high temperature limit restricts the permitted temperature rise from the shearplate to the junction of electronic piece parts. Thus junction temperatures during the bulk of a mission are much cooler than assemblies designed and tested at lower shearplate temperatures. The increase in theoretical reliability is on the order of a factor of 10 per 25°C. (refer to quotPart junction Temperaturequot, Reliability Preferred Practice No. PD-ED-1204) There are at least two failure mechanisms for both design and workmanship that should be screened by an adequate thermal environmental test of any given assembly. The first is based on Arrhenius rate related physics where time at high temperature is the key to demonstrating reliability during testing. Electronic part life is a prime example of an Arrhenius mechanism, but so are other elements of assemblies including interactions between metal traces within printed wiring boards (PWB's), certain component to board joints, and even solder joints to a certain extent. The other identifiable mechanism is thermally induced mechanical stress (including fatigue) as between components and the board and especially solder joints. Arrhenius Rate Physics: Contrast the test level of 75°C (shearplate) to 50°C short term worst case transients during flight and 25°C for the bulk of the mission. Based on Arrhenius reaction rate physics described in the following figures, the 75°C test provides a demonstrated reliability some 2 to 8 times that of short transients to 50°C, (typical of thermal cycling tests), and some 4 to 94 times that of long term mission shearplate temperatures (25°C). These reliability ratios are based on activation energies of 0.3 eV to 1.0 eV which cover most assembly element reaction physics. [D] [D] The Mariner and Viking spacecraft performed a hot dwell test (75°C) of 288 hours duration. This was reduced to 144 hours for the Voyager and Galileo spacecraft. The statistical database supporting this shorter test is unique to the JPL design rules and processes; therefore, the longer hot dwell duration of 288 hours is recommended for assemblies designed to non-equivalent or less conservative practices. The following figure shows the percentage of the screening test capability for Class S parts that is used by a JPL assembly test at 75°C for 144 hours. A very conservative assumption here is that all parts in the assembly test have a 35°C temperature rise and that they are at 110°C for the entire test. Even given this over-conservative assumption, the JPL test uses only 0.018% of the class S parts minimum screened capability. Clearly less than 2/10000's of the minimum parts capability being dedicated to the assembly protoflight test is not a concern. The parts are not over-stressed by this test. [D] Thermally Induced Mechanical Stress (Fatigue): JPL has historically done a thermal dwell test rather than a specific thermal cycle test. There are data that indicate thermal cycling uses up hardware life and therefore is degrading to the flight hardware. In practice, the JPL test approach is never really just a one-cycle dwell test. The assembly test program (plus any retest) and the systems test program (frequently two phases) result in a minimum of two cycles and as many as four (or more) are possible although they are not continuous and the transients are controlled to < 30°C/hr to prevent thermal shock. The Voyager hardware was tested as follows: [D] In a recent JPL study, a fatigue life relationship of equivalent thermal cycles was determined over different temperature ranges as follows: [D] where: C 1 is the number of thermal cycles over a T 1 range C 2 is the number of thermal cycles over a T 2 range and Y = 2.6 for eutectic solder. As a frame of comparison for workmanship purposes, the JPL protoflight test of 1 cycle over -20/75°C range can be correlated to an acceptance test of 6 cycles over a 0/50°C range. In this case: C1 = 1, T1 = 95°C, C2 = TBD, T2 = 50°C and the equivalent cycles of the JPL test are: C2 = 1(95°C/50°C)2.6 = 5.3 cycles. Therefore, in terms of solder joint fatigue life, the JPL protoflight test equivalency to 5.3 cycles over a 50°C range says that, for workmanship acceptance purposes, the JPL protoflight test is essentially the same as the example thermal cycle acceptance test, i.e., 5.3 equals approximately 6 cycles. The following figure provides comparison of solder joint fatigue life. The recommended -20/+75°C single cycle dwell test uses only 0.14% of the fatigue life of a solder joint qualified to NHB 5300.4 (3A-1). The point of this comparison is that the JPL protoflight test is less strenuous to solder joints than thermal cycle testing performed by most organizations. [D] Ground Test & Thermally Related Problem/Failure Statistics: These practices were applied to the Mariner spacecraft series, the two Viking 75 spacecraft, the two Voyager 77 spacecraft, and more recently Galileo. These spacecraft all completed (or exceeded) their intended mission successfully (the Galileo mission is still underway at the time of this edition). In fact, the Voyager spacecraft have worked for over 13 years. The total number of assembly problems/failures during these missions is small, and the number of thermally induced problems even smaller. This is shown in the following table where the number of problem/failures identified during assembly level thermal testing are compared with suspected flight problems/failures for the Viking, Voyager, and Galileo programs: [D] | This practice has been used on the Voyager, Galileo, Viking and Mariner Series programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/14/2000
784 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Powered-On Vibration | Preferred Practice for Design & Test. A failure to conduct powered-on vibration test may increase the risk of flight equipment containing flaws or intermittencies, such as electrical arcing, open circuits, and relay chatter, that may cause mission compromises or hardware failures. Supply power to electronic assemblies during vibration, acoustics, and pyroshock, and monitor the electrical functions continuously while the excitation is applied. | A failure to conduct powered-on vibration test may increase the risk of flight equipment containing flaws or intermittencies, such as electrical arcing, open circuits, and relay chatter, that may cause mission compromises or hardware failures. | Supply power to electronic assemblies during vibration, acoustics, and pyroshock and monitor the electrical functions continuously while the excitation is applied. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1405, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Aids in the detection of intermittent or incipient failures in electronic circuitry not otherwise found. This reliability practice benefits even those electronics not powered during launch. Apply service power to electronics assemblies. Monitor as many circuits as possible for intermittent behavior or change in voltage/current level. Record for later analysis the most critical electrical functions. Employ instrumentation such as a storage logic analyzer to monitor relay contacts, especially during pyroshock testing. The NASA and industry practice of powering electronic assemblies during dynamics testing has proven to be effective in uncovering otherwise undetected "soft" failures. Studies by the Institute of Environmental Sciences, the U.S. military, Tustin Technological Institute, Hobbes Engineering, and others have all arrived at the same general conclusion: power-on vibration is a valuable tool for exposing latent defects in electronic hardware with the eventual resultant improvement in product quality. Intermittencies in electronic circuitry can often be detected during vibration but may not be observed under ambient functional testing. These intermittencies may not reappear until after launch, where they sometimes degenerate into hard failures. Examples of these intermittencies include: Component shorts due to internal conductive particles, Loose or contaminated connectors, Fractured component-to-board solder joints, Electrical arcing, Data number changes in digital equipment, and Relay transfer or chatter. Powering of electronic equipment during vibration allows for detection of failures or intermittent conditions when they occur. This can be extremely useful in diagnosing the problem and formulating corrective action. In vibration, it is advantageous to know in what environment, level, axis, and time the anomaly occurred. Also, this procedure allows a test to be discontinued at the time the anomaly occurs to avoid the potential for further damage. | This practice has been used on the Mariner series, Viking, Voyager, Magellan and Galileo programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/14/2000
777 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Electrostatic Discharge (ESD) Test Practices | Preferred Practice for Design & Test. If protective design and verification measures are not taken when necessary, the worst impact that can occur is that the satellite will become completely non-functional. Total losses have occurred on several satellites in Earth geostationary orbits (a very severe space charging environment); the failures were attributed to the effects of electrostatic discharge. A less severe effect is transient disruptions in satellite operation. Test satellites for the ability to survive the effects of electrostatic discharges (ESDs) caused by a space charging environment. Such environments include Earth equatorial orbits above 8000 km and virtually all orbits above 40 degrees latitude, Jupiter encounters closer than 15 Rj (Jupiter radii), and possibly other planets. | If protective design and verification measures are not taken when necessary, the worst impact that can occur is that the satellite will become completely non-functional. Total losses have occurred on several satellites in Earth geostationary orbits (a very severe space charging environment); the failures were attributed to the effects of electrostatic discharge. A less severe effect is transient disruptions in satellite operation. Examples include Power On Reset events (Voyager at Jupiter encounter) and attitude control disruptions requiring frequent ground controller intervention (several Earth geostationary satellites). | Test satellites for the ability to survive the effects of electrostatic discharges (ESDs) caused by a space charging environment. Such environments include Earth equatorial orbits above 8000 km and virtually all orbits above 40 degrees latitude, Jupiter encounters closer than 15 Rj (Jupiter radii), and possibly other planets. | JPL | 01/27/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1414 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Proper implementation of this practice will assure that satellites will operate in the space charging environment without failure or awkward ground controller operations. Implementation Method: The following information has been partially derived from NASA Technical Paper 2361, quotDesign Guidelines for Assessing and Controlling Spacecraft Charging Effectsquot. That document is also recommended for further description of the test process. Subject the spacecraft to an environment representative of that expected. The environment applied to the spacecraft should include a safety margin (i.e., be greater than expected) that gives confidence that the flight spacecraft will survive the real environment. Have a design qualification test sequence that is extensive: test all units of hardware; use long test durations; examine many equipment operating modes; apply the environment to all surfaces of the test unit. Have a flight hardware test sequence of more modest scope: delete some units from test if qualification test shows great design margins; use shorter test durations; use only key equipment operating modes; and apply the environment to a limited number of surfaces. Simulation of Parameters The following items should be considered in test design: Spark location. Radiated fields, and/or structure currents. Area, thickness, and dielectric strength of material. Total charge involved in the event. Breakdown voltage. Current waveform: rise time, width, fall time, and rate of rise (amps/second). Voltage waveform: rise time, width, fall time, and rate of rise (amps/second). Table 1 shows typical values as calculated on some spacecraft. They have been compiled from a variety of sources, mostly associated with the Voyager and Galileo spacecraft. New values must be calculated for a different satellite. Table 1. Examples of Estimated Space-Generated ESD Spark Parameters [D] Several representative types of test equipment are described in Table 2. Where possible, typical parameters for that type of test are listed. Table 2. Examples of Several ESD Generators [D] MIL-STD-1541 Sparker The MIL-STD-1541 sparker is commonly used. The schematic and usage instructions are shown in MIL-STD-1541A. Flat Plate Capacitor A flat plate capacitor may be used in several circumstances. Examples of spacecraft areas which may be simulated by a flat plate capacitor are: (a) thermal blanket areas; (b) dielectric areas such as calibration targets; or (c) dielectric areas such as non-conductive paints. The chief value of a flat plate capacitor is to permit a wide-spread discharge to simulate the physical path of current flow. Lumped Element Capacitors Lumped element capacitors can overcome some of the objections raised about flat plate capacitors. They can have large capacitance in similar areas and this supplements a flat plate capacitor if it alone is not adequate. Switches There are a wide variety of switches that can be used to initiate the arc discharge. At low voltages, semiconductor switches can be used. The MIL-STD-1541 sparker uses an SCR to initiate the spark activity on the primary of a step-up transformer. Also at low voltages, mechanical switches may be used (for example, to discharge modest voltage capacitors). The quotbouncequot problem with mechanical switches can be alleviated by the use of Mercury-wetted switches. For high voltage switching in air, a gap made of two pointed electrodes can be used as the discharge switch. For tests which involve a fixed discharge voltage, gas discharge tubes are available with fixed breakdown voltages. The advantages of the gas discharge tube compared to needle points in air is its faster rise time and its very repeatable discharge voltage. Another gas discharge tube is the triggered gas discharge tube. This tube can be triggered electronically, much as an SCR can be turned on by its gate. Methods of ESD Application The ESD energy can be as much as one joule, but usually is in the range of millijoules of energy. The methods of application can range from indirect (radiated) to direct (applying the spark directly to a piece part). In general, the method of application should simulate the expected ESD source as much as possible. The following paragraphs describe several typical methods: Radiated Field Tests The sparking device can be operated in air at some distance from the victim. This can be used to check for RF interference to communications or surveillance receivers as coupled into their antennas. It can also check susceptibility of scientific instruments which may be measuring plasma or natural radio waves. Single Point Discharge Tests Discharging the arc onto the spacecraft surface (or a temporary protective metallic fitting), with the arc current return wire in close proximity, can represent the discharge and local flowing of arc currents. This test is more severe than the radiated test, since it is immediately adjacent to the spacecraft rather than some distance away. Structure Current Tests The objective of structure current testing is to simulate quotblowoffquot of charges from a spacecraft surface. If a surface charges and a resultant ESD occurs, the spark may vaporize and mechanically remove both material and charges without local charge equalization. In such a case the remaining charge on the spacecraft will redistribute itself, causing structural currents. Typically, such a test would be accomplished by using one or more of the following current paths: diametrically opposed locations (through the spacecraft). protuberances (from landing foot to top; antenna to body; thruster jets to opposite side of body). extensions or booms (from end of sensor boom to spacecraft chassis; end of solar array to spacecraft chassis). from launch attachment point to other side of spacecraft. Unit Testing Unit ESD testing serves the same purpose it serves in standard environmental testing; i.e., it serves to identify design deficiencies at a stage when design changes are more easily accomplished. However, it is very difficult to provide a realistic determination of the unit's environment as caused by an ESD on the spacecraft. Spacecraft Testing The system level test will provide the most reliable determination of the expected performance of a space vehicle in the charging environment. Such a test should be conducted on a representative spacecraft prior to exposing the flight spacecraft to assure that there will be no inadvertent over stressing of the flight units. Ideally the spacecraft should be in a 100% flight-like configuration. A detailed test plan must be developed defining test procedures, instrumentation, test levels, and parameters to be investigated. Test techniques will probably involve current flow in the spacecraft structure. Tests may be conducted in ambient environment, but screen rooms with electromagnetic dampers are recommended. MIL-STD-1541 system test requirements and radiated EMI testing are considered to be a minimal sequence of tests. The test levels should be determined from the analysis of discharging behavior in the substorm environment. It is recommended that full level testing, with test margins, be applied to structural, engineering, or qualification models of spacecraft with only reduced levels applied to the flight unit. The test measurements (structural currents, harness transients, upsets, etc.) are the key systems responses which are to be used to validate predicted behavior. Regions of space that contain plasmas (ionized gases, usually consisting of electrons and hydrogen ions) can sometimes be of high energy, as much as 20,000 electron volts or more. The interaction of this plasma with typical spacecraft dielectric surfaces (usually thermal control surfaces, such as Teflon thermal blankets) causes negative charge to be deposited on these surfaces. It has been documented that such charges can generate electric fields in excess of the breakdown strength of the dielectrics. The resultant ESD spark has been known to disrupt digital and analog electronics, and can even be so strong that it damages spacecraft electronic hardware. References: MIL-STD-1541A, quotElectromagnetic Compatibility Requirements for Space Systemsquot NASA Technical Paper 2361, quotDesign Guidelines for Assessing and Controlling Spacecraft Charging Effectsquot | This practice has been used on Voyager, Galileo | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/13/2000
778 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Selection of Spacecraft Materials and Supporting Vacuum Outgassing Data |  | Noncompliance with outgassing requirements could result in degraded science data due to excessive contamination of an instrument, or in the complete failure of a space flight mission. Noncompliance with outgassing requirements could result in non-approval of materials for space flight use. If the non-approved materials are already assembled in a flight vehicle or scientific instrument, they may have to be removed and replaced by approved materials. | Each flight project provides requirements for defining and implementing a contamination control program applicable to the hardware for the program. The program consists first in defining the specific cleanliness requirements and setting forth the approaches to meeting them in a Contamination Control Plan. One significant part of the Contamination Control Plan is a comprehensive Materials and Process Program beginning at the design stage of the hardware. This program helps ensure the safety and success of the mission by the appropriate selection, processing, inspection, and testing of the materials employed to meet the operational requirements for the application. The following potential problem areas are considered when selecting materials: radiation effects, thermal cycling, stress corrosion cracking, galvanic corrosion, hydrogen embrittlement, lubrication, contamination of cooled surfaces, composite materials, atomic oxygen, useful life, vacuum outgassing, toxic offgassing, flammability, and fracture toughness. The practice described here for the collection and compilation of vacuum outgassing data is used in conjunction with a number of other processes in the selection of materials. Vacuum outgassing tests are conducted on materials intended for space flight use, and a compilation of outgassing data, Reference 1, is maintained and constantly updated as new materials are tested. This includes materials used in the manufacture of parts intended for space applications. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1410, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: These test data provide outgassing information on a wide variety of materials and should be used as a guide by engineers in selecting materials with low outgassing properties. Implementation Method: Contamination Control Plans (CCPs), Reference 2, that are prepared and approved for space flight projects, require that materials intended for space applications must be tested and must comply with the outgassing test criteria defined below. These plans generally describe methods for controlling contaminates and verifying that they have been prevented or abated such that the hardware will meet performance requirements. Contamination requirements for space flight hardware specify that materials intended for use in space flight applications shall be tested for their vacuum outgassing properties in accordance with ASTM E-595-77/84. In general, a material is qualified on a product-by-product basis. However, lot testing may be required of any material for which lot variation is suspected. Only materials that meet the criteria of ASTM E-595-77/84 [i.e., have a total mass loss (TML) < 1.0% and a collected volatile condensable mass (CVCM) < 0.10%] are approved for use in a space environment unless application considerations dictate otherwise. The outgassing test is conducted in a vacuum of 10-6 Torr at a temperature of 125 deg. Centigrade with a test exposure time of 24 hours. The equipment and test procedures required to conduct the outgassing test are defined by ASTM E-595-77/84. Materials based on these selection criteria are normally used for space applications; however, some applications may require more or less stringent criteria depending upon such factors as the amount of material involved, expected temperature of exposure, location of the materials on the payload, the criticality of the contamination requirements, etc. A CVCM collector temperature colder than the standard may be required to reflect the intended use. The proposed use of a noncompliant material that does not meet the TML<1.0% and/or the CVCM<0.1% requirements is documented for GSFC review and approval by a Materials Usage Agreement. Data on tested materials included in reference 1 are presented in three different ways in order to facilitate materials selection. In Section A, the materials are divided by category into 18 probable uses, such as adhesives, greases, paints, potting compounds, and so forth. In Section B, all the material contained in Section A is listed in alphabetical order by manufacturer's identification. In Section C, the only materials listed are those having TML and CVCM equal to or lower than a maximum 1.0% TML and a maximum 0.10% CVCM grouped by use. It should be noted that data has been collected over a period of 20+ years and variations in materials may require retesting in some cases. The selection of polymeric materials with low vacuum outgassing characteristics is an essential part in the selection of materials for use in space flight hardware. Materials must be selected which do not exceed specified levels of outgassing in the vacuum of space. Excessive outgassing can degrade the structural integrity of materials, thereby changing their characteristics and causing excessive contamination of critical surfaces. Outgassing molecules can deposit on cold optical and other critical surfaces, become baked-on when exposed to sunlight, and in some cases change color. These baked-on deposits can not be removed easily. These deposits can significantly degrade ultraviolet scientific instruments and measurements and infrared measurements by obscuring specific wavelengths of interest. Additionally, thermal control surface properties such as solar absorption, infrared emissions, etc., can also be significantly affected. References: NASA, Reference Publication 1124, Revision 2, Outgassing Data For Selecting Spacecraft Materials, November 1990 GSFC, SPAR-3, Standard Payload Assurance Requirements (SPAR) for GSFC Orbital Projects, Paragraph 6.2.5.2 and Section 9, March 1990 | This practice has been used on all GSFC Flight Programs. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 04/13/2000
779 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Environmental Test Sequencing | Preferred Practice for Design & Test. If the thermal-vacuum tests do not follow the dynamics tests, more intermittent or incipient discontinuity type failures may go undetected. If the defects are not detected during assembly level tests and are subsequently detected during the system level tests, redesign or rework at this late stage of the process could cause delays, increase costs, or make it necessary to accept additional risk that might have been avoided. If the defects are not detected at the system level, the defects may then cause hardware anomalies during the mission, and in the extreme could cause a mission failure. Perform dynamic tests prior to performing thermal-vacuum tests on flight hardware. | If the thermal-vacuum tests do not follow the dynamics tests, more intermittent or incipient discontinuity type failures may go undetected. If the defects are not detected during assembly level tests and are subsequently detected during the system level tests, redesign or rework at this late stage of the process could cause delays, increase costs, or make it necessary to accept additional risk that might have been avoided. If the defects are not detected at the system level, the defects may then cause hardware anomalies during the mission, and in the extreme could cause a mission failure. | Perform dynamic tests prior to performing thermal-vacuum tests on flight hardware. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1412 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Experience has shown that until the thermal-vacuum tests are performed, many failures induced during dynamics tests are not detected because of the short duration of the dynamics tests. In addition, the thermal-vacuum test on flight hardware at both the assembly level and the system level provides a good screen for intermittent as well as incipient hardware failures. Implementation Method: Perform flight hardware testing in the following sequence: Sinusoidal or transient vibration, random vibration, pyroshock, and acoustics, as required. The order among these dynamics tests may be interchanged. Thermal-vacuum testing. To assure that this sequence is followed, specify in the test specifications or test plans, as appropriate, that all dynamic tests will be performed prior to thermal-vacuum tests on both the assembly and system levels. During the normal flight sequence, the launch environment is followed by vacuum and potential temperature extremes. In this flight sequence, the flight hardware is therefore exposed to acoustics and vibration followed by vacuum and temperature variations. Consequently, by performing dynamics tests prior to thermal-vacuum tests, the actual flight sequence is simulated. Also, if the flight sequence produces synergistic effects, the synergism will be simulated. In addition, preserving the sequence of the service environments in the environmental test program is a widely accepted practice. As a result, the effect of reversing the test sequence on spacecraft failure rates has not been quantified. However, evidence exists that many acoustic induced failures have not been detected until the spacecraft is exposed to the thermal-vacuum environment. These failures may not be detected during acoustics tests because of the short one-minute duration or a non-operating power condition. Typically, the identified failures that could be related to or caused by the dynamic acoustic environment were bad solder joints, intermittents, bad bearings, broken wires, poor welds, leaks, foreign materials, etc. An example of a failure that might be induced by dynamic tests but not revealed until thermal vacuum would be a broken wire or solder joint. This defect might be induced by acoustics but not be detected during the acoustic test due to the short duration or to an unpowered or unmonitored state of the affected equipment. During post-acoustic functional testing, the wire or solder joint broken ends may be making adequate contact to show electrical continuity. In the subsequent thermal-vacuum test, the thermal distortions could cause loss of contact, allowing the failure to be detected. Reversing the test sequence could result in the defect not being induced until after thermal vacuum test and not detected until exposure to the flight thermal environment. Even if all defects precipitated by the dynamics tests are revealed during the test, or during post-test functional testing, performing the dynamic tests first will still have the advantage of increasing the probability that defects will be detected earlier, when they will have less impact on the system test program cost and schedule. | This practice has been used on Mariner Series, Voyager, Viking, Galileo | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/13/2000
776 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Radiated Susceptibility System Verification | Preferred Practice for Design & Test. Erratic or uncontrolled performance may occur which could compromise or abort the mission. Verify that a flight vehicle or system is hardened to the launch, boost, and flight electromagnetic radiation environment by radiating simultaneously, during system checkout, on all major emission frequencies that are known to exist during vehicle operations. Monitor all critical systems for erroneous performance while the spacecraft or system is stepped through all operating modes. | Erratic or uncontrolled performance may occur which could compromise or abort the mission. | Verify that a flight vehicle or system is hardened to the launch, boost, and flight electromagnetic radiation environment by radiating simultaneously, during system checkout, on all major emission frequencies that are known to exist during vehicle operations. Monitor all critical systems for erroneous performance while the spacecraft or system is stepped through all operating modes. | JPL | 01/29/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1416 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Spurious interferences and responses can be identified during system checkout. After the spurious responses are evaluated, solutions can be proposed, and remedial action taken, if necessary, prior to the actual flight. Implementation Method: A system verification susceptibility test is planned as part of the system checkout. The susceptibility of all systems to the specified electromagnetic radiation environment is observed while each subsystem is stepped through a typical sequence of operations. The electromagnetic radiation environment is simulated by operating a number of separate signal generators/amplifiers connected to a cluster of antennas. As the system test progresses, the antenna cluster is directed sequentially at each subsystem from a distance of one meter or other prescribed distance which will provide adequate coverage. Figure 1 shows the physical arrangement for system test of the Galileo spacecraft; seven antennas are directed toward the Energetic Particle Detector (EPD). The antenna assembly was moved to appropriate locations to illuminate each sensitive area as the test progressed. [D] Figure 1: Galileo System Test with Seven Antennas Directed Toward the EPD When a spurious response is observed, each transmitter is turned off and on sequentially until the cause of the response is isolated to one or a combination of radiators. The probability of the particular signal or combination of emitted signals occurring simultaneously with the particular spacecraft mode must be evaluated before any remedial action is initiated. In a complex system which emits and is exposed to a number of radiated signals, there is a large number of spurious frequencies which may produce unexpected results during ground checkout, launch, and flight. Sources of electromagnetic radiation are listed in Table 1. Table 1: Sources of Radiated Emissions EXTERNAL Test Range Tracking Radars Space Shuttle Transmitters Booster Transmitters AM, FM, & TV Broadcast Transmitters INTERNAL On-board Transmitters Receiver Local Oscillators Data Bus Clock Frequencies These signals or their harmonics may combine to produce intermodulation products at a sensitive frequency which could cause an unwanted response. Susceptible frequencies that may respond to the emissions are receiver main tuning frequencies, image frequencies, and the 1st and 2nd receiver intermediate frequencies. By simulating the radiation environment that the vehicle will be exposed to during system checkout and free flight, potential sources of interference can be identified, evaluated, and corrected, if necessary. Synergistic combinations of sources may be detected with this approach. The probability of a successful flight will be increased by performing this verification test. References: quotINTERMODquot, A computer program to calculate intermodulation products of multiple transmitters that fall within the bandwidths of multiple receivers, Paul Rusales, Lockheed California Co., January 1987. | This practice has been used on Voyager, Magellan, Galileo, and Ocean Topographic Experiment (TOPEX/POSEIDON) | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
775 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Random Vibration Testing | Preferred Practice for Design & Test. Dynamic testing decreases the probability of in-flight failure due to design deficiencies or defective workmanship. Define an appropriate random vibration test, and subject all assemblies and selected subsystems to the test for design qualification and workmanship flight acceptance. | Increased probability of in-flight failure due to design deficiencies or defective workmanship. | Define an appropriate random vibration test, and subject all assemblies and selected subsystems to the test for design qualification and workmanship flight acceptance. | JPL | 01/30/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1413 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Implementation Method: Apply broadband, shaped, random vibration to the test item through its service attachments. The frequency band should span from approximately 20Hz to 2000Hz. Apply vibration in each of three mutually perpendicular axes (preferably the principal axes of the test item). Closed loop, servo control the vibration specification at one or more of the test item-to-fixture interface points. Narrow band test item response limiting or force limiting may be warranted to avoid unrealistically severe resonant responses of the test item. Duration of the random vibration application in each axis should be not less than the flight duration for which the vibroacoustic environment is within 6dB of its maximum or 30 seconds; whichever is greater. The flight acceptance (FA) test level should be equal to or greater than the maximum predicted flight environment, but not less than a level which has been found to provide an adequate workmanship screen for the type of hardware being tested. Qualification and protoflight test levels should have margin above the FA level. Random vibration testing has two principal objectives: To verify the test item design's capability, with some margin, to withstand the launch vibroacoustic environment, and To screen the workmanship integrity of the flight equipment. Random vibration criteria should be developed by the process described in the following four steps: Determine the Power Spectral Density (PSD) of the random vibration directly transmitted into the flight article through its mounts from the launch vehicle ources such as engine firing, turbopumps, etc (see Figure 1). These vibration conditions at the launch vehicle-to-payload interface are typically available from the launch vehicle builder. Perform an analysis to predict the payload/flight article's vibration response to the launch vibroacoustic environment. Statistical energy analysis (SEA) methods such as the VAPEPS (VibroAcoustic Payload Environment Prediction System) program are effective predictors in the higher frequencies (see Figure 2). The VAPEPS program can also effectively extrapolate from a database using SEA techniques to provide predictions for a similar configuration. If random vibration predictions are needed for the lower frequencies, finite element analysis methods, such as NASTRAN, are commonly used. The vibration is induced into the test article both directly and indirectly (through its mounting). [D] Figure 1: Vibration levels transmitted to flight article through mounts [D] Figure 2: Payload/flight article response to vibroacoustic environment Establish a minimum level of vibration which is necessary to ferret out workmanship defects--both existing and potential failures (see Figure 3). This is particularly applicable to electronic assemblies for which minimum effective workmanship levels have been established based on extensive test experience. Envelope the curves from 1-3 to produce a composite random vibration specification for the test article as follows: This resultant random vibration specification (Figure 4), which is employed as the flight acceptance test level, covers the two primary sources of this vibration while also providing an effective process for uncovering workmanship defects, particularly for electronics. Qualification and Protoflight test levels are increased typically 3 to 6dB above flight acceptance to verify that the design is not marginal. [D] Figure 3: Minimum vibration levels for workmanship defect detection [D] Figure 4: Composite Conventional rigid fixture vibration tests can severely overtest the hardware at resonances. It is accepted practice to response limit, or notch the input, at resonances of fragile hardware where it can be technically justified with flight or system test data, or analysis. Recently developed techniques to alleviate the overtest at resonances by specifying force limiting criteria potentially provides a much more accurate simulation of the flight vibration environment, but have not yet been implemented NASA-wide. The launch vehicle acoustically excites the spacecraft. This excitation is impractical to simulate for electronic assemblies at the assembly level because of fixture complexity, etc. Therefore, random vibration is substituted to excite the hardware. Random vibration is currently the most widely adopted type of dynamics environmental testing for spaceflight hardware. It is generally perceived by users to be the most realistic environment to reproduce in the vibration test laboratory as well as an effective tool for uncovering workmanship defects-- especially in electronics assemblies. | This practice has been used on Mariner series, Viking, Voyager, Magellan, Galileo | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
774 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Isolation Verification (DC) | Preferred Practice for Design & Test. Erratic or uncontrolled performance may occur which could compromise or abort the mission. Direct current (DC) electrical isolation verification tests are made as part of the EMC test of hardware prior to final spacecraft assembly. Flight acceptance isolation retest is required after any hardware rework of subsystems with electrical interfaces that utilize system wiring. | Erratic or uncontrolled performance may occur which could compromise or abort the mission. | Direct current (DC) electrical isolation verification tests are made as part of the EMC test of hardware prior to final spacecraft assembly. Flight acceptance isolation retest is required after any hardware rework of subsystems with electrical interfaces that utilize system wiring. | JPL | 01/27/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1417 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Inadvertent grounds of isolated circuits and ground loops are detected directly by this test. In some cases, such grounds may pass other tests with no apparent degradation. Failure may not occur until the vehicle is subjected to high level electromagnetic radiation. Since this test requires minimal test equipment and can be performed in a short time, its benefits are achieved at low cost. Implementation Method: Electrical isolation verification is a direct current resistance measurement of all circuits that are required to have electrical isolation from subsystem circuit common or subsystem chassis. The resistance must be at least 1 megohm between each isolated circuit and circuit common or chassis when measured with a suitable multimeter. A multimeter must be selected that will not overstress sensitive components. There are five types of isolation circuits which are tested in slightly different ways. Differences between the five types are shown in Figures 1 through 5 and in Table 1 below: [D] Figure 1: Single Unreferenced End-Circuit General Isolation Test Configuration [D] Figure 2: Multiple Unreferenced End-Circuits, Single Return General Isolation Test Configuration [D] Figure 3: DC Isolation Resistance for Subsystem or Assemblies Isolated from Chassis Ground [D] Figure 4: DC Isolation, Circuit Common to Chassis Ground [D] Figure 5: Isolated Circuit Common Configuration - C O N D I T I O N S - Figure Isolation Test Signal Chassis Common 1. Signal to Common isolated ground ground 2. Signal to Common multiple/isolation ground ground 3. Signal to Common isolated ground isolated 4. Common to Ground -- ground isolated 5. Common to Chassis -- isolated isolated Table 1: Testing of Five Types of Isolation Circuits When more than one end circuit shares a common return, as in Figure 2, the minimum allowable resistance is divided by the number of end circuits. Each measurement is made with the subsystem or assembly unpowered and disconnected from support equipment. The measurements are made in both polarities of the multimeter because semiconductors have polarity dependent resistance. No attempt is made to record the actual resistance; the only requirement is that it exceed 1 megohm per circuit (0.5 megohm for two circuits, etc.). This is a relatively simple measurement which can be made with minimum impact on other activities during spacecraft assembly. A number of problems, such as inadvertent grounds have been detected by this test which may have passed the normal checkout test operations. | This practice has been used on Voyager, Magellan, Galileo, and Ocean Topographic Experiment (TOPEX/POSEIDON) | N/A |  | Aeronautics Research, Science | Public | Not Specified |  | 04/11/2000
742 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Verification of Nominal Conditions After Restoration of Power |  | Personnel operating critical equipment should not assume that the support environment is intact after an outage. They should operate instead under the assumption that something might go wrong. | Appropriate precautions and checks should be made to ensure that critical equipment, when powered, will function as intended. An example is phase reversal which occurred the wiring during installation or maintenance was incorrect, causing equipment to function in reverse. | JSC | 02/29/2000 | On May 16, 1994, an AMDAHL 5995M mainframe computer overheated at approximately 8:20 AM in the Software Production Facility (SPF) in Building 30 at JSC. Physical damage to the computer due to this overheat was estimated at $669,000. This overheat occurred due to an inadvertent miswiring of a circuit breaker after a routine power outage and maintenance of the breaker. The quality inspection failed to check for the proper rewiring of the circuit breaker. The miswiring caused a phase rotation of the power, which in turn caused fans cooling the AMDAHL 2550 to turn backwards. Power isolation and monitoring equipment that could have prevented any impact from the phase rotation was not properly utilized. This led to insufficient cooling of the AMDAHL 2550 which resulted in the overheat and subsequent damage. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
741 | Murphy, Maria - 0000000000 : NO@ADDRESS.GIVEN | Murphy, Maria - 0000000000 : NO@ADDRESS.GIVEN |  | Hazards of Metal Desks |  | The employee was a safety-conscious professional furniture mover and was wearing heavy leather gloves. Unfortunately, this was not enough protection from the unexpected sharp edge of the leg cover. When performing any task that involves furniture moving, be on the lookout for potential pinch point hazards and wear personal protective equipment. A coworker took the employee to a local hospital for emergency treatment, although no one called the emergency numbers before leaving. It is important to ensure that employees are familiar with their facility emergency procedures and numbers. | Inspect furniture periodically. Identify possible pinch points, broken or loose parts, sharp edges, or other hazards. Report furniture that appears damaged or hazardous to the furniture repair department. Never move large furniture yourself. Call the moving and hauling department to schedule the rearrangement of furniture. Remember to call the appropriate emergency numbers for serious injuries. | JSC | 02/22/2000 | An employee severed the tip of his finger while unloading a metal desk from a truck. One of the desk's sheet metal leg covers had slid down the leg's support beam and created a pinch point between the sheet metal leg cover and the desktop, catching the employee's finger. [D] [D] |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
744 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Evaluation of Actual Operating Conditions in Hardware Designs Prior To Hazardous Testing/Operations |  | Failure to consider actual operating conditions in design prior to testing can lead to hazards and injury of those involved in the test | Actual environmental conditions should be collected and considered in design of tools, equipment, and operations early in the design and development process. | JSC | 03/06/2000 | On May 28, 1993, a NASA astronaut suffered frostbite on eight fingers during manned thermal-vacuum (MTV) testing in Chamber B, Building 32, at JSC. This test was the second portion of a two-part test designed to evaluate the extravehicular activity (EVA) hand tool functionality and flight crew operations for the Hubble Space Telescope First Servicing Mission. The actual test lasted 6 hours in the thermal-vacuum chamber with the suited astronaut repeatedly operating a large number of hand tools and hardware at temperatures as low as -140°F. At the conclusion of the test, upon removal of his extravehicular mobility unit (EMU) gloves, the astronaut noted to the test director that his hands appeared frostbitten. During this test, the astronaut had reported that his hands were cold and that he was experiencing pain. This report was not made in a way that indicated any concern or alarm, and it went undetected by the test team. Astronauts routinely note experiencing cold during MTV and some hand pain is also a normally experienced due to the effort required to function in the pressurized suit gloves. The astronaut never again indicated during the run that he was experiencing pain or cold in his hands. As the test continued, the astronaut operated virtually all of the flight tools, most of them repeatedly. Temperature of the tools and other items was consistently measured via thermocouples at between -113°F and -131°F. Furthermore, these tools required hand & finger intensive manipulation to operate, and were in some instances operated repeatedly for functional verification. The MTV test team as a whole shared an apparently universal perception that the EMU provides sufficient protection to an astronaut in extreme environmental conditions. Failure modes and effects analysis (FMEA) and hazards analysis were accomplished on the test; however, they concentrated on hardware malfunctions and did not thoroughly assess hazards associated with the unique human factors in this test run, nor adequately consider operational hazards. The EMU-specific hazard analysis also did not adequately address hazards associated with exposure to extreme cold. It was also noted during the investigation that certain of the tools did not operate properly, or had not undergone any type of thermal of vacuum testing prior to the MTV tests. Additionally, the thermal effects of these tools on the astronaut's hands were not a design consideration. Nothing had been done to reduce thermal conductivity of the hand tools, and most had bare metal surfaces. There was also a lack of specific test data on thermal effects within the EMU gloves. Tests had been done on maximum allowable temperatures for short/light exposure, and on warmer temperatures for longer exposures; but it is difficult to extrapolate from these to actual temperatures, grasp pressures, length (of time) of grasp and cumulative effects. These factors are also affected by a number of variables in EMU sizing and individual astronaut options. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
743 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Rigor in Integrated Design, Development, Documentation, and Configuration Control |  | The rigor with which a design is developed and documented and the configuration is controlled, including the portion of the design that is test-unique, must be commensurate with the financial and programmatic value of the test article and test objectives. | All critical parties to the configuration of a model and exectution of a test must be present and/or review the total integrated design during the design and integration process. | JSC | 02/29/2000 | On December 8, 1995, a full-scale model of the NASA JSC Experimental Crew Return Vehicle (XCRV) experienced a failure of its parafoil deployment system during a test drop at the U.S. Army's Yuma Proving Ground (YPG) near Yuma, Arizona. The wingless 24-foot model impacted the ground without the parafoil deployed due to damage sustained when two lines entangled during deployment from a Colorado Air National Guard C-130 Aircraft at 15,000 feet mean sea level. The design of the test-unique model, platform restraint and separation system was neither reviewed by all parties affected by its integration nor well documented. As a result, opportunities to identify design problems were missed, and there was little opportunity to ensure conformance with the intended design in the vehicle configuration process. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
876 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Recognition and Communication of Hazards During Operational Testing |  | Low hazard awareness by test team members, test subjects, and those performing hazard analyses can result in injury, especially where equipment is perceived to be "safe". | Those performing hazardous test operations should be specifically trained to recognize, report, and properly respond to all credible hazard situations. They should be sensitized to the possibility of these circumstances and remain alert to early symptoms. Specific terms for describing symptoms should be clearly defined before the test, and proper reactions developed and, where necessary, practiced. Those performing hazard analysis should be similarly trained on the possibility of all credible hazards, and should ensure designs consider appropriate mitigation. | JSC | 03/06/2000 | On May 28, 1993, a NASA astronaut suffered frostbite on eight fingers during manned thermal-vacuum (MTV) testing in Chamber B, Building 32, at JSC. This test was the second portion of a two-part test designed to evaluate the extravehicular activity (EVA) hand tool functionality and flight crew operations for the Hubble Space Telescope First Servicing Mission. The actual test lasted 6 hours in the thermal-vacuum chamber with the suited astronaut repeatedly operating a large number of hand tools and hardware at temperatures as low as 140°F. At the conclusion of the test, upon removal of his extravehicular mobility unit (EMU) gloves, the astronaut noted to the test director that his hands appeared frostbitten. During this test, the astronaut had reported that his hands were cold and that he was experiencing pain. This report was not made in a way that indicated any concern or alarm, and it went undetected by the test team. Astronauts routinely note experiencing cold during MTV and some hand pain is also a normally experienced due to the effort required to function in the pressurized suit gloves. The astronaut never again indicated during the run that he was experiencing pain or cold in his hands. As the test continued, the astronaut operated virtually all of the flight tools, most of them repeatedly. Temperature of the tools and other items was consistently measured via thermocouples at between -113°F and -131°F. Furthermore, these tools required hand & finger intensive manipulation to operate, and were in some instances operated repeatedly for functional verification. The MTV test team as a whole shared an apparently universal perception that the EMU provides sufficient protection to an astronaut in extreme environmental conditions. Failure modes and effects analysis (FMEA) and hazards analysis were accomplished on the test; however, they concentrated on hardware malfunctions and did not thoroughly assess hazards associated with the unique human factors in this test run, nor adequately consider operational hazards. The EMU-specific hazard analysis also did not adequately address hazards associated with exposure to extreme cold. It was also noted during the investigation that certain of the tools did not operate properly, or had not undergone any type of thermal of vacuum testing prior to the MTV tests. Additionally, the thermal effects of these tools on the astronaut's hands were not a design consideration. Nothing had been done to reduce thermal conductivity of the hand tools, and most had bare metal surfaces. There was also a lack of specific test data on thermal effects within the EMU gloves. Tests had been done on maximum allowable temperatures for short/light exposure, and on warmer temperatures for longer exposures; but it is difficult to extrapolate from these to actual temperatures, grasp pressures, length (of time) of grasp and cumulative effects. These factors are also affected by a number of variables in EMU sizing and individual astronaut options. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
877 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Testing of Environmental Conditions to Be Experienced During Operations |  | Testing of operational hardware must simulate actual hardware environmental operating conditions as closely as possible. | Specific testing of environmental conditions (emulating as closely as possible those which are to be to be experienced during actual testing and/or operations) should be undertaken and the results factored into design and operations analysis prior to any test or operation. | JSC | 03/05/2000 | On May 28, 1993, a NASA astronaut suffered frostbite on eight fingers during manned thermal-vacuum (MTV) testing in Chamber B, Building 32, at JSC. This test was the second portion of a two-part test designed to evaluate the extravehicular activity (EVA) hand tool functionality and flight crew operations for the Hubble Space Telescope First Servicing Mission. The actual test lasted 6 hours in the thermal-vacuum chamber with the suited astronaut repeatedly operating a large number of hand tools and hardware at temperatures as low as 140°F. At the conclusion of the test, upon removal of his extravehicular mobility unit (EMU) gloves, the astronaut noted to the test director that his hands appeared frostbitten. During this test, the astronaut had reported that his hands were cold and that he was experiencing pain. This report was not made in a way that indicated any concern or alarm, and it went undetected by the test team. Astronauts routinely note experiencing cold during MTV and some hand pain is also a normally experienced due to the effort required to function in the pressurized suit gloves. The astronaut never again indicated during the run that he was experiencing pain or cold in his hands. As the test continued, the astronaut operated virtually all of the flight tools, most of them repeatedly. Temperature of the tools and other items was consistently measured via thermocouples at between -113°F and -131°F. Furthermore, these tools required hand & finger intensive manipulation to operate, and were in some instances operated repeatedly for functional verification. The MTV test team as a whole shared an apparently universal perception that the EMU provides sufficient protection to an astronaut in extreme environmental conditions. Failure modes and effects analysis (FMEA) and hazards analysis were accomplished on the test; however, they concentrated on hardware malfunctions and did not thoroughly assess hazards associated with the unique human factors in this test run, nor adequately consider operational hazards. The EMU-specific hazard analysis also did not adequately address hazards associated with exposure to extreme cold. It was also noted during the investigation that certain of the tools did not operate properly, or had not undergone any type of thermal of vacuum testing prior to the MTV tests. Additionally, the thermal effects of these tools on the astronaut's hands were not a design consideration. Nothing had been done to reduce thermal conductivity of the hand tools, and most had bare metal surfaces. There was also a lack of specific test data on thermal effects within the EMU gloves. Tests had been done on maximum allowable temperatures for short/light exposure, and on warmer temperatures for longer exposures; but it is difficult to extrapolate from these to actual temperatures, grasp pressures, length (of time) of grasp and cumulative effects. These factors are also affected by a number of variables in EMU sizing and individual astronaut options. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
745 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Potential for Low Oxygen Levels in Non-Enclosed Areas |  | Under certain environmental conditions, oxygen deprivation hazards are possible during cryogenic operations in non-enclosed areas. | Care should be taken whenever cryogenic materials are involved in an operation to prevent injuries due to the development of local areas containing non-breathable atmospheres even if the operation is in an "open" area. Personnel involved should be trained to recognize this hazard and active ventilation should be provided where required. | JSC | 03/07/2000 | On January 4, 1995, at approximately 8:50 a.m., two technicians at WSTF were overcome and collapsed from breathing in an oxygen deficient atmosphere that formed during shutdown operations following a transfer of liquid nitrogen (LN2) from a vendor supply tanker to a WSTF storage tanker. This transfer operation was normally controlled by monitoring a tanker vent line. Flow from this vent line indicated the tank was full, and the operation was suspended. There is also a liquid level indicator and a pressure gage on the WSTF tanker for monitoring purposes. On the morning of the mishap, conditions (high humidity and still air) existed which caused a larger than normal water vapor cloud to form during continuous venting of cold gaseous nitrogen (GN2) during the filling operation. This venting is required to keep the WSTF tanker at a lower pressure than the vendor tanker during the fill operation. The cloud prevented the normal visual monitoring of the vent line, the liquid level indicator, and the pressure gauge. The technicians, instead of positioning themselves to be able to monitor the vent line and gauges, located approximately 30 feet away from the tanker to both remove themselves from the heavy vapor cloud and also to remain out of the rain. During the operation, the technicians would periodically approach the tankers to monitor the liquid level indicator and the pressure gauge. The vent line was never observed due to being obscured by the vapor cloud. After about 50 minutes, the weather got worse and the technicians decided to suspend the operation due to weather and because they thought the tanker was nearly full. Data collected later showed that the tanker was completely full, and that LN2 was being released through the vent line instead of GN2. As the first technician attempted to close the vent and transfer valves, he was overcome and collapsed due to the lack of oxygen. The second technician, who was monitoring the activity, also was overcome and collapsed due to the lack of oxygen. A few moments later, vendor personnel approached and eventually remove both technicians from the area. Later investigation indicated that LN2 flow from the vent line coupled with adverse weather conditions created an oxygen deficient atmosphere in the area. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
772 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Fault Protection | Preferred Practice for Design & Test. A decision to forego fault protection will increase the risk of unrecoverable single point failures. Fault protection is the use of cooperative design of flight and ground elements (including hardware, software, procedures, etc.) to detect and respond to perceived spacecraft faults. Its purpose is to eliminate single point failures or their effects and to ensure spacecraft system integrity under anomalous conditions. | A decision to forego fault protection will increase the risk of unrecoverable single point failures. | Fault protection is the use of cooperative design of flight and ground elements (including hardware, software, procedures, etc.) to detect and respond to perceived spacecraft faults. Its purpose is to eliminate single point failures or their effects and to ensure spacecraft system integrity under anomalous conditions. | JPL | 01/29/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1243; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Fault protection design maximizes the probability of spacecraft mission success by avoiding possible single failure points through the use of autonomous, short-term compensation for failed hardware. Implementation Method: Except during critical event periods, the primary purpose of an autonomous fault protection system is to place the spacecraft in a safe, commandable state which can be maintained for a reasonable period (typically two weeks) following a fault. During critical periods, the primary purpose of the fault protection system is to ensure the completion of the critical event. A simplified block diagram representing the following three general types of fault protection is illustrated in Figure 1: Subsystems alone. Subsystem to system, and System to ground control. [D] Fault Protection Allocations. All on-board, post lift-off, autonomous fault protection is designated as either quotsubsystem internalquot or quotsystemquot fault protection. Fault protection engineering elements which have been allocated fault protection responsibility must provide the requirements and design for the associated detections, monitors, responses, and diagnostic data in compliance with project functional requirements. Where science instruments include fault protection in their design, designers must still ensure compliance with spacecraft project fault protection requirements if one of the following conditions apply: The fault protection internal to the instrument is dependent on non-standard services from another subsystem (or another instrument), or Internal failures have an impact external to the instrument (viz, a change in power state, momentum, support to other instruments). Spacecraft Safing. Spacecraft quotsafingquot is a general purpose safe-state response which is initiated by both system and subsystem internal fault protection. The purpose of this response is to provide the following: A safe state for the hardware An uplink, and A downlink (with some exceptions for specific failure conditions). To achieve these goals, the normal stored sequence is terminated and non-essential spacecraft loads are powered off. Undervoltage Response. Most spacecraft designs include an undervoltage response, which is designed to protect the spacecraft in the event of a short or a bus overload. The hardware senses when the power drops below an established value for a specified time. If the criteria are met, the power system sheds all non-essential loads from the bus and indicates the undervoltage condition to the Command Subsystem, which will initiate the undervoltage recovery response. Critical spacecraft memories are maintained throughout the undervoltage. Functional Implementation Requirements. Fault protection is typically allocated to the on-board elements of the system in accordance with the following principles: Spacecraft versus ground control. Autonomous fault protection is included on board the spacecraft only if a response by Mission Operations is not feasible nor practical, or if action is required within two weeks of detecting the failure. Otherwise, ground control is responsible for fault recovery. In both cases, ground control is responsible for failure diagnosis and, if necessary, the configuration of the spacecraft to nominal operations after the fault. Protection against sabotage and operator errors. To simplify the development of fault protection, autonomous fault protection is not required to protect against sabotage or operator errors, although such protection is not prohibited. There is limited spacecraft protection against these failures (viz, information system data integrity checks and some software checks). Protection against spacecraft hardware and software design errors. To simplify the development of fault protection, autonomous fault protection is usually not required to protect against spacecraft design errors, although it is not prohibited if practical. The practice of fault protection typically provides some limited spacecraft protection against design errors (e.g., thermal fault responses). The autonomous fault protection function is responsible for all on-board fault detections and corrections except those routinely required to ensure spacecraft data integrity (viz, EDAC, Reed Solomon encoder, checksums, etc.). Data error detections and corrections may be used, however, for fault protection purposes. The spacecraft information system typically has the primary responsibility for ensuring data integrity. Fault Protection Design Requirements. Management and coordination of fault detection, monitoring, and response, for both system and subsystem internal fault protection, is performed in accordance with the following general rules: Enables/disables for responses. Where applicable, fault responses should have two enable/disable mechanisms (or the functional equivalent): an enable/disable by stored sequence, and an enable/disable by ground control or by fault protection algorithms. Enables/disables for monitor activation of any response. If a response can be initiated by more than one monitor, those monitors should include an enable/disable mechanism or the functional equivalent. Enable/disable state specification. Each enable/disable is specified by a single parameter unique to each fault protection algorithm. Enable/disable strategy - general. As a goal, fault protection monitors and responses should be designed to be enabled for the entire mission. This reduces the risk of incorrect fault protection states. Enable/disable strategy - critical events. For critical events, enable/disable strategies may be used to minimize or prevent the effects of an erroneous fault indication. Response initiation. Fault responses are initiated if and only if spacecraft performance is unacceptable, or there is a significant risk to the mission or to subsystem safety. Parameter modifications. All fault protection parameters which may reasonably be expected to change as a function of mission mode, type of activity, fault history, or operational experience should be alterable by ground control without requiring flight software modification. Software modifications. To the extent possible, monitor and response algorithms should be stored in programmable RAM. Configuration compatibility. On-board fault protection should be designed to respond to a fault while in any possible spacecraft configuration (e.g., fault protection should be able to accommodate all possible combinations). Independence from instruments. Engineering fault protection should not depend on science instruments or their data. Multiple faults. At a minimum, fault protection should be designed with the assumption that only one fault occurs at a time, and that a subsequent fault will occur no earlier than the response completion time for the first fault. As a goal, fault protection should be capable of recovering from multiple successive or coincident faults provided that the faults and associated fault algorithms are independent. Propagation of failures. Autonomous fault protection assumes that spacecraft hardware design ensures that a single failure in a subsystem (including instruments) cannot propagate to its redundant unit or to another subsystem, or prevent switching to its redundant unit. This can be verified by performing a failure modes, effects, and criticality analysis (FMECA) or fault tree analysis (FTA). Typical Fault Detection Design Requirements. Hardware and software detection sources have two criteria: Direct detection. Detection mechanisms should be as direct as possible (i.e., a direct measurement is preferred over a calculated or derived measurement). Detection coverage. Detection mechanisms should only be required to detect a failure to the level at which that failure can be isolated or corrected. Design Requirements for Fault Monitors. Software monitors used by system and subsystem internal fault protection have the following features: Monitor thresholds. Where possible, thresholds should use reasonableness checks, detection filtering (to exclude certain faults from a previously established fault database), or redundant detections. Threshold modifications. Monitor threshold values should be alterable by ground or sequence command, or by fault protection responses as appropriate. As a goal, monitors are best designed to detect and disregard failed sensors. Redundant detection. For detections where an inadvertent trip would result in a severe response (viz, downlink loss, irreversible hardware swaps, large use of expendables, critical sequence cancellation), and where a sensor anomaly could cause an inadvertent trip, independent physically or functionally redundant detections are employed such that simultaneous detections are necessary for response initiation. Fault response tolerance. Monitors are designed to be tolerant of off-nominal conditions following a reconfiguration resulting from a fault protection response (e.g., thresholds might be relaxed as part of a response). Design Requirements for Fault Responses. System and subsystem internal fault response concerns include: Fault response primary responsibility. Following an anomaly, fault responses should ensure spacecraft commandability and the maintenance of a safe state for at least two weeks. This requirement is superseded only by a requirement to complete a critical event. Fault protection priorities. Fault responses are designed with the following priorities: Protect critical spacecraft functionality, Protect spacecraft performance and consumables, Minimize disruptions to normal sequence operations, and Simplify ground recovery response, including providing for downlink telemetry. Multiple levels of response. Where possible, response design includes multiple levels of response, with the response actions executed in order of increasing severity. Real-time ground responses. Autonomous fault protection is designed so as to not require real-time ground responses for recovery from known faults. False alarm tolerance. Unintended entry into a fault protection response in the absence of a fault must not present a hazard to the spacecraft or mission. For critical event periods, however, this requirement is relaxed and is considered a goal. Use of redundant (and spare) units. Redundant or spare units may be used by autonomous fault protection responses if a satisfactory alternative design is not available. Unpowered redundant units. The transition of a unit from quotoffquot to quotprimequot must not require ground commands in order to support spacecraft fault protection and mission critical functions. Component warm-up times. Fault responses should take into account component warm-up times and similar delay requirements. Data Handling Requirements. The following data handling tasks are performed: Recording engineering data. The combination of sequences and fault responses should ensure the recording of engineering data prior to, during, and after the execution of any fault response. Some exceptions are made for recorder and command subsystems failures. Storage and preservation of diagnostic data. Fault protection is designed to include the storage of diagnostic data (see Telemetry and Diagnostic Data on page 7), and ensure that data are not overwritten as the result of a response action. This requirement only applies if the writing of diagnostic data is not affected by the original fault. Protection of critical science and engineering data. Fault responses must not destroy quotcritical dataquot stored on-board the spacecraft. quotCritical science and engineering dataquot must be defined by project policy. Requirements Interactions with Stored Sequences. The following interactions with on-board sequences may be necessary: Response design for critical events. Fault response is designed to ensure the completion of the critical event as and when required, with spacecraft safety having lower priority, until the critical events are completed. Orbit insertion is an example of a critical event. Response design for non-critical events. Unless required to execute a critical event, fault responses should stop any on-board sequence(s) only if the sequence(s) compromises the integrity of the fault response, or if the fault response compromises the integrity of the sequence. Reactivation of stored sequences. After completion of a response which terminates a non-critical stored sequence, fault responses should not autonomously resume the terminated sequence. Safing Requirements. quotSafingquot is defined as a general purpose fault response which results in the cancellation of non-critical sequences, the possible suspension of critical sequences, and a general reconfiguration of spacecraft components. Safing responses typically include the following general features: Uplink communications. The safing response provides for a spacecraft state and attitude that ensures uplink commandability in the long term. Downlink communications. The safing response provides for a spacecraft state and attitude that ensures continuous engineering telemetry with positive link margin. Environmental constraints. The safing response meets boresight and radiator environmental constraints. Safing priorities. When uplink, downlink, and hardware safing requirements are in conflict, the following priorities apply: Provide a safe state for the hardware, Provide an uplink, and Provide a downlink. Ultimately, uplink must be provided for in the long term. Benign spacecraft configuration. As a goal, safing responses should place the spacecraft in an operationally benign state. This includes but is not limited to the following: (1) powering off of all non-essential equipment including instruments, and (2) stopping of all non-essential spacecraft processes. Telemetry and Diagnostic Data Requirements. The spacecraft design should ensure that following an anomaly, spacecraft telemetry will be sufficient to perform the preliminary failure identification and analysis required for ground control to perform near-term corrective actions. At a minimum, the real-time telemetry stream includes the following: Measurements to unambiguously identify the current engineering subsystem configuration and operating status, Enable/disable states of fault protection software, and enable/disable states of fault protection dedicated hardware, Active/inactive states for fault protection software responses, Identification that a fault response has been activated, Monitor detection logic output (regardless of whether the monitor is enabled or disabled), and As appropriate, cumulative counters of faults detected. Telemetry design should ensure reasonable and timely sampling frequencies for these items. As a goal, the real-time telemetry stream should include monitor high water marks. A quothigh water markquot is defined as a measurement which identifies how close a monitor is to indicating a failure. Following an anomaly involving a fault protection activity, the spacecraft design should ensure that sufficient information is available to reconstruct the audit trail-- the sequence of fault protection events following the anomaly. Diagnostic data is also needed to analyze the anomaly and to identify the sequential effects of the anomaly on spacecraft performance. The data should be available in non-volatile telemetry or stored on-board for later retrieval by the ground system. At a minimum, diagnostic data should include unique identification and time-tagging of monitors and responses which have been active. It is also desirable that diagnostic data include the value of the measurement which initiated a response. Technical Rationale: JPL has incurred numerous instances of presumably redundant systems which failed to successfully transfer to the back-up path when the primary path did not function. A rigorous, systematic search, crosstrap FMECA, or sneak paths analysis could have foretold the failure, and redesign could have averted the problem. Prevention of propagating failures has its greatest value when supplemented by an on-board fault protection system. The practice of failure propagation prevention is of most value in a repairable system. Non-propagation minimizes the number of units requiring repair. In a non-fault protected spacecraft, this capability is limited to the preflight phases of either subsystem or system testing. In a fault protected spacecraft, it can be extended to the flight phase as well. The key to this investigation is a complete diagram of the involved interface circuits which penetrates each unit to a circuit depth sufficient to prove that no possible failures in one unit can propagate to become irreversible hardware failures in a second unit. Another input is a complete list of part or assembly failure modes for hypothesis. Successful transfer (or equivalently independence of the primary and back-up functions) is a necessity for either repairable or non-repairable systems and requires the same complete interface diagram and complete list of failure modes. Such a list must include items such as: Part failure modes (opens, shorts, stiction, etc.), Single event effects (latch-up, transfer, etc.), and EMI (latch-up, transfer, overvoltage). These last two items are critical since they can affect both sides of a redundant pair. References JPL D625-505; Vol. 8, Fault Protection System Design and Operations. 699-CAS-3-330; Fault Protection Requirements, Cassini Project. 699-CAS-3-331; System Fault Protection Algorithms, Cassini Project. | This practice has been used on Voyager, Galileo, Magellan, Cassini. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
771 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Voltage & Temperature Margin Testing | Preferred Practice for Design & Test. Voltage and Temperature Margin Testing (VTMT) is the practice of exceeding the expected flight limits of voltage, temperature, and frequency to simulate the worst case functional performance, including effects of radiation and operating life parameter variations on component parts. For programs subject to severe cost or schedule constraints, VTMT has proven an acceptable alternative to conventional techniques such as worst case analysis (WCA). WCA is the preferred approach to design reliability, but VTMT is a viable alternative for flight projects where trade-offs of risk versus development time and cost are appropriate. | Using neither WCA nor VTMT to simulate circuit functional performance, a unit is subject to functional peril from changes in uncontrolled circuit parameters due to part variations. Inadequate margins can result in sudden failure to operate, or the condition can lead to functional degradation of the circuit with a high probability of catastrophic failure due to drift outside the operational limits of the unit. Lacking insight from test or analysis, the project is likely to lack provisions for detection of these problematic areas in the failure intervention plan. Without the VTMT or WCA parameter change matrix as a readily available diagnostic tool, failure causes and remedies must be determined under post-failure constraints, where time and hardware limitations may inhibit adequate corrective action. | Voltage and Temperature Margin Testing (VTMT) is the practice of exceeding the expected flight limits of voltage, temperature, and frequency to simulate the worst case functional performance, including effects of radiation and operating life parameter variations on component parts. For programs subject to severe cost or schedule constraints, VTMT has proven an acceptable alternative to conventional techniques such as worst case analysis (WCA). WCA is the preferred approach to design reliability, but VTMT is a viable alternative for flight projects where trade-offs of risk versus development time and cost are appropriate. | JPL | 01/29/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1431 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. On spacecraft hardware where risk vs. cost trades permit higher risk (Class C), Voltage and Temperature Margin Testing (VTMT) is an economical alternative to classical worst case analysis (WCA). The major benefits in using VTMT instead of WCA are: Assurance of a systematic method for investigation of potential risks where the parameters are not adequately modeled by worst case analysis. An example is RF circuits which have distributed circuit parameters. Labor savings for units too complex to simulate and which generally require Monte Carlo or root-sum squares analyses. Real-time operation and review of complex circuits, allowing the weighing of alternative design actions. Cost savings from expedited risk assessment. Comparative studies have demonstrated that testing may be completed in less than one-third the time required for analyses. Implementation Method: The VTMT must be designed to achieve adequate variation of circuit parameters through a judicious choice of voltage, temperature, and frequency margin combinations to achieve an optimal, yet realistic check of the design margin. Sufficient margin must be demonstrated at beginning-of-life (BOL) to permit confident performance extrapolation for those conditions that are not achievable at component infancy. These conditions include radiation effects, initial tolerance variations, aging, and unit-to-unit variations defining end-of-life (EOL) conditions. VTMT applies power downstream of voltage regulating devices to permit an adequate range of voltage variations. Optimum limits for voltage and temperature must extend beyond the extremes of the derated part specifications, but must remain within manufacturer device limitations. The test plan pays careful attention to limits; it describes in detail the execution of the tests, including exercising the functional characteristics of the design and assessing the associated circuit parameters against the established pass/fail criteria. Potential failure modes must be identified prior to VTMT to ensure that no damage occurs to the unit under test. Typically the operational extremes are extended to demonstrate positive flight margins using temperature as the universal test parameter to simulate other parameters such as environmental and end-of-life changes. Thus the item under test is exposed to risk of damage by stress due to high temperature. Hence, the support equipment used to control the temperature and the test parameters must be extremely accurate, especially at maximum temperatures. Technical Rationale: VTMT has long been an important tool for verification of circuit operational limits that are dependent upon part parameter variations. The following techniques form the VTMT repertoire: (1) temperature variation, (2) applied voltage variation, and (3) clock frequency variations for digital circuits. The use of VTMT to simulate worst case functional performance is justified because the effects of voltage, temperature, and frequency upon device performance parameters is similar to the effects of radiation and end-of-life changes. This concept is very well demonstrated quantitatively at the part level, but less quantitatively at the assembly level. The rationale for use of these three test procedures is discussed below. 1. Temperature Variations: As temperature changes, so does the absolute values of the parameters of the individual parts. Temperature is the first order term in almost every variation of part parameters except for initial tolerance variation. Similarly for cables and transmission lines, distributed parameters exist that also vary with temperature. 2. Applied Voltage Variations: Changing the supply voltage to the circuit under test is equivalent to changing the voltage potentials across groups of parts. Thus the potential across each part within a circuit loop changes accordingly whenever the total applied voltage is changed. Varying the applied voltage can check the ability of an analog circuit to operate within specifications and generally can be added linearly to the temperature induced performance changes. 3. Variation of Clock Frequency for Digital Circuits: Varying the frequency of an input clock or pulse train can simulate changes of digital circuit delay parameters which may occur during flight. The limits of design degradation (and limits of absolute failure) with frequency can be determined. This knowledge can be used to determine if sufficient timing margins exist. Often voltage is reduced during the frequency margin testing to achieve even more margin. Clock frequency changes of ±25% are typical in performing the VTMT. In forming combinations of two or more of these test tools, considerable attention is given to simulating the effects of operating life, radiation, and initial tolerance. Preventive measures are ascertained from relevant experience, related reliability analyses, or test and manufacturing data that have been obtained on similar units and interfaces. VTMT duration should be sufficient for the devices to reach thermal equilibrium and exhibit steady-state operating conditions. The test requires approximately 3 hours at each temperature level over a 24-hour duration. Measurements before and after the tests are recorded and compared with a predetermined deviation, e.g., less than 15 percent. The test planner consults the failure prevention plan for the flight project to ensure the safety of the hardware. A test matrix may be used to form a safety prevention checklist of critical conditions, and the matrix may provide a catalogue identifying diagnostics and possible failure chain contributors. The VTMT technique is a closed-loop process; it comprises a checklist that is planned, monitored, and evaluated concurrently by quality assurance, reliability, and engineering personnel. Since the voltage, temperature, and frequency variations applied in VTMT can exceed those expected during flight, the additional circuit design margins successfully demonstrated by the test are assumed to encompass the parameter margins expected from radiation and operating life. Calculations can be performed to estimate the final margin. Note that although initial tolerances of parameters disappear when the to-be-flown hardware is the item under test, the initial tolerance variation must be considered in VTMT application to all other units of the same design. Figure 1 is a flow diagram of the VTMT process. [D] References Reliability Analyses Handbook (1990), Jet Propulsion Laboratory, D5703. Reliability Assurance Guidelines for Low Cost/Short Duration Missions (1995), Jet Propulsion Laboratory, NASA Technical Memorandum 4629. | This practice has been used on Magellan, NASA scatterometer, Microwave Limb Sounder, Galileo, Cassini | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
773 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Design Practice to Control Interference from Electrostatic Discharge (ESD) | Preferred Practice for Design & Test. ESD events can cause transient voltage spikes on sensitive circuits that can corrupt data, produce false commands, or cause system failure. Degradation of surface material can result from arcing or redeposition of material on other surfaces if precautions are not observed. Minimize the adverse effects of electrostatic discharge (ESD) on spacecraft by implementing the following three design practices: 1. Make all external surfaces of the spacecraft electrically conductive and grounded to the main structure. 2. Provide all internal metallic elements and other conductive elements with an “ESD conductive” path to the main structure. 3. Enclose all sensitive circuitry in an electrically conductive enclosure-- a “Faraday cage”. | ESD events can cause transient voltage spikes on sensitive circuits which can corrupt data, produce false commands, or cause system failure. Degradation of surface material can result from arcing or redeposition of material on other surfaces if precautions are not observed. | Minimize the adverse effects of electrostatic discharge (ESD) on spacecraft by implementing the following three design practices: Make all external surfaces of the spacecraft electrically conductive and grounded to the main structure. Provide all internal metallic elements and other conductive elements with an "ESD conductive" path to the main structure. Enclose all sensitive circuitry in an electrically conductive enclosure-- a "Faraday cage". | JPL | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1244; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Minimize the adverse effects of electrostatic discharge (ESD) on spacecraft by implementing the following three design practices: Make all external surfaces of the spacecraft electrically conductive and grounded to the main structure. Provide all internal metallic elements and other conductive elements with an "ESD conductive" path to the main structure. Enclose all sensitive circuitry in an electrically conductive enclosure-- a "Faraday cage". The first two practices should dissipate most electric charges before a difference in potential can become high enough to cause an ESD. If a discharge occurs, the third practice lowers the coupling to sensitive circuits, reducing the probability or severity of the interference. All external dielectric surfaces such as windows, radomes and solar panels are coated to make them slightly conductive without destroying their transparency to optical/IR/RF radiation. Cost and performance trade-offs must be made in order to select suitable materials for each application. The conductive layer should be less than 109 ohms per square and connected to structural ground. All internal metallic elements, greater than 3 cm2 in area or 25 cm in length, including unused wires in cables, connectors, circuit board traces, spot shields, and other conductive elements, have a conductive path to ground with a resistance less than 100 MW. Small metallic objects (< 3 cm2) may be ungrounded if grounding is not practical. Each metallic layer of thermal blankets is grounded to the main structure. All external metallic components are electrically connected to the common ground of the main structure. All electronics are enclosed in a Faraday cage shielded enclosure. External cabling outside of the Faraday cage are shielded by means of overshields with 360 degree backshells at the Faraday cage entry. Sensitive circuits should use independent, balanced wiring with each lead and its return twisted together. Filter all circuits coming into the Faraday cage; low-pass filters and transient suppressors are typical, but digital logic discriminators have also been used. Avoid the possibility of high differential voltages between components by connecting all conductive materials to a common ground. In the case of large structures, such as Space Station, surface charging can be controlled by use of an external ionizing plasma source. Since it is impractical to duplicate the space plasma environment, testing for ESD resorts to resistance measurement on one hand and circuit immunity to artificial discharges on the other hand. The requirements for each of these conditions depend on the spacecraft charging conditions anticipated for the particular orbit that the spacecraft will occupy. All spacecraft designers must consider space charging in the spacecraft design. Space charging arises when materials are immersed in an energetic space plasma. Different materials with different surface resistivities produce voltage gradients which can build up until the voltage breakdown limit is exceeded. When this occurs, a discharge is produced which causes transients in electrical circuitry and degradation or redeposition of material. References Purvis, C., Garrett, H., Whittlesey, A., Stevens, N. (1984), "Design Guidelines for Assessing and Controlling Spacecraft Charging Effects," NASA Technical Paper 2361. (This paper has an extensive bibliography.) Surface Charging/ESD Analysis, Reliability Preferred Practice No. PD-AP-1301 Thick Dielectric Charging/Internal Electrostatic Discharge (Draft), Reliability Preferred Guideline No. PD-AP-1316 | This practice has been used on Voyager, Magellan, Galileo, and Ocean Topographic Experiment (TOPEX). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
872 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Monitoring Processes for Cryogenic Transfer |  | A hazardous atmosphere can result in some environmental conditions when using overflow indications to monitor and control transfer operations of cryogenic fluids. | Monitoring of cryogenic transfer operations should be accomplished by a method that indicates directly the degree of completion of the transfer operation rather than monitoring for overflow indications indicating a full tank. | JSC | 03/06/2000 | On January 4, 1995, at approximately 8:50 a.m., two technicians at WSTF were overcome and collapsed from breathing in an oxygen deficient atmosphere that formed during shutdown operations following a transfer of liquid nitrogen (LN2) from a vendor supply tanker to a WSTF storage tanker. This transfer operation was normally controlled by monitoring a tanker vent line. Flow from this vent line indicated the tank was full, and the operation was suspended. There is also a liquid level indicator and a pressure gage on the WSTF tanker for monitoring purposes. On the morning of the mishap, conditions (high humidity and still air) existed which caused a larger than normal water vapor cloud to form during continuous venting of cold gaseous nitrogen (GN2) during the filling operation. This venting is required to keep the WSTF tanker at a lower pressure than the vendor tanker during the fill operation. The cloud prevented the normal visual monitoring of the vent line, the liquid level indicator, and the pressure gauge. The technicians, instead of positioning themselves to be able to monitor the vent line and gauges, located approximately 30 feet away from the tanker to both remove themselves from the heavy vapor cloud and also to remain out of the rain. During the operation, the technicians would periodically approach the tankers to monitor the liquid level indicator and the pressure gauge. The vent line was never observed due to being obscured by the vapor cloud. After about 50 minutes, the weather got worse and the technicians decided to suspend the operation due to weather and because they thought the tanker was nearly full. Data collected later showed that the tanker was completely full, and that LN2 was being released through the vent line instead of GN2. As the first technician attempted to close the vent and transfer valves, he was overcome and collapsed due to the lack of oxygen. The second technician, who was monitoring the activity, also was overcome and collapsed due to the lack of oxygen. A few moments later, vendor personnel approached and eventually remove both technicians from the area. Later investigation indicated that LN2 flow from the vent line coupled with adverse weather conditions created an oxygen deficient atmosphere in the area. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
871 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Safety Precautions in Operational Procedures |  | All credible unsafe conditions that may be encountered during the accomplishment of normal operating procedures must be anticipated, and alternate methods of action identified and included as appropriate. | Analyze operating procedures for credible hazards and/or environments that may create unsafe conditions. Provide alternate methods of procedure accomplishment to address these conditions and maintain operator safety during them. | JSC | 03/06/2000 | On January 4, 1995, at approximately 8:50 a.m., two technicians at WSTF were overcome and collapsed from breathing in an oxygen deficient atmosphere that formed during shutdown operations following a transfer of liquid nitrogen (LN2) from a vendor supply tanker to a WSTF storage tanker. This transfer operation was normally controlled by monitoring a tanker vent line. Flow from this vent line indicated the tank was full, and the operation was suspended. There is also a liquid level indicator and a pressure gage on the WSTF tanker for monitoring purposes. On the morning of the mishap, conditions (high humidity and still air) existed which caused a larger than normal water vapor cloud to form during continuous venting of cold gaseous nitrogen (GN2) during the filling operation. This venting is required to keep the WSTF tanker at a lower pressure than the vendor tanker during the fill operation. The cloud prevented the normal visual monitoring of the vent line, the liquid level indicator, and the pressure gauge. The technicians, instead of positioning themselves to be able to monitor the vent line and gauges, located approximately 30 feet away from the tanker to both remove themselves from the heavy vapor cloud and also to remain out of the rain. During the operation, the technicians would periodically approach the tankers to monitor the liquid level indicator and the pressure gauge. The vent line was never observed due to being obscured by the vapor cloud. After about 50 minutes, the weather got worse and the technicians decided to suspend the operation due to weather and because they thought the tanker was nearly full. Data collected later showed that the tanker was completely full, and that LN2 was being released through the vent line instead of GN2. As the first technician attempted to close the vent and transfer valves, he was overcome and collapsed due to the lack of oxygen. The second technician, who was monitoring the activity, also was overcome and collapsed due to the lack of oxygen. A few moments later, vendor personnel approached and eventually remove both technicians from the area. Later investigation indicated that LN2 flow from the vent line coupled with adverse weather conditions created an oxygen deficient atmosphere in the area. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
873 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Detailed Procedures on Critical Equipment |  | All work on critical equipment and its supporting interfaces (e.g., power, cooling) should follow clearly written, detailed procedures that are understood by all personnel who operate or work with that equipment. | Detailed procedures should be developed and used; and operations and maintenance personnel should be trained in power-up and power-down procedures. | JSC | 02/29/2000 | On May 16, 1994, an AMDAHL 5995M mainframe computer overheated at approximately 8:20 AM in the Software Production Facility (SPF) in Building 30 at JSC. Physical damage to the computer due to this overheat was estimated at $669,000. This overheat occurred due to an inadvertent miswiring of a circuit breaker after a routine power outage and maintenance of the breaker. The quality inspection failed to check for the proper rewiring of the circuit breaker. The miswiring caused a phase rotation of the power, which in turn caused fans cooling the AMDAHL 2550 to turn backwards. Power isolation and monitoring equipment that could have prevented any impact from the phase rotation was not properly utilized. This led to insufficient cooling of the AMDAHL 2550 which resulted in the overheat and subsequent damage. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
875 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Implementation of Sensors and Warning Devices to Detect Out-of-Tolerance Conditions |  | Malfunctions (including warnings and alarms) on critical equipment and its supporting interfaces require an appropriate and timely response by trained personnel capable of taking immediate action or countermeasures according to preplanned procedures. | All operators should be thoroughly trained on all equipment operations and potential malfunctions including troubleshooting procedures to clearly define actions to take for malfunctions. In addition, malfunctions that are hazardous to critical equipment or operator health and safety should be defined and "quick response" procedures developed and trained for these. Operational conditions that are potentially damaging to equipment should be identified and placards posted on the associated hardware. Sensors should be located such that they will detect the critical operational parameters under all credible malfunction conditions and environments. | JSC | 02/29/2000 | On May 16, 1994, an AMDAHL 5995M mainframe computer overheated at approximately 8:20 AM in the Software Production Facility (SPF) in Building 30 at JSC. Physical damage to the computer due to this overheat was estimated at $669,000. This overheat occurred due to an inadvertent miswiring of a circuit breaker after a routine power outage and maintenance of the breaker. The quality inspection failed to check for the proper rewiring of the circuit breaker. The miswiring caused a phase rotation of the power, which in turn caused fans cooling the AMDAHL 2550 to turn backwards. Power isolation and monitoring equipment that could have prevented any impact from the phase rotation was not properly utilized. This led to insufficient cooling of the AMDAHL 2550 which resulted in the overheat and subsequent damage. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
874 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Quality Inspection of Maintenance Work Performed on Critical Equipment |  | All operations and maintenance on critical equipment and its supporting interfaces (e.g., power, cooling) should be subject to a quality inspection by an inspector who understands the work done and who verifies the work is done correctly. | Quality inspection procedures and training should be developed to match the specific maintenance work being accomplished on critical equipment and its supporting interfaces. | JSC | 02/29/2000 | On May 16, 1994, an AMDAHL 5995M mainframe computer overheated at approximately 8:20 AM in the Software Production Facility (SPF) in Building 30 at JSC. Physical damage to the computer due to this overheat was estimated at $669,000. This overheat occurred due to an inadvertent miswiring of a circuit breaker after a routine power outage and maintenance of the breaker. The quality inspection failed to check for the proper rewiring of the circuit breaker. The miswiring caused a phase rotation of the power, which in turn caused fans cooling the AMDAHL 2550 to turn backwards. Power isolation and monitoring equipment that could have prevented any impact from the phase rotation was not properly utilized. This led to insufficient cooling of the AMDAHL 2550 which resulted in the overheat and subsequent damage. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/11/2000
766 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Reliability Considerations for Launch Vehicle Command Destruct Systems |  | Not adhering to the proven practices for the design, manufacture, and testing of the Command Destruct System could result in premature detonation of pyrotechnic devices which would terminate the SRB resulting in loss of mission, possible loss of crew, and possible injury and loss of life at the launch site. | Use built-in redundancies, safe and arm provisions, approved and qualified initiators and detonators, shaped charge development testing to collect empirical data for design (empirical testing), and fail-safe designs to achieve reliability in launch vehicle command destruct systems. | MSFC | 01/29/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1438 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. The benefits of implementing the practices spelled out herein are protection against inadvertent activation of the launch vehicle command destruct system, reliable activation and operation of the command destruct system in the event of vehicle malfunctions, and protection of the mission hardware and personnel prior to and during the launch. Implementation: Introduction: The Space Shuttle Command Destruct System (CDS) is a triplex configuration providing a redundant subsystem on the SRB. The CDS consists of RF receiving elements, dedicated power sources and pyrotechnics. When activated, the CDS terminates the thrust of the SRB by pyrotechnic charges that sever the Solid Rocket Motor (SRM) cases along 70 percent of their length. The SRB onboard command destruct system allows the Range Safety Officer to intentionally destroy the SRB in the event of flight path deviation, improper flight parameters, or inadvertent separations. The Command Destruct System consists of the components and quantities listed in Table 1. [D] Figure 1 is the SRB CDS Functional Diagram. [D] Ground commands arm the safe and arm (S&A) device approximately five minutes prior to SRB ignition. If destruct action is required, the nominal range safety destruct procedure will consist of energizing the quotarmquot command several times, application of a one second pause, then energizing the quotfirequot command several times or until the destruct action is accomplished. The fire command to the Pyrotechnic Initiator Controller (PIC) discharges its capacitor, igniting the NSD. The detonation from the NSD is propagated through the S&A device transfer charge and the CDF train to the linear shaped charge (LSC). The detonation output of the LSC cuts the case along 70 percent of the length of the Solid Rocket Motor causing destruction of the SRB. Reliability Considerations: The minimum overall system reliability goal for the Command Destruct System is 0.999 at a 95 percent confidence level. Some reliability considerations considered during design, development, qualification, and acceptance testing are listed below: Elimination of single point failures. Redundancy. Fail-safe functions. Personnel properly trained in handling, assembly, installation, and checkout of command destruct systems. Development testing, qualification testing, and, especially, acceptance of every pyrotechnic device lot manufactured are monitored by engineering and quality personnel. Adherence to the provisions of NHB 5300.4 (ID-2), quotSafety, Reliability, Maintainability, and Quality Provisions for the Space Shuttle Program.quot Redundant paths are verified by test. Electronics and cables are checked out after installation down to NSI installed in the NSD. NSD bridge wire resistance is verified after installation. Safe & Arm device function is verified after installation. Other reliability analysis such as Worst Case, Fault Tree, FMECA, Parts Stress, Single Event Effects, Thermal/Structural Strength, and Sneak Circuit Analysis should also be performed, where applicable. Design methods for reliable Command Destruct Systems are listed below: Separation of redundant equipment except the Range Safety Distributor, Hybrid Coupler, Safe and Arming Device, and dual systems mounted on the same mounting panel. Provide a fail-safe design for ascent critical functions. The Command Destruct System operates in a standby mode for ascent and is exempt from in-flight redundancy verification. The Command Destruct System electronics include sufficient instrumentation to provide self-diagnostic ground indicators except for the PIC which uses built-in test equipment for the ground checkout of the pyrotechnic electronics. Demating of electrical cables is not permitted except for the NSD. Redundant components susceptible to contamination or environmental failure are separated. Inadvertent electrical shorting due to debris is prevented by design. Design engineering and quality engineering review and approve manufacturing procedures and processes. Quality engineering also reviews and approves inspection criteria required to ensure that qualification and flight hardware are free of defects. Development testing, qualification testing, and acceptance testing are principal methods by which pyrotechnic devices are proven to meet design requirements and to meet the reliability levels necessary for manned launch vehicles. All test records and data are reviewed by NASA and prime contractor engineering and quality personnel. The Eastern Space and Missile Center Range Safety Officer's approval is required for Command Destruct System conceptual design, detailed design, qualification/acceptance test requirements, range prelaunch test requirements, test plans and procedures, installation and checkout procedures, failure corrective action, and launch approval. Technical Rationale: The design, manufacture, testing, and launching of the Command Destruct Systems have been proven over a period of more than 30 years. The Command Destruct Systems for the SRB have flown on the Space Shuttle for over 70 flights without a failure. References AFETRM 127-1: quotEastern Range Regulation,quot Range Safety Space Command, United States Air Force, June 30, 1993. NSTS 007700: quotSpace Shuttle Flight and Ground System Specification,quot Program Definition and Requirements, Volume X, Book 1, NASA, Johnson Space Center, Houston, TX, 77058, June 4, 1993. NSTS 08060: quotSpace Shuttle System Pyrotechnic Specification,quot NASA, Johnson Space Center, Houston, TX, 77508, February 11, 1994. 30A90506D: quotShuttle Range Safety Command Destruct System Specification,quot NASA, Marshall Space Flight Center, Marshall Space Flight Center, AL, 35812, June 5, 1989. 10MNL-0030: quotSolid Rocket Booster/External Tank Pyrotechnic System Handbook for Space Shuttle,quot Volume I and II, NASA, Marshall Space Flight Center, Marshall Space Flight Center, AL, 35812, July 14, 1989. | This practice has been used on Saturn I, IB, and V, External Tank prior to 1996, and Space Shuttle Solid Rocket Booster (SRB). | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
767 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Conducted and Radiated Emissions Design Requirements | Preferred Practice for Design & Test. Out-of-specification performance may occur during system EMC tests. The risk of higher cost and the impact on the schedule, late in the program, must be weighed against the cost of providing a reasonable design margin during the design phase of a program. Initially, the design requirements for each subsystem are established so that all non-functional emissions will be at least 9 Db below the emission specification limit. | Out-of-specification performance may occur during system EMC tests. The risk of higher cost and the impact on the schedule, late in the program, must be weighed against the cost of providing a reasonable design margin during the design phase of a program. | Initially, the design requirements for each subsystem are established so that all non-functional emissions will be at least 9 Db below the emission specification limit. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1225; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. By initially selecting a 9 Db margin, the probability of complying with the electromagnetic compatibility (EMC) specification during system test is high. Implementation Method: Radiated and conducted emission specifications established for the customer are based on overall theoretical requirements which will meet the system specifications. The following design practices for subsystems allow for measurement error, combined effects, and manufacturing tolerance. This assures that an adequate margin will be realized when the final system performance is evaluated. In those cases where an outside agency imposes the allowable emissions levels, the included margins must be taken into consideration so that excessive constraints are not applied. When a specific requirement is identified as a major cost driver for design, margin allocations should be reviewed for possible relief. Conducted Emissions: Out-of-specification conducted emission on power, control, and signal lines can usually be controlled by a low-pass filter to reduce or eliminate unnecessary high-order harmonics. On digital circuits, a compromise must be made between the need for square pulses and the suppression of high-order harmonics. Radiated Emissions: Radiated emission can be reduced by cancellation, cross polarization, or by either magnetic or electric field shielding. In some cases, radiated emission can be reduced by using a balanced design so that the external magnetic or electric fields are cancelled or cross-polarized at a particular sensor. Shielding can be added if the additional weight can be tolerated. Otherwise, increasing the separation distance between the emitter and a sensor may be adequate. Low frequency magnetic and electric field emissions must consider the inverse cube relation between amplitude and the separation between source and sensor in order to determine an adequate separation. Technical Rationale: By allowing a 9 Db margin at the design phase, there is sufficient tolerance to provide a high degree of confidence that the equipment will pass the system EMC tests. 9 Db is needed to account for the differences between idealized theory and practice plus the test margin. The test margin covers both manufacturing tolerance and measurement tolerance. | This practice has been used on Voyager, Magellan, Galileo, and Ocean Topographic Experiment (TOPEX). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
761 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Guideline for Developing Reliable Instrumentation for Aerospace Systems |  | Without applying a structured and disciplined approach to instrumentation system requirements and design throughout the system life cycle, there is increased risk of excessive costs and lower probability of meeting mission and science measurement needs. | The development of in-flight instrumentation, vehicle health management systems, and sensor systems for control and monitoring should be thoroughly integrated into the requirements generation, preliminary design, and early planning for payloads and space flight systems. Multi-disciplinary Product Development Teams (PDTs) must include instrumentation considerations at the very front end of the development process. This will allow maximum advantage to be gained from current and emerging technologies to provide both real time and postflight diagnostics that will reliably and consistently reflect the system's condition. The result will be improved vehicle and payload system reliability through accurate and well-planned access to performance information. Emphasis must be placed on early definition of instrumentation and measurement requirements to reduce the time and cost to develop reliable instrumentation systems and ensure mission success. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline number GD-ED-2215 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Very early consideration of instrumentation (Note: for purposes of this lesson, the term instrumentation refers only to sensor and signal conditioning subsystems and will not include the data management subsystem) requirements compatible with vehicle or payload system monitoring and control requirements will result in: (1) Choice of sensor technology and sensor hardware/software that is cost-effectively matched to specific vehicle environment, design, performance, and configuration requirements; (2) Up-front consideration of the effects of instrumentation system and sensor maintainability, calibration, and reliability during the operational phase over the specified lifetime; (3) Optimum sensor location, avoidance of failures due to vibration, shock, thermal and stress effects, efficient cable design and routing; and (4) Lower costs of instrumentation system integration due to well thought-out and preplanned designs that are less subject to change during the development process. Implementation: It has been the general practice in past programs and projects to conceive and design instrumentation systems and related sensors, hardware, and software well after requirements for the system have been established. Instrumentation considerations have frequently waited until well after the design of the parent hardware has been approved, and many times the instrumentation design has not been initiated until the initial test hardware is well into fabrication. In general, this practice has not been seriously detrimental to past programs because of the luxury of ample resources and schedule time to iterate the instrumentation configuration many times prior to flight. Furthermore, the technologies available were not as advanced as those becoming available in the present age of computer-aided analysis, engineering, design, testing, and manufacturing. New concurrent engineering methods and tools that are now available, and the use of integrated product engineering development teams allow instrumentation considerations, designs, and technologies to be introduced at the earlier phases of the project life cycle. Earlier consideration of instrumentation issues will result in greater efficiencies and more effective total instrumentation support of the space system development and flight operations. Background: There are three main purposes of instrumentation systems, (1) to perform measurements, (2) to provide for system control, and (3) to relay information. Measurements are needed to obtain information on system operation and the operational environment. Based upon this information, feedback and adjustments can be made to control loops to maintain system control. Finally, the information generated by the measurements must be processed and relayed from the operational system to data collection and analysis centers. Data processing and relay are outside the scope of this guideline and will not be discussed further. There are three types of measurements: (1) measurements for design, test, and evaluation; (2) measurements for calibration; and (3) measurements for control (Ref. 1). Each of these types of measurements impose unique requirements on the vehicle or payload instrumentation system. Science, design, test, and evaluation measurements seek to answer questions about a physical process or environment about which little or nothing is known. A key consideration in these types of measurements is the effect of the instrumentation system itself on the phenomenon being measured. Control measurements are made to ensure the process or system is working properly. This usually involves making adjustments in control loops so as to maintain an operating point within some acceptable range. Calibration measurements are made to characterize part of the instrumentation system, such as a sensor, in a known environment with specific boundary conditions. I. Key Instrumentation Considerations: There are a number of instrumentation issues that need to be addressed as early as possible in the system life cycle. The earlier these issues are addressed the more reliable the measurements, and thus the overall system, will be. Close communication and interaction among instrumentation engineers, system users, and system designers are essential if these issues are to be adequately addressed. These key issues are briefly discussed in the following paragraphs. A. What is the quotrealquot measurement requirement? Experience has shown that often the user does not state the real measurement requirement but rather an implementation. This must be avoided early-on as it results in limiting potential measurement solutions and affects reliability. A good question to ask to get at the core requirements is, quotIf you could only have one measurement, what would it be?quot In addition to the answer to this question, the type and purpose of each proposed measurement must be understood. B. Operating environment The environment in which a measurement must be made significantly impacts the selection of sensors and ultimately the reliability and accuracy of the resultant information. Examples of important environmental factors include vibro-acoustics, atmosphere, temperature, and pressure. C. Required accuracy and frequency response This is an area where significant tradeoffs and compromises must be worked out between the user and the instrumentation engineer. Since accuracy and frequency response of sensors are directly related to cost, it is incumbent on the instrumentation engineer to make program participants aware of the cost to the project of satisfying stated accuracy and frequency response requirements. Often, it will turn out that less stringent requirements in these areas can satisfy the quotrealquot requirements at significant cost avoidance to the project. D. Constraints There are a number of constraints with which the instrumentation system must comply. Some are limited resource allocations for things like size, power, weight, volume, and cost. Other constraints will arise with regard to possible locations for sensors and signal conditioners, and feasible routing for cables and connectors. All of these constraints must be dealt with in designing reliable instrumentation systems to meet user requirements. E. Maintainability/Reusability Instrumentation system components such as sensors, signal conditioners, and even cables and connectors are subject to failure. Requirements for access to these components to affect repairs will also impact the instrumentation system design for long-life missions. Related to maintainability are requirements for sensor checkout, calibration, and diagnostics which must also be factored into the instrumentation system design. Similarly, requirements for cleaning and refurbishment associated with reusable flight systems impact on the design. F. Electrical and mechanical interfaces Often early decisions are made on the avionics architecture and on the data management system which will impact the instrumentation system design. Such items as choice of flight computers and data bus standard will be driving requirements in selection of instrumentation system components. Likewise, specific requirements for mounting and other mechanical interfaces will affect instrumentation system design. II. Integrating Instrumentation System Design into the Project Life Cycle Instrumentation engineering is one of the engineering specialties which needs to be integrated into the overall system engineering process required to develop and operate reliable aerospace systems. The tendency has been to wait until the design phase of the life cycle before seriously addressing instrumentation requirements and issues. Often it is even later, even after the design is complete, before instrumentation is considered. When this occurs, it can result in less than optimum instrumentation solutions to engineering and science requirements. One consequence can be less reliable systems due to the inability to gather information on the true condition of the flight system in operation. An example of this problem can be seen in the Space Shuttle Main Engine (SSME) program at MSFC. Only after the High Pressure Fuel and Oxygen Turbopumps were designed did it come to light that the single most important measurement that the engineers wanted was turbine inlet temperature. However, because instrumentation considerations had not been addressed early enough, no provision had been made in the design to accommodate a sensor for this purpose, and it was deemed too costly to redesign the turbopump at that point in the program. A typical NASA flight system passes through several distinct phases in its life cycle as it proceeds from concept exploration to system disposal. NASA Management Instruction (NMI) 7120.4 (Ref. 2) and NASA Handbook (NHB) 7120.5 (Ref. 3) describe these phases and the associated activities and milestones associated with each. Figure 1 (Ref. 4) summarizes these phases and the major activities and outputs of each phase. [D] The appropriate instrumentation engineering activities for each phase are discussed in the following paragraphs. A. Phase A (Analysis Phase) This is a study phase in which mission needs are determined and preliminary concepts are explored. Project objectives, new technology requirements, and potential system concepts are developed and analyzed to determine the project feasibility and cost-effectiveness. Performance tradeoff analyses are conducted to refine the system concepts and to identify risk areas. A key activity in this phase is the definition of preliminary system requirements and the development of a Preliminary Program Plan. Early point designs and even configuration layouts are a product of this phase. Even in this earliest of project phases, instrumentation issues should be addressed. First, the instrumentation engineers should be involved in developing the preliminary system requirements to ensure the key considerations discussed in Section I above are addressed. Obviously, point designs and configuration layouts can have significant impacts on instrumentation concepts and solutions and need to be reviewed carefully. Armed with knowledge and understanding of the system requirements and objectives, the instrumentation engineers can begin to define both the purposes and types of measurements that will be needed and to develop preliminary instrumentation concepts. The instrumentation concepts, preliminary measurement definitions, sensor technology development needs (if any), instrumentation risk assessments, schedule and resource requirements should all be documented in a Preliminary Instrumentation Plan which should be an output of this project phase. Phase A ends upon approval of the Mission Need Statement. Instrumentation Guidelines for the Analysis Phase: Ensure user needs and mission requirements are understood by the instrumentation engineers. Ensure preliminary system requirements include appropriate instrumentation considerations. Prepare a Preliminary Instrumentation Plan that addresses instrumentation concepts, measurement definitions, sensor technology needs, risk areas, and resource requirements. Ensure the Preliminary Instrumentation Plan is reviewed by all program participants in conjunction with a Preliminary Requirements Review or other formal review. B. Definition and Preliminary Design Phase (Phase B) This phase accomplishes the refinement and baselining of system requirements, cost estimates, schedules, and risk assessments prior to final design and development. Alternative system concepts defined in Phase A are refined and a final selection is made. System analyses and simulations are conducted and further tradeoff analyses are made to refine system and support requirements. Preliminary manufacturing and test requirements are also defined and assessed in this phase. Key outputs of this phase include a baselined System Specification and a Preliminary Design Review (PDR) baseline. Instrumentation engineering involvement should increase in this phase with activities focused on influencing the system specifications and preliminary designs to facilitate reliable vehicle instrumentation and measurements. The Instrumentation Plan should be updated and baselined in this phase. Preliminary instrumentation system design and preparation of a preliminary Instrumentation Program & Command List (IP&CL) should be completed. The IP&CL is defined in MSFC-STD-1924 (Ref. 5). Instrumentation Guidelines for the Definition and Preliminary Design Phase: Ensure the System Specification, lower-level specifications, and the preliminary system design include all appropriate instrumentation considerations and requirements and satisfy user needs. Update and baseline the Instrumentation Plan which defines the instrumentation concept and design, measurement definitions, sensor technology needs, risk areas, and resource requirements. Ensure the Preliminary IP&CL accurately reflects the instrumentation system design and component selection. C. Design Phase (Phase C) In Phase C the detailed system design is completed and plans are refined for development, fabrication, verification and validation (V&V), and operations. Detailed subsystem design and performance specifications are baselined in this phase, as well as Interface Control Documents (ICDs). In addition, verification and validation requirements and specifications are finalized. This phase ends with the successful completion of the Critical Design Review (CDR). Instrumentation engineers should be intimately involved in this phase to ensure detailed designs are compatible with user needs and instrumentation requirements of the program. Detailed instrumentation system design and analyses will be completed and final selection made for all system components. Instrumentation Guidelines for the Detailed Design Phase: Ensure the detailed system and subsystem designs include all appropriate instrumentation considerations and requirements and satisfy user needs. Ensure the IP&CL accurately reflects the final instrumentation system design and component selection and is baselined after CDR. D. Development Phase (Phase D)/Operations Phase (Phase E) In Phase D the flight hardware and software are developed, manufactured/coded, verified, and qualified for flight operations. During this phase, prototype/protoflight hardware is developed and tested. This is followed by manufacture, integration, and verification and validation of the flight hardware and software. Finally, the flight system is checked out and launch and initial flight operations commence. Instrumentation engineers will be involved in the V&V effort, as well as vehicle checkout and flight operations. During Flight Operations (Phase E), the instrumentation engineers will be involved in evaluating and resolving on-orbit anomalies. Instrumentation Guidelines for the Development/Operations Phase: Document and evaluate on-orbit verification results and anomalies. Document lessons learned. Technical Rationale: Without reliable flight instrumentation systems, information needed to accomplish successful missions and document results will not be obtained. Increased emphasis in the early project phases on incorporating instrumentation considerations and requirements will help ensure NASA aerospace systems satisfy mission and science requirements. This guideline and its references provide project managers, chief engineers, and users with a set of instrumentation principles tailored to each phase of the system life cycle. Application of these principles should result in development of more reliable flight instrumentation, in less time, and at lower cost. References Stein, Peter K., quotThe Unified Approach to the Engineering of Measurement Systems for Test & Evaluation,quot 1992. NMI 7120.4, quotManagement of Major System Programs and Projects.quot NHB 7120.5, quotManagement of Major System Programs and Projects - Detailed Policies and Procedures.quot MSFC-HDBK-1912A, quotSystem Engineering Handbook,quot December 6, 1994. MSFC-STD-1924, quotStandard for Instrumentation Program and Command Lists (IP&CL),quot June 21, 1993. Reliability Preferred Practice PD-ED-1251, quotInstrumentation System Design and Installation for Launch Vehicles.quot |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
769 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Verification of RF Hardware Design Performance Early in the Design Phase | Preferred Practice for Design & Test. Once radio frequency (RF) hardware is delivered, it may be too late to select an alternative radio architecture or mitigate the impact of any constraints on radio performance. Analyses are performed early in the design of RF hardware to determine hardware-imposed limitations that affect radio performance. These limitations include distortion, bandwidth constraints, transfer function non-linearity, non-zero rise and fall transition time, and signal-to-noise ratio (SNR) degradation. Performance evaluation is a concern because RF hardware performance is sensitive to thermal and other environmental conditions, and reliability testing is constrained by RF temperature limitations. | The performance of the delivered product may be compromised if the hardware imposed limitations are not evaluated early in the design phase. Once the hardware is delivered, it is too late to select an alternative radio architecture, and there are few opportunities to mitigate the impact of any constraints on radio performance. Lacking insight into RF hardware characteristics, test engineers may waste valuable engineering hours determining the basis for the variance between expected and observed performance. For flight projects, costly problem/failure reports and project waivers will likely be processed due to the lack of an early understanding of hardware limitations. | Analyses are performed early in the design of radio frequency (RF) hardware to determine hardware imposed limitations which affect radio performance. These limitations include distortion, bandwidth constraints, transfer function non-linearity, non-zero rise and fall transition time, and signal-to-noise ratio (SNR) degradation. The effects of these hardware performance impediments are measured and recorded. Performance evaluation is a reliability concern because RF hardware performance is sensitive to thermal and other environmental conditions, and reliability testing is constrained by RF temperature limitations. | JPL | 01/29/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1435 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Identification of hardware-imposed limitations on RF subsystem performance permits designers to evaluate a selected radio technology or architecture against system requirements. In the test phase of the reliability assurance program, it also helps engineers to understand performance characteristics they encounter during testing. RF modeling and verification provides for designed-in reliability in accordance with NASA's project streamlining policy. Implementation Method: For each major telecommunication function (channel) such as carrier tracking, command demodulation, two-way ranging, differential one-way ranging, and downlink telemetry, generate a model which includes each of the major sources of performance-limiting characteristics. This simulation of major hardware limitations should accurately represent their effect on RF performance. These effects may include band-limiting, non-linearities, non-zero rise and fall times, and SNR degradations. Quantify the potential impact of these limitations on ability to meet mission uplink and downlink requirements. For example, the downlink telemetry function was analyzed for the Cassini radio frequency subsystem (RFS). The analysis was performed in eight steps, including development of: Distortion definitions for trapezoidal telemetry data waveforms. Block diagram for simulating an ideal telemetry control unit (TCU) telemetry subcarrier modulator, as shown in Figure 1. [D] Block diagram for converting ideal random data waveforms into trapezoidal random data waveforms. Block diagram for simulating an ideal linear phase modulator. Block diagram for simulating a non-ideal linear carrier phase modulator. Block diagram of a phase demodulator. Signal to distortion ratio (SDR) estimator block. Complete telemetry channel model. Strong signals were analyzed; no noise of any type was included. The specific products of this Cassini RFS analysis were: Development of a model of the telemetry channel which includes the nonzero rise and fall times of the telemetry waveforms, the non-linearities in the X-band downlink carrier phase modulator, and the non-linearities in the ground receiver demodulation process. Characterization of the distortion introduced in the telemetry signal by the nonzero rise and fall times. Characterization of the distortion of the demodulated actual telemetry waveform at the ground receiver output due to the combined effect of the nonzero transition times and the non-linearities in the carrier phase modulator and phase modulator. The modeled parameters were tabulated to verify compliance with Cassini downlink mission requirements. Technical Rationale: Early in the design phase, when the radio architecture and design concept are selected, it is necessary to understand assembly-level hardware limitations and their effect on radio performance. Given the subsystem complexity, it is often difficult to pinpoint the exact cause of unexpected test results once the subsystem has been integrated. References quotRFS Downlink Telemetry Analysis Report,quot Robert Mueller (Jet Propulsion Laboratory) IOM 3367-93-392 of 8/24/93, Cassini Project. Spurious Radiated Interference Awareness, Reliability Preferred Practice No. PD-AP-1310 | This practice has been used on Voyager, Galileo, and Cassini projects. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
768 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Thermal Design Practices for Electronic Assemblies | Preferred Practice for Design & Test. Designs that do not follow proper thermal design practices are subject to failure and loss of the mission or science data. Ensure that thermal design practices for electronic assemblies will meet the requirements of the mission's ground and flight environmental conditions, with an adequate margin. Special emphasis should be placed on limiting the junction temperature of all active components. Proper thermal design practices take into consideration the need for ease of operation and repairability to enhance overall system reliability. | Designs that do not follow proper thermal design practices are subject to failure and loss of the mission or science data. | Insure that thermal design practices for electronic assemblies will meet the requirements of the combined ground and flight environmental conditions defined by the spacecraft mission. Special emphasis should be placed on limiting the junction temperature of all active components. Proper thermal design practices take into consideration the need for ease of operation and repairability to enhance overall system reliability. The environmental conditions that the spacecraft encounters, both on the ground and in flight, are designed to include adequate margin. The use of proper thermal design practices ensures that the assemblies will survive the expected environmental conditions. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1226; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Constraining the electronic component junction temperature through proper design practices will ensure that the assemblies can withstand the mission's environmental conditions. Implementation Method: Sound thermal design practices are followed from the conceptual stage through the final design stage. A system for doing thermal design that takes into account the materials, fabrication methods and processes from the conceptual stage will increase the overall design flexibility as well as the reliability. This practice is primarily coupled to the JPL dual shear plate packaging approach. Packaging design reviews should be conducted with technical personnel participating. The results of these packaging reviews should then be summarized in the formal subsystem Preliminary Design Review and Critical Design Review. Electronic components that require higher thermal conductance than normal assembly methods can support should be mounted with thermally conductive material. High power dissipation axial lead components can be cooled through a thermal window in the printed wiring board providing a heat path directly to the chassis. Conductive heat sinks are also used to maintain the electronic components within their derated temperature range. Selection of the proper high power parts is very important to the success of the mission. Design of the system should avoid using high power analog devices as much as possible. Stud mount or screw mount devices should be used whenever possible. High power TO-type metal can devices should be mounted and bonded top down on the board or chassis using qualified thermal adhesives coupled to an efficient method for removing the excess heat. Placement of parts is as important as the selection. Good thermal design for electronic boards should provide the heat flow toward the mounting edge of the module. The end plates are considered as structural support only and not included as part of the thermal path. The path to the metal chassis or thermal control surface should be as short as possible. Surfaces and finishes should be selected to provide low resistant thermal paths through interfaces. Spacecraft or instruments used in low earth orbit or in the space shuttle payload bay should have a thermal control finish that is designed to withstand erosion from an atomic-oxygen environment. Technical Rationale: A spacecraft chassis and its electronic subassemblies are designed to meet the environmental conditions encountered by the given mission. Thermal analyses of heat dissipation, junction temperature control, and the elimination of hot spots during the design phase should be provided to ensure proper thermal design. Special emphasis is placed on reducing the junction temperatures of all semiconductors to safe levels throughout the mission. Related Practices: Part Junction Temperature, Reliability Preferred Practice No. PD-ED-1204 Thermal Test Levels/Durations, Reliability Preferred Practice No. PT-TE-1404 Thermographic Mapping of PC Boards, Reliability Preferred Practice No. PT-TE-1403 Thermal Analysis of Electronic Assemblies to the Piece Part Level, Reliability Preferred Practice No. PD-AP-1306 | This practice has been used on Voyager, Magellan, Galileo. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
770 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | RF Breakdown Characterization | Preferred Practice for Design & Test. Flight hardware may be damaged if operated at critical pressure or in a vacuum above the RF power levels at which the RF breakdown or multipaction phenomena occur. The damage may not be readily observable from external inspection of the hardware. Tests are performed to verify that radio frequency (RF) equipment, such as receivers, transmitters, diplexers, isolators, RF cables, and connectors, can operate without damage or degradation. Reliability assurance is necessary in both a vacuum environment and at critical pressure with adequate demonstrated margins above the expected operating RF signal levels. | The hardware may be damaged if operated at critical pressure or in a vacuum above the RF power levels at which the RF breakdown or multipaction phenomena occur. The damage may not be readily observable from external inspection of the hardware. | Tests are performed to verify that radio frequency (RF) equipment, such as receivers, transmitters, diplexers, isolators, RF cables, and connectors, can operate without damage or degradation. Reliability assurance is necessary in both a vacuum environment and at critical pressure with adequate demonstrated margins above the expected operating RF signal levels. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1432 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Knowledge of the dielectric breakdown characteristics of RF devices at low pressures or in a near vacuum environment can be used to protect sensitive flight equipment. RF breakdown is a concern because of the low, near-vacuum pressures at which spacecraft are tested and operated. RF breakdown testing is conducted to establish hardware resilience to the application of out-of-spec input signal levels, signal reflections due to mismatches at hardware interfaces, inadvertent evacuation of vacuum chambers during RF input, application of RF signals during the ascent phase of the spacecraft launch vehicle, etc. Implementation Method: Provide the expected signal level, plus an additional 6 dB over the expected operating frequency range, to the input of the device under test while monitoring the output frequency. Reduce the atmospheric pressure from ambient to vacuum at the controlled rate specified in the test plan. After dwelling at vacuum for a period of time sufficient to monitor the performance of the unit under test, increase the atmospheric pressure from vacuum back to ambient at a controlled rate. After the test has been completed, inspect the test article for damage. Hardware damage is manifested by a change in the monitored RF performance during the test, or by visible indicators such as burn marks on output connectors. If neither indication is evident, the equipment is considered to have passed the test. However, if the RF output signal dips or degrades, or external burn marks are seen, the test article is dismantled and inspected for internal burn marks in the vicinity of RF conductors. The typical corrective action is to redesign the equipment to provide wider gaps between RF signal conductors. Technical Rationale: Electrical damage to equipment or devices can occur due to dielectric breakdown. RF energy produces stress on the electrons in the gaseous medium between two electrodes situated within an electrical field. The RF breakdown phenomenon occurs at low pressure when an RF field generates a sufficiently high voltage potential for the gas in the gap between two electrodes to ionize and transition from an insulator to a conductor. This happens when the production of electrons in the intermediary gas exceeds the removal of electrons. The two main mechanisms are: Ionization Breakdown: Ionization by electron collision is the dominant electron production mechanism. Ionization of the gas by electron collision happens at higher ambient pressures when the electron mean free path becomes shorter than the electron separation distance. Multipaction: Multipaction, or secondary electron emission from the electrodes, occurs when the ambient pressure is sufficiently low that the electron mean free path is longer than the electron separation distance. Multipaction is observed at pressures below 10-2 Torr. As a result, damage can occur in the small gaps between conductive or dielectric surfaces which may result in serious degradation of hardware performance. To establish the available margins for safe operation of the hardware prior to spacecraft-level testing or launch, validate the RF power levels below which no damage will occur either in vacuum or at critical pressure. References Woo, R., "Final Report on RF Voltage Breakdown in Coaxial Transmission Lines," NASA Technical Report No. 32-1500, October 1, 1970. Radiated Susceptibility System Verification, Reliability Preferred Practice No. PD-TE-1416. | This practice has been used on Voyager, Galileo, Cassini | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
763 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Systems Test Considerations for High Performance Liquid Propellant Rocket Engines |  | Failure to conduct integrated ground system tests of launch vehicle propulsion systems could result in the inability to locate and correct critical interface and launch preparation problems that could cause launch delays, hazards to personnel, loss of the mission, and/or loss of the crew. | To achieve high overall liquid rocket fueled propulsion system reliability, conduct a comprehensive test program that verifies and validates the liquid rocket engine's operation as it interacts and interfaces with other elements of the propulsion system, (i.e., structures, propellant feed systems, propellant tankage, and control electronics). | MSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1439 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Experience in systems testing of the Space Shuttle Main Engine has shown that integrated propulsion system testing, (1) provides the necessary test data for "model basing," thus enhancing the reliability of system analysis techniques; (2) integrates vehicle hardware, ground hardware, and procedures for propellant loading, safing, and firing operations; (3) provides a resource for determining stage/engine design margins, establishing redlines, developing procedures and time lines, and confirming extrapolated criteria used in engine development; (4) identifies potential risks for catastrophic flight failure, vehicle hardware damage, and launch complex damage; and (5) identifies potential risks of a delayed initial launch and subsequent launches. Implementation Method: I. Background: The Space Shuttle Main Propulsion Test Article (MPTA) program was conducted at NASA's Stennis Space Center test site in Mississippi. The program involved NASA and Space Shuttle element contractors. The tests included an orbiter aft fuselage with three Space Shuttle Main Engines, an External Tank, and related ground and flight support equipment. Three non-firing tests and twelve combination development/verification firings met planned pretest objectives. The main propulsion test article was of a flight configuration with a few practical exceptions. External Tank insulation was of non-flight configuration. The auxiliary power unit was simulated by a ground powered hydraulic system. The Shuttle Avionics Test Set was used for propulsion system control rather than flight computers. A special load bearing structure was provided on the test stand to react against the engine's thrust. Non-flight hardware was used for payload bay purge into the aft compartment, propellant loading, ground umbilical disconnects, and some Ground Support Equipment consoles. II. Propulsion System Testing Twenty hot-firing attempts were required to meet the requirements of the 12 test series. Hot firing aborts were distributed throughout the 20 firing attempts, although the frequency of occurrence decreased after the sixth test series or after 50 percent of the test program was completed. Twenty-six terminal counts were required. Fourteen of these were required during the first six firing attempts. Hydrogen leakage within the aft compartment occurred on 12 tests. Two tests experienced high leaks. The degree of severity of some of the test failures underscores both the risk involved in propulsion system development and the absolute necessity of this type of testing in order to avoid and eliminate these types of failures during a flight mission. For example, fires occurred in nine firings. Eight of the nine fires resulted from engine discrepancies. Four of the fires at the vehicle base were typical of main fuel valve leaks through the engine after shutdown. One aft compartment fire resulted in extensive hardware damage. Two external fires produced significant damage to the vehicle and facility, particularly to the instrumentation. III. Changes and Modifications Brought About by the Main Propulsion Test Article (MPTA) Program The important issues that were addressed in the Space Shuttle Program to enhance the reliability, safety, and performance of the vehicle by MPTA testing were (1) unworkable designs and procedures were made workable by changes and then verified, (2) workable designs and procedures, for which adjustments to achieve acceptance were initially anticipated, were tested and the adjustments were accomplished. Many action items resulted and were resolved in each test series. Table 1 is an example listing of some of the most important action items that resulted from the propellant loading test, an early test where there was not a hot firing. Thirty to forty similar actions from a hot firing test were not unusual. Table 1. Example Action Items From Engine System Testing Review LH2 high point feedline liquid level sensor operation during propellant load test and repair. Review the need for redundancy. Determine the cause of tripped circuit breaker for LH2 recirculation pump #2. Determine requirements for a backup GHe injection system for the LOX antigeyser system operation Review the system requirements and reactivate MEC backup power. Provide necessary engineering to connect the KSC hazardous gas detection system to the LH2 vent system. Perform special cryogenic test of LOX and LH2 auxiliary dump valves using a solenoid actuated system as well as the existing pressure control actuation system and recommend system changes required to improve valve performance Review the need for changing the 1/8" sample line on the bottom of the LH2 tank to 1/4" or larger line to facilitate tank sampling and verification of purge procedures. Testing identified oversights which could have resulted in serious consequences under differing circumstances later in the development program. For example, design and manufacturing methods were changed to prevent the release of large hydrogen quantities as a result of main fuel valve structural failure. Design changes were made to prevent fuel preburner burn-through and associated engine software changes were made to facilitate automated prevalve closure under all failure conditions. Manual closure was delayed under some failure conditions until the prevalve benefits were seriously compromised. Changes to software corrected this anomaly. Procedures for unloading oxygen from the ET/Orbiter were corrected to prevent serious pressure surges within the facility hardware. The tests identified the necessity to locate launch facility igniters to burn released raw hydrogen at engine start. The Space Shuttle MPTA testing, as well as testing of previous launch vehicle integrated propulsion systems, resulted in preferred practices that will ensure reliable performance if conscientiously applied. Preferred practices are summarized in Table 2. Table 2. Improved Procedures Integrated testing is conducted to verify the performance of the feed system pressure drops, pressure surges, fluid-hammer responses, and resonances. Mixing of incompatible and hazardous substances in fluid systems are precluded. Contamination is excluded from contamination-sensitive systems. Actual environments, conditions, and designs are simulated. Margins are demonstrated during subsystem or system level tests. Test plans and results are fully documented. Stainless steel tubing and control lines are used for test facilities. Fuel and oxidizer prevalves are used in test facilities, and safe engine shutoff by prevalve closure is demonstrated in a subsystem test prior to propulsion system testing. Thermal and environmental controls of propulsion systems components are provided to prevent freezing, loss of lubrication, and collection of hazardous gases. An emergency source of ground power is provided to terminate the test in the event of a ground power loss. Provisions for pressure relief, flow diversion and control during chill down, and protection against geysering during propellant loading are designed into the test facilities' propellant feed system. Reliable hazardous gas detection and measuring systems and rapid response leak detectors are used for integrated propulsion system firing programs and pre-flight operations. Fire detection, fire protection capability, and internal protective neutralizing purges are used in static test programs, and are evaluated for launch site operations. Heat flux at the vehicle base is measured to determine the relative contributions of convective and radiative heating. Meticulous planning, training, and work control is employed in integrated propulsion system ground tests. Recirculation of rocket engine plume low energy gases into the vehicle base may be a predominant heat source for clustered engine vehicles. Heat flux measurements from ground test programs to determine the relative contributions of convective and radiative heating and analytical methods developed to compensate for flight altitudes assist in establishing design requirements. Meticulous planning, training, and work control is employed in integrated propulsion system ground tests. Specific preplanned and measured personnel training and demonstration of qualifications is a prerequisite for reliable and repeatable success. Steps to assure effective shift change communications and the use of only experienced and qualified personnel is required. A process where both contractor and government safety personnel perform spot checks on all hazardous work control documentation and operations is essential. IV. Other Related Development and Verification Testing In addition to integrated systems ground tests such as those performed on the Space Shuttle MPTA, structural test articles were built and tested, approach and landing tests were performed, an all-up hydraulic simulator Flight control Hydraulic Laboratory was developed and used, a Mated Vehicle Ground Vibration Test program was conducted, a Shuttle Avionics Integrated Laboratory was (and is) used, along with a Hydraulic Simulation Laboratory, for software verification prior to launch, and full scale external tank terminal drain tests were conducted. Extensive development testing was performed at KSC with the flight vehicle prior to the first launch to improve propellant loading procedures and to resolve other launch site/vehicle interface problems. Due to a thermal protection system failure on the External Tank and the desire to increase onboard propellant mass, several unplanned propellant loading tests were conducted both with the MPTA and with the flight vehicle at KSC. Technical Rationale: Several decades of integrated ground testing of launch vehicle propulsion systems, culminating in the MPTA Testing for the Space Shuttle Program, have proven that this type of testing is essential to perfect the interface between major hardware and software elements and to develop a reliable integrated launch vehicle propulsion system. The test programs themselves have shown that malfunctions, delays, and failures would be unacceptable in a flight situation. The successful performance of the Space Shuttle Main Propulsion System is attributable in great measure to the successful conduct of this series of ground tests and to the corrective actions that were taken to avoid failures. References "Advanced NSTS Propulsion System Verification Study," Space Transportation Systems Division, Huntsville Operations, Rockwell International, July 31, 1989. "History of MPT Test Program," Space Transportation Systems Division, Huntsville Operations, Rockwell International, February 9, 1986. "Main Propulsion System Testing Tanking Test History," Space Transportation Systems Division, Huntsville Operations, Rockwell International, July 1983. Quick-Look Test Reports for: MPT-S1-001, MPT-S1-002, MPT-S2-001, MPT-S3-001, MPT-S4-001, MPT-5A, MPT-5, MPT-6-001, MPT-6-02, MPT-6-03, MPT-SF7-01, MPT-SF7-02, MPT-SF8, MPT-9-01, MPT-9-02, MPT-10-01, MPT-11-001, MPT-11-02, MPT-12; Transportation Systems Division, Huntsville Operations, Rockwell International, 1978 thru 1981. | This practice has been used on Space Shuttle Main Engine (SSME), and Main Propulsion Test Article (MPTA) testing at MSFC, Rocketdyne, and Stennis Space Center. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
762 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Systems Design Analysis Applied To Launch Vehicle Configurations |  | Failure to effectively use the methods and tools described in this practice could result in excessive project development time or cost, and failure to attain the highest achievable reliability. | Use design management improvements such as matrix methods, quality techniques, and life cycle cost analyses in a systematic approach to systems analysis. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1230; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. The use of advanced design management methods in each program phase of major launch vehicle developments will maximize reliability and minimize cost overruns. Significant improvements in user satisfaction, error-free performance, and operational effectiveness can be achieved through the use of these methods. Implementation Method: Introduction: As emphasis in the aerospace industry shifts from maximum performance to low life cycle cost and high reliability, the rate of major technological design advancement is giving way to design management improvements. Common to these evolving improvements are the principles and tools of total quality management as applied to systems design analysis. This practice reviews successful systems engineering methodology as it applies to engineering design analyses for launch vehicles, and identifies total quality management applications that provide reliable, low cost aerospace designs. Since designing to high reliability can be correlated to reductions in the long-term cost of failures and spares, cost emerges as the systems common denominator. Systems management, systems design, and other systems approaches are well-established processes in the aerospace communities for developing all or any part of large, complex systems. The systems design process provides an orderly transformation of mission objectives into a detailed system design through three continuous and correlated phases: concept formulation, definition, and design. Effective use of these design phases has advanced design practice from an earlier single option procedure to the development of multiple options for trading and selecting optimum performance of mission systems. A total system decomposes into tiers of systems, elements, and components throughout the concept formulation, definition, and design phases. Each tier decomposes further into design parameter tasks which expand and interact with systems, elements, or components of the respective tier. Tasks identify design parameter requirements, develop design options to satisfy requirements, perform trades, and formulate criteria by which the best option leading to final design, specifications and plans can be selected. Total quality management procedures consisting of matrix methods, quality techniques, and life cycle cost analyses can be applied within the systems design analysis process throughout all design phases to achieve the simultaneous goals of high reliability and low life-cycle costs. Matrix Methods: A system is a set of parts whose behavior depends on the behavior of other parts. The need to flow scheduled information in a complex system often results in decisions based on limited analyses and understanding of user requirements and the complex relationship among interacting systems. Matrix methods are used to make these relationships more orderly, visible, and understandable. While the work breakdown structure (WBS) is a hierarchical relationship, it is still one-dimensional and, as such, cannot depict the many interactions between a system's subsystems, components, and parts. Matrices, however, can be multidimensional, and can interact with each other in much the same way they do in a relational data base. As an example, Figure 1 shows a multidimensional matrix progression for payload and launch vehicle subsystem analysis. Payload requirements, listed as rows in matrix 1(a), are determined by the characteristics of payload packages A, B, C, or D, which are arranged in columns. Each payload package, transferred to rows in matrix 1(b), can be accommodated by selected vehicle concepts arranged in columns E, F, G, and H. The varying vehicle parameters of each of the vehicle concepts can be displayed in a third matrix 1(c), showing the concept's impact on each launch vehicle system. In a three-dimensional matrix, shown on 1(d), the impact on each system element can be assessed. These matrices, which can progress down further into components and parts, permit interactive assessment of requirements flow-down and buildup as the design evolves for a launch vehicle that can accommodate a family of payloads. This arrangement is uniquely adaptable to computer-aided analysis. [D] Quality Techniques: Typical quality techniques applicable to systems design phases are quality leverage, quality function deployment, concurrent engineering, and Pareto's principle. Quality leverage, as shown on Figure 2, is greater during the earlier phases of a project. The earlier the control of objectives, the more timely and efficient are the solutions and modifications. [D]Concurrent or simultaneous systems engineering is a team effort in which all essential disciplines participate in the analysis and selection of concepts, components, materials, manufacturing processes, and major operations. Concurrent engineering is initiated during the concept phase and may expand and branch into systems and element integration working groups as required during the design phases. Team success depends on the adoption of the best available practices, avoidance of previously unsuccessful practices, and on a creative environment fostered by the team's technical leadership. Pareto's principle observes that 20 percent of parameters cause 80 percent of results. A reasonable approach for setting priorities to improve products or resolve problems is to first address the top 20 percent of the most significant parameters. These parameters are identified through histograms of their relative sensitivities to goals, e.g., ideal performance and lowest cost. The principle may also help specify hierarchic reliabilities. Life Cycle Cost Analyses: While user requirements and their accommodations represent one side of the balance, cost to implement them represents the other weighing pan. Judging from past projects, cost goals have not been achieved too well by the space industry. A major overrun cause is stretching the program to match fiscal appropriations. But aside from programmatics, designers have a unique responsibility to minimize overruns by completing design analyses at each design phase, controlling requirements buildup through all design phases, and reducing sources of engineering bottlenecks. The cheapest design changes are early paper changes. Cost models are the mechanisms for assessing trades and for tracking and controlling requirements buildup. They are initiated in the concept phase and expanded through all phases and levels of solutions. Models provide the basis for identifying cost driving requirements (Pareto's principle) and sensitivities in support of exploring innovative methods and concepts for reducing cost or for assessing vehicle evolution requirements. They provide the source and basis for making initial high leverage cost decisions and for setting development priorities on critical tasks. Cost models serve to formulate budget controls, detect cost overruns, and pace efforts relative to prevailing funds. Good cost estimates throughout the systems design analysis are the balance and enforcers of successful projects. Design Phases: The analytical design tools and principles described in the preceding paragraphs are used throughout the engineering analysis process with increasing intensity as greater detail is generated about the final product. In cost-constrained environments, the analytical tools and principles should be used to derive specifications and requirements in a quotreverse-engineeringquot process which designs the system to a life cycle cost target. The following paragraphs describe the activities in each phase that will result in the best design product. The concept phase is a first-order activity having the greatest quality leverage and, perhaps, is the most critical for the success of the mission. It is first and foremost a marketing phase which analyzes promising demands and competition for access to and for operation in space. It identifies a potential class of user needs, and it scopes missions within doable schedules and costs. Results of this phase are a set of select, top-level design specifications of customer needs and mission concepts to satisfy them. It includes a comprehensive set of mission requirements and constraints; first-order definition of vehicle configuration, systems, and elements; operation scenarios; and a basis for estimating costs. Subsequent phases peel the systems and elements to lower hierarchies, and expand the systems process of requirements, solutions, and selections. The definition phase is a detailed continuation of the concept process in identifying design parameters and requirements of the selected vehicle concept, and in developing solution options and selection criteria leading to a vehicle configuration and to system, element, and component preliminary designs. Results encompass a detailed definition of total vehicle systems and system elements including flight hardware, support equipment, software, and personnel, and the complete operational use definition, configuration description, preliminary design, and systems operational plans. Requirements identified in this phase are documented as vehicle specifications. A total life cycle cost of elements is also required. Concurrent engineering teams develop selection criteria and select and verify solutions. Teams include flight, propulsion, structures, avionics and facilities systems, and should have representation from the mass properties, reliability, manufacturing, verification, operations, safety, and costing disciplines. The design phase is the final systems analysis phase and perhaps the most consequential because its detailed design must fit and function as an integrated whole. It is also in the realm of lowest design quality leverage. This phase must proceed with detailed bottoms-up costing adjustments. The systems analysis must penetrate all final component designs for compliance with all tiers of specifications and requirements, and to amend emanating deficiencies through relevant upstream design phases. It must assess and assure that integration conflicts and issues are identified and resolved through all levels of components and systems. It must further analyze and modify detailed component designs and their integrations for (1) high quality performance, (2) manufacture, (3) verification, and (4) operations at lowest cost. Technical Rationale: Many years of experience in developing launch vehicles, propulsion systems, and payloads, have been combined with emerging design management techniques to formulate a rigorous methodology for developing low cost, high reliability, launch vehicle for space applications. Greater detail in employing this methodology than presented here can be found in the references, and in the recent classic literature on total quality management, project management, and systems engineering. Conscientious application of these latest methods, coupled with the use of emerging computer-based analysis and simulation tools, cannot only improve product reliability and cost effectiveness, but also reduce the cost and time required for the design process itself. References Ryan, Robert, and Verderaine, V.: quotSystem Design Analysis Applied to Launch Vehicle Configuration,quot NASA Technical Paper #3326, Marshall Space Flight Center, Alabama, 1993. Steward, D.V.: quotSystems Analysis and Management,quot Petrocelli Books, Inc., New York, 1981. Blanchard, Benjamin S.: quotSystem Engineering Management,quot John Wiley & Sons, Inc., New York, 1991. Hopkins, J.: quotApproaches to Reduced Launch Operations Costs,quot SAE 901877, Aerospace Technical Conference, October 1990. Rutledge, William S.: quotLaunch Vehicle Cost Trends,quot Aerospace America, June 1994. | This practice has been used on Saturn I, IB and V, Space Shuttle Main Engine (SSME), Space Shuttle External Tank (ET), Space Shuttle Solid Rocket Booster (SRB), Hubble Space Telescope (HST), High Energy Astronomy Observatory (HEAO), Lunar Roving Vehicle (LRV), Skylab, and many others. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
764 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Controlling Stress Corrosion Cracking in Aerospace Applications |  | Failure to adhere to proven criteria for controlling SCC could result in hardware failure, which could result in schedule slippages, excessive resource expenditures, shortened mission life, mission failure, and, in extreme cases, loss of life. | This practice presents considerations that should be evaluated and applied concerning stress corrosion and subsequent crack propagation in mechanical devices, structural devices, and related components used in aerospace applications. Material selection, heat treat methods, fabrication methodology, testing regimes, and loading path assessments are presented as methods to reduce the potential for stress corrosion cracking in a material's operational environment. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1227; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Selection of materials, heat treating methods, fabrication methodologies, testing regimes, and loading paths that are not susceptible to stress corrosion cracking will promote fewer failures due to Stress Corrosion Cracking (SCC) and will eliminate downtime due to the change-out of components. Implementation: Numerous materials have been tested for susceptibility to SCC in a 3.5 percent NaCl alternate immersion bath, a 5 percent NaCl salt fog cabinet and a 90-100 percent relative humidity cabinet. These tests resulted in the development of a specification on Design Criteria for Controlling Stress Corrosion (Reference 3). The information contained in the specification is based upon laboratory tests in which specimens were either sprayed with salt water or periodically immersed and withdrawn; by exposure of the specimen to simulated seacoast or mild industrial environments; and by service experience with fabricated hardware. This specification also lists materials that have a high resistance, a moderate resistance, or a low resistance to SCC. MSFC's Material Selection List for Space Hardware (Reference 4) also lists materials that have a high resistance to SCC. [D] [D] [D] To avoid failure, the tensile stress in service must be maintained at a safe level. Since stresses are additive, all sources of stress (see Table 1) must be considered to ensure that the threshold stress (the stress level which will result in a failure if stress corrosion is present) is not exceeded. There is not an absolute threshold stress for stress corrosion as there is with other material properties. Therefore, estimates of the stress corrosion threshold for a specific service application must be determined for each alloy and heat treatment by using a test piece, a stressing procedure, and a corrosive environment that are appropriate for the material's intended application. A simplified stress corrosion test fixture with a round tensile specimen installed is illustrated on Figure 1 in a simulated corrosion environment. A masking material is applied to the test fixture to ensure that the specimen alone is exposed to the corrosive environment. The tensile specimen is stressed to a desired level (typically 25, 50, 75 or 90 percent yield strength). The specimen is then submerged in a 3.5 percent NaCl alternate immersion bath, in a 5 percent NaCl salt spray (fog), or in a 90-95 percent relative humidity test. Test duration is typically three months for low alloy steels and aluminum alloys, and six months for stainless steel. The most common processing methods for production of wrought metal are rolling, forging and extruding. These processing methods produce a granular structure which is parallel to the flow of metal. As shown on Figure 2, grain orientation is parallel to the longitudinal direction of rolling, extrusion or drawing. When thin shapes are rolled or extruded, grains are oriented in a short transverse or long transverse direction as shown on Figure 2. The resistance of metals to SCC is always less when tension is applied in a transverse direction. It is least for the short transverse direction. Stress corrosion is aggravated when tensile stresses due to assembly have been applied in the short transverse direction. Table 2 lists typical materials and environments that may cause stress corrosion. [D] Technical Rationale: SCC is caused by the combined action of sustained tensile stress and corrosion which result in premature failure of materials. Certain materials are more susceptible than others. If a susceptible material is placed in service in a corrosive environment under a tension of sufficient magnitude, and the duration of service is sufficient to permit the initiation and growth of cracks, failure will occur at a stress lower than the material will normally be expected to withstand. References Hall, A. and Hongola, M: Stress Corrosion Test Procedure Applicable to Lot Acceptance Testing and Qualification Testing for Forward Separation Bolt Assembly. Hi-shear Corporation, Ordnance Group, Torrance, CA, June 1, 1988. Fontana, Mars G.: Corrosion Engineering. Third Edition, McGraw-Hill Book Company, New York, 1986. Design Criteria for Controlling Stress Corrosion Cracking. MSFC-SPEC-522B, NASA/Marshall Space Flight Center, AL, September 30, 1988. Material Selection List for Space Hardware. MSFC-HDBK-527F, NASA/Marshall Space Flight Center, AL, September 30, 1988. Crain, Bruce D.: Handbook of Corrosion Data. ASM International, Metals Park, OH, August 1989. McEvily, A. J. Jr.: Atlas of Stress Corrosion and Corrosion Fatigue Curves. ASM International, Metals Park, OH, 1990. Scully, J. C.: The Fundamentals of Corrosion. Third Edition, Pergamon Press, Inc., Elmsford, NY, 1990. Torres, P.D.: MSFC Corrosion Test Procedure Currently Followed for Testing Round Tensile Specimens. Memo No. EH24(92-24), NASA/Marshall Space Flight Center, AL, October 22, 1992. Standard Practice for Evaluating Stress Corrosion Cracking Resistance of Metals and Alloys by Alternate Immersion in 3.5% Sodium Chloride Solution. ASTM G44-88, American Society for Testing and Materials, Philadelphia, PA, June 1988. Standard Practice for Preparation of Stress Corrosion Test Specimens for Weldments. ASTM G58-85, American Society for Testing and Materials, Philadelphia, PA, November 1985, (reapproved 1990). Standard Test Method for Salt Spray Testing. ASTM B117-90, American Society for Testing and Materials, Philadelphia, PA, May 1990. | This practice has been used on Saturn IB, Saturn V, Lunar Roving Vehicle, Space Shuttle Solid Rocket Booster, Space Shuttle External Tank, Space Shuttle Solid Rocket Motor, Material Experiments Assembly, Inertial Upper Stage, Skylab, High Energy Astronomy Observatory, Hubble Space Telescope. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/06/2000
765 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Ultrasonic Testing of Aerospace Materials |  | Failure to detect cracks, flaws, and voids in aerospace materials through the proper use of ultrasonic testing and other approved nondestructive evaluation methods could result in the use of weakened structures, unbonded propellants and insulation layers, and potential pressure vessel failures or burnthroughs due to increased propellant surface area, resulting in potential mission failure. | Three general methods of ultrasonic testing can be used singly or in combination with each other to identify cracks, debonds, voids, or inclusions in aerospace materials. Each has its own unique application and all require certain precautions or techniques to identify potentially flawed hardware. This practice describes selected principles that are essential in reliable ultrasonic testing. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1422 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Careful attention to detail in ultrasonic testing can result in the identification of very small cracks, debonds, voids or inclusions in aerospace hardware that could be detrimental to mission performance. New ultrasonic technologies are enhancing the accuracy, speed, and cost-effectiveness of this method of nondestructive testing. Implementation: As schematically illustrated on Figures 1, 2, and 3 there are three principal methods of ultrasonic testing of aerospace materials: (1) the pulse-echo method; (2) the through-transmission method; and (3) the pitch-catch method. These three ultrasonic methods use pulses of energy during testing operations. These methods and their principal use in support of MSFC projects and technology programs are described below: 1. The pulse-echo method (Figure 1). In the pulse-echo method, a piezoelectric transducer with its longitudinal axis located perpendicular to and mounted on or near the surface of the test material is used to transmit and receive ultrasonic energy. The ultrasonic waves are reflected by the opposite face of the material or by discontinuities, layers, voids, or inclusions in the material, and received by the same transducer where the reflected energy is converted into an electrical signal. The electrical signal is computer processed for display on a video monitor or TV screen. The display can show the relative thickness of the material, depth into the material where flaws are located, and (with proper scanning hardware and software), where the flaws are located in the X-Y plane. In aerospace applications, the pulse-echo method is used primarily for the detection of flaws in metals, but has been used for first and second bondline interrogation in solid rocket motors (each transmitted/received wave in Figure 1 represents a pulse of energy). [D] 2. The through-transmission method (Figure 2). In the through-transmission method, an ultrasonic transmitter is used on one side of the material while a detector is placed on the opposite side. Scanning of the material using this method will result in the location of defects, flaws, and inclusions in the X-Y plane. This method is used for nondestructive testing of multi-layered and multicomponent materials as encountered in solid rocket motor case/insulation/liner/propellants, in composite materials, and on highly attenuative materials. (Each transmitted/received wave in Figure 2 represents a pulse of energy.) [D] 3. The pitch-catch method (Figure 3). The pitch-catch method, in which the ultrasonic energy is transmitted at any angle to the surface of the material and received as reflected energy returning at the reflected angle, is used primarily for cylindrical tubes and other nonlinear parallel sided surfaces. The pitch-catch method can determine depths of the flaw in the material as well as detect the location in the X-Y plane through scanning. (Each transmitted/received wave in Figure 3 represents a pulse of energy.) [D] All three methods are most effective on parallel sided surfaces, but techniques are being developed to inspect variable thickness materials or parts if and when the variation in thickness relative to the X-Y plane is known precisely. Precautions to be observed in ultrasonic testing include: (1) acoustical impedance matching of the sensors with the subject test material through the use of the correct coupling media; (2) use of air-coupling for moisture-sensitive materials; (3) resolution requirements needed to discriminate between adjacent anomalies; and (4) the use of electronic methods wherever possible to make corrections in distance inaccuracies encountered due to ultrasonic beam spreading; (5) characteristics of the transducer(s); and (6) the dependence of resolution on index, scan speed, repetition frequency, computer speed, etc., when using automated scanning. Water has been the best coupling media because of its ready availability, low viscosity, and its relatively safe use with most spacecraft construction materials. When immersion in water is not practical or desirable due to potential moisture absorption, material contamination, or part sizes and configurations, various forms of squirters bubblers have been devised to introduce a layer of water between the sensor and the material to serve as an acoustic coupler. In the pitch-catch method, a water-based gel has proven to be the most practical coupling agent. For solid propellant rocket motors, an elastomeric material similar to solid rocket propellant is used for acoustic coupling of sensors to the material during testing. Ultrasonic transmitters and receivers encased in a water jet nozzle have been used to provide continuous coupling during testing of large areas by continuously injecting a plane of water between the sensor and the material being tested. The most thoroughly researched application of ultrasonic testing at MSFC has been the detection of bond line failures between the case and insulation, the insulation and liner, and the liner and propellant. Ultrasonic waves can be focused at an oblique angle to establish the integrity of adhesive bonding. These oblique ultrasonic excitations cause standing waves in any unbonded areas which can then be detected by conventional ultrasonic methods. In this manner, weak or kissing bonds can be detected. NASA has had considerable success in detecting imperfections and debonds between the case or insulation and the liner, but work is continuing to develop reliable methods of detecting debonds at the second bondline between the liner and the propellant. In materials that have high attenuation impedance such as solid rocket propellants, relatively low ultrasonic frequencies (50kHz in an available ultrasonic range of 3kHz to 50MHz) are more effective than the high ultrasonic frequencies used for metals. Rapid strides are being made in information processing and display techniques which filter out extraneous acoustic signals and provide improved visual images of ultrasonic testing results. The pulse-echo method regularly reveals defects down to .047 inch in diameter. Through-transmission methods have been able to detect anomalies of .050 inch in diameter, which are far smaller than those which could detrimentally affect a solid rocket motor's performance. Ultrasonic capability to detect flaws depends on the wavelength (derived from the frequency and wave velocity). A general rule of thumb for the detection limit is: the smallest detectable flaw size is half the wavelength. The use of higher frequencies improves the sensitivity to small flaws, however there is an increase in the wave attenuation and the noise due to scattering from the material microstructure. Also, in any ultrasonic test there is a dead zone caused by the finite pulse length. This dead zone leads to the inability to detect flaws near the surfaces of the test materials. Ultrasonic testing personnel should be qualified and certified in accordance with MIL-STD-410E or SNT-TC-1A. Technical Rationale: Selection criteria for NDE techniques, specifically ultrasonic techniques, has been a subject of research by MSFC's Materials and Processes Laboratory for a number of years. These techniques have been verified by Thiokol Corporation, Martin Marietta, Aerojet, SAIC, The Naval Surface Warfare Center, and others. References Bray, Don E. and Don McBride: Nondestructive Testing Techniques, Chapter 11, Ultrasonic Testing of Aerospace Materials, John Wiley and Sons, New York, NY, 1992. Kutz, Myer: Mechanical Engineers' Handbook, Section 27.3; Ultrasonic Methods of Nondestructive Testing, John Wiley and Sons, New York, NY, 1986. Seydel, James, A. and Julian R. Frederick.: A Computer-Processed Pulse-Echo NDT System, Materials Evaluation, November 1973. Whaley, H.L. et. al.: Applications of Frequency Analysis in Ultrasonic Testing, Materials Analysis, January 1975. Smith, A.C. and H. Yang: Ultrasonic Study of Adhesive Bond Quality at a Steel-to-Rubber Interface by Using Quadrature Phase Detection Techniques, Materials Evaluation, December 1989. Green, R. E.: Ultrasonic Testing, Nondestructive Testing Handbook, Volume 7, American Society for Nondestructive Testing, Columbus, OH, 1991. Metals Handbook, Volume 17: Nondestructive Inspection and Quality Control, pp. 231-277, ASM International, Metals Park, OH, 1989. MIL-STD-410E: Nondestructive Testing Personnel Qualification and Certification, Military Standard, January 1991. SNT-TC-1A: Recommended Practice, Personnel Qualification and Certification in Nondestructive Testing, American Society for Nondestructive Testing, Columbus, OH, 1988. | This practice has been used on Space Shuttle External Tank, Solid Rocket Booster, Space Shuttle Main Engine, and in-house manufacturing technology programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/05/2000
759 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor Joint Reliability |  | These design solutions, while suitable for pinned joint configurations in large segmented SRM Systems, are not universally suitable for all SRM systems. Failure to adhere to the design principles described in this practice could result in leakage of hot combustion gasses past one or more sealing surfaces or seals during start-up or operation of solid propellant rocket motors. The result could be an anomalous trajectory, premature mission termination, or loss of life. | Critical design features that reduce joint rotation, improve seal features, provide close tolerances, provide for leak checks, and provide venting are used to improve the reliability of case-to-case and case-to-nozzle field joints for large solid propellant rocket motors. Principal design drivers are the combustion chamber pressure vs. time profile, segment stacking and assembly tolerances, insulation and sealing configurations, launch dynamic loads, flight dynamic loads, and environmental temperatures. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1257; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Proper design of solid rocket motor case-to-case field joints reduces joint rotation and potential leakage during ignition and operation. With detailed dynamic loads analyses, thermal analyses, careful insulation design, and suitable quotoquot-ring sealing, the leakage of hot combustion gasses through field joints is eliminated. This prevents potentially catastrophic burning or melting of the solid rocket motor and adjacent metal components. Similar benefits are obtained by using improved design practices for case-to-nozzle joints and factory joints between case segments. Implementation Method: 1. Background The Challenger accident (Space Shuttle Flight #51L) which was caused by the escape of hot gasses from case-to-case field joints in the SRM, triggered an in-depth, detailed review of analytical, design, manufacturing, assembly, and testing methods for solid rocket motor field and factory assembly joints. The case-to-case field joint was the primary target of the investigations and subsequent redesign efforts. However, other joints in the motor such as the case-to-nozzle joint and the factory joint between motor segments were thoroughly investigated and redesigned when the investigation allowed for optimization of the noted configurations. Reliable joint performance was achieved by a detailed review of the design drives and by comprehensive analysis, test, and redesign processes. 2. Case-to-Case Field Joint Improvements Space Shuttle Redesigned Solid Rocket Motors (RSRMs) are made up of four segments in which propellant is cast in monolithic form. The four segments are connected by the field joint shown in cross-section on Figure 1. The case portion of each segment consists of two cylinders connected in the center by a factory joint. A dynamic launch and flight load analysis confirmed that the field joint design, which has been the main focus of attention, needed to be modified after the Challenger accident to incorporate several improvements. The most significant of these improvements was the addition of a quotcapturequot feature, which is essentially an added circumferential band that is incorporated as an integral part of the quottangquot on the male side of the three case-to-case field joints. This capture feature creates an interference fit with the inner clevis surface and restricts the movement of the tang away from the two quotoquot-rings on the internal leg of the field joints during initial motor pressurization. The capture feature also incorporates a third quotoquot-ring which potentially serves as a heat barrier to the combustion process, in event of anomalous insulation performance. In addition to the change in the metal parts, the configuration of the internal insulation interface between adjacent segments was changed to permit an interference fit between adjoining insulation elements. This insulation joint is bonded with a pressure sensitive adhesive around its full circumference, and aided in its contact during motor operation with a circumferential quotJquot shaped pressurizing slot in the tang insulation. With the addition of the capture feature and its quotoquot-ring, a second leak check port, which also serves as a vent during assembly and a means of positioning of the primary quotoquot-ring, was added in the redesigned joint. This ensured that a redundant seal existed in the new design. A quotV-2quot fluorocarbon filler material was placed at the clevis tip between the primary and tang quotoquot-rings to reduce the free volume of the joint and limit the quantity of hot gas that would enter the joint in the event of leakage of the quotJquot seal and capture feature quotoquot-ring. In the new design, the inner clevis leg surface is machined to provide a sealing surface for the capture feature quotoquot-ring. The compression of both the primary and secondary quotoquot-rings was increased by increasing the quotoquot-ring diameter by 0.010 inch from the pre-Challenger configuration, and the quotoquot-ring grooves were widened by 0.005 inch to prevent four wall contact by the quotoquot-ring. All sealing surfaces were smoothed to an average roughness of 63 micro inches (63 millionths of an inch). A chamfered clevis leg was provided to aid in the assembly process. Each field joint in the Redesigned Solid Rocket Motor is connected by pins (a cross sectional drawing of one of these pins appears on Figure 1). A key reliability enhancement feature is an increased-length pin with a circumferential pin retainer band. Each pin includes a hole which assists in assembly, and an opening with a dovetail cross-section to assist in pin extraction for refurbishment after flight. The increased pin length causes the dovetail to lie outboard at the outer clevis leg outside diameter. A stress analysis confirmed that this would reduce unit area shear stress on the pin because the dovetail is outside of the high shear area. This modification eliminated the potential for pin deformation. Custom shims were inserted between the inside surface of the outer clevis leg and the outside surface of the tang to maintain a constant gap between the two surfaces and to limit the growth of the metal-to-metal gap at the primary and secondary quotoquot-rings during pressurization. [D] 3. Case-to-Nozzle Joint Improvements Concurrent with the improvements in the case-to-case field joints, case-to-nozzle joints were also improved to obtain higher reliability and to achieve a more robust design. Changes to the insulation configuration, joint adhesive material, quotoquot-ring and quotoquot-ring groove configurations, and the nozzle attachment fasteners provide positive assurance of sealing. As in the instance of the insulation surrounding the case-to-case field joints, a pressurizing slot in the case insulation, coupled with a layer of sealant between the case and nozzle insulation, provides protection against combustion gasses reaching the nozzle or case metal parts. A circumferential slot is located in the case insulation near the interface between the case and nozzle insulation. A circumferential flow baffle is installed in this slot to prevent erosion of the insulation, and a stress-relieving radius former is included at the base of this slot to prevent cracking. To provide an additional margin for reliability, polysulfide adhesive material is used to bond the carbon phenolic nozzle insulation material to the asbestos/silica-filled, nitrile butadiene rubber insulation in the rocket motor case. A wiper quotoquot-ring in the glass phenolic layer of the nozzle insulation and wiper vent slot in the rubber case insulation were incorporated to prevent entrapment of air in the case-to-nozzle joint during assembly, and to prevent the polysulfide adhesive from contaminating the primary quotoquot-ring. The wiper quotoquot-ring also provided the second of two barriers (the first is the polysulfide material in the insulation joint) to inhibit gas flow to the primary seal. Stress analysis studies and strength testing proved that radial bolts, as well as longitudinal bolts, were required to ensure an impenetrable seal between the nozzle and case metal parts under all environmental and motor performance conditions. Radial bolts ensure that sufficient compression of the primary quotoquot-ring is maintained to provide effective sealing. Increasing the diameter of the quotoquot-ring and redimensioning the quotoquot-ring groove to provide optimum quotoquot-ring squeeze while preventing quotoquot-ring entrapment were required reliability enhancement measures in the RSRM case-to-nozzle joint. 4. Factory Case-to-Case Joints Custom shims, widened quotoquot-ring grooves, slightly larger quotoquot-rings, increased pin length, and revised pin retainer bands were improvements made in the factory case-to-case joints. Because of the continuous insulation and propellant strata over the factory joints, special joint provisions were not required in the insulation. Clevis legs were chamfered and undercut at the leg tips for consistent final configurations after assembly. Technical Rationale: Based on detailed analyses of key design and manufacturing/assembly drivers, the SRM case-to-case field joints have exhibited satisfactory performance in close to 100 solid rocket motors since the Challenger accident without evidence of hot propellant gas leakage through the insulation to the joint sealing system. The critical parameters associated with the case-to-case field joint, case-to-case factory joint, case-to-nozzle joint, and ignition system mounting joints continue to be closely monitored on a flight-to-flight basis to prevent the occurrence of undesirable hot gas transmission through any of the multiple seals provided. References 360L001 Acceptance Review: Morton Thiokol, Inc. Aerospace Group, Brigham City, Utah, March 14-15, 1988. Design Data Book (DDB) for Space Shuttle Redesigned Solid Rocket Motor (RSRM), Thiokol Corporation, Space Operations, November 1990. quotSpace Shuttle Solid Rocket Motor Program, Lessons Learned,quot AIAA Paper #91-2291-CP, A. A. McCool, George C. Marshall Space Flight Center, Alabama, 1991. | This practice has been used on Space Shuttle Redesigned Solid Rocket Motor (RSRM). | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/05/2000
760 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Eddy Current Testing of Aerospace Materials |  | Failure to detect flaws in the surface or near surface areas of components could result in failure of the components and possibly failure of the mission. Failure to use ECT when applicable to aerospace materials could result in the use of a slower, less cost effective, and less reliable method for detecting surface and near surface flaws in aerospace materials. | Eddy Current Testing (ECT) can be used on electrically conductive material for detecting and characterizing defects such as surface and near surface cracks, gouges, and voids. It can also be used to verify a material's heat treat condition. In addition, wall thickness of thin wall tubing, and thickness of conductive and nonconductive coating on materials can be determined using ECT. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PT-TE-1421 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Eddy Current Testing (ECT) is a fast, reliable, and cost effective nondestructive testing (NDT) method for inspecting round, flat, and irregularly shaped conductive materials. Specific processes have been developed to determine the usability and integrity of threaded fasteners. In addition, ECT has the capability of being automated. With proper equipment and skilled test technicians readout is instantaneous. Implementation: Alternating Current (AC) flowing through a coil produces an alternating magnetic field about the coil. When the coil is positioned near to, or placed on, material that is capable of conducting electrical current, the magnetic field passes into the material and circular (eddy) currents are induced in the material near the coil. The flow of eddy currents in the material causes the excitation of a fluctuating magnetic field of its own. This magnetic field is always in opposition to the coil's magnetic field as illustrated in Figure 1. When the coil is placed on conductive material, the strength of the coil's magnetic field is reduced. This change in the magnetic field causes a change in the impedance of the coil, which causes a change in the current flowing through the coil. These changes are detected by an instrument placed in the circuit. [D] The flow of eddy current within the material is disrupted by the presence of discontinuities, such as, cracks, porosity, or inclusions. Discontinuities cause a decrease in the flow of current in the material by increasing the length of the path along which the current must flow as shown in Figure 2. This results in a reduction of current flow which causes a change in the impedance of the test probe coil. [D] There are three major factors that affect ECT. These are material conductivity, geometry, and permeability of the material being tested. In addition, there are contributors that affect the three major factors. These are shown in Table 1. Table 1. Factors Affecting Eddy Current Testing Conductivity Geometry Permeability Alloy Hardness Temperatur Residual stress Coatings Thickness Discontinuities Coil-to-Material Seperation (liftoff) Ferromagnetic* * Material capable of being magnetized The ECT signal is strongly related to the geometrical shape of the coil, i.e., the size, shape, and positioning of the coil; the relationship between the coil windings and suspected discontinuities; the effect of changes in liftoff or fill factors; the depth of penetration; and the edge effect. Identifying the various factors causing impedance changes depends upon the knowledge and skill of the ECT technician. Thus, selecting the appropriate eddy current probe is an important part of eddy current testing. Various types of test instruments available for ECT are: 1) conductivity testers, 2) crack detectors, 3) resistance and reactance measuring testers, 4) coating thickness testers, and 5) oscilloscopes and output devices such as strip chart recorders, printers, etc. when used as part of a test setup. A standard test specimen with known flaw sizes must be fabricated for use in adjusting the sensitivity setting of the test instrument for accurate interpretation of the test results. The standard test sample should be sound and of the same alloy, temper, and geometry as the part to be tested. Flaws may be produced in the standard test specimen by drilling, electrical discharge machining, milling, or any other means that will not distort the standard. Any flaw size outside the predetermined acceptable flaw size for the object being tested shall be a noted defect for corrective action or rejection. Table 2 lists advantages and disadvantages to be considered when selecting ECT. The most important elements required to maximize successful eddy current operations are dedicated personnel, training, proper equipment, and adequate standards. Also, at reasonable time intervals during ECT, routine checks should be made with the standard test specimen to insure equipment is operating properly. Table 2. Advantages and Limitations of Eddy Current Testing (ECT) Advantages Limitations 1. High speed testing (can be automated) 2. Accurate measuring of conductivity 3. Discontinuities at or near surface can be reliably detected 4. High-sensitivity to small discontinuities 5. Accurate coating thickness measurements 6. Direct Go/No Go answers can be quickly obtained 7. No physical contact required 8. Low cost 9. Portable 1. Limited penetration into test article 2. Several variables simultaneously affect output indication 3. Discontinuities are qualitative not quantitative indications 4. Material must be conductive 5. Requires skill when many variables are involved 6. False indications can result from edge effects and parts geometry ECT is useful in the areas of material heat treat determination, coating thickness measurements, and flaw detection. A list of typical applications is shown in Table 3. Table 3. Typical Applications of Eddy Current Testing Material Property Determinations Thickness Measurements Flaw Detection Heat treatment evaluations Hardness Fire damage Impurities Chemical compositions Corrosion damage Conductivity of ionized gas Thin sheet metal Foil Paints Anodic coatings Lacquers Thin insulation Rocket motor linings Sheet metal Foil Wire Bars Tubes Bolt holes Fasteners Welds Ball bearings Technical Rationale: For the past ten years, eddy current testing has been a necessary tool at MSFC for the inspection of bolts, (heads, grip length, and threads), nuts, and holes for defects. Standards are fabricated as required and special adapters have been fabricated which allows the probe (coil) to be positioned at the correct angle and distance from surface. ECT is a fast, accurate, and highly reliable method for determining defects in surface and near surface areas of aerospace materials. References MIL-HDBK-728/2: quotMilitary Handbook Eddy Current Testing,quot December 1985. MIL-HDBK-727/1: quotMilitary Handbook Nondestructive Testing,quot December 1985. Bray, Don E., and Don McBride: quotNondestructive Testing Techniques,quot John Wiley & Sons, Inc., 1992. CT-6-5: quotNondestructive Testing Eddy Current,quot Classroom Training Handbook, Second Edition, Convair Division of General Dynamics, 1979. PT-4-5: quotNondestructive Testing, Eddy Current Testing,quot Programmed Instruction Handbook, Convair Division of General Dynamics, San Diego, CA, 1967. Bray, Don E., and Roderick Stanley: quotNondestructive Evaluation,quot McGraw-Hill, Inc., 1989. Kutz, Myer: quotMechanical Engineers Handbook,quot John Wiley & Sons, Inc., 1986. ASTM E426-92: quotStandard Practice for Electromagnetic (Eddy Current) Examination of Seamless and Welded Tubular Products, Austenitic Stainless Steel and Similar Alloys.quot Birnbaum, George, and George Free: quotEddy Current Characterization of Materials and Structures,quot ASTM Special Technical Publication 722, American Society for Testing and Materials, 1916 Race Street, Philadelphia, PA, 19103, September 1979. McMaster, R.C., P. McIntire, and M. L. Mester: quotNondestructive Testing Handbook,quot Second Edition, American Society for Nondestructive Testing, Inc., 1986. Metals Handbook, Volume 1: quotNondestructive Inspection and Quality Controlquot ASM International Metals, Park, OH, 1989. | This practice has been used on Solid Rocket Motor (SRM) and Redesigned Solid Rocket Motor (RSRM). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/05/2000
757 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | The Team Approach to Fault-Tree Analysis |  | Failure to adhere to the guidance provided in this preferred reliability practice could result in: (1) prolonged investigations yielding either marginal or no fruitful results; (2) expenditure of the valuable time and efforts of engineering personnel with less than optimum performance; and (3) failure to pinpoint problem causes and corrective actions with precision. Overall results could be slippage of the schedule, increased costs, unidentified hazards to the crew and other personnel, and nonperformance of the mission. | Use a multi-disciplinary approach to investigations using fault-tree analysis for complex systems to derive maximum benefit from fault-tree methodology. Adhere to proven principles in the scheduling, generation, and recording of fault-tree analysis results. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice Number PD-AP-1312, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. The use of the team approach to fault-tree analysis permits a rapid, intensive, and thorough investigation of space hardware and software anomalies. This approach is specifically applicable when the solution of engineering problems is urgent and when they must be resolved expeditiously to prevent further delays in program schedules. The systematic, focused, highly participative methodology permits quick and accurate identification, recording, and solution of problems. The resulting benefits of the use of this methodology are reduction of analysis time, and precision in identifying and correcting deficiencies. The ultimate result is improved overall system reliability and safety. Implementation Method: Determination that a Team Approach to Fault-Tree Analysis is Required: In situations where program hardware or software anomalies are uncovered which could potentially reduce the possibility of mission success or cause harm to personnel, and where the pressure of schedules requires a rapid and accurate solution of problems, the team approach to fault-tree analysis should be strongly considered. Fault-trees are necessary when the system in question is complex and has many potential contributors to the problem so that the solution defies simple intuition, engineering judgement, or easy elimination of the events that contributed to the problem. The team approach to fault-tree analysis brings all disciplines to bear simultaneously in an interactive but controlled environment. A fault-tree is defined as, quota graphic depiction or model of the rationally conceivable sequences of events within a complex system that could lead ultimately to the observed failure or potential failure.quot It is a systematic approach to fault prevention achieved by postulating potential high level faults, and identifying the primary and secondary causes, down to the lowest piece-part, that could induce the high level fault. A typical arrangement of a fault-tree showing the potential types of quotgatesquot containing Boolean logic is shown on Figure 1. In situations of high urgency and cost or schedule sensitivity, it is often desirable to apply a team approach to development and use of the fault-tree methodology. [D] Fault-Tree Team Methodology: The keys to a successful team approach to a fault-tree analysis are: (1) selection of the right people to participate in the analysis; (2) interactive meetings of these people in a creative but focused environment; (3) thorough documentation of objectives, fault-tree structure, and action items; (4) parallel (but not redundant) participation by all team members; and (5) careful attention to general ground rules for effective team dynamics. All of the preceding must be backed up by a data base containing the hardware/software configuration, operational time lines, potential failure causes, and exonerating or indicting data. Logic flow networks are built based on the system's design, then laboratory test results, hardware/software test results, and modeling based on deterministic and/or probabilistic statistical analyses. These logic flow networks also feed into the information data base that is used by the fault-tree team. An integral part of successful fault-tree methodology is the selection of an orderly structure on which to base the fault-tree and the team participation. The Work Breakdown Structure (WBS) is an ideal starting point for the team as well as for the design. Each event or activity in the WBS is subdivided into its main contributing events or activities, then the tree is subdivided again until the smallest activity that cannot be further subdivided is reached. These final events or activities are the quotleavesquot on the fault-tree. Team Composition: Given the nature of the failure or anomaly being investigated, people should be assembled who have both an intimate disciplinary knowledge and a knowledge of the overall system. Elements heads and subteam leaders should be established for major investigative elements of the work breakdown structure. Important administrative functions to support the team are: (1) the maintenance of a current address, phone, and fax listing of all persons involved; (2) recording daily team meeting minutes; (3) preparation of agenda for the next day, (prepared at the end of the current day); (4) recording of all action items including the name of the person responsible, suspense dates, and the specific action required; and (5) the maintenance of a master schedule of major planned events, based in part on the suspense dates. Team Dynamics and Work Strategy: The entire team should meet together in one location in a meeting to expose all known data related to the anomaly or failure, then the team should meet at least once per day thereafter. Action items should be assigned and as much work as possible should be done in parallel without undue redundancy. Series activities of the team should be avoided. Team interaction is important because the fault-tree is built in a dynamic, contributory fashion. During the fault-tree team activities, the team leader and scribe should keep files of action items, agendas, technical data related to development of the fault-tree, correspondence, administrative reports, the master fault-tree diagram, and the team's schedule. Top management and other related organizations should be kept informed as to the progress of the team. Hand written notes to the key players from the team leader quoten route,quot at key milestones and critical junctures, and on successful completion of the investigation are particularly helpful. Rambling discourses should be avoided. Meetings and discussions must be diplomatically kept on track. The leader should be as democratic as possible in team meetings. No one should be affronted, but in case of an impasse, the team leader must make the decision. Refreshments should be provided occasionally, especially on Saturday or Sunday and after hours. This will boost morale and provide an atmosphere conducive to free discussion. Other General Techniques and Methods: The purpose of the team approach is to provide multidisciplinary perspectives that will uncover details and to resolve cause/effect relationships which may not be apparent in more narrowly focused detailed engineering analytical and design methods. Therefore, each element of the fault-tree must be doggedly and systematically analyzed, persistently subdivided into it's smallest elements, and pursued to the lowest level. The history of these types of investigations has indicated that a methodical, vigorous assessment is needed to develop and to utilize a fault-tree of sufficient depth. This vigorous assessment will eliminate illogical assumption, identify or eliminate synergistic effects, help to avoid partial fixes and reduce intuitive or random approaches that cannot be substantiated. The team should resist the temptation to preconceive a conclusion or take on a quotpet theoryquot to the exclusion of a systematic, orderly, and vigorous treatment of all elements in the decision tree. The team should avoid any tendency to slow down the analysis process or to assume that a conclusion has been reached when a likely cause candidate has been identified, because this potential candidate could mask the true cause or divert the team's attention from a more fruitful path. Probability and statistics are important disciplines to use in the fault-tree analysis process. The team should have an appreciation of the fact that if it is necessary to stack too many possible events together to eventually postulate the occurrence of the failure, then it is improbable that it occurred in that manner. The references list several computer-aided fault-tree analysis software packages that will aid in performing the statistical analysis and informing the decision tree graphics required to document a fault-tree analysis. Technical Rationale: The team approach to fault-tree analysis described in this practice was used very successfully in a number of in-depth investigations of problems that occurred in propulsion elements of the Space Shuttle, and related facilities and equipment. The procedure was first used in full measure in the investigation of a fire in the casting pit of the Space Shuttle Solid Rocket Motor (SRM) in 1984. It was also used in identifying causes of problems in the SRM propellant mix facility. Several problems and potential problems with the Space Shuttle Main Engine (SSME) were successfully investigated using the team approach to fault-tree analysis. These investigations involved the bearings for the alternate turbopump, and a synchronous vibration problem. Hydrogen leaks in the Space Shuttle Columbia were investigated and successfully resolved in an in-depth and intensive three-month team approach to fault-tree analysis. References Dhillon, Balbir S: quotFault-Tree Analyses,quot (Chapter 20 of quotMechanical Engineers Handbookquot) John Wiley & Sons, New York, NY, 1986. Koren, James: quotComputer-Aided Fault-Tree Analysis (CAFTA) User's Manual,quot Science Applications International Corporation, Los Altos, CA, 1993. Van Fleet, Kevin: quotRisk Spectrum Fault-Tree Software,quot User's Manual, Innovative Software Designs, Inc., Baltimore, MD, 1993. Wild, Tony, Ph.D.: quotTree Master Software,quot User's Manual, Management Sciences Incorporated, Albuquerque, NM, 1994. Schwinghamer, Robert: quotLeak Team's Final Eureka Anthemquot Hydrogen Leak Investigation Team Final Report (Presentation), NASA, Marshall Space Flight Center, A-L, November 8, 1990. Reliability Preferred Practice PD-ED-1208 - quotStatic Cryogenic Seals for Launch Vehicle Applicationsquot | This practice has been used on the Space Shuttle Solid Rocket Motor (SRM), Space Shuttle Main Engine (SSME), and Space Shuttle External Tank (ET). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
756 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Sneak Circuit Analysis Guideline for Electro-Mechanical Systems |  | Sneak circuits that escape cursory design screening can result in schedule delays, damage to equipment during test, downtime during operation, increased cost, and possible loss of spacecraft or crew. Too-late implementation of a sneak analysis can result in high project costs due to redesign and redevelopment efforts. | Sneak circuit analysis should be used in safety critical systems to identify latent paths which cause the occurrence of unwanted functions or inhibit desired functions, assuming all components are functioning properly. It is based upon the analysis of engineering and manufacturing documentation. Because of the high cost of a sneak circuit analysis, it should be conducted only in areas where there is a high potential for a hazard. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice Number PD-AP-1314, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Identification of sneak circuits in the design phase of a project prior to manufacture can improve reliability; eliminate costly redesign and schedule delays; and eliminate problems in test, launch, on-orbit, and protracted space operations. Sneak circuit analysis can also be beneficial in identifying drawing errors and design concerns. Implementation Method: Some of the devices and equipment benefiting from hardware sneak circuit analysis are solid state electronic devices, relay logic systems and digital systems. The relay equipment includes associated items such as: resistors, capacitors, single load devices, diodes, switches, integrated circuits, and other semiconductors. Another type, analog equipment, includes amplifiers, inverters, converters, and feedback systems. Sneak circuit analysis is an effective tool for locating potential problems in software, and for identifying potential drawing errors and design concerns. Sneak circuit analysis is a labor intensive technique which requires specialized training and is often limited to those areas of a design where safety compliance is an issue. When considering sneak circuit analysis as an applicable tool to be applied to a program, the following considerations are recommended: Reasons for conducting a sneak circuit analysis: Improve reliability which results from the identification and resolution of system problems. Conduct an independent analysis of the design. Locate unresolved system problems that could not be found by other analyses or tests. Identify high criticality items (crew and mission-critical). Respond to a high change rate in baseline design. Applicable systems: Systems which perform active functions. Electrical power distribution and controls. Computer programs which control and sequence system functions. Sneak circuit analysis can be implemented on a limited subsystem, a complete functional system or a complete vehicle or program. Analysis is based on documentation in the form of quotas builtquot schematics, drawings, wire lists and quotas codedquot source computer programs. The preferred start time to begin sneak circuits analysis is during the engineering development phase prior to Critical Design Review (CDR), but sneak circuit analysis can be performed during any phase of the program. The analysis cannot be completed until the overall program/project drawings are baselined. Performing sneak circuit analysis during the last phases of the program tends to drive program costs up because of the potential redesign effort. The effects of making a change later in a program are illustrated in Figure 1. [D] The data used for sneak circuit analysis must represent the system circuitry as built, contingent upon quality control checks, tests, and inspections. The technique for sneak circuit analysis requires the analyst to accumulate detailed circuit diagrams and wire lists, arrange circuit elements into topological network trees, and to examine these network trees for suspected sneak circuits. After the topological trees have been produced, the next step is to identify the basic topological patterns that appear in each tree. The five basic topological patterns are: (1) the single line (no-node), (2) the ground dome, (3) the power dome, (4) the combination dome, and (5) the quotHquot pattern. These topological patterns are illustrated in Figure 2. The quotPWRquot represents electrical power, quotSquot=switching element, quotLquot=electrical load, and quotGquot=ground. The quotHquot pattern usually has the highest incidence of problems due primarily to the higher number of power sources, returns, loads, and switches. The problems normally occur in the quotHquot crossbar, which includes L3, S3, and S4. This can result in power reversals, ground reversals and current reversals. As the analyst examines each node in the network tree, the analyst must identify which pattern or patterns that node is part of and apply the basic clues that have been found to typlify sneak circuits involving that particular pattern. [D] Associated with each pattern is a list of clues to help the analyst identify sneak circuit conditions. The clues are questions that the analyst must ask about the circuit in question. The clue list becomes longer and more complicated with each successive topograph. The clue list for the quotHquot patterns includes more than 60 clues. Almost half of the critical sneak circuits can be attributed to the quotHquot pattern so this pattern should be analyzed very carefully. (Depending upon contract provisions, the developed clues may be proprietary to the performing contractor.) Sneak conditions are classified into four basic types: Sneak paths - which cause current to flow along an unexpected route. Sneak timing - which may cause or prevent the activation or inhibition of function at an unexpected time. Sneak indications - which may cause an ambiguous or false display of system operating conditions. Sneak labels - which may cause operator error through inappropriate control activation. When a suspect sneak condition is identified, the analyst should verify that the circuit is valid. The circuit should be checked against the latest drawings, revisions, as-built documentation and equipment; and operational information should be reviewed concerning the system in question. Upon verification of the sneak condition, a sneak circuit report should be written which includes the drawings, an explanation of the condition, system level impact, and a recommendation for correcting the sneak circuit. Software sneak analysis should be used to discover program logic which causes one of the four sneak condition types. During the sneak circuit analysis, unnecessary or undesired conditions may be discovered. These conditions could be newly identified failure points, unsuppressed inductive loads, unnecessary components, unnecessary software codes and inadequate redundancy provisions. These conditions should be documented in design concern reports. Any documentation discrepancies should be reported in document error reports. A final sneak analysis report should be written that details the scope, procedures, results and conclusions of the analysis. The final report should also include all sneak conditions, design concern reports, documentation error reports and report tracking status sheets. Technical Rationale: Sneak analysis is a reliability-enhancement method used to identify designed-in conditions that could introduce undesired events and inhibit desired system functions which could adversely affect crew safety or mission success. The sneak circuit analysis technique differs from other system analysis techniques in that it is based on identification of designed-in inadvertent modes of operation and is not based on failed equipment or software. References Buratti, Davey L. and Sylvia G. Godey: quotSneak Analysis Application Guidelinesquot, RADC-TR-82-179, Boeing Aerospace Company for Rome Air Development Center, Griffis AFB, NY 13 441, June, 1982. Hill, E.J. and C. J. Bose: quotSneak Circuit Analysis of Military Systemsquot, Boeing Aerospace Company, Seattle, WA, 2nd AIAA International Systems Safety Conference, San Diego, CA, July 21-25, 1975, Proceedings, A77-16726- 31, Newport Beach, CA, System Safety Society, 1976, pgs. 351-372. Miller, Jeff: quotIntegration of Sneak Analysis with Designquot, RADC-TR-109, Vol. 1 of 2, Sohar Incorporated for Rome Air Development Center, Griffis AFB, NY 13441, June, 1990. Walker, Frank Ellis: quotSneak Circuit Analysis Automationquot, Boeing Aerospace, Seattle, IEEE, 1989 Proceedings Annual Reliability and Maintainability Symposium. Wilson, Joe L. and Robert C. Clardy: quotSneak Circuit Analysis Application to Control System Designquot, The Boeing Company, Houston, TX, AGARD-AG-224, In AGARD Integrity of Electronic Flight Control Systems for Aircraft Reliability, April, 1977. Vogas, James L.: quotSneak Analysis of Application Specific Integrated Circuitsquot, Boeing Aerospace Operation, Inc., Houston, TX, AIAA-92-0976, 1992 Aerospace Design Conference, Irvine, CA, February 1992. MIL-STD-785B: quotReliability Program for Systems and Equipment Development and Productionquot, Military Standard, September 15, 1980. NSTS 22254B: quotMethodology for Conduct of Space Shuttle Program Hazard Analysisquot, NASA, Johnson Space Center, Houston, TX 77058, December 30, 1993. | This practice has been used on the Redstone, Apollo, Skylab, and Shuttle programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
755 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Precision Diamond Turning of Aerospace Optical Systems |  | Failure to properly anchor or isolate optical diamond turning equipment or to protect it from the environment could result in an inferior product and cause unreliable manufacture of precision optics. The results would be costly due to rework, and cause schedule delays. | Meticulous control of vibration, environmental factors, and machining parameters are required to produce precision diffractive, refractive, reflective and hybrid optical components for aerospace applications. | MSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1265; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Highly reliable diffractive, refractive, reflective, and hybrid aerospace optical systems can be produced by a meticulously controlled and protected diamond turning process. The result can be rugged, temperature-compensating achromatic precision optical elements suitable for a wide variety of applications. Implementation: Diamond turning is a well-established fabrication process for shaping high quality optical surfaces on metals, polymers, and crystals. Diamond turning has the capability of precision machining with a single point cutting tool to an accuracy of a fraction of a wavelength of light which makes it suitable for fabricating lenses. The surface finish quality of diamond turning is satisfactory for optical components in the mid to long wavelength regions of the infrared spectrum. Diamond machining can be beneficial for metal mirrors because of the ability to machine a reflective surface directly onto a structural substrate which may contain mounting bosses, alignment flanges, and rib reinforcements. The precision to which components can be machined is partially dependant upon the extent to which the dynamic motion of the machine tool can be controlled with the work piece. The detrimental dynamics of the diamond turning machine can be minimized by stiffening the machine, or mounting it on a vibration isolating mount. Vibration can be reduced by mounting the machine on a block of granite, or in-ground concrete blocks surrounded with vibration isolation material. Other necessary features and components of a diamond turning lathe include stiffness, balanced air bearing spindles, straight square ways and closed loop controllers using laser interferometric feedback. Changes in humidity and partial pressure of atmospheric gases affect accuracy and should be avoided. Thermal considerations are also important. Lack of temperature control is the greatest cause of error in this machining process. Therefore, the environment housing the diamond turning lathe should be maintained to ± 0.01°F. To minimize errors caused by temperature changes, the work piece, machine and its components should be at thermal equilibrium before material removal begins. In diamond turning the surface finish is determined by the radius of the cutting tool, cutting feed rate, depth of cut, rake angle, tool wear, coolant supply consistency, stiffness of the machine and the material being machined. Materials compatible with diamond turning include: copper, gold, silver, aluminum, platinum, electrolyzed nickel, beryllium, copper, germanium, silicon, plastic, and lithium niobate. Metals that contain carbon are not considered machinable because of the chemical reaction that occurs between the carbon and diamond tool due to the high temperatures of machining. Diamond turning is insensitive to cutting speed. For example, when facing a circular disk a cutting speed of 4572 meters/minute at the outer edge decreases to zero at the center of the disk, while maintaining a specular finish. Progressively finer cuts are usually taken to reduce damage from previous cuts. Finish depths of 127 to 510 nanometers are not uncommon. The feed rate can be as large as the tool size and shape will permit, but is normally below 0.25 millimeters per revolution. Rigid machine tools are an essential part of diamond turning. Vibration or sudden impact shortens the life of the diamond tool. Sufficient spindle power is required for high cutting speeds, which reduces the pressure on the cutting edge. The use of cutting fluids reduces wear and aids in chip removal. The most common cutting fluids are kerosene and lightweight machine oil. For protection against inadvertent damage during handling or setup, the cutting edge of the diamond tools should be covered with plastic or rubber caps when not in use. Design features that distinguish diamond turning lathes from standard machine tools are: Machine base stiffness and stability, Spindle accuracy and repeatability, Slide accuracy and repeatability, Servo performance, Vibration control, Temperature control, Positioning accuracy, and Tool support and setup. External vibrations, even the sound waves of speech, can affect the surface finish of a diamond turned workpiece. Three point pneumatic damping systems isolate vibrations and shocks from the machine and provide automatic leveling to accommodate changes in the slide position and the workpiece weight. Some machines are built on a solid granite base, other machines use a solid cast metal base. New designs should be run through a computer simulation and finite element analysis to determine the machine stiffness and natural frequencies. Hydrostatic supported spindles are required for accuracy and repeatability from revolution to revolution. Air bearings are used to lower heat generation and to avoid vibration from the hydraulic supply pump. Both systems can provide rotational accuracies below 10 micro-inches. All motors and drive mechanisms must be dynamically balanced and isolated to eliminate vibration between the tool and the workpiece. The machine slides should give smooth repeatable motion between tool and spindle for control to one micro-inch or less. Technical Rationale: Precision diamond turning and other advanced production techniques are gradually replacing conventional lens grinding and polishing procedures because these methods can produce accurate optics more rapidly than traditional methods and because they can produce optical elements such as diffractive and hybrid systems that are not producible by previous methods. The newer optical elements have improved weight-efficiency, reliability, ruggedness and superior precision if machined in a carefully controlled environment. References Benjamin, R. J.: Diamond Machining Applications and Capabilities," SPIE Vol. 433, pp. 24-31, August 1983. Donaldson, R. R. and S. R. Patterson: Design and Construction of a Large Vertical Axis Diamond Turning Machine," SPIE Vol. 433, pp. 62-67, August 1983. Dow, Thomas A.: Third Annual Report on Precision Engineering SR0154," Precision Engineering Laboratory, North Carolina State University, Raleigh, NC, 1986. Dow, Thomas A.: "Precision Engineering Center Annual Report, 1986", Precision Engineering Laboratory, North Carolina State University, Raleigh, NC, 1986. Drescher, Joseph Dean: Tool Force Measurement in Diamond Turning," Department of Mechanical and Aerospace Engineering, A Thesis Submitted to the Graduate Faculty of North Carolina State University, Raleigh, NC, 1989. Johnson, E. E. and M. E. Curcio: Production Diamond Machining of Optics," SPIE, Vol. 433, pp. 37-45, August 1983. Krauskopf, B.: Diamond Turning: Reflecting Demands for Precisians," Manufacturing Engineering, Vol. 92, No. 5, pp. 90-100, May 1985. Krauskoph, B.: At the Cutting Edge: Ultra Precision Machining," Manufacturing Engineering, Vol. 91, No. 4, pp. 66-68, April 1984. Rohorer, R. L.: Update on Precision Machining at Los Alamos," SPIE Vol. 433, pp. 107-111, August 1983. Saito, T. T.: Diamond Turning of Optics: The Past, The Present, and the Exciting Future," Optical Engineering, Vol. 17, No. 6, pp. 570-573, November-December 1978. Sanger, G. M.: Optical Fabrication Technology, The Present and Future," SPIE Vol. 33, pp. 2-18, August 1983. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
758 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Computational Fluid Dynamics (CFD) In Launch Vehicle Applications |  | Failure to thoroughly analyze the pressures, temperatures, and flow rates of gases and fluids in propulsion systems using Computational Fluid Dynamics (CFD) techniques prior to design and manufacture could result in inadequate strength, thermal protection, and operational control of liquid rocket propulsion systems and related launch vehicles and components. The ultimate result of inadequate designs could be excessive redesign and testing, increased costs, and the potential for launch vehicle, engine, system, or component failure. | Use high-speed, computer-based computational fluid dynamics analytical techniques, verified by test programs to establish propulsion and launch vehicle hardware designs for optimum performance and high reliability. These procedures will validate designs and provide an early assurance of operational viability. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice Number PD-AP-1311, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. The use of computer-based computational fluid dynamics methods will accelerate the design process, reduce preliminary development testing, and help create reliable, high-performance designs of space launch vehicles and their components. In addition to design verification and optimization, CFD can be used to simulate anomalies that occur in actual space vehicle tests or flights to more fully understand the anomalies and how to correct them. The result is a more reliable and trouble-free space vehicle and propulsion system. Implementation Method: Accurate definition of flow-induced pressure and temperature loads can be achieved long before actual hardware testing through the use of high-speed, computer-based computational fluid dynamics analytical techniques. Designs can be constructed in electronic three-dimensional computer-aided design format, and the flows of fluids and gases can be accurately simulated using CFD techniques. Computer-based simulations of this type can be accomplished so rapidly that designs can be changed in real time even before hardware is fabricated. CFD techniques are being successfully used as diagnostic tools to provide insight into problems with existing rocket engine components and to develop optimum designs of liquid rocket engine pump components such as impellers, diffuser vanes, and shrouds; turbine components such as turbine blades, turbine staging, volutes, and turbine wheels; launch vehicle base thermal protection configurations; transpiration and conductive cooling methods for rocket nozzles; flow paths within solid rocket motors at various stages of combustion; and launch and reentry pressure and thermal loads on vehicle configurations. The Team Approach to CFD Code and Data Base Development MSFC has found that a very effective way of developing and selecting CFD codes (the computer-based equations that control a CFD analysis) and CFD Data Bases (the empirically derived factors that fit the CFD codes to various specific applications) is to form multi-organizational teams in specialized areas related to propulsion and to other space flight applications. These teams, which are part of a CFD Consortium for Applications in Propulsion Technology (CAPT) are comprised of individuals from within MSFC, other NASA centers, prime and subcontractors, and the academic community, communicate frequently and meet periodically to exchange and disseminate information about the rapidly growing field of computational fluid dynamics as related to rocket propulsion and other related space flight applications. The teams take into account the best available theory on CFD, the most advanced computer computational and graphic capabilities, and the latest test techniques and results of component, subsystem, subscale and full scale rocket engine tests. This information is used to continuously develop and improve the computer-based representation of the temperatures, pressures, and flow patterns (velocities, accelerations, and directions) in space vehicles and their propulsion systems. Implementation of CFD Into the Design of Rocket Engine Pumps The implementation of CFD into the design process for rocket engine pumps has been aided by the activities of a Pump Stage Technology Team (PSTT) which is a part of the NASA/MSFC CFD Consortium for Applications in Propulsion Technology. The team's goals have included the assessment of the accuracy and efficiency of several CFD methodologies and application of the appropriate methodologies to understand and improve the flow inside fuel and oxidizer pumps for liquid propellant rocket engines. As an example of the type of CFD work that has been done under the cognizance of this team, subtle changes in the axial impeller length, blade count, and blade configurations of pump impellers resulted in efficiencies of up to 98 percent. This resulted in head coefficients (which are measures of pump power) increasing from 0.53 to 0.66 in experimental impeller designs. CFD Analysis of Base Flowfields in Clustered Nozzle Configurations As a launch vehicle proceeds up through the atmosphere into space from its near sea-level launch position, the rocket exhaust plumes expand to a point where a plume reverse flow is encountered. Where multiple nozzles are used, the closed impingement of the exhaust plumes can cause a reverse jet. The reverse jet impinges on interior base surface areas, components, and base shields causing heating, contamination, and/or possible combustion in the launch vehicle base areas. Computational fluid dynamics has proven to be a useful tool in predicting the recirculating exhaust base flow patterns encountered in various launch vehicle configurations, and these patterns can be used as an input to the design and development of reliable vehicle configurations and thermal or pressure protection schemes. Figure 1 is a typical output from a CFD analysis which shows velocity vectors indicating the flow patterns that are generated at high altitude (approximately 92,000 feet above sea level) when a launch vehicle has four exhaust nozzles. With the knowledge of the pressure, temperature, and flow profiles in the base region provided by a CFD analysis, components and insulation systems can be designed to withstand environments in the base region or insulated to protect them against the potentially hostile environment that occurs due to exhaust recirculation at high altitude. [D] Turbine Improvements Using CFD Computational fluid dynamics techniques are being used in the advancement of turbine aerodynamic design techniques as well as the development of a understanding and characterization of the unsteady aerodynamic environments in existing rocket engine turbines. The CAPT Turbine Technology Team is addressing several areas of CFD application to existing and future liquid rocket engines. The techniques reduce developmental risk, decrease the amount of intermediate testing, improve performance and durability, and reduce cost. In one turbine improvement effort, gas turning angle in the turbine blades was increased from the traditional design limit of approximately 140 degrees to 160 degrees. The CFD analysis showed that this change, coupled with other minor improvements, would increase turbine efficiency by almost 10 percent and reduce the required number of turbine blades by approximately one half. Maximum blade mach number was decreased dramatically from the 1.32 of the original design to 0.87 for the new design. The new configuration employed a single stage turbine rather than an originally planned two stage configuration. CFD has also proven to be a useful tool in the evaluation of secondary losses and turbine blade tip loss control mechanisms such as endwall fences, blade fences, tip grooves, tip cavities, and mini-shrouds. This technique is also useful in the simulation and design of inlet and outlet turbine volutes. Cold flow testing of reduced scale and full scale turbines has verified many of the CFD simulations. Flow Fields, Flow Separation, Film Coolants, and Heat Transfer in Rocket Engine Combustors Computational fluid dynamics analyses have been successfully applied in areas related to the prediction and simulation of combustion flow behavior and heat transfer to the internal walls of rocket engine injectors, combustion chambers, and nozzles. These analyses have been used to optimize nozzle entrance geometries, evaluate new step nozzle exit configurations that adapt to altitude changes, determine pressure and temperature profiles in rocket engine chambers and nozzles, and to study the effects of coolant flows in liquid rocket engine chambers on internal wall temperatures. These analytical procedures have helped to evaluate anomalies discovered in actual engine firings and to design reliable combustion chamber, nozzle, and coolant arrangements that result in high thrust coefficients under various atmospheric and space conditions. The CAPT Combustion Devices Technology Team has been instrumental in many of these investigations. Computational fluid dynamics simulations have also been useful in determining pressure, heating, and insulation requirements for launch vehicles during liftoff, ascent, and reentry into the atmosphere. Technical Rationale: NASA/MSFC has sponsored the CFD Consortium for Applications in Propulsion Technology since the early 1980s. Symposia have been held for the past twelve years in which participants from MSFC, other centers, prime contractors, laboratories, other agencies, and the academic community have exchanged information in the development and application of CFD analytical techniques related to rocket engine propulsion systems. MSFC has also been involved in the other aerodynamic and fluid dynamics applications of CFD. Computational fluid dynamics is a discipline that has come of age in the concurrent engineering process that results in the design, development, and flight of highly reliable and cost effective launch vehicle systems. References quotProceedings of Workshop for Computational Fluid Dynamic (CFD) Applications in Rocket Propulsion,quot April 19-21, 1994, Marshall Space Flight Center, NASA. quotOverview of the NASA/MSFC CFD Consortium for Applications in Propulsion Technology,quot McConnaughey, P.K. and L.A. Schutzenhofer, AIAA, 92-3219, AIAA/SAE/ASME/ASEE 28th Joint Propulsion Conference, July 6-8, 1992, Nashville, TN. quotComputational Fluid Dynamics Analysis for the Reduction of Impeller Discharge Flow Distortion,quot R. Garcia, et al, 32nd AIAA Aerospace Sciences Meeting, January 10-13, 1994, Reno, NV. quotNumerical Analysis of Base Flowfield at High Altitude for a Four-Engine Clustered Nozzle Configuration,quot T.S. Wang, 29th AIAA Joint Propulsion Conference, June 28-30, 1993, Monterey, CA. quotAnalytical Investigation of the Unsteady Aerodynamic Environments in Space Shuttle Main Engine (SSME) Turbines,quot Lisa W. Griffin, et al, May 24-27, 1993, ASME, New York, NY. quotAdvancement of Turbine Aerodynamic Design Techniques,quot Lisa W. Griffin, et al, May 24-27, 1993, ASME, New York, NY. quotAdvanced Technology Low Cost Engine (ATLCE) 50K Testbed Combustion Chamber Film Coolant Parametrics,quot Joe Ruf, November 5, 1993, MSFC, AL. quotUnified Navier-Stokes Flowfield and Performance Analysis of Liquid Rocket Engines,quot T.S. Wang, et al, Journal of Propulsion and Power, September 1993, AIAA, New York, NY. quotNumerical Analysis of the Hot-Gas-Side and Coolant-Side Heat Transfer for Liquid Rocket Engine Combustors,quot T.S. Wang, et al, 28th AIAA Joint Propulsion Conference, July 6-8, 1992, Nashville, TN. quotNumerical Study of the Transient Nozzle Flow Separation of Liquid Rocket Engines,quot T.S. Wang, CFD Journal, October 1992, MSFC, AL. Reliability Preferred Practice PT-TE-1427, quotRocket Engine Technology Test Bed Practice.quot | This practice has been used on the Space Shuttle, Space Shuttle Solid Rocket Motor (SRM); Space Shuttle Main Engine (SSME) programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
754 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Contamination Control of Space Optical Systems |  | Failure to adhere to sound contamination control for optical systems could result in degradation of the expected scientific data return by obscuring the optical surfaces with particles and molecular deposits. | Contamination of space optical systems is controlled through the use of proper design techniques, selection of proper materials, hardware/component precleaning, and maintenance of cleanliness during assembly, testing, checkout, transportation, storage, launch and on-orbit operations. These practices will improve reliability through avoidance of the primary sources of space optical systems particulate and molecular contamination. | MSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1263; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Controlling contamination of space optical systems limits the amount of particulate and molecular contamination which could cause performance degradation. Contamination causes diminished optical throughput, creates off-axis radiation scattering due to particle clouds, and increases mirror scattering. Controlling molecular contaminates minimizes performance degradation caused by the deposition of molecular contaminants on mirrors, optical sensors and critical surfaces; improves cost-effectiveness of mission results; and improves reliability. Implementation Method: Contamination control of space optical systems consists of the planning, organization, and implementation of all activities needed to determine, achieve, and maintain the required cleanliness level of the optical system. Each optical system has its own unique contamination control requirements. To effectively control contamination, concurrent engineering procedures should be employed during design, manufacturing, precleaning, assembly, testing/checkout, transportation, storage, launch and on-orbit operations. The desired level of cleanliness, established during the design phase, determines the techniques required to accomplish the desired results. These steps should be documented in a contamination control plan which can be developed by utilizing the following steps: Determine degree of cleanliness required. Prepare design with optimum materials, configuration, and tolerances to help accomplish the desired cleanliness level. Select and train personnel in contamination control techniques. Select and use the proper materials, equipment, and processes to accomplish the desired end result. Implement contamination budgeting and monitoring throughout each program phase. Plan the product flow to minimize the chance of recontamination after cleaning. Select qualified personnel and equipment to monitor the cleaning processes. The major sources of particulate contamination are: Airborne particulates settling on hardware surfaces during manufacturing, assembling, and testing operations. Paint overspray, insulation shreds, clothing fibers, and other human-induced substances. Trapped particles on internal surfaces of subassemblies and in other hardware crevices. These are released and redispersed from acoustic vibration, transportation, and launch. Reaction control system (RCS) or main propulsion system plume exhaust and flash evaporator water release that may create residual cloud environments. The major sources of molecular contamination are: Manufacturing residues (machine and cutting oils) which result from fabrication of hardware. Material outgassing. Space vehicle surface outgassing during ascent, deployment, and retrieval operations. Ground and air transportation environments. Volatile condensable materials in the environment to which contamination-sensitive, critical surfaces may be exposed during assembly operations. Return flux of outgassed molecules due to collisions with residual atmospheric molecules. Propulsion system plume impingements causing deposition of nonvolatile substances (MMH-Nitrate) on optical surfaces. Oxidation through exposure to atomic oxygen present in low-earth orbit. A contamination control engineer should be assigned the responsibility for coordinating contamination control requirements. This person should not only interface with the systems engineers, but with the engineers and technicians responsible for design, materials, manufacturing, testing, checkout, facilities, and quality assurance. The contamination control engineer's responsibilities should include: 1) contamination control coordination, planning, and budgeting; 2) coordination of materials selection and testing; 3) participation in design reviews; 4) preparation of detailed contamination control requirements; 5) review and sign-off of engineering drawings, specifications, and procedures; and 6) monitoring with witness samples to meet budgeting allocations throughout each program phase. The contamination engineer and the quality assurance engineer should establish contamination control procedures for the assembly and test facilities. Monitoring of the facilities should be performed by quality assurance personnel. To avoid contamination of the optical critical surfaces, contamination control should be a foremost consideration in the design. Contamination sources can be minimized in the design by careful selection and testing of materials, coatings, and processes. Purging the optical system with clean, dry nitrogen during time the system is not in a clean environment (i.e., storage, transportation, idle times during test, etc.) is an effective method of controlling contamination. The selection and testing of organic materials should be accomplished per MSFC-SPEC-1443 (ref. 6). Clean room assembly areas should be maintained to class 10,000 and clean benches to class 100 per MSFC-STD-246. After fabrication, all parts should be cleaned, outgassed per established procedures, doubled-bagged using approved material and sealing methods, and placed in bonded storage. Electronic assemblies should be assembled in a separate class 10,000 or better clean environment and double bagged. Mechanical assemblies should be assembled in a separate class 10,000 or better clean environment. Electronic assemblies, mechanic assemblies, and structural subassemblies should remain double-bagged until brought into final assembly clean area. Structural assemblies and optical instrument assemblies should be assembled in a closely-monitored and controlled class 10,000 clean room. All required personnel required for assembly must be trained for work in a clean room environment. After assembly, optical instruments should be double-bagged for purging with dry nitrogen to help maintain cleanliness. The final assembly should be tested in at least a class 100,000 clean area. Optics should be protected when they are exposed during the test and monitored with witness samples which should be checked after the test. After testing, the optical instrument is double-bagged and prepared for purging with dry nitrogen during storage or shipping to the launch site. Measurement, Tracking, and Control The following training in precision cleaning should be provided to personnel required to enter a clean room: clean room maintenance, hardware handling, and clean room operational procedures and principles. The optical system and clean room should be monitored and measurements recorded using automatic particle counters, total hydrocarbon analyzers, temperature/relative humidity measurements, and pressure fallout sampling of particulate and molecular contaminants. These measurements should be tracked against the contamination budgeting plan. Fallout sampling is usually checked with optical witness samples that are strategically placed throughout the clean room and optical system. During the monitoring for contamination of the clean room and optical system, any contamination control discrepancy should be resolved with the contamination control engineer to determine the impact on the optical system. This impact will be weighed against the contamination budget and should be dispositioned by the materials review board. Technical Rationale: Contamination control is vital in aerospace optical systems to maintain high reliability and clarity of images. Ground and space contamination prevention, detection, and control are essential for the high-resolution space optical systems now in development or planned. In-depth studies have shown that contamination avoidance is feasible and enhances mission success. References SPIE 967: "Stray Light and Contamination in Optical Systems." The International Society for Optical Engineering, Proceedings 17-19, August 1988. SPIE 1329: "Optical System Contamination Effects, Measurement, Control II." The International Society for Optical Engineering Proceedings, July 10-12, 1990. SPIE 1754: "Optical System Contamination Effects, Measurement, Control III." The International Society for Optical Engineering, Proceedings, July 23-24, 1992. SPIE 777: "Optical System Contamination Effects, Measurement, Control." The International Society of Optical Engineering Proceedings, May 19-22, 1987. NASA SP-5076: "Contamination Control Handbook." Technology Utilization Division, Office of Technology Utilization, NASA, 1969. MSFC-SPEC-1443: "Outgassing Test for Non-Metallic Materials Associated with Sensitive Optical Surfaces in a Space Environment." Materials and Processes Laboratory, Marshall Space Flight Center, December 3, 1987. MSFC-SPEC-2223: "Outgassing Test for Materials Associated with Sensitive Surfaces Used in an Ambient Environment." Materials and Processes Laboratory, Marshall Space Flight Center, May 17, 1993. MSFC-STD-246: "Standard Design and Operational Criteria for Controlled Environmental Areas." Rev. B, Marshall Space Flight Center, NASA, March 1992. SP-R-0022A: "General Specification Vacuum Stability Requirements of Polymeric Material for Spacecraft Application." Johnson Space Center, NASA, September 9, 1974. PA 01: "Space Telescope Project, Wide Field Planetary Camera Cleanliness and Control Plan." Jet Propulsion Laboratory, California Institute of Technology, Pasadena, CA, May 16, 1978. CON 218: "Passive Contamination Control Monitoring Plan for the Hubble Space Telescope During Transportation through Launch." Lockheed Missiles and Space Company, Inc. Engineering Memorandum, July 14, 1985. MSFC-RQMT-691.8A: "Space Telescope On-Orbit Maintenance Mission Contamination Control Requirements." Space Telescope Systems Integration Branch, Marshall Space Flight Center, July 1984. K-DPM-11.96.1: "Contamination Control Implementation Plan for Hubble Space Telescope Maintenance and Refurbishment (HST M&R)." Kennedy Space Center, September 1987. FED-STD-209: "Clean Room and Work Station Requirements Controlled Environments." MIL-STD-1246: "Product Cleanliness Levels and Contamination Control Program." LMSC/D975220D: "Hubble Space Telescope Maintenance and Refurbishment Contamination Control Master Plan." Lockheed Missiles and Space Company, Inc. June 30, 1988. LMSC4176437D: "Hubble Space Telescope Contamination Control Program Plan." Lockheed Missiles and Space Company, Inc., January 30, 1987. LMSC/F157834: "Contamination Control Implementation Plan for HST Rework and Storage." Lockheed Missiles and Space Company, Inc., November 1, 1986. 52100.200.90.0039: "Advanced X-Ray Astrophysics Facility, VETA-1 Contamination Control Plan." TRW Space and Technology Group, Redondo Beach, CA, June 1, 1990. Reliability Preferred Practice PD-ED-1241, "Contamination Budgeting of Space Optical Systems." Reliability Preferred Practice PD-ED-1233, "Contamination Control Program." | This practice has been used on Apollo Telescope Mount (ATM), Hubble Space Telescope (HST), and High Energy Astronomy Observatory (HEAO). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
752 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Check Valve Reliability in Aerospace Applications |  | Failure to adhere to the practices described herein could result in internal or external leakage of the aerospace check valve or failure of the valve to open or close properly and quickly during operation. Internal leakage could be caused by the poppet failing to close, seat damage, contamination, and instability or chattering of the valve poppet. Internal leakage could result in detrimental back flow, loss of pressure downstream, and system malfunction. A variety of final effects could include improper response to control system commands, loss of fluids through purge ports, fire due to the mixing of hypergolic components, and engine or system premature shutdown, causing a mission delay or abort. | In check valve design for aerospace applications examine all design features, materials, and tolerances to evaluate the effects of contamination and exposure to cryogenic or hypergolic propellants. Conduct long term compatibility tests simulating the operational environment to assess material suitability for each unique application. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-ED-1267, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: The benefits of using special design and test procedures for aerospace check valves are long life, consistent operation, and trouble-free performance during prelaunch, launch, and orbital operations. Implementation Method: Introduction: Aerospace check valves allow fluid flow of propellants and gasses in one direction and, if the system pressure reverses, close quickly to prevent flow in the opposite direction. Aerospace check valves are normally self-contained, spring loaded devices, requiring no external actuation signals or sources of power. The valving elements are activated by the pressure forces of the flow media. Ball type check valves are suitable for smaller applications, while poppet type valves are more appropriate for large flows, such as in the Space Shuttle Main Engine (SSME) application shown on Figure 1. Internal check valve leakage due to contamination is the main reliability detractor for both types of valve, although other failure modes such as external leakage, failure of the poppet or ball to open, and poppet or ball chatter are other potential failure modes. Highly reliable check valves have been designed, built, installed, and operated for extended periods in launch vehicle and propulsion applications with no detrimental in-flight failures. [D] Figure 1. SSME Purge Check Valve Design Practices: Successful design practices have evolved that have resulted in failure-free aerospace check valve configurations. Large flow paths are provided through poppet-type check valves to reduce flow velocities and erosion of seats. Figure 1 is a cutaway view of the SSME purge check valve, a typical check valved used in aerospace applications. Teflon sleeves are provided for smooth operation and quick opening and closing of the poppets to permit rapid response to pressure differentials. Valve housings are configured to avoid areas that can trap contaminants. quotSwept-byquot designs are employed where the fluid flow tends to pass contaminants through the valve. Material compatibility with the working fluid is an important design consideration. The material evaluation includes dynamic as well as static implications, and considers temperature, pressure, and phase variations of the fluid. To minimize valve-induced contamination, material selection includes consideration of wear particle size on useful life. (Particle sizes vary as the Youngís Modulus divided by the square of the compressive yield stress.) Where threaded connectors are used, rolled threads are used in preference to machined threads to minimize burrs and to achieve higher strength. Pipe threads are avoided, and the check valve should have female threads to avoid thread damage. Dead-end passages and capillary passages are avoided. All materials and tolerances must be examined to account for material properties after exposure to fluids and contaminants. Testing should include exposure to fluids and contaminants in the failure mode operation. Materials compatibility testing is particularly important for check valves used to isolate bipropellant tanks of hypergolic systems where the valves can be exposed to both oxidizers and fuel vapors and their byproducts. Teflon in particular swells after exposure to nitrogen tetroxide vapor or liquid and adequate clearance must be provided in the valve after swelling to prevent binding of moving parts. Aerospace check valves work best in a contamination-free system, but where contamination is likely to be present, internal leakage due to contamination is minimized if the spring force is matched with material softness to ensure compression and closure. Self-aligning poppets or balls are desirable in most instances. System contaminants are identified to determine particle size and material properties. Metal-to-metal sliding parts are avoided as they not only are prone to produce contamination, but can also entrap externally induced contamination. Valving elements are designed with quick-opening areas to preclude chattering, flow instability, and high fluid velocities around the valve seat. Guidance of the poppet onto the valve seat to allow for a maximum alignment and eccentricity tolerance is achieved by providing a large diameter guide bearing surface length to poppet diameter ratio. (Minimum ratio should be 2:1). A finish of 16 or 32 microns root-mean-square is recommended. Positive stops are provided at the end of travel to minimize transient stresses due to poppet travel. Leakage rates are minimized by lapping poppet and seal surfaces to produce very smooth finishes. Reduced life due to vibration sensitivity is minimized by decreasing available clearances in bearings and guides, avoiding large overhung moments, and restricting lateral motion of poppets. Stress corrosion is controlled by avoiding stress corrosion susceptible materials and by designing the parts to operate at low stress levels. External leakage is minimized or eliminated by using welded valve body construction, requiring the use of vacuum-melt bar stock material, and by impregnating valve body castings with sealants. Process and Control Practices: Aerospace check valve parts are ultrasonically cleaned, assembled in specified clean areas, and controlled by a single contamination control specification during manufacturing, assembly, and testing. Test fluid media is governed by this same contamination control specification. Fabrication barriers (bags) are used to protect clean parts. Vendor controls are used to warrant that contamination particle size and count will not exceed specified limits. In some instances, a continuous purge of dry Helium is needed on the downstream side of check valves for cryogenic applications to prevent freezing of water vapor or atmospheric Nitrogen on the downstream sealing surface. Testing Practices: Contamination susceptibility tests are conducted during development to determine the levels of contaminant that the check-valve can tolerate. Verification of valve operation is achieved through 50 to 100 run-in cycles. Rapidly cycling valves designed for liquid applications for functional verification is not done in a dry condition because the lack of fluid damping can increase seat stress and reduce check-valve lifetime. Life cycle endurance tests and long term materials compatibility testing are conducted under operational environmental conditions. In launch vehicle applications, it has proven desirable to perform eight-cycle leak checks on each check-valve prior to launch. Integration and Application Practices: Aerospace check valves are often used in redundant configurations to increase reliability. Valves are installed into functional groups within systems using permanent connections, (such as welded or brazed connections) to avoid contamination and to prevent leakage. This type of installation allows a group of valves to be replaced in the event of a malfunction. Technical Rationale : The six purge check valves on the Space Shuttle Main Engine (SSME) have performed successfully in more than 67 missions to date without a failure. Five check valves used on the engine's pneumatic control system have performed equally as well in all missions. These check valves, and others used in the SRB and ET, were designed, built, tested, and operated in accordance with the practices described herein. References: SSME Orientation: Space Transportation System Training Data, Report # ME110(A)RIR, Rockwell International Corporation, December 1991. Long Life Assurance Study for Manned Spacecraft Long Life Hardware, Report #MCR-72- 169, Martin Marietta Corporation, September 1972. | This practice has been used on the Saturn Launch Vehicles, Space Shuttle Main Engine (SSME), Space Shuttle Solid Rocket Booster (SRB) programs. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
753 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Integrated Optical Performance Modeling of X-Ray Systems |  | Failure to employ optical performance modeling, coupled with inadequate testing and comparison with modeling results, could result in blurred x-ray images, inaccurate energy level results, and loss of scientific data. Repeat flights to regain lost data could be enormously expensive. | To ensure that high resolution mirror assemblies for grazing incidence x-ray optical systems meet their requirements, image quality must be predicted during design and verified during fabrication by modeling the system for in-orbit and x-ray test configurations. Computer based modeling programs should be used to verify that both the initial design and the as-built configurations will reliably produce the required image quality. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1264; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The use of computer-based models for integrated x-ray optical performance modeling will provide an independent check of optical systems design and will ensure high quality optical systems by providing in-process verification of the fabrication process. These models can save time and money in optical systems design and development, and should result in highly reliable x-ray imaging. Implementation Method: Software has been developed and is being refined to model the images produced by the grazing incidence optics of the Advanced X-ray Astrophysics Facility (AXAF-I) based on a number of optical system and mirror parameters. Commercial optical design and analysis programs are not tailored for grazing incidence mirror systems with their highly annular entrance apertures and cylindrically shaped mirrors. Analytical modeling is required to verify the design and to check fabrication in real time based on in-process mirror inspection metrology. A computer model has been developed that includes the effects of x-ray source position, x-ray source size, mirror figure errors, mirror surface roughness, mirror reflectivity, mirror alignment, and detector shape. Links are provided in the program to mirror surface metrology data and the mirror distortion predictions of standard structural analyses programs. Mirror figure errors are incorporated into a ray trace model by interpolating metrology data and structural model results onto a finely spaced grid. Individual surface parameters such as curvature and slope errors can also be applied to influence model results. The ray trace results can be convolved with the x-ray scattering predicted from the roughness of the mirror surfaces, and with the detector aperture shape and x-ray source size. An integrated, interactive program has been developed which will produce various two and three-dimensional image plots as well as parameters such as x-ray collecting area, root mean square image size, and image encircled energy distribution. This model is being developed as part of the AXAF-I project, but it is applicable to other grazing incidence x-ray optical systems. Figure 1 is an illustration of the Wolter I combined paraboloid/hyperboloid mirror system used for x-ray telescopes. [D] Figure 1. Combined Paraboloid/Hyperboloid Mirror Systems Used in X-ray Telescopes Where: r = radius z = coordinate along the optical axis (z = 0 at midpoint between the mirrors, z > 0 at system focus) r o = radius at z = 0 S = subnormal k = conic constant = 1 - e 2 2 = eccentricity ¦R¦ = ¦vertex radius of curvature¦ = [D] The mirrors are bodies of revolution around the longitudinal or z- axis. A flow diagram of the integrated optical performance computer model is shown on Figure 2. The model will produce a three-dimensional picture of the image intensity distribution as well as an X/Y plane contour map of this intensity distribution at preselected intensity intervals. These outputs can be compared with the ideal output configurations by running test cases from a collection of stored parameters and by comparison with the results of ground tests and the analyses of independent investigators. Contamination and gravity (weight) effects are not included in the model's parameters and must be considered separately. Gravity structural and thermal effects for the ground test can be analyzed by exercising the structural/thermal distortion program inputs. [D] Figure 2. Flow Diagram of Integrated Optical Performance Technical Rationale: Due to the expense of ground x-ray tests of precision grazing incidence x-ray mirrors for aerospace applications and the extensive time required for fabrication, it is imperative to have performance predictions ahead of time and to evaluate actual configurations in near real time as they reach completion during the manufacturing process. Optical performance modeling is necessary to ensure accurate and reliable performance before the mirror is put into service. References: Final Report: quotSoftware to Model AXAF Image Quality,quot Center for Applied Optics, University of Alabama in Huntsville, Huntsville, AL, June 1993. Zissa, D. E.: quotAXAF-I Performance Analysis Software Development,quot (a presentation), Marshall Space Flight Center, AL, February 1, 1994. quotSoftware for AXAF-I Performance Analysis,quot (a presentation), Center for Applied Optics, University of Alabama in Huntsville, February 1, 1994. D. E. Zissa: quotComparison of Ring-Focus Image Profile with Predictions for the AXAF VETA-I Teat,quot Proc. SPIE, Vol. 1742, pp. 91-103, 1992. P. Glenn, P. Reid, A. Slomba, and L. Van Speybroeck: quotPerformance Prediction of the AXAF Technology Mirror Assembly using Measured Mirror Surface Errors,quot Proc. SPIE, Vol. 830, pp. 278-282, 1987. M. Freeman: quotInterim Report, Transfit, Finite Element Analysis Data Fitting Software,quot Smithsonian Astrophysical Observatory Memorandum SAO-AXAF-DR-93-052, September 1993. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
739 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Design Considerations For Lightning Strike Survivability |  | Failure to adhere to the set of constraints, stated herein, could jeopardize the flight and mission success of any launch vehicle. | Implement lightning survivability in the design of launch vehicles to avoid lightning induced failures. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1231; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Experience learned from the Atlas/Centaur and Space Shuttle flights serve to emphasize the importance of the implementation of the proper protection/design enhancements to avoid and survive natural or triggered lightning for all launches. Implementation Method: Due to the lightning strike incident on Apollo 12, the AC-67 failure, and the numerous lightning strikes to the shuttle launch complex at 39-B, significant changes were made to improve electromagnetic compatibility (EMC) of launch vehicles and ground support equipment. The EMC approach is essentially the same for all of these vehicles with special considerations given to specific payload and launch requirements. The Atlas/Centaur and the Shuttle protection design are described in Reference 2. The major areas that a designer needs to address for lightning and transient hardening are: proper grounding of vehicle and ground support equipment, bonding requirements, and circuit protection. This is accomplished primarily through wire shielding and secondarily through transient limiters. Following the detailed requirements will limit the damage inflicted by lightning or high current transients. Ground Support Equipment The Launch System Fixed Service Structure (FSS) stands considerably taller than the airborne vehicle, creating a 45 degree quotcone of protectionquot relative to the vehicle (as illustrated in Figure 1). The probability of a lightning strike is a function of the design of the cone and the location of the object within the cone. The tower itself acts as a low impedance down conductor. [D] Figure 1. Shuttle Vehicle Complex Lightning Protection The ground support equipment (umbilical tower, service tower, etc.) must contain the appropriate conductive paths for lightning currents. These structures should follow the code in the quotU.S. Lightning Protection Code (NFPA-78)quot. The reason these requirements are placed on the structure is to avoid large potential differences between the lightning conductor and ground support equipment within the tower. All equipment susceptible to high current must be sufficiently grounded and bonded. Critical circuits are normally protected with transient limiters. All cable harnesses should have an overshield, which is grounded on both ends. Also, to protect against induced electromagnetic transients circuit wire twisting should be implemented. All wires and components connecting ground support equipment with payloads should be appropriately grounded. Circuits or components which interface with the vehicle should be hardened against lightning transients and electromagnetic interference. The following lists the recommended practices for circuit protection: a) Lightning suppression devices and appropriate mechanisms should be placed at areas of critical circuit interfaces and in current loop areas where potential differences can be substantial during direct and induced lightning strikes. Such areas would be the inertial navigation unit (INU) uplink and data acquisition system (DAS) downlink circuit interfaces and telemetry connections. b) Individual equipment should be grounded to facility structure when ground support equipment is installed. c) Items subjected to transient charging must meet MIL-B-5087 (Class S) bonding requirements. Components should be connected to the tower facility grid. d) Heavy gauge grounding cables should be instituted to ground external items to major structural members. e) Auxiliary grounding straps should be employed, as needed, to relieve differences in potential for items being mated and demated. Airborne Vehicle Equipment Airborne vehicle equipment consist of the launch vehicle and the payload (satellites, experiments, etc.). Since lightning will predominately strike the nose or fairing of a rocket, the equipment contained there should be shielded to withstand the current and induced effects. To protect the vehicle and components, several lines of defense are used starting with the vehicleís structure, bonding requirements, and cable shielding. In order to protect the internal equipment, a large conductive surface must extend the length of the vehicle. This is easily resolved by constructing an all metal surface vehicle with adequate bonding between the stages. With composite skin vehicles, a cable raceway is needed to extend the entire length of the vehicle, and conductive paint should be used on the skin. All memory sensitive devices should be EMI hardened and placed far from the raceway. The purpose of overall airborne system bonding is to maintain an equipotential system (see Figure 2). To ensure this all tank sections should be welded and bonded to achieve a low impedance reference plane. All metallic parts of linear length greater then 12 inches should have a discharge path to structure. In launch vehicles all critical areas must follow MIL-B-5087B (Class R) or NSTS 07636 bonding to satisfy NASA bonding requirements. The bonding of all electrical components (connections, metallic plumbing, etc.) is mandatory to achieve an equipotential environment. This is important in areas where large current loops might be formed (see Figure 2) or on the vehicle where critical electrical components are found. All areas should follow the MIL-B-5087B (Class S & R) or NSTS 07636 requirements for electrical bonding. The designer should also note that adequate cross-sectional area and skin area must be taken into account when applying the bonding requirements. All connection surfaces must be free from insulation material and foreign material such as, paint, oxide, and corrosion. It is also important to reduce sharp bends in conductors. Sharp bends cause high conductor separation forces and are areas of high impedances to the leading edge of the current pulse; more importantly, they are potential arcing points. [D] Figure 2. Example of Ground Plane Bonding on the Atlas/Centaur Shielding guidelines were established after the critical failure of AC-67. In order to reduce magnetic induced voltages in cable wires, it is possible to design cables such that the induced voltages can be self-cancelling. This is completed through twisted-pair wiring enclosed by a copper braid shield. The following shielding list can be applied to all launch vehicles. a.) Power and Low Frequency. Twist the power or signal wire/wires with its return line. This should be referenced to the vehicle structure on both ends. Any power lines leading to inductive loads that are not locally diode suppressed should be shielded with the shield grounded on both ends. Do not shield power leads between power supply and a subsystem, or between units of a subsystem. b.) Radio Frequency Circuit Shielding. RF circuits or circuits susceptible to RF should have the outerbraid of the coaxial cable grounded at both ends and all points along the length of the shield as necessary. c.) Digital Data Lines. Use a shielded twisted pair with the shield being grounded at both ends. d.) Ordnance Circuit Shielding. Twisted shielded wire should be used from electroexplosive devices to the ordnance power switching device. The shields should be grounded at both ends. e.) Memory Device Shielding . Due to the difficulty in predicting the shield attenuation on at metallic structural corners, an adequate safety margin should be used for protection against excessive interior flux. f.) Rules for Circuit Shielding. Circuits with impedances greater than 100 ohms or are sensitive to high frequency must have the twisted pairs shielded. All circuit shields should be grounded to structure at both ends of the circuit via the connector backshell. g.) Harness Shielding. All cable or harness shields must be terminated at both ends of a conductive EMI backshell. The 360 degree peripheral shield termination technique should be applied. In order to reduce the amount of induced effects caused by lightning, it is important that the electrical wiring follow the requirements for shielding. This will limit the possibility of quotnoisequot throughout the system or quotcircuit upsetquot. The designer should also consider the possibility of using fiber-optic cables, thus eliminating the susceptibility to the electromagnetic effects of lightning. This can be applied in the areas for control, data, and transmission lines. Structural Design Provisions. In addition to hardening the electrical system, structural designs should avoid susceptibility to triboelectric or frictional charging. Fairings should be of an all metal stringer construction. This encases the inertial navigation unit and all electrical components in a Faraday cage enclosure (Ref.4 &5). Technical Rationale: All ground station equipment and airborne vehicle equipment should be hardened against lightning transients and electromagnetic interference. When lightning strikes an object, current flows and voltages are produced across impedances. The voltage becomes large if the impedance is high, and thus produces substantial arcing. This occurred on AC-67 during flight resulting in a improper yaw command and destruction of vehicle and payload. Arcing and circuit upset can even occur if lightning does not strike directly, but discharges nearby producing a high magnetic flux which will induce a current in the electrical components. This was observed while AC-43 was on the launch pad resulting in several components experiencing circuit upset. As a result of these modifications and improvements, the flight history of Atlas II has not been affected by lightning transients or electromagnetic interference (EMI). Compliance with transient and bonding requirements, harness shield termination improvements incorporated throughout the system will provide the necessary immunity to any lightning-induced effects at the unit/subsystem level. References: Atlas/Centaur AC-67, quotProblem Report Closeout,quot No. AK44901 CT, General Dynamics Space Systems Division, 1987. AFSC DH 1-4, quotElectromagnetic Compatibility,quot4th ed., March 1984. Gabrielson, Bruce C., The Aerospace Engineerís Handbook of Lightning Protection, Interference Control Technologies, Inc., Gainesville, VA, 1988. Hasbrouck, R.T. , Lightning-Understanding It and Protecting Systems from Its Effects, Lawrence Livermore National Laboratory, 1989, UCRL-53925. Hart, William C. & Malone, Edgar W., Lightning and Lightning Protection, Don White Consultants, Inc., Gainesville, VA, 1979. KSC-STD-E-0013, quotFacility Lightning Protection Design Standardquot. MIL-B-5087B, quotBonding, Electrical, and Lightning Protection, for Aerospace Systems,quot October, 1964. NSTS 07636, quotSpace Shuttle: Lightning Protection, Test and Analysis Requirements,quotNovember 1991. NSTS 16007, Revision F, quotLaunch Commit Criteria and Background,quot NASA, 1992. quotReport of Atlas/Centaur-67/FLTSATCOM F-6 Investigation Board Vol. I-Final Report,quot NASA, July 15, 1987. NFPA-78, quotU.S. Lightning Protection Codequot. Fisher, F.A. & Plummer, J.A., Lightning Protection of Aircraft, Lightning Technologies, Inc. SL-E-0002, quotNSTS EMI Characteristics, Requirements For Equipmentquot. Electrical Shielding of Power, Signal and Control Cables - Reliability Preferred Practice No. PD-ED-1213 Electrical Grounding Practices for Aerospace Hardware - Reliability Preferred Practice No. PD-ED-1214 | This practice has been used on Saturn, Atlas/Centaur, Titan, Space Shuttle. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
740 | Oberhettinger, David - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, David - 0000000000 : NO@ADDRESS.GIVEN |  | Deficiencies in Mission Critical Software Development for Mars Climate Orbiter (1999) | The root cause of the MCO mission loss was an error in the “Sm_forces” program output files, which were delivered to the navigation team in English units (pounds-force seconds) instead of the specified metric units (Newton-seconds). Comply with preferred software review practices, identify software that is mission critical (for which staff must participate in major design reviews, walkthroughs and review of acceptance test results), train personnel in software walkthroughs, and verify consistent engineering units on all parameters. | Non-compliance with preferred software review practices may lead to mission loss. To identify mission critical software, require concurrent engineering and thorough review by a team of systems engineers, developers, and end users. See Lesson No. 0641, Recommendation #12 For all mission critical software (or software interfaces between two systems or two major organizations), systems engineers, developers, and end users should participate in 1) major design reviews, 2) walkthroughs of requirements, design, and acceptance plans, and 3) examination of acceptance test results. See Lesson No. 0641, Recommendation #2, 8, 11 Train personnel in the proper conduct of software walkthroughs, including disseminating minutes to appropriate management, tracking action items, and reporting liens. See Lesson No. 0641, Recommendation #5 For mission critical software, specify and require verification of consistent engineering units on all parameters. See Lesson No. 0641, Recommendation #1 | Same as in Lesson Learned | JPL | 02/24/2000 | Upon arrival at Mars in September 1999, the Mars Climate Orbiter (MCO) began a scheduled 16-minute Mars orbit insertion (MOI) maneuver to achieve orbit. Approximately 49 seconds before the anticipated occultation by Mars, communication was lost and never reestablished. The root cause of the mission loss was an error in the "Sm_forces" program output files. The JPL MCO review board determined that the files containing the magnitudes of the small impulses applied to the spacecraft had been delivered by the Spacecraft Operations Team to the Spacecraft Navigation Team in English units (pounds-force seconds) instead of the specified metric units (Newton-seconds). See Lesson No. 0641, first paragraph under Lesson Learned The discrepancy in these files led to an underestimate (by a factor of at least 4) of the influence of the twice-a-day momentum wheel desaturation burns on the spacecraft trajectory. The cumulative effect of these small impulses led to a 169 km navigation disparity, which was catastrophic to the mission. The erroneous engineering units provided by these files to the navigation software were not discovered in the walkthroughs of requirements, design, code, and testing. Contrary to preferred practice: The "Sm_forces" software was misclassified as non-mission critical, which reduced the rigor of the review program. The Software Management and Development Plan (SMDP) was not followed in the walkthroughs of the "Sm_forces" software, and the overall training in the software walkthrough process was not adequate. Specifically, required persons were not always in attendance, the Software Interface Specification (SIS) was not used, minutes were not taken, and action items were not published. An (end-user) navigation representative was not specifically requested to be present at any of the major development phase reviews, software walkthroughs, or the software acceptance test. The "Sm_forces" software interface with navigation software was not tested. There was no flowdown of requirements from the higher-level MCO SIS to the software requirements document. The "Sm_forces" requirements specification did not state the required engineering units for parameters. References: Report on the Loss of the Mars Climate Orbiter Mission, JPL D-18441, JPL Special Review Board, November 11, 1999. Phase I Report, (NASA) Mars Climate Orbiter Mishap Investigation Board, November 10, 1999. "Mars Climate Orbiter Mishap Investigation Board - Phase I Report", Lesson Learned Number 0641, December 1, 1999. Corrective Action Notice No. Z66254, MCO-JPL/SRB Finding 4.2: "Software Development Process," November 23, 1999. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.11.1 ("Engineering Practices: Software Development"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.11.3.3 ("Flight Software System Design: Interfaces - Parameter and Argument Specification"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 04/04/2000
890 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | High Performance Liquid Oxygen Turbopumps |  | Failure to design-in and build-in reliability measures that have been found to create successful operation of the SSME HPOTP could result in less than nominal performance, loss of mission objectives, loss of the vehicle, or loss of life. More likely, subtle inactions or inattention to detail could cause lifetime of the turbopump to be reduced due to the discovery of flaws upon inspection and/or disassembly. | Unique cooling, sealing, draining, and purging methods, along with precision interference fits and vibration damping methods are used in high performance liquid oxygen turbopumps. Coatings and dry lubricants are used to provide protection against cracking, fretting, and generation of contamination. Silicon nitride bearings resist wear and provide long life. | MSFC | 12/01/1994 | This Lesson Learned is based on Reliability Practice number PD-ED-1269, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. The use of special design features, materials, and coatings in high pressure liquid oxygen turbopumps will prevent inadvertent overheating and combustion in the liquid oxygen environment. Special sealing, draining, and purging methods prevent contact between the oxygen in the pump section and the hydrogen rich gasses that drive the turbine. These precision design and manufacturing procedures prevent latent or catastrophic failure of the LOX turbopump. Silicon nitride bearings, coupled with other bearing enhancements, prevent bearing wear in advanced LOX turbopumps. Implementation Method: I. Background The high pressure oxidizer turbopump (HPOTP) of the Space Shuttle Main Engine raises the pressure of liquid oxygen flowing to the main engine combustion chamber injector and preburner injectors sufficiently to ensure positive injection of oxygen into the chambers at all thrust levels. Its centrifugal pump contains both a double-entry main impeller and a single entry preburner oxygen boost impeller. The pump bearings are cooled by internal flows of oxygen from points of higher pressure to points of lower pressure. A hollow retaining bolt and hollow turbopump shaft provides a liquid oxygen coolant flow path to two of the pump bearings. The other two bearings are cooled by liquid oxygen that flows down the back face of the preburner pump impeller, through the hub seal, through the bearings, and into the main pump inducer. The pump bearings consist of two matched pairs of angular-contact ball bearings whose inner races are clamped and whose outer races are preloaded. Excessive axial loads are counteracted by two balance cavities which lie between the front faces of the impeller and adjacent stator rings. The HPOTP turbine is a two-stage, cantilevered turbine powered with hot, hydrogen-rich gas generated in the oxidizer preburner. The second stage turbine wheel is an integral part of the turbopump shaft and the first stage wheel is bolted to the second stage wheel. II. Special Considerations for High Pressure Oxidizer Pumps Because of the oxygen environment, any condition that results in heat generation must be avoided to prevent inadvertent combustion. Contamination, rubbing, and cracking of components are closely monitored and controlled. More stringent tolerances are required in LOX turbopumps than hydrogen turbopumps, and silver plating is used rather than gold plating because silver does not as readily decompose in an oxygen environment. The cantilevered turbine, coupled with the heavier fluid being pumped, creates a greater load on the oxygen pump bearings. Operation of the bearings in an oxygen environment with these high loads increases their susceptibility to wear. Routine tear-down and inspection of bearings is required to ensure continued reliable operation. The use of silicon nitride bearings has shown promise in long-term component tests for longer lifetime and greater wear resistance. The addition of a preburner liquid oxygen pump to the main liquid oxygen pump makes the pump design more complex. Multiple interference fits require precision assembly procedures. III. Sealing, Draining, and Purging Between Liquid Oxygen and Hydrogen-Rich Turbine Gasses To prevent contact between the liquid oxygen being pumped and the hot, hydrogen-rich gasses that drive the turbine a sophisticated three-cavity labyrinth seal is used. The first cavity next to the turbine drains the fuel rich gasses overboard. The second cavity is purged with helium to eliminate any other fluids or gasses that may leak in from the first and third cavities, and the third cavity drains off liquid oxygen that leaks in from the oxygen pump side. Cavity pressures are carefully monitored and represent redline values for engine control. It was found early in the SSME liquid oxygen turbopump development effort that three-step shaft mounted labyrinth seals with stationary plastic wear rings were superior to bellows loaded hydrodynamic liftoff seals for isolation of pumped liquid oxygen and turbine hydrogen. IV. Reduction of Vibration and Addition of Damping Provisions Vibration of liquid oxygen turbopumps, can be reduced significantly by careful analysis of the dimensions, weights, and clocking of turbopump components on the turbopump shaft. Precision optical methods have been developed for computer-based balancing of turbopumps through precise assembly of components at the proper rotational position on the shaft. Two-piece dampers were installed on the first stage turbine blades to reduce dynamic stress and to eliminate transverse blade shank cracks. Resonant frequencies are reduced by the proper design of seals. Internal clearances for bearings was increased by elongating cage pockets in the turbine and preburner pump bearings. V. Design, Fabrication, and Assembly Practices An effective means of controlling or eliminating cracking in the high pressure oxidizer turbopump components has been to provide higher radius fillets. Assembly process improvements have aided in the effective disassembly, inspection, and reassembly of the turbopump when required. For example, Hot Isostatic Pressure (HIP) Process was performed on turbine nozzle castings to eliminate near-surface porosity. A visual inspection system was developed for the inspection of turbine blades. Bearing defect specifications were tightened, as were the specifications for protective platings and installation procedures. VI. Alternate Liquid Oxygen High Pressure Turbopump To extend the operational lifetime of liquid oxygen turbopumps for the Space Shuttle Main Engine, an alternate turbopump development program was undertaken by MSFC in conjunction with the cognizant contractors. In the new turbopump development effort, it was necessary to eliminate bearing wear and distress of the pump-end ball bearings, which was the primary failure mode in early development tests. Potential failure mechanisms that were investigated were: (1) misalignment, (2) inadequate prelubrication, (3) bearing cage instability, (4) inadequate inner bearing race clearance, (5) high fixed and dynamic loads on the bearings, (6) inadequate cooling (7) inadequate lubrication, (8) high ball/race heat generation, and (9) inappropriate bearing material configuration. In a detailed fault-tree-based investigation, all but items (6), (7), and (8) were eliminated as not being a likely cause or at the most being a secondary factor in excessive bearing wear. Inadequate cooling can be caused by an inadequate source pressure and resulting inadequate coolant flow rate or by a higher than required coolant temperature. Lubrication of bearings of cryogenic rocket engine turbopumps have traditionally depended upon the transfer of a polytetrafluorethylene (PTFE) film from the bearing cage by rubbing to the bearing balls and races. This film must be of adequate thickness to achieve adequate lubrication. Excessive heat generation is a function of the friction factor of the materials, the contact loads, and bearing geometry. The corrective actions taken to eliminate bearing wear were to improve the coolant supply at the inner bearing race ball contact, to use an outer race guided cage, and to use silicon nitride ball bearings. Larger ball-to-cage pocket clearances were provided, prelubrication was used on the inner race only, and a colder coolant was directed to the inner race. These changes were completely successful in correcting the advanced liquid oxygen turbopump pump-end bearing wear problem. No wear of these bearings has been observed since these incorporations. Technical Rationale: The Space Shuttle Main Engine Turbopump has operated successfully in over 200 flight uses, and has steadily improved in resistance to potential failure through three major design phases. Nine improvements were made from Phase II to reflight after Challenger, and ten improvements have been made since the Challenger accident. Engineers at MSFC and the prime contractor continue to closely monitor performance during flight and the condition of the turbopump after flight to determine if additional improvements are necessary to continue to maintain the SSME's record of high reliability. References Engineering Change Proposal #11-17R1: Space Shuttle Main Engine, Rocketdyne Division of Rockwell, International, Canoga Park, CA, 1988. Space Transportation System Training Data: Report No. ME-110(a) R1R, Rocketdyne Division of Rockwell, International, Canoga Park, CA, December 1991. Reliability Preferred Practice PT-TE-1439, 'Systems Test Considerations for High Performance Liquid Rocket Engines.' Reliability Preferred Practice PD-ED-1268, 'High Performance Liquid Hydrogen Turbopumps.' | This practice has been used on the Space Shuttle Main Engine, Liquid Oxygen Turbopump, and Alternate Turbopump Program. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
750 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | High Performance Liquid Hydrogen Turbopumps |  | Insufficient sealing of hydrogen liquid or hydrogen gasses in the fuel turbopump could cause improper operation and/or loss of hydrogen to the environment, causing a potential catastrophic fire or explosion. Failure of bearings or turbine blades could cause loss of power and turbopump in operation. Failure to operate could result in mission abort, and an explosion could cause loss of life as well as the mission hardware. | Understanding and addressing the design environment, component interactions, and potential failure modes are the keys to high reliability in high performance liquid hydrogen turbopumps for launch vehicle engines. Designing and using a combination of unique sealing, cooling, processing, material selection, and balancing techniques in response to engine design requirements will permit the development, production, and reliable flights of hydrogen turbopumps. | MSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-ED-1268, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Use of precision design; manufacturing; and advanced material selection, fabrication, and treatment techniques will ensure reliable operation of large, high performance liquid hydrogen turbopumps. Many of these practices will also lengthen the operational life of the turbopump, increasing the number of uses before teardown, inspection, refurbishment, and re-assembly for subsequent flights. In addition to higher reliability, lower costs and continued assurance of high performance are resulting benefits. Implementation Method: I. Background: The 85,000 horsepower liquid hydrogen turbopump being flown on each flight of the Space Shuttle represents almost three decades of design, development, and fine-tuning of its performance and reliability. It is a three-stage centrifugal pump driven by a two-stage hot gas turbine. The pump rotates at 37,000 revolutions per minute (RPM) which is over 600 revolutions each second. The high horsepower, high RPM, high flow rates, and high pressures in this turbopump created a unique set of design and engineering challenges to the prime contractor and to NASA (Marshall Space Flight Center). Problems have been encountered over the years that manifested themselves in bearing wear, turbine blade cracking, turbine blade erosion, and rotodynamic issues. In overcoming these problems, specific design features, materials, and fabrication methods have been developed and perfected for the hydrogen turbopump that permit the Space Shuttle Main Engine (SSME) to maintain its unprecedented high performance while exhibiting manned space flight levels of reliability. The practices that have been developed and included in this document are essential to the continued high reliability of the SSME and can also be applied in next-generation turbopumps for reusable and expendable launch vehicles. II. Bearings and Blades The two major components of the fuel turbopump that have required focused engineering and manufacturing attention are the turbopump bearings and the turbine blades. Both the bearings and the blades have performed well in initial firings and flights of the engine, but have resulted in unsatisfactory condition reports when subjected to detailed inspection on disassembly after flight. The bearings have exhibited wear before their expected rated lifetime has been reached, and tiny hairline cracks have been observed in the turbine blades. Fractures in bearing cages were discovered during disassembly inspection of the turbopump in early engines. Investigations indicated that the failures were most likely due to high cycle fatigue; and stress analyses showed a marginal factor of safety on high cycle fatigue for "infinite" life. Post disassembly inspection of some engines also revealed rub marks, evidence of wear, and indentations on bearing races and balls. Although the slightly damaged bearings were still suitable for development testing, a bearing wear potential prior to end of rated life still exists. Reliable, long-life fuel turbopump bearings are made possible by sophisticated cooling arrangements and by careful material selection. The fuel pump bearings are cooled by internal flows of liquid hydrogen. The coolant source for pump-end bearings, including an axial load-carrying thrust bearing, is the output of the first impeller of a three-impeller fuel pump. Liquid hydrogen flows from the back face of the impeller through orifices in the impeller hub, through the bearings, and back into the pump inlet. The bearing inner races are clamped to the pump shaft with the bearings free to slide axially within the bearing cartridge. Liquid hydrogen performs the function of a highly effective coolant because all heat is removed from the bearings, resulting in very little, if any, bearing wear. Bearing specifications are very tight, minimizing bearing defects. An alternate bearing material, silicon nitride has successfully demonstrated long life in oxygen turbopumps and the same benefits are expected in hydrogen turbopumps. The provision of ample cross-sectional area and the addition of Fluorinated Ethylene Propylene (FEP) coating to the bearing cages eliminated a bearing cage cracking problem. The turbine blades experience enormous centrifugal force loads as well as high thermal loads at 600 revolutions per second. High cycle fatigue and hydrogen embrittlement effects, have caused small hairline cracks in the turbine blades of the high pressure fuel turbopump. These cracks are an order of magnitude shallower than the critical depth of 0.100 inch, but have persisted throughout the program. Although the hairline cracks are not detrimental to performance, periodic disassembly inspection is needed to continue to monitor this condition. Attention is given to blade porosity after machining (less than or equal to 5 mil pores). Shot peening of blades on the blade-to-wheel interface improves toughness and resistance to cracking. Gold plating of blade shanks resists hydrogen embrittlement. An important design feature in the turbine blade-to-wheel connection is a "loose" fit that gives the blades freedom to adapt to dynamic turbine environments. III. Turbopump Seals One of the keys to high reliability liquid hydrogen turbopumps is the use of a variety of compression and flow restricting seals. The compression seals, which include gaskets and piston rings, contain the liquid hydrogen and hot gas inside the pressure vessel or chamber. Flow restricting or flow redirecting seals restrict liquid hydrogen and hot gas flow in one direction and/or redirect flow in another. The principal types of seals are pump interstage (or "damping") seals, fluorocarbon seals, liftoff seals, labyrinth seals, platform seals, and turbine blade tip seals. The interstage seals permit a small amount of liquid hydrogen to flow between impeller stages. A knurled surface on the seals at the impeller interface slows down axial and circumferential flow of liquid hydrogen and traps enough fluid to provide cooling and vibration damping. Stepped fluorocarbon seals that contact ridges around the impeller face on all three pump stages control the amount of propellant flow around the impeller front shrouds. The liftoff seal assembly, which acts as a check valve ---permitting flow in only one direction---prevents hydrogen leakage into the turbine end of the turbopump prior to engine start and after engine cutoff. During engine start, a pressure unbalance develops across the seal to offset the spring load and retract the seal, allowing liquid hydrogen to enter and cool the turbine end. A turbine hub labyrinth seal directs part of the coolant flow from the liftoff seal to the bearings, disc, and coolant liner to cool the turbine end bearings and discs. Forward and aft platform seals restrict flow and enhance cooling balance while maintaining efficiency of the first and second stage turbine wheels. Turbine blade tip seals help direct hot gas flow through the turbine blades, improving turbine efficiency. One of the most critical seals in the high pressure fuel turbopump is the lift-off seal. Avoidance of contamination is important because it must act as a static seal when closed. It must avoid trapping contamination, and work properly repeatedly in the dynamic engine environment. Repeated and consistent response to pressure differentials is required. The seal must resist rubbing and wear while retaining its capability to pass fluids reliably when open and to seal off fluids completely when closed. The seal is a complex component in itself, incorporating 55 springs, guide bushings, carbon nose, adaptor, retainer plate, and additional secondary seals. IV. Materials and Fabrication Methods Because of the hydrogen environment, the wide temperature ranges, the high structural and thermal stresses, and the close tolerances encountered in the turbopump; a thorough knowledge of material properties is necessary, and precision fabrication methods must be used. A variety of manufacturing techniques are used such as TIG (tungsten inert gas) welding, EDM (electrodischarge machining), conventional machining, investment casting, CNC (computer numerically controlled) machining, broaching, grinding, polishing, and burnishing. Directional solidification is used when casting the turbine blades to produce grains parallel to the major operational stresses. Copper and gold coating and plating techniques are used to protect certain critical components such as turbine housing struts and the blade attachment "firtree" slots in the turbine discs from hydrogen embrittlement. Replacement of sheet metal components with castings eliminates and/or reduces potential hardware failures due to welding defects. Replacement of some titanium rotating components with Inconel 718, the addition of a baked-on dry film lubricant, the use of stellite bore inserts, and the use of knurled pump inserts to smooth out and enhance the damping characteristics of coolants resulted in beneficial improvements in turbopump reliability and lifetime. V. Advanced Design and Inspection Methods Advanced computer simulations are now available to characterize the flows, stresses, and thermal environments in rocket engine fuel turbopumps. Computer analyses, well anchored and authenticated by thoroughly instrumented tests, will do much to provide the most reliable and effective turbopump design. Verification of design environments is essential. Advanced computed tomography inspection of critical fuel turbopump components such as the first and second stage turbine blades has been proven to be an effective way to screen the hardware for potential blade failure modes. Sophisticated analytical techniques and precise balancing methods were used in solving a "subsynchronous whirl" problem that caused spurious turbopump vibrations. Technical Rationale: Specific design features, materials, and fabrication methods must be used in high performance liquid hydrogen turbopumps to ensure satisfaction of performance requirements while exhibiting manned space flight levels of reliability. References Engineering Change Proposal #11-17R1: Space Shuttle Main Engine, Rocketdyne Division of Rockwell, International, Canoga Park, CA, 1988. Space Transportation System Training Data: Report No. ME-110(a) R1R, Rocketdyne Division of Rockwell, International, Canoga Park, CA, December 1991. "Space Shuttle Main Engine Instrumented High Pressure Fuel Turbopump Technology Test Bed Testing Results Summary," AIAA Report No. 93-1908, June 28-30, 1993. "Fabrication of the Space Shuttle Main Engine High Pressure Fuel Turbopump," Marshall Space Flight Center, Huntsville, AL, April 1994. "Solution of the Subsynchronous Whirl Problem in the High Pressure Hydrogen Turbomachinery in the Space Shuttle Main Engine," Paper # 78-1002, AIAA/SAE 14th Joint Propulsion Conference, July 25-27, 1978. Reliability Preferred Practice PT-TE-1439, "Systems Test Considerations for High Performance Liquid Rocket Engines." Reliability Preferred Practice PD-ED-1269, "High Performance Liquid Oxygen Turbopumps." | This practice has been used on the Space Shuttle Main Engine, Liquid Hydrogen Turbopump, and Alternate Turbopump Program. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
751 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Binary and Hybird Optics for Space Applications |  | Failure to apply binary and hybrid optics technology in space applications could result in higher weight, higher cost, less reliable systems than possible using these emerging technologies. | Binary (diffractive) optics combined with conventional (refractive) optics offer a significant potential for space optics reliability improvement. | MSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number PD-ED-1266, from NASA Technical Memorandum 4322A, Reliability Preferred Practices for Design and Test. Benefit: Improved ruggedness, reduced size, and greater opportunity for redundancy are the potential benefits of using binary and hybrid optical systems for space applications. Hybrid optical systems can be designed that are less sensitive to color (or chromatic variations) and to temperature variations. When combined with conventional optics, binary optical systems can correct for spherical aberrations. Implementation Method: Binary Optics: Binary (diffractive) optics uses computer-aided design (CAD) tools and very-large-scale-integration (VLSI) electronic circuit manufacturing technology to create novel optical devices and to provide design freedom and new materials choices for optical elements. When combined with conventional (refractive) optical lens systems, binary optical systems cannot only provide athermalization and achromatization, but offer the opportunity for miniaturization, significant weight savings, and resulting opportunity for redundancy in aerospace telescope systems, sensors, vision systems, and microelectronic optical systems. While conventional optics lenses are polished to a desired profile, binary optics uses high resolution lithography (the design and replication process used in electronic circuit fabrication) to transfer a binary surface relief pattern to the optical element. This pattern is then etched into a surface using ion-beam etchers. A single etching step produces a two-level surface, thus the term ìbinary optics.î The etching process can be repeated with different etch depths to produce multi-level optical elements. A binary coded set of lithographic masks can double the number of phase levels with each etching step. For example, four etching steps result in a 16-level optical element with a theoretical diffraction efficiency of better than 99 percent. The etch profile approximates a continuous phase surface. Hybrid Optics: Hybrid diffractive/refractive lenses are being considered for NASAís Geostationary Earth Observatory (GEO) to reduce weight and increase reliability of its sensors, telescopes and imaging systems. Hybrid lenses can be built that weigh less than half of conventional lenses, offering the possibility of providing redundant systems. Since the color separation properties of binary optic lenses are opposite in sign to those of a traditional lens, achromatic, lenses can be constructed using combined diffractive/refractive elements. Certain optical materials, particularly plastics and infrared materials, have optical and mechanical properties that may cause decreased performance over a wide temperature range. For space applications, the unique properties of diffractive lenses offer significant advantages in this regard when used in combination with traditional refractive or reflective systems. Temperature compensation may also be achieved in an optical system mounted in a housing that is subject to expansion or contraction in various thermal environments. It is possible to design an element that contains both refractive and diffractive surfaces such that the change in focal length with increasing or decreasing temperature is equal to the change in position of the image detector in relation to the lens. Optical technicians have developed an opto-thermal expansion coefficient that is used to design athermalized lenses that combine refractive and diffractive surfaces. Opto-Electronics: Since binary optics are fabricated using the same equipment and techniques used to make semiconductor chips, the next step is to fabricate binary optics into the chips themselves, which results in opto-electronic assemblies with built-in processing functions. Micro-optic lens arrays can be integrated with semiconductor detector arrays to produce compact, lightweight, rugged, integrated imaging/detector systems. If the system is spaceborne, radiation resistance can be improved, since each smaller active detector element now presents less cross sectional area for gamma ray interactions. Technical Rationale: Binary and hybrid optics have created a revolution in the way lenses, and ultimately, opto-electronic systems are designed and manufactured. Hybrid optics combines the best features of diffractive and refractive optics technology. Many highly reliable types of hybrid lenses, filters, multiplexers, and diffractive coatings have recently become feasible. By applying a mixed optics approach to system design and fabrication, the number of series elements in a complex system can often be halved, improving reliability. The lower weight of the systems, in addition, offer the opportunity of increased redundancy through the use of multiple backup systems. Further evidence of the usefulness of these technologies should become evident as they are put into practice. References: Behrmann, Greg: "Influence of Temperature on Diffractive Lens Performance," Applied Optics, May 1993. Behrmann, Greg: "A Hybrid Approach Opens the Door to Diffractive Optics," Photonics Spectra, May 1993. Morris, G. Michael: "Diffractive and Binary Optics," University of Rochester, Rochester, NY, January 1994. Morris, G. Michael: "Diffractive Optics Technology and the NASA Geostationary Earth Observatory (GEO)," Rochester Photonics Corporation, Fairport, NY, July 31, 1992. Veldkamp, W.B.: "Binary Optics: A New Approach to Optical Design and Fabrication," Optics News, December 1988. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/04/2000
738 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Problem Reporting and Corrective Action System |  | Hardware/software problems that require further investigation may not be identified and tracked. Development of corrective action and need for improvement will not be highlighted to engineering. Opportunities for early elimination of the causes of failures and valuable trending data can be overlooked | A closed-loop Problem (or Failure) Reporting and Corrective Action System (PRACAS or FRACAS) is implemented to obtain feedback about the operation of ground support equipment used for the manned spaceflight program. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1255; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The information provided by Proplem Reporting and Corrective Action System (PRACAS) allows areas in possible need of improvement to be highlighted to engineering for development of a corrective action, if deemed necessary. With this system in place in the early phases of a program, means are provided for early elimination of the causes of failures. This contributes to reliability growth and customer satisfaction. The system also allows trending data to be collected for systems that are in place. Trend analysis may show areas in need of design or operational changes. Implementation Method: A closed-loop system that collects, analyzes and records failures that occur is developed. Documented procedures for the analysis of failures to determine their root cause and then the establishment of effective corrective action are also developed. This aids in the prevention of future reoccurrences by elimination of problem areas in the equipment. Technical Rationale: Figure 1 illustrates the closed loop PRACAS with the necessary steps required to get full use out of such a system. This continuous loop provides the program with the opportunity to fine tune hardware reliability and performance through repeated iterations of reporting and corrective action. [D] Figure 1. Closed-loop Problem Reporting and Corrective Action System Essentially the system must provide information on: What was the failure? How did the failure occur? Why did the failure occur? How can such failures be prevented from occurring in the future? The documentation procedures should include instructions for initiating problem reports, analyzing the failure and method of providing corrective action to the design and operation of the equipment. The most important step in the process is documentation of the problem. The quality of the document will determine the effectiveness of the PRACAS for creating an acceptable solution. Minimum documentation for the problem should include: The location of the failure The date and time of the failure The applicable part numbers, serial numbers, model numbers The operation being performed The failure symptom The name and number of the reporting individual(s) The environment under which the failure occurred The impact of the failure on hardware and personnel safety For each test-related failure, a quotStress statementquot on whether or not the failure induced any stress in the hardware. A means should also be available for tabulating the failure information for determining trends and the mean-time-between-failure of the equipment. Besides being useful to design and reliability engineering, this information may also be useful to maintenance personnel for determining maintenance periodicity of the equipment already in use. Failures that require quotstress statementsquot shall include test failures, operator induced failures, test equipment failures, environmental equipment failures, or any other problem/failures which did result in overstress, or which could have resulted in overstress, to any portion of flight hardware. Use at KSC The KSC PRACA System provides the means to monitor and track the health of the Space Shuttle Ground Support Equipment and identify problem areas that require further investigation. See figure 2 for the report that is used to identify and track problems at KSC. The majority of problems that are reported deal with component failures. However, any other condition that results in the system or equipment not meeting the requirements that were specified is also reported (corrosion, out-of-calibration, etc.). [D] Figure 2. KSC Problem Tracking Form Click on image for larger form in PDF format The PRACA system incorporates the following features: Tracking - The system encompasses the reporting, documentation, analysis and initiation of corrective actions relative to nonconformances detected during ground processing operations that are associated with flight systems, ground support equipment and facilities. Recurrence Control - The system provides a recurrence control function which is directed toward ensuring that specific problems or failures do not reoccur. History - The system maintains historical data that supports ongoing problem resolution, trend analysis and recurrence control activities. This historical problem data is needed to support reliability, maintainability, and availability analysis. NASA Centers - The system provides on-line visibility of the nonconformance data to other NASA Centers. Johnson Space Center and Marshal Space Flight Center can view the data on-line. Extracts of data are also provided to JSC for input to the PCAS (Program Compliance Assurance and Status) System. Batch Report - The system provides for the generation of batch reports on demand, weekly and/or monthly. Security - The system provides access control that ensures that only authorized personnel may write to the database and then only to areas in which authority has been established. Query capability of the system is available to valid users at any time. Automated Management Document Control System (AMDCS) - The system provides for the automatic transfer of nonconformance report data to AMDCS when final acceptance data is entered. Ad Hoc Reports - The system provides for the generation of ad hoc reports using a user-friendly language. It also provides for the user to save ad hoc report specification for later use. These reports are needed for specific trend and failure reports. Document Accountability Control System (DACS)- The PRACAS utilizes the DACS for document tracking by attaching a bar-code symbol to each PRACA report. As the report is routed through the closure process the bar-code symbol is scanned at each stop. The location of the report can then be determined by query of DACS. Disposition/Causes/Corrective Action - The system identifies all actions associated with troubleshooting, remedial action, cause identification, recurrence control and unexplained problem resolution. Trouble shooting and remedial action steps are documented. Critical Items - The system identifies the criticality of the failure mode of the problems encountered. A Critical Items List (developed from a Failure Modes and Effects Analysis) is maintained in the database and the criticality code is entered based on the part number. Failure Analysis - The system identifies if failure analysis is required and provides the data for the analysis. Orbiter Thermal Protective System - The system provides for the documentation and disposition of the Orbiter Thermal Protective System nonconformances. This includes a diagram showing the location on each tile of the nonconformance. Corrective Action Assistance Request - The system supports addition, modification and retrieval of the Corrective Action Assistance Requests. Formatted Problem Report - The systems provides for the formatted problem report to be printed on local printers. Status - The system provides real-time status visibility of open and closed nonconformances and constraining nonconformances. It identifies whether the nonconformance is a constraint to further test or precludes the performance of any sequence in the work document. Search and Retrieval - The system provides for interactive search and retrieval which can be displayed on a terminal or, if large volume of data, sent to a printer. Number Generation - The system provides for automatic number generation for the nonconformance documents. The automatic number generator can be turned off as is the case when the nonconformance reports that are initiated when the system is not available are entered in the system. Real-Time - The system supports testing operations and closeouts with real-time status information. Other Useful Information - The system contains other useful information such as part numbers, serial numbers, end item control numbers, next higher assemblies, FSCM (Federal Supply Code for Manufacturers), STS (Space Transportation System) #/effectivity, when failure is detected and operational document, including document type and number of the operation being performed, name of the technician, government quality assurance and contractor quality assurance who accepted the completion of the work. Other information such as, the need for critical skills, the need for retest and the system restore date are provided. References: Reliability Engineering for Electronic Design, Norman F. Fuqua, Marcel Dekker, Inc. 1987, pp. 322-325. Lockheed Space Operations Company, Standard Practice Instruction, Problem Reporting and Corrective Action (PRACA) System - QA-001(3)K. Problem Failure Reporting Procedures, Reliability Preferred Practice PD-ED-1250. Problem/Failure Report Independent Review/Approval, Reliability Preferred Practice PD-AP-1304. Risk Rating of Problem/Failure Reports, Reliability Preferred Practice PD-AP-1305. | This practice has been used on Space Shuttle Program. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/03/2000
736 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Arcjet Thruster Design Considerations for Satellites |  | Failure to use the design concepts presented in this guideline could result in more complex thruster designs, lower reliability, and higher launch vehicle costs. | Use flight proven arcjet thrusters in the design of satellites and as a lightweight reliable propulsion maneuvering system to lower propellant mass, increase orbital lifetime, and use smaller less costly launch vehicles. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1253; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Long-term spacecraft and propulsion system compatibility in near earth orbital environment has been demonstrated by several experimental test flights. This thruster system is currently being incorporated into the new series of Martin Marietta satellites as well as a new series of military reconnaissance satellites. The benefits are a decrease in propulsion system weight, a potential reduction in mission cost, and an increase in orbital lifetime and satellite reliability. Implementation Method: Electrothermal (arcjet) engines and thrusters have been around for the past thirty years. It has only been in the last ten years that these devices have gained popularity due to the decrease in weight of the power conditioning systems and improved performance of the thrusters. Lewis Research Center and Olin Aerospace Corporation are jointly working on several varieties of low power arcjet thrusters for use as North-South stationkeeping thrusters for satellites. The mechanics of electrothermal propulsion is shown in the schematic of Figure 1. Propellant is pumped into a chamber where it is passed through an arc and electrically heated. This hot gas is then thermodynamically expanded through a nozzle and accelerated to supersonic speeds. Exhaust velocities of 1000 to 5000 m/sec have been produced with thrust ranges of 0.01 N to 0.5 N.1 [D] [D] Several areas of development at Lewis Research Center in cooperation with outside vendors, have focused on the advancement of electrothermal propulsion and integration of this into commercial and military satellites as a reliable maneuvering propulsion system. These areas include investigations into new propellants, low power capabilities, and advanced power processing. Propellant considerations Current propellant considerations for north-south stationkeeping have been ammonia, hydrogen, and hydrazine. The ideal propellant for arcjet engines is one which can be stored easily, has a low atomic mass, and favorable thermodynamic conditions during heating and expansion. The chart below shows the advantages and disadvantages for the various arcjet thruster propellants. Table 1. Electrothermal Propellant Considerations2 Electrothermal Propellants Advantages Disadvantages Hydrogen (H2) High specific heat and thermal conductivity. Difficulty in storage. Suffers from frozen flow losses in the nozzle expansion. Ammonia (NH3) Liquid phase does not require refrigeration. Heavy molecule which dissociates into low-molecular-mass constituents which introduces frozen flow loses. Hydrazine (N2H4) Can be dual used for a combination propulsion system on satellites. Can be easily stored. Chemical erosion problems are intensified at higher specific impulses. Heat transfer problems at the nozzle and chamber. Power Processing Development The current research and testing of arcjet thrusters is the low power (1-2kW) range. NASA LeRC and Olin Aerospace are investigating the use of a low power arcjet thrusters on the new generation of satellites. Early work on low power arcjet thrusters used a ballasted DC power supply hich transitioned the arc to steady-state operating conditions4. This caused significant electrode erosion and nonuniform arcs. These problems were overcome through changing the geometry of the electrode, providing vortex flow stabilization, and development of a pulse-width modulated power processor with limiting current circuit for startups.5 These improvements have lead to a 1000h/500 cycle lifetest which demonstrated long-term, reliable, non-damaging arcjet operation. Also demonstrated was an 891 hr qualification lifetest of a 1.8 kW hydrazine arcjet with 918 restarts and a specific impulse of 520s.6 The 1.8 kW hydrazine has been developed and approved for use on Lockheed Martin Series 7000 geosynchronous telecommunications satellites to provide a highly efficient means of north/south stationkeeping. AT&T's Telstar 401 spacecraft was the first application of Lockheed Martin's Series 7000. Technical Rationale Due to the gravitational perturbations caused by a combination of forces from the sun/moon/earth system, most geosynchronous satellites require north/south (N/S) stationkeeping. For a satellite to maintain a positional accuracy of between 0.05 and 0.1 degrees, a delta velocity of approximately 49 m/s/year must be added in the north or south direction, perpendicular to the orbital plane.7 The propellant requirements for N/S stationkeeping can represent up to 80% of the mass of total propellant and up to 20% of the on-board quotwetquot mass of the satellite. Therefore to improve the efficiency of stationkeeping class thrusters various designs and improvements have been developed. The latest and most efficient thruster design developed thus far is the hydrazine arcjet system. Table 2 compares the use of hydrazine in various thruster configurations. The high specific impulse and the decrease in propellant weight add to the arcjet's competitive edge over other propulsion thruster systems. Table 2. N/S stationkeeping propellant mass comparison for a 12 Year, 1700 kg dry mass satellite.7 Thruster Systems Typical Thrust Level (N) Specific Impulse (lbf-s/lbm) N/S Stationkeeping Propellant (kg) Hydrazine (N2H4) 0.4-20 220 532 Bipropellant (MMH/N2H4) 20-40 302 373 Resistojet (N2H4) 0.2-0.4 302 373 Arcjet (N2H4) 0.15-0.3 520 207* *Does not include dry mass penalty of approximately 20 kg. The hydrazine arcjet not only outperforms existing propulsion options, it also has several key advantages over other electric propulsion options. The performance and economic edge is derived from three major areas. The first is that arcjets have a relatively higher thrust than other electric propulsion devices which reduces duty cycles and battery demands. Second, the arcjet's use of hydrazine propellant allows commonality and simplicity in the feed system. Third, the arcjet system is relatively compact in size and has a very high thermal efficiency which provides relatively simple structural and thermal spacecraft integration. While trade studies for different satellite masses and lifetimes will show a greater or lesser advantage for the arcjet, the conclusion reached is the same: arcjet thrusters will have a major impact on reducing propellant mass and increasing the economic return on investment for many commercial satellite systems. References Sutton, George P. , Rocket Propulsion Elements: Introduction to the Engineering of Rockets, John Wiley & Sons, 1992 Jahn, Robert, Physics of Electric Propulsion., McGraw-Hill Series in Missile and Space Technology, McGraw-Hill Book Company, 1968 Smith, W.W., Smith, R.D.,Yano, S.E., quotLow Power Hydrazine Arcjet Flight Qualificationquot, IEPC-91-148, October 1991. Smith, R.D., Roberts, C.R., Davies, K. and Vaz, J., quotDevelopment and Demonstration of a 1.8 kW Hydrazine Arcjet Thrusterquot, AIAA-90-2547, July 1990. Curran, Francis M., Sovey, James S.,and Myers, Roger M.,quotElectric Propulsion: An Evolutionary Technologyquot, Acta Astronautica Vol. 29, No. 9 pp. 651-665, 1993. Sovey, James S., Curran, Francis M., Haag, Thomas W., Patterson, Micheal J., Pencil, Eric J., Rawlin, Vincent K., quotDevelopment of Arcjet and Ion Propulsion For Spacecraft Stationkeepingquot, NASA TM-106102. Sovey, James S., Pidgeon, David J., quotAdvance Propulsion For LEO and GEO Platformsquot, AIAA 90-2551, July 1990. | This practice has been used on ELITE, STS 5 & 6, FLTSATCOM. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/03/2000
735 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Material Selection Practices |  | Failure to access and survey the MAPTIS system could result in overlooking important materials or process advancements, mistaking vital material parameters, or using materials in applications where they would be subject to potential degradation or failure. The result could be mission compromise, mission delays, loss of mission, or loss of life. | Aerospace systems designers must ensure that the most reliable material is used to meet the design requirements for aerospace systems. Test results regarding corrosion resistance, susceptibility to stress corrosion cracking, flammability, toxicity, thermal vacuum stability, and compatibility with rocket engine fuels, oxidizers, and hydraulic fluids; as well as extensive chemical and physical properties data; are included in the Materials and Processes Technical Information System (MAPTIS). This information is used to assist the aerospace designer in identifying the most reliable material candidates for space systems. | MSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1252; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Reliable materials can be selected for aerospace applications by choosing those materials that have demonstrated reliability in carefully controlled laboratory testing and in operational space flights. Use of the Materials and Processes Technical Information System (MAPTIS) data base by system designers will ensure that materials that have demonstrated reliable performance in flight and test experience are the first to be considered in new or revised designs. Engineers will then have the confidence in their selections, knowing that the data on which their decisions have been made have been thoroughly validated. Implementation Method: Introduction: The Materials and Processes Technical Information System (MAPTIS) resides on a DEC Alpha 7620 Computer located at the George C. Marshall Space Flight Center in Huntsville, Alabama. It can be accessed through the Internet after assignment of an account number by completing a user request form which can be obtained from MSFC. The MAPTIS data base contains properties and test histories on both metals and nonmetals. Searches of the database can be accomplished by material code, material specification, manufacturer, or by a string or phrase search. Materials are rated based on criteria in NASA Handbook 8060.1C [reference 1] , Marshall Space Flight Center Specification 250 [reference 2] , Marshall Space Flight Center Specification 522 [reference 3] , and SP-R022A [reference 4] . For metals, information is included in the database on corrosion, stress corrosion cracking, and compatibility with: (1) gaseous oxygen, (2) liquid oxygen, (3) nitrogen tetroxide, (4) hydrazine, (5) low pressure hydrogen (<450 psi) and (6) high pressure hydrogen (>450 psi). In addition MAPTIS contains: a material code index, an alloy designation, the heat treatment, material specifications, and the generic identification and form. The database elements for nonmetals includes information on flammability, toxicity, thermal vacuum stability, and compatibility with: (1) liquid oxygen, (2) gaseous oxygen, (3) nitrogen tetroxide, (4) hydrazine, (5) liquid hydrogen, and (6) hydraulic fluid. Nonmetallic data is included for adhesives, elastomers, plastics, tapes, tubing, potting compounds, coatings and lubricants. Material Selection: The materials selection portion of MAPTIS is a design selection tool that can also be used for material surveys and design reviews. It is based on comprehensive storage of test data and handbook information on metals, nonmetals, and standard parts. It includes a thermal vacuum stability data base which is a compilation of vacuum outgassing data from tests conducted at MSFC and various other organizations including the White Sands Test Facility, the Goddard Space Flight Center, the European Space Agency, the Jet Propulsion Laboratory, and others. Data elements included are total mass loss, residual mass loss, volatile condensible material, pressure, temperature, duration, and test facility description. An atomic oxygen data base includes the effects of atomic oxygen on various materials, guidelines for selection of materials based on this parameter, and protective techniques. A special database included in MAPTIS is an analytical tool to evaluate toxic outgassing data. The analysis provides a method for determining if the material or the assembled article meets the requirements of NHB 8060.1C acceptance criteria including the comparison of projected contaminant concentrations with maximum allowable concentrations. The material selection function is a vital part of achieving high reliability for long duration space missions or missions on which the materials encounter severe environments. Material Properties: The material properties portion of MAPTIS contains comprehensive online materials information including physical and mechanical properties. Materials are listed specifically by designation, trade name, and manufacturer. The metallic materials portion includes such information as mechanical properties, design allowables, variations with environment and temperature, graphical and tabular tensile and compressive yield and ultimate strengths, elongation, fatigue, stress-strain, and elastic modulus. Physical properties such as density and thermal expansion are also included, as are chemical, thermal, and electrical properties. Many of these same properties are also included for nonmetals with additional information on peel, tear, and impact resistance; lap shear, creep, and resilience. Physical and chemical properties such as viscosity, hardness, color, formulation, flashpoint, chemical and environmental resistance, and pH are included in the data base. For nonmetals, processing parameters such as extrusion or molding temperatures, pressures, and times; cure conditions, mix ratios, rise, and demold times are also included. The types of materials contained in the nonmetals portion of the database are: plastics, nozzle materials, coatings, tapes, adhesives, and lubricants. Verification and Control: The MAPTIS is also used to obtain information on where the materials listed have been used, to determine the history of hardware and material selection rationale, and to correlate U.S. material designations with those of foreign material designations. The "where used" data aids in the identification, tracking, and control of all material usage as a function of part number, environment, contractor, and/or project. This information is available for the SRM/SRB, External Tank, Space Shuttle Main Engine, and Spacelab programs. The data includes configuration information, application information, materials usage information, and support information. Configuration information includes the associate contractor, the detailed drawing numbers and part numbers, and the next assembly drawing and part numbers for the device, part, or structure that used or uses the material. Application information includes test data, fluid systems compatibility, environmental conditions to which the item(s) have been subjected, evaluation and analysis rationale, and process specifications. Materials usage and support information includes: (1) all materials by designation, code, and specification; (2) an overall material evaluation rating; (3) a record of the weight, surface area, and thickness of nonmetals; (4) a record of material usage agreements; and (5) material specifications. These success stories of materials which performed in an acceptable manner in real programs, as well as in laboratory tests, are indispensable inputs to the aerospace designer. Structural Materials Failure Analysis Database: It is not only the success stories that are important inputs to the designer, but also an in-depth knowledge of the failures that have occurred and why they occurred is another vital link to high reliability. The NASA-wide failure analysis data base for structural materials is also a part of MAPTIS. It provides fast and easy access to selected NASA and contractor reports on failure investigations for structural materials and processes that have been conducted over a period of 35 years. The database fulfills the stated requirements of personnel surveyed at NASA centers, the Department of Defense, and contractors who need to be able to retrieve data quickly, cross reference large quantities of technical information, and share results in a standard format between organizations. The database presents failure analysis information in a simple format. It is used by engineers and managers to get a head start on investigations, minimize duplications of effort, use resources effectively, and ensure that problems have been resolved or can be avoided. There are approximately 900 records in the database at this writing, and the information is continuing to be updated and amended as new information becomes available. The database has nine identifying data fields plus an abstract averaging about 100 words to describe the nature of the failure, its cause, and corrective actions. Failures are categorized into 15 categories as follows: Critical Defect Growth Corrosion Fatigue Corrosion Creep High Cycle Fatigue Hydrogen Embrittlement Hydrogen Environment Embrittlement Low Cycle Fatigue Liquid Metal Embrittlement Overload Oxidation Stress Assisted Grain Boundary Oxidation Crack Stress Corrosion Cracking Stress Rupture Other Knowledge of the types of structural failures that have been encountered, the details of the failure analysis, and the corrective actions taken are essential elements in the material selection for systems which must perform reliably. Project Support Data Base: MAPTIS contains a project support data base designed for both external and internal support to the major ongoing NASA and MSFC projects. The project support data base includes an electronic bulletin board, lead engineer data records, a standards data base, specifications status, and correspondence status. The electronic bulletin board provides a method for rapid dissemination and exchange of materials and processes news, developments, and problems NASA-wide. Lead Engineers are listed for each project. A standards data base lists all NASA specifications and standards. The specifications tracking data file provides evaluation or approval status, disposition, description and effectivity for material and process specifications, operations, and procedures reviewed and evaluated by MSFCís Materials and Processes Laboratory. Technical Rationale: Historically, materials and their properties have been inextricably tied to the ability to withstand severe environments and to provide hardware that will operate successfully in multiple missions. An intimate knowledge of the materials, their composition, their reaction under various operating conditions, and their success and failure history will provide the designer with the ability to select the right material for any given task. MAPTIS contains an accumulated body of data and evidence that has been documented over many years and perfected into an electronic access system that is still being updated and growing. Use of this system has become an essential element in the continuing pursuit of the ultimate in reliable space flight systems. References: NHB 8060.1C;" Flammability, Odor, and Offgassing Requirements and Test Procedures for Materials in Environments that Support Combustion." MSFC-SPEC-250A; "Protective Finishes for Space Vehicles, Structures, and Associated Flight Experiments." MSFC-SPEC-522B; "Design Criteria for Controlling Stress Corrosion Cracking." SP-R022A; "Vacuum Stability Requirements of Polymeric Materials for Spacecraft Applications." | This practice has been used on Saturn I and Saturn V programs, Space Shuttle Main Engine, Solid Rocket Booster, Solid Rocket Motor, Space Shuttle External Tank, and Spacelab. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/03/2000
737 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Design Reliable Ceramic Components With Cares Code |  | The CARES computer program is used worldwide for fracture and life prediction of structural ceramic components for automotive, aerospace, electronic, and nuclear applications. Spacecraft are composed of many complex assemblies that contain ceramic materials. CARES is proven software especially useful for ensuring that ceramic components are designed to survive different temperature extremes and stresses in the space environment. Failure to adhere to proven design methods and/or reliability analysis practices could cause shortened mission life, degraded levels of mission success, premature termination of component or experiment operation, and in extreme circumstance, loss of mission and human life. All phases of the spacecraft design process, from design, development, fabrication to installation in the spacecraft, must adhere to proven reliable design and safe practices. | Use the Ceramics Analysis and Reliability Evaluation of Structures (CARES) computer program to calculate the fast-fracture reliability or failure probability of macroscopically isotropic ceramic components. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1254; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The increasing importance of ceramics as structural materials places high demand on assuring component integrity while simultaneously optimizing performance and cost. Components using ceramics can be designed for high reliability in service if the contributing factors that cause material failure are accounted for. This design methodology must combine the statistical nature of strength controlling flaws with fracture mechanics to allow for multiaxial stress states and concurrent flaw populations. The Ceramics Analysis and Reliability Evaluation of Structures (CARES) uses results from MSC/NASTRAN or ANSYS finite-element analysis programs to evaluate how inherent surface and/or volume type flaws affect component reliability. Implementation Method: Introduction The unique properties that advanced ceramics have to offer for future commercial industries, propulsion and space related programs are phenomenal, such as high temperature strength, environmental resistance, and low density materials. NASA is dedicating a major effort to propulsion systems that reduce pollution, noise, and fuel consumption while improving reliability and service life. Consequently, research has been focused on improving ceramic material processing and properties as well as on establishing a sound design methodology. Because of the variable severity of inherent flaws, the nature of ceramic failure is probabilistic and optimization of design requires the ability to accurately determine a load component's reliability. Methods of quantifying this reliability and the corresponding failure probability have been investigated and refined at NASAís Lewis Research Center. The result of this effort is a public domain computer program with the acronym CARES. The design methodology used by CARES combines three major elements: (1) linear elastic fracture mechanics (LEFM) theory which relates the strength of ceramics to the size, shape, and orientation of critical flaws, (2) extreme value statistics to obtain the characteristic flaw size distribution function, which is a material property, and (3) material microstructure. Inherent in this design procedure is that component integrity is a function of the entire field solution of the stresses and is not based only on the most highly stressed point. In addition, the size of the stressed material surface area and volume affect the component strength. Program Capability and Description CARES is an integrated computer program written in FORTRAN 77 WAT V compiler which uses Weibull and Batdorf fracture statistics to predict the fast fracture reliability of isotropic ceramic components. CARES has three primary functions: (1) to analyze statistically the data obtained from the fracture of simple uniaxial tensile or flexural specimens, (2) to estimate the Weibull and batdorf material parameters using these data, (3) to perform a fast fracture reliability evaluation of a ceramic component experiencing thermomechanical loading. Component reliability is predicted by using elastostatic finite element analysis output from the MSC\NASTRAN or ANSYS computer programs. The CARES code includes a number of fracture theories to predict material response due to multiaxial stresses. These methods are summarized in Table 1. Weakest Link Fracture Model Size Effect Stress State Effects Compensational Simplicity Theoretical Basis Weibull (1939) Yes Unaxial Simple Phenomenological Normal stress Yes Multiaxial Complex Phenomenological Principle of independent action (1967) Yes Multiaxial Complex Maximum principal stress theory Batdorf: Shear-insensitive (1974) Shear-sensitive (1978) Yes Multiaxial Complex Linear elastic fracture mechanics Table 1. Statistical Fast-Fracture Models Available with CARES The Batdorf method is recommended because it couples LEFM with the Weibull weakest link theory (WLT). The Weibull normal stress averaging method and the principle of independent action (PIA) theories are included for comparison purposes and because of their previous popularity. All the fracture models available of strength distribution. Figure 1 shows the fracture criteria and crack geometries available to the user for both surface and volume distributed flaws. The PIA and Weibull normal stress averaging fracture theories do not require a crack geometry. Batdorf's fracture theory can be used with several different mixed-mode fracture criteria and crack geometries. For coplanar crack extension, CARES uses the total strain energy release rate theory. Out-of-plane crack extension criteria are approximated by a simple semiempirical equation. This equation involves a parameter which can be used to approximate various mixed-mode theories or experimental result. For comparison, Griffith's maximum tensile stress analysis for volume flaws is also included. The highlighted boxes in Figure 1 show the recommended fracture criteria and flaw shapes. [D] Figure 1. Available Failure Criteria and Crack Shapes. (Recommended failure criteria and crack shapes are highlighted) Two version of the code, designed as CARES1 and CARES2, are available. The CARES1 version assumes that stress and temperature gradients within each element are negligible, and, therefore, only element centroidal principle stress is used in the reliability calculations. The CARES2 version takes into account element stress gradients by dividing each brick element into 27 subelements and each quadrilateral shell element into 9 subelements. Subelement centroidal principle stress is then computed and used in the subsequent reliability calculations. CARES2 enables the finite-element model to consist of fewer elements for the same level of convergence to the true solution as CARES1. Input Requirements To control the execution of the CARES program, an input file must be prepared. On the tape or disks provided with the program is a file called TEMPLET INP that can be used to construct an input file for a particular problem. Input to CARES is keyword driven. Data are input by the user under each keyword. An explanation of the input required or a list of input choices is provided next to the keyword. The CARES program requires three categories of input: (1) Master Control Input, (2) Material Control Input, which includes temperature-dependent material data, and, optionally, (3) MSC\NASTRAN or ANSYS output data files from finite-element analysis. The Master Control Input is a set of control indices that directs the overall program execution. The Material Control Input consists of control indices and either the data required to estimate the statistical material parameters or direct input of the statistical parameter values themselves for various temperatures. This input category includes the choices of fracture criteria and flaw shapes shown Figure 1. The Master Control Input and the Material Control Input are contained in the TEMPLET INP file. The third input category, MSC/NASTRAN or ANSYS output data files, includes finite-element analysis data files containing the element stresses, volumes/areas, and temperatures. [D] Figure 2. Block Diagram for Analysis and Reliability Evaluation of Ceramic Components Output Information The first part of the CARES output is an echo of the choices selected (or default values) from the Master Control Input. If a finite-element model reliability analysis is not performed, then CARES proceeds to echo the Material Control Input. If postprocessing of a finite-element model is done, then, for each element, the centroidal or subelement principle stresses with appropriate element area or volume and temperature are listed. The printing of element stress tables in CARES is optional. In addition, two element cross-reference tables are printed. The first table lists the shell element number and gives the corresponding solid element to which it is attached. The second table lists the solid element identification number and lists up to six associated shell element (a brick element could have all of its six faces as external surface). CARES echoes the user inputs for each section of the Material Control Input. If statistical material parameters are directly input, then output pertaining to calculated values of the normalized Batdorf crack density coefficient kb will follow. If statistical material parameters are determined from experimental fracture data, then the output will identify the method of solution, the number of specimens in each batch, and the temperature of each test. In addition, the output echoes the sorted input values of all specimen fracture stresses with proper failure mode identification. Results from the statistical analysis of the fracture data are then printed. The fracture strength and corresponding significance level are listed for detected outliers followed by the estimated statistical material parameters from least-squares or maximum likelihood analyses. The biased and the unbiased values of the Weibull shape parameter, the specimen Weibull characteristic strength, the upper and lower bound values at 90-percent confidence level for both parameters, the specimen Weibull mean value, and corresponding standard deviation are printed for each specified temperature. For censored statistics these values are generated first for volume flaw analysis and subsequently for the surface flaw analysis. The K-S goodness-of-fit test is done for each specimen fracture stress and the corresponding K-S statistics D+, D-, and significance level are listed. Similarly, the K-S statistic for the overall sample set is printed along with the significance level. This overall statistic is the absolute maximum of individual data D+ and D- factors. For the A-D goodness-of-fit test, the A-D statistic A2 is determined for overall population and its associated significance level is printed. The next table of the output contains data to construct K-S 90-percent confidence bands about the Weibull distribution. The table includes fracture stress data, the corresponding Weibull probability of failure values, the 90-percent upper and lower confidence band values about the Weibull line, and the median rank value for each data point. The last table from the statistical analysis section of CARES summarizes the material parameters used in component reliability calculations. These parameters, which are listed as a function of temperature, include the biased Weibull modules, the normalized Batdorf crack density coefficient, and the Weibull scale parameter or the unit volume or unit area characteristic strength, whichever is appropriate. The values printed correspond to the experimental temperatures input and five additional interpolated sets of values between each input temperature. The interpolated parameters are output for checking purposes. Information on the selected fracture criterion and the crack shape is printed as required. If a component reliability analysis with finite-element data is being performed, then tables will be generated to summarize the reliability evaluation of each finite element. One table is provided for volume flaw analysis (solid elements) and one table is given for surface flaw analysis (shell elements) as requested by the user. The tables list the element identification (ID) numbers and the corresponding element material ID, survival probability, failure probability, risk-of-rupture intensity (risk-of-rupture divided by element volume or area), and temperature-interpolated statistical material parameters. Following each table is a list of the 15 most critical risk-of-rupture intensity values and corresponding element numbers. Also included is the probability of failure and survival for the component surface or volume, whichever is appropriate. Finally, the overall component probability of failure and the component probability of survival are printed. Theory and Example For additional information on theory and example of different applications such as statistical material parameter estimation, rotating annular disk and Si3N4 mixed flow rotor, please refer to NASA TM 102369 and other referenced articles on the reference section of the practice. Technical Rationale: The CARES computer program was developed by NASA LeRC's Structural Integrity branch. The branch combines the three disciplines of analytical modeling, mechanical testing, and nondestructive testing to understand and predict the behavior of advanced high-temperature materials, particularly brittle ceramic and inter-metallic matrix composites. CARES is an enabling technology primary created to foster the introduction of ceramic materials in demanding engine environments to achieve breakthrough gains in energy efficiency and emissions reduction. The specific purpose of the project is to transfer and upgrade technology for understanding and predicting the behavior of brittle ceramic materials. To accomplish this, CARES incorporates the capability to design for any component shape and services environment. The resulting software is a comprehensive general-purpose design tool for government, industry, and academia that predicts the probability of a ceramic component failing as a function of its time in service. For the past three years over 100 companies worldwide have obtained the CARES software. As the only general-purpose public domain integrated design program for predicting the reliability of brittle materials in the United States, CARES has tremendous impact on helping U. S. industrial competitiveness. The CARES probabilistic design methodology is necessary for accurate failure prediction and efficient structural utilization of brittle materials subjected to arbitrary stress states. This technology applies to materials such as glass, graphite, and advanced ceramics including silicon nitride and silicon carbide. Many commercial products, such as turbocharger rotors, rocker arm and cam followers, poppet valves, radiant heater tubes, heat exchanges, and prototype ceramic turbines, are widely designed by using the CARES series of software. In addition, these programs are used to design large infrared transmission windows, glass panels for skyscrapers, ceramic packaging for microprocessors, cathode ray tubes, and even ceramic tooth crowns and knee caps. Although similar codes now exist, CARES has two unique features. The code is public domain software and thus readily available. Furthermore, it can be integrated with popular finite element analysis computer programs such as ANSYS, NASTRAN, and ABACUS. Software Release Request Form (.pdf) References: Nemeth, N. N. and Manderscheid, J. M. and Gyekenyesi, J. P., Design of Ceramic Components With the NASA/CARES Computer Program, NASA Technical Memorandum 102369, 1990. Nemeth, N. N. and Powers, L. M. and Janosik, L. A. and Gyekenyesi, J. P., Designing Ceramic Components for Durability, American Ceramic Society Bulletin, Volume 72, No. 12, December 1993. Research & Technology - 1993, NASA LeRC TM 106376, 1993. Nemeth, N. N. and Power, L. M. and Janosik, L. A. and Gyekenyesi, J. P., Durability Evaluation of Ceramic components using CARES/LIFE, NASA Technical Memorandum 106475, 1994. Ratajczak, A. F., NASA Software of the Year Award, NASA Tech Briefs, Volume 18, No. 12, December 1994. | This practice has been used on SSME. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/03/2000
734 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Instrumentation System Design and Installation for Launch Vehicles |  | Failure to adhere to the practices suggested herein could result in contamination entry into sensors, excessive uncompensated sensor drift, incompatibility of the instrumentation system with other subsystems, failure to meet telemetry requirements, and possible loss of the mission through inadequate diagnostics and inappropriate control or vehicle destruction. At the minimum, expensive delays, replacement and repair may be incurred to achieve successful flight objectives. | Instrumentation systems and related sensors (transducers), particularly those designed for use in reusable and refurbishable launch systems and subsystems, are analyzed, designed, fabricated and tested with meticulous care in order to ensure system and subsystem reliability. | MSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1251; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The benefits of implementing these reliability practices for instrumentation system and related sensors are: (1) consistent performance and measurement results, (2) minimum need for continuous or periodic calibration, (3) avoidance of and resistance to contamination, and (4) reduced necessity for repair or replacement in repeated usage. Implementation Method: Introduction: Close attention to design details, precision craftsmanship, and an integrated approach to design, manufacturing, testing, installation, and operations are paramount to sustained accuracy and reliability of performance in launch vehicle and propulsion system instrumentation and related sensors for aerospace applications. Instrumentation systems and their related sensors have reached a high degree of maturity, and preferred practices have evolved in recent years which will ensure high reliability if meticulously followed throughout the life cycle of the instrumentation system. Design Practices: During the preliminary design, critical design review, and initial development phases, the integrated design and concurrent engineering processes have proven to be essential in producing instrumentation that will continue to perform reliably in repeated and long term usage. Instrumentation systems should be planned and designed in close connection with and parallel with the design and analysis of the principal systems and subsystems they are intended to monitor, measure, and control. Sensor vendors and suppliers must be an integral part of the design team for effective coordination and communication. Error budget analyses and metrology considerations are considered up front in the design process. Designing the instrumentation system and its components for contamination-free manufacturability and ease of inspectability is vital. Calibration considerations and compensation methods are developed early in the design process to permit analysis of sensor shift and drift, and to provide a means of predicting and adjusting for both anticipated and unanticipated variances from nominal sensor performance. Sensors, connectors, and wiring are designed to avoid the potential of contamination creation or entrapment, damage during removal and refurbishment, misidentification, leakage, solder wire fatigue failure, electrical shorts, insulation breakdown, or vibration-induced deterioration. Testing and Verification Practices: Careful analysis of all instrumentation system design requirements and development of comprehensive test and verification plans help ensure that all instrumentation requirements are thoroughly verified in testing. For manned missions, continued testing and retesting of sensors and other components on a sampling basis from each production lot is required to ensure that delivered parts are continuously meeting standards. Experience has shown that careful attention must be given to any rework processes, and that reworking of lead wire channels should be avoided. Source control drawings are established to ensure that manufactured items conform exactly to those of the qualified parts. Leak checks are performed on all sensor welds. Manufacturing and Assembly Practices: Closely controlled manufacturing and routing procedures have proven to be essential in the manufacturing and assembly of sensors as well as the installation and testing of instrumentation systems. Inspection points are added during pre-assembly or partial assembly steps if inspection would be difficult at later steps in the process. Inspection steps are added prior to any cavity closeout, and prior to the use of coatings, sealants, or potting compounds that could mask contaminants. Potting compounds for connector terminals, printed wiring boards, or connector boards are formulated, installed, and inspected to eliminate voids and potential resulting failure in a dynamic vibration environment. Inspection for contamination is conducted following secondary machining operations and prior to the assembly of machined parts. Magnification is specified for all inspection operations during manufacturing and assembly. Handling containers, tooling, and support equipment that will come into close contact with the flight hardware is meticulously cleaned and closely controlled during manufacturing and assembly. Alternate rework procedures are evaluated and acceptance or rejection criteria for these rework procedures are developed. Heat sinks are provided in tooling for electron-beam weld joints. High temperature solder is used to improve strength under elevated temperature environments. Changes to Instrumentation Systems and Sensors: Changes to instrumentation systems and sensors are subjected to certification through analysis, by similarity, through laboratory verification, and by hot fire testing on the selected launch vehicle, propulsion system, or component. A stress analysis accompanies any change in configuration to ensure that the resultant component or system is at least as strong, if not stronger, than the original. Resulting improvements in material properties, reduction in weight, and improvement in reliability are verified through analysis. A dynamic evaluation of modified configurations is conducted to identify changes in resonant frequency and load capability. Verification of changes by similarity is based on hot fire experience of sensors or other instrumentation system components with identical features. Laboratory testing to verify changes includes verification of diaphragm burst pressures (pressure sensors, for example), case structure burst pressures, and leak tests. Hot fire verification includes the testing of one sensor in each vibration zone (as in the SSME) and multiple long duration tests in each planned sensor location. General Practices for Instrumentation Sensors (Transducers) in Long Lifetime, Refurbishable or Reusable Vehicles: Selected pressure and temperature transducers are capable of lifetimes in excess of 10 years. Flow meters have less life capability, but meters without moving parts and operating in an environment of low contamination and corrosion are capable of long life. Humidity, oxygen, and carbon dioxide sensors are life limited, requiring periodic maintenance actions such as cleaning and replacement of cartridges. A prime problem with transducers is the lack of long-term stability (freedom from drift). One solution to this problem lies in making the total transducer dimensionally stable over long periods of time. Accordingly, it is important to minimize the use of nonmetallic materials and to employ and control processes that yield parts in a stress free condition. Long term stability (and process control) must then be demonstrated through testing of the assembled transducer under appropriate environmental conditions such as temperature cycling. A second solution is to provide sensitive and pre-calibrated ground-based software that will detect unpredictable sensor drift and adjust the software to compensate for this drift where possible. However, this process can yield an increased uncertainty of the measurement because the instrument, has in effect, been recalibrated through a process that could have less accuracy than the original calibration standard. If the reference drifts, this uncertainty grows with time. There is more to be gained from correction of unpredictable drift if a cross check can be performed with a statistically significant number of instruments. Cross checks are of great value for determining when an instrument has drifted outside the allowable tolerance band. When this occurs, the instrument can be replaced or calibrated as required by corrective maintenance. A well-constructed test program provides the best assurance that a transducer will perform satisfactorily in a long-life application. Unfortunately, the lead time available from selection of a transducer to commitment of the transducer to service may be only a fraction of the time required for a comprehensive test program. Therefore, transducers should be chosen where such data has already been acquired. Long-life transducer applications fall into two broad classifications: open-loop and closed-loop. Open-loop applications only provide information regarding the performance of a system. Closed-loop applications involve a control function to regulate a system based upon transducer output. Transducer failures in open-loop applications result in uncertainty about the condition of the system, while similar failures in closed-loop applications of transducers are more critical from the standpoint of failure effects. They require greater attention to the factors influencing reliability and life. In general, redundancy techniques do not provide solutions to transducer problems. Active redundancy cannot provide a solution if a known life limiting mechanism exists in the transducer. Multiple potentiometer wipers, for example, exposed to the same wear, may fail within the same time span. Standby redundancy is generally not feasible. In standby redundancy a non-active transducer is protected from the failure producing condition until the first transducer has failed. Applications involving standby redundancy are severely restricted by size, weight, and the complexity of devices required to switch from the active to the standby transducer. Technical Rationale: Each Space Shuttle Solid Rocket Booster (SRB) has 65 measurements during flight to monitor parameters such as chamber pressure, actuator positions, temperature, and vibration. In addition to these measurements, there are 142 ìeventî measurements that are telemetered back to earth for each SRB. Therefore, for each Space Shuttle flight, the SRB contributes over 400 channels of telemetered data. Each Space Shuttle Main Engine (SSME) contributes 66 more channels of telemetered data, making a total of 466 channels of telemetered data for the reusable propulsion system components of the Space Shuttle. In the Critical Design Review of the SSME pressure sensor, which is only one of the many sensors used in a Space Shuttle flight, fourteen design changes and a number of process changes were identified to reduce contamination and to improve the reliability of this sensor alone. These design and process changes implemented many of the practices described in this document, and a much higher reliability of the resulting modified sensor is expected. The changes involved sensor body, wiring, potting materials, manufacturing methods, a slightly revised configuration, increased strength, and improved inspectability. References: Solid Rocket Booster Instrumentation Program and Components List, Report No. 16A00103, Marshall Space Flight Center, AL, March 15, 1983. SSME Flight Measurement Location Document, Revision D, Rockwell International, Rocketdyne Division, Canoga Park, CA, May 1991. Critical Design Review of Eaton SSME Pressure Transducer, Rockwell Aerospace, January 31, 1995. Space Station Furnace Facility Metrology Plan, NASA/MSFC Astrionics Laboratory, November 1994. "Long Life Assurance Study for Manned Spacecraft Long Life Hardware," Report # MCR-72-169, Martin Marietta Corporation, September 1972. | This practice has been used on Space Shuttle Main Engine (SSME), Space Shuttle Solid Rocket Booster (SRB), and selected space payloads and experiments. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/03/2000
733 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Pre-Flight Problem/Failure Reporting Procedures |  | Without this practice with its formal reporting procedures, problems/failures, particularly minor glitches, may be overlooked or not considered serious enough to investigate or report to Project Management. This could result in recurrence of the problem/failure during the mission and result in significant degradation in performance. | A formal procedure is followed in the reporting and documentation of problems/failures occurring during test, pre-launch operations, and launch operations for both hardware and software. A separate system, the quotSpacecraft Orbital Anomaly Report (SOAR)quot, is used for the reporting, evaluation and correction of problems occurring on-orbit (see Reliability Preferred Practice No. PD-ED-1232). | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1250; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. This practice significantly enhances the probability of mission success by ensuring that problems/failures occurring during ground test are properly identified, documented, assessed, tracked and corrected in a controlled and approved manner. Another benefit of the PFR procedure is to provide data on problem/failure trends. Trend data may then be analyzed so that errors are not repeated on future hardware and software. Implementation Method: A formal procedure (Reference 1) establishes the GSFC system for the identification and documentation of Problem/Failure Reports (PFRs), the data collection and monitoring of PFRs, the risk assessment and rating of problems/failures, and the Project and Center management approvals of corrective actions. For hardware, the procedure begins with the first application of power (or first test usage for mechanical items) at the lowest level of assembly of qualification or flight configuration hardware. For software, the procedure begins with the first test use of the software item with a hardware item of the mission system at the component level or higher. Identification and Documentation of PFRs: Anyone with knowledge of a problem or failure may initiate a PFR. PFRs are generated for any departure from a design, performance, testing, or handling requirement that affects the function of flight equipment, ground support equipment that interfaces with flight equipment or that could compromise mission objectives. All GSFC generated PFRs begin as problem records identified on applicable Certification Logs (Ref. 3), Problem Records (Ref. 4) and work orders. After a PFR occurrence, the Certification Log and Work Order, as applicable, are used to document, define and control any repairs, fixes, or modifications that may be performed on the hardware or software. PFRs are generated and entered electronically into a PFR database, normally accessible on designated personal computers in hardware assembly and test areas. The PFR database program's on-screen instructions indicate certain required data that is to be provided, and automatically assigns a PFR number for traceability. PFRs can be prepared manually on GSFC PFR Form 4-2 (Figures 1 & 2) when the PFR database is not available or the system is inoperative. The PFR data on this form is entered into the database at the earliest opportunity following the problem/failure, but must be filed within 24 hours. All PFRs, including both hardcopy and electronic formats, are forwarded to the Project Office for routing to designated personnel. Contractor-generated PFRs are provided to the Project Office in accordance with applicable contract requirements. PFRs generated in-house or at launch sites are provided directly to the Project Flight Assurance Manager (FAM) and the Systems Assurance Manager (SAM) or their designees, as appropriate. The Project FAM/SAM or their designees enter all the hardcopy PFRs that they receive into the GSFC PFR database. Data Collection and Monitoring of PFRs: The FAM/SAM provide copies of all PFRs to the members of a Failure Review Board (FRB) that is established and authorized by each project to investigate, analyze, and determine the cause of each problem/failure and the appropriate disposition of each PFR. The FRB consists of the following project personnel as a minimum: The project FAM/SAM or designees (serves as chairman) The Project Manager or designee The cognizant engineer(s) responsible for the failed item(s). Continuation of operations or immediate initiation of troubleshooting operations after the occurrence of a problem or failure is at the discretion of the cognizant engineer and other members of the FRB as appropriate and is based on the following factors: The number and severity of problem/failure occurrences during the operation in question; The degree of confidence in ability to quickly diagnose the source or cause of the problem or failure; The potential risk to hardware or software posed by continuing the operations after the problem or failure; The consequences of terminating an operation in which a failure has occurred (e.g., thermal vacuum testing). Risk Assessment and Rating of Problems/Failures: The residual risk of each PFR must be considered by the FRB before it can be considered for closure. A two-factored risk rating system is used. The first rating factor identifies the impact that the problem/failure would have on the flight hardware and/or software performance capabilities if it occurred during the mission. Redundancy is ignored in establishing this rating. The failure effect ratings are illustrated in Table 1. Table 1. PFR Failure Effect Ratings RATING FAILURE EFFECT 3 Catastrophic or major degradation to mission, system or instrument performance, reliability or safety 2 Moderate or significant degradation to mission, system or instrument performance, reliability or safety, defined as: a) Appreciable change in functional capability b) Appreciable degradation of engineering or science telemetry c) Causing significant operational difficulties or constraints d) Causing reduction in mission lifetime 1 Negligible or no impact on mission, system, or instrument performance, reliability or safety. The second rating factor identifies the confidence in understanding both the cause(s) of the problem/failure and the effectiveness of the resulting corrective action. The failure corrective action ratings are shown in Table 2. Table 2. PFR Failure Corrective Action Ratings RATING FAILURE CORRECTIVE ACTION 1 The root cause of the problem/failure has been determined with confidence by analysis and/or test. Corrective action has been determined, implemented and verified with certainty. There exists no credible possibility of problem/failure recurrence. 2 The root cause of the problem/failure has not been determined with confidence. However, some corrective action has been determined, implemented and verified with certainty. There exists some possibility that the problem/failure may recur. 3 The root cause is considered to be known and understood with confidence. Corrective action has not been determined, implemented or verified with certainty. There exists some possibility that the problem/failure may recur. 4 The root cause has not been defined with certainty. Corrective action has not been determined, implemented nor verified with certainty. There exists some possibility that the problem/failure may recur. Any PFR with a failure effect rating of quot2quot or quot3quot, coupled with a failure corrective action rating of quot3quot or quot4quot is identified as a Red Flag PFR indicating significant residual risk associated with the problem/failure in question. GSFC Project Manager signatures are required on all red flag PFRs. No delegation of signature authority is permitted. All red flag PFRs are highlighted at GSFC Project Flight Assurance Reviews. Project and Center Management Approval of Corrective Actions: A PFR is considered for closure when the FRB determines that appropriate and sufficient investigation of the cause of the problem/failure has been completed and that commensurate corrective action has been completed and properly documented. The following signatures are required to formally close a PFR: The Contractor Program/Project Manager and Contractor QC for PFRs initiated by off-site GSFC contractors The GSFC FRB chairman The GSFC Project Manager or his delegated FRB representative. Red Flag PFRs, defined above require the signature of the Project Manager. Technical Rationale: This practice ensures that all problem/failure occurrences including minor glitches are fully reported and dealt with as appropriate in a formal procedure with Project and GSFC management oversight and approval. References GSFC Flight Assurance Procedure, No. FAP P-303-849, quotProblem/Failure Reportingquot Guidelines for Standard Payload Assurance Requirements (SPAR) for GSFC Orbital Projects The GSFC Certification Log, FAP P-303-820 Problem Record Items, GSFC, FAP P-303-845 NASA NHB 5300.4 (1A-1) ReliabilityProgram Requirements for Aeronautical and Space Systems Contractors (January 1987) Reliability Preferred Practice PD-AP-1304, Problem/Failure Report Independent Review/Approval Reliability Preferred Practice PD-AP-1305, Risk Rating of Problem/Failure Reports Reliability Preferred Practice PD-ED-1232, Spacecraft Orbital AnomalyReport (SOAR) System Reliability Preferred Practice PD-ED-1255, Problem Reporting and Corrective Action System [D] Figure 1. GSFC PFR Form 4-2: Problem/Failure Report (Click on Image for .pdf file) [D] Figure 2. GSFC PFR Form 4-2 (cont.): Instruction Sheet for Problem/Failure Report (Click on image for .pdf file) | This practice has been used on all GSFC in-house flight programs in accordance with the GSFC Quality Assurance Requirements defined in Reference 2. Out-of-house contractors may use their system so long as it meets the provisions of the GSFC Quality Assurance Requirements and is approved by GSFC. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/03/2000
732 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Electrostatic Discharge (ESD) Control In Flight Hardware |  | Not following this practice in the handling of ESDS devices can and most likely will result in damage to these devices. One common form of this damage is a deterioration-to-failure process which may not be detected by ground testing. The damaged device may result in early degradation in performance or in mission failure. | Apply an Electrostatic Discharge (ESD) Control Program to all spaceflight projects to ensure that ESD susceptible hardware is protected from damage due to ESD. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1249; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. This ESD Control Practice significantly enhances mission reliability by protecting susceptible flight and critical flight support electronic parts and related hardware from damage and/or degradation caused by ESD and Induction Polarization Charge (IPC) during the prelaunch phases of the mission. Implementation Method: NHB 5300.4 (3L) "Requirements for Electrostatic Discharge Control " (Reference 1) specifies the NASA requirements for ESD avoidance and control. It describes basic considerations and requirements for ESD control programs including responsibilities of NASA Installations for invoking ESD control programs. GSFC Document No. P-303-840 "Electrostatic Control Program" (Reference 2) describes the ESD control program that has been established by GSFC for its spaceflight projects. The GSFC program incorporates the ESD requirements of Reference 1. The Reference 1 and 2 documents as well as this practice do not include ESD control requirements and programs for electrically initiated explosive devices. Special requirements for the control of these devices exist at the various NASA centers. This ESD Control Practice describes the procedures and controls whereby ESD sensitive components and devices are received, distributed, assembled, disassembled, handled, tested, repaired, and stored at GSFC. This practice applies to spacecraft, launch vehicles, mission peculiar equipment, mission-essential support equipment and elements thereof; when invoked contractually in procurements. The Practice includes many elements with many details. This description of the Practice can only cover the highlights with limited details. Refer to Reference 2 for complete details and a list of references to ESD control documents. The following are the primary features and requirements of this Practice. Quality Assurance Responsibilities for the ESD Program: ESD trained and certified personnel are assigned to support each project and are responsible for the following items: 1). Follow established procedures to verify that all ESD requirements are complied with in applicable work areas. 2). Certify the adequacy of ESD-controlled areas and grounded work stations prior to their use. 3). Ensure the use of protective personnel clothing and proper personnel grounding at all locations where ESD sensitive components and devices are handled. 4). Ensure that all personnel with access to ESD controlled areas and who handle ESD sensitive components and devices have been trained and certified in accordance with Reference 2. 5). Perform audits to assure the integrity of ESD-controlled areas. 6). Verify that all documentation including drawings and work instructions contain ESD marking precautions and handling procedures as appropriate. 7). Verify proper ESD markings or labels on ESD dissipating or shielding boxes/carriers/bags containing ESD sensitive components and devices, printed circuit boards or flight ready hardware with ESD sensitive components and devices. 8). Ensure that purchase documentation includes ESD requirements as appropriate. 9). Ensure that all handling of ESD sensitive components and devices are performed in ESD controlled areas. 10). Prepare and maintain internal records of each certification and audit to ensure compliance with the ESD Control Program. 11). Provide internal reports to the project and to the AMO with results and recommendations from audits. 12). Ensure that corrective actions are initiated for all NASA deficiencies noted during audits and certifications. Responsibility for ESD Work Sites and Spaces and for Workstations: The organizations responsible for the facilities where work/test sites or spaces are assigned are responsible for the implementation of the ESD Programs in their facilities. The cognizant System/Subsystem Electrical Engineer is responsible for the initial setup of ESD approved work stations. ESD Training of Personnel: All personnel with access to ESD-controlled areas and those who handle ESD sensitive components and devices receive training from an approved NASA training Facility. Additionally, those with any management or quality assurance responsibilities for ESD sensitive components and devices also receive training. This includes project management personnel, engineering, test, and integration personnel, acquisition and quality assurance personnel, field engineers for installation and maintenance where appropriate, and production, material handling, and stockroom personnel as appropriate. Janitorial and facility maintenance personnel receive on-site training and/or facility/project procedures as needed. Each individual attends one of several specific courses appropriate for his/her job assignment. All certified personnel must have their certification card with them whenever they are performing tasks which require ESD control. Certification must be renewed every two years. ESD Control Requirements: A long list of ESD control requirements too long to include herein is imposed when ESD sensitive components and devices are handled. The following is an outline of these requirements. Refer to Reference 2 for complete details. Control of ESD-controlled areas including personnel access and relative humidity. Control of ESD work surfaces and floors. Receiving and shipment of ESD devices. Equipment and materials used in the protection and handling of ESD devices. Protective packaging materials. ESD Audits: ESD-certified AMO personnel conduct audits of the facilities and the personal and work station equipment handling ESD devices in accordance with Reference No 2. These audits are scheduled in accordance with the schedule shown in Table 1. TABLE 1. ESD CERTIFICATION AND PERIODIC INSPECTION SUBJECT INITIAL CERTIFICATION CONTINUOUS EACH WORK SHIFT MONTHLY SEMI-ANNUALLY ANNUALLY Work Surface Resistivity (Including ESD Dissipative Mats) X X Work Surface Grounding X X Work Surface Solvent Resistance X X Work Surface Static Charge Dissipation X X Wrist Strap Release Force X X Wrist and/or Heel Strap Continuity X X Tool and Equipment Grounding X X Stool and Chair Grounding X X Facility Earth Ground X X ESD Controlled Area Metal Frame EntryDoors X X Humidity (RH) X X Certification of Electrostatic Field Survey Meter X X Monitoring Static Levels X X Nuclear Air Ionizer Effectiveness X X Corona Discharge Air Ionizer Effectiveness X X Check both Ionizers for: Ion Balance EMI Radiation X X X X Soldering Iron Tip Grounding X X Cart, Wagon and Tram Grounding (When Used) X X Temperature Chambers X X Personnel Garmets (Testing Physical Condition with an Eslectrostatic Field Survey Meter) X X Part of the audit is monitoring the testing of the equipment and recording the test measurements and the electrostatic voltage readings of the ESD-controlled work stations and areas. Records are kept of all ESD audit data, corrective actions, written reports on corrective actions, and follow up ESD audits conducted after corrective actions have been completed. Formal reports are prepared from these records and include comments/observations on any ESD-control deficiencies and suggestions for preventing recurrence. Technical Rationale: The generation of triboelectric and electrostatic charges are a common cause of damage and/or degradation to unprotected ESDS devices. A carefully devised and implemented ESD control program can provide protection from this damage and/or degradation. References NHB 5300.4 (3L), Requirements for Electrostatic Discharge Control (Excluding Electrically Initiated Explosive Devices) GSFC Document No. P-303-840, Electrostatic Discharge (ESD)Control Program | This practice has been used on all Flight Programs managed by the Goddard Space Flight Center (GSFC). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 04/03/2000
731 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Data System (SDS) Hardware Design Practice |  | If these design practices are not incorporated into the design of the SDS, early, partial, or complete curtailment of the mission could occur due to component failure or to false or inappropriate commands. SDS performance data may not be available for failure analyses and the capability for work-around procedures may not be available. | Use a standard SDS in spacecraft where possible which utilizes a standard data bus and space flight qualified versions of widely used hardware and operating software systems. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1248; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. This practice enhances reliability of the SDS and the probability of mission success by simplifying the design and operation of the SDS system and providing capability to work-around spacecraft and instrument problems. Implementation: The first SDS system described in this practice was successfully flown on the SAMPEX mission that was launched in 1992. This SDS system is being used on a number of later missions such as the X-Ray Timing Explorer (XTE), the Earth Observing System (EOS), and the Tropical Rainfall Measuring Mission (TRMM). The SDS is a dual-redundant command and data handling system which functions as a command decoding and distribution system, a telemetry/data handling system, and a data storage system. It provides on-board computational capability for processing attitude sensor data and generating commands for the attitude control actuators in a closed loop fashion. It also provides stored command processing and monitoring of the health and safety functions for the spacecraft and instrument subsystems. The system design allows for modularity and flexibility in adapting the system for many different spacecraft. The use of standard interfaces and space qualified versions of widely used processors and related software, translates into higher reliability and major cost and schedule reductions not possible with the use of spacecraft unique interfaces, processors and software. The higher reliability results from widespread experience with the standard hardware and software in both space and nonspace related applications. The following are design practices incorporated into the SDS to improve reliability. 1) Use of MIL-STD-1773 Protocol For Data Bus Interfaces: The use of the MIL-STD-1773 fiber optic data bus and associated standard processors and operating systems significantly simplifies the design of command and data handling systems and the test and integration of spacecraft systems. This approach also significantly reduces the number of failure prone wires and electrical connections previously needed in the discrete wiring method. The fiber optics also reduces the probability of upsets and other radiation problems due to the radiation environment. A SDS for a typical spacecraft, such as the X-Ray Timing Explorer (XTE),will provide three data buses, namely Attitude Control, Spacecraft, and Instruments. Figure 1 is a block diagram of the XTE SDS system architecture. [D] 2) Redundancy and Cross-strapping: The reliability of the SDS system is significantly enhanced by the total redundancy of the system with each unit provided an identical backup unit to the other. The SDS units are cross-strapped to their respective data buses which provide the interconnections between them. All bus connected subsystems, components, and instruments are cross-strapped to their respective data buses. The cross-strapping of the SDS with the up and down links is shown in Figure 2. This figure does not show the cross-strapping of the transponders with their antennas. The SDS receives both primary and redundant power lines. [D] 3) Error Detection and Correction (EDAC): An EDAC capability designed into the SDS system improves reliability by preserving the integrity of data and protecting against induced errors. The backplane for the SDS is based on a modified PC-AT 386 backplane design which has been optimized by the GSFC for use in a space environment. A significant modification is the addition of an 8-bit wide check bit bus to the PC-AT design to support the EDAC function. 4) Uplink Board: The reliability of spacecraft operations and control are enhanced by ensuring that the uplink board is the sole avenue by which commands and data are received by the spacecraft from ground support systems during orbital operations. The design for this board is modeled after the SAMPEX uplink board design, but incorporates a number of design modifications unique to the SDS design. The primary command link circuitry and operation is fundamentally unchanged, but a capability to accept hardware decoded uplink commands (bypassing the SDS system software) and cross-strapping between dual transponders has been added. A power converter has been added to the board design in order to permit the board's power supply to always remain on and independent from the rest of the SDS system power. The input to this power converter is unswitched power from the essential SDS power bus. The uplink board interfaces to the SDS and the rest of the spacecraft primarily through communication on the SDS MIL-STD-1773 data bus, on which it is designated as a remote terminal. There are 64 discrete hardware decoded command lines from the uplink card to various spacecraft subsystems. 5) Bulk Memory Boards: The reliability of the Bulk Memory Boards is increased by memory isolation circuitry which isolates a failed segment of the memory board and keeps it from affecting the entire data system. The SDS bulk memory board is modeled after the SAMPEX memory board design, but incorporates the memory isolation as well as a number of other SDS design modifications. 6) Low Voltage Power Converter Boards (LVPC): The design of the 2 redundant LVPCs in the SDS system are similar to the SAMPEX Recorder/Packetizer/Processor (RPP) power converter board except for two significant SDS changes to enhance reliability by providing capability for improved control of discrete RESET commands. One change was the addition of a redundant power line. The other change was the addition of a hardware-decoded discrete RESET input command which allows commanding of an 80386 reset independent of the SDS MIL-STD-1773 data bus and system software. 7) Reliability Related Command Execution Capabilities: Every SDS autonomous function is capable of being enabled or disabled by command. The SDS by command can perform preplanned diagnostic and operations checkout of itself. No single command can place the SDS into a configuration from which it cannot recover. The SDS can supply telemetry data such as configuration and health and safety status, indications of anomalous conditions, and performance monitoring data to enable ground controllers to assess the operational state of the SDS and its software. The SDS will execute only ground commands to exit from quotsafequot modes. 8) Failure Tolerance: The reliability of the SDS is significantly enhanced by its capability to tolerate single failures including the failure of spacecraft harnesses servicing the SDS. The SDS design does not permit a single failure to cause another failure or the loss of a redundant critical function path. Technical Rationale: The redundancy and cross-strapping features of the SDS and its data bus provide a wide range of fault isolation and work-around capabilities that can significantly increase the reliability and the useful life of spacecraft missions. In addition, a number of other design features minimize the impact of component failures and prevent the execution of false or inappropriate commands. References MIL-STD-1773: Fiber Optic Mechanization of an Aircraft Internal Time Division Command/Response Multiplex Data Bus Individual Project C&DH Specification and Interface Control Documents | This practice has been used on Solar, Anomalous, and Magnetospheric Partial Explorer (SAMPEX). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/31/2000
729 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Integration and Test Practices to Eliminate Stresses on Electrical and Mechanical Components |  | Noncompliance with these practices can result in damage to flight components during the integration and test program. Some of this damage will require replacement of components during the integration and test program whereas other damage can result in early failures during the mission. | Use proven GSFC practices during the integration and testing of flight hardware to prevent electrical and mechanical overstressing of flight hardware parts and components, thereby, assuring that the "designed in" reliability is not compromised. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice Number PT-TE-1429 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. These practices prevent the long term degradation and early failure of electrical parts and components due to electrical and mechanical overstressing. Damage due to overstressing may not result in immediate failure and may not be detected by component or assembly level testing but can result in early failures. Implementation: Formal Electrical Integration Procedures are prepared, reviewed, and approved to document and control the step by step procedures used in mating, testing, integrating, etc. of flight hardware at all levels of assembly. A number of practices are incorporated into these procedures to prevent electrical and mechanical overstressing of electrical parts and components. These practices are described in the following: Safe-To-Mate Cable Harness Test: This test is performed on flight cables and harnesses prior to their connection to flight hardware. A breakout box is inserted at one end of the cable. Power and signal flow, continuity, isolation, etc. are tested through the entire cable. This test checks for wiring errors that could apply over-voltages, reverse polarities, improper signals, etc. that could cause electrical stress to parts and components. Safe-To-Mate Cable And Simulator Test: This test is performed on cables and harnesses connected to simulators prior to their connection to flight hardware, A breakout box is inserted at the flight unit end of the cable or harness. Power and signal flow, continuity, isolation, etc. is tested through the entire cable or harness. This test checks for wiring errors in both the simulator and the cable that could apply over-voltages, reverse polarities, improper signals, etc. that could cause electrical stress to parts and components. Disconnect Meters Before Changing Range Scales: Meter probe connections to flight hardware and to GSE when connected to flight hardware are disconnected and grounded during meter range switching in order to drain off electrostatic charges and voltage transients that may develop during the range switching. Ground Cable and Harness Connectors Before Mating: Cable and harness connector shells are grounded before mating with flight hardware in order to drain-off electrostatic charges. Verify Ground Connections: The resistance of ground connections between flight hardware boxes and packages and between flight boxes and packages and structure ground are verified by measurement and must be no greater than 2.5 milliohms. Verify Power-off Before Mating Or Demating Connectors: Power-off is verified for ground support and test equipment and for flight hardware before signal and power connectors are mated or demated with flight hardware. This is to prevent transients and partial and intermittent connections that could occur during the connection process. Ground Scaffolding and Workstands: Scaffolding and workstands located near flight hardware are grounded to a central ground point to prevent electrostatic buildup and discharges to the flight hardware. Painting of scaffolding and workstands is not permitted in order to prevent electrostatic charge buildup on the painted surfaces that can be transferred to the flight hardware. Paint also prevents proper ground connections to the scaffolding and workstands. Unroll Tapes Slowly: Tapes used on or around flight hardware are unrolled slowly in front of an ionized air source if available in order to prevent electrostatic charge buildup and discharges to the flight hardware. Connector Savers: Connector savers are used on those flight connectors where frequent mates and demates are required during the integration and test program. The connector savers minimize the wear and stress on the connector pins due to frequent mate and demate procedures. Connector Demate Tools: Connector demate tools are used to demate flight connectors in order to minimize stress on flight connector pins. Log of Flight Connector Mates And Demates: A log of all flight connector mates and demates is maintained and monitored in order to access the impact on the connectors of the mates and demates and to facilitate cleaning of connector pins every 10 mate and demate operations. Secure Flight Cables To Connectors: Flight Cables are secured to the back of connectors with strain relief clamps or by potting in order to minimize strain at the connector pins and wire crimp areas. Check Cable Assemblies For Sharp Edges: Cable assemblies are carefully checked for sharp edges that could cut into or nick wire insulation and flight components and boxes during installation and handling and could cause a failure at a later date. Typically, these sharp edges are caused by the aluminum foil wrapped around cables for EMI shielding purposes. Abrasiveness Of Cable Harnesses On Flight Structure: Cable harnesses are designed and installed on flight structures so as to prevent abrasions on the structure and on flight boxes and parts. Abrasions can be caused by moving parts, handling during integration and test activities, insufficient bending radiuses, etc. Harness Flexing Across Hinged Joints: Harnesses across hinged joints are designed for the number of planned operations of the joint and also for an appropriate number of additional operations of the joint that could be required during the integration and test activities. Protection Of Flight Cables And Harnesses: Flight cables and harnesses are appropriately stored and protected from stress and damage until they are installed. This is to ensure that damage to cables and harnesses will not lead to early failures. Quality And Protection of GSE Cables: GSE and test cables are fabricated to good quality standards and are protected from damage to prevent failures that could result in stress to and early failures of flight hardware. This includes appropriate separation of power, signal , and ground wires to minimize cross coupling of signals and transients that could stress electrical parts and result in early failures. Technical Rationale: Electrical components in flight hardware can be very susceptible to damage due to overvoltages including transients and electrostatic buildups and discharges, application of voltages in the reverse polarity, application of improper signals etc. Flight connectors can be degraded and damaged by excessive and improper mates and demates. The damages can be so severe that the performance is affected and the faulty part can be identified and replaced during the integration and test program. However, in many cases the damage is not immediately apparent and can begin a process of gradual degradation to failure during the mission life of the hardware in space. The above practices have been adopted to prevent the damaging influences that can cause the degradation of components and the loss of reliable operation during the flight mission. | This practice has been used on all GSFC Flight Programs | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/31/2000
728 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Mechanical Fastener Inspection System |  | Inadequate procedures in the procurement and acceptance of fasteners could permit the use of inappropriate or defective fasteners in flight hardware and result in mission failure. | Applies a formal Flight Assurance inspection system for mechanical fasteners used in flight hardware and critical applications on ground support equipment (GSE), including all flight hardware/GSE interfaces. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice Number PT-TE-1433 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. This practice significantly enhances flight reliability by ensuring that mechanical fasteners do not fail during the mission due to inadequate integrity requirements or Quality Control inspection procedures. Implementation Method: The mechanical fastener inspection system, defined in detail in Ref. 1, assigns responsibility to specific Quality Assurance individuals assigned to each project team. These individuals are responsible for ensuring that the various steps, provisions, requirements, and procedures defined by the inspection system are appropriately complied with including review of fastener procurement documentation, monitoring of inspections and tests, reporting, and problem resolution. Specification, Ref. 2, defines the fastener integrity requirements for all fasteners used in flight hardware and for critical nuts and bolts used on ground support equipment, including all flight hardware/GSE interfaces. This specification includes specific requirements for material selection, audit of manufacturers and approval of their products, material test reports, and traceability. Quality Assurance Provisions include screening inspections and testing, visual inspections, tensile testing, nondestructive evaluation, dimensional inspection, and hardness and proof testing. The fastener inspection system ensures that the requirements of this specification are appropriately applied in the procurement of fasteners by each project by requiring that the Flight Assurance Manager or his/her designee review and approve all fastener procurements in accordance with Ref. 2. Fasteners, along with their vendor test and inspection reports, are delivered to the Assurance Management Representative, (AMR) assigned to the specific project. The project Cognizant Engineer, (CE) originates a work request for incoming inspection by a contractor operated inspection facility, (Lanham Inspection Facility) and also generates a Certification Log in accordance with Ref. 3. He also forms a Certification Log package by attaching appropriate vendor test and inspection reports and data to the Certification Log. The AMR reviews the Certification Log package and the work request and forwards this documentation and the fasteners to the Lanham Inspection Facility for inspection in accordance with a Fastener Inspection Test Plan, Ref. 4. All fasteners are identified as acceptable/rejectable in accordance with the Certification Log. Fasteners that exhibit nonconformance are tagged and impounded until they are dispositioned by the CE in accordance with the Problem Record, Ref. 5. On occasion, the Material Review Board will disposition discrepant fasteners and initiate corrective action to resolve nonconformance issues that can not be dispositioned by the CE in accordance with Ref. 5. Upon completion of the fastener inspection/test by the Lanham Inspection Facility, the Lanham inspector completes the Certification Log which includes all inspection reports and pertinent data associated with the inspection. The Certification Log and the fasteners are returned to the AMR for review. The AMR returns the conforming fasteners to the CE. Figure 1 is a flow diagram of the Fastener Inspection System. [D] Technical Rationale: The integrity of fasteners is a significant element in the reliable operation of flight hardware. The high reliability required of fasteners is dependent upon appropriate procurement documentation and acceptance inspection and testing procedures. References Fastener Inspection- GSFC Doc. No. P-303-625 GSFC Fastener Integrity Requirements- S-313-100 The GSFC Certification Log- FAP P-303-820 Fastener Inspection/Test Plan- GSFC Doc. No. FAP P-303-626 Problem Record Items - GSFC Doc. No. FAP-303-845 NASA | All Flight Programs at GSFC are required to use this practice. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/31/2000
730 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Sine-Burst Load Test |  | If sine-burst testing is not performed, structural load requirements should be satisfied by a static, sine sweep/dwell, or centrifuge load test or by conservative analysis. | The sine-burst test is used to apply a quasi-static load to a test item in order to strength qualify the item and its design for flight. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice Number PT-TE-1420 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. The sine-burst test is a simple method to apply a quasi-static load using a vibration shaker and shock testing software. Depending on the complexity of the test item, it often can be used in lieu of , and is more economical than, acceleration (centrifuge) or static tests. For components and subsystems, the fixture used for vibration testing often can also be used for sine-burst strength testing. For this reason, strength qualification and random vibration qualification can often be performed during the same test session which saves time and money. Implementation Method: The process involves subjecting each orthogonal axis of the test item to five-to ten cycles of a sine wave whose peak is equivalent to the qualification load level. The qualification load root-sum-squaring (RSSing) the limit loads that cause the most significant stress to the critical elements in the test item and multiplying this value by a qualification margin of 1.25 (Reference 1) . If the item can be placed in a combined axis fixture that orientates the test item in a manner that allows application of the correct combined qualification load vector, only one test has to be conducted. This option often prevents any overtesting of elements in the test item. Since the test is intended to impart a quasi-static load to the test item, the test frequency must be below the fundamental resonant frequency of the test item. As a general guideline, the test frequency should be less than one-third the test item resonant frequency to avoid dynamic amplification during the test. This is a strongly recommended guideline. In some cases, it is allowable to use a sinal-burst closer to the test items fundamental frequency if it solves a test procedure problem. Such a case would be where the qualification load input can not be theoretically applied due to constraints of the equipment such as exceeding shaker stroke. Using a sine-burst whose frequency is closer to the first primary resonant frequency, thus taking advantage of the first modes dynamic amplification factor, will result in achieving the correct loading. If test item/fixture weight rather than stroke is the limiting constraint, it is possible to achieve the desired level by overdriving the shaker current. The short duration of the test will allow this overdrive of shaker current. After the test level and fixturing method is determined, a sine-burst open loop program must be built to drive the vibration table. The practice at GSFC has been to synthesize the waveform using a short program, written in Time Series Language, a general purpose application program from GenRad. The resulting waveform is then transferred to the shaker control program, quotTransient Waveform Controlquot, which runs on a GenRad 2514 Vibration Control System. The actual test is conducted in a stepwise manner applying a number of lower level sine-bursts that are fractions of the full load. For example 1/8,1/4, and then 1/2 of full level. This assures the test conductor that the test item/fixture/shaker table is reacting in a linear manner. If it is not the waveform can be modified by outputting only a percentage of the programmed level, i.e., 90%. After these preliminary runs with corrections are made then the full load is applied to the item under test. The figure shown below is a typical sine-burst waveform. The waveform is sinusoidal with a ramp up to maximum level, several cycles at maximum level, and then ramp down to zero. The number of cycles at maximum level is usually 5 to 10 cycles. The sine-burst test is performed with the same fixturing used for sine and random vibration. [D] Technical Rationale: The sine-burst test was developed at GSFC to satisfy requirements for strength qualifying structures to quasi-static load specifications. The primary objective of the sine-burst test is to apply the specified acceleration to the test item in a uniform manner. A secondary objective is to minimize potential fatigue damage to the test item. At GSFC the test item can be a flight unit undergoing Protoflight qualification . Protoflight hardware is flight hardware that is flown after qualification testing. Since the applied loads in this test are significant, it is important that the total number of cycles of peak strain be minimized. The test frequency must be sufficiently below any resonant frequencies of the test item. This requirement will preclude sine-burst testing of large structures, which usually have lower resonant frequencies. The sine-burst test has been shown to be a cost effective alternative to either static loads or to centrifuge testing. References General Environmental Verification Specification for STS and ELV Payloads, Subsystems, and Components, GEVS-SE, January 1990, GSFC | This practice has been used on Sampex Spacecraft, COBE instruments and electronic boxes, and ISTP instruments. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/31/2000
723 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Independent Verification and Validation of Embedded Software |  | Failure to perform IV&V for software projects could result in software system weaknesses, performance of unintentional functions, and failure of the system and the mission. Anything less than a methodical, systematic rigorous treatment of IV&V could cause loss of mission, life, and valuable resources. | To produce high quality, reliable software, use Independent Verification and Validation (IV&V) in an independent, systematic evaluation process throughout the software life cycle. Using the IV&V process; locate, identify, and correct software problems and errors early in the development cycle. | MSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1228; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The use of Independent Verification and Validation (IV&V) processes ensures that computer software is developed in accordance with original specifications, that the software performs the functions satisfactorily in the operational mission environment for which it was designed, and that it does not perform unintended functions. Identification and correction of errors early in the development cycle are less costly than identification and correction of errors in later phases, and the quality and reliability of software are significantly improved. Implementation: Independent verification and validation is defined as a series of technical and management activities performed by someone other than the developer of a system to improve the quality and reliability of that system and to assure that the delivered product satisfies the user's operational needs. Verification is an iterative process aimed at determining whether the product of each step in the development cycle (a) fulfills all of the requirements levied on it by the previous step and (b) is internally complete, consistent, and correct enough to support the next phase. Validation is the process of executing the software to exercise the hardware, and comparing the results to the required performance. Embedded software is software that is designed to execute in a computational device to control or perform a specific process in support of an end item. End item examples include payloads, vehicles, experiments, flight avionics, ground support equipment, and other mission support activities such as mission, payload, and science operations. It could also be incorporated into laboratory experiments or simulations such as training, verification, or breadboard simulators. Embedded software is not used for general purpose computing applications. Some of the technical and management activities included in IV&V for embedded software are: requirements analysis and tracing; peer reviews; status monitoring and reporting; walk-throughs; dynamic analysis; simulations; risk analysis; code inspection; software library maintenance; audits; and IV&V testing using software analysis tools. These activities come into play during the various phases of the software development life cycle, and are usually documented in a family of reports as shown on Figure 1. [D] Figure 1: Synchronizing IV&V with the Software Development Life Cycle Although the IV&V is generally concurrent with the software developer's life cycle phases, the completion of the IV&V corresponding phases lags the completion of the software development phase slightly as shown on Figure 1. Typical key IV&V functions that are performed in each phase are summarized as follows: 1. Concept Analysis Phase: Documentation that is produced in the software development conceptual phase is independently evaluated. These documents include the statement of work, advanced planning reports, project initiation descriptions, and feasibility study reports. The allocation of functions to hardware and software elements, and the criticality of each software element are assessed. 2. Requirements Analysis Phase: Software requirements are verified through independent derivation of requirements, comparison to standard reference systems, functional simulations, and timing and sizing analysis. A software requirements traceability analysis and a software interface analysis are performed. A system test plan is developed, and acceptance test requirements are established. IV&V software is designed, and requirements analysis phase reports are prepared. 3. Design Analysis Phase: A number of techniques are used to verify the satisfaction of software requirements. These techniques include correlation of traceability between design elements, functional simulations, independent derivation of equations and algorithms, comparison with standard references and models, analysis of interfaces, and identification and development of a software test program. Design analysis techniques to be used for any particular function are dependent on the nature of the function (such as filtering, display output, and device interfacing). For example, logic analysis techniques are appropriate for executive control functions while mathematical methods are better suited for numerical functions. The proposed design of each software function is verified by using the selected method to determine the extent to which it satisfies the corresponding software requirements. Control logic is similarly verified to ensure proper interaction between software functions. 4. Implementation Analysis Phase: During this IV&V phase, two parallel activities are performed: (1) coding analysis and (2) testing. Coding analysis includes version comparison, textual and syntactical analysis, standards auditing, equation reconstruction, data structure analysis, flow charting, logic reconstruction, manual code inspection, traceability analysis, interface analysis, and database analysis. Software tools are employed to automate many of these program analysis techniques. They are used to help identify actual or potential errors in the developed code, and to reformat and consolidate information to facilitate manual analysis, software tools present a reliable, cost-effective means to supplement manual program analysis techniques. To maximize the visibility of software development quality, coding analysis is performed in parallel with code development. Coding analysis is achieved by analyzing the incremental code deliveries and modifications introduced in the updated program versions. Testing analysis includes the application of independent tests performed to determine compliance with software and system requirements. Component testing and interface testing are planned for both nominal and extreme conditions within the required performance limits. 5. Independent Verification and Validation Phase: Simulation, testing, inspection and computer-aided software verification and validation are performed during this phase. Problem reports are prepared which identify anomalies in formal documentation, source code analysis, software database analysis, and the software developer's test results. Component test results and interface test results are documented. 6. System Integration Analysis Phase: The credibility of the system in its operational environment is established in this phase. In this phase, the final results of the software development effort are evaluated after the software has been fully tested in IV&V, and all problems and discrepancies have been corrected. During this IV&V phase, integration, system, and acceptance tests are performed in a serial fashion to validate the software. 7. Operational and Maintenance Analysis Phase: The validated system is placed under configuration control during installation, checkout, operation, and maintenance. IV&V functions during the operation and maintenance analysis phase include monitoring problems reported and ensuring that they are resolved according to established configuration management procedures. Outputs of this phase are IV&V problem reports, installation and checkout reports, configuration management reports, and flight software problem reports. Technical Rationale: IV&V has proven to be a necessary function for software projects of all sizes, but is particularly important in large, critical software packages. Although the level of IV&V performed will be proportional to project size, its performance in embedded flight software projects is widely considered to be mandatory. References: 1. Lewis, Robert O.: Independent Verification and Validation. John Wiley & Sons, Publishers, New York, NY, 1992. MSFC Software Management and Development Requirements Manual. MM8075, George C. Marshall Space Flight Center, Huntsville, AL, January 21, 1991. IEEE Guide for the Use of IEEE Standard Dictionary of Measures to Produce Reliable Software. IEEE Standard No. 982.2-1988, Institute of Electrical and Electronics Engineers, New York, NY, June 12, 1989. IEEE Standard Dictionary of Measures to Produce Reliable Software. IEEE Standard No. 982.1-1988, Institute of Electrical and Electronic Engineers, New York, NY, April 30, 1989. Beizer, Boris: Software Testing Techniques, Second Edition. Van Nostrand Reinhold, New York, NY, 1990. Perry, William E.: How to Test Software Packages. John Wiley & Sons, Publishers, New York, NY, 1986. Hollocker, Charles P.: Software Reviews and Audits Handbook. John Wiley & Sons, Publishers, New York, NY, 1990. Wallace, Dolores R. and Fujii, Roger F.: Software Verification and Validation: Its Role in Computer Assurance and Its Relationship with Software Project Management Standards. NIST Special Publication No. 500-165, National Institute of Standards and Technology, Gaithersburg, MD, September 1989. Tauswarthe, Robert C.: A General Software Reliability Process Simulation Technique. JPL Publication No. 91-7, Jet Propulsion Laboratory, Pasadena, CA, April 1, 1991. Cost-Effectiveness of Software Independent Verification and Validation. NASA RTOP No. 323-51-72, Jet Propulsion Laboratory, Pasadena, CA, October 15, 1985. | This practice has been used on Apollo Launch Vehicles and Engines, and Space Shuttle Elements, Payloads, and Experiments. | N/A |  |  | Public | Not Specified |  | 03/30/2000
724 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Maintenance Concept For Space Systems |  | The need to identify quantity, cost, types of spares, and related servicing techniques required to sustain a space system mission capability is a prime driver in developing maintainability requirements for a space system at the onset of its design. A system maintenance concept should be developed to define the basis for establishing maintainability requirements and to support design in the system conceptual phase. The maintenance concept provides the practical basis for design, layout, and packaging of the system and its equipment. The number of problems associated with product support and maintenance of space systems can be reduced, if not eliminated, by applying the principles prescribed in the system's maintenance concept. | Develop a maintenance concept early in the program life cycle to provide a basis for full maintainability support. It should be used to influence systems design to ensure that attributes for ease of maintenance, minimization of repair and down time, and logistics support will be present in the final design. | GRC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique Number PM-3 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. Effective development of a maintenance concept can enhance the effectiveness of maintenance support planning and aid both logistics planning and design of a maintainable system. The maintenance concept can also provide assessments of cost savings for maintenance activities and resources allowable at each maintenance level. The maintenance concept provides the basis for overall maintainability design requirements for the program, and contains detailed planning of maintenance policy for the operational system. It establishes the scope of maintenance responsibility for each level (echelon) of maintenance and the personnel resources (maintenance manning and skill levels) required to maintain a space system. Early development and application of the maintenance concept in structuring the maintainability plan can eliminate or reduce occurrence of problems that may interrupt system operation. The maintenance concept for a new system must be systematically formulated during the early conceptual design phase of a program to minimize maintenance problems during the operational phase. This proactive approach is being used on Space Station-based experiment development programs at LeRC to incorporate current Space Station Program support principles, prescribed Space Acceleration Measurement System (SAMS) and Combustion Module One (CM-1) operational and repair policy, and identified sparing requirements. Elements This maintenance concept will aid in logistics planning and will guide design by providing the basis for establishment of maintenance support requirements in terms of tasks to be performed, frequency of maintenance, preventive and corrective maintenance downtime, personnel numbers and skill levels, test and support equipment, tools, repair items, and information. Inputs to the maintenance concept should include: a mission profile, system reliability and availability requirements, overall size and weight constraints, and crew considerations. The concept should support the following design elements as they apply to a manned orbital space program where on-orbit and ground maintenance is planned. Repair Policy The repair policy should consider the support to be provided at the maintenance echelons (levels) summarized in Table 1. Table 1. Echelons of Maintenance Organizational Maintenance Depot Maintenance Where Performed On-orbit NASA Center or Contractor System Maintainer Flight Crew Center Engineers and Technicians Basis Repair and retain equipment Repair and return equipment to stock inventory Type of work accomplished Inspect equipment Repair at module, ORU, and component level Remove and replace modules and ORU's Repair and maintain ground support equipment Adjust equipment Calibrate equipment Organizational Maintenance Organizational maintenance is maintenance performed by the using organization (e.g., flight crew) on its own equipment. This maintenance consists of functions and repairs within the capabilities of authorized personnel, skills, tools, and test equipment. Organizational level personnel are generally occupied with the operation and use of the equipment, and have minimum time available for detailed maintenance or diagnostic checkout; consequently, the maintenance at this level is restricted to periodic checks of equipment performance. Cleaning of equipment, front panel adjustments, and the removal and replacement of certain plug-in modules and Orbital Replaceable Units (ORUs), referred to as black boxes, are removed and forwarded to the Depot Level. Depot Maintenance Depot maintenance is maintenance performed at NASA Centers or contractor facilities for completely overhauling and rebuilding the equipment as well as to perform highly complex maintenance actions. The support includes tasks to repair faulty equipment to the part level, if deemed necessary. This level of maintenance provides the necessary standards for equipment calibration purposes, and also serves as the major supply for spares. System Availability Operational Availability (Ao ) is defined as the probability that at an arbitrary point in time, the system is operable, i.e., is quotup.quot It is a function of the frequency of maintenance, active maintenance time, waiting time, logistics time, administrative time, and the ready time of the system, and is expressed as: [D] (1) Where: UPTIME = the total time a system is in an operable state, and TOTAL TIME = the combination of uptime and downtime, in which downtime is the time in which a system spends in an inoperable state. Repair vs. Replacement Policy Normally, on-orbit repair should not be performed on any plug-in modules or ORUs. If any on-orbit repair actions are planned, they should be clearly identified in the concept. At the organizational level, failed items should be either discarded or sent to the NASA Center or contractor for exchange and repair in accordance with repair/discard policies identified in the system requirements. Corrective maintenance, limited to replacement of faulty ORUs and plug-in modules, should be specified to be performed during the mission period. Prime equipment should be designed to have ready access for maintenance. Quick-opening fasteners should also be specified. Level of Replacement The design for proper level of ORU definition should consider compatible failure rates for hardware parts within the same ORU. Relative ranking of ORU's through reliability and maintainability considerations and mission criticality analysis can also contribute toward the proper level of replacement definitions. The required level of replacement should be specified at the plug-in module and ORU levels. Maintenance and support of a system should involve two-tier maintenance echelons. The first level provides for repair of the end- item on-orbit by replacing select faulty or defective plug-in modules and ORUs identified through use of specified diagnostic procedures. Faulty ORUs should then be evacuated to the second level of the maintenance echelon (depot level), which will be at a NASA Center for repair if deemed necessary. The particular NASA center/ facility should act as the depot for repair of faulty items. Skill Level Requirements Hardware should be designed to aid on-orbit and ground maintenance, inspection, and repair. Special skills should not be required to maintain a system. The following design features should be incorporated: Plug-in module and ORU design to minimize installation/removal time and requirements for hand tools, special tools, and maintenance skills. Plug-in modules and ORUs should be designed for corrective maintenance by removal and replacement. Plug-in module and ORU designs requiring preventive maintenance should be optimized with respect to the access, maintenance hours, and maintenance complexity. Software and its associated hardware should be designed so that software revisions/corrections can be easily installed on-orbit with minimum skill level requirements. Flight crew training for payload flight operation should identify hands-on crewmember training, at the NASA center where the system is built, to familiarize crewmembers with the removal/replacement of hardware. Spares Philosophy Two basic types of spares should be required to support a maintainable system: development spares and operational spares. Development spares are those that must be identified and acquired to support planned system test activities, integration, assembly, check-out and production. Operational spares are those spares that must be acquired to support on-going operations on-orbit. The quantity of development spares required for each system, and the total quantities to sustain the required availability during the planned test activities, integration, assembly, and check-out test should be determined according to the following: Custom-made components/parts Long-lead time items The quantity of spares required for each system and the total quantities to sustain the required operational availability on-orbit should be determined according to the following: Items that are critical to system operation Items that have high failure rate Items that have limited life In the initial spares provisioning period and to the maximum extent practical, spares should be purchased directly from the actual manufacturer; i.e., lowest-tier subcontractor, to eliminate the layers of support costs at each tier. The initial provisioning period should cover early test and evaluation, plus a short period of operation, to gain sufficient operational experience with the system. This will provide a basis for fully competitive acquisition of spares. Spares with limited shelf life should be identified and should be acquired periodically to ensure that adequate quantities of spares are available when needed. Spares with expired shelf lives should be removed and replaced. Procurement of spares should be initiated in sufficient advance of need to account for procurement lead time (administrative and production lead time). The location of the spares inventory (on- orbit and on-ground) should be a function of the on-orbit stowage allocation capabilities and requirements. A volume/weight analysis should be conducted to determine the quantity and types of spare items necessary to sustain satisfactory operational availability. The volume/weight analysis shall assure available or planned payload volume and weight limits, and planned or available on-board stowage area. Breakout should be addressed during initial provisioning and throughout the replenishment process in accordance with NMI 5900.1, Reference 1. Breakout is the spares procurement directly from the original equipment manufacturer, prime contractor, or other source, whichever proves most cost-effective. A spare item requirement list should be maintained by procurement and technical personnel. Diagnostic/Testing Principles and Concepts The system should meet the following failure detection requirements as a minimum: The system should have the capability to detect, isolate and support the display of failures to the plug-in module level. Crew observations may be used as a method of failure detection of the following: visual displays, keyboards/buttons, general lighting, speakers. System design should provide the capability for monitoring, checkout, fault detection, and isolation to the on-orbit repairable level without requiring removal of items. Manual override and/or inhibit capability for all automatic control functions should be provided for crew safety and to simplify checkout and troubleshooting. All failures of the system should be automatically detected and enunciated either to the flight crew or the ground crew. Accesses and covers should be devoid of sharp corners/edges and be equipped with grasp areas for safe maintenance activities. Systems/subsystems/items should be designed to be functionally, mechanically, electrically, and electronically as independent as practical to facilitate maintenance. The concept should also describe operating/testing techniques to identify problems and consider the complexity of the various types of items in the space system and associated maintenance personnel skills (for all software, firmware, or hardware). The techniques will identify maintenance problems. In all cases of fault simulation, the safety of personnel and potential damage to system/equipment should be evaluated in the concept. The concept should request that a safety fault tree analysis be the basis for determining simulation. Also, a Failure Modes, Effects, and Criticality Analysis should be used to evaluate and determine fault simulation. Some of the fundamental maintenance actions to be evaluated, monitored, and recorded are as follows: Preparation and visual inspection time Functional check-out time Diagnostic time: fault locate and fault isolate Repair time: gain access, remove and replace, adjust, align, calibrate, and close access Clean, lubricate, service time Functional check-out of the repair action Responsibilities for Contractor Maintenance The prime contractor's maintainability program should provide controls for assuring adequate maintenance of purchased hardware. Such assurance is achieved through the following: Selection of subcontractors from the standpoint of demonstrated capability to produce a maintainable product. Development of adequate design specifications and test requirements for the subcontractor-produced product. Development of proper maintainability requirements to impose on each subcontractor. Close technical liaison with the subcontractor (both in design and maintainability areas) to minimize communication problems and to facilitate early identification and correction of interface or interrelation design problems. Continuous review and assessment to assure that each subcontractor is implementing his maintainability program effectively. Responsibilities for Payload Maintenance Director of field installations responsible for launch preparation, maintenance, or repair activities should be responsible for maintenance planning and for providing the resources necessary to support the efficient identification of maintenance related problems in accordance with system requirements. These responsibilities include: Implementing a system that will identify, track, and status problems related to routine maintenance activities attributable to the design characteristics of flight hardware and software. Providing information for use in a data collection system to improve the accuracy of quantitative maintainability and availability estimates. This information can be used to identify failure trends influencing reliability growth characteristics during design and to communicate quotlessons learnedquot from ground maintenance experience. Recommending to the Program Manager, responsible for design and development of flight hardware/software, areas for design improvement to increase the efficiency in ground processing or maintenance operations. The rationale for supporting these recommendations should include factors such as reduction in ground turnaround time and operational support costs. Allocation of Crew Time for Maintenance Actions Crew time for maintenance should be identified in accordance with system complexity, reliability, and criticality of the items to the system and mission requirements. Analytical methods exist which can be used to prioritize and allocate crew time for maintenance actions. References NASA Management Instruction, Spare Parts Acquisition Policy, NMI 5900.1A, NASA Responsible Office: HM/Procurement Systems Division, Washington, DC, November 6, 1992. NASA Management Instruction, Maintainability and Maintenance Planning Policy, NMI 5350.1A, NASA Responsible Office: Q/Office of Safety and Mission Quality, Washington, DC, September 26, 1991. NASA Handbook, Maintainability Program Requirements for Space Systems, NHB 5300.4(1E), Reliability, Maintainability, and Quality Assurance Publication, Washington, DC, March 10, 1987. Space Acceleration Measurement System (SAMS) Experiment, SAMS-SS Product Assurance Plan, SAMS-SS-005 (Preliminary), NASA Lewis Research Center, Ohio. Space Acceleration Measurement System (SAMS) Experiment, Express Payload Integration Agreement, SAMS-SS PIA, NASA Lewis Research Center, Ohio. Space Station Program, Space Station Program Definition and Requirements, Sections 3 and 4, SSP 30000, NASA Lewis Research Center, Ohio. Combustion Module One (CM-1) Experiment, Product Assurance Plan, NASA Lewis Research Center, Ohio. Blanchard, Benjamin S., Jr. and Lowery, E. Edward of General Dynamics, Electronics Division, Maintainability Principles and Practices, McGraw-Hill Inc., N.Y., 1969. | This practice has been used on Space Acceleration Measurement System (SAMS), Combustion Module-1 (CM-1), Shuttle/Station Experiment. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/30/2000
727 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Thermal Control Coatings Design and Application |  | If this practice is not followed, thermal control may not be maintained and spacecraft and their instruments and equipments may be damaged and fail due to exposure to temperature ranges beyond operating and failure limits. Also, ESD could occur which can cause damage and failures to hardware. | Select and apply thermal coatings for control of spacecraft and scientific instrument temperatures within required ranges and for control of spacecraft charging and RF emissions. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1239; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. This practice enhances the probability of mission success by controlling temperatures of flight hardware as well as spacecraft charging and RF emissions over the life of the mission. Implementation: Spacecraft and scientific instruments usually contain hardware, including sensitive detectors, which require that temperatures be maintained within specified ranges. A good thermal design is therefore essential to a successful mission. Thermal control coatings is one of several systems, such as thermal blankets and electric heaters, that are used to control temperatures. In space, the operating temperature of a spacecraft is determined by the heat input from the sun, the reflected solar energy from the earth, the background temperature of space, the internal heat generated by the spacecraft and by the emittance and absorptance of spacecraft coatings. Predicting the operating temperature of the spacecraft therefore requires a knowledge of the thermal properties (absorptance and emittance) of the coatings used. In addition to these basic requirements, it is usually necessary to be cognizant of other spacecraft requirements such as spacecraft charging and particulate and molecular contamination requirements in order to choose the proper thermal control coating. It is also important to know how those properties are going to degrade throughout the life of the spacecraft due to exposure to UV, high energy protons and electrons, low energy solar wind protons, and contamination from other parts of the spacecraft. The practice for the selection and application of thermal control coatings includes the following key elements in the selection and application of thermal coatings: 1) The absorptivity and emissivity of particular thermal control coatings are determined and verified by testing. When possible, test measurements are made with the test sample subject to actual flight conditions such as vacuum, temperature, etc. Electromagnetic theory can give useful insights into the absorption and emission of electromagnetic energy from thermal control coatings and how the absorption and emissivity vary as a function of angle, temperature, and wavelength. Maxwells equations can be used to show a theoretical description of the interaction of electromagnetic radiation with spacecraft coatings if one knows the optical constants of conductivity, permittivity, and permeability of the coating. However, in a number of cases, it has been shown that predicted reflectivity and emittance do not agree with test measurements. This can be due to lack of precise data and also due to the fact that electromagnetic theory does not always account for factors that can cause irregularities in the actual performance. Therefore, the absorptivity and emissivity of particular thermal control coatings are determined and verified by testing. 2) Effects of surface roughness and coating thickness are primary considerations in applications of coatings. The surface roughness and the thickness of thermal coatings can have a significant effect upon the emittance and absorptance of the coating. The absorption and emittance will begin to change when the surface is no longer optically smooth; that is when surface defects are much smaller than the wavelength of radiation being absorbed or emitted. When the wavelength becomes comparable to the size of the imperfections, multiple reflections and diffraction effects can occur resulting in changes in the absorption and emittance. Also, if the coating is too thin, the coating becomes partially transparent in the infrared or visible part of the spectrum. This makes the effective emittance or absorption of the coating the sum of the emittance of the coating plus some portion of the emittance of the substrate. It is important to test samples analogous in roughness and thickness (same coating processes and substrate) as used in the space application. Thickness is also a consideration for optimum adhesion and stability during thermal cycling. 3) Flight data is researched and laboratory testing is performed to determine a thermal coating's susceptibility to space radiation and the amount of degradation that can be expected during the lifetime of a mission. Degradation of thermal control coatings in space can manifest itself as changes in emittance, solar absorptance, loss of adhesion, changes in specularity, or changes in electrical conductivity. These changes can be caused by absorption of electromagnetic photons, contamination of the coating by outgassing from other parts of the spacecraft, and by thermal effects on the coatings. The degree to which thermal coatings degrade also depend upon the energy and total contamination that the coatings receive during the mission. It is therefore, necessary to assess the mission radiation environment. This includes the energy fluency at each energy level of protons, the total UV exposure and atomic oxygen exposure level over the life of the mission. From this data, a test program is devised to determine the susceptibility of the coating to each form of radiation as well as to assess the synergistic effects of multiple radiation sources. 4) A detailed analysis of the contamination of the spacecraft is performed in order to determine the amount and type of contaminates expected to develop on surfaces of the spacecraft. Chemical contaminants on surfaces including oxide layers deposited either by absorption or through a chemical reaction with the surface can cause significant changes to the absorptance, emittance and conductivity. These surface contaminants can change the chemical composition of the outer layer and the electrical conductivity thereby increasing the emittance of most metals. Particulate surface contaminates can also affect the thermal properties of coatings. This effect though is usually much less than that caused by chemical contaminants. Particulates tend to scatter incident radiation but since the total area coverage is small they generally do not greatly affect the absorption or emittance unless the contamination becomes excessive. In addition, very thin layers of particulate contamination can have an effect on the emittance of a coating and must be taken into account. 5) Electrical properties are primary considerations used in the selection of thermal control coatings. Electrostatic discharges (ESD) can occur in space between various parts of a spacecraft due to differential charging of the spacecraft caused by energetic charged particles. This ESD is a source of electromagnetic interference (EMI) which can be coupled to electronic circuits and devices. Sensitive ICs can be damaged by several micro-joules (uJ) of ESD and circuits can be upset with only several nano-joules (nJ). This charging phenomena has been blamed for arcing that has caused blown fuses and loss of data transmission on several spacecraft. ESD can also cause electronic parts failure, operational anomalies, degradation of thermal control surfaces, and can also render low energy particle detectors useless. It is recommended that the energy stored by each electrical nonconductive surface be less than milli-joule (3mJ) and that ESD should not be allowed to occur near receivers or antennas operating at frequencies less than 8 GHz or near sensitive circuits. This implies that the spacecraft must be immune to 3 mJ ESD. Differential spacecraft charging is primarily the result of low energy electron flux. High energy electrons penetrate the thin thermal coatings and therefore do not contribute to the differential charging process. The relatively few high energy protons encountered do not penetrate the coatings and therefore contribute to the charging although to a much less extent than the low energy electron flux. This is because the mass of electrons is much less than the mass of protons and they must travel much faster than protons in order to reach the same kinetic energy and hence thermodynamic equilibrium. This means that the total number of electrons passing a given point in a fixed amount of time is greater than for protons, therefore the spacecraft receives a much greater electron flux than proton flux. Finding a coating which satisfies both thermal and electrical conductivity requirements is sometimes difficult to achieve, particularly if a low absorptance high emittance coating is needed. The conductivity of coatings can depend upon a number of factors. First, the length of time the coating has been exposed to vacuum can cause outgassing of volitales and water vapor which can alter the conductivity. Second, the energy of the electron flux can have a bearing on the extent to which a coating will charge since the conductivity is a function of particle energy. And thirdly, the temperature of the coating can also play a significant role in the charging process. Therefore the measurement and the verification of the conductivity of space flight coatings is performed under as close to actual conditions as is possible in a laboratory. In those cases where a coating is applied over a nonconductive substrate, charge control is achieved through the conductivity of the coating. Provisions are made for grounding the edges of the coating. In some cases the substrate is coated with a conductive medium before the thermal coating is applied in order to alleviate a high charge with respect to ground. Refer to the following Figures 1 and 2 for methods for grounding conductive coatings to spacecraft ground. [D] [D] 6) Specific, detailed, and written GSFC approved methods and procedures have been prepared for the selection, handling, and application of each thermal coating used on GSFC instruments and spacecraft. These procedures have been prepared for both paint and tape coatings. The procedures include general considerations on the use and applications of the coatings, formulation where applicable, and complete procurement and acceptance inspection and testing requirements. Acceptance testing includes outgassing tests, electrical charging and erosion characteristic measurements as applicable, adhesion, and optical measurements and degradation. Materials and equipment lists for handling and applying the coatings are provided including safety and toxic considerations and equipment such as air filtration and ventilation hoods etc. Formulation and blending procedures are detailed where applicable as well as surface preparation and cleaning procedures including post coating operations and cleaning and touch up. The application of the coating whether by brush, spraying, or by applications of strips of tape are defined. The procedures require monitoring samples for inspection and testing and in some cases require that monitoring samples be maintained for inspection and testing throughout the life of the coating in space. Storage requirements and shelf life limitations of coating materials must be observed. Curing times can be a factor to be considered in the selection of coatings due to interference with other testing or hardware activities. Complete documentation is maintained of the coating material from delivery to launch of the spacecraft. A procurement log of delivery date, manufacturer's batch and lot numbers, expiration of shelf life date, etc. and incoming inspection and testing data including monitor samples are maintained. A processing work order document is filed in the coating facility to provide a description of the specific coating requirements including required tests and test samples. A complete log of the coating process including any problems and test failures is maintained. Technical Rationale: The reliable operation of a spacecraft and its complement of scientific instruments and equipment require thermal control coatings to maintain temperatures within specified ranges. In addition, these coatings must also control spacecraft charging and ESD. This practice ensures good thermal coating design and application procedures to reliably meet a wide variety of thermal design and ESD requirements. References Handbook of Heat Transfer, (Rohsenow & Hartnett), GSFC Library Reference No. QC320.R528 C.1 Engineering Radiation Heat Transfer, (J. A. Wiebelt), GSFC Library Reference No. QC320.W64 C.1 Radiation Pyrometry and Its Underlaying Principles of Radiant Heat Transfer, GSFC Library Reference No.QC.338.H31 C.7 Thermal Radiation Heat Transfer Vol.1 NASA SP-164 Environmental Testing of Thermal Control Coatings Design Material IITRI Proposal 72-422C Solid State Physics, Ashcroft and Mermin Long Term Performance of Thermal Control Coatings at Geosynchronous Altitudes Hall and Fote Spacecraft Dielectric Materials Properties and Spacecraft Charging A. R. Fredrickson and D. B. Cotts TL 1492 SG2 1986 J. A. Wall and F. L. Bouqet NASA Reference Publication 1121 Entitled quotSolar Absorptance and Thermal Emittance of Some Common Spacecraft Thermal Control Coatingsquot Prepared by John Henniger Individual Procedures For The Formulation, Application And Maintenance Of Thermal Control Coatings Prepared by GSFC Thermal Control Branch |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/30/2000
725 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical, Electronic, And Electromechanical Parts Selection Criteria For Flight Systems |  | Selecting nonstandard parts for use in flight systems is definitely not recommended but is allowed depending on the hardware function, criticality, application, and environment. Unreliable components have delayed flight projects on the launch pad and have caused serious flight problems, adding significant expense to the flight operation. | Use highest reliability EEE parts available, consistent with functional requirements, program cost, and schedule constraints, for spaceflight systems. | GSFC | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1236; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. One of the most important considerations in designing reliable flight hardware is selection and use of the highest quality possible components. Proper selection, application, and testing of Electrical, Electronic, and Electromechanical (EEE) components will generally contribute to mission success and provide long term program cost savings. An effective EEE parts program has helped many projects in achieving optimum safety, reliability, maintainability, on-time delivery, and performance of program hardware. The resulting reduction in parts and part-related failures saves program resources through decreased failure investigation and maintenance costs. Implementation Method: The selection of EEE parts should be driven by performance demands, environmental and circuit application, reliability, and maintenance allocations defined by the equipment specification. EEE parts should be selected based on the suitability for their applications and proven qualifications to the requirements of their specifications. Selection of standard EEE parts when required or where feasible, will help minimize the number of styles and generic types and will provide parts with proven technologies and inherent reliability features. Program Requirements Documents (PRDs) for the various NASA hardware usually includes EEE parts selection criteria, including definitions of standard and nonstandard parts. There is an order of precedence for selection of EEE parts that range from MIL-STD- 975 grade 1 parts down to commercial off-the-shelf parts/hardware. When standard parts are required by the PRDs, but the design requirements cannot accommodate any of the parts listed in MIL-STD-975, there is a provision for submittal of a nonstandard part approval request (NSPAR). A NSPAR request is made and approved prior to procurement and use of the part in the design. 1. Standard Parts General. The parts listed in MIL-STD-975 have been selected to meet the needs of a project while providing parts that are available, economical, and recognized within the parts industry as quality parts. The specifications for these parts are based largely on the Department of Defense (DoD) parts standardization program and methods. All users of MIL-STD-975 have a responsibility to inform the NASA Parts Project Office (NPPO) of the requirement for new or improved parts . NASA Headquarters has designated GSFC as the lead Center. Requirements. Standard parts are listed in MIL-STD-975; procured in accordance with the specifications listed; processed in accordance with any special requirements shown; procured from the designated sources of supply; bear the specified part designations, and are properly classified. Parts exhibiting equivalent performance requirements and having the same generic part designation as the standard part, but not procured to the MIL-STD-975 specifications or from the qualified manufacturing sources, are not standard parts. These parts are treated as nonstandard parts. Assurance requirements for standard parts are included in the procurement specification for these parts. These requirements typically include qualification testing, in-process tests, inspections, quality conformance testing, screening, and any special processing requirements. Standard part grade levels. MIL-STD-975 provides two levels of parts to accommodate part reliability, cost, availability, and delivery. Grade 1 parts are those which demonstrate a low failure rate. Grade 2 parts are available at a lower cost than grade 1 parts, but often exhibit higher failure rates. The requirements for grade 1 and grade 2 parts are contained in the controlling source control documents which describe the differences in part design, processing, qualification, quality conformance inspection, and screening to ensure appropriate reliability and performance. Screening. The screening requirements for standard parts are included in the procurement specification for the part. Radiation effects. The radiation requirements for standard parts are specified in the source control document for the part. For those parts that require radiation hardness, two important requirements need to be specified: total dose and single event effect (SEE) magnitudes. Derating. Derating is the reduction of electrical, thermal, and mechanical stresses applied to a part in order to decrease the degradation rate and prolong the expected life of the part. Derating increases the margin of safety between the operating stress level and the actual failure level for the part, providing added protection from system transients. All parts must be derated in their application in accordance with the PRD's derating requirements (usually MIL-STD-975, Appendix A). 2. Nonstandard Parts General. Any part that is not listed in MIL-STD-975 is a nonstandard part. Nonstandard parts are submitted for review and final approval by the project office. Requirements. All nonstandard parts must perform satisfactorily in the mission envelope. Risks using nonstandard parts are identified. The following steps are often taken when selecting a nonstandard part (i.e. data required to complete Form 4-15): Establish that the part is required for form, fit, and function. Prepare a source control drawing for the part if none are available. Identify screening and quality conformance requirements for the part. Develop a rationale for why the part is needed. Explain why this part has been accepted. Identify problems with the part (i.e., GIDEP ALERT or NASA TWX). (This should be completed for all parts.) Select and certify qualified manufacturers for the part. Identify radiation hardness requirements, if applicable. Processing nonstandard parts. Nonstandard parts are divided into the following categories based upon their nearest equivalent part availability: Nonstandard military parts. Standard Military Drawing (SMD) parts that are listed in MIL-I-38535 Qualified Manufacturers List are non-standard parts unless they are listed in MIL-STD-975. Acceptance of this category of part should be considered if: (a) proper grade level of part is being used; (b) there is any reason a standard part cannot be used; (c) there are any reported problems with the part; (d) there are any additional tests, screening, or quality assurance provisions required by MIL-STD-975 for the nearest equivalent standard part; or (e) the part meets the expected radiation environment. Commercial parts. A commercial part is any part for which the part requirements, processing, and tests are stipulated solely by the parts manufacturer and are exclusively under the manufacturer's control. Establishing qualification for these parts takes time, costs money and depends on the application, mission environment, and tailored test program. Items (a) through (e) from paragraph on nonstandard military parts should be reviewed even more carefully for these parts. New improved or developed parts. Accepting new-technology parts is somewhat difficult. It is important that their form, fit and function be necessary. They must also be qualified for the mission environment. A comprehensive qualification test program should be conducted and the test results must be examined carefully to ensure the new part meets the mission needs and that it will perform in the expected radiation environment. Custom and limited-application parts. Nonstandard parts that are intended for a custom use or for a limited application often do not have qualification data. Here again, careful study is important to ensure these parts are really necessary and if they have special form, fit or function that cannot be obtained from heritage parts. They must meet the mission environmental and radiation requirements. The response to these items should be addressed prior to procurement and installment of the nonstandard part in the flight system. Acceptance of nonstandard parts. If nonstandard parts are used in spaceflight systems, they should be qualified to meet the mission requirements. Nonstandard parts should be qualified to identify predominant failure modes and mechanisms. They should be screened against the known failure modes and mechanisms, to verify conformance of the electrical characteristics against the controlling procurement specification, and to assure the absence of workmanship defects. The evidence supporting their acceptance must be verified, documented, and approved by the project office. Final acceptance for procurement is the responsibility of the Project Office. Technical Rationale: One of the aspects affecting mission success of flight systems is the selection of standard EEE parts which have designed in reliability at the part level. This implies utilizing proven technology parts, procured from qualified manufacturers, and selected from an established program based on project approved parts lists which are, based on the requirements levied for the program. A parts program assures that the selected parts, derating and testing activities are sufficient to achieve mission success for the application environment and expected life of the program. The projects are responsible for providing acceptable parts for their mission classification and for the circuit design, production, and testing to verify flight readiness. The selection of mission classified parts for spaceflight systems is an essential part of the design of flight hardware. With the rapidly growing technologies in the microelectronics area, the selection of parts has become a challenge to designers. The selected part has to perform reliably in the application. References NHB 5300.4(1F) "Electrical, Electronics, Electromechanical (EEE) Parts Management and Control Require-ments for NASA Space Flight Programs," July 1989. MIL-STD-975 "NASA Standard Electrical, Electronic, and Electromechanical (EEE) Parts List," January 1994. MIL-STD-978B NASA Parts Application Handbook, Vol. 1 - 5, March 1988. Reliability Preferred Practice PD-EC-1101, Environmental Factors Reliability Preferred Practice PD-ED-1201, EEE Parts Derating Reliability Preferred Practice PD-ED-1203, Class S Parts in High Reliability Applications Reliability Preferred Practice PD-ED-1212, Design and Analysis of Electronic Circuits for Worst Case Environments and Part Variations Reliability Preferred Practice PD-AP-1303, Part Electrical Stress Analysis Reliability Preferred Practice PD-AP-1306, Thermal Analysis of Electronic Assemblies to the Piece Part Level Reliability Preferred Practice PT-TE-1401, EEE Parts Screening Reliability Preferred Practice PT-TE-1411, Heat Sinks for Parts Operated in Vacuum Reliability Preferred Practice GD-ED-2202, Design Considerations for Selection of Thick-Film Microelectronic Circuits Reliability Preferred Practice GD-ED-2203, Design Checklists for Microcircuits |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/30/2000
726 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | End-To-End Compatibility and Mission Simulation Testing |  | Nonpractice of End-to-End Compatibility and Mission Simulation Testing could result in marginal performance or failure of the mission due to incompatibilities in the Ground Data System. Control center operational errors due to inadequate training could significantly impact the health and safety of the spacecraft. | End-to-End Compatibility and Mission Simulation testing are conducted on all portions of the Ground Data Systems (GDS). These tests are performed to fully demonstrate the operational compatibility and the ability of the entire system to perform as expected during the flight mission. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice Number PT-TE-1437 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: This testing significantly enhances flight reliability by ensuring that all portions of the flight operational system work together as expected. This includes the proper flow of data to the end users. Implementation Method: The GSFC Mission Operations and Data Systems Directorate (MO&DSD) develops, maintains, and operates a worldwide Ground Data System (GDS) to support a wide range of flight missions. Various organizational units within the MO&DSD such as branches, sections, and mission readiness test teams collaborate with the Flight Project and the Flight Assurance Directorate in planning and performing a wide range of mission readiness testing. The purpose of this readiness testing is to verify the performance and to demonstrate the readiness of the integrated GDS to support specific flight missions. This practice is implemented by the MO&DSD in the following three basic phases. Phase A: Acceptance and Interface Testing of Individual Elements of GDS Acceptance and Interface testing is performed on each element of the GDS for each flight mission. This testing is particularly applicable to those hardware and software elements in the GDS that have been updated, modified, or added to meet specific requirements of a mission. The acceptance and interface testing is followed by a formal Project Integration and Test Program. The Project Integration and Test Program verifies that the GDS can meet all of the project mission support requirements and documents the system's operational readiness. After all requirements have been verified, all discrepancies have been resolved, and all corrective actions have been completed, the verification process through Integration and Test is complete. The GDS is now ready to participate in Phase B, Compatibility Testing. Phase B: Compatibility Testing Compatibility testing is conducted on all portions of the operational system including the payload, the operational software, and the ground systems. The ground systems include the Space and Ground Networks, the Mission Operations Control Center (MOCC), and the data processing facilities. When the mission scenario calls for electrical operation of the payload aboard the STS or in conjunction with it, compatibility of the operational system is demonstrated with the use of the appropriate elements of the STS, such as the Orbiter Payload Data Handling System and the Mission Control Center. After completion of compatibility testing, the GDS is ready to participate in Phase C, Mission Readiness and Mission Simulations Testing. Phase C: Mission Readiness And Mission Simulation Testing Mission Readiness Testing is conducted to verify that system design specifications are being routinely met, to ascertain the level of operational proficiency being maintained throughout the networks, and to evaluate the network's abilities to meet or exceed design specifications in response to project requirements. An evaluation phase follows in which all Discrepancy Reports (DRs) are reviewed by a DR Review Board. Mission Simulation Testing includes data flow tests performed on the total system in a realistic mission timeline. When practical, external stimulus of the spacecraft instruments and attitude control sensors are used. Mission Readiness and Mission Simulation Testing is carried out in accordance with formal test plans prepared and approved by the MO&DSD with concurrence by the flight projects. These test plans define test coordination, system requirements, test procedures, problem resolution procedures, and reporting requirements. In order to ensure an integrated testing effort, testing and planning is coordinated through a Mission Readiness Test Team comprised of project and MO&DSD development, test, and operations representatives. Test Facilities and Systems Used for Compatibility and Simulations Testing This section on test facilities and systems used for compatibility and simulation testing provides a description of the major elements of the GDS and how they are used in these test programs. The Simulations Operations Center (SOC) located at the GSFC provides support and test tools that can emulate the spacecraft, the MOCC, the Network Control Center, and the Ground and Space Networks. System evaluations and validation test and simulation programs are also conducted to characterize new or modified Space and Ground Network capabilities, to verify that system design specifications are being met routinely, to ascertain the level of operational proficiency being maintained throughout the networks, and to evaluate network abilities to meet or exceed design specifications in response to user requirements. The SOC provides various resources used to simulate and test ground data system elements. These resources include the Project Platform Training Simulator, the SOC Mission Control Simulator, the RF Simulations Operations Center, the Portable Simulations System, and various utility programs such as a Super Programmable Data Formatter and the data blocker/deblocker. The SOC has a standard NASA Communications (NASCOM) interface which permits it to communicate with all ground data system elements during Simulation and End-to-End Testing. The Platform Training Simulator provides support for training Flight Operations Teams (FOT) in normal and contingency operations of the spacecraft. The FOT can refine and practice operations and contingency procedures without using valuable spacecraft time. The Training Simulator is also used to support the Integration and Test data flows and the Network Simulation tests. The SOC Mission Control Simulator emulates the Johnson Space Center's payload support functions for simulations with the MOCC. The RF SOC is a simulations facility used for Space Network (SN) simulations and data flows. It has the capability to communicate with the Tracking and Data Relay Satellite E through a small satellite earth terminal located at the GSFC. The Data Evaluation Lab (DEL) provides recording systems, engineering support, and special data services. It can generate, quality check, and provide distribution for pre-mission simulation tapes and analog tapes. Additionally, the DEL can playback generated tapes in the form of data flow to the Mission Operations Center (MOC) and other elements in support of engineering, pre-mission, and operational readiness tests. The SUPER Programmable Data Formatter (PDF) is a portable, stand-alone system used in the SOC or at remote sites for ground system data flow tests, interface verification tests, and end-to-end rehearsals. The SUPER PDF can generate simulated real-time and playback telemetry. It is packaged in a portable unit for supporting tests from the Ground network (GN), spacecraft integration areas, or launch sites. Mobile Compatibility Test Vans (CTV), normally stationed at the GSFC, travel to the spacecraft factory or to the launch site. They are used for verifying the spacecraft's RF compatibility with the network by performing initial checkout of the spacecraft RF interface with the tracking and data networks. The CTVs also provide the MOCC with a direct link to the spacecraft at the manufacturer's plant. The CTV can send spacecraft telemetry data via the GN and NASCOM to all support elements and can receive commands from the MOC via the SN and the NASCOM. They can also be used as a data source for performing network verification tests. Monitoring and Witnessing of Ground Data System Testing The GSFC Office of Flight Assurance assigns an Assurance Management Representative (AMR), a Systems Assurance Manager (SAM), and others as needed to perform assurance functions on flight projects. These functions include identifying tests to be monitored or witnessed, determining the level of coverage based on the test objectives and criticality, and arranging for the coverage by assurance representatives or their contractors. The assurance functions also include observing and reporting on the success of the test in meeting its objectives. The results are documented and identify any events or anomalies for use by engineering and management. The AMR test report contains the objectives of the test, anomaly reports, corrective actions expected, and the AMR's appraisal of whether test objectives were met. Technical Rationale: The detailed performance of the Ground Data System in meeting the specific technical requirements of spaceflight missions is thoroughly evaluated and validated in order to ensure mission readiness and compatibility with mission requirements. This readiness includes the training of control center operational personnel by simulating and practicing both nominal and contingency flight operations. References GSFC Document Entitled "Directorate Test Support", Subject - Code 500 Directorate Test Support GSFC Document Entitled "Flight Assurance Procedure" No. P-303-1025, Subject-Monitoring and Witnessing Ground Data System Testing" GSFC, SPAR-3, Standard Payload Assurance Requirements (SPAR) for GSFC Orbital Project, Paragraph 3.7 March 1990 | This practice has been used on all flight programs managed by the Goddard Space Flight Center (GSFC). They are required to use this practice. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/30/2000
720 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Star Image Metrology Part II: Irradiance Measurements |  | If end-to-end systems measurements are not made on spaceborne or space-related optical imaging systems, then the consequences could be the ultimate failure of the mission in-whole or in-part. The Hubble Telescope should be a constant reminder of this. | The fundamental behavior of a spaceborne (or space-related) optical imaging system is contained in its response to an impulse, i.e., a point source. The point source image is referred to by a variety of names: star image, point spread function, far field pattern, impulse response, Fraunhofer diffraction pattern. Here we will use quotstar image.quot This guideline provides information on instruments and procedures used in measuring star image irradiance distributions. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GT-TE-2406 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Star image measurements provide the primary means of appraising end-to-end health of an optical imaging system. These tests represent good engineering practice, and are reliable indicators of system performance. Star image tests are thus the final arbiter of quality control. A system passing the star tests discussed here ensures that the optical instrument is performing in a reliable way. Measurements of irradiance distributions provide important quantitative information concerning the fidelity of the star image to theoretical expectations. Such measurements either validate performance, or provide important clues as to the nature of a problem. For example, the problem might be a decentered component or an inappropriate conic constant. Implementation Method: 1. Description of Star Image Test Apparatus The basic equipment needed to perform laboratory star image visual measurements is indicated in Figure 1. The optical system on the left half of the drawing is a Star Simulator. This is a Collimator with a back-illuminated pinhole located in the focal plane. The Collimator can be either reflective or refractive, and its pupil should be larger than the imaging system being tested. The pinhole represents the star, and its diameter should be smaller than the Collimator Airy Disc, (i.e., unresolved). Depending on the application, the pinhole back-illumination can be either from a coherent or incoherent source. An example of the former is a laser; the latter, a point arc lamp. Between the source and the pinhole there is usually some coupling optics to maximize the power through the pinhole, and to fill the aperture of the Collimator with light. [D] Figure 1: Basic Layout of a Star Image Test Setup Caution: The pinhole acts like a quotpinhole camera.quot If a coiled filament lamp is used, an image of the coil will be formed on the collimator pupil and the output irradiance will be quite nonuniform. A support structure is needed to hold the optical system under test. This mounting fixture should provide modest azimuth and elevation tilt control to allow alignment of the quottest systemquot to the Collimator optical axis. The test support fixture should also allow the quottest systemquot to be accurately rotated through its operational field of view. For refractive quottest systems,quot the rotation axis should ideally pass through the system's rear nodal point. A mechanical support fixture that accomplishes this is called a T-Bar Nodal Slide. (Reference 1.) However, for catadioptric and reflective systems, rotation through the rear nodal point is impractical because this point is usually far removed from the physical embodiment of the quottest system.quot In this Guideline, the rotation axis will be at, or near, the entrance aperture of the quottest system.quot For irradiance measurements the quottest systemquot star image can be probed directly by some methods. Other methods need a magnified star image. In the latter case, this can be accomplished using a high quality microscope objective which should be well-corrected for both axial color and spherical aberration. Its numerical aperture must be sufficient to collect all the light emerging from the star image. In the Reliability Preferred Practices Guideline No. GT-TE-2405, ìStar Image Measurements, Part I: Visual Measurementsî, we relied on making dimensional measurements by eye on key features of the star image both laterally and axially. In this Guideline, irradiance is the key measurement parameter. The dimensional features discussed in Part I are not lost but contained within this broader measurement context. 2. Ideal Star Image Please refer to Reliability Preferred Practices Guideline No. GT-TE-2405 (Lesson Learned 0718). 3.1 Axial Intensity Method A new technique (Reference 2) has been developed in recent years that makes use of axial intensity scans on star images to extract quantitative information about aberration content. Laboratory embodiments can have a number of forms. One embodiment is illustrated in Figure 2 which makes use of a commercially available quotscanning micrometer eyepiece.quot The star image is magnified with a microscope objective. The magnified image is centered on the entrance face of a fiber optic. The exit face of the fiber is coupled to a detector such as a photomultiplier tube (PMT). The output signal of the detector is connected to the y-axis of an xy-recorder. The x-axis is driven by a signal from a linear transducer attached to the Z-axis motion of the microscope. The experiment generates an intensity plot as a function of axial microscope position. [D] Figure 2: Experimental Configuration for Measuring Spherical Aberration via Axial Intensity Scans We will use spherical aberration as an example to illustrate the utility of the axial scan profile. It is well known that the axial intensity of a lens free of spherical aberration has a symmetric axial intensity profile about paraxial (Reference 3) focus as is shown in Figure 3. However, it is not well known that the axial intensity pattern remains symmetric in the presence of spherical aberration.(Reference 3). The pattern is not the same shape as that for the zero aberration case, and the center of symmetry is no longer in the paraxial focal plane. However, the axial separation, d, between the plane of symmetry and the paraxial focal plane is directly relatable to the exit pupil spherical aberration coefficient W040 (in micrometers) present through the equation: [D](3) [D] Figure 3: Axial Intensity of Diffraction Limited System Figure 4 (a) shows an experimental axial intensity plot for a system with significant spherical aberration. The F-number of the system is F/10.3. The operating wavelength is 0.6328 micrometers. The separation between the plane of symmetry and the paraxial focal plane is 3.07 mm. (Note, paraxial focus is established by a separate axial intensity scan with a small aperture in the entrance pupil). Using Eq.4, we find that the amount of spherical aberration is 5.7 waves! Figure 4 (b) shows a theoretical plot with the same amount of spherical aberration. The two plots are virtually identical. A recent paper (Reference 4) also shows how axial intensity scans of star images with mixed Seidel aberrations can be used to identify and quantify those aberrations. [D] Figure 4: Axial Intensity where W 040 = 5.7 Waves (a) Experimental; (b) Theoretical. Courtesy Dr. Qian Gong 3.2 Lateral Irradiance Methods 3.2.1 CCD Arrays The magnified star image formed by the microscope can be focused on the detector chip of a CCD camera. A video frame-grabber tied into a PC can be used to acquire a frame of data for analysis. Hardcopy can be acquired via a video printer. Software packages are commercially available that will allow analysis of the data frame. Among the useful features are: a) power profiles across the star image; b) power centroid location; c) calculation of encircled energy; d) 2-D contour and 3-D power maps. The profiles can be compared to theoretical predictions like the one shown later in Figure 8(b). Not only is the size of the Airy Disc obtained, but also the relative power between the central peak and the rings. (Note: Small aberrations rob power from the core and shunt most of it into the first bright ring). In addition, an encircled energy calculation should show 84% of the energy within the core (for a circular unobscured entrance pupil). Potential problems with some CCD arrays are: dynamic range, linearity, and pixel uniformity. For example, the ratio of the peak power in the Airy Disc to the peak power in the first bright ring is about 68. Some CCDs do not have enough dynamic range. To see the first few rings means the central core is saturated. An unsaturated core means that the second bright ring, and sometimes the first, are buried in noise. Nonlinearity and pixel nonuniformity imply that profile shapes would be wrong. 3.2.2 Fiber Optic Probe The fiber probe scanner used in Sec.3.1 to obtain axial profiles can also be used to obtain lateral profiles. The fiber optic probe assembly is mounted on a motion controlled boom. This boom can be translated horizontally either manually or under computer control. In this way the probe can be scanned through the magnified star image. A transducer provides a voltage signal proportional to the linear position of the boom. The entire scanning micrometer eyepiece can be rotated and the axis of rotation is the optical axis of the microscope. This allows the observer, who views both the star image and the probe location through an eyepiece attached to the device, to select the orientation of the scan relative to the star image. The boom signal can be used to drive the x-axis of an xy-recorder while the signal from the PMT/radiometer can drive the y-axis. PMTs have significantly more dynamic range than CCDs, and excellent linearity. This will allow more accurate profiles through the star image. (A commercially available eyepiece of this type can be obtained from EG&G/Gamma Scientific. The unit is shown in Figure 5.) [D] Figure 5: Commercial Scanning Probe Eyepiece Figure 6 shows a combination of axial and radial scans for 5 waves of spherical aberration (Reference 5). The radial scans are made at various image planes of interest as defined by either geometric (e.g., minimum blur) or diffractive (e.g., Strehl) criteria. [D] Figure 6: Axial and Radial Irradiance Plots Using Scanning Fiber Optic Probe Eyepiece 4. Modulation Transfer Function Measurements 4.1 Connection Between MTF and Star Image In imaging theory, an object is considered to be made up of an array of sinusoidal patterns differing in spatial frequency, amplitude, and lateral positioning. It is akin to a Fourier series decomposition of a periodic waveform of arbitrary shape, e.g., a square wave. If an imaging system is presented with a pure linear sinusoidal amplitude object having unit modulation, then the image of this pattern (assume unit magnification for now) will also be sinusoidal of the same spatial frequency but with reduced modulation, and a possible decentering or shifting of the pattern as illustrated in Figure 7. [D] Figure 7: Physical Basis for MTF In Fourier transform theory (Reference 6 and 7), it can be shown that a point object contains all sinusoidal spatial frequencies at unit modulation at all spatial orientations and that the star image, the point spread function (PSF), is related to the MTF by a Fourier Transform, FT{ }: [D](4) If we scan the point spread function with a slit (as illustrated in Figure 8) we generate a line spread function (LSF). [D] Figure 8: Scanning the PSF with a Slit Sampling Aperature Mathematically this means we have integrated out the y dependency: [D](5) It can be shown that the Fourier transform of the line spread function yields an MTF profile through the origin: [D](6) 4.2 Scanning Slit One method of obtaining the star image line spread function is now described. The standard microscope eyepiece is replaced with a scanning micrometer eyepiece similar to that described in Sec. 3.1 and 3.2.2. However, in the plane of the magnified star image, the scanning probe is a slit. Note that the slit's width should be significantly smaller than the PSF diameter, and its length should be significantly longer. Light passing through the slit is coupled into an optical fiber and then into a fiber optic cable. The fiber optic cable is brought out through the side of the scanning micrometer eyepiece and coupled to the PMT/radiometer. The latter drives the y-axis of an xy-recorder while the x-axis position is controlled by the lateral position of the slit. For a rotationally symmetric PSF, slit scans along any diameter will generate identical MTFs, i.e., the MTF is also rotationally symmetric. On the other hand, MTFs for asymmetric PSFs will be direction dependent. PSF slit scans will have to be made along several different directions to build up a valid picture of the MTF. 4.3 Knife Edge Scan Instead of scanning the star image with a slit sampling aperture, suppose we scan across it with an opaque straight edge (knife edge). We collect the power (not blocked by the knife edge) and measure it with a radiometer. The signal output of the radiometer can be used to drive the y-axis of an xy-recorder. A linear transducer connected to the knife edge translation drives the x-axis. The resulting plot is called a knife edge distribution (KED). The steepness of the slope is a direct indication of image compactness. The LSF is the derivative of the KED in the scan direction. [D](7) This is illustrated in Figure 9. This also implies that the knife edge distribution and modulation transfer function are related via the line spread function as per Sec. 4.1. [D] Figure 9: The Line Spread Function is the Derivative of the Knife Edge Distribution 5. Measuring Wavefronts at the Star Image 5.1 Scanning Knife Edge The scanning knife edge technique is a clever enhancement of the classical Foucault knife edge test (References 8 and 9). The optical set-up is illustrated in Figure 10. A pair of orthogonally oriented knife edges is scanned across the image point (so that slope data can be acquired along two orthogonal directions). A lens behind the knife edge pair is used to image the pupil onto a CCD. [D] Figure 10: Wavefront Sensing via Double Knife Edge Scan The intensity is monitored at each pixel of the CCD. When a knife edge interacts with a quotrayquot from the conjugate pupil position, the intensity in the pixel changes. Data is accepted from that location when the intensity reaches 50% of its original value. This is also tied into the position of the knife edge at that moment (to yield the transverse ray aberration measurement). After both knife edges have passed through the image point, the data ensemble is passed to a computer program for analysis. Local slope data is fitted with a global Zernike polynomial (References 1 and 10) which can be related (via a large matrix inversion) to a Zernike description of the pupil optical path difference (OPD). 5.2 Point Diffraction Interferometer The point diffraction interferometer (PDI) (Reference 1) is a simple self-referencing interferometer. (It is a commercially available instrument built by Ealing Corp.) A physical description of the PDI is shown in Figure 11(a). It is a monolithic device consisting of two concentric circles (thin-film coated onto a thin transparent substrate). The fat annular region is semitransparent and acts like a neutral density filter. The small inner circle (pinhole) is a diffraction aperture and plays a spatial filtering role. PDI operation is illustrated in Figure 11(b). The aberrated wavefront is focused onto the PDI disc. Most of the beam passes through unhindered except for a reduction in intensity. The tiny part of the beam interacting with the pinhole is diffracted into a clean spherical wavefront, i.e., it has become the reference wavefront. Immediately on the far side of the PDI, interference takes place between the aberrated main beam and the reference beam. The operational F-number range of the commercial PDI is between F/2-F/11. However, at the extremum fringe contrast is down considerably. [D] Figure 11: (a) Construction of PDI; (b) Operational Principle Technical Rationale: All optical imaging systems used on spaceborne or space-related instruments should undergo an end-to-end systems check to validate performance. Star image testing is the primary means of conducting this validation process. It provides data pertinent to the pass/fail criteria associated with the optical imaging system. References: 1. J. Geary, Introduction to Optical Testing, Tutorial Text TT-15, SPIE Press,(1993). J. Geary and P. Peterson, quotSpherical Aberration: a Possible New Measurement Approach,quot Opt.Eng. 25, 2, (1986). V. Mahajan, Aberration Theory Made Simple, Tutorial Text TT-6, SPIE Press, (1991). Q. Gong and S. Hsu, quotAberration measurement using axial intensity,quot Opt.Eng. 33, 4, pp 1176-1186, (1994). P. Peterson and J. Geary, quotIntermediate spherical aberration,quot Opt.Eng. 25, 11, pp 1232-1240, (1986). J. Gaskill, Linear Systems, Fourier Transforms and Optics, John Wiley, (1978). J.Goodman, Introduction to Fourier Optics McGraw-Hill (1968). J. Geary, M. Yoo, P. Davila, A. Wirth, A. Jankevics, M. Ruda, R. Zielinski, and L. Petrilli, quotComparison of Wavefront Sensors,quot SPIE Proc. Vol. 1776, pp 58-72, (1992). D. Vanderberg, W. Humbei, and A. Wertheimer,quotQuantitative Evaluation of Optical Surfaces by Means of an Improved Foucault Test Approach,quot Opt.Eng. 32, 8, pp 1951-1954, (1993). J. Wyant and K. Creath, Applied Optics and Optical Engineering, Vol. 11, Chap. 1, ed. R. Shannon and J. Wyant, Academic Press (1992). Reliability Preferred Practices, Guideline No. GT-TE-2405, Star Image Metrology Part I: Visual Measurements Reliability Preferred Practices, Guideline No. GT-TE-2404, Optical Testing Guideline: Fizeau Interferometry. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/29/2000
721 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Design Considerations For Space Trusses |  | Aerospace structures and spacecraft are complex assemblies of structural components that are subjected to a variety of hazardous conditions. Failure to adhere to proven space truss reliability analysis practices could cause shortened mission life, impact mission success, premature termination of component or experiment operation, and in extreme circumstance, loss of mission and human life. All phases of space truss design process, from development, design, fabrication and all the way to installation in the spacecraft, must adhere to proven reliable design and safe practices. | Use the PSAM (Probabilistic Structural Analysis Methods) contained in the computer code NESSUS (Numerical Evaluation of Stochastic Structures Under Stress) to identify and quantify the reliability of space structures. | GRC | 01/31/1999 | This Lessons Learned is based on Reliability Practice Number PD-ED-1242; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: This practice can be used to determine an optimum truss configuration (e.g. minimum number of members) for a given loading condition and specified reliability. Probabilistic Structural Analysis Methods (PSAM) provides a formal and systematic way to evaluate structural performance reliability or risk at minimal time and low cost. Implementation Method: The purpose of this application is to probabilistically evaluate a three-dimensional, three-bay, space cantilever truss by using the computer code NESSUS (Numerical Evaluation of Stochastic Structures under Stress). Using PSAM will enable design engineers to identify and quantify the sensitivities associated with uncertainties in primitive variables (structural, material and load parameters) describing the truss. The primitive variables for a given space truss such as stiffness parameters, strength parameters, spatial truss geometry, and applied loads or moments will vary continuously due to changes in the space environment. Each of these primitive variables distribution is characterized in terms of one of several available probability distributions, such as the Weibull, exponential, normal, log-normal, etc. The cumulative distribution functions for the response functions considered and sensitivities associated with the primitive variables for given response are investigated. These distributions have significant impact on the separation/range of the response variables such as nodal displacements, eigen-values, member forces, vibration frequencies, etc. These sensitivities help in determining the dominating primitive variables for a particular response. Program Capability and Description The NESSUS code consists of three major modules: (1) NESSUS/PRE (pre-processor) module is used to obtain the characteristic of a partially correlated Gaussian field in terms of a set of uncorrelated random vectors. (2) NESSUS/FEM (Finite Element Methods) module is a finite element analysis code that can generate perturbed solutions about a deterministic state. It contains an efficient perturbation technique such that the perturbation of each variable is done rapidly. Each perturbation corresponds to a prescribed deviation from the deterministic model. (3) NESSUS/FPI (Fast Probability Integration) module contains several advanced reliability methods including Monte-Carlo simulation. Since NESSUS/PFEM combined the NESSUS/FEM and NESSUS/FPI modules into a single computer program, the entire probabilistic finite element analysis including perturbations of the primitive variables can be performed in a single execution step. The fast probability integration (FPI) techniques are one or several orders of magnitude more efficient than the Monte-Carlo simulation methods. FPI module extracts the database of perturbed solutions from NESSUS/FEM to calculate the probability distribution functions of the response variables. In general, the primitive variables are specified with their mean values (m), standard deviation (s), and the type of distribution. Note: Each module can be operated independently. Probabilistic Finite Element Analysis In general, the finite element equation for motion is written as: [M] {ü} + [C] {m} + [K] {u} = F(t) Equation (1) Where: [M] denotes mass matrix. [C] denotes damping matrix. [K] denotes the stiffness matrix {ü} denotes acceleration vector. {m} denotes velocity vector. {u} denotes displacement vector. Note: These matrices are calculated probabilistically in the NESSUS code. The forcing function vector, {F(t)}, is time dependent at each node. In this practice, the static case is considered by setting the mass and damping matrices to zero and considering the forcing function being independent of time in equation (1) such that [K] {u} = {F} Equation (2) Furthermore, by just setting the damping matrix to zero, eigenvalue analysis can be accomplished by using [[K] - w2 [M]] {u} = 0 Equation (3) where w denote eigenvalues and {u} are the corresponding eigenvectors. Finite Element Model A three-dimensional, three-bay cantilever truss is computationally simulated using a linear isoparametric beam element based on the Timoshenko beam formulation. The element is idealized as a two-noded line segment in three-dimensional space. The cantilever truss is assumed to be made from 44 hollow circular tube members (see Fig. 1). The tubes are made up of wrought Aluminum alloy with modulus of elasticity (E) equal to 10 Mpsi. The outer and inner radii (ro and ri) of the tube are 0.5 and 0.4375 in., respectively. All 6 degrees-of -freedom are restrained at the fixed end (left side) nodes. The truss is analyzed twice, once using beam elements and then using pseudo-truss elements. The beam element is converted into a pseudo-truss element by suppressing the effective shear areas in the principal planes (Axx and Ayy), the two principal moments of inertias for the tube cross-section, (Ixx and Iyy), and torsional constant, J. In the case of truss elements, 3 rotational degrees of freedom at each node and 3 translational degrees of freedom at support nodes are restrained. Each bay of the truss is 5 ft wide, 8 ft long, and 6 ft high ( see Fig. 1 ). The overall length of the truss is 24 ft. Six vertical and two longitudinal loads are applied. Twisting moments are applied at the truss-end top nodes for truss elements. The directions of the forces and moments are shown in Figure 1 and the mean values are given in Table I. Probabilistic Model The following primitive variables are considered in perturbation analysis: ( 1 ) Nodal Coordinates ( X, Y, Z ) ( 2 ) Modulus of elasticity ( E ) ( 3 ) Outer radius of the tube (ro) ( 4 ) Inner radius of the tube (ri) ( 5 ) Vertical loads ( V ) ( 6 ) Longitudinal loads ( H ) ( 7 ) Truss-end moments ( M ) ( 8 ) Truss-end coupling forces ( P ) It is possible that the above primitive design variables will vary continuously and simultaneously due to extreme changes in the environment when trusses are used in upper Earth orbit for space station type structures. The normal distribution is used to represent the uncertainties in E, ro, ri, and X, Y, Z coordinates. [D] The applied loads, moments and coupling forces are selected to represent anticipated loading conditions for a typical space truss. These are represented by log-normal distributions. Initially, NESSUS/FEM module is used to take into consideration the mean value of these primitive variables. In the subsequent probabilistic analysis each primitive variable is perturbed equidistant from the mean value. However, each variable is perturbed independently and by a different amount. Usually, the perturbed value of the design variable is taken as a certain fraction of the standard deviation at either side of the mean value. Finally, the NESSUS/FPI module extracts response variable values (one deterministic and two times the number of primitive variables) to calculate a probability distribution function of the response variable considered. The mean, distribution type and percentage variation for different primitive variable are given in Table I. [D] Data Analysis The three-dimensional, three-bay cantilever truss is probabilistically analyzed and the cumulative probability distributions for the truss end displacements, member forces and vibration frequencies are plotted. The sensitivities of the primitive variables on the scatter in the truss structural responses (truss free end displacements, member axial forces and vibration frequencies) are quantified in Table II. Please refer to the reference articles of this practice for other information/figures such as the probabilistic displacement of the truss free end nodes (top and bottom) in X, Y, and Z directions using the truss element. The cumulative distribution functions of frequencies of modes 1 and 2 using truss elements are plotted (see sample Figure 2, others please refer to the reference articles). Please refer to the reference articles for other valuable information such as data plots for the truss modelled with beam elements. It is important to note from Table II that the cross-sectional area (primitive variables ro and ri) has a significant impact on the probabilistic distribution of the vibration frequencies. For additional result formats please refer to reference 1. [D] [D] Technical Rationale: Traditional deterministic methods applied to the analysis of space truss design only consider applied loads for given operating condition. To account for uncertainties in assumptions of loading and material strength, load factors and safety factors are applied to assure the final design will satisfy design specifications. This traditional approach to stress analysis does not formally address the natural uncertainties of primitive variables (fundamental parameters describing the structural problem) such as the uncertainties of loading and material strength. Numerous uncertainties associated with truss structures in space environments require a quantitative and systematic method to ascertain that the structural response will be within the acceptable limits during the life of the structure. Probabilistic structural analysis provides a formal way to properly account for all these uncertainties. Currently available software tools do not easily allow determination of any local instability in any of the internal members of the truss during probabilistic analysis. Therefore, NASA Lewis Research Center developed PSAM, which provides a formal and systematic way to reliably evaluate structural performance and durability. PSAM takes into account the uncertainty of primitive variables and will yield a stable and optimum configuration for given load conditions. This probabilistic approach also takes into account the uncertainties of primitive variables in the space environment. References Pai, S.S., quotProbabilistic Structural Analysis of a Truss Typical for Space Stationquot, NASA Technical Memorandum 103277, 1990. Pai, S.S. and Chamis, C.C., quotProbabilistic Progressive Buckling of Trussesquot, NASA Technical Memorandum 105162, 1991. Research & Technology - 1992, NASA LeRC TM 105924, 1992. Pai, S.S. and Chamis, C.C., quotProbabilistic Structural Analysis of Adaptive/Smart/Intelligent Space Structuresquot, NASA Technical Memorandum 105408, 1991. Pai, S.S. and Chamis, C.C., quotProbabilistic Assessment of Space Trusses Subjected to Combined Mechanical and Thermal Loadsquot, NASA Technical Memorandum 105429, 1992. NOTE: Please refer to the attached Software Release Request form for information on how to obtain the NESSUS software. SOFTWARE RELEASE REQUEST | This practice has been used on SSME, Space Station. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/28/2000
719 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Short Circuit Testing for Nickel/Hydrogen Battery Cells |  | Failure to adhere to proven Ni/H2 battery test practices could cause shortened mission life, impact mission success, premature termination of component or experiment operation, and in extreme circumstance, loss of mission or human life. All phases of battery processes, from development, design, fabrication and all the way to installation in the spacecraft, must adhere to the proven reliable design and safe battery practices. | Use Short-Circuit testing method or response characteristics on Nickel/Hydrogen (Ni/H2) battery to characterize the battery impedance. This data is necessary for designing power processing equipment and electric power fault protection system. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice Number PT-TE-1430 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Ni/H2 battery technology is gaining wide acceptance as an energy storage system for use in space applications because of its reliability, weight and long cycle expectancy at deep depths-of-discharge (DOD). When a charged Ni/H2 battery is short-circuited, its short circuit current data can be used to calculate the internal resistance of the cells for the purpose of determining the overall characteristics of the energy storage system. Also, by examining the cell impedance only, a Ni/H2 battery simulation utilizing low cost lead-acid cells can be developed. Implementation Method: Ni/H2 batteries will be used as the secondary source of electric power systems for many space applications, such as a space station. Most long term spaceflight will be orbiting in Low-Earth-Orbit (LEO) once every 90 minutes, which equals to approximately 6000 cycles per year and during each cycle there will be an eclipse period of approximately 30 minutes. During the eclipse period, electric power must be maintained to support many on going activities, such as life support, communication and experiments. A typical Ni/H2 battery will contain 76 Ni/H2 cells connected in series to produce a nominal battery voltage of 112 volts DC. Each cell has a capacity of 81 Amp-hours and will operate at nominal 35 % DOD. Based on the short-circuit testing conducted here at LeRC, Ni/H2 battery is inductive in nature (no large current spike) and this was later confirmed by analysis of its internal cell structure. A 76 cell battery was not available, therefore, characteristics of a single cell and two cells in series were used to extrapolate the overall characteristics of the entire 76-cell Ni/H2 battery. Figure 1 shows the external configuration of a typical Nickel/Hydrogen cell. [D] Figure 1: Typical Nickel/Hydrogen Aerospace Cell The test setup for the single cell short circuit test is shown in Figure 2. For safety reasons, the instrumentation and test personnel were separated from the short circuit test stand by means of a separate room. The test equipment located in the control room consisted of: a battery charge/discharge controller to monitor and control state of charge, the relay control panel to control relay activation, and a four channel Digital Oscilloscope to record current and voltage transients. In the energy storage room the Ni/H2 cell was mounted on a cold plate and contained in a sealed chamber which was purged with Gaseous Nitrogen (GN2) in case of hydrogen out-gassing. The cell was connected to a 400 Amp relay by a pair of 1/0 welding cables, keeping cable length and inductance to a minimum. Current measurements were obtained using a Pearson current transformer (to capture quick alternating current (AC) transients) and a Hall effect current sensor. Initial tests showed that the Hall effect current probe had ample bandwidth to capture the current transient, and the Pearson current transformer was removed. [D] Figure 2: Ni/H 2 Cell Short Circuit Test Block Diagram The test setup for the two-cell short circuit test differs only in the configuration of the cells. Instead of a single cell, two cells are connected in series and both are placed inside the test chamber. TEST DESCRIPTION: The cell(s) are setup as shown in Fig. 2, and the cell(s) are either charged to 100% state-of-charge (SOC) or discharged to a 65% SOC. The digital oscilloscope is set to trigger on the current rise and the relay is closed by the operator. The relay activation switch automatically de-energizes the relay after only 175 milliseconds of short circuit current. The test cells never lost any capacity and were not subjected to any thermal stress. The following are brief descriptions of the seven test measurements: Short Circuit Current Response of Ni/H2 Cell (100% SOC) with the Pearson Current Transformer. The result shows a peak current of 746 A. During the short, it shows a cell voltage drop from 1.477 to 0.692 Vdc and a relay voltage drop of 0.339 Vdc. Short Circuit Current Response of Ni/H2 Cell (100% SOC) with the Hall Effect Current Sensor. The result shows a peak current of 775 A. During the short, it shows a cell voltage drop from 1.479 to 0.691 Vdc and a relay voltage drop of 0.329 Vdc. Short Circuit of Ni/H2 Cell (re-conditioned 100% SOC). The cell was fully discharged then fully charged again. This re-conditioning method has shown to improve the ampere capacity of the cell(s). However, little change in short circuit current (Isc) was measured. Same test as NO.3, but the time base was reduced to examine the start-up transient and switch bounce effect It has shown a good transient after the initial bounce. Short Circuit of Ni/H2 Cell (re-conditioned 65% SOC). After the cell had been discharged to 35% DOD, results were lower cell voltage (1.295 Vdc) and consequently lower Isc of 659 A. Short Circuit of two series Ni/H2 Cells (100% SOC). The Hall effect current of 987 A peak falling to 950 A within 171 ms. During the short, total cell voltage dropped from 2.967 to 0.795 Vdc. Short Circuit of two series Ni/H2 Cells (65% SOC). The Hall effect current of 856 A peak falling to 832 A within 171 ms. During the short, total cell voltage dropped from 2.595 to 0.685 Vdc. Test Result Comparison Analyzed test results between single and duel cell test measurements. The short circuit current of a cell is not increasing at the same rate as the voltage from a single cell (test no. 2) to a double cell (test no. 6). The dual cell test had the NiH2 cells connected in series. The cell voltages would add up to be about double the voltage of a single cell (2.967 V vs. 1.479 V). However, in a series connection, the short circuit current is not expected to double. The short circuit current is simply a function of the cell voltage and the resistance in the short (Isc=Voc/R). The resistance, R, is comprised of the internal cell resistance (Rb) and the external circuit resistance, Rext (cable and relay contacts). In an ideal test Rext= 0 the short circuit current should not change since both the voltage and the resistance is doubled when the cells are connected in series. However, since the external circuitry adds resistance, the short circuit current will increase as the external resistance becomes a smaller part of the total resistance. For example: analysis of the single cell data shows that the external circuit had 0.87 mOhms of resistance and that the internal cell resistance was about 1.06 mOhms. Therefore, the short circuit current should have about 1.479 V/1.93 mOhms = 766 A. The test results were 775 A. Analysis of the two cell data goes along the same line. Assuming that both the voltage and the internal resistance were doubled, adding in the external resistance gives the expected short circuit current of: Isc=2.967 V/(1.06 mOhms * 2 +0.87 mOhms)= 2.967 V/2.99 mOhms = 992 A. The Actual test result was 987 A. In the same manner the voltage across the cell(s) during the short circuit is a function of the external resistance and the short circuit current (Vsc=Rext*Isc). Since Isc does not double and Rext remains constant, then Vsc is not expected to double. It will, however, increase as Isc increases. Note: Figure 3 shows a data plot of test NO. 7. Please refer to reference 1 for additional data plots of the other tests. [D] Figure 3: Plot No 7, Short Circuit Response of Two Series NI/h 2 Cells at 65% SOC Data Analysis The internal impedance of the Ni/H2 cell was calculated from the data presented above. Using the single cell and multiple cell tests, an internal resistance/inductance was calculated. The data is used to extrapolate the short circuit current of the entire 76-cell battery. The equivalent Ni/H2 single and dual cell(s) circuits are shown in Figure 4 and 5 respectively. All of the resistive components' values are derived by using direct-current (DC) circuit analysis. The internal cell inductance is calculated by simplifying the circuit in Figure 4 and 5 to a voltage source switched into a series resistor-inductor (RL) circuit. [D] Figure 4: Single Cell Equivalent Circuit Model [D] Figure 5: Dual Cell Equivalent Circuit Model Single Cell DC Analysis Measured values: Open circuit voltage (Voc), short circuit voltage (Vsc), battery voltage (Vbat), short circuit current (Isc), switch/relay voltage (Vsw). Cable values: Cable resistance #1 (Rc1), cable resistance #2 (Rc2). Calculated component values: Battery resistance (Rb), switch/relay contact resistance (Rsw). >From handbook or manufacturer specifications, look up cable resistance of 1/0 copper stranded welding cable with .09 mOhm/ft. Rc1= 2 ft. = 0.18 mOhms, Rc2 = 3 ft. = 0.27 mOhms, therefore total cable resistance (Rct) equals 0.45 mOhms. Relay resistance quotONquot calculation: Rsw= Vsw/Isc An average value of Rsw was obtained: Average Rsw = 0.42 mOhm Battery resistance calculations: Voc represents the battery cell's ideal voltage source. Method #1: Isc = Voc / (Rb + Rc1 + Rc2 + Rsw ), therefore, Rb = (Voc / Isc ) - Rc1 - Rc2 - Rsw Method #2: Isc = (Voc - Vsc ) / Rb , therefore, Rb = (Voc - Vsc ) / Isc Note: Please refer to reference 1 for the detailed analysis of all the components values and calculation. Technical Rationale: ASA Lewis Research Center has conducted and will continue to support future research on Ni/H2 cell battery technology for commercial and aerospace applications. From the current test equipment setup, and with the data obtained through the testing methods of a single cell and two cells in series, the internal cell characteristic impedance has been determined to be of approximately 1.0 mOhm and an internal inductance of approximately 0.55 microhenrys. Based on these test results, the short circuit current depends on the voltage and the resistance in the short. Knowing that the Ni/H2 cell internal resistance was about 1.06 mOhms, the ultimate short circuit current could easily be calculated. Therefore a short worst-case short circuit current of 1753 Amps was predicted for a long term spaceflight, 76 Ni/H2 cell battery design. References: Button, Rob; Pease, Gary; Birchenough, Art; Petrik, John; quotNi/H2 Cell Short Circuit Testquot, Electrical Systems Division, NASA LeRC, Preliminary Test Report # 14, April 20, 1992. Button, Robert M., quotNi/H2 Short Circuit Test of an Abnormal Cellquot, Electrical Systems Division, NASA LeRC, PIR #243, May 22, 1990. Research & Technology - 1992, NASA LeRC TM 105924, 1992. Dunlop, J. D.; NASA Handbook for Nickel-Hydrogen Batteries, Preliminary draft, Goddard Space Flight Center, May 1992. Gates Energy Products, Sealed Rechargeable Batteries Application Manual, 1989 quotBattery Selection Practice For Aerospace Power Systemsquot, Reliability Preferred Practice PD-ED-1221 quotDesign and Analysis of Electronic Circuits for Worst Case Environments and Part Variationsquot, Reliability Preferred Practice PD-ED-1212 | This practice has been used on NTS-2, INTELSAT V, and Hubble Space Telescope | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/28/2000
891 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Preventive Maintenance Strategies Using Reliability Centered Maintenance (RCM) |  | RCM is the best approach to developing the preventive maintenance program for a new system. It provides a step-by-step approach, prioritizes preventive maintenance tasks, and optimizes the repair cost. | Institute a Preventive Maintenance Program based upon current reliability-centered maintenance (RCM) techniques. | JSC | 11/30/1994 | This Lesson Learned is based on Maintainability Technique number PM-4 from NASA Technical Memorandum 4628, Recommended Techniques for Effective Maintainability. In the past, preventive maintenance was performed without any guidance or regard for safety or cost concerns, as long as systems performed their functions. The primary reason for the development of RCM was to implement a preventive maintenance strategy that could adequately address system availability and safety at the lowest possible cost. The RCM process answers and directs preventive maintenance decisions as to the what, where, and when types of questions. Introduction In the past, product development and manufacturing engineering dominated the technical disciplines in the U.S. industrial community with operations and maintenance (O&M) taking a lower priority to corporate success strategies. This priority has dramatically shifted to the point that O&M is now on a par with the development and manufacturing disciplines. Concerns about maintenance and logistics costs caused this shift in priority. A valid question is how to get maximum use of resources committed to the preventive maintenance program. This technique discusses preventive maintenance and defines RCM as part of an effective preventive maintenance program. Some cost-benefit considerations realized through the use of RCM are also illustrated. Introduction to Preventive Maintenance The majority of systems have long been operating in the corrective maintenance mode. Corrective maintenance is the performance of and almost total commitment of resources to unplanned or unexpected maintenance tasks. Preventive maintenance, however, is the pre-planning of inspection and/or servicing tasks. Corrective approaches restore the functional capabilities of failed or malfunctioning equipment or systems. However, corrective maintenance is more costly than preventive maintenance because of the unplanned interruptions of operations, idle time waiting for spare parts, and haphazard troubleshooting for failure causes. Preventive Maintenance Program In general, when creating a new or upgrading an existing preventive maintenance program, two items of essential information are required: (1) identification of what preventive maintenance tasks are to be performed and (2) when each task should be performed (see Figure 1). [D] Whatever method is used to determine what or if a task is to be performed results in a time-directed, condition-directed, or failure-finding task selection or a run-to-failure decision (as defined above). The next step is to incorporate the preventive maintenance program into the existing operations infrastructure and to ensure that it is implemented in everyday operations. Moreover, a series of questions must be answered before any program can be implemented. Typically, such questions might include the following: Are new procedures or modifications to existing procedures required? Are all the standard materials (tools, filters, etc.) available? Is any special tooling or instrumentation required? Are an appropriate number of people available to conduct the program? Are any capital investments required? Will the new/upgraded program affect the quantity of on-hand spares required? How long will it take to incorporate the new/upgraded program into the maintenance management information system (MMIS)? Is the existing MMIS capable of accepting the entire new/upgraded program (e.g., tracking time sequenced data in condition-directed tasks)? If full shutdown must be periodically planned, do the tasks and task intervals lend themselves to such a schedule? Do new tasks require a cycle that is a common denominator with other existing task intervals? Preventive Maintenance Program Elements Figure 1 is a simplified illustration of a preventive maintenance program development. Many supporting management and technical disciplines are involved in the development of the ideal preventive maintenance program and task packaging, and they are important in supporting the RCM concept that is discussed later in this technique. The important supporting technologies used in the development process are described below. A product malfunction or failure can present a significant learning opportunity in that much technical knowledge can be gained from comprehensive failure reporting, root cause analysis, and corrective action feedback programs. Without such programs, it is virtually impossible to establish proper corrective action or to intelligently decide if any preventive maintenance action is possible. A good failure reporting system is vital to the quotretain or increase mean-time between failuresquot portion of an availability improvement program. To prudently employ condition-directed tasks requires an entire diagnostic technology that is still evolving with new techniques and applications. The technology is dedicated to following, understanding, and contributing to the area generally referred to as quotpredictive maintenance technology.quot Some of the tools that comprise predictive maintenance technology are as follows: Vibration, pulse, and spike energy measurement. Acoustic leak detection. Thermal imaging. Fiber optic inspection. Trace element sensing. Debris analysis. Lubricant analysis. Stress/strain/torque measurement. Nonintrusive flow measurement. Microprocessors with expert system software. Preventive Maintenance Task Packaging This task consists of three major elements: Task Specification. The task specification provides complete technical definition and direction of specific requirements to the implementing maintenance organization. This document, which is the key transition from the ideal to the real world, either (1) details the data measurement and evaluation requirements for a condition-directed task along with the limiting acceptance criteria or (2) specifies critical requirements that must be met in a time-directed overhaul task. Procedure. The procedure is a basic document that guides the execution of a preventive maintenance task. The document may be a one page instruction for a simple task or complex details on precisely how the preventive maintenance task is to be achieved. Logistics. The logistics entail a variety of administrative and production support activities. Typical logistic considerations include tooling, spare parts, vendor support, training, documents and drawings, make/buy decisions, test equipment, scheduling, etc. Clearly, these considerations closely interplay with both the task specification and procedure and constitute a major portion of maintenance planning. In summary, a preventive maintenance program can be created or upgraded by implementing the ideas given above. With the support of key technologies, it will produce the quotwhat taskquot and quotwhen donequot information. Reliability Centered Maintenance (RCM) As conveyed above, the objective of most of the current preventive maintenance practices is to preserve equipment operation. Until recently, this has resulted in little, if any, consideration as to why certain preventive maintenance actions and are taken and what priority should be assigned to the expenditure of preventive maintenance resources. Almost without fail, maintenance planning starts with the equipment and seeks to specify as quickly as possible those components necessary to keep it running. RCM is not just another approach to this repetitive process. The basic RCM concept is really quite simple and might be characterized as organized engineering common sense. The features that define and characterize RCM and set it apart from any other preventive maintenance planning processes in use today are described below. Preserves System Function. Unlike the ingrained notion that preventive maintenance is performed to preserve equipment operation, the primary objective of RCM is to preserve system function. Although equipment preservation leads ultimately to system preservation, it is not the initial step in the RCM process. In RCM, the expected output is known, and preserving that output or function is the primary task. This feature enables systematic decisions in later stages of the process as to just what equipment relates to that function and does not assume a priori that quotevery item of equipment is equally important,quot a tendency that seems to pervade the current preventive maintenance approach. Identifies Failure Modes That Can Produce Unwanted Functional Failures. After preserving system function, avoiding loss of function or functional failure is the next item of RCM consideration. Functional failures take many forms and may occur in various stages, all of which must be considered. The loss of fluid boundary integrity is a functional failure that illustrates this point. A system loss of fluid can be caused by (1) a minor leak that may be qualitatively defined as a drip; (2) a leak defined as a design basis leak (any loss beyond a certain gallon per minute value will produce a negative effect on system function); or (3) a total loss of boundary integrity, which can be defined as a catastrophic loss of fluid and loss of function. In this example, a single function could lead to three distinct functional failures. The key to the failure identification feature is to identify the specific failure modes in specific components that can potentially produce those unwanted functional failures. Enables Prioritization of Failure Modes. In preserving system function, RCM provides a systematic approach to deciding what priority must be assigned to budget and resource allocations. Since functional failures and their related failure modes are as diverse as the functions and components they affect, the prioritization of failure modes is essential. Allows Preventive Maintenance Tasks To Be Judged As To Applicability and Effectiveness. The features described above help in developing a very specific roadmap to the where and why, of the maintenance task and the priority that should be assigned to it. Each potential task must then be judged as to (1) its applicability (i.e., will it prevent or mitigate a failure, detect the onset of a failure, or discover a hidden failure) and (2) its effectiveness (i.e., does it justify the spending of resources to do it). Generally, if more than one candidate task is judged to be applicable and effective, the least expensive task will be selected. If a task fails either the applicability or effectiveness test, a run-to failure decision must be made. Cost-Benefit Considerations. The primary force behind the invention of RCM was the need to develop a preventive maintenance strategy that could adequately address system availability and safety without creating a totally impractical cost requirement. Figure 2 illustrates the success of keeping commercial aircraft maintenance cost per flight hour constant from the late 1960's to the early 1980's. [D] Table 1 presents another way to view the impact of RCM on the commercial aircraft world. [D] Two significant points can be observed from these data: (1) the dramatic shift in the reduction of costly component overhauls during the pre-1964 and post-1960/1987 periods; and (2) the constancy of the condition-directed task structure. The reduction in expensive component overhauls, brought about by run-to-failure decisions, was made possible by a design philosophy that included double and triple structural design redundancy in the flight-critical functions. RCM was used to take advantage of these structural design features when preventive maintenance was critical and the run-to-failure decision was appropriate. The constancy of the condition-directed task structure is attributed to the fact that the commercial aircraft industry was one of the early users of performance and diagnostic monitoring as a preventive maintenance tool. It has continued to successfully apply this practice throughout the generation of the newer jet aircraft. The results indicated in figure 2 and table 1 have led to a growing interest in other such areas as nuclear power generation and electric utility plants. The obvious reasons for this growing interest are (1) control and reduction of O&M costs and (2) increase in plant availability. All of this indicates that the cost-reduction benefits of RCM that dramatically impacted commercial aviation offer similar potential dramatic payoffs in other areas in which complex plants and systems are routinely operated. Conclusion RCM is a logical approach to preventive maintenance which does not rely on any heuristic processes. RCM helps in making direct and deliberate preventive maintenance decisions that were not previously possible. It can also be used as the methodology for defining preventive maintenance for a such new systems as the Space Station. Virtually every organization that has conducted an RCM program has recognized the value of the system analysis process as a training ground for system engineers. In addition, the failure scenarios developed in RCM analyses may be used beneficially as simulator inputs to plant transient or upset conditions in order to anticipate such occurrences in the future. References Annual Reliability and Maintainability Symposium, 1991 Proceedings. Matteson, Thomas D., quotThe Origin of Reliability-Centered Maintenance,quot Proceedings of the Sixth International Maintenance Conference, Institute of Industrial Engineers, October 1989. quotReliability-Centered Maintenance for Aircraft Engines and Equipment,quot MIL-STD-1843, February 8, 1985. quotRCM Cost-Benefits Evaluation,quot Electric Power Research Institute, Interim EPRI Report, January 1992. | This practice has been used on Space Shuttle Orbiter. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/20/2000
717 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Guideline for Use of Fizeau Interferometer in Optical Testing |  | If optics destined for spaceborne or space-related instruments are not tested, or are improperly tested, then the consequences could be the ultimate failure of the mission in-whole or in-part. The Hubble Space Telescope primary mirror is a case in point. | The Fizeau interferometer is the most commonly used interferometer for testing optical components and systems used aboard spaceborne or space-related instrumentation. This guideline provides information on the proper use of this instrument. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GT-TE-2404 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The Fizeau interferometer is used to measure the quality of optical components and systems. It provides a guide for the manufacturing of components, an aid for alignment, and a validation of system performance. Implementation Method: Description of Fizeau Interferometer The basic layout of a Fizeau interferometer is shown in Figure 1 (Reference 1.). A laser source is spatially filtered via a microscope objective and a pinhole. This pinhole is located at the focal point of a collimating lens. Between the pinhole and lens is a beam-splitter. The collimated beam encounters a slightly wedged glass plate. This is the heart of the interferometer. The surface adjacent to the collimating lens is of good optical quality. However, the next surface is of exceptional optical quality, l/20 peak to valley (PV) or better. This is the reference surface and part of the collimated beam is reflected by this surface. Part of the collimated beam continues on to interrogate the optic being tested. The return beam contains information on aberration introduced by the test optic. The two wavefronts recombine inside the interferometer. The beam-splitter diverts the combined beams toward a recording medium, either film or a TV (CCD or vidicon). An intermediate lens together with the collimating lens forms an image of the test surface onto the recording plane. An observer will see a sharp image of the test surface with an interference (or fringe) pattern running through it. [D] Application of Fizeau Interferometer 1. Testing a Flat Suppose the test object is a plane glass surface whose quality (flatness) we wish to inspect. We must first align the test surface to the interferometer. Most commercial Fizeau interferometers have an quotalign mode.quot This requires the user to center a bright dot (the reflected return) on a crosshair on some viewing screen. Suppose the test surface has a depression in it as illustrated in Figure 2. The flat wavefront from the interferometer is incident on the test surface and reflected back into the interferometer. Note that the reflected portion shown in Figure 2 has picked up twice the surface error inherent in the test surface. This aberrated wavefront returns through the reference plate to combine with the reflected reference. [D] Wherever two coherent wavefronts overlap they interfere with each other. The equation describing interference (Reference 2) is as follows: [D] To obtain good high contrast fringes requires that the reflection off the reference and off the test piece must be equivalent in intensity. Maximum fringe contrast occurs when I1 = I2 . For example, a bare glass test surface reflects 4%. To maximize fringe contrast the reference surface must also reflect 4%. If a 4% reference surface is used to test a mirror (with 90% plus reflectivity), then a very thin beam-splitter (e.g., a pellicle) can be used to reduce the intensity from the test optic. Alternatively, a reference surface having a much higher reflectivity can be used to improve fringe contrast. In the latter case, one will notice that the dark fringes become much thinner, like sharp pencil lines. A sample interferogram of a supposed quotflatquot mirror is shown in Figure 3. If the mirror were flat, equally spaced straight line fringes should be observed (depending on the relative tilt between the reference surface and the test surface). Obviously, the mirror is not very flat at all. Each fringe is a height contour as in a topographical map. (The metric or unit of measure in most Fizeau interferometers is the wavelength of the source. For example, the helium near laser wavelength is 0.6328 microns.) The height difference between each contour or fringe is 1 wave. If knowledge of the surface error or its departure from flatness is desired, we must interpret these fringes as representing half-wave contours! [D] In addition we must know whether the pattern seen in Figure 3 is a hill or a valley on the mirror surface. This can be determined by placing your finger on the front of the reference surface metal support ring (Figure 1) and pressing lightly toward the interferometer housing. If the fringe patterns collapse or contract, the pattern represents a hill or bump. If they expand, the pattern represents a valley. 2. Testing a Lens The setup for testing a lens is illustrated in Figure 4. The lens is carefully aligned to the Fizeau beam. The beam is focused by the lens to an image point. To return the beam back to the interferometer another auxiliary reference surface is needed. In this example a small concave spherical mirror is used. This sphere should be mounted so that X,Y, and Z translation degrees of freedom are available. The center of curvature of the sphere is then made coincident with the focal point of the lens. (Be careful–make sure that the focussed beam is not on the surface of the small retro sphere). The beam is reflected by the reference sphere and returned through the system. [D] The interferogram that is initially seen is likely to be an off-center bull's eye pattern. This means that the reference sphere's center of curvature is not axially coincident with the lens focal point. Use the tip and tilt adjustments on the Fizeau reference surface to center the bull's eye as shown in Figure 5(a), then use the axial translation on the concave sphere to move the interferogram into a best null condition (i.e., minimizing the number of fringes seen over the interferogram), Figure 5(b). Now use the adjustments on the reference flat to introduce tilt fringes as shown in Figure 5(c). It should be noted that the test system has significant spherical aberration. [D] An alternate setup for testing a lens is shown in Figure 6. Here the Fizeau reference surface is a sphere. It is a specially designed positive power lens where rays emerging from the last surface of the lens are normal to that surface. The test lens is aligned to the test beam and oriented so its rear focal point is coincident with the transmission spheres focal point. The beam emerges from the lens as collimated light. A flat auxiliary referencesurface is needed to retro-reflect the test beam back to the interferometer. [D] We note that transmission spheres come in a variety of F-numbers. Since your test lens has a certain F-number, pick a transmission sphere whose F-number provides a beam that either fills or overfills the test lens. Never pick a transmission sphere that underfills because then you are not testing the lens over its full aperture. Aberration content will appear lower than it actually is. Configurations for testing a wide variety of other systems are illustrated in Figure 7. [D] 3. Retrace Error The purpose of the reference sphere in Figure 4 is to return the incoming ray back upon itself so that it follows the same path on the second pass as it did on the first pass. This occurs exactly only when the incoming beam happens to be perfect, i.e. exhibits a spherical wavefront. As aberration accumulates on the first pass through the test system, the match to the reference sphere becomes less perfect. Path deviations appear on the return ray, which is now no longer coincident with the first pass ray. The optical path difference picked up by the second pass ray is not the same as the first pass ray. This is retrace error (also called ray-mapping error) (References 1, 3 and 4). As a consequence, it is no longer true that we can simply divide the results by two to obtain the single pass wavefront aberration from double pass fringe data. There are some visual clues to indicate if retrace error is significant. First, with the room darkened, check to see that the beam diameter of the light returning through the test optic on the second-pass is the same as that for the first pass after setting the null-fringe. Second, examine the irradiance distribution of this second-pass beam at the test optic. If the second-pass beam overfills or underfills the test optic aperture, and/or the intensity distribution is nonuniform, then retrace error is significant in the test setup. To minimize the effect of retrace error, a different retro optic is usually needed. If retrace error were significant in the case illustrated in Figure 4, then a longer radius of curvature retro sphere is needed and it should be convex instead of concave. This is shown in Figure 8. The longer radius convex surface reduces the angular disparity between the incident and reflected rays. It also reduces the lateral offset between the first and second pass rays at surfaces in the test optic. [D] 4. Collecting and Handling Data It is not the purpose of this guideline to describe methods used to analyze interferograms. That deserves a guideline of its own. However, we will describe the various data collection schemes and how they interface with the analysis software. There are basically three options available to the user: 1) digitizing tablet, 2) automatic fringe following; 3) uniform grid phase measuring. The simplest and least expensive means of selecting and inputting data to an analysis code is via a digitizing tablet. A hard copy of the interferogram is placed on the tablet. The user interfaces with the tablet (and the fringe analysis code) with a digitizing pen or mouse. The code first asks the user to define the pupil. Next, data points for each fringe are entered in proper sequence from low to high contour. Once this data file is entered into the computer, the fringe code can proceed with its analysis and determine aberration content. To avoid the toil of hand digitizing, software packages are commercially available that incorporate a fringe following routine. The interferogram is imaged onto a CCD. A frame-grabber captures the fringe pattern and formats it for the computer. This intensity digitized image is then operated on by the fringe following software. It automatically generates data centered along a fringe. However, the user still must define the fringe order. An alternative approach to fringe following is a phase measuring interferometer (PMI). This is a highly automated data acquisition system. The reference plate of the Fizeau is mounted in a fixture which is piezoelectrically driven, i.e. minute cyclic axial shifts are introduced. (This is equivalent to introducing a piston into the fringe pattern.) The pupil image (with fringes across it) is recorded on a CCD. The CCD is a uniform array of sensors. Each pixel monitors the variation in local irradiance as the reference plate is moved by the actuators. Data is acquired at every pixel for four or five discrete positions of the reference plate during its sweep. This enormous amount of data is fed into a computer where the analysis software calculates the local phase at each pixel. Fringe ordering is done automatically. Plus, the huge amount of data collected on a uniform grid offers a dramatic improvement in accuracy and repeatability. Also note that this method allows the user to analyze the quotnullquot interference pattern, something the first two techniques cannot do. For a particular test setup it is usually a good idea to take four separate interferograms with fringes tilt-biased top, bottom, right, and left respectively. Fringe codes usually have an option whereby several interferograms can be averaged. An interferogram from each fringe bias is entered into the code, and the ensemble average obtained. This average is a better estimate of aberration content than any single interferogram. When testing imaging systems it is a good practice to repeat the test setup at least three times. This is because misalignments in the setup can introduce unwanted aberrations (usually coma). For each setup obtain the four fringe biased data sets mentioned above and calculate the subaverage. Then average these subaverages. 5. Environmental Constraints Vibration, whether induced through the floor into the air-isolated optical table supporting the interferometer or coupled via acoustics, is a major weakness of interferometers. This mechanical noise makes the fringe pattern unstable; it dances around at high frequency. It is hard to do meaningful interferometry under such shaky circumstances. Hence it is very important when establishing a metrology lab to locate it in a quiet area. For example, you would not want to place it between a machine shop and an optical fabrication shop. At times it may even be necessary to come in at night, when everyone else is gone and all other machines are turned off, just to get stable fringes. Another source of trouble is air currents or turbulence from air vents, or thermals (from electronic equipment for example). The fringes don't dance as with mechanical vibration but actually change shape. They meander! When an interferogram is obtained under these circumstances you are not sure how much is the test piece and how much due to changes in the refractive index in the intervening air. Shrouding the work area can be a considerable help. For example, commercial foam board from office supply houses is a useful shrouding material. Also, with a PMI, frame averaging can sometimes reduce the problem considerably. 6. Mounting Sometimes an aberration attributed to a test optic is actually induced by the manner in which the optic is held in a mount. People are sometimes afraid that an optic might fall out, so they clamp it in (or down) good and tight. As a result, the interferogram may show significant aberration (usually astigmatism) even though the optic itself is of excellent quality. So be careful, you want to constrain the test optic with a minimum of force–snug enough so that it doesn't rattle around–but loose enough to avoid stress-induced deformation. Large optics (meter class) have an additional mounting difficulty. They are usually quite heavy and can deform under their own weight (Reference 5). The fringe pattern will show significant astigmatism. Astronomical primary mirrors are particularly susceptible to this. Elaborate fixturing is sometimes required to alleviate the problem. Technical Rationale: All optics to be used on spaceborne or space-related instruments should be tested to validate their performance as required by specification. The Fizeau interferometer is the primary tool in this optical validation process. It provides the standard against which other optics are compared. Therefore proper use of a Fizeau interferometer ensures that the resulting data can be employed as a pass/fail criteria on the component or system. References J. Geary, Introduction to Optical Testing, Vol. TT 15, SPIE Optical Engineering Press (1993). P. Hariharan, Basics of Interferometry, Academic Press (1992). D. Malacara, Optical Shop Testing, 2nd edition, John Wiley (1991). L. Selberg, quotInterferometer accuracy and precision,quot in SPIE Proceedings, Vol. 749, pp. 8-18 (1987) and in Vol. 1400, pp. 813-820. P. Yoder, Opto-Mechanical System Design,quot Marcel Dekker, Inc., 2nd edition (1993). J. Geary and L. Parker, quotNew test for cylindrical optics,quot Opt. Eng. 26, 8, pp. 813-820. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/17/2000
716 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Deployed Appendage Test Guidelines |  | Without a comprehensive test program, the following types of failure would not be caught and corrected prior to flight: No lock-in, or poor lock-in No release Deployment stops prematurely Electrical cable degradation Incorrect final positioning Deployment rate too high, resulting in high impact loads, thus possibly causing failures in other systems Fluid leak (causes contamination) Improper wiring | Perform thorough testing of all flight deployable appendages, including the design, analysis, fabrication and checkout of the test facility and related hardware; the planning and conducting of the actual tests; the post-test data reduction and analysis; and the re-testing after correction of anomalies. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline Number GT-TE-2403 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Adherence to this Guideline gives confidence that mechanisms will operate successfully during flight. The design phase analytical methods and results are verified. Testing determines margins to show by how much the design requirements are exceeded and pinpoints potential problem areas. Experience gained from failures and anomalies during testing help prevent recurrence in future programs. Implementation Method: In order to realize the benefits of a deployable appendages test program, the following steps should be taken: Use the design requirements for the hardware to be tested to generate a list of tests that will verify that each requirement will be met. This list should include how many times each test must be conducted, and the pass/fail criteria for each test. From this list, determine which tests can be combined to save time and costs. Select the critical design parameters for which test values and margins are to be measured. Decide what facilities and equipment will be needed for the tests. Design, analyze, fabricate, and check out any new items needed. Determine what personnel will be required for each test. Put together an overall schedule of tests, paying particular attention to the logistics of personnel, facilities, and material needed for each test. Use the results of the previous steps to write a comprehensive test plan. Follow the plan to set up and conduct the tests, then perform data reduction and analysis. Write up the results of the tests in one or more test reports. Correct deficiencies revealed in testing and re-test to verify the modified configuration. Technical Considerations: To realize all the benefits, the test program should include: Thorough testing to qualify the design and correlate the design analysis. Acceptance criteria must be established prior to the start of testing. Testing at greater extremes (temperatures, vacuum, loads) than expected during flight to determine margins. Testing of flight-like hardware to prove designs. Testing of actual flight hardware to prove workmanship and determine values of specific design parameters. Comprehensive part and component testing, to lessen the risk of failure at subsystem and system program phases, when such failures are very costly. Parts and components include: Bearings Springs Dampers Motors, gear trains Switches, position indicators Testing of subsystems (such as drive assemblies, hinge assemblies, gimbals, etc.) should include the following general tests: Mass properties Component interfaces System interface Subsystem performance verification (including margins) Subsystem strength verification Subsystem life, including lubricant/lubricant systems Thermal vacuum EMI/EMC Magnetic Vibration/acoustics Specific subsystem tests should include (where applicable): Restraint/release assembly tests Hinge assembly tests Drive assembly tests (solar array-antenna) Gimbal assembly tests System tests of complete deployable appendages should include: System tests should match flight configuration as closely as possible. Where practical, full deployment testing in simulated zero-G environment, including release, deployment, and lock-in. Deployment in thermal-vacuum is preferable, but generally impractical. Vibro/acoustic testing of the system in launch configuration should precede full deployment testing. Parameters to measure (where applicable) should include: Deployment time, release to lock-in Motor current Stiffness stowed and deployed Alignment Envelope of motion during deployment Electrical integrity of cables across hinges and gimbals Release shock Velocity at end of travel Torque margins System life, if applicable In-depth investigation of all anomalies. Test facilities include: Design and Analysis - deployment testing of large appendages usually requires special, tailor-made facilities to simulate actual flight conditions as closely as possible, and to perform special engineering tests. Such hardware includes: G-negation devices Inertial load simulators Thermal control devices capable of producing temperature levels and gradients Fixtures for environmental tests Fixtures for conducting stiffness measurements, modal tests, etc. Facility Design Parameters Simulation of mechanical and electrical launch configuration interfaces Space available for full deployment Type , number, size, and location of g-negation supports Weight, size, cost, manufacturability of fixtures Transportability of fixtures, if required Analysis Parameters Load carrying capacity of fixtures Effect of fixtures on measured data Pre-test predictions and establishment of pass/fail criteria Pre-test Environmental test fixtures must be calibrated and safety tested in actual facility prior to use Technical Rationale: Testing of deployable appendages for spacecraft differs somewhat from the testing of other space hardware. It involves special considerations for dealing with large, cumbersome devices that usually require some degree of manual handing after each operation. Since ground testing is done in a 1-g environment, a complex facility is usually required for simulating the zero-g space condition (g-negation device). This guideline covers the complete test program for spacecraft deployable appendages, including the general tests that also pertain to other space hardware, and the tests specifically pertinent to deployable appendages. References: GSFC Engineering Directorate paper, "Spacecraft Deployable Appendages," May 1992. Reliability Preferred Practice No. PD-EC-1101, Environmental Factors |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/17/2000
718 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Star Image Metrology Part 1: Visual Measurements |  | If end-to-end systems measurements are not made on spaceborne or space-related optical imaging systems, then the consequences could be the ultimate failure of the mission in-whole or in-part. The Hubble Telescope should be a constant reminder of this. | The fundamental behavior of a spaceborne (or space-related) optical imaging system is contained in its response to an impulse, i.e., a point source. The point source image is referred to by a variety of names: star image, point spread function, far field pattern, impulse response, Fraunhofer diffraction pattern. Here we will use quotstar image.quot This guideline provides information on instruments and procedures used in visual star image measurements. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GT-TE-2405 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Star image measurements provide the primary means of appraising the end-to-end health of an optical imaging system. These tests represent good engineering practice, and are reliable indicators of system performance. Star image tests are thus the final arbiter of quality control. A system passing the star tests discussed here ensures that the optical instrument is performing in a reliable manner. Visual inspection of the star image pattern is a simple and efficient means of determining whether a problem exists. If something is wrong, important clues as to its nature (e.g., decentered component, inappropriate conic constant) can be provided. Implementation Method: 1. Description of Star Image Test Apparatus The basic equipment needed to perform laboratory star image visual measurements is indicated in Figure 1. The optical system on the left half of the drawing is a Star Simulator. This is a Collimator with a back-illuminated pinhole located in the focal plane. The Collimator can be either reflective or refractive, and its pupil should be larger than the imaging system being tested. The pinhole represents the star, and its diameter should be smaller than the Collimator Airy Disc, (i.e., unresolved). Depending on the application, the pinhole back-illumination can be either from a coherent or incoherent source. An example of the former is a laser; the latter, a point arc lamp. Between the source and the pinhole there is usually some coupling optics to maximize the power through the pinhole, and to fill the aperture of the Collimator with light. (Caution: The pinhole acts like a quotpinhole camera.quot If a coiled filament lamp is used, an image of the coil will be formed on the collimator pupil and the output irradiance will be quite nonuniform). [D] Figure 1. Basic layout of a star image test setup A support structure is needed to hold the optical system under test. This mounting fixture should provide modest azimuth and elevation tilt control to allow alignment of the quottest systemquot to the Collimator optical axis. The test support fixture should also allow the quottest systemquot to be accurately rotated through its operational field of view. For refractive quottest systemsquot, the rotation axis should ideally pass through the system's rear nodal point. A mechanical support fixture that accomplishes this is called a T-Bar Nodal Slide (Reference 1). However, for catadioptric and reflective systems rotation through the rear nodal point is impractical because this point is usually far removed from the physical embodiment of the quottest system.quot In this Guideline, the rotation axis will be at, or near the entrance aperture of the quottest system.quot For visual measurements the quottest systemquot star image needs to be magnified. This can be accomplished using a high quality microscope. The microscope objective should be well-corrected for both axial color and spherical aberration. Its numerical aperture must be sufficient to collect all the light from the quottest system.quot The eyepiece must also be of good quality, and contain at least a cross-hair reticle to provide reference lines. The reticle plane will be coincident with the image formed by the objective. The microscope should have micrometer controlled XYZ-translation capability. 2. Ideal Star Image The structure of the star image is controlled by diffraction and aberrations in the imaging system. If aberrations are negligible, the system is said to be diffraction-limited. For a given focal length, the size and shape of the stop (i.e., the limiting aperture) determines the size and shape of the star image. This is considered the best one can do. The diffraction-limit is a benchmark or standard by which all other imagery is judged. Since most systems have circular unobscured stops, the resultant star image has a special name. It is called an Airy pattern and is shown in Figure 2. The central core is called the Airy Disc (and is measured across a diameter to the center of the first dark ring). Figure 3 (a & b) shows theoretical lateral and axial profiles about paraxial focus. (Although they look similar they actually represent two different mathematical functions). The separation between the zero intensity points on both plots is directly related to the system F-number (f/#). Note: F-number is the effective focal length divided by the entrance pupil diameter. (1) Lateral Scale = 2.44 l(f/#) (2) Axial Scale = 16 l (f/#)2 [D] Figure 2. Airy Pattern For an unaberrated diffraction-limited optical imaging system, the monochromatic star image is symmetric for an equal ± focus shift. Reflective imaging systems (e.g., Cassegrain telescope) typically contain central obscurations which modify the profile shapes shown in Figure 3. The extent of the modification depends on the obscuration ratio. As the obscuration ratio increases, the diameter of the central core contracts and more relative power enters the first bright ring. [D] Figure 3. Profiles of diffraction-limited star image Most optical systems are not diffraction-limited across their entire field. They suffer from defects called aberration (Reference 2). Given a single color (monochromatic), there are five primary (Seidel) aberrations. Two of these, field curvature and distortion, do not affect star image structure but rather its axial and lateral location with respect to the paraxial image plane. The remaining three aberrations, spherical aberration, coma, and astigmatism, do change the size and shape of the star image. It is the latter three that are of interest in this Guideline. (Note: There are higher order aberrations that can affect star image structure. But their influence is usually minor). For chromatic aberration, the effective focal length of a system and its magnification varies as a function of color or wavelength. This is because the refractive index of glass components in the imaging system are color dependent. This is called dispersion. In refractive systems the primary aberrations are also color dependent. It is common practice to measure the aberration over a restricted spectral bandwidth. The width and center wavelength of the band will depend on the application of the optical system. 3. Direct Visual Measurements on Star Image 3.1. Unaberrated System Align the microscope with the quottest systemquot and view the star image. Center the cross-hair on the pattern. Adjust the focus of the microscope until the Airy pattern is found. (This can be accomplished by: minimizing the number of observed rings; making the first dark ring as dark as possible; minimizing the power in the first bright ring). This establishes the location of paraxial focus. Offset the microscope laterally until the center of the cross-hair is in the middle of the first dark ring. Note the position on the lateral micrometer. Traverse to the opposite side and place the cross-hair center in the middle of the first dark ring. Note this position on the micrometer. Subtract these two micrometer readings to obtain the diameter of the Airy Disc. As a confirmation of F-number, substitute the measured Airy Disc value into Eq.1 and solve for f/#. Center the cross-hair on the Airy Disc. Adjust the focus and locate the first zero axial intensity positions on either side of paraxial focus. Note the Z-micrometer readings for both positions. Subtract these two Z values. Substitute this difference into Eq.2 and solve for f/#. 3.2. Axial Color In refractive imaging systems we rely on the curvatures, thicknesses, and refractive indices of the glasses used to form a point image at a certain plane. Unfortunately, the index of refraction of glass is wavelength dependent, a phenomenon known as dispersion. This is illustrated in Figure 4. A white light collimated input beam is imaged at various points along the optical axis according to color. [D] Figure 4. Dispersion in simple lens results in color dependent axial image points [D] Figure 5. Axial Color of Complex Lens To measure axial color (Reference 1), align the quottest systemquot to the Collimator. A white light source is needed but the source housing should have a provision for supporting narrow band color filters between the source and the pinhole. Five to ten spectrally separated filters should be enough to sufficiently sample the visible region. (Note: If there is significant spherical aberration, stop the lens down to about 3/4 of the aperture). Using the microscope, we measure the axial location of the Airy pattern for each filter. A sample plot is shown in Figure 5 for a 6quot f/1.5 airborne surveillance objective. 3.3. Primary Aberrations The success with which one can visually measure an aberration type in the star image depends on the relative purity of the aberration. On-axis there should only be spherical aberration. Off-axis will be a mixture of spherical, coma, and astigmatism. If spherical is well-corrected, coma will tend to dominate small field angles. As field angle increases, a point is reached where astigmatism and coma are the same magnitude. Thereafter, astigmatism increases at a faster rate than coma, and dominates the larger field angles. 3.3.1. Spherical Aberration Spherical aberration (References 2 and 3) arises when different annular zones of a lens focus at different points along the optical axis as illustrated in Figure 6. The location of the minimum blur circle is where the marginal ray intersects the caustic. (In Figure 6 note the point where the marginal ray crosses the next innermost ray. This point starts the caustic which is the envelope of crossover points of adjacent rays.) [D] Figure 6. Ray fan showing the caustic and minimum blur circle (courtesy Dr. John Loomis) We examine the aberrated star image with the microscope and adjust the focus back and forth until we find the minimum blur circle. Using the lateral translation capability on the microscope, we measure the diameter, Dmb, of this blur circle (in a manner similar to the Airy Disc measurement). Dmb is related to the wavefront aberration coefficient W040 (References 1 and 2) by: (3) D mb= 4(f/#) W 040 The above method will generally work for spherical aberration magnitudes above 2 waves. i.e., W040= 2l. Below this a different technique can be used for unobscured systems. (Reference 4). Stop the quottest systemquot down by centering a small circular aperture in the entrance aperture. Observe the enlarged diffraction pattern. Move the microscope axially back and forth to identify the best Airy pattern as discussed in Sec.3.1. This establishes the paraxial plane. Note the reading on the micrometer. Remove the small circular aperture. Readjust the microscope axially once again to identify the best Airy-like pattern. Note the new micrometer reading. Take the difference, d, between the two micrometer readings. This difference can be related to the aberration coefficient by: (4) d = 8 (f/#) 2 W 040 By averaging over 10 readings an accuracy of a quarter wave should be attainable. 3.3.2. Astigmatism Astigmatism (Reference 2 and 3) arises in a system because sagittal and tangential rays from an off-axis point source do not come to a common focus as is illustrated in Figure 7. The images formed by the two fans both lie on the chief (or principal) ray but are longitudinally separated. Further, the images formed at these two locations appear as lines orthogonal to each other. These are called the tangential and the sagittal line images. [D] Figure 7. Illustration of astigmatism showing sagittal and tangential ray fans (Modern Optical Engineering) Astigmatism can be measured (Reference 1) by determining the separation between the two line foci (along the chief ray) as a function of field position. (Note: If the quottest systemquot has a significant amount of spherical aberration it would be helpful to stop the system down to about 3/4 of its aperture). Referring back to Figure 1, we rotate the quottest systemquot about the rotation axis to some field angle. Because this rotation does not take place at the rear nodal point, the microscope will have to be translated laterally to reacquire the image. Center the microscope cross-hairs the on the star pattern at medial focus (or circle of least confusion). Adjust the focus of the microscope and locate each line focus. Note the Z-micrometer readings. These can be plotted up as a function of field angle, and the separations between the line focii will be readily apparent as illustrated in Figure 8. If higher order astigmatism is negligible, the longitudinal separation at maximum field angle can be related to the 4th order aberration coefficient by: (5) d = 8 (f/#)2W222 [D] Figure 8. Astigmatism plot for Aerojet lens (Ref. 1). Significant higher order astigmatism is present. 3.3.3. Coma Coma (Reference 2 and 3) is zonal dependent like spherical aberration. Coma formation is illustrated in Figure 9. (Reference 1). Each circular zone in the lens pupil forms a ring in the image plane. The rings are of different sizes, and are shifted relative to each other as shown in Figure 9 (b). The pattern resembles an ice cream cone. The chief ray intersects this image plane at the tip of the cone. The line bisecting the coma pattern in the image plane passes through the optical axis. The lines tangent to the ensemble of rings on either side form a 60o angle. The ring from the marginal ray zone is the largest and its center is farthest from the chief ray intersection point. The paraxial-like zone about the chief ray forms the smallest ring and its center is closest to the chief ray. The length from the chief ray to the farthest point on the marginal ring is called tangential coma. The radius of this ring is termed sagittal coma. It can be shown that: (6)Tangential coma = 3 Sagittal coma [D] Figure 9a. Formation of coma from an off-axis object point [D] Figure 9b. Coma pattern Coma is usually measured in the paraxial plane. This means that in addition to moving the microscope laterally to reacquire the image after rotation, some predetermined axial adjustment must also be made to place our point of observation in the paraxial plane. (If a T-Bar nodal Slide is being used, such adjustments are accomplished automatically). Tangential coma is then measured. Tangential coma (TC) can be related to the aberration coefficient at the maximum field position by: (7) TC = 6(f/#)W 131 Unfortunately, unless coma is pure or heavily dominant, it will be difficult to measure. Unlike axial color and astigmatism, stopping the lens down does not help us because coma, like spherical, is zonal dependent. Hence, in the presence of competing aberrations, the anchor points for the lateral coma measurement become difficult to define. Note: Further information on star image testing can be found in Reference 6. 4. Indirect Visual Measurements ... Knife Edge Test In this procedure a knife edge (e.g. a razor blade) explores the region around the star image while the observer views the quottest systemquot pupil directly by eye or on an observation screen. The setup is illustrated in Figure 10. The microscope has been removed from the XYZ-translator, and a knife edge put in its place. [D] Figure 10. Knife edge test on star image Figure 11 illustrates the basic operating principle of the knife edge test for an unaberrated quottest system.quot In the exit pupil, we have a spherical wavefront. Ray normals to the wavefront converge to a point focus. We place an observation screen well outside of the focal region. On the screen we see a circular patch of uniform light (essentially a scaled version of the light distribution in the pupil). Next, we set up a razor blade on an Y-Z translator in the neighborhood of the focal point. Assume we are inside focus (between the pupil and the image point). As we translate the knife edge laterally and start blocking light, we see a straight edge shadow move across the box of light on the observation screen in a direction opposite the knife edge motion. [D] Figure 11. Knife edge scan inside focus We then move the knife edge axially the same distance outside of focus (between the image point and the screen), and then cut across. Again we see a straight edge shadow creep across the light box, but now in the same direction as the scan. At paraxial focus the observer is not aware of a shadow transition...just a general dimming and then darkness. This effect occurs very quickly as the knife edge is translated. If we rotate the knife edge about the optical axis so that it cuts the beam along a different vector, the shadow pattern behavior rotates through the same angle as the knife edge. This holds true not only for unaberrated systems but for all rotationally symmetric aberrations as well. It is not true, however, for asymmetric aberrations. When aberrations are present, the shadow and its boundaries can take on rather complicated behavior. Further, pattern behavior depends on the axial location of the knife edge relative to paraxial focus. (Reference 7). Knife edge testing has been used in optical shops for generations. Though not easily quantifiable, it is quite sensitive and provides an important source of information to the trained eye of an optician. The knife edge patterns guide the optician to locate and correct sources of figure error. In recent years a modified knife edge test coupled with sophisticated software has successfully quantified this venerable technique. (References 8 and 9). Note: Further information on knife edge testing can be found in Reference 10. Technical Rationale: All optical imaging systems used on spaceborne or space-related instruments should undergo an end-to-end systems check to validate performance. Star image testing is the primary means of conducting this validation process. It provides data pertinent to the pass/fail criteria associated with the optical imaging system. References: J. Geary, Introduction to Optical Testing, Tutorial Text TT-15, SPIE Press (1993). J. Wyant and K. Creath, Applied Optics and Optical Engineering, Vol. 11, Chap. 1, ed. R. Shannon and J. Wyant, Academic Press (1992). J. Hecht and E. Zajac, Optics Addison-Wesley (1975). J. Geary and P. Peterson.quotSpherical Aberration: a Possible New Measurement Approach,quot Opt. Eng. 25, 2 (1986). M. Born and E. Wolf, Principles of Optics, Pergamon, 6th Ed. (1980). W. Welford, in Optical Shop Testing, 2nd Ed. Chap. 11, ed. D. Malacara, John Wiley (1991). M. Cagnet, M. Francon, and J. C. Thrierr, Atlas of Optical Phenomenon, Springer-Verlag (1963). D. Vandenberg, W. Humbei, and A. Wertheimer, quotQuantitative Evaluation of Optical Surfaces by Means of an Improved Foucault Test Approach,quot Opt. Eng. 32, 8, pp 1951-1954 (1993). J. Geary, M. Yoo, P. Davila, A. Wirth, A. Jankevics, M. Ruda, B. Zielinski, and L. Petrilli, quotComparison of Wavefront Sensor Techniques,quot SPIE Proc. Vol. 1776 (1992). J. Ojeda-Castaneda, in Optical Shop Testing, 2nd Ed. Chap. 8, ed. D. Malacara, John Wiley (1991). Reliability Preferred Practices Guideline No. GT-TE-2404 - Guideline for Use of Fizeau Interferometer in Optical Testing. Reliability Preferred Practices Guideline No GT-TE-2406 - Star Image Metrology: Part II Irradiance Measurements. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/17/2000
705 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Micrometeoroid Protection | Preferred Practice for Design & Test. The absence of micrometeoroid protection measures in spacecraft and mission design will increase the risk of significant damage to the spacecraft, particularly in areas of high meteoroid flux and during vulnerable mission phases. Provide protection for the spacecraft structure and instruments to minimize damage from micrometeoroid penetration. Typical reliability engineering measures range from structural positioning to protect sensitive hardware to placement of protective blankets on the spacecraft exterior. | The absence of micrometeoroid protection measures in spacecraft and mission design will increase the risk of significant damage to the spacecraft, particularly in areas of high meteoroid flux and during vulnerable mission phases. Micrometeoroid protection requirements are difficult to verify due to the absence of data on actual meteoroid damage in interplanetary flight. However, use of micrometeoroid protection measures within technical and economic constraints is a prudent design approach. | Provide protection for the spacecraft structure and instruments to minimize damage from micrometeoroid penetration. (For the purpose of environmental modeling, a micrometeoroid is defined as being in the range of 10-18 to 1.0 grams in mass.) Typical reliability engineering measures range from structural positioning to protect sensitive hardware to placement of protective blankets on the spacecraft exterior. The extent of the protective measures is based on estimates of the meteoroid environment for the flight profile, the ability of micrometeoroids to penetrate the external skin, and the likelihood of critical damage from a penetration. | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice Number PD-EC-1107; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Micrometeoroid protection minimizes the risk of impacts that can damage spacecraft systems and jeopardize flightworthiness. Sources of meteoroids include planetary ejecta and particles of asteroidal and cometary origin. Impacts on spacecraft can cause partial penetration, perforation, spalling, local deformation, or secondary fractures, any of which can result in failure of a critical system. Typical failure modes include: Catastrophic rupture. Leakage. Deflagration. Vaporific flash. Reduced structural strength. Erosion. Implementation Method: Micrometeoroid protection is designed to attain an acceptable failure probability for critical spacecraft subsystems. It involves the application of spacecraft and mission design measures which are also used to control other aspects of the spacecraft environment — radiation protection, thermal protection, thermal insulation, and space radiators — requiring an integrated approach to environmental design. Damage Assessment The first step in determining the appropriate level of spacecraft protection is evaluation of the environment as defined by the meteoroid fluence, defined as the number of impacts per square meter (m2) of the spacecraft over the mission duration. The meteoroid environment is calculated based on models of near-Earth and interplanetary space (Ref. 4, 5), with particular attention to the asteroid belt between Mars and Jupiter. The current models describe meteoroid mass and orbital distributions based on data from impact detectors aboard the Pioneer 10 and 11, Helios 1, Galileo, and Ulysses spacecraft and measurements of the interplanetary flux (particles/m2/second) near Earth. Meteoroid fluence models are continously updated based on flight experience. However, because the major portion of the meteoroid flux has a random distribution, a statistical model is used to determine the probability of a spacecraft encountering a meteoroid of a given critical mass. The meteoroid fluences /m2 are then evaluated for different mission phases — for example, transit, aerobraking, mapping, and relay. The fluences as a function of particle mass may then be calculated from the spacecraft trajectory and velocity as determined by the mission profile. Following evaluation of the meteoroid environment for each mission phase, three additional factors — areas of interest, field of view, and spacecraft attitude — are then factored into the fluences for all mission phases. For the areas of interest, spacecraft drawings are reviewed to obtain the surface areas in m2 for each critical spacecraft system. The field of view, or geometric factor corresponding to all visible surfaces of an object, is calculated using a ray tracing computer code. The geometric factor specifies the fraction of the fluence that will be detected by a detector placed on one of the surfaces. The spacecraft attitude during the mission is important because the surface perpendicular to the velocity vector will receive the highest fluence, while the trailing edge surface will receive the lowest fluence. To derive the probability of failure of each spacecraft system, the fluence (as a function of velocity) is multiplied by the appropriate area (m2), geometric factor, and attitude factor to give the expected number of impacts on the area of interest. Penetration equations are then used to estimate the critical mass as a function of velocity necessary to cause penetration of a surface. For example, a review of Mars Global Surveyor (MGS) propellant and helium tanks indicated that the probability of propellant tank No. 1 being struck by a meteoroid (though not necessarily damaged) during the mission is 30 percent, and 25 percent for propellant tank No. 2. Based on the damage assessment, a decision is made on suitable protective measures to minimize damage to critical spacecraft subsystems. (For a linear component, calculation of the surface area may not be feasible. Damage assessment for the cables along the MGS high gain antenna boom, for example, was based on a determination that only one side of the cables is vulnerable: the other side is protected by the boom.) Protective Measures System Design Measures. Micrometeoroid protection is considered in the design of the spacecraft structure and the location of critical assemblies relative to the spacecraft structure. Critical assemblies may be positioned so that their field of view is shielded by less critical assemblies or by structures which may be penetrated or deformed without resultant mission-critical damage. With this approach, the most crucial or easily damaged circuit board, for example, should be placed deepest in the electronics bay; the board's long axis could also be positioned parallel to the velocity vector to minimize the fluence. More realistically, however, meteoroid protection requirements must be balanced against the need for radiation and thermal protection in an integrated environmental design. Operational Measures. Due to the directional properties of particle impact velocities, spacecraft attitude has an effect on the micrometeoroid fluences that each side of the spacecraft receives. Certain mission phases, such as planetary mapping, place the spacecraft in a high flux location in interplanetary or orbital space. Hence, a measure of protection may be attained from a mission profile which adjusts spacecraft attitude to minimize damage to critical systems during hazardous mission phases. For the Mars Global Surveyor (MGS) project, fluences were calculated for the different sides of the spacecraft (+X, -X, +Y, -Y, +Z, and -Z). For the Cruise phase of the mission, the +X side of the spacecraft will face the Earth, and the varying attitude will cause the -Y and -X sides to receive similar fluences. During the Mapping and Relay phases, with MGS orbiting Mars while moving with Mars in its orbit around the sun, the +Z side of MGS will face the planet while the +Y side will face in the direction of Mars orbital velocity. The net effect is a rotation of MGS about its Y axis. Calculations indicate that the flux at the leading edge of the spacecraft (+Y) will be approximately 20 times larger than the trailing edge. [D] The MGS propellant and helium tanks are located on the +Y side of the spacecraft, as indicated in Figure 1. Combining the formulas for penetration with the meteoroid fluences, and multiplying by the field of view (geometric factor), the attitude factor, and the area of each side of the spacecraft, gives the number of impacts per unit area that can produce failures. Applying a Poisson distribution gives the probability of failures over each mission phase. Figure 2 indicates the probability of success for the MGS tanks. [D] Protective Shielding. The primary technique for meteoroid protection is placement of multi-layer insulation (MLI) blankets on critical areas of the spacecraft, such as propellant and helium tanks. MLI blankets are composed of layers of a Kapton polyamide or mylar; gold foil on one side and silver on the other provides very effective thermal insulation and thermal radiation transfer. In its use as a projectile shield, the blanket function is to break up the projectile before it strikes an exterior wall, disperse the fragments, and reduce the velocity of the fragments below that of the original projectile. Spacecraft damage is caused by the debris from the projectile and the shield. MLI effectiveness in preventing damage to critical spacecraft subsystems depends on the: Blanket material, location, and number of layers. Meteoroid mass, impact velocity, density, and angle of impact. Impacted structure material, thickness, temperature, stress level, and the number and spacing of the plates composing the structure and the subsystem package. However, an MLI layer density approximating that of tissue paper is sufficient to stop most strikes due to the very small mass of the typical micrometeoroid. Specification of MLI blankets for meteoroid protection is not generally practiced because the blanket characteristics are established for the objective of maximizing thermal control, with penetration shielding as a secondary benefit. A single exception is the use of MLI specifically to shield certain components of the rocket nozzles on the Cassini spacecraft. However, the spacecraft MLI design — the MLI integration with the spacecraft structure — is planned to provide the optimal level of meteoroid protection. The primary MLI design variable for providing micrometeoroid protection is the blanket-structure separation distance. Modeling and ground test have demonstrated that the likelihood of micrometeoroid damage decreases with increasing separation between the blanket and external spacecraft structural surfaces. This is mostly due to the dispersion of the projectile and shield fragments with increasing distance. Where a tight cluster would result in penetration by debris approaching the mass of the original projectile, dispersion may produce scattered separate craters, bulges, or holes. Penetration equations derived from modeling, and from tests using particle accelerators and light-gas guns, are used to calculate the critical meteoroid mass (mc) necessary to cause the failure (i.e., penetration) of a given surface. Separate equations are used for single surfaces (e.g., the spacecraft wall and attached shield) and double surfaces (e.g., spacing between the spacecraft wall and blanket). Equation 1 calculates the critical penetration mass (mc) of the meteoroid in grams for a single surface geometry. [D] Eq 1. (Single Surfaces) Where: m c = critical penetration mass of the meteoroid (grams) t = wall thickness (inches) K t = material constant (0.54 for aluminum alloys) r m = meteoroid mass density (2.5 g/cm 3) V = impact velocity (km/s) Equation 2 is used to calculate the critical mass (mc) for a double-wall structure where a blanket shields the exterior of a spacecraft structure (such as a propellant tank) or component (such as a cable along a spacecraft boom). [D] Eq 2. (Double Surfaces) Where: S = spacing between blanket and tank wall (cm) t b = thickness of tank wall (cm) s y = yield stress for the tank wall (47,000 lb/in 2) r m = meteoroid mass density (2.5 g/cm 3) r t = blanket mass density (0.3 g/cm 3) V = impact velocity (km/s) Equation 2 demonstrates that the critical penetration mass will increase and the probability of failure will decrease with increased spacing between the blanket and the shielded surface. For example, when applied to a review of Mars Global Surveyor (MGS) propellant tanks, Equation 2 showed that a 2-inch spacing between the surface of each tank and the MLI blanket will decrease the probability of failure during the mission to about 6 percent on both tanks, given the expected meteoroid fluences. This represents a decrease from the 30 percent probability of failure for propellant tank No. 1 and 25 percent for propellant tank No. 2, given no separation, which was previously mentioned. Figure 3 depicts the effect of blanket separation on the probability of success for the MGS tanks. [D] The applicability of these equations is limited by data availability. The practice has been to extrapolate the equations over the micrometeoroid mass and velocity anticipated during a spacecraft mission. They provide the best available estimate of penetration in the 0 to 10 km/s velocity range; lacking experimental test data for higher impact velocities, they have also been used for velocities exceeding 10 km/s. However, there may be insufficient validating data on impact velocities exceeding 7 km/s. Although JPL is presently working on extending the penetration equations to higher velocities, JPL has no reason to believe that micrometeoroid protection practices for long missions have been other than successful. Technical Rationale: The ability of meteoroids to penetrate the external skin of a spacecraft has been amply demonstrated by meteoroid detection satellites and other near-earth spacecraft. The ability of micrometeoroids in interplanetary space to damage spacecraft is inferred. Environmental models of meteoroids in near-earth and interplanetary space, and particularly in the asteroid belt between Mars and Jupiter, are continuously updated. However, because the major portion of the meteoroid flux has a random distribution, a statistical model is used to determine the probability of a spacecraft encountering a meteoroid of a given critical mass. The damage capability of a meteoroid depends on its mass, velocity, density, and angle of impact. The physical response of an impacted structure depends on the material, thickness, temperature, stress level, and the number and spacing of the plates (including shielding) composing the structure. Based on models of the micrometeoroid fluence and calculations of the number of impacts that can lead to failure, the degree of damage can be estimated and appropriate design or operational measures can be implemented. References: Aguero, R.C., quotMeteoroid Impacts on MGS,quot (Mars Global Surveyor Project), Jet Propulsion Laboratory IOM 5050-95-316 to T.D. Newell, November 6, 1995. Frost, V.C., Meteoroid Damage Assessment, Space Vehicle Design Criteria (Structures) Document SP-8042, National Aeronautics and Space Administration, May 1970. quotSpacecraft Environmental Estimates,quot (Mars Global Surveyor Project), Jet Propulsion Laboratory Document MGS 542-203, October 14, 1994. Divine, N., quotFive Populations of Interplanetary Meteoroids,quot Journal of Geophysics Research, 98, pp. 17,029- 17,048, 1993. Divine, N. and Gruen, R., quotModeling the Meteoroid Distributions in Interplanetary Space and Near-Earth,quot Proceedings of the First European Conference on Space Debris, Darmstadt, Germany, April, 1993. quotMeteoroids/Space Debris,quot Reliability Preferred Practice No. PD-EC-1102. | This practice has been used on Magellan and Galileo. The Mars Global Surveyor (MGS) and Cassini programs utilize new, updated interplanetary fluence models and penetration formulas. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
706 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Monitoring Spacecraft Exposure to Magnetic Fields | Preferred Practice for Design & Test. If there is no process in place to monitor the magnetic field exposure of flight hardware between integration and launch, there is no assurance that high permeability materials are in their lowest magnetic state. Magnetized components could result in erroneous magnetometer experiment data or other adverse effects. This reliability practice provides a read out of magnetic field exposures which could adversely affect the magnetic cleanliness of the spacecraft. When transporting a spacecraft or flight instrument to a launch site or other facility, monitor the D.C. magnetic field peak exposure with a “tell tale” sensor. This practice is also applicable to flight hardware placed in storage for extended periods. | If there is no process in place to monitor the magnetic field exposure of flight hardware between integration and launch, there is no assurance that high permeability materials are in their lowest magnetic state. Magnetized components could result in erroneous magnetometer experiment data or other adverse effects. | This reliability practice provides a read out of magnetic field exposures which could adversely affect the magnetic cleanliness of the spacecraft. When transporting a spacecraft or flight instrument to a launch site or other facility, monitor the D.C. magnetic field peak exposure with a quottell talequot sensor. This practice is also applicable to flight hardware placed in storage for extended periods. | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice Number PD-EC-1104; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The quottell talequot device will provide an indication of the peak D.C. magnetic field intensity to which the transported (or stored) system has been exposed. High residual fields are sometimes caused by nearby lightning strikes, power system faults or exposure to strong permanent magnets. Compliance with the peak magnetic field exposure, as defined in the Magnetic Control Plan document, assures that the flight hardware is in its lowest magnetic state, thereby minimizing any adverse effects on the integrity of science data. Implementation Method: JPL uses a version of the quottell talequot sensor devised by the Ames Research Center to verify compliance with the magnetic control imposed on the Apollo program and by the science requirements for the Pioneer spacecraft. This 3 cm cubic sensor is comprised of 3 orthogonal Dumet wires (20 AWG, approximately 5 cm long) embedded in a plastic block (provided with a ground strap to avoid electrostatic discharge). The block is demagnetized in a near zero field environment and the net magnetic moment is measured in the earth's field (0.05 mT) [Typical value at mid-latitudes (0.5 Gauss), Gauss = 10-4 Tesla, mT = milliTesla] and at several intermediate points up to a maximum exposure of 2.5 mT (25 Gauss). After a demagnetization, the device is ready for use. For practical considerations, the device characteristics are expressed in terms of the observed effect of field exposure, i.e. magnetic field in nanoTeslas (nT) produced at a distance of 0.3 meter (12 inches) from the tell tale. Figure 1 shows a sample calibration. [D] Given the measured field exposure characteristics for peak exposure of the device, subsequent measurements are indicative of the maximum field exposure since the last demagnetization. Sample results are indicated in Table 1, where the maximum field exposure was less than 0.3 mT (3 Gauss). Table 1: Magnetic Exposure Recorder, Sample Results Serial Number Measured Magnetic Field @ 0.3m (12quot)* X-Axis Y-Axis Z-Axis SN 003 <1 1 1 SN 002 1 1.5 1 SN 001 <1 <1 <1 SN 009 2 1 <1 * (nT, peak to peak) Typically, 4 to 6 sensors are mounted around the perimeter of the system being monitored. At significant points in the processing of the flight hardware, the sensors are removed for measurement, demagnetized, and returned to their initial locations. In the event that excessive field exposure is detected, cognizant hardware personnel can determine if the flight hardware being monitored requires demagnetization. Knowledge of the locations of the sensors, their relative field exposure, and the hardware processing performed since the last measurement can aid in the identification of the source of the magnetization and in determining if the spacecraft needs localized demagnetization. An example of the use of this device is the transport container for the Galileo spacecraft. Four sensors were located on the inside of the truck container wall around the spacecraft. Two sensors were mounted ahead of the spacecraft on the right and left side wall and two more were mounted behind the spacecraft. Thus, the sensors would be more exposed than the spacecraft to any external magnetic field that might pass by the transport truck. At the end of the cross country trip, none of the twelve magnetizable rods showed any evidence of exposure to an excessive magnetic field. Technical Rationale: Because it is impractical to completely eliminate the use of ferromagnetic materials on spacecraft and flight hardware, it is important to control the maximum magnetic field exposure for hardware used on those missions for which a magnetic control plan has been implemented. In most cases, a magnetic control plan is required for missions which have a science magnetometer or a plasma wave experiment as part of the payload. Verification of compliance with the specified maximum field exposure is difficult because not all sources of strong magnetic fields are obvious, and there is no sensual perception of magnetic fields in the range of interest for spacecraft concerns, 0.1 to 2.5 mT (1 to 25 Gauss). In addition, the time interval over which monitoring may be required can be very long-- particularly if the flight hardware has to be shipped over long distances or placed in storage. Hence, a passive sensing device is needed. Dumet, a ferromagnetic alloy, has mechanical properties which make it suitable for applications such as component leads requiring a hermetic seal to glass. An ancillary characteristic of this material is a high magnetic permeability. This property, coupled with the fact that the material is available in the form of small diameter wire, makes it suitable for use in the fabrication of the quottell talequot sensors. Alternate materials include Kovar and ferrites. References: quotAssessment and Control of Spacecraft Magnetic Fieldsquot, NASA SP-8037, September 1970. Magnetic Design Control for Science Instruments, Reliability Preferred Practice No. PD-ED-1207 Demagnetization of Ferromagnetic Parts, Reliability Preferred Practice No. PD-ED-1220 Magnetic Field Restraints for Spacecraft Systems and Subsystems, Reliability Preferred Practice No. PD-ED-1222 | This practice has been used on Apollo, Pioneer, Mariner Venus '67, Voyager, Galileo. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
707 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Fault Tolerant Design | Preferred Practice for Design & Test. Systems that do not incorporate fault tolerant design as a part of their development process will experience a higher risk of a severely degraded or prematurely terminated mission. Incorporate hardware and software features in the design of spacecraft equipment which tolerate the effects of minor failures and minimize switching from the primary to the secondary string. This increases the potential availability and reliability of the primary string. | Systems which do not incorporate FTD as a part of their development process will experience a higher risk of a severely degraded or prematurely terminated mission, or it may result in excessively large weight volume, or high cost to achieve an acceptable level of performance by using non-optimized redundancy or overdesign. | Incorporate hardware and software features in the design of spacecraft equipment which tolerate the effects of minor failures and minimize switching from the primary to the secondary string. This increases the potential availability and reliability of the primary string. | JPL | 01/31/1999 | This Lesson Learned is based on Reliability Practice Number PD-ED-1246 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Fault tolerant design provides a means to achieve a balanced project risk where the cost of failure protection is commensurate with the program resources and the mission criticality of the equipment. By providing compensation for potential hardware failures, a fault tolerant design approach may achieve reliability objectives without recourse to non-optimized redundancy or overdesign. Implementation Method: The practice of fault tolerant design (FTD) presumes that the potential causes of failures are identifiable. This identification is performed by means of the existing practices of hardware and software failure modes, effects, and criticality analysis (FMECA). Similarly, fault tree analysis (FTA) identifies safety issues and potential faults in mechanical and electromechanical devices. Design engineers utilize the preliminary results of FMECAs and FTAs to establish fault tolerant equipment design priorities. FTD is an iterative process; its current validity relies on the current iteration of the FMECA and FTA and their corresponding criticalities and probabilities of occurrence. The iteration cycle ceases when either the cost of the next design iteration is programmatically unacceptable or when the risk has been reduced below a stated goal. It is assumed that all of the normal reliability design tools such as part stress derating, worst case performance analysis, qualification testing, life demonstration, quality control, etc., have already been used to preclude any design or material deficiencies. The FTD process also assumes that, in spite of the above practices, an in-flight failure may occur in a given set of manufactured hardware. This process flow is illustrated in Figure 1. The diagram illustrates that FTD is a top-level system design philosophy covering other NASA preferred reliability practices, including analytical design disciplines, FMECA and FTA studies, fault protection plans, and test results. The FTD process at JPL includes four phases beginning with analytical design. [D] Technical Rationale: To increase the reliability of a spacecraft system, two complementary but fundamentally different approaches are taken: Fault prevention (fault intolerance), and Fault tolerance. Fault prevention deals with the objective of increasing reliability by elimination of all faults, which is not feasible in reality. Therefore, the goal of fault prevention is to reduce the probability of system failure to an acceptably low value. The fault tolerance approach expects failures to occur. However, their effects will be automatically counteracted by incorporating either redundancy or other types of compensation. A fault tolerant design approach differs from a pure design redundancy approach in that provisions are made for planned degraded modes of operation where acceptable. For example, the high gain antenna of a spacecraft is usually non-redundant because of its size. An FTD would favor the use of a backup medium gain antenna operating at reduced data rates as a degraded but acceptable operating mode. Similarly, a partially failed power source within a solar panel array or a failure of one of three radioisotope thermoelectric generators (RTGs) could be accommodated: an appropriate failure detection circuit and a software fault protection algorithm would be provided to shed low priority electrical loads or instruments, while maintaining most mission capabilities. Also, FTD may be preferable to mere hardware redundancy in that higher probability multiple failures can be identified and accommodated. For example, the common design practice for inertial sensors (gyros) is the use of three packages of orthogonally located dual axis sensors (i.e., the X-Y, Y-Z, and Z-X axes). This scheme is tolerant of the loss of any one gyro but can be extended to accommodate the loss of any two gyros by the use of a pair of two-axis positionally adjustable gyros insertable by command or by detection algorithms. It can be placed in the X-Y or X-Z directions, thereby providing at least one signal on each axis even if two pairs of fixed mounted gyros are lost. In this case, dual failures are accommodated with only a short interruption of service and some additional mechanical complexity, but with no significant loss in system performance. The essential ingredients to achieving a fault tolerant design are the performance of a thorough FMECA and FTA, the detailed communication of these identified failure modes and effects to the fault protection design engineers, and strong participation by the project engineer and program management in assessing design cost/benefit trade-off iterations. An FTD will be limited by either weight, volume, schedule, or cost constraints. Presentation of fault tolerant design options to program management requires a skilled engineering team with intimate knowledge of system operation and close communication with system designers. An FTD can provide dramatic improvements in system reliability and lead to a substantial reduction in flight failures as a consequence of fewer disabling system failures. References: Fault Protection System Design and Operations, JPL Document D625-505, Vol. 8, Galileo Project, October 1989. Fault Protection Requirements, JPL Document 699-CAS-3-330, Cassini Project, March 1994. System Fault Protection Algorithms, JPL Document 699-CAS-3-331, Cassini Project, January 1995. Fault Protection, Reliability Preferred Practice No. PD-ED-1243 Active Redundancy, Reliability Preferred Practice No. PD-ED-1216 Failure Modes, Effects, and Criticality Analysis (FMECA), Reliability Preferred Practice No. PD-AP-1307 | This practice has been used on Voyager, Galileo, Magellan, Cassini | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
708 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Plasma Noise in EMI Design | Preferred Practice for Design & Test. Electromagnetic interference (EMI) sources may cause unpredictable operational anomalies and compromised science data. Missions with payloads that can interact strongly with the ambient plasma, such as a high power electron beam, a high power RF source, or an ion engine, may require a structural current test for conducted susceptibility and higher radiated susceptibility test levels. The practice is to perform an analysis early in such a program to estimate the amplitude of plasma noise induced EMI. This may identify potential adverse effects on operational reliability. | Unpredictable operational anomalies and compromised science data may result. | Missions with payloads that can interact strongly with the ambient plasma, such as a high power electron beam, a high power RF source, or an ion engine, may require a structural current test for conducted susceptibility and higher radiated susceptibility test levels. The practice is to perform an analysis early in such a program to estimate the amplitude of plasma noise induced electromagnetic interference (EMI). This may identify potential adverse effects on operational reliability. | JPL | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-EC-1106; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Potential EMI sources are identified in time so that appropriate measures can be incorporated into the electromagnetic compatibility (EMC) program. If the high predicted levels turn out to be a problem, the early identification allows time to develop a solution. Implementation Method: Perform a comprehensive survey of the mission environments and payload characteristics, then determine the possible sources of plasma generated noise. If the source of plasma noise is from the natural occurring space plasma or arises from the motion of a spacecraft through the earth's geomagnetic field, the radiated susceptibility (RS03) test levels specified in MIL-STD-461C will be adequate. The magnitude of plasma waves in the natural space environment is usually limited by the thermal energy of the ambient plasma. Due to the low plasma densities of the earth and other planets, the energy content of the naturally occurring space plasma is relatively low. It can easily be shown that the MIL-STD-461C radiated susceptibility RS03 limits are adequate to demonstrate a spacecraft's immunity to EMI generated by natural plasma noise. The RS03 specifications are: Frequency Range E-Field (Volts/meter) 14 kHz to 30 MHz 10 30 MHz to 10 GHz 5 Above 10 GHz 20 For large conducting structures moving across the geomagnetic field, additional plasma noise is generated as a result of wave emission due to the motion induced VxB electric field. In low earth orbit, the noise level generated by a typical space station structure is estimated to be 10-3 V/m per ampere current (ref. 1) and that of a tethered satellite system is 10-1 V/m (ref. 2). Since the typical current flow for the space station and the tethered satellite is less than 1 Amp, the electric field generated by motion of a space structure will also be enveloped by the MIL-STD-461C RS03 limits. Plasma can also cause structure current (conducted emission) to flow in the spacecraft. In the absence of any externally induced events, the net current to the spacecraft structure is always zero. When the spacecraft goes in and out of eclipse, a transient current would be induced on the spacecraft structure. Since the time scale of this type of transition is relatively long, on the order of seconds, and the current involved is the plasma current that can be collected by a spacecraft (which is on the order of 0.1A), this transient current will not be a EMI source of any concern. Technical Rationale: Electron beam experiments can generate high levels of conducted and radiated EMI. When an electron beam is injected into the plasma from a spacecraft, a return current must be present in order for the current loop to be completed. The rise time of this return current is determined by the transit time of thermal electrons through the sheath surrounding the spacecraft. This time scale is >0.1 ms (ref. 3 and 4). The upper bound value of the peak return current is given by the peak injected electron beam current. Therefore, the dI/dt of the structure current will be in the range of 108 A/s (assuming a peak current of 10 Amp). For programs that have tests to demonstrate immunity against lightning or ESD inducted structure current, the dI/dt of those test specifications are usually >104 A/ms and thus they envelope the dI/dt induced by electron beam. For a program that has no test specifications for structure current, it should be added to the EMC program if an electron beam experiment is on-board. This is particularly important when the beam current exceeds 10 Amp. The injected electron beam also generates large amplitude waves in the ambient plasma (ref. 5). A comprehensive analysis is needed to determine the maximum amplitude of the beam generated plasma noise. This analysis involves an estimate of the conversion efficiency of the beam energy into electromagnetic wave energy. Usually this conversion efficiency has an upper bound value of 1% (ref. 6). Once the amplitude of the EMI produced by beam generated waves has been determined, the adequacy of the MIL-STD-461C RS03 specifications can be evaluated. Similar approaches can be applied to determine the EMI resulting from the interaction of an ion engine plume and the ambient plasma. References: Hastings, D. and Wang J. (1989), "Induced Emission of Radiation from a Large Space-Station-Like Structure in Ionosphere," AIAA Journal, 27, N4. Wang, J. and Hastings, D. (1991), "A Dynamic Analysis of the Radiation Excitation from the Activation of a Current Collecting System in Space", Journal of Geophysical Research, 93, A3. Singh, N. and Hwang, K. (1988), "Electric Potential Structures and Propagation of Electron Beams Injected From a Spacecraft Into a Plasma", Journal of Geophysical Research, 93, A9. Neubert, T., et al. (1986), "Waves Generated During Electron Beam Emissions from the Space Shuttle", Journal of Geophysical Research, 91, A10. Wincler, J., et al. (1989), "Echo 7: An Electron Beam Experiment in the Magnetosphere," Eos, Transactions, American Geophysical Union, 70, 657. Winglee, R. and Kellog, P. (1990), "Electron Beam Injection During Active Experiments, 1, Electromagnetic Wave Emissions", Journal of Geophysical Research, 95, A5. | This practice has been used on Atmospheric Trace Molecules Observed by Spectroscopy (ATMOS) mission in the ATLAS series. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
711 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Magnetic Field Restraints for Spacecraft Systems and Subsystems |  | If this practice is not followed, appropriate magnetic field restraints on components and systems may not be employed and the resulting magnetic interference could significantly interfere with the proper functioning of magnetic field experiments. Also, any high level magnetic dipole moments would increase magnetic torquing effects and place additional loads on attitude control systems. | Control magnetic field disturbance of spacecraft systems by avoiding the use of components and sub-assemblies with significant magnetic dipole moments. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1222; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Limits magnetic field interference at flight sensor positions and minimizes magnetic dipole moments that can increase magnetic torquing effects that place additional loads on attitude control systems. Implementation Method: A magnetic test procedure has been established which includes separate determinations of the permanent, induced, and stray field magnetization of parts and sub-assemblies. These three conditions represent the prominent sources of spacecraft magnetic field restraint problems. Applied field vectors are utilized to determine the induced magnetic field properties which the spacecraft will experience in orbit. The stray field measurements are designed to differentiate between the power-on vs power-off conditions of operation as well as the shifts in the stray-field levels during operation of the equipment. In the case of the permanent magnetization measurements, the following conditions or states are normally measured: A. Initial Perm - "as received" magnetic state of the item which indicates: one possible level of perm which may exist for a newly manufactured item of the same design. a relative magnitude of the field used to determine the effectiveness of the deperm treatment. the stability of perm by initiating a record of its magnetic history. B. Post Exposure - Magnetic state of the item after exposure to a 15 or 25 gauss D.C. magnetic field which represents the most probable maximum field to which the item is expected to be exposed during the environmental testing. C. Post Deperm - Magnetic state of the item after being demagnetized in a 50 gauss field (normally 60 Hz AC field). Appendix C of Reference 1 provides further data related to methods of demagnetization and compares the results obtained. A substantial amount of test data has been accumulated which relates to the magnitudes of magnetic field for various components normally used in spacecraft systems by indicating the magnetic field disturbance in gamma (10-5 oersted) at a distance of 12 inches from the center of the item. These magnitudes have been measured directly or extrapolated, (by inverse cube) from supplementary distance data. In many cases two or more identical items were measured to insure more representative data; however, in those cases only the maximum value has been listed. In the case of particular components which are required to be non-magnetic, i.e., resistors and connectors, the data is presented for the distance of 2 inches. This data is intended to represent the various magnetic field levels to be expected from the items rather than representing an acceptable or nonacceptance parts list. Magnetic test data has been accumulated from tests of various types of batteries used in flight programs such as IMP, UA-2, OAO, OGO, MMS, and DE. These data show that cells with the nonmagnetic silver cadmium electrodes should be used for spacecraft containing magnetic field experiments. Nickel Cadmium cells should be particularly avoided since these cells have a substantial permanent magnetic field characteristic due to the presence of the nickel material. In the case of other spacecraft where the nonmagnetic requirements are not quite as stringent, it might be more desirable to use the nickel cadmium cells because of their preferred electrical characteristics. While the use of silver cadmium cells will minimize the permanent magnetic field disturbance, their use will not reduce the stray field disturbance which depends on the current flow in the individual cells as well as the combined terminal connection arrangement. Reduction and cancellation of the stray field can be best achieved in those cases where an even number of cells have been combined to form the complete battery pack. Cancellation of the stray field, would be accomplished by combining the cells back-to-back in pairs so that the stray field of one cell effectively opposes that of the other. When an odd number of cells is combined, the stray field of the one unmatched cell can be canceled by adding a supplementary loop of wire which generates a stray field in opposition to that of the single uncompensated cell. Similar magnetic test data has been accumulated for a variety of flight capacitors, connectors, various materials and products such as metals and alloys, electric motors, relays, wiring, etc. These tests were performed a number of years ago and the test samples may not represent some of the materials and components used in more recent years. The magnetic test technique and the approach used in selecting materials with suitable magnetic characteristics can provide a guide to the testing and selection of newer materials and components. References 1, 2 and 3 provide more details on the testing and include many tables of test data. Technical Rationale: The problem associated with magnetic field restraints for components and spacecraft vary according to the spacecraft program requirements. Those spacecraft which include magnetic field experiments must control and limit the magnetic field disturbance of the integrated spacecraft so that no undue magnetic field interference will occur at the flight sensor positions. In the case of spacecraft which employ magnetic or gravity gradient attitude control systems, the magnetic restraint problems are normally not as stringent; however, all spacecraft designers should avoid the use of components and sub-assemblies with significant magnetic moments since these will increase magnetic torquing effects and place additional loads on the attitude control system. This practice is primarily intended for use by spacecraft programs subject to magnetic field restraints, i.e., spacecraft containing magnetic field experiments or magnetic attitude control systems. Accordingly it can be used as a guide in the magnetic testing, assessment, and selection of parts and materials to be used by such programs. References: "Magnetic Field Restraints For Spacecraft Systems And Subsystems," Dated February 1967, GSFC Document No. X-325-67-70 Supplement 1 (1971) to "Magnetic Field Restraints For Pacemaker Systems and Subsystems," Dated December 1971, GSFC Document No. X-325-71-488 "Spacecraft Magnetic Test Facility (Attitude Control Test Facility)," Dated April 1984, GSFC Document No. X-754-83-9 Reliability Preferred Practice No. PD-ED-1207, "Magnetic Design Control For Science Instruments" Unit Conversions: 1 gauss = .1 millitesla (mT) 1 oersted = 79.57747 ampere/meter (A/m) 1 inch = 2.54 centimeter (cm) | This practice has been used on OGO, EPE-D, IMP, Pioneer, AE-B, ATS, DME, OAO, ISTP, GRO, EUVE, Ulysses. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
709 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Class S Parts in High Reliability Applications | Preferred Practice for Design & Test. Low parts failure rates associated with Class S Parts in typical circuit applications result in a significant enhancement in system reliability. Use Class S and Grade 1 or equivalent parts in all applications requiring high reliability or long life (>3 years) to yield the lowest possible failure rates. | Figure 1 shows an analysis of a typical radio and digital subsystem for a flight instrument with a 3- year mission, no redundancy (except TWTs), and partial redundancy in critical circuits for both Class S and B parts. The parts count method provided in MIL-HDBK-217E was applied. These calculations are not considered accurate for any usage in an absolute sense, due to other design and test factors the database cannot estimate. However, relative comparisons are very useful and accurate for tradeoff studies of effects of redundancy and parts classifications. [D] The data are presented in graphical format for ease of understanding. On each plot, the basic reliability for the assumed conditions is plotted on the left ordinate, years are plotted on the abscissa, and the ratio of the analyzed condition is plotted on the right ordinate. In a single-string (nonredundant) design like Figure 1, the decline in system reliability over time is much less for a system built entirely of Class S parts than if it were built of Class B parts. The ratio of the two reliabilities for a 5-year mission indicates the system built of Class S parts is 50 times more reliable than the system built of Class B parts. When critical system circuits are made redundant, the time dependent reliability with both Class S and B parts is improved, but the improvement for the system built with B parts is greater (Figure 2). However, the 5-year mission reliability for the system built with B parts is still 20 times less than for the system built with Class S parts. [D] A correlation is made between the single string (nonredundant) system built with Class S parts and the system with redundant critical circuits and Class B parts (Figure 3). In this correlation, it is clear that for a 5-year mission the single-string system with Class S parts was still 10 times more reliable than the system with redundancy made from Class B parts. [D] This example reflects that the payoff in reliability is significant for Class S parts compared to Class B parts (for a 5-year mission, Class S is 20 to 50 times more reliable depending on redundancy). Additionally, the return on reliability, addressing non-random failures, is higher for Class S parts than for redundancy used with Class B parts. The highest reliability is obtained with Class S parts with redundancy in the critical circuits. | Use Class S and Grade 1 or equivalent parts in all applications requiring high reliability or long life to yield the lowest possible failure rates. (Long life is defined as a requirement to perform the defined function without sacrifice to the primary mission objectives for a period longer than 3 years. Criticality of a function may require high reliability for any period of time and is not necessarily coupled to long life. However, when high reliability is coupled with long life, increased attention to the best reliability design practices is appropriate.) | JPL | 01/30/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1203; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Low parts failure rates in typical circuit applications result in significant system reliability enhancement. For space systems involving serviceability, the mean-time-between-failure (MTBF)is greatly extended, which significantly reduces maintenance requirements and crew time demands. Implementation Method: Redundancy is an appropriate usage of resources-- especially in critical applications to protect against random failures -- but is not a justification for using less than Class S or quotequivalentquot parts. Establish a policy that Class S parts will be used without exception or that limited exceptions are only permitted with extensive testing and inspections for upgrading of Class B to an acceptable level (approximately Class S or Grade 1). Technical Rationale: Basic reliability is a function of parts failure rates. In any analytical calculations of reliability, the usage conditions of parts (derating, temperature, stress, etc.) are expressed as a failure rate that integrates these conditions from empirical or analytical considerations. High reliability parts (Class S or Grade 1) are screened and tested to yield the lowest failure rate parts producible in large quantities. (Refer to Table 1 for the relationship of Class S to Class B). The failure rates of Class S parts are generally about one fourth the rates for Class B. When parts failure rates are coupled into circuit applications, the effects can be significantly magnified, depending on the circuit configuration. ISSUE CLASS S CLASS B IMPACT Wafer lotacceptance Required ---------- Uniformity and pedigreetraceability Certification ofproduction facilities To specificassemblylines To technologiesand generalfacilities only Burn-in and screening valuerelates to consistency of originalproduct Precap internalinspection 100% Sampled Significant driver on level ofreliability - criteria much morestringent in MIL-M-38510H PIND for looseparticle detection Required ---------- Loose metallics in zero g field cancause failures Serialization Required ---------- Traceability lost Interim electricaltest between testphases Required ---------- Potential of passing overproblems and their causes Burn-in 240 hours 160 hours Later problem discovery Reverse biasburn in Required ---------- Impurity migration not detected Interim electricaltest after reversebias burn Required ---------- Effects of reverse bias burn-inmay be masked by subsequentactions Radiographicinspection Required ---------- Observation of latent defects Nondestructive100% bond pull test 100% Sampled Parts with mechanical deficiencesget into equipment When spaceflight equipment is not serviceable in a system requiring high reliability and long life, the lowest possible failure rate parts should be selected. This is especially true when considering the economics associated with the launch costs. For example, when changing from Class S to Class B parts, the parts cost decreases by a factor of 4x to 10x but the reliability of the system decreases significantly (by 20 to 50 times in the typical 5-year mission example provided). When total system, mission operations, and launch costs are considered, the delta between the parts costs for Class S and Class B is a minute percentage of total cost. This is especially true for Space Shuttle payloads. On systems that are serviceable, the MTBF of an assembly is extended in proportion to the basic failure expectation. This significantly longer MTBF reduces on-orbit service requirements with less time demands on the crew, less risk associated with extravehicular activity (EVA), fewer spares required, and fewer launches to transport spares. Redundancy has a much lower reliability payoff than does parts class-- until it is needed. Maverick parts, workmanship flaws, and other uncertainties justify redundancy for critical circuits in high reliability, long life applications to protect against random failures. For long life, the use of high reliability hardware, Class S (or Grade 1) parts, and redundancy in critical applications, provide an optimum and cost-effective approach. | This practice has been used on Viking, Voyager, and Galileo. | N/A |  | Aeronautics Research, Science | Public | Not Specified |  | 03/16/2000
710 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | EMC Guideline for Payloads, Subsystems, and Components |  | Not establishing EMC design and test requirements for space hardware and payloads could lead to an adverse affect of its own subsystems or components or the safety of the launch vehicle or launch site. | Guidance is provided for establishing design and test requirements for the control of electromagnetic emission and susceptibility characteristics of space hardware and payloads. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline number GT-TE-2401 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Implementing the Guideline provides the following technical controls in the Electromagnetic Compatibility characteristics of hardware: a. The payload and its elements do not generate electromagnetic interference that could adversely affect its own subsystems and components or the safety and operation of the launch vehicle (STS or ELV), or the launch site. b. The payload and its subsystems are not susceptible to emissions that could adversely affect their safety and performance. This applies whether the emissions are self-generated or derived from other sources, or whether they are intentional or unintentional. Implementation Method: Electromagnetic compatibility requirements have been established to ensure that a payload or its elements do not generate electromagnetic interference that can adversely affect its own subsystems and components, or other payloads, or the safety and operation of the launch vehicle (STS or ELV) and launch site. Additionally, the payload (spacecraft) and its subsystems and components should not be susceptible to emissions that could adversely affect their safety and performance. This applies whether the emissions are self-generated or emanate from other sources, or whether they are intentional or unintentional. The Guideline consists of verification requirements in each of the following categories: conducted emissions, conducted susceptibility, radiated emissions, and radiated susceptibility. Most of these requirements are taken from the widely used MIL-STD-461, 462, and 463 EMC specifications and have been tailored by the GSFC for space flight application and incorporated into the GSFC's General Environmental Verification Specifications For STS & ELV Payloads, Subsystems, and Components (GEVS-SE). The Guideline also incorporates the applicable EMC requirements defined in the Shuttle Orbital/Cargo Standard Interfaces Document (JSC 07700 Volume XIV Attachment 1 (ICD 2-19001). These EMC test requirements when performed as a set are intended to provide an adequate measure of hardware quality and workmanship. The tests are performed to fixed levels which are intended to envelope those that may be expected during a typical mission and allow for some degradation of the hardware during the mission. The levels are tailored by the user to meet mission specific requirements, such as the enveloping of launch vehicle and launch site environments, or the inclusion of very sensitive detectors or instruments in the payload. The following table is a matrix of EMC tests that apply to a wide range of hardware intended for launch either by the STS or an expendable launch vehicle (ELV). Tests are prescribed at the component, subsystem, and payload levels of assembly. Not all tests apply to all levels of assembly or to all types of payloads. A project or hardware designer must select the requirements that fit the characteristics of the mission and the hardware, e.g., a transmitter would require a different group of EMC tests than a receiver. Symbols in the hardware levels of assembly columns assist in the selection of an appropriate EMC test program. Table 1. EMC Requirements per Level of Assembly Type Test STS ELV Component Subsystem/ Instrument Payload* Spacecraft CE DC power leads X X Sb,Rb,R Sb,Rb,R Sb CE AC power leads X Sb,Rb Sb,Rb Sb CE Spikes on orbiter DC power lines X Sb Sb Sb CE Spikes on orbiter AC power lines X Sb Sb Sb CE Antenna terminals X X R - - RE Magnetic fields (STS payloads) X - - Sb RE AC magnetic field X X Rb,R Rb,R Rb,R RE E-fields X X Rb,R Rb,R Sd,Rb,R RE Payload transmitters X X - - Sd,** RE Spurious (transmitter antenna) X X - Rb,R - CS Power line X X Rb,R Rb,R Rb CS Intermodulation products X X Rb,R - - CS Signal rejection X X Rb,R - - CS Cross modulation X X Rb,R - - CS Power line transients X X Rb,R Rb,R Rb RS E-field (general compatibility) X X Rb,R Rb,R Rb,R RS Compatibility with orbiter transmitters X - - Rb RS Orbiter unintentional E-field X - - Rb RS Magnetic-field susceptibility X X Rb,R Rb,R Rb,R RS Magnetic properties X X R R R CE - Conducted Emission CS - Conducted Susceptibility R - Test to insure reliable operation of payload, and to help ensure compatibility with the launch vehicle and launch site Rb - Test to ensure reliable operation of orbiter attached payloads RE - Radiated emission RS - Radiated Susceptibility Sb - Items interfacing with orbiter power in payload bay or in the cabin: required by ICD 2-19001 Sd - Items operating on or near orbiter: required by ICD 2-19001 * - Payload, Mission, or highest level of assembly ** - Must meet any unique requirement of launch vehicle and launch site for transmitters that are on during launch Once the program is selected, all flight hardware is tested. The EMC test program is meant to uncover workmanship defects and unit-to-unit variations in electromagnetic characteristics, as well as design flaws. The qualification and flight acceptance EMC programs are the same. Performance of both will provide a margin of hardware reliability. A wide range of EMC test requirements are provided to cover a variety of free flyer and shuttle-attached operating modes. For example, some free flyers will be operated with the orbiter during prerelease and checkout procedures and must be tested to ensure EMC with the orbiter. In other cases, the most stringent EMC requirements can occur after the free flyer moves away from the orbiter when it or its sensitive instruments can become susceptible to the operation of its own subsystems. Because some free flyers will not be operated or checked out before release from the orbiter, they do not have to meet the orbiter EMC requirement and the tests need only ensure self-compatibility and survival to exposure to the high-level emissions from the orbiter's transmitters. Requirements are also provided for attached payloads that may be subjected throughout the mission to EMI from the orbiter and from other payloads. It is recommended that testing be performed at the component, subsystem, and payload levels of assembly. Testing at lower levels of assembly has many advantages: it uncovers problems early in the program when they are less costly to correct and less disruptive to the program schedule; it characterizes box-to-box EMI performance, providing a baseline that can be used to alert the project to potential problems at higher levels of assembly: and it aids in troubleshooting. The tests and their limits are considered minimum requirements, however they may be revised as appropriate for a particular payload or mission. Technical Rationale: The Guideline presents EMC verification requirements for GSFC payloads, subsystems, and components and includes a baseline for demonstrating by test satisfactory performance of hardware in the expected mission environments. The Guideline includes the applicable requirements for Shuttle carried hardware. References: General Environmental Verification Specification for STS & ELV Payloads, Subsystems, And Components (GEVS-SE) Shuttle Orbiter/Cargo Standard Interfaces Document (JSC 07700 Volume XIV Attachment 1 (ICD 2-19001). Power Line Filters - Reliability Preferred Practice No. PD-ED-1206 Electrical Shielding Of Power, Signal, and Control Cables - Reliability Preferred Practice No. PD-ED-1213 |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
713 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Vehicle Integration/Tolerance Buildup Practices |  | The principal effect of nonadherence to proven and verified vehicle hardware integration and tolerance specification practices is the potential delay and attendant costs that would be encountered either in the factory or in the field due to the attempted mating or assembly of parts that do not fit together properly. In such cases, waivers need to be obtained, parts may need to be exchanged, or factory/field modification may be required. The effects of specifying tolerances that are too stringent for the application are increased machining, inspection, and shipping protection time and costs. Since tolerances that are either too tight or too loose can create schedule and cost impacts, optimum tolerances and related tooling provisions must be derived for each specific application. | Use master gauges, tooling, jigs, and fixtures to transfer precise dimensions to ensure accurate mating of interfacing aerospace hardware. Calculate overall worst-case tolerances using the root sum square method of element tolerances when integrating multiple elements of aerospace hardware. | MSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1219; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Using prudent and carefully planned methods for specifying tolerances and for designing, manufacturing and mating major elements of aerospace hardware, will result in a cost-effective program with minimal rejects and waivers, and will avoid costly schedule delays due to potential mismatching or misfitting of major components and assemblies. Implementation Method: Introduction: Elements of large aerospace hardware, such as those encountered in the Space Shuttle program, are often (1) manufactured in diverse locations; (2) manufactured and assembled by different centers, prime contractors, and subcontractors; and (3) manufactured and assembled in varying climates and environments. Several additional factors must be considered in establishing design tolerances and in providing jigs and fixtures to assure that the major elements can be mated successfully prior to launch. Specifically, the size and weight of these major components and assemblies (such as the ET and SRB) are so great that special consideration must be given to hardware deflection and deformation due to vehicle mass; wind loads; and environmental factors, such as temperature, humidity, and atmospheric contamination. A variety of methods of calculating and allowing for tolerance buildup and for ensuring matching components at the assembly site have been developed to meet the specific needs of these large hardware elements of the Space Shuttle program. No one method suits all needs. In some instances (in the ET project, for example), the overall tolerance between major critical dimensions is the sum of all of the quotworst-casequot tolerances of the subassemblies. In the SRB project, for example, the root sum square of the tolerances of segments is used to arrive at the tolerance on major critical dimensions. In addition, adjustable supports are used at critical attach points to permit minor variations in matching and assembling these two major Space Shuttle hardware elements. This practice provides selected methods that have proven successful in ensuring that major elements of aerospace hardware will be successfully and accurately assembled both in the factory and in the field; and it provides methods and definitions of dimension and tolerance buildup practices that have proven successful in designing, building, and flying large aerospace vehicles. Master Tooling/Jigs And Fixtures: Master tooling should be used when machining a number of interchangeable parts to ensure that each part will fit and function properly. Another method of assuring interchangeability of parts during manufacturing is through the use of jigs or fixtures. This method is used primarily when an operation such as welding, drilling, or reaming is performed by hand on interchangeable parts. Example: Thiokol, Inc. is under contract to NASA MSFC to fabricate the motor segments of the SRB. These segments must fit together precisely when they are assembled at KSC; therefore, each segment must be indexed when it is manufactured by drilling the indexing holes in the tang and clevis joints of the Solid Rocket Motor (SRM) segment using a master tool. All of the master tools are made from transfer gauges, and the transfer gauges are made from a master gauge, resulting in the same indexing regardless of where the segments are manufactured (see Figure 1). [D] [D]Master Gauge: The master gauge is a stable, heavy cast iron fixture into which the master interface hole pattern has been precision bored. The bored holes are lined with pressed-in, hardened bushings (see Figure 2). The exact location of each hole is determined by independent inspection and is entered on the master gauge drawing as a basic no-tolerance dimension. This drawing, and the master gauge it depicts, describe and establish the mastered hole pattern. The master gauge is used as a template when bushings are potted into the transfer gauge. Transfer Gauge: Transfer gauges are stable, rigid fixtures into which hardened bushings are potted with an epoxy compound. During potting, the bushings for the transfer gauge are held in the correct position by potting pins located in the master gauge. (As shown in Figure 2), transfer gauge is fitted over the master gauge before potting, and the transfer gauge bushings are located precisely before potting using the potting pins. After the potting material has cured, check pins are inserted first through the master tool and then through the new bushing location. Master Tool/Drill Jig: [D] Master tools are fixtures into which hardened bushings are potted with an epoxy compound. The transfer gauge is used as a template when bushing are potted in the master tool (see Figure 3). The bushings are held in position by the transfer gauge and potting pins. After the potting material has cured, check pins are inserted through the transfer gauge into the master tool to verify the location of the potted bushings. Master tools are used as drill jigs to assure that the assembly holes and pins and the indexing holes and pins in the tangs and clevis joints of the SRM segments are precisely the same (see Figure 4). Master tools are made from the same material as the SRB segment casings. Therefore, the coefficient of expansion is the same for both. It is critical that the master tools and the SRB segments be subjected to the same environment until they stabilize with the area temperature before attempting to mate them or initiate drilling. Inspection pins are used to verify hole locations in the SRM segment relative to the master tool. Mobile Launch Platform (MLP) Preparation for SRB Stack: [D] The support post #2 under the MLP is adjusted to a certain height in reference to a benchmark in the Vehicle Assembly Building (VAB). There is a corresponding support post #2 and benchmark at the launch pad. Once support post #2 has been adjusted to the correct height, a triangular reference plane is established using two other points under the MLP. This reference plane is then transferred to the top of the MLP. The eight support posts (four per SRB) are then adjusted by the following means: Shims are added between each support post and the haunch which is permanently attached to the MLP to raise the support post to a reasonable height. Shims may be added under each spherical bearing for height adjustment up to a maximum of 0.5quot (see Figure 5). Eccentric bushings and the eccentric spherical bearings are rotated to bring them into alignment with a bias to give the SRBs a very slight inward pitch (towards ET). The bearings are then locked so they cannot move when the SRB aft skirt is installed. SRB Stacking: [D] The SRBs are stacked on the spherical bearings on the MLP in five separate sections, one section at a time. The aft skirt, kick ring, and aft motor segment are preassembled in another area and stacked on the MLP as the aft booster assembly. The aft center segment is then stacked on top of the aft booster assembly. The forward center segment is stacked on top of the aft center segment. The forward motor segment is stacked on top of the forward center segment. The forward skirt, separation ring, frustum and nose cap are also preassembled and stacked on top of the forward motor segment as one unit. All of these sections make up one SRB. The fit of one section with the next is ensured because their mating parts (tangs and clevis joints) were all drilled using a master tool. There is no alignment adjustment between the sections and the deviation from vertical in the quotyquot plane is +0.8299quot per stack. Tolerance Buildup Practices: External Tank: In the External Tank project, manufacturing drawings have tighter tolerances than the interface control documents (ICD) to eliminate the need for waivers if tolerances are exceeded slightly. The ICD tolerance for the overall length of the external tank (ET) is +0.74quot, while the manufacture drawing tolerance is +0.62quot. The ET assembly drawing overall length tolerance represents the worst-case stack-up of the major ET assemblies, and the lower level assembly drawings use the same philosophy. For instance, the aft dome roundness is +0.50quot, the barrel attach points are +0.02quot, the machined and fabricated (formed) parts are +0.03quot, and thin sections are +0.10quot. ET design engineers strive for tolerances of fabrication tools up to 10 times better than the flight hardware tolerances. For example, if the target tolerance on a part is +0.1quot, engineers strive to make the tool tolerance +0.01quot. If the worst-case tolerance on a part is +0.1quot, they strive to make the tool worst case tolerance +0.05quot, or no greater than one-half of the part tolerances. ET design engineers use the ANSI Standard for Dimensioning and Tolerancing for block tolerances; i.e., x.x=+0.10quot, x.xx=+0.03quot, x.xxx=+0.010quot, and x.xxxx=+0.000xquot. In some instances, match drilling is used during ET fabrication to ensure a perfect fit rather than using machine-to-drawing holes which would require a very tight tolerance on the machining process. Methods of Calculating Tolerance Buildup: In aerospace hardware, two methods are normally used to calculate tolerance buildup. They are the root sum square (RSS) method and the root mean square (RMS) method. Each seems to serve best for particular applications. The RSS method is generally used for calculating the tolerance buildup of large pieces of hardware like the SRBs when they are assembled at KSC. This method of tolerance buildup assumes a random ordering of the various combinations of the interface theoretical tolerances and resulting misalignments. The following formula is used for RSS calculations: [D] Where: A, B, C, and D are the tolerances of mating segments of an assembly. The RMS method is generally used in calculating the tolerances of piece parts for small assemblies such as pumps and valves. The RMS method is also used in connection with surface roughness. The roughness value is assumed to be approximately equal to the square root of the mean value of the squares of the heights and depths of the surface roughness irregularities measured from the nominal surface in micro-inches. This value is considered to be representative of the surface condition because it is assumed to give appropriate emphasis to the peaks and valleys comprising the surface. The following formula is used for RMS calculations: [D] Where: A, B, C, and D are the tolerances of mating segments of an assembly, and N is the number of tolerances. Environmental and Physical Factors: When designing a part and establishing tolerances, it is important to consider both the environment where the part is initially manufactured and assembled, and the environment where the part may have to be replaced or reassembled. Factors to be considered include assumptions as to whether the part has to be disassembled and reassembled at a later time and/or different location from the initial assembly. Tolerances of the part will be determined by expected variations in temperature, material, coefficient of expansion, humidity, wind load, or cleanliness. Example: Several precision components such as the LO2 and LH2 pumps and valves in the Space Shuttle Main Engine may be assembled initially in a clean environment of 68 degrees and low humidity. If it is anticipated that one of these parts may have to be replaced on the launch pad at KSC, the fit of its parts could be affected if the temperature was 98 degrees and the humidity 95 percent, if the wind was blowing at 45 mph, or if sand and dirt were present in the local atmosphere. Potential Cost/Schedule Impact Avoidance: Cost and schedule are two of the most important factors to consider when establishing tolerances. Designers should never specify a tighter tolerance on any part or component than is absolutely necessary for that part to fit and function properly. Tighter tolerances require more precise machining, and result in potential scrappage of parts or components at inspection. Excessively tight tolerances also require more time for machine setup and machining as well as extra time for inspection. The loss of material, the extra time for machining and inspection, and the potential overtime required to meet a schedule can result in higher overall costs. Example: The critical mating surfaces for interface mounting flanges designed for a pump or valve are required to be flat within .002quot. If the designer were to unnecessarily require the same tight tolerance on the size and location of the mounting holes, flanges could be unnecessarily rejected if the holes did not meet the specifications. This could increase the cost of the flanges because of the wasted material and machining time. Technical Rationale: The rationale for tolerancing is to assure that the majority of small and large parts will fit and function as they were designed to when they finally come together as an overall assembly. It is also essential that these parts can be disassembled and reassembled if necessary under less than ideal conditions with the minimum amount of effort in the least amount of time. The selected tolerance buildup and hardware integration approaches described in this practice have evolved over the past four decades of developing launch vehicles and their related propulsion systems and structures. Minor deviations have been made from standard ANSI practices in instances where the prior U. S. standards were not applicable to large aerospace hardware components, subassemblies, and assemblies. Specific design requirements, specifications, and procedures are described in detail in the references and in documents identified in the references. References: ANSI Standard for Dimensioning and Tolerancing Y14.5M 1982, published 1983, The American Society of Mechanical Engineers, United Engineering Center, 345 East 47th Street, New York, NY 10017. External Tank Tolerance Control Drawing Number 82600209001, W.E. Warren, May 24, 1974, Martin Marietta Corporation, P. O. Box 179, Denver CO 80201. Modern Geometric Dimensioning and Tolerancing, Second Edition, 1982, Lowell Foster, National Tooling and Machining Association, 9300 Livingston Road, Fort Washington, MD 20744, Catalog Number 5021. Space Shuttle Stacking Tolerance and Mating Assessment for (MLP/ASRB/ET) 20ENR-0001, S. Fisher, July 30, 1991, United Technologies USBI, P. O. Box 1900, Huntsville, AL 35807. Space Shuttle Vehicle MLP/SRB/ET Stacking Tolerancing and Mating Assessment, 30A90507, Bill Cole, March 4, 1977, National Aeronautics and Space Administration, George C. Marshall Space Flight Center, Huntsville, AL. | This practice has been used on Saturn I and Saturn V, Space Shuttle External Tank (ET), and Space Shuttle Solid Rocket Booster (SRB) programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
712 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Design Considerations for Fluid Tubing Systems |  | Noncompliance may result in fluid system failures resulting in collateral damage to surrounding hardware and jeopardizing of mission success. | The above practice delineates basic criteria for use in the design of fluid tubing systems for use on space flight equipment. These criteria are meant to enhance reliability and maintainability of these systems through standardized practices in design. | JSC | 02/01/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1224; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: By using standard military and industry-accepted tubing design criteria, the overall design of a system consisting of tubing will achieve maximum reliability, producibility, and safety at a minimum cost. Implementation Method: CONFIGURATION DESIGN Configuration design considerations of tubing systems should be coordinated among the engineering disciplines (structures, electrical, mechanical, etc.) that will be affected by the proposed paths of the tubing systems. Mockups and/or interface control drawings (ICD's) should be used in an interactive, iterative manner to verify outside tube diameter, bend radii, and end connector locations and interfaces. Drawings used during the configuration design phase should be to a level of detail which will accurately show all applicable equipment, structures, and general clearances (such as tubing support spacing) in order to accurately assess the acuteness of space limitations and effective tube lengths. Design layouts of tubing systems should allow for on-orbit access for maintenance, inspections, and removability if necessary. Electrical lines and their acceptable proximity to tubing paths should be fully assessed in accordance with operational parameters of the systems and the effects of failure of each system upon the other. Design elements such as material selection, tube fittings and routing, and maintenance properties must receive special consideration in systems using corrosive fluids. Tube routing should follow straight paths, avoiding bends and fittings whenever possible, thus avoiding flow head losses associated with such configurations. In routing straight tubes between fixed points, thorough consideration should be given to tube length tolerances needed because of thermal and pressure differential induced stresses, structural/mechanical movement, vibrational movement, and end fitting thermal expansion induced stress differentials. Supports should be designed and implemented in such a way as not to overrestrict or underrestrict motion of tubing via proper material selection, structural design, and interval placement onto the tubing. Additionally, manufacturing, maintenance, inspection, and fabrication limitations should be considered during layout configuration. MATERIAL SELECTION Material selection for tubing should be compatible with the intended use of the tubing, its surrounding environment, and fluid commodity it is intended to carry. Special consideration should be given to offgassing properties in a space flight environment; corrosion/stress corrosion susceptibility (such as defined in Reference 1) for both the tubing, associated support structures, blind fasteners; and the effects of using dissimilar materials as exemplified in References 2 and 3. Additionally, a minimum of different types of tubing materials and sizes should be used to lower production costs and increase the reliability and safety of the system. All tubing used in a flight environment should be of a seamless configuration. BENDS In many design applications, tube bending will be necessary to compensate for relatively large induced thermal contraction or expansion stresses, to act as equal distant pressure manifolds, or to route around adjacent hardware in the surrounding configuration. Therefore, when tube bending is necessary, the linear distance from the end of the tube to the bend or from a fitting to a bend should be as great as possible. Bends in close linear proximity to one another along a common tube are not desirable because of the increase of stress concentrations in the area of the end of a tube and the bend, increased fabrication time to make the piece, and a possibility of high scrap rates during fabrication. When the bending of tubing is necessary, the bend radius is an important consideration. Factors governing the bend radius limitations of the tubing are: tubing material properties, tube wall thickness (WT), outside tube diameter (OD), and internal pressure differentials. The WT/OD ratio will place limitations on the degree of bending allowable because of inside bend radius buckling and outside bend radius stretching. Material properties, microscopic grain structure, and annealing processes will additionally limit the degree of bending. Common and current industry and military standards that are sufficient for orbital conditions should be consulted to determine the minimum and maximum bend radii allowable for tubing as a function of these considerations. Additionally, the selected standards should delineate the amount of ovalization ("out of roundness") allowable as a function of internal pressure and tubing material. The amount of tubing ovalization will usually be defined in terms of tube flatness and given as a percent of original outside diameter. As a rule of thumb, most standards will not allow a minimum bend radius of less than three times the outside diameter of the tubing because of excessive tubing ovalization as exemplified in Reference 4. COIL MOTION Coil motion tubing should be installed into a system such that the tubing is in a relaxed, unstressed position. The coil design should be such that motion of the tubing is concentric about the centerline of the tubing coils. Additionally, the motion should not adversely affect tube fittings, overly stress the tubing, or cause damage to surrounding equipment. Specific individual material property characteristics should be considered when designing coil motion systems. Proper coil pitch distances should be decided upon after consultation with current military standards. UNDESIRABLE PLASTIC DEFORMATION During the cold forming of a tube bend radius, care should be taken to minimize the degree of material buckling occurring in the inside portion of the bend radius. Buckling in this area reduces the strength of the tubing and could cause transition turbulence in flows with relatively high Reynolds numbers. Additionally, caution should be taken to minimize the degree of tubing ovalization. Ovalization creates a situation of hoop stress concentrations in tubing walls that could give way to lengthwise splitting of the tubing wall. Precautions such as the use of appropriate bending shoes should be used to minimize ovalization. SPRINGBACK During the cold forming process of tube bending, most materials will exhibit a springback characteristic when bent into the plastic deformation region of the material. Structurally, the degree of springback varies as a function of the WT/OD ratio, the degree of the bend, and the bend angle and radius. The finished bend radius should be coupled with the appropriate bending shoes, internal tube mandrills, and applicable standards delineating finished bend radius as a function of tube WT/OD ratio, and tubing material. PROOF PRESSURE As a minimum, each tube and tubing assembly should be exposed to a proof pressure testing procedure consistent with the pressures, pressure cycles, and temperature gradients that the part will experience. Standards for proof testing should be consistent with current appropriate standards. The part must be able to withstand the test without any evidence of premature failure. Using appropriate liquid or gaseous testing mediums, the test should verify that the tubing material and applicable fitting(s) are sound and leak free based upon the requirements of the applicable design drawing and project. The designer should take measures to ensure that the drawing or specification delineating the fabrication details of the part contains requirements for proof and leak testing of all parts, usually at minimum and maximum fluid operating temperatures. For example, the Space Shuttle Program assigns general minimum factors of safety for proof pressure and ultimate pressure testing at 4.0 times the maximum operating pressure (MOP) for tubing less than 1.5 inches in outside diameter, and at 1.5 times MOP for tubing greater than 1.5 inches in diameter (References 5 and 6). TUBE FITTINGS Standard and NASA approved tubing fittings should be used whenever possible to avoid excessive use of nonstandard part types and the manufacture of nonstandard tube endings. Unless otherwise necessary, tube fittings should be of the same material as the tube and adjoining fittings. Use of dissimilar materials should be strongly weighed with respect to material incompatibilities, differential thermal properties, and possible dielectric incompatibilities. Offgassing properties should also be evaluated for all materials used in tube fittings when used in space flight situations. Tube ends and tube fitting interfaces should be free of burrs both inside and outside the tubing. Tubing ends should be finished square, within tolerance limits well defined by the designer and consistent with current engineering standards as applicable. Additionally, surfaces should be cleaned within tolerances for foreign particulate presence defined by the engineering organization for the intended use of the part. All welded surfaces should be fabricated in a fashion that applies military standards with considerations for flight and space environments. For the purposes of this document, extensive discussion of mechanical and welded fittings is left to related standards, practices, and other documentation. Technical Rationale: Use of this practice as a standard will result in a higher degree of design and configuration coherency than previously realized. Engineering judgments can be baselined according to military and industrial standard practices such as References 7 and 8. This practice is not all-inclusive; special care and sound engineering judgments must be made when tubing is being used for high-velocity liquid and gaseous substances and in applications where comparatively large cross-sectional-average Reynolds numbers are present. The latter is especially true, since flows that possess Reynolds numbers near 2300 may be transitioning from laminar to turbulent flow conditions, creating a condition of quasi-steady flow. Additionally, special considerations should be exercised and explored for orbital and space environments. Specific standards are revised as lessons are learned and technologies change. The most current standards should be cited when designing fluid systems, and sound engineering judgment should be exercised when deciding which standard will be consistently applied to a given project. References: KSC-SPEC-Z-0007C, "Specification for Tubing, Steel, Corrosion Resistant, Types 304 and 316, Seamless, Annealed." MSFC-SPEC-250, "Protective Finishes for Space Vehicle Structures." KSC-STD-C-0001B, "Standard for Protective Coating of Carbon Structures." MS33611, "Tube Bend Radii." NSTS 07700, "Program Definition and Requirements." NSTS 08318, "NSTS Hydraulic System Exceptions to MIL-H-5440." MIL-F-45764C, "Fabrication and Installation of Fluid Lines and Fittings for Missiles and related Ground Equipment." MIL-H-5440G, "Design and Installation Requirements for Hydraulic Systems, Aircraft, Types I and II." Schlichting, H., "Boundary-Layer Theory (Grenzschicht-Theorie)," 1979, McGraw-Hill Book Company, New York, New York. Boyerk, H., Gall, T., "Metals Handbook," 1985, American Society for Metals, Metals Park, Ohio. "Installation Considerations for Fluid Tubing Systems", Reliability Preferred Practice GD-ED-2208 | This practice has been used on Space Shuttle | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
715 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Near Field Measurement for Large Aperature Antenna Pattern Determination |  | Failure to use near field measurements for determining far field patterns of high frequency, large aperture antennas, constrains testing due to exposure of test antenna to weather. In addition, test results can may be influenced by local weather conditions and the existence of uncontrolled reflections from traffic within the region of the test path. | Use near field antenna measurement facilities for determination of far field antenna patterns of large aperture, high frequency antennas (For the purposes of this Guideline, quotlarge aperture, high frequency antennasquot are those antennas for which the far field (D2/l) distance exceeds reasonable building size and/or controlled range space. See Technical Rationale in this Guideline.) This guideline supports reliable communications with spacecraft. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GT-TE-2402 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: For high frequency, large aperture antennas, near field antenna facilities provide more timely, cost effective, and efficient pattern measurements resulting in the following benefits: protection for environmentally (and gravitationally) sensitive antennas from elements such as wind, rain, smog, wildlife, etc.; characterization of complete far field pattern over region corresponding to sampled near field; measurements are not affected by weather or uncontrolled reflections; diagnostic capability for feed misalignment, phased array element amplitude and phase excitation, holographic determination of reflector surface accuracy; and depending on range geometry, accurate characterization of far sidelobes and backlobe patterns; accurate far-field pattern construction of both co- and cross-polarization patterns from the same set of near field data. Implementation Method: The implementation of near field antenna measurements for the determination of far field antenna patterns involves the following. A near-field probe is placed in close proximity to an antenna under test. The probe or test antenna or both are moved in such a manner that a set of complex field measurements can be made at known locations, with respect to the test antenna. The surface containing the measurements should, in general, completely enclose the antenna. However, for most directional (larger aperture) antennas, an abbreviated plane, which intercepts all but a small percentage of the radiated energy, can be used, resulting in negligible loss in accuracy. A spherical, cylindrical, planar, or other convenient surface can be used. At each measurement point, on the measurement surface, the complex field and position are measured. The set of measurements are transformed, via near-field to far field transformation algorithms, to obtain the far field patterns for the test antenna. The near field antenna test facility at LeRC is in an in-door, environmentally controlled test area. The facility contains a moveable antenna mount that is used to orient and position the antenna and a structure used to move the near-field probe within a 22 ft x 22 ft vertical plane. The facility is designed to test antennas with horizontal orientation of the antenna boresite. A block diagram of the LeRC Near Facility is shown in Figure 1, below. [D] A laser distance measuring system, shown in Figure 1, is used to measure x and y position of the probe in the scan plane. The complex electric field is measured at each measurement point in the scan plane using a Hewlett Packard 8510 automated network analyzer; and Hewlett Packard 8340 frequency synthesizers are used to provide RF and local oscillator signal sources. Fiber optic links are used to distribute local oscillator signal to RHG mixers. The data acquisition and system control are performed by an on-site computer. Data processing is performed in an offsite computer facility. The LeRC near field test facility was designed for frequencies of operation from 0.8 GHz to 60 GHz. The scanner can test antennas having a D/l to 1100 for antenna apertures up to 18 ft. D is a characteristic dimension of the test antenna (i.e. diameter for a circular aperture antenna), andl is the wavelength for the antenna operating frequency. For detailed description of design, operation and performance see references 1, 2, and 3. Other near field antenna test facilities within NASA (see Appendix) are located at JPL, and JSC. In selecting a near field range for antenna testing, just as in selecting a far field range, attention must be given to the determination of measurement uncertainty. This can be of importance for applications requiring low measurement uncertainties or high precision. As in far field ranges, near field ranges are affected by electronic equipment sources of error such as drift, noise, dynamic range, nonlinearity, signal leakage, and reflections. However, the error manifestations may differ between the near field and far field ranges. In addition, the near field range is affected by error sources from probe interactions with the near fields, probe position, antenna alignment, and errors caused by flexing cables. Mathematical errors are generally very small in comparison to experimental errors. For more information on the effects of errors in near field antenna testing see references 6 and 7. Technical Rationale: The measurement of far field antenna patterns can be accomplished by using a far field range or a near field measurement facility. For measurements made in the far field, the distance between the test antenna and the measurement transmitting source (or receiver) must be greater than 2D2/l, where D is a characteristic dimension of the test antenna and l is the wavelength. (For antennas having significant aperture phase deviations and requiring low measurement uncertainties, the spacing required can exceed 8D2/l.) From this relation it can be seen that large distances are required for far field testing of large aperture, high frequency antennas. For example the test distance required for far field pattern measurement of a 12 GHz parabolic reflector antenna with a 12 ft diameter would be 3500 ft. Because of the large distances the far field tests are conducted outdoors where the testing is constrained by weather and the transmission path is influenced by the weather. In addition, the path between the test antenna and the source must be controlled to preclude variations due to reflections from traffic entering the path. The determination of far field antenna patterns, obtained by using near field measurements, has been demonstrated and proven, references 4 and 5. The validity and accuracies have been shown to be comparable to measurements made using far field ranges, under conditions controlled to preclude environment errors. The determination of far field antenna patterns, from near field measurements, can be done indoors in a protected, controlled environment, where the testing is not constrained by the effects of weather on the test antenna or results. The anechoic environment can provide protection for costly flight hardware from weather, smog, wildlife, and other environmental hazards. The region of testing can be designed and controlled to minimize the effects of reflections. And, for spacecraft antennas designed in a microgravity environment, the effects of gravitational deformations can be reduced or eliminated when tests are conducted with vertical boresite orientations. These advantages are gained at the expense of increased measurement times and complexity. Many measurements must be made to define the near field pattern, see reference 7. The set of near field measurements must be made up of complex field quantities (e.g., a+jb) and an accurate determination of probe position. Data acquisition time is a function of desired accuracy, aperture area, and frequency. In addition, computation time is required to transform the near field data to the far field patterns. Appendix: This appendix provides a listing of near field antenna test facilities within NASA, and lists their salient characteristics. The table below lists the location of the facility, the type of scanning surface used, the size of the scanning plane, the maximum frequency of operation, and antenna boresite orientation. The table also describes the mode of operation supported for the test antenna, i.e. transmitting and/or receiving, and notes if the test antenna must be moved during testing. Location Type Size, m Frequency, GHz Boresite Orientation Mode Probe motion Note JPL Cylindrical 5.2 18 horizontal trans 1d rotate antenna JPL Plane polar 6.1 32 vertical trans 1d rotate antenna JSC Plane rectangular 12.2x12.2 40 vertical trans 2d fixed LeRC Plane rectangular 6.7x6.7 60 horizontal trans rec 2d fixed The following is a brief description of each center's near-field capability. Jet Propulsion Laboratory Cylindrical Near-Field Facility The cylindrical near-field scanning facility at JPL contains an anechoic chamber that is 20x20x40. The chamber contains two automated positioners, one for the test antenna and the other for the sampling probe. Cylindrical near-field scanning is performed by rotating the test antenna in an azimuth direction while the probe step along the z-direction after the test antenna completes a full 360 degree rotation. The Jet Propulsion Laboratory has conducted recently an extensive research in the area of cylindrical near-field that led to the development of efficient and fast algorithms for far field construction, probe pattern compensation, probe characterization, and an error analysis. Plane-polar Near-Field Facility The plane-polar near-field range facility is located in an anechoic chamber with a dimension of 20'x20'x40'. The facility utilizes two automated positioners, one for the test antenna (generally has a large planer aperture) and the other for the sampling probe. The test antenna aperture is horizontally situated close to the ground with the aperture placed in the x-y plane facing up and rotated azimuthally around the z-axis. The probe is situated close to the ceiling facing down with a single linear translational motion in the x or y direction above and across the center of the test antenna. The probe is generally separated several wavelengths away from the test antenna. The near-field amplitude and phase data are taken with the probe initiated at a particular incremental location while the test antenna is rotated 360 degrees incrementally, which is repeated at the next incremental probe location, etc. The probe has a total rms deflection of 0.025 cm over the total run of the carriage (7m long). This provides sufficient accuracy for measurement up to Ku-band and can be improved for Ka-band measurement. Johnson Space Center Plane Rectangular Near-Field Facility The anechoic chamber at the Johnson Space Center is capable of testing antennas up to 30 ft in diameter. The frequency range of the facility is from 1.0 Ghz to 60.0 Ghz. The near-field facility includes a two-axis horizontal scanning system. The scanner is configured with a RF probe which can function as a transmitter or receiver. The probe travels in the Y-direction for each step increment moved by the translation beam in the X-direction. The movement of the scanner will describe a raster scan geometry. During testing, the position of the test antenna will be fixed such that its boresight will be perpendicular to the horizontal scan plane of approximately 40'x38'. The planarity of the scanner as described by the probe tip motion will be flat within +/- 0.005 inch. This accuracy is especially critical at the maximum operating frequency of 60.0 GHz. References: Sharp, G. R., et al: quotCharacteristics and Capabilities of the NASA LeRC High Precision 6.7-by 6.7-m Planer Near-Field Scanner,quot NASA TM 83785, October 1984. Kunath, Richard R. and Zakrajsek, Robert J.: quotNear-Field Testing of the 30-GHz TRW Proof-of-Concept Multibeam Antenna,quot NASA TM 87357, September 1986. Kunath, Richard R., and Garrett, Michael J.: quotNear-Field Antenna Testing Using the Hewlett Packard 8510 Automated Network Analyzer,quot NASA TM 103699, October 1990. Joy, Edward B. and Paris, Demetrius T.: quotSpatial Sampling and Filtering in Near-Field Measurements,quot IEEE Trans. Antennas and Propagation, Vol. AP-20, May 1972, pp. 253-261. Newell, A. C., and Crawford, M. L.: quotPlanar Near-Field Measurements on High Performance Array Antennas,quot NBS, NBSIR 74-380, July 1974. Evans, Gary E.: quotAntenna Measurement Techniques,quot Artech House Inc., 1990. Acosta, Roberto J., and Lee, Richard Q.: quotCase Study of Sample Spacing in Planar Near-Field Measurement of High Gain Antennas,quot NASA TM 86872, September 1984. Yaghjian, A. D.: quotNear-Field Antenna Measurement on Cylindrical Surface: A Source Scattering Matrix Formulation,quot NBS Tech. note 698, July 1977. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
714 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Battery Selection Practice for Aerospace Power Systems |  | Failure to adhere to proven battery selection practices could cause shortened mission life, premature cessation of component or experiment operation, mission failure, and in extreme cases, loss of mission or life. All phases of battery use, from battery selection to installation in the launch vehicle or orbiting spacecraft, must adhere to the proven design and safe battery practice. | When selecting batteries for space flight applications, the following requirements should be considered: ampere-hour capacity, rechargeability, depth of discharge (DOD), lifetime, temperature environments, ruggedness, and weight. Many batteries have been qualified and used for space flight, enhancing the ease of selecting the right battery. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1221; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Selection of the optimum battery for space flight applications results in a safe, effective, efficient, and economical power storage capability. The optimum battery also enhances launch operations, minimizes impacts to resources, supports contingency operations, and meets demand loads. Implementation Method: Primary batteries, those which are not recharged are and useful for short duration, are used principally for providing electrical power for launch vehicles. These batteries must have high energy density, high current capabilities, and good reliability. MSFC has had experience with Lithium/Monoflouride (Li/CF), Lithium/Thionyl Chloride (Li/SOCl2), and Silver/Zinc (Ag/Zn) primary batteries. Secondary batteries, those which are discharged and then recharged numerous times, are principally used for spacecraft, satellite, and other long-term space-oriented applications. In space applications, reliability, costs, producibility, responsiveness, risks, safety, and maintainability are more important than high current content. MSFC has had experience with Silver/Zinc (Ag/Zn), Nickel/Hydrogen (Ni/H2), Nickel/Cadmium (Ni/Cd), Nickel/Metal Hydride (Ni/MH), and Bi Polar-Lead Acid (Bi-Pb/Acid). [D] Battery types are selected for specific applications based on a number of factors including specific energy and energy density (see Figures 1 and 2), lifetime, number of cycles, discharge rate, charge retention, shelf life, ruggedness, operating temperature, and other factors. Figure 3 presents these factors for various battery types. Figure 3 should be used by the designer as an initial tool for selecting the required battery type. The design of batteries for space flight should be accompanied by battery level electrical, mechanical and thermal analysis. [D] A typical battery selection flow chart is shown on Figure 4. After the program is identified and electrical power requirements are established, a trade study should be performed to determine the actual battery (primary or secondary) that will fulfill the requirements at a reasonable cost. Cell selection includes charge voltage, discharge capacity, and discharge voltage after cycling. Establishing the battery size is determined by the number of cells required to provide the required electrical power, i.e., a 24-volt battery using a 1.5 volt cell will require 16 cells. Mechanical packaging of the cells into a battery requires such parameters as cell type, number of cells, weight, length, height, temperature requirements, mounting method, vibration environment, electrical feed through, and venting requirements to ensure proper functioning of the battery. Perhaps the most important part of selecting a battery is the selection of a reliable cell/battery manufacturer. Preferably one that has consistently produced high quality and reliable batteries. Manufacturing engineers should critique the design for producibility and testability early in the design process and make corrective suggestions when problems are discovered. [D] Accelerated life testing of batteries is extremely difficult due to the nature of the chemical reaction between the electrolyte and the positive and negative electrodes. Therefore, preferred type and configuration of the battery should be selected early in the program to allow for lifetime testing. Performance testing of the selected battery can be accomplished in parallel with life testing. Performance testing should be accomplished in an environment to which the battery is expected to be exposed during operation. The battery should demonstrate during testing that it will deliver the required electrical power and will charge and discharge as designed. Technical Rationale: MSFC's aerospace flight battery experience comes from a combination of its own in-house laboratory experience on numerous programs; from coordination with battery manufacturers, prime contractors, and subcontractors for a number of launch vehicles, space vehicles, and experiments; and from many years of participation in NASA/industry aerospace battery workshops. Two such workshops, hosted by the Marshall Space Flight Center in Huntsville, Alabama, were attended by approximately 200 persons each, representing both Government and industry. Credit must be given to the interdisciplinary efforts of Goddard Space Flight Center, NASA Headquarters, Jet Propulsion Laboratory, Johnson Space Center, Kennedy Space Center, Ames Research Center, Langley Research Center, Lewis Research Center, and their suppliers and contractors, as well as to many academic and nonprofit organizations who have contributed to the battery research leading to this body of knowledge. References: Bykat, Alex, quotDesign of an Expert System for Diagnosis of a Space Borne Battery Based Electric Power System,quot University of Tennessee at Chattanooga, IECEC, Vol. I Aerospace Power Systems Conference, August 1990. Dunlop, J. D., quotNASA Handbook for Nickel-Hydrogen Batteries,quot Preliminary Draft, Goddard Space Flight Center, June 1991. Glover, D.G., quotAerospace Energy Systems Laboratory: Requirements and Design Approach,quot Ames Research Center, Dryden Flight Research Facility, Edwards AFB, CA, NASA Technical Memorandum 100423, 1988. Guthals, D.L. and Olbert, Phil, quotCRRES Battery Workshop,quot Ball Space Systems Division, letters dated March 11 and 16, 1992. Halper, G., Subbarao, S., and Rowlette, J.J., quotThe NASA Aerospace Battery Safety Handbook,quot JPL Publication 86-14, July 15, 1986. Jones, Dr. G.M., quotATM Electrical Power System Post Mission Design and Performance Review,quot George C. Marshall Space Flight Center Report No. 40M22430, February 6, 1975. Kennedy, L. M., quot1990 NASA Aerospace Battery Workshop,quot 1991, NASA Conference Publication 3119, Marshall Space Flight Center, December 4-6, 1990. Linden, David, Handbook of Batteries and Fuel Cells, McGraw Hill Inc., 1984. Manned Space Vehicle Battery Safety Handbook, NASA, Johnson Space Center, JSC 20793, September 1985. MIL-B-81502B(AS), quotBattery, Silver-Zinc-Alkali, General Specification for,quot February 26, 1980. MIL-B-82117D, quotBattery, Storage, Silver-Zinc, Rechargeable, General Specification for,quot July 25, 1983. NASA SP-172, quotBatteries for Space Power Systems,quot NASA 1968. | This practice has been used on Space Shuttle Solid Rocket Booster (SRB); Space Shuttle External Tank (ET); Materials Experiment Assembly (MEA); Inertial Upper Stage (IUS); Tethered Satellite System (TSS); Transfer Orbit Stage (TOS); Saturn IB Launch Vehicle; Saturn V Launch Vehicle; Skylab; High Energy Astronomy Observatory (HEAO); Lunar Roving Vehicle (LRV); and Hubble Space Telescope (HST). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/16/2000
704 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Nickel-Hydrogen Spacecraft Battery Handling and Storage Practice |  | The impact of not following this practice is that batteries may be damaged during handling and storage and may exhibit degraded performance during the mission including early life failure. Additionally, batteries may not be properly charged prior to launch and therefore may not meet their mission performance requirements or may require a lengthy recharging procedure before the satellite can be fully activated. | Develop and implement handling and storage procedures to ensure reliable operation, minimize deterioration, and prevent irreversible effects on the flight performance of Ni-H2 flight batteries due to improper handling and storage. | GSFC | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1109; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Nickel-Hydrogen (Ni-H2) batteries will significantly deteriorate, principally due to capacity fading, if the proper storage and handling procedures are not followed in a number of stages in the cell/battery lifetime. A set of proven guidelines is followed by flight projects in the preparation and utilization of project unique handling and storage procedures in order to minimize these deterioration effects and ensure the reliable performance of Ni-H2 batteries. Implementation Method: A sealed Ni-H2 secondary cell is a hybrid, combining battery and fuel-cell technologies. The nickel positive electrode comes from the nickel-cadmium cell and the negative platinum electrode from the hydrogen-oxygen fuel cell. The cell is contained in a pressure vessel designed to operate up to 1,200 p.s.i. of hydrogen gas when the cell is fully charged. Pressure measurements can be used to determine the "state of charge" of batteries in flight. Salient features of the Ni-H2 battery are a long cycle life that exceeds any other maintenance-free secondary battery system, high specific energy (gravimetic energy density), high power density (pulse or peak power capability), and a tolerance to overcharge and reversal. It is these features that make the Ni-H2 battery system the prime candidate for the energy storage subsystem in many aerospace applications, such as geosychronous-earth-orbit (GEO), commercial communications satellites, and low-earth-orbit (LEO) satellites. The GEO and the LEO applications have two different requirements for batteries. The LEO applications require charge/discharge cycles of 18,000 to 30,000 cycles with depth of discharges (DOD) up to 40% and up to a 5 year lifetime in orbit. The GEO applications require lifetimes in orbit of 5 to 10 years and about 100 cycles per year with maximum DODs of 60% for a total of 500 to 1,000 cycles. To meet these mission requirements, a number of different design approaches are used by a variety of Ni-H2 battery manufacturers. Generally, two or more batteries are used per spacecraft to meet the power requirements. The major advantage of using multiple batteries is reliability. If one battery fails, the other battery or batteries can maintain all or at least the most significant functions of the spacecraft. The storage and handling of Ni-H2 cells and batteries can significantly alter performance during both prelaunch and mission lifetimes. The development of a low-voltage plateau in the discharge mode or capacity fading (loss of capacity to 1.0 volts) is the major concern. Under most circumstances, capacity can be recovered. However, if a cell or battery is overheated, it can be permanently damaged. The following storage and handling procedures cover the three stages in the cell/battery lifetime: Stage 1 - Storage of cells after manufacture and before assembly into batteries: Storage periods can range from a few weeks to several years depending upon the launch schedule. The following three methods are used to store and maintain capacity of cells for periods of time from several weeks up to three years. Store fully charged cells open-circuited at temperatures below 0°C. These cells must be recharged, (topped off), every 7 to 14 days. Store fully charged cells at temperatures below 0°C with a trickle charge rate of C/100. Store discharged cells open-circuited at 0°C for up to three years. Stage 2 - Storage of batteries after assembly: Once the flight batteries are assembled, they are generally stored until they are shipped to the launch site for integration into the spacecraft. For flight batteries, the storage period can range from a few months to three years. The longer periods represent program delays that affect launch schedules. The same methods for the storage of batteries can be used as defined above for cells. Regardless of the method of storage used, the capacity of batteries is measured both before and after storage to determine if any capacity fading has occurred during storage. Stage 3 - Storage of cells/batteries during shipment: Cells/batteries are fully discharged and short circuited during shipment. Each cell/battery is wrapped separately with its own packaging material to exclude humidity and control temperatures to 5°C (+/- 5°C). Five to 10 cells can be packed within the same container and shipped air express to minimize shipping time. The shipping container should be equipped with temperature recorders to provide assurance that flight cells/batteries have not been exposed to temperatures exceeding 25°C. The capacity of cells/batteries is measured both before and after shipment to determine if any capacity fading has occurred during shipping. Stage 4 - Storage of batteries at the launch site: Batteries should be in the fully discharged state during handling operations at the launch site. Batteries can then be maintained during short term storage in the charged state at room temperatures but must be recharged every 7 to 14 days. Also, flight batteries can be maintained on trickle charge prior to launch. The final reconditioning of flight batteries should be performed 14 days prior to spacecraft launch. Upon completion of the reconditioning, flight batteries should be kept on low rate trickle charge until launch or reconditioned every 30 days if the launch is delayed. The batteries should be kept in cold storage if the launch is delayed beyond 90 days. The following additional general guidelines and procedures are used in the handling and operation of Ni-H2 batteries. A battery should be "reconditioned" if it has been on open circuit, subjected to intermittent use, i.e., open circuit, trickle charge, occasional discharge, etc., for a cumulative period of 30 days. Reconditioning is effected by performing the following sequence at 20°C. Discharge at C/2 constant current rate until the first cell reaches 1.0 v/c. Drain each cell with a 1 ohm resistor until each cell's voltage is less than .03 V/C. Recharge battery at C/20 constant current rate for 40 hours (+/- 4 hours). Repeat steps a and b. Charge battery at C/10 constant current rate for 16 hours ( +/- 4 hours). Repeat steps a, b, and e. Batteries are not charged or discharged in parallel. Isolation is provided in spacecraft power systems to ensure that a failure of one battery does not affect another battery. Batteries are charged and all functions and cells are checked out thoroughly prior to installation in a flight spacecraft. Batteries are installed into a spacecraft in a discharged state. "Tap"s are never installed on any portion of a string of cells in series that can cause unbalanced loading of portions of a battery. Shorting resistors are normally placed across individual cells to prevent cell reversal which could damage individual cells when flight Ni-H2 batteries are stored short circuited. Power system designs include circuitry to prevent overcharging of batteries and the generation of excessive heat which can damage batteries. The temperatures of Ni-H2 batteries are monitored during operation and storage. Operating temperatures are not permitted beyond 18°C and non-operating exposures are not permitted beyond 25°C. Exposure to temperatures beyond 30°C results in permanent loss of capacity. Heaters are used as required to insure that the temperature of Ni-H2 batteries do not go below -25°C at any time in order to prevent freezing of the electrolyte. Flight batteries should not be subjected to extended spacecraft integration and test activities. The open circuit and intermittent use of Ni-H2 batteries during extended spacecraft integration and testing activities are known to significantly accelerate the degradation of batteries. Results from controlled tests have shown permanent and irreversible changes. The design of flight batteries should include the following provisions for ground console interfacing with the batteries while integrated into the spacecraft. Signal lines for monitoring total battery voltage, charge and discharge currents, battery temperatures, and individual cell voltages. Capabilities to charge and discharge the battery from the ground test console. Capability to place a resister and a shorting plug across each individual cell. A log book shall be maintained on each flight battery including the complete test histories of each cell, of the assembled battery, and of all integration and test and launch site activities. Each log book shall identify the project and battery and individual cell serial numbers. Chronological (date and time) entries for all test sequences, summary of observations, identifications of related computer stored records, malfunctions, names of responsible test personnel, and references to test procedures controlling all tests shall be recorded. Since Ni-H2 batteries are perishable, their ability to satisfactorily complete their mission life is directly related to their storage, their ground use, and handling. Historical performance information is required to ensure their flight worthiness at launch time. Technical Rationale: Ni-H2 batteries can deteriorate due to improper storage and handling. This practice which avoids this deterioration is based on a long period of battery development, testing, and flight experience. References: NASA Handbook for Nickel-Hydrogen Batteries: NASA Reference Publication 1314, September 1993 | This practice has been used on Hubble Space Telescope (HST) (NASA's first flight use of Ni-H2 batteries in a low Earth orbit application); Earth Observing System AM, (EOS AM), LANDSAT | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/15/2000
703 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Part Junction Temperature | Preferred Practice for Design & Test. Reliability of electronic parts will be reduced significantly if junction temperatures exceed 60°C. Maintain part junction temperatures during flight below 60°C. (Short-term mission excursions associated with transient mission events are permissible.) | Reliability of electronic parts will be reduced significantly if junction temperatures exceed 60°C. | Maintain part junction temperatures during flight below 60°C. (Short-term mission excursions associated with transient mission events are permissible.) | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1204; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Reliability is greatly increased because the failure rate is directly related to the long-term flight temperature. Implementation Method: Establish in-specification design (and test) temperatures >75°C and limit part junction temperatures (JT) to <110°C which constrains permissible part junction temperature rise (DJT) to <35°C. (This practice has been verified on programs in place before the release of MIL-STD-975H. If the MIL-STD-975H junction temperature of 100°C is used, junction temperature rise should be changed to assure that long-term flight junctions stay below 60°C.) Technical Rationale: Basic reliability is directly related to temperature and time, i.e., l = f(T,t). The following relationship is obtained either theoretically from the Arrhenius relationship (l= Aexp[-Ea/k (1/T - 1/T0)]) or empirically from the data in MIL-HDBK-217E. [D] Given: Specific part Specific derating factor Specific chemical activation energy The curve shape is representative of all electronic parts (and most mechanical processes) in the range of temperature typified by space exposure. Simply stated, the higher the long-term flight temperatures, the lower the reliability: [D] Assume that a design and test temperature of 75°C is chosen. In the graph from MIL-STD-883B observe that a 25°C D T corresponds to a failure rate increase of more than an order of magnitude-- i.e., >1000% difference. MIL-HDBK-217E has different values, but the factor is up to approximately 3X on some parts (depends on derating criteria and parts qualification). The following example illustrates the effect of this relationship on design and test temperatures. Assume the following conditions as an example: Case A: T = 75°C in-specification design temperature for baseplate Case B: T = 50°C in-specification design temperature for baseplate Case A and Case B: T = 25°C long-duration flight temperature for baseplate J T = 110°C limit for any exposure or analysis Then: Design/Test Parameters Case A Case B Design Baseplate 75°C 50°C JT limit 110°C 110°C Permitted DJT rise 35°C 60°C Flight Conditions [D] from Arrhenius [D] NOTE: In the example given, short-term ground test exposure on the order of 1-2 weeks will use an insignificant amount of life in hardware designed for long-life and high reliability. For example, a 1-week thermal vacuum test at 75°C provides a short-term high temperature screen in the actual circuit usage configuration to provide confidence for a long-term exposure under flight conditions (JT<60°C), and uses only 0.018% of the parts capability. This demonstration is an important element in establishing pre-launch confidence in design adequacy. [D] (Click image for a larger view) References: Gibbel, M. and Clawson, J.F., quotElectronic Assembly Thermal Testing Dwell/Duration/Cycling,quot Proceeding of the 12th Aerospace Testing Seminar, March 13-15, 1990. Gibbel, M. And Cornford, S.L., quotSurface Mount Technology Qualification Methodology (Testing and Verification),quot Proceeding of the NASA Surface Mount Technology Workshop, NASA Lyndon B. Johnson Space Center, Houston, Texas, July 28-29, 1992. Thermal Design Practices for Electronic Assemblies, Reliability Preferred Practice No. PD-ED-1226 | This practice has been used on Voyager, Viking, Mariner series, Galileo. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/15/2000
701 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Static Cryogenic Seals for Launch Vehicle Applications |  | The principal impact of nonpractice is unacceptable joint leakage of cryogenic and/or gaseous propellants from propulsion systems and stages. These leakages, if entrapped in specific areas of launch vehicles in the presence of ignition or heating sources, sparks, or rocket system exhausts could result in catastrophic loss of the vehicle and of lives of astronauts or ground crew. These catastrophic events, or location of leaks at critical times in the schedule can also cause program delays and can result in excessive program costs. Table 1 is a generic listing of selected typical conditions which could result in excessive leakage rates. [D] | Practice: Deflection actuated, pressure assisted coated metal seals, or spring energized Teflon® seals, along with prudent flange joint designs, should be used for high pressure static cryogenic sealing applications in launch vehicle engines and related propulsion system components. | MSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1208; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Leak-free joints can be achieved in cryogenic lines, joints, valves, and pumps for launch vehicles through the use of proven, state-of-the-art static cryogenic seals. These seals adapt to wide ranges of temperature and continue to seal when subjected to high pressures, in-flight static stresses, and in-flight dynamic loads. Implementation Method: 1. Introduction: Low or zero fluid or gas leakage in flight and ground-based cryogenic systems can be achieved through meticulous joint design and testing, selection of the proper seal configuration and materials, thorough cleaning and inspection of seal and flange surfaces, carefully controlled installation, and carefully controlled fastener tightening procedures. The most widely used and successful cryogenic seal for NASA space flight applications has been the deflection actuated, pressure assisted coated metal seal. High nickel content steel alloys coated with a thin layer of Teflon® or plated with gold, silver, indium, palladium, lead, copper, nickel, or aluminum have provided good sealing properties at elevated as well as cryogenic temperatures. This practice covers experience with pressure assisted and spring energized cryogenic seals in the SSME and ET. Experience was derived from earlier programs (Saturn I and Saturn V) to develop these effective seals. Although the subject of this practice is cryogenic seals, the pressure assisted and spring energized seals described are also effective over the broad temperature ranges from liquid hydrogen (-423 deg.F) to hot gas (1000/1200 deg.F). 2. Nonspacer Type, Deflection Activated, Pressure Assisted Seals [D] The nonspacer type seal shown in Figure 1, fits into a groove in the flange. It can be used with a separate spacer to eliminate the need for a seal groove, but a retaining groove is preferred. As shown in Figure 1, these seals have two sealing surfaces that mate with adjoining flanges. Diameters range from 0.55quot to 16.75quot as used in the SSME. Cross sections of the seal ring vary from 0.200quot x 0.164quot to 0.150quot x 0.120quot in radial width and installed length, respectively, and the seals can be made in other diameters and other cross-sectional configurations. They are found throughout the SSME in both cryogenic and hot gas applications. The seals are machined from high nickel alloy steel and coated with either silver or silver with rhodium overcoat. The silver coated seals have a temperature range of -423 deg.F to +1000 deg.F, while the silver with rhodium can be used over a -423 deg.F to +1200 deg.F range. The seals are used in both fuel and oxidizer systems. In installing both the nonspacer type and the spacer type seals, the seals are compressed during joint assembly, which provides a load at the sealing circumference to effect sealing at low pressures. As the pressure increases, it acts on the internal surfaces of the seal, increasing the force on the seal tips to augment sealing capability as pressure increases. The seal coating presses into the flange surfaces, filling microscopic asperities and irregularities in the flange sealing surfaces. The combination of the installation deflection and the pressure on the internal surfaces permits the sealing faces to compensate for joint separation under system pressure and for shrinkage during exposure to cryogenic temperatures. 3. Spacer Type, Deflection Activated, Pressure Assisted Seals [D] This type of seal was originally used on the Saturn program and was later adapted for use on the Space Shuttle. The seal incorporates a flange, drilled to match the mating parts, which provides a positive stop to control seal compression and secondary pressure barriers on each side of the seal to facilitate leak checking. While some seals were originally silver plated, present use is confined to Teflon® coated high nickel alloy steel seals. The seals are used on the ET and on the piping connecting the Tank to the Orbiter. Most have rated temperatures of -423 deg.F to +350 deg.F except for one which has a -423 deg.F to +800 deg.F rating. A typical seal installation as it is used on the ET is shown on Figure 2. Notice that the seal has both a dual-sided primary seal located at the interior periphery of the seal and a dual-sided secondary pressure barrier just inside the bolt circle. A Teflon® coated seal is used in the LH2 and GH2 systems while a silver plated seal is used in the LO2 and GO2 systems. 4. The Raco®/CreaveyTM Seal Configuration [D] Figure 3 shows the combination Raco®/CreaveyTM seal as used for 17-inch diameter feed lines on the ET. The primary Raco® seal consists of a metal hoop-spring inside an energized Teflon® jacket. The secondary CreaveyTM seal is a metallic coil spring housed within an energized tubular Teflon® casing. 5. Recommended Practices a. Design Practices In general design practice, the development of a good leak-free joint design requires an integral look at the design of all the parts: seal(s), flanges, and fasteners. It also requires some foreknowledge of the degree of access required for leak checking, inspection, and potential disassembly and reassembly during downstream operations and particularly on the launch pad. Leak-free joint design is based on the seal maintaining contact between a surface on one flange and the mating surface on the other flange under all operating conditions. The fasteners take the dynamic loads and are installed in a preloaded condition to maintain seal contact with the flange surfaces. The seal in the joint must prevent leakage in excess of the allowable limit. The advantages of deflection actuated, pressure assisted seals are that they maintain a nearly constant fastener loading under pressurized and nonpressurized conditions and that they result in minimum flange deflection at the sealing surface. Sealing surfaces on flanges can be recessed to protect them from damage, and seal grooves can be configured for easy seal installation, centering of the seal, and for error-free assembly. The seal and joint can be designed with detents to prevent misaligned or reverse installation. The design of joint assembly and seal installation tooling, equipment, fixtures, and procedures should proceed concurrent with joint design. The designer must remember that a separable joint is used to permit later disassembly, inspection, and reinsertion of seals or refurbishment/replacement of systems or components either in the manufacturing shop, on the test stand, or on the launch pad. The joint design and the assembly tooling or fixtures should provide: (1) protection to the seal and mating surface; (2) concentric and accurate seal positioning; and (3) even pressures around the periphery of the seal and joint during the fastener tightening process. Circumferential indexing that will ensure relocation of impressed seal surface deformities over corresponding flange deformities is desirable if the seal is to be reused. A good design practice is not to depend entirely on flange bolt locations to position seal components radially. A notch or groove should be provided to retain the seal. Gaskets, seals, parts, and subassemblies should be designed to preclude improper alignment or rotation. Using seals very close to the same size in the same area should be avoided. The design should be adaptable to using the same size seal (or a very different size) in all locations which are in close proximity. This practice will reduce the potential of installing the incorrect size seal. The following design suggestions pertain to seals for cryogenic and gaseous hydrogen and oxygen: Where feasible, secondary seals with a vent for direct measurement of leakage should be provided. The materials in cryogenic/gaseous hydrogen seals should be resistant to hydrogen embrittlement. Walls should be provided in the seal groove to carry the seal hoop load when pressurized. Designs of liquid oxygen seals should include LO2 compatible materials. Designs of liquid hydrogen seals should include LH2 compatible materials. Potential flange ovality resulting from flange stresses or temperature cycling must be taken into account in establishing the width of flange sealing surfaces. The seal material(s) must be compatible with any anticipated purge or cleaning material that may contact the seal during its intended use. Purge or cleaning material restrictions should be noted on engineering drawings and in procedural documentation. A seal alignment provision should be incorporated in the design process. Design optimization in metal seals for cryogenics can be accomplished with currently available general purpose finite element analysis programs such as ANSYS (produced by Swanson Analysis Systems, Inc., see reference #13) or by specially programmed finite element models (reference #14). Modeling of seals can take into account surface texture, gas transmission flow methods, seal load distribution, material properties, and dynamic environmental conditions (temperature, pressure, vibration, shock, etc.). New seal designs should be evaluated using these analysis and modeling techniques and qualified before use. (see below). b. Qualification Practices Prior to incorporation into the production design, the entire joint system, which includes the flanges, seal(s), and fasteners, should be qualified for use in the specific environments expected to be encountered in operations. [As part of the qualification procedures for SSME seals, seals of 0.8quot, 1.1quot, and 3.8quot diameter were chilled to -250 deg.F and pressure cycled from ambient pressure to 8,970 psig for 240 cycles while demonstrating their ability to continue to meet leakage requirements. Seals were also subjected to structural verification at pressures up to twice operating pressures after completion of 240 pressure cycles, while still meeting leakage requirements.] If different temperatures, pressures, or gases are used for qualification and/or leak checking, leak and nonleak conditions must be carefully calibrated and correlated with leak and nonleak conditions in the actual environments expected. These calibrations must be meticulously adhered to in interpreting leak test results. c. Manufacturing Practices Cleanliness and inspection at intermediate manufacturing steps are extremely important in the manufacture of deflection actuated pressure assisted seals as well as for other types of seals used in liquid oxygen and liquid hydrogen environments. Nonspacer type seals are usually silver plated with an initial gold undercoat. The gold undercoat prevents oxidation of the substrate at temperatures above 600 deg.F, when used in hot gas environments, and this prevents blistering of the silver plating. Silver is used for its low compressive yield strength and ductility required for effecting a seal, and for its corrosion resistance. Rhodium overplate is used to prevent bonding of the silver plate to the mating flange surfaces at high temperatures. A chromate coating is used to prevent discoloration of the seal or flange due to tarnishing of the seal's silver plating. Care must be taken to thoroughly clean and inspect each seal between the plating and coating operations. Adherence of the Teflon® primer coat and subsequent final coat to spacer type seals also requires stringent cleaning and inspection between each operation to prevent inclusions, voids, contamination, and surface defects. d. Inspection Practices Seal and flange mating surfaces should be visually inspected after manufacture and immediately before installation with a 10X magnification device. Very tiny scratches across the face of the seal's coated or plated sealing surface can cause leaks. [In one instance, a scratch .001quot wide and .0005quot deep extending across the radial length of the sealing surface was of sufficient size to cause a Class I leak.] The inspector should look carefully not only for nicks and scratches in seals, but also for metal or foreign particles on the seal or on the mating flange surfaces. NASA problem reports have indicated that, in at least one incidence, metal flange faces were allowed to contact each other and to rub together prior to seal installation, causing fine metal particles to be created which interfered with the seal's ability to seat properly against the flange sealing surface. Optical microscopy up to a power of 50X has been used to detect very small flaws and irregularities in flange and seal surfaces when leakage tests failed. Seal flatness or waviness can be confirmed or detected by the glass test in which the seal is placed against a plate glass sheet and observed from the underside. This method can be used to detect potential nonparallelism or small deviations in seal contact or coating thickness. Precision flat bars can be used with a light source to verify that flange faces are flat. e. Protection Practices Many of the leaks detected from joints of cryogenic and gaseous lines were possibly caused by scratching or nicking of the flange sealing surfaces or the seal, after initial manufacturing and inspection, but before assembly. Post manufacturing, in-transit, and preassembly protection of both the seals and the joint sealing surfaces have proven to be essential in ensuring leak-free or acceptable leakage rate joints. LO2-compatible protection caps or plugs should be used to protect sealing surfaces between manufacturing inspection and final assembly. Liquid oxygen compatibility is required of materials protecting oxidizer system joints because small particles of the protection material can rub off against the seal or flange surface and could lead to a fire or explosion. Cleanliness is more easily maintained with proper protection while the joint is in a disassembled condition. f. Preparation Practices As with in-transit or in-storage protection, thorough cleaning of the seals and flanges, accompanied by preinstallation inspection, is required to ensure leak tight joints. If the flanges are to be in storage for an extended period, they require a protective grease or jelly. If so, this material must be removed and the flange cleaned and reinspected prior to assembly, as this substance may have picked up fine particles during storage. If a protective substance has not been used, thorough visual inspection must take place to ensure that there are no evidences of corrosion. If corrosion exists, it must be removed and the flanges or seals reinspected both dimensionally and visually. g. Installation and Assembly Practices Several of the unacceptable leaks of joints carrying cryogenic fluids reported in NASA's Problem Reporting and Corrective Action (PRACA) system resulted from scratches to the seal or flange faces during the assembly process after preassembly inspection. These scratches may have been caused by the flanges rubbing together or the seal rubbing against corners or edges of the flanges. Several methods have been proposed or implemented to reduce the potential of seal or joint sealing surface damage during assembly. One method is to place Teflon® shims on both sides of the seal while it is being inserted into place between the flanges, and then to remove the shims once the seal is in place. Procedures have been developed which would not allow the flanges to touch the seal until the bolt torque pulls the flanges together. Special seal retaining or insertion tools and other assembly equipment can be designed to minimize the potential of damage during assembly. Operators must be thoroughly trained and certified in these procedures. To provide uniform compression of the seal and a final uniform load around the seal's circumference, fasteners should be tightened in stages in a prescribed alternating fashion, starting with fasteners located 180 degrees apart. h. Leak Checking Methods The most common method of seal and joint inspection after assembly is the leak test. Several leak detection procedures are used to check the integrity of LH2, GH2, LO2 and GO2 joints and seals: (1) bubble method; (2) gas analysis method; (3) pressure decay method; and (4) flow meter method. The most prominent method of leak testing is the bubble method. In the bubble test, a leak test solution is applied to the periphery of the joint while the interior is being pressurized with liquid helium gas or nitrogen in a manner that has been calibrated against the operational fluid's temperature, pressure, and flow rate to provide acceptable or nonacceptable leak rates. The bubble test method is confined to gaseous systems or cold gas simulations of cryogenic joint pressures and temperatures. Four classes of leakage have been defined. In general, they are: Class I: Steady formation of very small, long persisting bubbles. Class II: Mixture of random size bubbles of moderate persistence. Class III: Large, fast-forming bubbles. Blowing: Bubble formation does not take place because of large gas flow. Another common method of leak detection is the gas analysis method using a mass spectrometer. Although this method will determine that a leak exists, it is difficult to measure or to calculate the leak rate from mass spectrometer test results. Advanced methods of leak detection using palladium sensors, colorimetric methods, and nonintrusive sensors are being studied, but none has yet been as successful in both detecting the leak and indicating its magnitude as the leak test solution method. The solution test method is simple, easy to use, and readily observable with the naked eye. Two precautions are important, however: (1) complete coverage of the joint with the leak test solution; and (2) close observation of the complete periphery of the joint. The technician should observe the leak test solution immediately after application so that a blowing leak is not missed. The general practice is to releak test whenever a joint is disturbed. In the case of the SSME, all joints are leak tested both before and after final hot firing acceptance. A total engine leak test is conducted at final acceptance to determine the total leakage from all 154 joints (80 oxidizer system joints, 44 fuel system joints, and 30 hot gas joints), which must be less than six standard cubic inches per minute. In general, ambient temperature leak checks are not as accurate as testing in the chilled condition. Therefore, at least in initial development and checkout, the system must be cooled to its operating temperature, and realistic pressures and flow rates must be provided to identify potential leak conditions. The alternative is to use a different cryogenic or gas with prior accurate calibration of leakage results with the operational fluids, as mentioned earlier. i. Storage Practices Joints, flanges, or seals in storage must be protected against corrosion and against inadvertent damage of the seal or sealing surfaces. The protection device or substance must be compatible with the fluid for which the joint was designed and with which it will be operated. In-storage protection devices or substances must be completely removed and the parts must be recleaned and inspected prior to assembly. j. Refurbishment and Reuse Practices Seals can be refurbished by replating and reinspecting them to the original manufacturing standards. Seals that are reused without refurbishment should be indexed to provide reassembly in the same position as originally installed. Seals with damaged coating can be stripped and recoated or replated as long as the parent metal seal is dimensionally correct. Technical Rationale: These practices were derived from a review of Unsatisfactory Condition Reports (UCRs) of the PRACA system at Marshall Space Flight Center; from sources listed in the references including professional journal articles, presentations, books on cryogenics, and Government reports; and from over 30 years of experience in designing propulsion systems and stages incorporating cryogenic sealing requirements. References: Allen, P. and H. Becker, quotSealing for Long-Term Space Applicationquot, 3rd Annual AIAA/GNOS Aerospace Technology Symposium, November 7-8, 1985. American Institute of Aeronautics & Astronautics. Brincka, D. R., quotHigh Pressure Static Seals for Aerospace Applicationsquot, 36th International Astronautical Congress: Stockholm, Sweden, October 7-12, 1985. IAF. Burr, M. E., quotDevelopment of Large Diameter High Pressure, Cryogenic Radial Static Sealsquot, Lubrication Engineering, (December, 1977), 638-643. quotCritical Items List (CIL) MC-ET-RA04b-Hquot, Volume II Propulsion/Mechanical, Huntsville: NASA, MSFC, May 1, 1991. Daniels, C. M., quotAerospace Cryogenic Static Sealsquot, Lubrication Engineering, (April 1973), 157-167. Daniels, C. M., quotDevelopment of Flightweight Static Face Seals for 75.84 MPa (11,000 psi) Pressure and Cryogenic Temperaturesquot, Lubrication Engineering, (October 1978), 552-562. quotDucts/Lines, Joints and Orificesquot, Volume XI. Failure Mode and Effect Analysis (RSS-8553-11) Critical Items List (RSS-8740-11): January, 1991. Rockwell International, Rocketdyne Division. quotFailure Modes and Effects Analysis (FMEA) MMC-ET-RA04a-Kquot, Volume II Propulsion/Mechanical, Huntsville: NASA, MSFC, May 1, 1991. Hunter, Rick C. and Ready J. Johnson, quotGas Transmission Through a Plastically Deformed Metallic Interfacequot, Energy Sources Technology Conference and Exhibition: Houston, January 22-25, 1989. American Society of Mechanical Engineers. Russell, Dr. John M., quotOn the Selection of Materials for Cryogenic Seals and the Testing of Their Performancequot, 1989 NASA/ASEE Summer Faculty Fellowship Program, August 18, 1989. John F. Kennedy Space Center and University of Central Florida. Schwinghamer, quotLeak Team's Final `Eureka' Anthem,quot Hydrogen Leak Investigation Team Final Report, (Presentation) Huntsville: NASA, MSFC, November 8, 1990. CreaveyTM is a registered trademark of the Creavey Seal Company. Raco® is a registered trademark of the Furon Company. Teflon® is a registered trademark of E.I. DuPont de Nemours & Co. Inc. Definitions cryogenics. Temperature region of liquified gases below 123 deg.K (-150 deg.C). ET. External tank. GH2. Gaseous hydrogen. GO2. Gaseous oxygen. high nickel alloy steel. A heat-treatable, nickel-base (53 percent) steel alloy with good properties at both cryogenic and elevated 922 deg.K (1200 deg.F) temperatures. leak. Defined in text. LH2. Liquid hydrogen. LO2. Liquid oxygen. scim. Standard (atmospheric) cubic inches per minute; volumetric flow rate. scratch, nick, or gouge. A damaged area in which material has been removed, or moved, with a resultant decrease in wall thickness. SSME. Space Shuttle Main Engine. static seal. A device used to prevent leakage of a fluid through a mechanical joint in which there is no relative motion of the mating surfaces other than that induced by changes in the operating environment. | This practice has been used on Saturn I, Saturn V, Space Shuttle External Tank (ET), and Space Shuttle Main Engine (SSME). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/15/2000
700 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Fracture Mechanics Reliability |  | Nonpractice of deterministic fracture mechanics analysis (or test) in a spacecraft or launch vehicle program would result in the failure to meet NASA design requirements for fracture control [references 11 and 12]. Failure to adequately consider fatigue in the design of structural and mechanical components subject to fluctuating loads may, at best, result in recurring costs for repair or replacement of components before their intended design life. At worst, a catastrophic failure, in terms of economic loss and loss of life, may result. It is standard JSC engineering practice to specify fracture control requirements on structural and mechanical components that are classified as fracture critical. As a part of these requirements, it is required that a component be shown by analysis or test to be able to survive a deterministic minimum number of service lifetimes (usually 4) without the largest possible undetectable flaw growing to failure [references 11 and 12]. While this process has proven to be adequate to ensure against failure, design practices which do not take advantage of stochastic methods for fracture analysis may produce over-conservative and uneconomical structures and mechanisms. In mechanical or structural system reliability analyses, failure to use a stochastic fatigue or fracture mechanics approach to the estimation of reliability will result in life estimates that are incompatible and inconsistent with the results of the standard NASA deterministic safe-life analyses required by the Space Shuttle and Space Station Programs [references 11 and 12]. | Use a fracture mechanics formulation to estimate the design fatigue life and reliability of metallic or ceramic structural and mechanical components subject to fluctuating stress. For reusable spacecraft, update the reliability analysis based on in-service inspection and repair data. | JSC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GD-AP-2304 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Consideration of fracture mechanics reliability during the design process can assist in the prevention of failures of structural and mechanical components subject to fluctuating loads in service. Explicit consideration of the reliability of structural and mechanical components provides the means to evaluate alternate designs and to ensure that specified risk levels are met. Probabilistic fracture mechanics analyses may also be applied to life extension of existing structures, and for problem assessment of in-service fatigue failures. Potential applications of this method to the Space Shuttle or Space Station include: landing gear, control surfaces, main engine components, auxiliary power unit components, external tank and solid rocket booster welds, pressure vessels, propulsion modules, and logistics modules. The method is also applicable to reusable, Shuttle launched payloads or spacecraft such as Spacelab, Spacehab, EURECA, SPAS and Spartan. Stochastic fracture mechanics analysis provides the basis for analysis consistency between reliability analysis of mechanical systems, such as reliability block diagram analysis, and traditional deterministic fracture mechanics safe life estimation. Implementation Method: The method outlined below is a stochastic elastic fracture mechanics approach (for metallic or ceramic materials) which neglects any crack retardation or acceleration effects. Composites and other materials with insufficient crack growth data or intractable flaw growth characteristics are not considered. The detailed development of this approach is essentially the same as that given in references 1 through 6. The purpose of the simplified approach described herein is to illustrate some of the advantages and typical results of a stochastic fracture mechanics analysis. Discussion of technical implementation details, such as the use of crack growth laws other than the Paris equation (for example, the modified Forman equation [reference 15]), follows in the technical rationale section. For illustration, a Paris crack growth law is assumed, which may be written in the form of a differential equation. For random applied stress processes, a solution can be written in the form of a limit state function, M, as: [D] (1) in which: [D] Failure is defined to occur when the critical crack length, a c, is exceeded, so that at failure M <0. The probability of failure is then the probability that the limit state function is equal to or less than zero: [D] (2) The first term of Equation 1, the integral, essentially defines the fatigue resistance of the structure against a crack growing from an initial size, ao, to critical size ac. This integral must be evaluated numerically in all but the simplest of cases. Particular forms of the geometry function, Y(a), are available for simple configurations in the literature or from general purpose fracture mechanics software packages. For unique structural details, other approaches are available to determine Y(a), such as detailed finite element modeling of the cracked structure. The second term of Equation 1 defines the accumulated quotdamagequot caused by the applied stress process. A random stress process is characterized by its power spectral density and may be described as being narrowband (slowly varying random) or as wideband. In either case closed form approximations for the second term of Equation 1 are available. If the stress process is deterministic or if time histories of the stress process are available time domain methods, such as rainflow cycle identification [reference 10], approximations are available for determining the factors in the second term of Equation 1. It should be noted that all of the terms in Equation 1 may be treated as random or uncertain. This enables the modeling of all the sources of uncertainty pertinent to the problem, such as crack size and location, scatter in crack growth data, etc. Subsequent sensitivity analyses can be used to determine which variables contribute the most to the fatigue life uncertainty and require treatment as random, and which variables may be considered as fixed (deterministic). Sensitivity analysis can also indicate the parameters for which further data collection could reduce the overall uncertainty in the fatigue life. Modern reliability methods, the so-called First-Order Reliability Method (FORM) or Second-Order Reliability Method (SORM), are available in commercial computer programs to solve Equation 2. Monte Carlo or more sophisticated simulation techniques are also available [references 1, 7, 8, and 9]. In particular, PROBAN [1] has been available commercially from Det Norske Veritas (Oslo, Norway) since 1986 and has been used extensively in the offshore oil industry. PROBAN is available for UNIX and VAX/VMS based workstations. STRUREL is a PC/Windows based application available from RCP, GmBH, of Munich, Germany. RELACS is a similar package available from REA, Inc., of Golden, Colorado. A NASA-funded application called NESSUS, which runs on UNIX workstations and mainframes, is available from the Lewis Research Center. The commercial codes are recommended because of better user-interfaces and better user support. Monte Carlo approaches generally require direct programming for the solution for the specific problem under study. For a structure or mechanism in service, the results of inspections may be incorporated into the analysis and the estimated failure probabilities updated to show the change in reliability based on the additional information on existing crack size. For each inspection, two outcomes are possible: either no crack is detected, or a crack is detected and its size or length is measured. Figure 1 is an example analysis result (from reference 1) showing reliability as a function of time for which inspections were assumed at 10 and 20 years, with no crack detected at 10 years, but a 4.0 mm crack detected at 20 years. Note that with the new information gained from inspection at t=10 years, the reliability is shown to increase as no crack was found. After inspection at t=20 years, reliability is also shown to increase even though a small crack was detected, but only for a short time. The increase at t=20 years can be attributed to the discovery that the crack length was less than the critical crack length for the structure, but it should also be noted that the reliability decreases much faster with the uncertainty tied to the presence of a flaw. Inspection of structures and the new information that is gained can essentially reset the reliability, and even though a crack may be discovered, this new information can lead to increased inspections, which can lengthen the life of the item. However, a crack detection generally decreases the reliability, as in this case after about t=22 years. [D] Technical Rationale: A stochastic fracture mechanics approach to fatigue gives an estimate of the reliability of structural and mechanical components as a function of time in service and allows the reliability estimate to be updated if the results of in-service inspections and/or in-service load data are available [references 1 and 2]. The procedure may also be used to optimally schedule inspections, and to compare the adequacy of different inspection types or quality levels [references 1 and 2]. Type and quality of repair techniques may also be compared and selected to maintain a desired reliability level. Updating of these analyses as actual inspections or repairs occur is also possible [references 2 and 3]. The application of in-service reliability estimates is dependent on the availability of some form of flight load data and accessibility to the structure or mechanism for inspection. Without such data no updating of the initial design reliability analysis is possible. The primary intent of this guideline is to make available to the NASA reliability engineering discipline the engineering mechanics-based methods for estimating the reliability of structural and mechanical components. Use of such methods would allow for consistency of models and data between the reliability and structural/mechanical engineering disciplines within NASA. A stochastic fracture mechanics approach provides a quotphysics-of-failurequot basis for estimating the reliability of components subject to fatigue and fracture. This enables fault tree or reliability block diagram analyses, or probabilistic risk assessments, for structural and mechanical components in spacecraft systems to be performed using the same data and engineering mechanics models as the NASA accepted, deterministic fracture analysis procedures [reference 14]. For example, the mean time to failure for a pressure vessel girth weld (as may be needed for a propulsion system reliability block diagram analysis) estimated using probabilistic fracture mechanics would be rationally consistent with the safe-life analysis performed to meet current NASA fracture control and safe-life analysis requirements. The approach outlined herein is a simplified formulation that neglects load interaction effects, such as retardation, by using the Paris crack growth law. If a Paris equation is properly fit to the basic crack growth data, the resulting deterministic safe life estimate will be more conservative (shorter) than the estimated life resulting from a fracture analysis which incorporates retardation. The current NASA accepted practice in fracture mechanics analysis uses the computer program NASA/FLAGRO, which includes interaction effects. Load interaction effects may be included in a stochastic fracture mechanics analysis by using crack growth laws such as the modified Forman equation found in NASA/FLAGRO. For example, a FORM/SORM formulation which included the modified Forman equation has been used to study aircraft durability and damage tolerance [reference 14]. A direct Monte Carlo solution implementing the modified Forman equation may also be found in references 7, 8, and 9. Issues related to the implementation, applicability, and accuracy of FORM/SORM and Monte Carlo methods are beyond the scope of this guideline. In general, if a fracture mechanics reliability analysis is to be performed and it has been determined from a preliminary deterministic fracture analysis thatthe Paris formulation is inadequate, the modified Forman equation (as in NASA/FLAGRO) should be used following either the approach described in reference 14 or in references 7, 8, and 9. Two critical parameters in any fracture analysis, deterministic or stochastic, are the size, location and distribution of initial flaws or cracks, and the ability of nondestructive evaluation (NDE) techniques to detect a flaw or crack smaller than a certain size. NASA has established standard NDE flaw sizes for Space Transportation System (STS) payloads [reference 14]. Two recent NASA research projects, one directed at establishing NDE probability of detection (POD) data, and one directed at gathering initial flaw distribution data, also may provide additional data for modeling initial flaws and NDE quality. Deterministic fracture analysis practice uses relatively large safety or quotscatterquot factors to account for the many inherent sources of uncertainty or error, such as analytic model inadequacies, inaccuracy of stress intensity predictions, and the scatter of experimental crack growth data. Stochastic analysis methods extend the accepted deterministic methods by allowing (or forcing) the analyst to explicitly account for these uncertainties by treating them as random variables (or process or fields), requiring the analyst to consider the likely range and distribution of the parameters. Both the deterministic and the stochastic analysis will suffer from the same shortcomings of model inadequacy, etc. The stochastic model has the advantage of addressing the uncertainties specifically using probability and statistical theory, while the deterministic approach addresses uncertainty in a general manner through the use of the safety or scatter factor. Use of a stochastic approach and a reliability based design criteria can be beneficial in avoiding over- or under-conservatism that may result from the use of a deterministic safety factor approach. References: PROBAN-2: Example Manual, Report No. 89-2025, A.S Veritas Research, Hovik, Norway, August, 1989 Madsen, H.O., Skjong, R.K., and Kirkkemo, F., quotProbabilistic Fatigue Analysis of Offshore Structures - Reliability Updating Through Inspection Resultsquot, A.S Veritas Research, Hovik, Norway Madsen, H.O., Skjong, R.K., Tallin, A.G., and Kirkemo, F., quotProbabilistic Fatigue Crack Growth Analysis of Offshore Structures, with Reliability Updating Through Inspectionquot, Society of Naval Architects and Marine Engineers, Proceedings, Marine Structural Reliability Symposium, Arlington, VA, October 5-6, 1987 Wirsching, P.H., Torng, T.Y., and Martin, W.S., quotAdvanced Fatigue Reliability Analysisquot, International Journal of Fatigue, Vol. 13, No. 5, 1991, pp. 389-394 Wu, Y.-T., Burnside, O.H., and Dominguez, J., quotEfficient Probabilistic Fracture Mechanics Analysisquot, Numerical Methods in Fracture Mechanics: Proceedings of the Fourth International Conference, Luxmoore, A.R., Owen, D.R.J., Rajapakse, Y.P.S., and Kanninen, M.F., Eds., Pineridge Press, Swansea, U.K., 1987 Veers, P.S., Winterstein, S.R., Nelson, D.V., and Cornell, C.A., quotVariable-Amplitude Load Models for Fatigue Damage and Crack Growthquot, Development of Fatigue Loading Spectra, STP 1006, American Society for Testing and Materials, 1989 Sutharshana, S., et al., quotA Probabilistic Fracture Mechanics Approach for Structural Reliability Assessment of Space Flight Systemsquot, Advances in Fatigue Lifetime Predictive Techniques, STP 1122, American Society for Testing and Materials, 1991 Sutharshana, S., et al., quotComputational Methods for Probabilistic Flaw Propagation Analysesquot, Proceedings of the ASCE Structures Congress '91, April, 1991 Moore, N. R., et al., quotAn Improved Approach for Flight Readiness Certification - Probabilistic Models for Flaw Propagation and Turbine Blade Failurequot, JPL Publication 92-32, December, 1992. Matsuishi, M., and Endo, T., quotFatigue of Metals Subjected to Varying Stressquot, Presented to the Japan Society of Mechanical Engineers, Fukuoka, Japan, March, 1968. Fracture Control Requirements for Payloads Using the National Space Transportation System, NHB 8071.1A Fracture Control Requirements for Space Station, SSP 30558 Sigurdsson, G., et al., quotProbabilistic Methods for Durability and Damage Tolerance Analysisquot, presented at the 1992 USAF Aircraft Structural Integrity Program Conference (ASIP), San Antonio, Texas, December 1-3, 1992. quotFatigue Crack Growth Computer Program NASA/FLAGRO Version 2.0quot, JSC-22267A (Draft), January, 1993. Reliability Preferred Practices Guideline GD-AP-2303: Spectral Fatigue Reliability |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/15/2000
702 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Magnetic Design Control for Science Instruments | Preferred Practice for Design & Test. Magnetometer experiment data will be corrupted by variable and unpredictable spacecraft residual magnetic field noise, thus limiting the accuracy of the magnetic field experiment. Design flight subsystems with low residual dipole magnetic fields to maintain the spacecraft's total static and dynamic magnetic fields within science requirements. | Magnetometer experiment data will be corrupted with variable and unpredictable spacecraft residual magnetic field noise, thus limiting the accuracy of the magnetic field experiment. | Design flight subsystems with low residual dipole magnetic fields to maintain the spacecraft's total static and dynamic magnetic fields within science requirements. | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1207; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Provides for a magnetically clean spacecraft, which increases the quality and accuracy of interplanetary and planetary magnetic field data gathered during the mission. Implementation Method: Because the dipolar portion of a spacecraft's magnetic field at its magnetometer experiment sensor location dominates the nondipolar part, each spacecraft subsystem is assigned a maximum allowable dipole magnetic field specification based on the magnetometer sensor sensitivity and the distance between the bulk of the subsystems and the sensor location. A typical maximum dipolar field allocation is 10 nanoTeslas (gammas) at a distance of 1 meter from the geometric center of a spacecraft's subsystem, assuming the magnetometer sensor is mounted at the end of an 8-meter boom. To ensure that each subsystem will meet its respective dipole field specification, several design practices are observed during the early stages of the subsystem design. These practices include: Magnetic Shielding of Magnetic Components A magnetic source can be enclosed in a high permeability material shield, which in effect confines the source's magnetic flux to within the walls of the shield enclosure. The shield should be completely enveloping, with the minimum number of holes and cutouts. The shield must be annealed after all machining and forming operations are completed. A general rule of thumb is to design the shield to operate within the linear range of the permeability curve between points A and B. [D] Compensation of Magnetic Components A magnetic component can be neutralized by placing on or near its surface an equal but opposite field vector using compensation magnets or current loops. [D] Redesign of Circuit Board Current Paths to Reduce Loop Area Coverage Because a magnetic field B is proportional to loop area geometry A, number of loop turns N, and current flow I through a circuit, a reduction in A produces a reduction in the magnetic field B, while still leaving I and N intact. [D] Replacement of Ferromagnetic Parts with Nonmagnetic Parts Another method for reducing magnetic fields is by simply replacing ferrous materials with nonmagnetic materials, preferably with relative permeability mr of approximately 1 so that the magnetic susceptibility cm is kept at approximately 0. [D] where m = momr, mr = 1 + cm, and mo is the permeability of vacuum. All spacecraft subsystems are individually subjected to a testing program aimed at fully characterizing each of the subsystems' magnetic traits, as well as determining compliance with dipole field specifications. This testing program includes several exposures to magnetizing fields of 25 Gauss and 3 Gauss to uncover easily permeable materials contained within the subsystem, and several exposures to demagnetizing fields of 50 Gauss and 40 Gauss to eliminate or reduce a subsystem's residual magnetic field. Based on the above test program, a data base is established containing subsystem information such as the X, Y, and Z spacecraft coordinates, maximum and minimum measured static magnetic fields, measured dynamic fields, and the calculated dipole moment components. From this data base, the total spacecraft static and dynamic dipole fields at the magnetometer sensor location are calculated using computer code, and are continually updated as new information becomes available. Results then are compared with the spacecraft's static and dynamic magnetic field science requirements. Technical Rationale: A spacecraft's total allowable magnetic field at the magnetometer sensor location r usually is determined by the sensor's sensitivity level or by an agreed upon science requirement. The total field can be approximated by N number of dipoles, with N representing all of the spacecraft subsystems. To guarantee that the spacecraft's total magnetic field at r is within the desired allowable range, the individual moments due to N number of dipole sources must be kept to within predetermined dipole moment specifications. These individual specifications are derived by distributing the total allowable spacecraft moment amongst N number of spacecraft sources using a model that consists of a number of randomly oriented dipoles of strength Mj. The magnitude of the spacecraft's dipole magnetic moment is approximated by the Pythagorean sum of these individual subsystem dipole moments, with the radial part tending to be greater than either of the transverse components for the dipole portion. The individual magnetic dipole field allocation, therefore, is determined from this model by the following equations: [D] where B R,B Q, and B F are the field components of the spacecraft's magnetometer experiment sensor sensitivity or the science requirement levels at location r. Thus, M j can be determined for all spacecraft N sources assuming that M j is the same for all j and the magnetic moments determining the far field are linear functions of the vectors M j. Because the dipolar portion of the spacecraft magnetic field dominates the nondipolar part and the spacecraft is dominated by the few largest sources, the general field allocation B s for a subsystem at a normalized distance of R meters is thus derived from M j as follows: [D] By ensuring that the dipole moment specifications of all spacecraft subsystems, as represented by N number of dipolar sources, are within their respective allocated dipole moment specifications, the overall spacecraft magnetic field at the magnetometer sensor location can be kept to within its science requirement or to below the magnetometer's sensitivity level. Final verification is done by measuring the magnetic fields of all spacecraft subsystems and, subsequently, calculating the magnitude and orientation of their respective dipole moment components Mxj, Myj, and Mzj at spacecraft coordinates Xj,Yj, and Zj. The total spacecraft magnetic field at the magnetometer sensor location r then can be modeled using computer code to verify compliance with the specified science requirement or magnetometer experiment sensitivity. | This practice has been used on Mariner series, Voyager (VGR), Galileo (GLL), Ulysses. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/15/2000
699 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Structural Analysis in the Design of Optical Mirrors |  | Not using a detailed structural analysis of a mirror/mount design can lead to a design which in the worst case will not meet its optical performance objectives. Even if optical performance objectives are met, the design may be overly conservative in certain aspects resulting in a design that is overweight, more complex, and more expensive than necessary, For example, an interface flatness may be over specified in the design when in reality it may not be a major source of overall mirror distortion, thereby greatly increasing manufacturing cost. | The use of structural analysis as part of a concurrent engineering effort including thermal and optical analysis in the design of optical mirrors and assessment of their optical performance to assure reliable optical and structural performance. Early in the design process, structural analysis can assist in determining allowable thermal conditions, evaluate various mounting concepts, and provide initial optical performance for assumed thermal environments. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline number GD-AP-2305 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The use of detailed structural analyses throughout the design/development process of a mirror, either stand-alone or as part of a concurrent engineering structural-thermal-optical performance (STOP) analysis, will result in a minimum weight mirror design which is able to meet all of its performance criteria and enhance the reliability of the overall optical system. Implementation Method: A detailed structural analysis of an optical mirror and its mounting performed throughout the design/development cycle is crucial to developing a design which will meet all mirror requirements. The first step in being able to predict reliable mirror performance characteristics is in the development of an accurate detailed finite element model (FEM). This involves not only developing a model using good modeling techniques, but also ensuring mathematical validity of the model. Next, the required analyses must be identified. Besides having to meet optical requirements under effects such as deformations due to thermal profiles and 1-G release, the design will have to exhibit adequate strength capability due to loads from launch and possibly thermal induced growth. Also, desired design features such as coating thicknesses can be derived from early analyses. Because of the extremely small deformations involved in mirror distortion analyses, the validity of the use of finite element models has been suspect. As long as the disturbance sources (typically temperatures) are large enough to develop forces large enough to be out of the numerical noise of the computer, the resulting results should be linear and valid from a numerical standpoint. Finite Element Modeling Techniques [D] Because extremely small deformations can significantly degrade mirror performance (on the order of micro-inches), the use of good modeling techniques is essential. A typical lightweight mirror design is based on a rib-stiffened facesheet. This structure may be either closed on the back with a back facesheet or left open. In either case, plate elements are typically used for the facesheet and ribs, and the back close-out if appropriate. An example of an open back lightweight mirror is shown in Figure 1. A minimum of three nodes of resolution through the thickness of the structure is often desired. This level of detail will allow a 2nd order variation in temperature through the thickness of the mirror to be applied in subsequent analyses. The minimum facesheet nodal resolution may be dictated by the rib mesh necessary to maintain good aspect ratios in the rib elements. Beyond this level of detail, it is many times of interest to include at least one grid on the facesheet interior to a given cell (i.e., not a part of any rib structure). This will allow the facesheet deformations typical of quilting to be portrayed. Plated facesheets are commonly represented as composites using composite property behavior. In addition, the supporting rib structure may also be represented as a composite material if it is also plated. By doing this, deformations due to the coefficient of thermal expansion (CTE) difference between the base material and the plating when undergoing bulk temperature changes will be able to be portrayed (many times a very significant factor). Because of the relatively large uncertainty in the disturbance sources and the material property characteristics relative to the deformation magnitudes being calculated, many times it is more desirable to do the analyses on a parametric basis where sensitivities of the deformations to various parameters may be more significant than the absolute answers themselves. By identifying the most sensitive parameters, mirror design trades can be made on a relative basis for a given environmental condition. Also, an already selected mirror design may either be modified, or the fabrication process closely monitored to minimize the effect of these parameters instead of having to rely on the absolute correctness of the optical degradation. For example if the interface flatness of a mirror is found to be an unusually critical design factor, this finding alone may be enough to cause the design details to be modified or to trade off different mirror designs in an attempt to minimize this effect. Finite Element Model Validation Again, because of the typically small deformations of interest in mirror distortion analyses, the importance of performing a complete mathematical validity check of the FEM cannot be overemphasized. To ensure proper mathematical FEM behavior, following are some of the model checks which should be performed: Line-by-line check of input data decks to ensure input accuracy. Static run with fixed boundary conditions and 1-G loads applied separately in each axis, reviewing resultant displacements, forces, and stresses for reasonableness, symmetry, etc. Free-free modal run to calculate rigid body modes. These modes should be two orders of magnitude less than the first flexible mode, generally less than .001 Hz to ensure that there is no inadvertent grounding of the structure. Equilibrium checks of the model which are calculated by multiplying the free-free stiffness matrix by the geometrically derived rigid body modes. Nodes at which the structure is grounded should be displayed in a tabular form. A thermal equilibrium check in which a bulk temperature change is imposed on a kinematically constrained model which has all thermal expansion coefficients set equal to a common value. Negligible element forces should be generated with the model exhibiting free expansion with relative deformation values between points equal to CTE x L x DT where CTE is the coefficient of thermal expansion of the mirror material, L is the distance between the points, and DT is the temperature difference from reference being imposed. RMS and peak-to-valley mirror surface deformations calculated should be equal to theoretical values. The difference being the quotnoisequot level inherent in all subsequent analyses (analysis predictions can only be made to levels approaching this level). A bulk temperature check with all CTE values set to their correct values. The resulting structure should deform in a predictable way (i.e., concave or convex) depending on material mismatches and platings present. Inspection of all FEM software messages and warnings which might indicate among other things, improperly shaped elements, ill-conditioning, mechanisms, etc. Comments relative to automatically imposed constraints in particular must be verified to be appropriate. Mass properties should be compared to approximate hand calculations during the early stages of design and to the actual value if the mirror has been fabricated. Correlation with actual mirror fundamental mode shapes and frequencies if data exists. A duplicate analysis run should be made with the input disturbance (typically temperatures) doubled. Results should also double indicating that the actual solution is not operating in the numerical noise of the computer. Data Reduction and Reporting Optical distortions are typically reported as a wavefront error in units of waves where one wave is equal to the shortest wavelength of interest. The performance of an optical system is frequently given in terms of cumulative RMS wavefront error at the focal plane. Errors in the wavefront are twice the mirror surface deformations. Typically these values are specified in both RMS and peak-to-valley relationships. Initial structural analyses may only report the mechanical distortions of the mirror surface in these terms for a quick assessment of optical performance. Later analyses, however, should not only report these mechanical deformations, but should be evaluated in terms of the Zernike coefficients. These coefficients are typically calculated as part of an optical analysis and provide a mathematical means of describing the mirror surface. When analyzing an existing mirror design for distortion, it may be desired to include the effect of the actual mirror surface figure errors as polished. Because these surface figure errors are small and will not alter the mechanical behavior of the mirror FEM if included in the undeformed geometry data, their effect should be added to the deformations resulting from a structural distortion analysis. Initial Design Activity During the initial phase of a lightweight mirror design, the first design parameters that must be specified are the rib thicknesses, rib spacing, and facesheet thickness. The minimum facesheet thickness required for a given rib spacing (described by the diameter of an inscribed circle in a single cell pocket) is determined by deciding on an acceptable level of optical distortion at ambient conditions due to quilting — the phenomenon whereby the facesheet material is pushed away from the polishing tool as opposed to being polished away. As a result, once the tool passes a given cell, the center of the facesheet in that cell will tend to spring back close to its original position. Because of the higher stiffness of the facesheet along the ribs, this motion does not occur and relatively larger amount of facesheet material is removed along the ribs. As a result, when finished, the facesheet is higher at the center of each cell pocket as opposed to along the rib paths and the mirror surface appears to be quotquiltedquot when tested optically. Once an acceptable level of quilting is determined (many times as low as 1/80th of a wave), the facesheet thickness is fixed for a given rib spacing and assumed mechanical polishing pressure. It should be noted that for certain optical figuring techniques, e.g. ion beam figuring, there is no mechanical pressure applied to the mirror surface and therefor no resulting quilting. During this initial design phase, mirror optical performance is typically tracked primarily mechanically in terms of RMS and peak-to-valley deformations of the mirror surface. Because thermal conditions are not typically known to a detailed level, optical degradation is calculated for general thermal conditions such as uniform bulk temperature changes, linear gradients in each axis, and a radial gradient from the center of the mirror to its edges. These initial studies are not only necessary for preliminary optical performance assessment, but give an early insight into sensitivities to certain thermal conditions which can possibly impact the thermal design. Also, simultaneously during this phase, various means of supporting the mirror are investigated. At this time preferred support points and methods are selected based not only on thermal growth requirements, but on stress requirements due to launch loads. Detailed Design Activity The anticipated thermal environment has been defined prior to detailed design and can be incorporated into the structural model for on-orbit thermal distortion optical degradation calculations. Depending on the thermal model employed and where temperature data is calculated, different methods of mapping these temperatures onto the structural model are employed. [D] [D] A common method is to rely on a thermal model developed similar to the structural model, ie. thermal nodes corresponding to individual rib elements and the facesheet. Temperatures at thermal nodes then will have a physical point on the structural model at which this temperature can be specified. By doing this for all thermal node points, which is typically a much smaller set of points than the structural grids, a thermal analysis is performed on the structural model to determine temperatures at all remaining structural grid points. A potential problem exists with this technique, however, due to the fact that unspecified structural temperatures are interpolated from surrounding temperatures in an iterative fashion until thermal equilibrium is achieved (relaxation technique). Figures 2 and 3 illustrate this potential problem by showing vastly different thermal equilibrium temperature distributions resulting from attempting to specify a 1. to 10. degree linear gradient in a plate two different ways. Figure 2 shows the resulting equilibrium temperature distribution when the temperatures are specified only at the four corners. Figure 3 shows the temperature distribution when the same gradient is applied by specifying a fixed temperature along both edges of constant temperature. The structural distortions which would result from the imposition of these two thermal environments would be vastly different. Therefore it is advised that the structural analyst work closely with the thermal analyst to determine if additional temperature constraints need to be imposed upon the set of discrete temperatures specified at distinct thermal nodes obtained from the thermal analysis. Another technique used to map thermal analysis temperature results onto a structural model is based on developing a thermal model consisting of homogeneous bricks for the rib structure with the thermal behavior of these bricks modified to account for discreet rib behavior. Temperatures at individual structural grids can then be calculated by a using a simple three dimensional interpolation of the surrounding thermal nodes. A third technique which eliminates all thermal mapping errors is for the thermal structural analysts to use the same model. A potential problem with this method, however, is the long computation time necessary for full orbital temperature calculations. Mechanical surface deformations at this time are then input to an optical analysis for an assessment of the optical quality of the surface. These deformations can be directly input into certain optical analysis software packages (CODE-V for example) or by calculating Zernike polynomials for the deformed surface which can then be used for further optical analysis. Technical Rationale: The use of finite element analyses to predict structural deformations due to loads (both mechanical and thermal) is a widely understood and used practice that is readily available. With a relatively minor effort, the major sources of distortion in a mirror can be identified and minimized. References: Valenta, Tina M. and Vukobratovich Daniel, quotA Comparison of the Merits of Open-Back, Symmetric Sandwich, and Contoured Back Mirrors as Light-Weighted Optics,quot SPIE - the International Society for Optical Engineering, Vol. 1167, 1989. Yoder, Paul R., quotOpto-Mechanical Systems Design,quot Marcel Dekker, Inc., New York, 1986. Mehta, Pravin K., quotFlexural Rigidity Characteristics of Lightweighted Mirrors,quot SPIE - the International Society for Optical Engineering, Vol. 748, 1987. Cho, Myung K., Richard, Ralph M., and Hileman, Edward A., quotA Comparison of Performance of Lightweight Mirrors,quot SPIE - the International Society for Optical Engineering, Vol. 1340, 1990. Pepi, John W., quotAnalytical Predictions for Lightweight Optics in a Gravitational and Thermal Environment,quot SPIE - the International Society for Optical Engineering, Vol 748, 1987. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/15/2000
698 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Ammonia-Charged Aluminum Heat Pipes with Extruded Wicks |  | Heat transfer by means other than the heat pipe can have the following impacts: a price paid with respect to weight and size of the heat transfer equipment, significant heat lost in transfer over considerable distances, electromotive devices, such as liquid pumps, required to move the heat, and possible problems presented by operation in zero gravity. Nonadherence to the implementation methods presented above could result in the following possible impacts: improper cleaning and processing of the aluminum container could result in contaminants reacting with the ammonia to form NCG, which will interfere with the flow of vapor and reduce the heat transfer effectiveness. Contaminants reacting with ammonia normally produce hydrogen, and the gas collects in the condenser region. As more and more of the condenser is blocked, the surface area available for heat rejection decreases, reducing the heat transfer effectiveness; ultimately, the heat pipe may cease to function. Failure to certify welds at the end caps and the fill tube could result in improper or defective welds permitting leaks or catastrophic failure of the pressure vessel. For long-term space missions, working fluids in the appropriate temperature range, such as methanol and water, exhibit an incompatibility with aluminum, and should not be used. | Use heat pipes, preferably aluminum heat pipes charged with anhydrous ammonia, in spacecraft and instrument thermal control applications. This practice enhances the control and flow of heat generated within the spacecraft. | GSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1209; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Heat pipes use the latent heat of vaporization of a working fluid to transfer heat efficiently at a nearly constant temperature. This characteristic can be used to control the temperature of spacecraft components and systems. The Goddard Space Flight Center (GSFC) has chosen ammonia-charged aluminum heat pipes for most near-room temperature (200°K to 350°K) applications. The axial groove aluminum pipe is the design of choice, because it is easy to design and relatively easy to fabricate. The aluminum container and axial grooves are extruded in one process. At the operating temperature of unmanned spacecraft, ammonia has the most favorable thermodynamic properties that make it an excellent heat pipe working fluid. Anhydrous ammonia is compatible with the aluminum heat pipe body and wick if proper care is taken in the manufacturing process. Implementation Method: All heat pipes have three physical elements in common. These include an outer container, a small amount of working fluid, and a capillary wick structure. In addition to these basic components, heat pipes may also include gas reservoirs (variable conductance/diode heat pipes) and liquid or gas traps (diodes). Functionally, the heat pipe consists of three sections: evaporator, condenser section, and adiabatic regions. The evaporator section is mounted to the heat-producing components, while the condenser is thermally coupled to a heat sink or radiator. The adiabatic section allows heat to be transferred from the evaporator to the condenser with very small heat losses and temperature drops. Figure 1 depicts the basic heat pipe. [D] Heat pipes can operate in the fixed conductance, variable conductance, or diode mode. The fixed conductance heat pipe can transfer heat in either direction and operates over broad temperature ranges, but has no inherent temperature control capability. Constant conduction heat pipes allow isothermalization of shelves, radiators and structures; spread heat from high heat dissipating components; and conduct heat away from heat producing devices embedded within instruments and satellites. In the variable conductance heat pipe (VCHP), a small quantity of non-condensable gas (NCG) is loaded into the heat pipe. The VCHP can be used to control the temperature of equipment within very narrow limits; control is possible to less than 1°K by using careful design techniques. This is accomplished by controlling the location of the NCG/vapor interface within the condenser end of the heat pipe, thereby varying the active length of the condenser and causing a modulation in the condenser heat rejection capability. Temperature control of the attached device is achieved by an active feedback system consisting of a temperature sensor at the heat source and a controller for a heater at the NCG reservoir. The heater causes the gas in the reservoir to expand, thus moving the gas/vapor interface. Diode heat pipes permit heat to flow in one direction and inhibit heat flow in the opposite direction. Specific benefits of heat pipes are: 1) heat pipes have enormously more heat transfer capability than other methods on a weight and size basis, 2) heat pipes permit configuration flexibility in contact areas with heat sources and heat sinks, 3) heat can be transported over considerable distances with insignificant temperature drop, 4) capillary pumping in the wick is generated by the heat transfer process and requires no other power or moving parts to pump the condensate, and 5) heat pipes operate satisfactorily in a zero gravity environment. The choice of working fluid is dictated by several considerations, including operating temperature, latent heat of vaporization, liquid viscosity, toxicity, chemical compatibility with container material, wicking system design, and performance requirements. Figures 2 and 3 and Table 1 depict some of the above characteristics for several fluids. The highest performance from a heat pipe is obtained by utilizing a working fluid that has a high surface tension (s), a high latent heat (l), and a low liquid viscosity (n1). These fluid properties are contained in the parameter N1 the Liquid Transport Factor. Figure 4 is a plot of N1 for five typical heat pipe working fluids. These data are used as selection criteria for heat pipe working fluids. Once an application is defined, the heat pipe designer reviews the requirements and selects the best working fluid. Below the freezing point of water and above about 200°K, ammonia is an excellent working fluid. Regardless of the fluid chosen, minimum purity must be at least 99.999 percent. A careful analysis of the purity of the ammonia should be obtained from an independent laboratory prior to use. [D] [D] [D] Table 1: Comparison of Latent Heat to Specific Heat for Typical Heat Pipe Fluids FLUID PROPERTIES FLUID BOILING POINT &$176;K LATENT HEAT kJ/kg hfg SPECIFIC HEAT kJ/kg-°K cp RATIO K hfg/cp Helium 4 23 4.60 5 Hydrogen 20 446 9.79 46 Neon 27 87 1.84 47 Oxygen 90 213 1.90 112 Nitrogen 77 198 2.04 97 Argon 87 162 1.14 142 Propane 231 425 2.20 193 Ethane 184 488 2.51 194 Methane 111 509 3.45 147 Toluene 384 363 1.72 211 Acetone 329 518 2.15 241 Heptane 372 318 2.24 142 Ammonia 240 1180 4.80 246 Mercury 630 295 0.14 2107 Water 373 2260 4.18 541 Benzene 353 390 1.73 225 Cesium 943 49 0.24 204 Potassium 1032 1920 0.81 2370 Sodium 1152 3600 1.38 2608 Lithium 1615 19330 4.27 4526 Silver 2450 2350 0.28 8393 [D] The outer container usually consists of a metal tube to provide mechanical support and pressure containment. The chosen design and processing of the container are extremely important in selecting the metal, because they can affect the useful life of the heat pipe. In addition, a compatibility must exist between the pipe material and the working fluid. For heat pipes, working fluid/container compatibility issues encompass any chemical reactions or diffusion processes occurring between the fluid and wall/wick materials that can lead to gas formation and/or corrosion. Table 2 lists the compatibilities of several metals and working fluids. Along with the metal/fluid compatibility, other considerations in the metal selection are ease of working the material, extrusion capability of the material, and its weldability. Proper container cleaning and heat pipe processing procedures are of extreme importance, since residual contamination within the heat pipe may also lead to gas generation. Steps must also be taken to ensure the purity of the fluid charge; trace amounts of water in ammonia can lead to a reaction with the aluminum container and the formation of hydrogen gas. Chi [reference 1] and B & K Engineering [reference 2] list standard cleaning and filling methods for a variety of working fluid/wall material combinations. Special consideration must be given to the processing of heat pipes to be used at temperatures below 250°K. As the temperature drops, the vapor pressure of the fluid falls off. This allows any non-condensable gas created by contamination to expand, thus creating an even larger problem. The heat pipe wick structure provides a porous medium for the formation of liquid menisci (which cause the capillary pumping action) and a vehicle for returning the working fluid from the condenser to the evaporator. To accomplish these wick functions effectively, the designer must provide pores, cavities, or channels of the right size, shape, quantity and location. An optimization technique is used in wick design to find the desired combination of ultimate heat transfer capacity, pumping capability, and temperature drop. The designer must also consider ease of wick fabrication, compatibility with the working fluid, wetting angle and permeability of the selected wick material. Figure 5 depicts a cross-sectional view of an axial groove wick; this design probably is the most commonly used for space application. [D] In addition, X-ray certification of all welds at the end caps and fill tube is required to ensure good weld penetration and the absence of voids. The heat pipe container must be pressure tested to at least twice its maximum expected operating pressures (MEOP) prior to filling [reference 3]. Other qualification procedures include performance tests at adverse tilt angles to demonstrate proper wick function, and gas pocket tests performed with the heat pipe in the reflux mode. Heat pipes should be handled with care, especially those that contain ammonia or other high vapor pressure fluids. They should be treated as any other pressure vessel, and appropriate safety precautions must be exercised. Exposure to ammonia vapor can cause severe irritation to eyes and other mucous membranes. Exposure to ammonia liquid can cause severe burns to the skin. Whenever possible, heat pipes should be stored in a cold, dry environment. This will inhibit any internal chemical reactions which produce non-condensable gas. Technical Rationale: Spacecraft applications to date have been for heat pipes operating between 200°K and 350°K. Consequently, a working fluid whose freezing and boiling points encompass this temperature range and has a high latent heat, a low viscosity, and high heat transport capability must be selected. GSFC has selected ammonia as an appropriate working fluid whose fluid properties meet these criteria. However, for safety reasons, the toxicity of ammonia precludes its use in manned environments such as the shuttle cabin [reference 4]. GSFC has selected aluminum alloys, such as 6061 and 6063, for the container material of the heat pipe because of their long-term compatibility with ammonia (see Table 2); heritage; ability to have an extruded axial groove wick structure; ease of fabrication, shaping, and configuring; good thermal compatibility with aluminum radiators and heat sinks; and weldability characteristics. References: Chi, S. W., quotHeat Pipe Theory and Practice,quot Hemisphere Publishing Corp., New York, 1976 Brennan, P. J., and Kroliczek, E. J., quotHeat Pipe Design Handbook,quot B & K Engineering, Inc., Towson, Maryland, 1979 MIL-STD-1522A (USAF), quotMilitary Standard General Requirements for Safe Design and Operation of Pressurized Missile and Space Systems,quot May, 1984 NSTS-1700.7B, quotSafety Policy and Requirements for Payloads Using the Space Transportation Systemquot, January, 1989 | This practice has been used on OAO-C, ATS-F, IUE, HST. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/15/2000
692 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Coordinate Systems for Attitude Determination and Control |  | The primary impact of nonpractice is reduced reliability of ACS caused by mis-communication of technical information. The result of mis-communication can vary in severity -- from a delay in schedule to resolve any discrepancies, to the cost of reworking ACS components, to (in the extreme) an un-recoverable mission failure due to ACS design errors. | This guideline provides a procedure which specifies and documents consistent, useful, and well-defined coordinate system (or frame) definitions for spacecraft attitude control design and analysis. Several example coordinate frames and transformations are presented to show how these definitions are used to address various Attitude Control System (ACS) design issues. Past experience has shown the most efficient convention varies from project to project as a function of mission type, constraints, and performance requirements. This procedure addresses the process and documentation to reliably define the most efficient reference frame convention for a given mission or spacecraft. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2211 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The primary benefit is increased mission reliability due to a reduction in design errors occurring during spacecraft development caused by inconsistent coordinate frame definitions. A document will be created early in the development of a spacecraft mission defining Attitude Control System (ACS) coordinate frames which will facilitate data transfer among subsystem engineers, speed documentation and communication during design and analysis reviews, expedite verification of instrument and sensor pointing, and assure that a record of the coordinate frames used will be available throughout mission planning, design, analysis, and flight. Implementation Method: Early in the development stages of a mission program, a document should be created, published, and distributed to all ACS and ACS related mission engineers. This document will list coordinate frame definitions needed for ACS design and analysis. It should also be periodically updated as mission objectives evolve and hardware changes are made. The following discusses ACS coordinate frame definitions and the format for listing them in the ACS Coordinate Frames Definition Document. 1. Overview of Coordinate Frame Definitions for ACS Design and Analysis: ACS coordinate frames contain an origin location and three unit vectors emanating from that origin. quotThe most convenient set of these vectors is a dextral (i.e., right-handed), orthonormal (i.e., mutually perpendicular and of unit length) triadquot [reference 4, p. 6]. Vector quantities can be expressed as projections onto each of the three triad unit vectors of a coordinate frame. Triads or frames can be related to each other through the use of rotation matrices [reference 4, pp. 8-10], thus permitting the expression of vectors in any desired frame. With the use of coordinate frames and vectors, the orientation and changes in orientation of spacecraft, celestial bodies, instruments, mechanisms, and other ACS related hardware and objects can be described. An overall base coordinate frame must be defined relative to which all other coordinate frames (discussed below) are defined. In many cases, this overall base frame will be an inertial frame which is used to determine overall mission success. For example, if the primary mission of the spacecraft is to point instruments at the sun, a good choice for the overall base frame might be the heliocentric reference frame [reference 7, p. 29] since the sun's motion can be easily established in this frame. Typically, within the ACS subsystem, several design issues must be addressed. These design issues can often be arranged into categories, such as overall spacecraft pointing; environmental disturbances; spacecraft mass properties; sensor, actuator, and instrument motion; and flexible body dynamics. A category reference frame should be established to address each design issue. For example, when modeling environmental disturbances in Earth orbit, an Earth centered inertial frame is usually used as the category reference frame. For defining the spacecraft mass properties, sensor, actuator, and instrument motion, and flexible body dynamics the category reference is some sort of spacecraft body fixed coordinate frame. If information is to be transferred between these ACS categories, transformations can be established through the overall base coordinate frame discussed above. Additional coordinate frames may be needed to define the motion or effect to be modeled within an ACS category. The effect to be analyzed may be defined in terms of an intermediate axis with this intermediate axis related back to the category reference frame. The coordinate frames needed for defining spacecraft motion within the orbital plane provide a good example of this process. A frame which is fixed to the spacecraft is defined first. This frame is used to define the motion of the spacecraft relative to the orbit plane. Then, a frame which is fixed to the orbital plane is used to define the motion of the orbit plane relative to an inertial frame. The result will determine the spacecraft motion relative to the inertial frame. Another example of the use of intermediate axes for addressing ACS design issues is the relationship among sensor and instrument reference frames. One axis of these frames is almost always defined along the boresight of the sensor or instrument. The other two axes should match some other characteristics (e.g., parallel to the edges of a square field of view). The origin is at any convenient point. The relationships of the nominal and quottrackingquot (a frame that moves with the boresight to track the sensor motion) boresight frames to the category reference can be achieved in many different ways depending on accuracy and knowledge requirements. Several intermediate frames might be needed to achieve these relationships. Often, both the nominal and tracking boresight frames must be related to a payload interface frame, and all requirements of alignment are specified between this interface frame and another frame, the spacecraft optical frame. Typically, the interface frame axes are nominally parallel to the spacecraft optical axes, and the optical axes are defined with respect to an optical master reference cube. The nominal position of this cube relative to the spacecraft mechanical build axes (used for defining hardware locations within the spacecraft) must be defined next. Finally, this mechanical build frame may be used as the category reference or is then related to the category reference. The figure below shows the nominal orientations of these frames used in the SOHO spacecraft [reference 1, p. 2.8]. This example demonstrates the process of how coordinate frames are used to define the sensor and instrument pointing relative to its category reference frame. [D] A discussion of the frames needed to model how actuators are used for attitude control is presented as a final example of the use of intermediate frames. Momentum wheels, control moment gyros (CMG's), torque rods, and thrusters are commonly used control actuators. Frames are needed to represent the nominal orientation and location, misalignments produced when installing, and movement of the actuators. Also, rotation matrices which relate these frames to the category reference, usually the spacecraft ACS axes, must be determined. As a specific example, consider the frames needed in distributing control torques among a reaction wheel set containing 4 wheels. The wheels are usually aligned in a pyramid configuration as shown below. A frame is first defined for each wheel with one axis along the spin axis of each wheel. Then, rotation matrices are created relating each wheel frame to the spacecraft ACS frame (called roll, pitch, and yaw for this case). This example demonstrates how intermediate and category frames are used to relate the orientation and motion of actuators (in this case, reaction wheels) to achieve desired torques. [D] 2. Document Format A suggested format or outline for the coordinate frame definitions document is summarized below. However, this format is only a guide, and the user may need to change or add to the format depending on the spacecraft mission. Since the choices of ACS coordinate frames to be defined are dependent on the overall spacecraft pointing objectives and the proposed ACS mission hardware required, these topics should be discussed first. To avoid any ambiguity, coordinate system symbols and nomenclature to be used should be listed next. Specific coordinate frame definitions should follow -- an overall base frame, category reference frames, and frames needed within each category. Finally, a way of relating all the coordinate frame definitions should be included. ACS Coordinate Frames Definition Outline Document Title Table of Contents Mission Objectives, Requirements, and Criteria for Success State overall spacecraft pointing objectives and specifications Overview of ACS Hardware State what instruments, control actuators, and other mechanisms are being used for sensing, data collection, and control actuation Nomenclature and Symbols Discuss the nomenclature and symbols to be used for the coordinate frame definitions Overall Base Frame Definition Define a frame to which all other frames are referenced. Category Frames Group design issues into appropriate categories, e.g., spacecraft, instrument, and sensor pointing, actuator sizing, environmental disturbances, spacecraft mass properties, etc. Within each category, a category reference frame should be listed along with all other frames needed to address design and analysis issues. Figures showing the physical relationships among these frames would be helpful. Coordinate Frame Transformations Relate each frame to the overall base frame. The first section of the document (after the table of contents) states the overall mission objectives and the criteria for a successful operation. The objectives include a list of celestial, Earth based, or other bodies to which the spacecraft and instruments must point. A discussion of the pointing accuracy and knowledge error definitions and specifications for performance needs to be given. Orbit parameters, spacecraft mass properties, and any issues that might affect the mission objectives or success criteria are provided in this section. This section will aid the reader in understanding the rationale behind the choice of coordinate frames. The second section of the document contains an overview of ACS hardware. Included in this discussion are locations, orientations, and functions of all ACS related hardware. The locations and orientations are best shown with a figure or a reference to an interface drawing. If the hardware moves or reorients itself (such as solar array rotation to track the sun) relative to the spacecraft, this change is to be documented. The anticipated effects of flexibility should also be considered. Instrument and attitude sensor functions are given in relation to the overall ACS concept. For example, a magnetometer is used to determine the magnetic field of the Earth relative to the spacecraft. The location and orientation of the magnetometer relative to the spacecraft needs to be given, along with a statement of how the magnetometer may be used in conjunction with other ACS hardware and software. The magnetometer output may be used for attitude sensing or for determining when to pulse a torque rod to provide an attitude control moment. These different functions for the magnetometer may result in different coordinate frame choices. The third section of the document needs to discuss the nomenclature and symbols to be used for the coordinate frame definitions. The format may vary depending on the spacecraft mission. An example definition taken from reference 6 [p. 4], and shown below, demonstrates a possible format which may be used for defining reference frames. A descriptive or commonly used name is given first. A one or two letter symbol is listed next, which is also used for labeling the vectors comprising the axes of the frame. Then, a description of the frame is provided, and this description is to contain enough detail to unambiguously locate the frame. Equatorial Inertial Coordinate System, E (E1, E2, E3) This is the basic inertial coordinate system. All other coordinate systems are defined with respect to E. The origin is at the center of the Earth. The E3 axis is in the equatorial plane and it is positive toward the vernal equinox. The E2 axis is perpendicular to the equatorial plane, and it is positive toward the Earth's North Pole. (The E1 axis completes the orthogonal triad.) The vernal equinox position is defined as its mean position at 1950.0. All the frames included in the document are related to the overall base frame. Rotation matrices are commonly used to convert components of vectors from one frame to another, and the development of the mathematics is available in the literature [reference 4, pp. 6-31], [reference 6, pp. 10-20], and [reference 7, pp. 410-420, 758-759]. To avoid any ambiguity in the definitions of coordinate frame rotations and their matrices, a discussion of this topic is to be included at the beginning of this section of the document. This discussion should include definitions of Euler angles, quaternions, direction cosine matrices, or other mathematics to be used to relate the frames. Then, a table or any convenient format is included at the end of the document which contains information relating each frame back to the overall base frame. Finally, figures illustrating the nominal relationships among all these frames and the possible reorientations of the frames during flight is essential and is included in the document. Technical Rationale: Due to the increased complexity of ACS work for spacecraft, a document is needed in the early stages of the project development which contains consistent and well-defined coordinate system definitions. Definitions are needed to accurately communicate within and between various design and analysis disciplines affecting ACS performance. These disciplines include spacecraft pointing, environmental disturbances, spacecraft mass properties, sensors, actuators, and instrument motion, structural dynamics, and mechanisms. Analytical and design mistakes can occur due to communicating erroneous information within and between design and analysis groups. This erroneous communication can be caused by inconsistent or ambiguous coordinate frame definitions. If a document listing coordinate frames to be used for ACS design and analysis is published and adhered to, then many problems can be avoided. For example, an ACS engineer may need to know the mass and inertia of the spacecraft in order to simulate the dynamics. However, when obtaining this information from structural or design engineers, often the ACS and the structural body frames are not consistent. If a mission standard was established early in the program life, both body frames would be consistent, or at least, the creation of a rotation matrix between frames would be readily obtained. Documentation of ACS frames would also be clear, consistent, and complete if this guideline is followed. During preliminary and critical design reviews, much time is spent searching for definitions of ACS frames and information relating those frames. If all the frames are compiled into one document and are related to an overall base frame, considerable time and effort will be saved. Verification of spacecraft, instrument hardware, and other mechanism pointing will be facilitated. Often it is necessary to visually or otherwise make quotsanityquot checks to make sure that component rotations will result in the desired orientation. For example, for Earth orbiting spacecraft it is necessary as part of the mission systems verification to make sure that spacecraft solar arrays quottrackquot the sun. To make this verification, the sun and the solar array normal vectors must be written in the same frame and compared. This process involves several coordinate frame rotations which should be defined in the document generated through this guideline. An accurate record of these coordinate frames will be available throughout mission planning, development, and flight. If during development of hardware and software for flight a technical glitch occurs, it will be necessary to review the ACS design analysis work performed. Without documented ACS coordinate definitions, analyses may be difficult to validate causing additional costs and delays in the mission. Also, ACS engineers will be able to review coordinate frame definitions created with this guideline enabling them to better plan and analyze for future spacecraft missions. References: Berner, C., quotSOHO Solar Terrestrial Science Programme Experiment Interface Document, Part A,quot PLP/410/EID A, January 7, 1990. Ford, Terry, Spacecraft PDR Update, quotEOS Pointing Error Budgets, Prediction, and Verification Concept,quot EOS-DN-SE&I-043 Rev A, August, 1993. Frederick, Martin E., quotTropical Rainfall Measurement Mission, Attitude Control System Specification,quot Goddard Space Flight Center, Greenbelt, Maryland, TRMM -712 - 046, August 13, 1993. Hughes, Peter, C., Spacecraft Attitude Dynamics, John Wiley and Sons, Inc., 1986. Kaplan, Marshall, H., Modern Spacecraft Dynamics and Control, John Wiley and Sons, Inc., 1976. Kennel, Hans F. , quotSpace Telescope Coordinate Systems, Symbols, and Nomenclature Definitionsquot, Systems Dynamic Laboratory, George C. Marshall Space Flight Center, Alabama, NASA TM X-73343, September, 1976. Wertz, James R., quotAttitude Geometry,quot Spacecraft Attitude Determination and Control, Kluwer Academic Publishers, Netherlands, 1991. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/13/2000
691 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Orbital Anomaly Report System |  | If the practice is not followed, in-orbit anomalies may not be recognized, analyzed, and possibly corrected in a timely manner leading to continued degraded performance and possible damage to the spacecraft. Additionally, deficiencies in designs may not be recognized and corrected in new or follow-on flight missions. | Implement a positive feedback system for reporting, documenting, collecting, analyzing, and closing orbital anomaly (A departure from normal operation. An abnormality in the mission operations of a spacecraft (in orbit)) information on spacecraft. An example of such a system is currently managed by Goddard Space Flight Center. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice Number PD-ED-1232 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The Spacecraft Orbital Anomaly Report (SOAR) System provides a single uniform, effective, and efficient computer data base for in-orbit reliability studies to identify performance trends for use in design reviews, flight readiness reviews, and in the evaluation of test, reliability, and quality assurance policies. Implementation Method: Anomaly Reporting - Immediately after the occurrence of an anomaly, the orbiting spacecraft's control center initiates the procedure shown on the SOAR Flow Diagram, Figure 1, by notifying the cognizant Project Operations Director (POD) or other cognizant NASA/government representative. The originator then enters all known information onto a SOAR reporting form (GSFC Form 4-29), Figure 2 and sends it to the POD. The POD assigns a person to be responsible for determining the cause of the anomaly, corrective actions to be taken, etc. The responsible person conducts an anomaly investigation and analysis with the help, as required, of control center personnel, the system or instrument representative, the system integration contractor, the subsystem fabricator, and the Flight Assurance Manager (FAM) or the SOAR System Manager. The cause of the anomaly is determined, if possible, and corrective action is proposed, agreed to and approved by project and Center management, as appropriate. This information is entered onto the SOAR form by the responsible person. The FAM or SOAR System Manager assures that the agreed-to corrective action indicated on the SOAR form takes place. When all the SOAR corrective actions have been completed, the FAM or SOAR System Manager is responsible for entering the information onto the SOAR reporting form and closing out the SOAR. The completed SOAR form is distributed to the appropriate project, Flight Assurance, and other interested personnel by the SOAR System Manager. The SOAR System Manager enters information from the SOAR report into the SOAR computer data base and distributes a printout. [D] [D] Yearly Summary Reports - These reports present a summary of the in-orbit reliability and performance of active spacecraft built under the management of the Goddard Space Flight Center and collectively form a continuous, published record of this performance. These reports provide a variety of statistical summaries including the total number of anomalies, the number of spacecraft over which the anomalies were distributed and a comparison with the anomalies of the previous year. A brief discussion is included of the condition and performance of each active spacecraft. The yearly SOAR reports contain a complete list of all anomalies that occurred during the year, each with the subsystem identified that caused each anomaly, the criticality, effect, and a description of the anomaly, and any corrective action that was taken. In addition, graphics show the distribution of anomalies among spacecraft and subsystems and comparisons of levels of criticality, effects, failure categories, and types of anomalies. Anomalies are classified and described in these summaries, lists, graphics, etc. as shown below. These classification categories are defined on the SOAR Form along with instructions for their use. Subsystems - The spacecraft is divided into the following nine subsystems: Attitude Control & Stabilization Power Propulsion Structure Telemetry & Data Handling Thermal Timing, Control & Command Instrument (Payload) Other Mission Effect (Criticality) - The following schedule describes the impact of the anomaly on the mission: Negligible Non-negligible but Small (minor) 1/3 - 2/3 Mission Loss (Substantial) 2/3 to Nearly Total Loss (Major) Essentially Total Loss (Catastrophic) 0 - 5% loss 5 - 33% 33 - 66% 66 - 95% 95 - 100% Anomaly Effect - Spacecraft Failed Subsystem/Instrument Failed Component Failed Assembly Failed Part Failed Subsystem/Instrument Degraded Indeterminate Loss of Redundancy None Failure Category - Design Problem Workmanship Problem Part Problem Environmental Problem Other (w/explanation) Unknown Type of Anomaly - Systematic (would occur if identical equipment were operated under identical circumstances) Random Wearout (a special case of systematic) Indeterminate Intermittent An appendix of the yearly SOAR report also presents a table of spacecraft lifetime data. Table 1. is a sample sheet of spacecraft lifetime data from a yearly SOAR report. [D] Technical Rationale: The SOAR System provides a positive feedback system for reporting, documenting, collecting, analyzing, and closing orbital anomaly information. The timely recognition and analysis of anomalies can lead to corrective measures that can restore performance and, in some cases, protect the safety of the spacecraft and its payload instruments. The yearly SOAR reports provide GSFC management, spacecraft projects and designers, as well as flight assurance personnel with both short term and long term in-orbit performance and reliability trends which can indicate areas where design improvements should be made on follow-on spacecraft programs. They also can be used to evaluate the effectiveness of the prelaunch integration and environmental test programs. References: Procedure for the Spacecraft Orbital Anomaly Report (SOAR) System GSFC Report No. 303-PROC-013 (Rev C) Individual Yearly Reports --- Orbital Anomalies In Goddard Spacecraft | This practice has been used on Sampex, COBE instruments and electronic boxes, ISTP instruments, etc. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/13/2000
676 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical, Electronic and Electromechanical (EEE) Parts Derating |  | Derating lowers the probability of failures occurring during assembly, test, and flight. Decreasing mechanical, thermal, and electrical stresses lowers the possibility of degradation or catastrophic failure. Derating policy documents such as those prepared by NASA and DoD, and generally required in their contracts, allow the designer to avoid lengthy and involved calculations by mandating the derating of specific characteristics and parameters. | Practice: Derate applied stress levels for electrical, electronic, and electromechanical (EEE) part characteristics and parameters with respect to the maximum stress level ratings of the part. The allowed stress levels are established as the maximum levels in circuit applications. | GSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1201; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. EEE parts derating can be established as either design policies or from reliability requirements. In general, NASA has taken the approach of establishing derating policies that cover all applications of the various part types in space flight equipment. These policies are available in MIL-STD-975, quotNASA Standard Parts List.quot Table 1 provides typical derating factors from that document. If derating is to be determined from a reliability requirement, the reference document is MIL-HDBK- 217, quotReliability Prediction of Electronic Equipment.quot MIL-HDBK-217 contains the information necessary to quantitatively estimate the effects of stress levels on reliability. Table 1. Typical Part Derating Guidelines PART TYPE RECOMMENDED DERATING LEVEL Capacitors Max. of 60% of rated voltage Resistors Max. of 60% of rated power Semiconductor Devices Max. of 50% of rated power Max. of 75% of rated voltage Max. junction temperature of 110°C Microcircuits Max. supply voltage of 80% of rated voltage Max. of 75% of rated power Max. junction temperature of 100° Inductive Devices Max. of 50% of rated voltage Max. of 60% of rated temperature Relays and Connectors Max. of 50% of rated current NOTE: Maximum junction temperature levels should not be exceeded at any time or during any ground, test, or flight exposure. Thermal design characteristics should preclude exceeding the stated temperature levels. Technical Rationale: The reliability of a EEE part is directly related to the stresses caused by the application, including both the environment and the circuit operation. MIL-HDBK-217 contains specific part failure rate models for a wide variety of part types. The models include factors for calculating the effects of various stresses on the failure rate and thus on part reliability. The types of factors include (for example): environment, quality levels, voltage, frequency, and temperature. Given the extensive tables of factors in MIL-HDBK-217, one can formulate reliability predictions for piece parts. As shown in Figure 1, the plot of piece part failures versus an application stress level such as temperature, voltage, or current indicates decreasing failure rates for lower levels of stress. Therefore, a part's reliability in an application can be increased by decreasing the maximum allowed stress levels from the absolute maximum for which a part is rated. [D] | This practice has been used on all Goddard Space Flight Center (GSFC) flight programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
675 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Fastener Standardization and Selection Considerations |  | If the guidelines recommended are not followed, greater numbers of fastener types, sizes, materials, and finishes may be specified or procured resulting in excessive cost. Mission performance may be also degraded due to incompatibility of materials and finishes, or due to substandard hardware that lacks sufficient screening and testing. | Verify that a structured, multidisciplinary approach to parts selection, design evaluation, and procurement has been applied prior to committing to a final design. | JSC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline number GD-ED-2201 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: One of the most important considerations when mechanical fasteners are required is the selection of fasteners of certified quality that meet the requirements of the hardware assembly. Proper fastener selection and application is the first step toward building reliable hardware; therefore, a standard approved parts list consisting of a limited number of types and styles will result in optimum performance, reliability, maintainability, and economy. Implementation Method: Fastener reliability begins with the preparation of an approved parts list (APL), consisting of certified parts with proven performance, selected for the appropriate application, and procured only from approved suppliers. To ensure certified quality and reliability, fastener types and styles should be kept to a minimum, with fasteners obtained from an approved source. Fastener cost can be better controlled by implementing, in the initial phases of a program, a plan of consolidation and centralization of efforts related to fastener selection, receiving inspection, testing, and traceability. Providing sufficiently detailed design selection and procurement information for an APL requires that the fasteners be identified, described, and controlled by a Government specification or standard, an industry standard formally adopted by the Government for general applications, or a contractor specification or standard acceptable to the Government. Additionally, precautions should be exercised to ensure, as a minimum, that fasteners are procured from only qualified suppliers based upon surveyed performance. Critical fasteners, generally defined as used in either the primary or secondary load path of a structure, together with specialty fasteners, should be given particular attention to ensure that selection and procurement is only from approved manufacturers. An example of a specialty fastener would be a design created either in-house or by a manufacturer for a very specific and limited application (high strength, temperature, configuration). Care and good engineering judgment should be used at all times during design selection and procurement of fasteners for flight hardware, safety-critical facilities, and mission-essential ground support equipment to ensure that each design is examined from a reliability, maintainability, and producibility aspect. General criteria that should be examined for a suitable selection of fasteners include: Materials. Fasteners intended for critical applications should be made from corrosion and heat resistant steels or alloys such as A286 corrosion resistant steel (CRES), titanium, Inconel 718, or MP35N. Fasteners intended for GSE, noncritical, or non-flight hardware may be made from either 300 series or A286 CRES. The tensile strength for noncritical types of fasteners should be 130 ksi minimum. The maximum expected load (tensile and shear) and criticality for the applicable joint is important in the selection of fastener material. Stress corrosion sensitive fasteners should be avoided (refer to MSFC-Spec-522). Fasteners considered for use in composite structure must be selected to ensure conformance to requirements of material compatibility, acceptable installation procedures, and part configuration. Corrosion resistant steel fasteners should be passivated per MIL-S-5002 or QQ-P-35 during the manufacturing process. The passivation process will prevent rust spots from forming on corrosion resistant steel parts by removing embedded iron particles. Passivation must always be the last operation performed. Environmental conditions (salt spray, temperature, vibration, etc.) both for storage and operation should be considered so that material and finish requirements can be evaluated for galvanic couples. Spacecraft hardware may spend a considerable amount of time on earth due to factors such as assembly, test, and storage due to launch scheduling. Fastener selection should be based upon considerations of weight, cost, and availability. The operational aspects of the installation, extravehicular activity (EVA), intravehicular activity (IVA), maintenance and repair, together with initial assembly may require a unique or specialty fastener. An analysis should be performed early in the design and selection phase as a considerable impact may result to both the hardware design and cost if a specialty fastener is required. EVA/IVA and Torque requirements. External wrenching fasteners should have a 12 point head for applications with tensile strengths above 180 ksi. Hexagonal heads (6 point) should be used for fasteners of 180 ksi UTS or less. Threads should also conform to MIL-S-8879 requirements "Screw Threads, Controlled Radius Root with Increased Minor Diameter, General Specification for". Captive fasteners should be used whenever possible for flight hardware. All nuts, nut plates, and threaded inserts should have an integral prevailing torque locking device. The minimum fastener head size for suited glove operation should be 1.5 inch diameter and .75 inch high. Sizes larger than 2 inches in diameter should be avoided to prevent the fastener from being larger than the maximum grip size of the smallest crewman. Fasteners that will be manipulated by tools or robots in space should have a standardized head size of 7/16 inch (measured from flat to flat) for 1/4 inch threaded fasteners, and 3/4 inch head for 1/2 inch threads. The thread sizes may be varied independently from the fastener head, thereby reducing or eliminating the requirement for different tool or end effector sizes, but allowing the fastener to be tailored to the application. The minimum head size must be considered in relation to the maximum torque required upon assembly. The assembly and operational aspects of the fastener may require lubrication or a special finish to insure reuse of the fastener during these phases. Lubrication. Silver plating should not be used on any fastener that would be removed and reinstalled more than twice as part of normal operation or maintenance procedures. Silver reacts rapidly with atomic oxygen to form silver oxide, therefore silver plated components should not be used in any application in which the part is directly exposed to atomic oxygen. Due to corrosion potential, silver plated parts must not contact titanium. Dry film lubricant is the preferred method of coating fasteners. Lubricants for fasteners should meet the vacuum stability requirements of JSC SP-R-0022, "Vacuum Stability Requirements of Polymeric Material for Spacecraft Application". Fastener procurement and testing. All received fastener shipments should contain reports of tests conducted on the parts at an accredited laboratory in compliance with Public Law 101-592 "Fastener Safety Act". All test reports require a similar format such as stated in Public Law 101-592, Section 5. Critical fasteners procured from sources other than the original manufacturer should only be accepted if original chemical and physical certifications can be validated and the lot traceability can be documented. Together with fastener testing, a system for providing traceability of parts to the initial assembly should be maintained, to reduce the time and associated costs of tracking problems concerning suspect hardware. Without traceability, the location of suspect hardware becomes difficult and may make dispositions very subjective and complex, perhaps leading to extensive disassembling of structure or other hardware. To maintain such a level of traceability, lot segregation should be implemented. Technical Rationale: Substandard and counterfeit fasteners in industry have heightened the government's concern about the reliability of hardware procured for use on various projects and programs. In response to this concern about the integrity of fasteners, Public Law 101-592, "Fastener Safety Act", has been enacted to provide an improved level of confidence in fasteners by requiring improved manufacturing, testing, certification, and quality assurance for all fasteners sold or delivered within the United States. References: 10107-70915, EVA Bolthead & Socket Interface Study & Definition, ILC Space Systems, Houston, Texas. MSFC-Spec-522, Design Criteria for Controlling Stress Corrosion Cracking, Marshall Space Flight Center. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
687 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Spacecraft Deployed Appendage Design Guidelines |  | Incorrect analysis parameters for critical moveable components can result in improper loads and under- or over-design of supporting structure or improper loads in deployables, causing malfunction or breakage. Insufficient force/torque margins, parts hangup or unaccounted drag can result in non-release. Sharp edges and difficult assembly can degrade parts, lubricants and coatings, allowing passage of ground tests but causing flight failure. | This guideline describes design practices for deployable appendages which can improve accuracy of analyses, simplify and optimize designs, and minimize fabrication and test problems to produce reliable deployables. This guideline includes techniques used on successful missions and will help avoid past deployment problems. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2209 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Increases confidence in designs and their operational reliability. Ensures accuracy of design analyses, completeness of requirements in procurement documents and thoroughness of test planning. Ensures functional compatibility of assembly and test fixtures. Implementation Method: Designs must factor in effects of the space environment. Relevant differences between ground test conditions and flight deployment should be identified for consideration at the design and test stages to assure operation with adequate margins. G-negation pickup points can be designed in. Historically, some deployables have passed ground tests but failed in space. Space imposed conditions include thermal gradients and thermally induced loads, outgassing, low moisture, zero gravity and ballooned thermal blankets. Handbook material values do not always apply for the space environment. Physical parameters vary such as solid film lubricant friction which varies with moisture content. The space environment is not easy to simulate in earthbound tests and allowance should be made for expected parameter variations. Deployed appendages should be designed using the following guidelines: Avoid complication; simple designs are more reliable. Avoid single point failures. If unavoidable, assure generous margins. Where practical, design them out or employ redundancy unless redundant complication reduces reliability. Assure redundancy is truly independent, not coupled. Margins - Provide minimum torque/force margin: Tt = 1.25 Tf + 4.0* Tv where: Tt = minimum total available torque/force Tf = fixed and non-variable loads such as Ia terms Tv = worst case variable torques/forces such as coulomb friction and other loads which vary with environmental conditions and operating life. *Factor 4.0 is the Design Goal, reduced where excessive mass, power or volume is required, e.g., motor driven mechanisms. Maintain a minimum factor of 2.0 under worst case degraded conditions. Force analyses should use best available loads and forces and examine the full range of expected minimum and maximum parameter values, make adequate allowance for uncertainty. Torque requirements are higher with high friction, deployment velocity and momentum higher with low friction. Use test verified values where available for such critical parameters as friction (if only handbook values available, multiply by 3 to cover uncertainties), cable flexure torque, bearing drag torque. Include worst case thermal effects, wearout, friction changes and end-of-life conditions. Designs should tolerate moderate increases in friction. Maintain calculated torque/force margins above 2 with m assumed up to 0.5 for typical material combinations. Friction force estimates are untrustworthy, handbook values represent controlled conditions. Use cautiously, test if possible. Consider case differences between published numbers and actual conditions such as effects of part surface treatments, differences between ground test conditions and space environment (humidity, pressure, loads). Use appropriate fits, alignment tolerances, surface treatments, deburring and hardness differentials to avoid galling which nullifies friction estimates. Temperature effects at deployment should be accounted for, e.g., torque/force changes at hingelines and separation points from temperature gradients within assemblies, bulk temperature effects and differential temperatures between deployables and mounting structure. Humidity effects, e.g., molybdenum disulfide (MoS2) friction varies and nonmetals change size with moisture content, can affect torque margins and fit clearances. Moly lube should not contain graphite. Rolling element bearing loads for long life devices should be kept below 320,000 psi mean Hertzian stress for launch, 200,000 psi or lower for operation, less if lubrication is marginal. Consider effects on bearing preload, torque and life due to thermal gradients and bulk temperature variations. Analysis. Loads analyses and load sharing between deployed appendages and spacecraft structure can be greatly affected by compliance of typical appendage joints. Examples are bolt preloaded joints, separation joint clamping devices, bearing supported hinge lines, and movable mechanical joints such as gimbals and solar array drives. Accurate stiffness knowledge of these devices is crucial for valid loads analyses. Verification and validation should be addressed in design, and plans made to acquire sufficient data to verify models. Kinematic diagrams should be constructed including all degrees of freedom and constraints. For accurate loads and stress analyses, assure correct component parameters are used in the Finite Element Analysis (e.g., bearing stiffness, friction coupling, compliance of bonded joints, stiffness of movable joints - clearance fit or preloaded, transmissibility across joints). Perform loads analysis based on true compliance of individual members for accurate assessment of load sharing. Cross-check with deflection analyses, compare with measured values. Incorporate proper deployment angles, velocity, acceleration and impacts to size components with adequate predicted margins. Include critical component parameters in analysis based on actual measured unit data where possible, eg. bearing friction, compliance of assemblies. Account for fabrication and assembly variables which affect design parameters used in analysis. Evaluate zero-g case to determine impact on design and verification. Jerking (non-uniform acceleration) can be critical in deployment. Its effects should be evaluated. Stick-slip friction conditions can worsen the condition. Stowed and deployed frequencies should be evaluated. These affect launch loads and Flight Attitude Control. Separation Planes Employ kickoff springs where practical in the separation joints; especially important for long appendages. Use anti-seize, anti-weld coatings, dissimilar materials. Provide retention joint flexure capability to accommodate launch loads, e.g., spherical, vs conical cup-cones. Assure adequate dynamic envelope clearance. Use the following guidelines for wire and cable routing at hingelines. Mechanical design of appendages should allow cabling across the hinges to be left fixed and undisturbed after component deployment testing throughout spacecraft assembly and integration. Provide field joints for connection of hinge and cable subassemblies. Minimize flexure torque through entire travel, allow for temperature effects. Test new designs. Use wire guides and clamps, braided and laced cables to maintain free loop control in 1g testing and launch environment and to avoid snags during deployment. Control chaffing during deploy and stow tests and launch vibration. Use proper cable clamp size for no-slip position control and cushioned clamps for Coax cables. Control Coax cable minimum bend radius. Coax Cable Protection during Component Assembly and Integration and Test Design-in armor protection where possible. Provide takeup allowance for connect/disconnect without cable kinking. Train personnel in correct handling procedures. Follow planned Coax cable handling procedures, use safe temporary support when free ends are not connected, provide for safe and gentle tie-down, prevent crush. Sharp Edges Eliminate sharp corners that cut through lube coatings, produce galling. Use specific drawing callout to control break and blend of sharp corners on moving elements. This is not always covered by general drawing callouts or implemented under General Workmanship Standards. Double-check workmanship during assembly; visually inspect for sharp corners, handcheck running fits and clearances and verify clearance of chamfers to inside corners. Contamination Control Design-in labyrinth or contact type seals to contain lubricants, minimize outgassing and limit external contamination. Limit Switches for Position Monitoring Switches are prone to misadjustment and failure. Use only to indicate safe/stow/deploy positions, not to control deployment sequence. Allow for overtravel and deadband (hysteresis) effects, provide adequate margins for actuation force and stroke. Provide simple, stable adjustability at assembly. Avoid galling of close-fit parts in moving members during assembly or operation. Prefer non-galling metal-metal couples. Provide adequate differential hardness of parts. Substitute anti-galling stainless steel for conventional SST. Provide anti-gall surface treatments to prevent damage in assembly/disassembly/adjustment operations. Provide anti-gall treatment for titanium parts and fasteners. Provide adequate clearance fit allowances in moving members to accommodate: Bulk temperature effects, thermal expansion (CTE) mismatch effects and temperature gradient effects. Design slip fit interfaces for thermal expansion takeup. Assure friction control where intentional slip is required. Use surface treatments, lubricants and fit clearances which prevent lockup or cocking where slip is intended. Deployment and Temperature Effects. Determine temperature effects on stowed and deployed frequencies. If explosive deployment devices are used, determine near source shock levels and effects on deployables (instruments, optical devices, etc.). Deploy latches must not rely on appendage momentum; latches should lockup under static (zero velocity) appendage force/torque. If friction dependent, control surface contamination for predictable friction. Avoid thermally induced misalignment (e.g., differential temperature of deployable boom legs). Consider post-deployment thermal contraction of deployable boom lanyards causing limit switch reactuation at low temperature. Control deployment end-of-travel impact, use energy absorbing dampers where necessary. Use floating pin/flange arrangement for hinge joints where practical to provide redundant sliding surfaces. If system will be dormant for a long time, it should be designed so all deployable parts can be partially deployed and retracted periodically to prevent "lockup" due to stiction, lubricant changes, or adhesion of plastics. Handling - large items Design-in handling fixture attachment points. Locate attachment points to position c.g. for stable lifting. Where feasible, provide for 1g counterbalance attachment on hardware for functional testing. Design-in self-fixturing alignment and assembly guides. Self-aligning guides permit assembly without expensive fixtures, reduce need for highly skilled personnel. Provide self-aligning parts, with lead-in where practicable to protect precision surfaces, interfaces and bearings and minimize assembly debris generation. Provide disassembly features. Plan for unexpected disassembly, rework or reinspection. Design-in pry slots on close fit parts to permit easy separation without damage during typical assembly and disassembly for fit checking, shim selection or end shake checks. Provide puller holes, slots, jacking screw threaded holes or punch holes for disassembly of press fit components. Key electrical connections. Use differently keyed or dissimilar electrical connections for squibs and motors to prevent inadvertent interchange between prime and redundant and prevent malfunction. Use specific fastener hardware designs for appendages. Use plated self-locking nuts that reduce thread wear and reduce probability of galling and thread seizure but withstand few reuses. Fastener seizure and removal degrades critical hardware. Limit reuse of self-locking designs. Threads can become damaged, generate wear particles. Choose head designs for driver engagement appropriate to application, torque requirement and accessibility for tools. Small hex drive screws strip easily, Torque-Set and coinslot drive types are difficult to remove. Torque stripe where appropriate to ensure integrity, permit later verification. Avoid countersunk (flat head) fastener usage where practical; driver engagement is easily damaged. Provide clearance for thermal blankets and tiedowns at moving interfaces. Provide a taping edge or draw string flange to control blanket edges at moving interfaces. Provide adequate clearance for launch environment dynamic deflections with no protrusions or sharp edges to catch blankets. Provide adequate clearance gap with securely taped edges at moving interfaces; minimum one inch between hard surfaces which get blanketed. Lubrication for deployed appendages. Lubrication is crucial for deployables, many of which are mission critical. Key lubricant functions include the separation of surfaces and friction reduction. This is critical because often the deployment forces and kickoff spring forces are kept small to minimize dynamic forces. For sensitive science missions, extremely low outgassing is essential. Most deployables are single use and experience few cycles through test and flight so long wear life issues are not paramount in the lube selection. However, movable joints must sustain ground and launch environments, Flight conditions of sometimes long duration, and then deployment, often at temperature extremes. The clamped separation joints may experience micromotion at interfaces during ground handling, test and launch environments which can disturb surfaces. Lubes must stay in place to effectively separate surfaces, not outgas excessively and minimize friction. Surfaces that must separate or move relative to one another (e.g. hinge line bearings and latching devices) must be designed to preclude the possibility of metal-to-metal adhesion which causes increased friction and, in extreme cases, galling. Launch shifts or on-orbit thermal gradients can produce unexpected added forces at the separation points. To minimize friction problems the following guidelines are followed: Maximize utilization of rolling surfaces, as opposed to sliding motion. Lubrication or separation of all moving surfaces either by a suitable aerospace grease or dry lubricant coating should be used without exception, even for lightly loaded "friction compatible" surfaces. On hard mating surfaces where hard coatings are used (such as Type III anodizing on aluminum) loads must be kept below the bearing yield strength of the substrate metal (e.g. 60 ksi for 6061-T6 aluminum). Smooth and polished mating surfaces are preferred. Dissimilar material mating surfaces should have low mutual solid solubility, or at least one of the two should have a heavy dissimilar coating (e.g. nitride, carbide or oxide). Caging devices should be designed to positively preclude relative motion between clamped surfaces when subjected to shipment or launch vibration. Any separation (gapping) under launch loads is undesirable. Small amplitude oscillatory motion between mating surfaces can damage lubricating films and, in the extreme, result in fretting (adhesion) of the surfaces. Two alternatives are available for lubrication - "wet" lube with a low vapor pressure aerospace grease and "dry" lube by means of bonded or sputtered MoS2 coatings. The wet lube is generally preferred because the lubricating film is self healing and frictional behavior is more consistent and predictable. The grease with the most heritage is Bray 600 series, a synthetic fluorinated oil thickened with micron sized TeflonTM powder. The grease is extremely low outgassing (TML<0.1% and CVCM <0.05% for the standard 125°C - 24 hour test) making contamination concerns negligible for virtually all S/C applications. The wet lube usable temperature range is -80°C to +200°C. For extreme low temperatures, cryogenic applications and other special circumstances, MoS2 coatings are suitable. For most consistent performance and lowest possible outgassing these films should be applied by the ion sputtering process. Epoxy and polyimide bonded films can be successfully employed with proper application and burnishing to remove excess material. Technical Rationale: Careful and critical review during the design stage can produce better, more reliable designs. Such foresight can help avoid many fabrication, assembly, test and deployment problems. These guidelines highlight often overlooked but recurring troublesome problems. Incorporation of successful practices from past experience can reduce cost, avoid unexpected schedule impacts and improve reliability of new devices. References: GSFC Engineering Directorate paper, "Spacecraft Deployable Appendages," May 1992 MIL-A-83577 General Specification for Moving Mechanical Assemblies for Space and Launch Vehicles |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
688 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Management of Limited Failure Analysis Resources for Electrical, Electronic and Electromechanical (EEE) Parts |  | Failure to utilize these suggestions can cost a program resources when unnecessary or futile failure analysis occurs. When analyzing a part, board or system, care should be taken on the available data as well as other factors, and if all factors are not carefully considered, much time, effort and money could be wasted. Also, inability to perform failure analysis could cost a program dearly in failed hardware, loss of mission or even loss of life. Clearly understanding the failure tendencies of a part is critical to mission and program success. | Implement a strategy for Electrical, Electronic, and Electromechanical (EEE) Parts failure analysis in which the analysis resources employed are optimized. Provide all engineers involved with the tools and data necessary to complete failure analysis, knowing that resources may be limited. | JSC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2213 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Analysis of EEE parts failures during manufacture and usage in flight hardware has proven a useful tool in identifying part infant mortality, assembly processing and manufacturing defects, subtle assembly design overstress, and end of part life. However, the need to conserve essential program resources, combined with continued diminishing program funds, requires that a strategy for managing part failure analysis be established. Such a strategy can ensure that important failure analysis is still performed while making optimum use of available resources. This will provide maximum cost benefit to a program in which budgets are tight. Implementation Method: EEE parts failure analysis is essential in design and development of on-orbit space systems. A complete understanding of when and how these components fail can increase the reliability and chances for mission success of a system and is essential in the design process. Often times limited resources are available for such analysis, and management of those resources is the key. EEE part failure analysis is essential if the hardware is in the developmental stage, as defined by the following criteria: The parts are leading edge technology or based on new technology The part emulates a specific function The part has no reliability data available The system design is evolving or being enhanced prior to hardware manufacturing The parts are currently being manufactured or purchased The assembly hardware is currently being manufactured Failure to identify latent defects, infant mortality, manufacturing process deficiencies, and subtle design overstress conditions may result in additional cost to a program. If these deficiencies are caught in the beginning at the board, system, or field level, the cost of redesign to correct the defects can increase by a factor of ten or more, depending on the amount of rework, retest, and recall of the fleet hardware considered necessary. If the hardware is mature, as defined by the following criteria, a decision whether to perform failure analysis or to trend for generic failure causes should be determined. The following criteria should be utilized: The parts are from a proven technology and reliability data exists; The system design is certified; The hardware has successfully flown more than one mission; The parts have been demonstrated to be reliable and mature; Similar parts are not being installed into assembly hardware; ESD handling, testing and checkout procedures are well established and adequate; The parts are known to have adequate tolerance for Total Ionizing Radiation Dose and Single Event Effects for the mission. Space quality military parts used in the Space Shuttle Orbiter Program have a minimum expected life of ten years. If the part has failed with less than ten years field service life, failure analysis is recommended. If the part has had successful field service over ten years, trending of the part failure should be considered. The trending process itself must ensure that: sufficient investigation is performed to isolate the hardware failure, the process can detect an increasing failure rate, end of part life issues, tolerance shift does not give an undesirable system operational effect, the part is retained to support future trend investigations. If the flight hardware is mature, and the part is over twenty years old, a decision should be made whether the part should be submitted to the trend process or scrapped. This determination should be based on whether the part is obsolete and unavailable (or available in only limited quantities), whether sufficient information is available to make a failure analysis possible, or if failure analysis will provide valuable results for the program. A process flow of the decision process is provided in figure 1. [D] There is also a simple, cost effective way of performing failure analysis which requires delidding a part and examining it under a microscope to look for visible signs of ESD damage or overcurrent conditions. This may be sufficient if the box failed immediately after handling. If delidding does not reveal any of these symptoms, then one may use a Scanning Electron Microscope for more detailed examination of a device or component. If a device fails parametrically rather than functionally then analysis on the integrated tester may give clues about the failure modes. Each of these procedures adds a different value to the program. The investigator can request the appropriate level of analysis. Finally, a quotreality checkquot of the decision to failure analyze, failure trend or scrap the part should be made using the following criteria: Has the box failed immediately after handling? (It may be due to ESD damage to a device). Can random failures be tolerated? Have all sources of usage history, i.e. program, NASA Institutional, and Government - Industry Data Exchange Program been examined for related information to determine if a failure trend is indicated? Have other similar equipment impacts been evaluated and coordinated? Has the part provided quotreasonable, expected servicequot? Have all sources of processing errors, subtle overstress, and mishandling been considered? Is the equipment providing reasonable support to program goals? Will the equipment continue to support program goals in the foreseeable future? This criteria allows the designer or end item user to determine the most feasible and cost effective approach for their hardware and program. Sometimes a reality check can provide a simple means of identifying and resolving technical problems. Technical Rationale: This guideline provides a strategy for assessing part failure analysis as used in the Orbiter Program. This strategy has the benefit of a program that has redundant hardware/function, meets the fail operational-fail safe requirement, and can tolerate random failures and system maintenance while supporting its program goal. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
689 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Fiber-Reinforced Polymer Composite Material Selection |  | Avoidance of the material selection considerations can result in a fiber composite part or component that 1) does not satisfy design properties, 2) is unnecessarily difficult to fabricate, and 3) adds substantial program. Item 1 may lead to an expensive redesign. Item 2 can impact cost and program schedule. Item 3 can jeopardize the entire project. | Material selection is an important aspect of design. Often the success of the design is critically dependent on a material or materials performing as desired. This is especially true in the case of advanced composite materials with polymer matrices reinforced with carbon or aramid (Kevlar®) fibers. The important considerations necessary for a proper selection of a fiber-reinforced polymer composite material in NASA spacecraft and satellite structures include fiber material, fiber reinforcement form, fiber volume, matrix material, ply lamination, processing, cost, database, health and safety factors and end-item properties. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2210 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Proper selection of the fiber, fiber-reinforcement form, and polymer matrix will produce a material system that 1) satisfies design property requirements thermal/physical/mechanical), 2) facilitates fabrication processes (lay-up and cure) and 3) minimizes program risks (cost, schedule, and technical). Implementation Method: Overview Unlike a monolithic, homogenous material or an alloy, a composite is composed of two or more materials that retain their identity on the macroscopic level. Materials composing a composite can be classified as a reinforcement or strengthening phase and a matrix or binder phase. Reinforcement materials can be ceramics, polymers, or wires. Reinforcement forms can be continuous fibers, discontinuous or chopped fibers, whiskers, particles, platelets, etc. Matrix materials can be polymers, metals, or ceramics. The primary consideration of this guideline is fiber reinforcements and thermoset polymer matrices in the most common product form, a prepreg (pre-impregnated and partially cured) sheet or ply. This is done out of practical considerations, since these composites possess the highest structural efficiency (specific properties) and are the most highly developed in terms of processing methods and material characterization (data base). Much of the information in the guideline is, however, relevant to other manufacturing forms and methods, such as Resin Transfer Molding, Filament Winding, Fiber Placement, Pultrusions, and Injection Molding. The content by volume of fibers in the composite is a critical parameter from which the composite derives thermo/physical/mechanical properties. A body of science called micromechanics [references 1-4] exists to predict the properties of composites as a function of fiber volume given the material properties of the reinforcement and matrix. Micromechanics will not be discussed in this article. Fiber reinforcement in a ply can be unidirectional or multidirectional. The latter applies to woven and non-woven fabrics. Choice of reinforcement form is a degree of freedom that can result in better processing and labor savings in part fabrication. Plies with either or both reinforcement scheme are stacked and cured to make a laminate. The ply fiber angles in the laminate are oriented to satisfy application design requirements (stiffness, strength, thermal expansion, etc.). Laminate design/analysis methods will not be covered in this article. Information on this subject can be found in many publications [references 5-8]. The matrix phase is typically the material that most affects the processing, and most directly the curing of the composite. Choices for polymer matrices include a variety of epoxies, polyimides, and others. The choice of polymer matrix determines to a great degree the operational temperature limits for the composite. The matrix phase also affects other physical properties, such as outgassing and moisture diffusion. Lastly, there are additional considerations that include economic, experience (flight history), and safety considerations that factor into the selection of a composite material. Table 1 summarizes relevant selection considerations for a fiber-reinforced composite with a polymer matrix. A more detailed discussion of the selection considerations follows. Table 1. Composite Selection Considerations Fiber Considerations Thermo/physical/mechanical properties and relevance to end application Ply thickness and tow size availability Ply flexibility and part curvature Sizing and surface treatments for matrix bonding and wetting Cost, availability, lead time, and stable supply source Reinforcement Considerations Part curvature Ply thickness Laminate ply orientations Machining Weaving styles (drape) and weaving vendors Cost, availability, lead time, and stable supply source Resin Considerations Fiber sizing compatibility and wetting Cure temperature and related items: laminate residual stresses, tooling expansion, upper use temperature, composite glass transition temperature (Tg), and microcracking Prepeg handling characteristics: tack, drape, outlife Flow characteristics and processing method Mechanical properties: shear and tensile strength, modulus and strain compatibility with the reinforcing phase Physical properties: outgassing, moisture absorption/diffusivity/swelling, others Toxicity and health concerns Cost, availability, lead time, and stable supply source Other Considerations (Composite Level) Material characterization data base Flight history Cost, availability, lead time, and stable source Fiber Selection The designer or material specialist has a wide range of fibers from which to make a selection. Often a fiber is selected because of physical properties. For example, graphite or carbon fibers are electrically and thermally conductive, while aramid (Kevlar®) and glass fibers are non-conductive. In certain applications, such as an antenna reflector, electrical conduction is required. Hence, graphite (carbon) fibers are generally chosen for reflector-type applications. In other applications, for example a radome, radar transmissibility is desired. Here, Kevlar® and glass fibers are the materials of choice. Fiber selection should also consider mechanical and thermal properties. The salient mechanical properties are modulus and strength. Those for thermal properties include coefficient of thermal expansion (CTE) and thermal conductivity. Table 2 presents typical properties of some commercially available fibers presently utilized for space and spacecraft structures. Table 2. Typical Fiber Properties (Axial Direction) Trade Name/ Type Young's Modulus (Msi) Tensile Strength (Ksi) CTE (PPM/°F) Thermal Conduct. (BTU/hr- ft-°F) Density (Lb/in3) T300 33.5 530 -0.3 5 0.064 AS4 33.5 530 0.065 IM7 41.1 710 -0.5 9 0.065 T50 56.4 350 -0.55 40 0.0654 UHMS 64 550 0.067 P75S 75 300 -0.72 107 0.072 P100S 105 325 -0.8 300 0.078 Kevlar® 49 18 525 -2.2 5.3 0.052 E-glass 10.5 500 2.8 0.56 0.094 S2-glass 12.6 665 3.1 0.090 Quartz 10 500 0.3 0.0795 K1100 130-145 350-550 -0.9 550-676 .0777-.0813 M46J 63.3 611 -0.5 0.0665 M50J 69 569 -0.55 57 0.0672 M55J 78.2 583 -0.61 90 0.690 M60J 85.3 569 -0.61 88 0.0694 XN-50 75 530 -0.8 100 0.0773 XN-70 105 530 -0.9 180 0.0780 XN-80 114 530 -0.9 235 0.0780 Often figures of merit (FOMs) are used in fiber selection. FOMs are ratios of composite material properties [references 5,6], for which the fibers may be unidirectional or cross plied depending on the application. Some typical FOMs are E/r, F/r, E/r/a, and Ek/r, where E, F, r, a, and k denote Young's modulus, strength, density, coefficient of thermal expansion, and thermal conductivity, respectively. Broadly speaking, most structural applications fall into two categories: strength critical and stiffness critical. The choice of fiber must be attuned to the driving design requirement of the application. For example, in primary structure, strength is usually the dominant factor influencing fiber selection. Therefore, F/r is the appropriate FOM for fiber selection. Whereas in secondary structure having vibration frequency and/or deflection requirements, stiffness may be the dominant selection factor. In this case E/r is the pertinent FOM. For dimensionally stable applications, E/r/a is the meaningful FOM. For thermal applications, Ek/r is a relevant FOM. Tensile strength and modulus are controlled principally by the fibers in the composite. Compressive and shear properties, however are derived from both the fiber and matrix and the interface (bond) between them. The thickness of a ply or layer is also determined by the fibers, more specifically the fiber diameter and the number of fibers in bundle or tow. Thin plies (2.5 mils or less) require low tow counts (500 to 1000 filaments), which are not available for some fibers. Ply flexibility, which is a function of fiber modulus and ply thickness, should be considered with respect to part curvature. For example, the brittleness and thickness of a ply with ultra-high modulus carbon fiber may preclude its use in fabricating a deeply curved part. The choice of fiber also can impact the type of reinforcement form possible. For example, ultra-high modulus graphite fibers may present weaving difficulties, which can preclude the availability of certain fabric styles with tight weaves. The availability of fabric woven with high-modulus fibers has improved greatly in the recent past. Lastly, fiber selection must consider wetting, bonding, and material compatibility of the matrix resin. A coating or sizing on the fibers is applied for these purposes. In material selection, one should be aware of the importance of a proper coupling agent between the fibers and resin. This is particularly important for carbon fibers. Coupling agents for carbon fibers are usually proprietary formulations of the fiber producer or the prepreg vendor. Reinforcement Form Choices of fiber reinforcement forms include unidirectional and multidirectional. Selection aspects of each form are discussed below. The most commonly used product containing unidirectional fiber reinforcement is prepreg tape. Unidirectional tape has collimated bundles of fibers called tows, which run in the length or long direction of the tape. Unidirectional tape gives the ability to tailor the fiber orientations from layer to layer in a laminate. This results in design flexibility. Also, the widest choice of fibers are available in unidirectional tape. Unidirectional tape is available in a range of widths. The choice of tape width can facilitate lay-up and can promote efficient material usage. An example of the latter is less wasted material from cutting ply pattern details. When laying up unidirectional tape, the continuity of the fibers should be maintained. End-to-end butt splices that result in fiber discontinuity should be avoided. On the other hand, butting the sides of adjacent layers with parallel fibers is permissible. Use of unidirectional tape to produce parts with deep, double curvature can prove difficult. Lay up may be facilitated by cutting the tape into narrow strips. However, labor increases in doing so. The most common multidirectional reinforcement form is woven fabric. Fabric weave styles can have drastically different draping characteristics, which is an important characteristic in making doubly-curved parts and those with integral flanges and bends. Harness-satin weaves are more drapable than plain weaves. Other desirable characteristics of fabrics include bidirectional properties at a minimum gage, resistance to microcracking (matrix splitting between fibers), and good machining characteristics. In a woven fabric, the fibers will be curved to some degree or another depending on the weave style. Fiber curvature results in decreased composite moduli and strengths, especially in compression. Weaving also reduces the volume available for fibers in the composite. As a result, laminates made from woven fabric composites are less structurally efficient than those made from unidirectional tapes. Recent manufacturing advancements have made possible ultra-thin unidirectional and fabric reinforced composites. These materials have been manufactured in a thickness of one mil or less for unidirectional prepreg and about two mils for fabric prepreg. Such ultra-thin composites are especially attractive for lightly-loaded, minimum gage structures. Here, the weight of the structure and, importantly, the weight savings potential of the composite are directly proportional to layer thinness. Other benefits of ultra-thin composites include less micro cracking under thermal cycling and the potential for more homogeneous laminate stacking sequences for a given laminate thickness. The latter usually results in improved strength due to a more thorough interspection of ply-angle orientations in the laminate stacking. The disadvantages of ultra-thin composites are increased handling difficulty, cost, and lead time. Fabric prepregs may offer labor efficiency in lay ups. For example, a [0/90] (Fiber angles are 0 degrees and 90 degrees) laminate needs 50% fewer plies to be laid up using an orthogonally woven fabric, since fibers in two directions are obtained with every ply applied. Some fabric prepregs are available with hybrid fibers, such as carbon warp-yarns and Kevlar® fill-yarns, which may provide more potential design solutions. Theoretically, the possibilities of fiber type and weave style are unlimited. Practically, off-the-shelf choices are limited. Certain non-standard fabrics made from high- and ultra high-modulus fibers can be obtained from specialty weavers. The design use of such fabrics should be tempered by cost and lead-time considerations. Matrix Selection The choice of prepreg matrix resin is of critical importance in fabrication. The composite part quality is extremely dependent on the resin matrix and its handling and cure processing characteristics. The matrix vendor is usually the vendor that makes the prepreg, i.e., incorporates the fibers in the matrix. Handling characteristics are most important during ply lay up. Here the tack and drape of the prepreg are critical properties. If the prepreg is too stiff and boardy, then difficulty will be encountered in making curved parts, such as hollow tubes. Maintenance of ply-to-ply fiber orientations can be affected as well. If the prepreg is too sticky, then positioning and, in particular, repositioning of layer during layup is difficult. The handling characteristics are affected by the cumulative exposure of the resin in the prepreg to room temperature. The time limit at room temperature is called the out-life of the prepreg. For large parts especially, outlife should be considered in resin selection. Some resins have out-lives as long as 30 days; others, only several days. The resin in the prepreg determines the cure temperature of a composite part. Most epoxies and polycyanates cure around either 250°F or 350°F. Polyimides cure at higher temperatures. The cure temperature usually determines the glass transition temperature (Tg), which is associated with the useful upper-temperature limit of a composite. (Prudent design practice is to limit the use of a composite to below its Tg. The safe number of degrees below Tg depends upon the magnitude and direction(s) of the applied load with respect to the laminate fiber directions. It is advisable to experimentally confirm the maximum usage temperature of a composite for a particular application.) A higher cure temperature or, alternatively, a post cure generally raises the Tg. However, a high cure temperature results in greater cool down or residual stresses, which arise from CTE mismatches: ply to ply and fiber to matrix. Also for elevated cure temperatures, the thermal expansion effects of cure tooling become more critical, which adds to the difficulty in making parts and achieving desired dimensions. Besides the cure temperature, the prepreg resin determines other important cure characteristics, such as rheology and viscosity. These characteristics affect consolidation of the layers, most notably in the amount of voids or porosity produced during cure. The choice of resin should be compatible with the consolidation process. For example, low-flow systems are usually unsuitable for vacuum-bag/oven processing. High-flow, low-viscosity systems can present difficulties in net-resin (no bleed) processing, since resin leakage may be difficult to prevent. The resin material also affects the contamination concerns of the composite: outgassing and moisture diffusivity. For space use, a polymeric composite must pass mass-loss and condensibles requirements, such as those defined in SP-R-0022A, MSFC-SPEC-1443 and JSC 0022-A. In addition, moisture absorbed on the ground will be desorbed in orbit. This may result in undesirable shrinkage for parts with strict dimensional stability requirements. The resin must have suitable shear and extensional modulus, strength, and strain for the composite to function correctly. Matrix shear is the mechanism through which stresses are introduced and spread to the fibers. Matrix shear and tensile strength largely factor into the resistance of an unidirectional layer in a laminate to microcracking from thermo-mechanical loads. Also, the resin must have compatible extensional strain with the fibers in the composite. Lastly, the resin material determines the toxicity of the prepreg. Resin systems with carcinogenic compounds and other unsafe ingredients should be avoided. Other Considerations These considerations deal with the economics and experience with a composite. Economic considerations include cost and availability (lead time). Experience considerations include extent of data bases and previous successful flight applications. Some space applications are given in publications [9] and [10]. The importance of the stability of the material supplier or vendor should also be taken into account, as a long term source of supply is highly desirable and sometimes essential. References: Z. Hashin and B.W. Rosen, "The Elastic Moduli of Fiber-Reinforced Materials", ASME Journal of Applied Mechanics, Vol. 31, 1964, pp. 223-232. Z. Hashin, "Theory of Composite Materials", NASA CR-1974, 1972. R.M. Christensen, Mechanics of Composite Materials, John Wiley and Sons, New York, 1979. Z. Hashin,"Analysis of Composite Materials - A Survey", ASME Journal of Applied Mechanics, Vol. 50, 1983, pp. 481-505. DOD/NASA Advanced Composites Design Guide, Air Force Wright Aeronautical Laboratories, Dayton, OH, prepared by Rockwell International Corporation, 1983 (distribution limited). Military Handbook,"Polymer Matrix Composites", MIL-HDBK-17-3C, 4 November 1992. R.M. Jones, Mechanics of Composite Materials, Hemisphere Publishing Corporation, New York, Washington, Philadelphia, and London, 1975. S.W. Tsai, Composites Design, Fourth Edition, Think Composites, Dayton, Paris, and Tokyo, 1988. M.M.Schwarz, Editor In Chief, Composite Materials Handbook, McGraw-Hill, Inc., 2nd ed., 1992. Engineered Materials Handbook, Vol.1 - Composites, ASM International, The ASM Composite Materials Collection, Metals Park, OH. Structural Laminate Composites for Space Applications, Reliability Preferred Practice PD-ED-1217. Selection of Spacecraft Materials and Supporting Vacuum Outgassing Data, Reliability Preferred Practice PT-TE-1410. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
682 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Design and Manufacturing Guideline for Aerospace Composites |  | Failure to use state-of-the-art design techniques, tooling, manufacturing techniques, and automated manufacturing and inspection techniques for composite materials could result in the choice of inappropriate materials, costly scrappage, and potential failures in use. Failure to use composites in appropriate applications could result in noncompetitive products with greater complexity, weight, or damage susceptibility. | Composites must be considered as unique materials in the design and manufacturing process because manufacturing equipment, tooling, and inspection equipment and processes have a pronounced effect on design. Since the material is formulated while the part is being built; (1) multidisciplinary, concurrent engineering design principles and (2) careful material selection and fabrication processes must be used to obtain optimum properties in aerospace composites. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2205 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Conscientious adherence to proven concurrent engineering principles and careful design and material selection guidelines in the design, manufacture, and testing of aerospace composites will result in low rejection rates and high product integrity. Successful composite designs can provide design flexibility, lightweight parts, ease of fabrication and installation (generally fewer parts), corrosion resistance, impact resistance, high fatigue strength (compared to metal structures with the same dimensions), and product simplicity when compared to conventional fabricated metal structures. Implementation Method: Introduction: Composites are combinations of two or more distinct materials present as separate phases and combined to form desired structures. They take advantage of the desirable properties of each component. The manufacturing technique used to fabricate a composite structure is dependent upon material performance requirements, structure configuration, and production rates. The composite design and manufacturing methods discussed in this guideline are primarily for structural and mechanical applications and are composed of a resin (matrix) and a fiber reinforcement. Typical reinforcements are shown on Figure 1. [D] Performance of composite materials in aerospace applications is superior to conventional structural materials such as steel and aluminum. Composite materials and their manufacturing processes can be tailored specifically to given design constraints. The superior physical properties of composites allow for design with minimum concern for dimensional stability, corrosion, and crack formation. While it is possible to tailor the properties of a composite structure to minimize problems in these areas, it is imperative that this be taken into consideration during the design process. Composite materials are significantly superior to conventional materials in strength-to-weight ratio, one of the most important requirements of aerospace structures. Design: Concurrent engineering principles (i.e., the team approach to design using designers, thermal and structural analysts, manufacturing engineers, materials process engineers, tool designers, machinists, quality engineers, quality control specialists, and reliability engineers) contribute noticeably to the success of a composite materials program. Designs of composite components which are fault tolerant to known manufacturing conditions and variables should be selected. The success of a composite program is dependent upon establishing material properties early in the program. Establishing an accurate and reliable material property data base is one of the most important steps toward achieving a functional design. Experience indicates that the basic material allowables of a specific composite product should be determined utilizing the manufacturing facilities where production will take place prior to finalizing design. The preferred process should approximate the following: (1) define environmental and performance requirements; (2) review available materials against requirements to determine the family of material to be used; (3) determine materials; (4) determine materials allowables using material processed at the intended manufacturer; (5) proceed with design based on known material allowables; (6) test geometric configurations (i.e., special joints, specific contours, special ply layups, etc.); (7) along with nondestructive evaluation (NDE), use destructive evaluation to determine voids, ply dropoff, resin rich areas, etc., during initial manufacturing process development; (8) begin manufacturing production. Typical mechanical and impact damage properties of selected composites are shown in Tables 1 and 2. Table 1. Typical Mechanical Properties of Selected Composites Material Type Nomenclature Tensile Strength (ksi) Modulus (Msi) Strain (%) Carbon/Epoxy Glass/Epoxy Kevlar®/Epoxy Carbon/PEEK Carbon/Phenolic T300/934 IM7/8551-7 P75/934 AS4/3501-6 IM6/3501-6 E-glass/934 K-49/7934 IM7/APC-2 FM5055 245 400 135 100 330 150-170 80-85 419 15-20 20 24 44 10 23 6-8 4 24 2.6-2.8 1.0-1.2 1.62 0.2-0.5 1.0 1.5 2.75 1.85 1.6 1.0-1.2 PEEK= Polyetheretherketone Note: All samples were prepared from 16-ply quasi-isotropic layups. Table 2. Typical Impact Damage Properties of Selected Composites (1), (4) Nomenclature Max Impact Load (lb) Energy at Max Load (ft-lb) Compression After Impact (CAI) (ksi) (2) IM6/3501 IM7/SP500 IM7/F3900 IM7/977-2 T300/934 T650-42/1939-3 IM7/8551 IM8/8553 850 1100 1080 1170 560 1010 1240 900 9.2 9.1 9.7 10.3 3.7 8.5 12.1 7.4 23.2 36.2 39.9 47.1 (3) (3) 50 (3) Notes: (1) All samples prepared from 16-ply quasi-isotropic layups. (2) CAI values are normalized to approximately 125 ft-lb impact energy per inch thickness. MSFC M&P Lab data unless noted otherwise. (3) MSFC M&P Lab CAI testing planned for these materials. (4) Hercules data unless otherwise noted. The factors of safety shown in Table 3 should be used in the analysis and design of composites. During design and manufacturing process development, credible accept/reject criteria and acceptable repair methods should be developed. Table 3. Safety Factors for Composites Item Ultimate Minimum Test Factor Acceptance Test Flight Units Qual Unit Flight Unit Nonprotoflight (1) Structure Protoflight (2) Structure 1.4 2.0 (3) 1.5 2.0 (3) 1.4 1.2 1.05 Notes: (1) Fly separate test article. (2) Fly the article tested. (3) Stress riser or discontinuity Recommended Design and Analysis Guidelines for Composites: During the concept definition phase of the composite part design cycle, all of the critical design parameters are established. Geometric constraints and material considerations are outlined in order to establish the amount of design flexibility allowable. Maximum loads, both mechanical and thermal, are estimated. Weight, cost, and producibility concerns should be considered at this juncture. These factors should then be weighted and balanced to produce an initial design concept. For example, thermal material limitations should be balanced against cost and producibility concerns to select the appropriate composite material. Likewise, the layup of the laminate should be chosen considering not only the desired load capability, but also the thermal environment. High heat transfer areas could be cooled by using additional plies to act as a heat sink. These two factors in turn are offset by weight considerations. Several preliminary analysis and sizing tools can be used at this stage. PANDA, an elastic-plastic composite shell optimization program, is used in the analysis of stiffened panels. For flat composite panels, PASCO is sometimes used for preliminary sizing. The use of a Computer Aided Design (CAD) package is highly desirable in drawing the initial configuration. The configuration is then subjected to stress analysis. Depending on complexity, the part may be subdivided into subcomponents for separate analysis. If required, a structural computer model may be generated. For most parts, a finite element model is generated using PDA/PATRAN and the surface definitions from the CAD drawing. PATRAN is used as preprocessor and post-processor for MSC/NASTRAN, which has the capability of analyzing composite plate elements. Aerodynamic, vibroacoustic and thermal loads are obtained from the appropriate discipline areas for input into the stress analysis. The vibroacoustic analysis is performed by dynamics loads engineers using MSC/NASTRAN as a processor and IDEAS as a preprocessor and post-processor. A temperature profile for the part is provided by thermal engineers using MIDAS, a finite difference thermal analyzer, and thermal material properties supplied by the composites materials engineers. For shells of revolution under axisymmetric loading, BOSOR, a finite difference structural analysis program, may be employed. A simple general shell element finite element program, STAGS, is sometimes used to obtain input loads for BOSOR models. For more detailed analysis at a particular point, SQ5, a point stress laminate analysis program, is used. Edge loads for a critical element from a finite element or finite difference model are input into this program to obtain more detailed results. Thermal effects may be approximated using this program. However, if temperature gradients become excessive, in-house developed software may be required. Although buckling coefficients may be obtained from NASTRAN, NASA-supplied buckling knockdown factors for plates with complex curvature are used to compensate for inaccuracies inherent in the finite element program. Specialized computer programs are used to analyze joints and fasteners and their interface with the composite parts. Bolt programs determine the capability of bolted joints under combined bending, tension and shear applied loads, as well as tension due to preload and differential thermal expansion. Clip analysis programs analyze metal clips using empirical data. Composite joint programs are also employed; for example, BJSFM is used for bearing loads, and JOINT is used for elastoplastic multiple bolt joints. Below is a list of representative commercial computer programs that are available for analyzing stresses and strains in composite materials under various conditions. The ones most often used by MSFC are indicated as: [MSFC]. These computer programs are available from the company or source shown in parentheses. ABAQUS (Hibbitt, Carlson & Solenson, Inc.) ADINA (ADINA Engineering) ANSYS [MSFC] (Swanson Analysis Systems, Inc.) BOSOR [MSFC] (David Bushnell) NASTRAN (MacNeal-Schwendles Corp.) STAGS (COSMIC) CHAMPION (MSFC-used but not commercially available) Critical factors affecting strength and stiffness for fiber are modulus of elasticity, strength, strain to failure, and curvature. Critical factors for the matrix are modulus of elasticity, elongation to failure, stress-strain behavior, void content, and fatigue performance. Manufacturing: Typical aerospace composite manufacturing processes consist of filament winding, fiber placement, pultrusion, tape laying, tape wrapping, press molding, hand layup and resin transfer molding. Typical fiber/matrix composite uses and processing techniques for various MSFC programs are shown in Table 4 and Table 5, respectively. A summary of composite manufacturing processes is shown in Table 6. Table 4. Typical MSFC Users of Fiber/Matrix FIBER/MATRIX USAGE Carbon (Graphite)/Epoxies 1. Most used material for structural composites 2. Used in trusses, pressure vessels, optical benches, racks 3. Available in low, intermediate, and high modulus forms 4. Damage tolerance typically varies inversely with modulus Glass/Epoxies 1. Used in pressure vessels and sacrificial layers 2. Used as flame barriers for carbon/epoxy structures and as galvanic corrosion barrier between carbon/epoxy, carbon/phenolics and aluminum components Kevlar®/Epoxies 1. Used in pressure vessels and small solid rocket motors 2. Excellent damage tolerance 3. Low compressive strength Fiber-Reinforced Thermoplastics 1. Excellent damage tolerance 2. Good repairability 3. Lower structural performance thermosets Fiber-Reinforced Bismalemides, Phenolics 1. Excellent high temperature properties 2. Used in areas of high heat flux (nozzles, fairings, nosecaps) 3. Requires higher processing temperatures Table 5. Processing Techniques SUPPLIED FORMS PREPARATION METHODS CURING METHODS Prepreg tape of varying widths - unidirectional or fabric Prepreg quottowquot - preimpregnation fiber bundles Dry fiber plus wet resin Fiber-reinforced bulk modulus compound Filament winding-wet winding or prepreg tool Hand layup Tape wrapping Tape laying Pultrusion Polar winding Braiding Resin transfer molding Fiber placement Autoclave/hydroclave Oven Press Compression molding Table 6. Summary of Composite Manufacturing Processes PROCESS COMPOSITE MATERIAL COMMON USES TYPICAL TOOLING AND/OR EQUIPMENT Filament Winding Glass/Epoxy Graphite/Epoxy Kevlar®/Epoxy Carbon/PEEK Carbon/Phenolic Thermosets Solid Rocket Motor cases, pressure vessels Removable mandrels, automated lathe, resin bath, heat source, vacuum source, curing oven, autoclave, hydroclave, handling tools, trial fixtures, drill fixtures, and assembly tools. Pultrusion Glass/Epoxy Graphite/Epoxy Thermosets Thermoplastics Structural shapes of constant cross-section, e.g., tees, angles, channels, rods, tubing, and squares Pultrusion machine similar to metal extrusion machine, heat source, resin bath, cut-off device. Resin Transfer Molding Glass/Epoxy Graphite/Epoxy Kevlar®/Epoxy Carbon/PEEK Carbon/Phenolic Small to large structures of simple to complex shapes. Ply fibers placed in mold, mold closed, resin injected into mold (heated or room temp.) Low tonnage press, contoured molds (male and female), low- cost tooling using standard production steel, room temperature cure, over or autoclave. Hand Laying Glass/Epoxy Graphite/Epoxy Kevlar®/Epoxy Carbon/PEEK Carbon/Phenolic Small quantity production of test panels, prototype parts, or parts of complex contour Lay-up molds, vacuum bags, vacuum source, autoclave or hydroclave, and curing oven. Mechanized Tape Laying Glass/Epoxy Graphite/Epoxy Kevlar®/Epoxy Carbon/PEEK Thermosets Thermoplastics Small to large structures of simple or complex shapes Molds, computer-controlled ply cutting, flat and contoured tape laying, automated ply lamination, autoclave, hydroclave, curing oven. Fully Automatic Tape Laying Glass/Epoxy Graphite/Epoxy Kevlar®/Epoxy Carbon/PEEK Carbon/Phenolic Bismalemides Thermoplastics Small to large structural components of simple to complex shapes Contoured molds, automatic tape laying equipment consists of automatic cutter, broadgood dispenser, trim table, ply transfer table, tape laying, stitching module and contour ply handling system, autoclave, hydroclave, curing oven, handling tools, trim fixture, drill fixture, and assembly tools. Press Molding Glass/Epoxy Graphite/Epoxy Kevlar®/Epoxy Carbon/PEEK Carbon/Phenolic Flat panels, molded components for subscale solid rocket motor ablative materials Planten press molds (top and bottom) and heat source to mold. There are sensitive manufacturing variables that must be closely controlled during composite fabrication. Therefore, using certified and highly skilled technicians is required. Typical manufacturing variables are heat input, cooling input, roller pressure, machine speed, tape tension, curing temperatures and curing pressures. Technicians must understand what to do when one of these variables changes. Properly controlled manufacturing processes will result in proper tensile strength, density, thermal conductivity, and interlaminar shear strength. Tooling: Major factors to be considered in the design and fabrication of tooling for structural and mechanical components are: (1) dimensional tolerance control and configuration stability, (2) location of parts in a structurally reliable assembly to give the lowest possible cost, (3) contour and size of the part, and (4) control of fiber orientation. Other significant factors which control final tool concept selection are cost, tool service life, heat up rate, total energy requirements, production rates and related facility costs. The tooling required to fabricate most composite parts can be subdivided into several major categories including ply layup tools, skin or mold forms, curing aids, handling tools, drilling and trimming tools, assembly tools, molds and mandrels. Additional tooling and equipment are shown in Table 6. Testing: Component, subcomponent, and generic structural tests are performed to verify analysis. Particular component tests may include elements of aerodynamics, vibroacoustic and thermal loading conditions, as well as significant externally applied mechanical loads. Subcomponent tests may be performed for critical areas of the component. Generic tests include flange and stiffened panel tensile tests, damage tolerance tests, and standard temperature effect tensile and compressive coupon tests. Inspection: Quality assurance for composite parts centers on techniques for validating the physical and mechanical properties of a cured composite. However, quality assurance begins long before the end item is tested. A logical approach to quality control follows the fundamentals of composite reaction control: (1) raw material validation reaction control; (2) material characteristics; (3) in-process fabrication/handling/tooling effects; (4) cure process control and documentation; (5) post cure machining. Visual inspection is used to inspect bond lines that are visible in the various bond stages and to detect any visible surface discontinuities and/or delaminations. Mechanical inspection is used to verify design dimensions, acoustics, input resistance, static loads and dynamic loads. Non-destructive evaluation is perhaps the most important inspection technique for determining defects in composites, particularly the defects specified in Table 7. Table 7. NDE Techniques for Detecting Defects in Composite Materials Defect/ Composite Method* X-ray Ultrasonics Computer Tomography Alcohol Wipe Thermography Eddy Current Dye Penetrant Delaminations/ All 8 X X X X X Density Variations/ #5 X X Resin Rich-Resin Poor/All 8 X X Voids/#1 X X X Crazing (Micro-cracks)/ All 8 X X X Wrinkles/ All 8 X X Conductive Materials/ #2 X * Composite Methods: 1. Filament winding 2. Fiber placement 3. Pultrusion 4. Tape laying 5. Tape wrapping 6. Press molding 7. Hand layout 8. Resin transfer molding Technical Rationale: MSFC experience with composites includes filament winding, tape laying, fiber placement, hand layup, computerized pultrusion, and automated tape wrapping. Computer programs are available to assist in the composite design process. The mechanical properties and impact damage properties that have been derived from tests of various composite materials can be used by designers to select the proper material and configuration for the job. Research is continuing to expand the available storehouse of design guidelines, leading to the production of reliable aerospace composite components. Valuable references which provide detailed design and analysis parameters for composite materials are provided in this guideline. References: Agarwal, B.D., Broutman, L.J.: quotAnalysis and Performance of Fiber Composites,quot John Wiley and Sons, Inc., Second Edition, 1990. ASM International Handbook Committee: quotComposite, Engineered Materials Handbook,quot Volume 1, Third Printing, August 1989. DOD/NASA: quotAdvanced Composites Design Guide,quot Volume I-IV, 1989. Jones, W.K.: quotTest Report Graphite/Bismalemide Allowables Data Base,quot Martin Marietta Composites Technology Group, August 1987. Lubin: quotHandbook of Composite Materials,quot 1982. MSFC-HDBK-505A: quotStructural Strength Program Requirements,quot January 1981. MSFC-HDBK-1453: quotFracture Control Program Requirements,quot October 1987. Morgan, Jr. L., Sigur, W.A.: quotFastening Techniques for Composite Materials,quot Martin Marietta Composites Technology Group, August 1985. NHB 8071.1: quotFracture Control Requirements for Payloads,quot September 1988. Sherrouse, M., Blum, C.: quotRecommend Practices for Composites, Design and Analysis,quot Martin Marietta, Michoud, LA, March 1992. Strong, Dr. A. Brent: quotFundamentals of Composites Manufacturing; Materials; Methods, and Applications,quot Society of Manufacturing Engineers, Dearborn, MI, 1989. Whitney, J.M., Daniel, I.M., Pipes, R.B.: quotExperimental Methods of Fiber Reinforced Composite Materials,quot SESA Monograph Number 4, Prentice-Hall, Englewood Cliffs, NJ, 1982. Applications of Ablative Composites in Solid Rocket Motor Nozzles Reliability Preferred Practice No. PD-ED-1218; Marshall Space Flight Center. Structural Laminate Composites for Space Applications Reliability Preferred Practice No. PD-ED-1217; Marshall Space Flight Center. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
681 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Concurrent Engineering Guideline for Aerospace Systems |  | Failure to: (1) have all critical disciplines represented on the concurrent engineering team; (2) standardize methods of creating and maintaining three-dimensional models; (3) display or furnish all design and engineering information to key team members on a timely basis; and (4) provide effective configuration management controls on the master model could result in wasted expenditures for hardware, software, training, and concurrent engineering management. | Use concurrent engineering techniques, coupled with computer-based three-dimensional solid modeling, simulation, and engineering analysis methods to design and develop reliable hardware and software. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2204 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Reliable hardware and software can be designed and developed in a shorter time and at a lower cost and at a short schedule if maximum use is made of a computer-aided concurrent engineering techniques. Operational, manufacturing, assembly, quality, reliability and safety considerations can easily be interjected at the beginning of the design process through the prudent use of the team approach, aided by computer based rapid prototyping techniques, methods, and tools. Implementation Method: Background: Concurrent engineering is the simultaneous and integrated engineering of all design, manufacturing, and operational aspects of a project from the conceptual formulation of the project through project completion. It is a team-engineering process in which all of the specialists who normally get involved in a project combine into a multi-disciplinary task force to carry out a project. They work together, trading ideas, and ensuring what they do early in the project (like major design decisions or changes) will not adversely affect what they do later (like quotmanufacturing inquot quality or supporting flight operations). All disciplines are addressed simultaneously. Until the advent of high-powered, networked computers and communications systems, effective concurrent engineering was an ambitious goal, particularly for large, technically complex aerospace projects. The advent of interactive three-dimensional computer-aided design, solid modeling, simulation, and virtual reality methods has created a naturally adaptive environment for the complex interactions that are required in a truly effective concurrent engineering process. This guideline describes the desirable elements of a successful concurrent engineering process and enumerates the ways computer-aided techniques can facilitate the effective meshing of the simultaneous engineering process with currently available design, analysis, processing and image processing tools. The Concurrent Engineering Process: A key to the success of the concurrent engineering process is to gather together a complete and competent team to carry out the project. All disciplines that will be affected by the hardware and software configurations must be represented. Typical engineering disciplines that must be represented on a concurrent engineering team are: flight hardware or software design, mission operations, manufacturing and assembly, tooling and fixture design, and safety and mission assurance. As shown on Figure 1, consideration of each of these disciplines, coupled with the client, user, or customer requirements is the key to a successful integrated design. The fully integrated design is then subjected to process engineering and production functions to provide operational hardware and software. Concurrent engineering teams must be encouraged to develop a free flow of ideas between team members. The object of the team approach is to provide an environment in which potential problems can be easily and quickly exposed to creative and synergistic problem solving by the innovative engineering and design processes of the team itself. To do this, the hardware and software configurations under consideration must be communicated to all team members with equal rapidity and understanding. This is where computer-aided solid modeling, simulations, kinematic modeling, virtual reality, and graphical computer-aided engineering analysis techniques come into play. [D] The Use of Computer-aided Concurrent Engineering Methods: In recent years, computer-aided design tools that have become available have augmented, and in many instances, replaced the design—build—test, design—build—test cycle. A master model usually takes the form of a three-dimensional, color image of the element, mechanism, system, or component being developed. Software programs now available can be programmed to interface (in varying degrees of seamlessness) with this master model to perform a wide variety of engineering functions. The resulting refined master model can be used to define, design, and provide manufacturing and operational control codes for the tooling, fixtures, and the element itself. On-screen, three-dimensional animated simulations are made possible through sophisticated software coupled with high-speed computers. In many instances, effective use of these simulations will eliminate the need for hard mockups, operational models, and engineering prototypes. High reliability, and a shorter development cycle, are feasible through the use of these systems. Computer Modeling and Integrated Engineering Analysis: Through the use of three-dimensional solid modeling and related computer-based kinematic and dynamic analyses, interference analysis and interface checking can be automated. Engineering analysis procedures such as structural and thermal finite element analyses, mass properties analyses, tolerance analyses, and ergonomic studies can be performed using the master three-dimensional model as an input to currently available engineering analysis software modules. Motions and forces generated in simple or complex mechanisms can be derived accurately without building and testing the actual hardware. Virtual imaging and virtual reality interactive displays can help the concurrent engineering team to establish valid mechanical or human interfaces. Simulations of the robotic mechanisms interaction personnel and with hardware can yield off-line programming codes that will control robots. Three-dimensional solid models of aerospace structures have proven useful for the routing of electrical or fluid lines, the confirmation of manufacturing and maintenance access to structures, and the design of master tooling and fixtures. Rapid transmission of structure designs to other disciplines (propulsion, electrical, manufacturing, and quality) has speeded up the process of team engineering design. Simultaneous electronic linking of documents and specifications with hardware designs and software coding has enhanced traceability and data compatibility with designs in rapidly changing configurations. Solid, three-dimensional prototypes can be created directly from a three-dimensional computer image through stereolithography and laser-fused deposition techniques. The design and configuration of tooling, fixtures and prototypes of these elements can be created through interaction with the master model, and machine instructions can be generated that will produce the master model. Thus, engineering designs can be rapidly converted into manufacturing aids and control codes. By linking engineering, project management, and work flow information to computer aided drawings and models, the speed and reliability of product data management, file management, and work process flow management can be enhanced. Real-Time Participation of the Concurrent Engineering Team in the Computer-Aided Design and Development Process: Availability and proper use of currently available computer-based systems can significantly improve the communication of engineering information among members of the concurrent engineering team. Each member is able to view parts, components, subsystems, and system, as they appear in final form well before hardware is built. Thus, interfaces and interactions between system elements and disciplines can be significantly enhanced. General guidelines for optimum use of these techniques and methodologies are as follows: In planning multiple-organizational support of the computer-aided concurrent engineering process, strive for standardization in the following areas: The manner in which computer-aided drawings and models are identified, constructed, and filed. The color coding, layer designations, scale, symbols, graphic ground rules, and format of computer-aided design documents. The quothandshakingquot between computer-aided capabilities of participating organizations. Provide rapid transmission or networking of information and central displays of pictorial, graphical, and text information about the project for concurrent review by all key concurrent engineering design team members. Provide configuration management controls for the master model, with free access for viewing, analysis, and alternate design creation. Put prudent restrictions on changes to the master model. Provide more time in the beginning stages of a project to allow the interactive design process to operate. Permit this longer initial concept definition and design phase to create a faster production and operations phase by freezing the design once all engineering interactions and considerations have been thoroughly input, negotiated, and established. Technical Rationale: The concurrent engineering process by its nature does not require the normal control and review activities historically performed in the management of product development. The degree to which the concurrent engineering process is empowered to proceed with parallel process actions is believed to be directly proportional to potential schedule, cost, and reliability improvements. The use of concurrent engineering practices, coupled with the application of current state-of-the-art three-dimensional solid modeling and analysis tools, has proven to dramatically reduce new project development times while maintaining or further improving quality, reliability, and safety. MSFC has implemented several projects using concurrent engineering techniques and has reduced to practice several software and hardware elements using computer based three-dimensional kinematic and dynamic analysis. Although the project development teams now in operation have not yet completed the development cycle, the concurrent engineering process is working smoothly. Beneficial results are expected. Manufacturing and refurbishment cells using robots that were designed and programmed with kinematic and dynamic simulation techniques were put into operation in record time and are producing high quality results. References: Ashley, Steven: quotDARPA Initiative in Concurrent Engineering,quot Mechanical Engineering, ASME, New York, NY, April 1992. Aukstakalnis, Steve: quotVirtual Reality and Experiential Prototyping of CAD Models,quot Design Net, Ariel Communications, pp. 62-65, January 1992. Babai, Majid et-al: quotMobile Robot Hydroblast System, CAD/CAM, Robotics and Factories of the Future,quot pp. 350-355, Southbank Press, London, 1991. Bein, Christopher: quotRobot Simulation and Manufacturing, Aerospace Engineering,quot SAE, pp. 11-13, October 1992. Edwards, David E.: quotInteractive Computer Graphics,quot Aerospace America. AIAA, New York, page 41, December 1992. Hartley, John R.: quotConcurrent Engineering,quot Productivity Press, Cambridge, MA, 1990. Hedberg, Sarah: quotConcurrent Engineering,quot The Spang Robinson Report on Intelligent Systems, Vol. 8, No. 4, Wiley, New York, NY, April 1992. Hurwitz, Ken: quotIntegrating 3-D Solids in Design,quot Design Net, Ariel Communications, pp. 49-51, Austin, TX, January 1992. Kramer, Bill: quotThe CAD/CAM Link to DFM (Design for Manufacturability),quot Design Net, Ariel Communications, pp. 17-51, Austin, TX, February 1992. Kusiak, Andrew: quotConcurrent Engineering: Automation, Tools and Techniques,quot John Wiley & Sons, New York, NY, 1992. Park, Brian V.: quotConcurrent Documentation,quot Design Net, Ariel Communications, pp. 25-30, Austin, TX, January 1992. Wahlin, Greg: quotIntelligent Interference Checking,quot Design Net, Ariel Communications, pp. 35-38, Austin, TX, June 1992. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
683 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Fabrication of Gaseous and Liquid Fluorine Systems |  | Failure to use the design data presented in this guideline may result in unsafe systems and failures which are costly and potentially injurious to personnel and environment. | Use established guideline in fabrication and assembly of components for use in gaseous and liquid fluorine systems to eliminate failures and improve reliability of such systems. | GRC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2208 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: This guideline compliments Reliability Guideline GD-ED-2206, "Selection of Compatible Materials for Use With Gaseous and Liquid Fluorine". The use of these guidelines will benefit a designer in choosing the correct materials, proper fabrication, and assembly of the components for safe and reliable operation. Implementation Method: The effect of elemental fluorine and fluorine-oxygen (FLOX) mixtures with most materials is reactive under suitable conditions. As addressed in the Reliability Guideline GD-ED-2206 "Selection of Compatible Materials for Use With Gaseous and Liquid Fluorine", no organic material is totally resistant to elemental fluorine. Failures in fluorine systems are due to improper fabrication, assembly, and cleaning/removal of contaminants. The major cause of failures in fluorine systems is due to weld defects, trapped moisture, foreign and incompatible materials. Fabrication The following conditions should be followed to preclude any failure due to improper fabrication of fluid system components: Machine parts, castings,and purchased parts. Any parts that contain scales or oxides must be cleaned and passivated. Porous casting must be avoided since foreign material is difficult to remove from the surface of the material. Soldering and brazing parts. Joints should be free from pits, pockets, and crevices. During soldering and brazing flux should never be used, silver solder or nicro-braze are preferred. If any flux is deposited from the solder it must be completely removed from the system. Welding or welded component parts. All welds must be free of pinholes, slag, cracks, and crater defects, and have 100% penetration of the welded zones. Welded components with pockets, surface flaking, flux, or slag cannot be permitted. Welded parts and connections must be properly cleaned and passivated prior to service. Tubing connections and bend radius. The bend radius of tubing should be as large as possible at high flow rate areas. Avoid using sharp angle connections, 90° or 45° pipe fitting connections. All parts (internal and external surfaces) should be visually inspected for pits, discontinuities, and inclusions. It is also recommended that components be x-rayed to make certain all material discrepancies are found. Cleaning Procedure Cleaning of all parts is necessary to remove any possible contaminants that are in the components. A list of common contaminants is shown in Table 1, and the possible reaction occurring under the tested conditions. Table 1. List of common fluorine contaminants Contaminants Gaseous fluorine @ atm. pressure & temperature Gaseous fluorine @ 1500 psi. & atm. temperature Liquid fluorine @ -195.5°C & atm. pressure Liquid fluorine @ -195.0°C & 1500 psi. Water no reaction reaction no reaction reaction Ice no reaction N/A (Not Attempted) explosive N/A (Not Attempted) Fluorolube HO no reaction reaction no reaction no reaction Molylube no reaction reaction explosive N/A (Not Attempted) Slag on stainless steel joint no reaction reaction no reaction reaction Flux on silver-solder stainless steel joint no reaction reaction no reaction reaction When cleaning components, the proper solvents should be used to prevent ignition from fluorine exposure. A list of recommended cleaning solvents are shown in table 2 (see Reference 1). Table 2. Recommended Cleaning Solvents Solvent or Cleaner1 Material West Penetone TPC Solvent All metals Halon TFE Teflon TFE Teflon FEP Nickel-filled Teflon Acetone Kel F-81 Plaskon 2000 Halon TVS 1Soap and water are preferred for final cleaning of all materials listed, since elastomers absorb solvents. All solvents must be completely removed after cleaning. West Penetone TPC solvent should be used for vapor degreasing of individual parts. General procedures should be followed when preparing metal parts for cleaning and assembly. The following list, which is detailed in reference 1, shows the recommended procedure for cleaning metallic components. All components (valves, pumps, etc.) should be disassembled, and any parts incompatible with solvents, such as gaskets and O-rings, must be removed. Any amount of scale, slag, flux, etc., must be removed from the surface that will come in contact with the fluorine. The surface can be cleaned with nitric acid or abrasive cleaner. The final result should leave the surface bright and the base metal exposed. Care should be taken to avoid disturbing metal-to-metal sealed joints. There should be no sign of the foreign material on the metal. All solvents must be removed from the cleaned surface such that there is no sign of residue. Piping and components that are visually clean should be dipped into a nitric acid bath solution (10 - 25% nitric acid). Once removed all components should be flushed with deionized water and thoroughly dried. When needed, components may be vapor degreased, solvent bath degreased, and hand wiped. After hand-wiping the component should be immersed in a nitric acid bath or solvent and thoroughly flushed and dried. Vapor degreasing nozzles should be used for components with holes, ports, or complex configurations. To increase drying time and aid in removal of any liquid, helium or dry nitrogen should be used. Valves and complex components can be heated in a vacuum chamber to ensure all liquid or moisture is removed. Components should be immediately used or packaged to prevent recontamination. Final preparation, after assembly of components, is to passivate the system with a small amount of fluorine gas. Fluorine will react with the metal to form a metal fluoride film. A slight pressure of helium should be maintained in the system to prevent any contamination from moisture. (Note: After final assembly and passivation avoid sharp tapping or rapping of components. The tapping, rapping or movement of passivated components may cause flaking of the fluoride film inside the components which may result in a reaction point.) If components are being processed and cleaned, they should be immediately used or packaged in an approved contaminant free plastic bag. Silica gel packets should be contained with the cleaned components to reduce any moisture contamination during storage. Technical Rationale: Due to the extreme reactivity of fluorine with certain materials it is necessary that the designer and technicians become knowledgeable with fluorine material compatibility, fabrication, and assembly of components. Carelessness during fabrication or failure to remove contaminants will result in some form of reaction (e.g., fire, explosion). With this understanding of the chemical reactions with fluorine and other materials, system designers will be able to prevent critical failures in the system. This will reduce the unnecessary risks involved in developing fluorine systems. References: Schmidt, H. W., Fluorine and Fluorine-Oxygen Mixtures in Rocket Systems, NASA SP-3037, 1967. Price Jr., H. G. and Douglass, H. W., Nonmetallic Material Compatibility With Liquid Fluorine, NACA RM E57G18, 1957. Slesser, Ph.D. Charles and Schram, Stuart R., Preparation, Properties, and Technology of Fluorine and Organic Fluoro Compounds, McGraw-Hill, New York, 1951. Reliability Preferred Practice GD-ED-2206 Selection of Compatible Materials for Use With Gaseous and Liquid Fluorine Reliability Preferred Practice PD-ED-1224 Design Considerations for Fluid Tubing Systems |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
685 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Electrostatic Discharge Control in GSE |  | Voltage potentials on surfaces can result in uncontrolled electrostatic discharge (ESD). The results of ESD can cause ignition of solid propellants, explosives and flammable/combustible materials, cause damage to or inadvertent actuation of electronic devices/systems, and more familiar shock experienced by personnel. Shock to personnel could cause (depending on the magnitude of the charge and the health of the individual) involuntary muscle reaction which can result in injury or flight hardware/equipment damage. | Reducing the risk of Electrostatic Discharge (ESD) during Space Transportation Systems (STS) processing requires an understanding of the problems and proper reliability practices or controls for various conditions/situations. When conductive materials are present, proper bonding and grounding techniques are essential. When non-conductive materials (i.e., wood, paper, glass, plastics, etc.) are present, these materials must either be eliminated or properly selected or treated for the particular application and use. Another important factor in ESD control is the percent relative humidity (RH) which should be monitored and regulated/controlled, where feasible. | KSC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number GSE-3008 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Proper control of electrostatic discharge can significantly reduce the possibility of: Inadvertent ignition of solid propellants, explosives and flammable/combustible materials, Inadvertent actuation of electronic devices/systems Personnel shock or injury and Ground Support Equipment (GSE) hardware/equipment damage that could lead to flight hardware damage. Implementation Method: Electrostatic controls are implemented at KSC to reduce the effects of ESD during the following operations: General STS and Payload Operations - The percent relative humidity in an operational area is recorded every four hours prior to the start and during operations involving exposed solid propellants, open flammable/combustible fluid systems and category A Electro-explosive Devices (EED) when the Faraday (electrically conductive shield) cap is removed or firing circuits to EEDs are exposed. At or below 50% RH, bonding and grounding measures are verified. In addition, non-conductive materials in the area and personnel not wearing personnel grounding devices are checked with an electrostatic meter to ensure voltages greater than 350 volts are not present. Electrostatic scanning, not exceeding one hour intervals, is performed during the operation when at any time: additional personnel, equipment or hardware are introduced into the immediate area, the RH decreases, or the handling of non-conductive materials is required. At or below 30% RH, operations involving exposed solid propellant, except Solid Rocket Booster (SRB) segments, or open flammable/combustible fluid system and category A EEDs (with Faraday caps removed or firing circuits exposed) are not permitted. In the Orbiter Processing facility (OPF), the RH is controlled to within 40 - 50% thus minimizing the effects of ESD. STS SRB Processing - Segment processing may continue below 50% RH using the following guidelines, segment processing is not permitted at or below 10%: Between 50% and 30% RH the above requirements apply. With proper approval, operations may continue at RH levels below 30% down to 10%. In addition to the above requirement, electronic scanning is required to to be accomplished at 10 minute intervals if the propellant is exposed, and at 30 minute intervals if the propellant is covered. At no time will operations continue on the segments with propellant exposed and a potential of 350 volts or greater is measured on the segment case, propellant, or any equipment/personnel within five feet of exposed propellant. When the segment and rings with shipping covers are installed (propellant protected by a Faraday cage), the following guidelines apply: A reading of one kilovolt or less on the case is acceptable and work may continue. A reading of greater than one kilovolt, but less than four kilovolts on the case requires all segment processing to cease and personnel will stand back four feet. An electrostatic scan will be repeated every five minutes and recorded. If the reading of one kilovolt or up to four kilovolts exists for 30 minutes, connection to facility ground will be verified. If this connection is open, then the ground will be reconnected thru a resistor (1 Meg ohm +/-20%). Processing may continue when the electrostatic scan indicates less than one kilovolt. An electrostatic reading of four kilovolts or greater requires all work to stop. All personnel will evacuate to a location 500 feet from the processing area. Designated personnel may re-enter for electrostatic scan. This scan is repeated not less than every 15 minutes. No attempt to check grounds will be performed. If, after an hour, readings still exceed four kilovolts, then a separate ground with a resistor (1 Meg ohm +/- 20%) in line may be connected to another ground point on the segment case. Work may resume when a reading of one kilovolt or less is obtained and all grounds have been rechecked. Launch Processing System (LPS) Operations - LPS operators coming in contact with the LPS hardware subsystems are required to wear approved grounding wrist straps during test and launch processing operations in environmental conditions below 45% relative humidity. LPS system, maintenance, or support personnel coming in contact with low voltage LPS hardware Line Replaceable Unit (LRU) / Components are required to wear approved grounding wrist straps at all times. LPS / Checkout, Control and Monitor Subsystem (CCMS) console stations are equipped with approved terminated ground cables containing quick connect / disconnect type wrist strap snaps. Systems, maintenance or support personnel will connect the grounding lead clip to a conductive surface on the LPS grounded hardware structure. Testing stations are available for proper go/no go testing of the approved grounding cable and wrist straps. Logistics - The effects of ESD on static sensitive Line Replaceable Units (LRU's) during transportation and storage is alleviated with the use of transparent electrostatic-shielding bags. This packaging scheme affords static protection against both external static fields and internal triboelectric charge. All programmable read-only memories (PROM's) are transported and stored in static-shielding tubes or approved foam and shielding bags for distribution to installation in LPS hardware sets. These tubes protect against triboelectric charging and direct discharge yielding a dynamic response rating of less than 1 millisecond. All integrated circuits (IC's) for temporary staging are placed (leads inserted) on crosslink, noncorrosive, high density, conductive foam. This foam ensures that all device leads are kept at the same potential, thereby protecting the device from ESD damage. Other - inspection, testing and repairs of static sensitive electronic components or LRU'sare performed at approved ESD work stations. These work stations, designed to bleed off static charges, utilizes static dissipative table mats electrically connected to a static dissipative floor mat which is connected to ground thru a series resistor (1 Meg ohm +/-20%). The operator connects a wrist strap, to a single point ground, to make himself equal to the same potential as the components that are on the table, thus, prohibiting static discharge on conductive components. Technical Rationale:Fundamentals of Electrostatics - To insure successful implementation of proper guarding against harmful effects of ESD, familiarity with the concepts of electrostatics and ESD is necessary. Here, the basic elements are briefly discussed. For more extensive discussion, refer to books listed in the references. The main basic elements of ESD are&colon. electric charges, electric field, electrostatic potential, capacitance, charge generation and charge removal. Electric Charges - Experiments have shown that when two dissimilar objects are brought into contact with each other and then separated, the two objects become charged. The classic example is the rubbing of a silk cloth on a glass rod where the charge is visually evident when the charged objects cause the hair on your arm to stand up or cause small bits of paper to be attracted to the charged objects. If two corks are charged by the glass rod, the corks will repel each other because of like charges. Conversely, if one cork is charged by the glass rod and the other is charged by the silk (opposite charges), the corks will attract each other. The charge on these objects is due to an excess or deficiency of electrons on their surfaces. These charges are referred to as static electricity. This is because they can remain stationary on an object for substantial long periods of time. It is to be noted that this sudden transfer of charge from one body to another (by oppositely charged bodies being brought into close proximity) is called electrostatic discharge or the better known acronym "ESD". Lightning is a very high energy form of ESD. The interactions between electric charges are described by Coulomb's law: F=kq1q2/r. Where F is the magnitude of the force, k is the proportionally constant, q1 & q2are the charges on the object and r is the distance between them. Electric Field - describes the influence of an isolated charge on other charges in its vicinity. This electric field is the direction and magnitude of the force exerted by the charge on a unit charge at any point in its environment. The field strength (E) of an object is force(F)/charge(q). A good example of electrostatic field is when a person generates a charge on a balloon and then holds it above his head to make his hair stand up. The balloon never touches the hair, but an electrostatic field has been created. Electrostatic Potential - the amount of energy (work) per unit charge required to move a charge from one point to another in a field. The movement of the charge (q) along a distance (X) requires work (W). Thus the equation W=FX and, substituting the forementioned, W=qEX or W/q=EX . This work per unit charge is the potential difference expressed in volts. Thus the formula E=V/d, where E is the electric field intensity, V is the electric potential and d is the distance between the potential voltages. Ideally, we want to make sure that all charges remain at the same level or same potential so that no ESD (zap) occurs. Capacitance - the ratio between the charge on two plates and the potential difference between them, or, C= Q/V. In the case of two parallel plates this capacitance C=eA/d where A is the area of the plates and d is the distance between the plates (potential voltages) and, e is the dielectric constant. Where typical capacitance (C) values for humans ranges from 50 to 500 picofarads (pf) and dielectric constants of 1 (air and insulators) to 10 (insulators). The energy stored in a capacitor is given by the expression E= 1/2CV2 or 1/2Q2/C. Charge Generation - charging that occurs as a result of contact and frictional motion is referred to as triboelectricity. To describe, whenever two materials (one must be an insulator) are brought together and then separated, there will be a flow of electrons from one material to the other. The material giving up the electrons becomes positively charged while the material accepting the electrons becomes negatively charged. Charge Removal - dissipation of electrostatic potential with the use of soft grounding, static dissipative materials and air ionizers. Listed below are some of the more common materials and their polarity (+ or -) in the triboelectric series. Asbestos Acquires a more positive charge Glass Human Hair Nylon Wool Aluminum Paper Polyurethane Cotton Neutral reference point Wood Steel Sealing Wax Hard Rubber Mylar Epoxy Glass Nickel, Copper, Silver Brass, Stainless Steel Acrylic Polystyrene Foam Polyurethane Foam Polyester Polyethylene Polypropylene PVC (vinyl)Teflon Silicone Rubber Acquires a more negative charge When the charged object is an insulator, the charge can last for extended periods of time. This is true because insulators are poor conductors of electricity. Conversely, when the charged object is a conductor, the charge will decay rather quickly. The factors affecting the magnitude of the rate of charge generation are: Relative position in the triboelectric series. Intimacy of contact (proximity of the materials). Coefficient of friction between materials. Rate of separation. The factors affecting the magnitude of a rate of discharge (dissipation) are: Conductivity of the materials. Relative humidity. Moisture on the surfaces of the materials. Rate of recombination. Some typical electrostatic potential (volts) generated for typical events with various levels of relative humidity (RH) are respectively: Walking across a carpet 35,000 volts @ 10% RH 15,000 volts @ 40% RH 7,500 volts @ 50% RH Walking across a vinyl floor 12,000 volts @ 10% RH 5,000 volts @ 40% RH 3,000 volts @ 50% RH Pulling tape quickly from its roll 10,000 volts @ 30% RH ESD is not normally a concern when the relative humidity is greater than 50% RH because moisture in the air will act as a high resistance bleeder. This will then dissipate voltage potentials on the surface before they can build up to a level of approximately 350 volts and result in ESD. A few materials such as teflon, vinyl, etc. do not absorb moisture and therefore, will not bleed off readily even in environments above 50% RH and should be avoided where ESD is a concern. Environments below 50% RH require special attention for selection of and use of tapes, plastic films and electrostatic flooring material. Operations below 30% RH should be carefully assessed and avoided when possible. At levels below 30% RH, additional precautions shall be employed (e.g., air ionizers, humidifiers). Voltages, especially on large surfaces, should be dissipated using a high resistance resistor (1 Meg ohm +/- 20%) in series with the ground wire until the charge is eliminated before going directly to ground. Note: Surface resistivity changes exponentially with humidity changes. Therefore, relative humidity levels maintained between 40% and 60% are recommended. References: Electrostatic Discharge Control Program for Protection of Electrical and Electronic Parts, Assemblies and Equipment, MIL-STD-1686B. Electrostatic Discharge Control Handbook for Protection of Electrical and Electronic Parts, Assemblies and Equipment, MIL-HDBK-263A. Requirements for Electrostatic Discharge Control, NHB 5300.4(3L) ESD Program Management by G. Theodore Dangelmayer of AT&T. Investigation Analysis of the ESD Protection in the Facilities at the John F. Kennedy Space Center by Peter Stonefield, LSOC QE. Passive Static Protection: Theory and Practice by George R. Berbeco. KSC Ground Operations Safety Plan, GP-1098G. SPC Standard Practice Instruction (SPI) QA-016(3)K entitled Receiving Inspection of Parts and Materials (SPC procured & Government furnished). SPC Standard Practice Instruction (SPI) LP-021(5)K entitled Electrostatic Discharge Prevention (to LPS). SPC Standard Practice Instruction (SPI) LG-661(7)K entitled Preservation, Packaging, and Packing of Materials. | This practice has been used on the Space Shuttle Program, Launch Processing at the kennedy Space Center. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
684 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Designing for Dormant Reliability |  | When designing systems with aspects of dormancy in their life cycle profile, it is vitally important that consideration be given to mitigating the opportunity for failure while in the nonoperating state. Devices that wait in a dormant state as backup items to operating devices must operate properly when called upon, or the designed-for system redundancy will be negated. Some components of space systems may also spend several years after assembly in a storage environment before being launched. The costs involved in obtaining, repairing, or replacing those items that were in storage and that were thought to be operable will be very extensive, and launch schedules could easily be impacted. | Use appropriate design considerations to enhance the reliability characteristics of a system or item when its intended use involves long periods of dormancy or nonoperation. | JSC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2207 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: The likelihood of successful system operation after long periods of dormancy can be increased by assessing the long term environmental effects on the characteristics of parts and materials, and mitigating the detrimental effects through appropriate parts selection and use of protective design options. Implementation Method: The approach involves detailed examination of the materials, parts, and manufacturing methods used in the design and construction of systems and appropriate consideration of the system's intended environmental factors. The steps involved include the following: Categorize the system or item into constituent components. Define the system or item life environments and consider the effects of environmental factors on the constituent components. Where possible, examine quantitative estimates of dormant failure rates for indications of potential problems. Use published guidelines and checklists for dormant system design considerations. Categorize the System/Item Into Constituent Components The item under consideration should be itemized by its constituent parts down to the "component," material, and electronic piece-part level, if possible. For the purposes of this guideline, a component is defined as a functional unit viewed as an entity for analysis, manufacturing, maintenance, or record keeping tasks. Materials, parts, and components used in the system may also be characterized into the following general types when in the nonoperating or dormant states: Components or parts with indefinite nonoperating lives which are subject to "random failure" mechanisms (Type A). Electronic parts and components are usually associated with this characteristic. Materials and components which degrade at a slow but relatively predictable rate over time (Type B). Many electromechanical and mechanical components, pyrotechnics, and organic materials can be considered to exhibit this characteristic. Materials and components which have known, relatively short, limited shelf lives (Type C). Items with this characteristic are generally well known: batteries, some solar panels, gas generators, etc. Type A Devices The principal failure mechanisms for electronic equipment and parts occurring during non-operative phases of the part's life are caused by latent manufacturing defects or deficiencies in materials rather than specific aging mechanisms. As a result of these latent manufacturing defects, environmental conditions and stresses act upon these defects until sufficient conditions exist for degradation failure to occur. One of the most effective ways to reduce these types of failures is to subject the component or assembly to programs such as environmental stress screening (ESS). Programs such as these should be capable of detecting failure mechanisms including defects in bulk material, metallization, final seals, wire bonding, glassivation, die bonding, oxide, and diffusion as well as general contamination problems. However, an ESS program should be carefully designed to restrict the environmental excursions and stress cycles so as to not induce incipient failures. Types B and C Devices and Materials In general, nonorganic materials such as metals deteriorate by electrochemical processes, and organic materials deteriorate by chemical reactions. Most organic materials used in spacecraft are long-chain polymeric compounds which degrade through the breakdown of the compound into smaller, more volatile fragments, making polymers the most likely to be affected by the vacuum of a hostile space environment. Therefore, organic materials exposed to a vacuum may decompose into volatile products in warmer areas, and redeposit onto relatively cooler surfaces. If the cooler surfaces are thermodynamically or electrically conductive by design, a malfunction is likely to occur. Of particular concern are failure modes that occur because of plasticizers redepositing onto exposed relay contacts preventing proper closing of the circuit. In the absence of oxygen, polymers are more stable at elevated temperatures. However, nylons, polysulfides, cellulosics, acrylics, polyesters, epoxies, and urethanes possess unstable properties in low-pressure or vacuum environments. The stability of the polymer in a vacuum is dependent upon formulation and curing procedures used during the manufacturing processes where plasticizers, mold lubricants, and polymerization catalysts are generally detrimental to long-term reliability. Therefore, the use of devices constructed with polymers that use these agents should be avoided. Nevertheless, exposure to vacuum conditions generally causes no loss of engineering properties in seals or gaskets unless an appreciable loss in mass occurs. Define the System or Item Life Environments and Consider the Effects of Environmental Factors on the Constituent Components The designer should identify and develop the environmental operating conditions and factors that will apply to each phase of the item's life cycle. For instance, if an item is to be stored in a warehouse for most of its life cycle, the environment it sees would be significantly different than a component on an orbiting satellite. The primary environmental factors encountered during storage or nonoperating phases of space systems are listed below. High Temperature Extremes Low Temperature Extremes Temperature Cycling Moisture Low Pressure (Vacuum) Atmospheric Pollutants Thermal Shock Nuclear Radiation Electromagnetic Fields Corrosion Solar Radiation/Atomic Oxygen Mechanical Shock/Vibration Mechanical Shock/Vibration Bacteria, Fungi Static Electrical Charges The relative stress levels experienced by individual components or assemblies during a dormant period are very greatly reduced from operating levels. Consequently, designs for dormant reliability must focus much more heavily on understanding the failure mechanisms which will be experienced in the dormant environments, the factors which cause each of the failure mechanisms to occur, and methods for controlling the occurrence of the failure mechanism. The most important environmental stresses produced by the environmental factors encountered in dormancy are mechanical, chemical, and low thermal (Reference 8). The mechanical stresses are primarily due to inertial forces (during transportation and handling) and thermal-mechanical interactions which introduce differential expansion between materials within a device and between subassemblies and interconnections. Diurnal- and/or orbital-induced temperature cycles should therefore be as small as possible. Chemical stresses are primarily influenced by contaminants such as halogen ions, residual process chemicals, and water (moisture). In fact, moisture within a device or assembly package is the most important factor for both corrosion and mechanically induced failures (Reference 8). There is a substantial number of design techniques and methods to mitigate the effects of these environmental factors found in sources such as References 7 and 8. Radiation particles, ultra-violet wavelength light exposure, and atomic oxygen are all detrimental to exposed polymeric materials. Solar flare emissions will probably affect exposed surfaces of the materials more sensitive to radiation damage. The results of the Long Duration Exposure Facility have recently been released and indications are that low Earth orbits cause significant wear and erosion to exposed materials. Kapton seems to be highly susceptible to atomic oxygen, and erosion of silverized Teflon is somewhat more than that predicted by ground-based tests. Examine Quantitative Estimates of Nonoperating Failure Rates of Items Considering the Appropriate Environments Examination of historical failure rates of similar items may provide indications of areas for concern. For electronic parts and other mechanical items classified as Type A items, several publications provide methods and historical data for estimating a failure rate in a dormant or nonoperating state. Reference 7 provides a compendium of models for estimating the failure rate for various types of components as a function of environment, part type and quality level, and ambient temperature similar to the methods used in MIL-HDBK-217. Values for base failure rates and modifying parameters were derived from numerous field data sources (which are primarily missile and aircraft system information), and are delineated in the document. Other documents (e.g., Reference 4) also provide estimates of the nonoperating or dormant rate of failure for components that have been derived from historical field and test data. The general characteristics of the failure properties of Types B and C items can usually be described as a period of fairly low rate of failure followed by an increasing propensity to fail as the item begins to degrade or wear out. Therefore, constant failure rates are not applicable to these items, and the designer should consider sources or methods for estimating the life limits or life parameters. Mathematical equations for calculating the individual component reliabilities over a prescribed mission time may also be used. In less complex systems, appropriate reliability block diagrams may be used to aggregate the component reliabilities and to derive the likelihood of the system being able to perform its function over a specified period of time. However, the inherent uncertainty involved in applying the observed nonoperating failure rates of older technology parts to more current components limits the ability to provide an accurate specification for system reliability over long time periods. Use Published Guidelines and Checklists for Dormant System Design Considerations The designer is urged to use published sources such as "Reliability/Maintainability/Testability Design for Dormancy," (Reference 8) that provide detailed design guidelines and checklists for reference when designing systems for storage or long periods of nonoperation. Table 1 lists some of the general points that should be considered from an overall system viewpoint. Table 1. General Dormant Reliability Checklist Yes No N/A Has a packaging, transportation, handling, and storage environmental analysis been completed? Has the dormant mean time between failure attained in service been used as a criterion for component selection? Have the major dormant/storage failure modes and effects been analyzed? Are adequate integrity checks identified for uncovering dormant/storage failures prior to flight? Can dormant/storage failures be readily detected and isolated? Will the equipment withstand any natural combination of the dormant/storage environments(e.g., shock vibration, acceleration, temperature cycles, humidity, and atomic oxygen.) in the intended application? Have the restrictions in employing dissimilar metals in intimate contact been considered? Have thermal stresses and differential thermal expansion been considered? Is aging a factor considered? Is the production process likely to degrade the dormant/storage reliability? Are provisions made to prevent the entrapment of moisture or other fluids? Do protective coatings meet requirements? Are limited-life items identified? Was corrosive degradation considered? Technical Rationale: When designing systems with aspects of dormancy in their life cycle profile, consideration must be given to degradation and failure while in the nonoperating state. Items can and will fail during periods of nonoperation. Dormant reliability is defined here as the probability (or likelihood) that an item or system will operate as intended after undergoing a long period of inactivity or nonoperation. Dormant systems may spend 90 percent or more of their life cycle profile in environments that may be detrimental to their survival. Environmental stresses, as well as aging effects, will precipitate failures just as do stresses during operating periods. References: AFWAL-TR-83-2079, "Weibull Analysis Handbook," Air Force Wright Aeronautical Laboratories, United States Air Force, Wright-Patterson AFB, November 1983 EERD-3, "Nonelectronic Parts Reliability Data," Rome Air Development Center, Reliability Analysis Center, 1986 MIL-STD-1540B (USAF), "Military Standard Test Requirements For Space Vehicles," October 10, 1982 NONOP-1, "Non Operating Reliability Databook," Rome Air Development Center, Reliability Analysis Center, 1987 NPRD-3, "Nonelectronic Parts Reliability Data," Rome Air Development Center, 1985 PRC-R-4416, "Analysis of In-Flight Spacecraft Performance and Anomaly Data," October 1984 RADC-TR-85-91, "Impact of Nonoperating Periods On Equipment Reliability," Rome Air Development Center, May 1985 RADC-TR-88-110 "Reliability/Maintainability/Testability Design For Dormancy," Rome Air Development Center, May 1988. SD-TR-86-02, "Analysis of Orbital Satellite Stage," Air Force Systems Command, November 1985. "Dormant Reliability Awareness Seminar," The BDM Corporation, May 1986 "RADC Reliability Engineer's Toolkit," Rome Air Development Center, July 1988 Fisher, Dr. William F., and Price, Charles R.: "Space Station Freedom External Maintenance Task Team Final Report," July 1990 "Reliability & MIL-HDBK-217 Prediction," Reliability Review, Volume 10 pp. 7-9, September 1990 Reliability Preferred Practice No. PD-EC-1101: Environmental Factors |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
695 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Guidelines for Thermal Analysis of Spacecraft Hardware |  | Not performing a detailed thermal analysis of a spacecraft or instrument can result in a thermal design of questionable reliability, or it may be so conservative that it utilizes excessive power and weight. The lack of a comprehensive thermal analytical model limits the capability for evaluating the thermal performance in test or orbit. | This guideline describes the general criteria and methodology for the development of thermal models for predicting temperatures of spacecraft, instruments and other spaceflight hardware. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GD-AP-2302 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Thermal analysis when used throughout the development cycle will (1) provide an optimum thermal design within the constraints of the overall system design, (2) provide temperature distributions and temperature histories to the level of detail required, (3) provide early identification of design problems, and (4) provide the basis for predicting and evaluating thermal performance in test and flight. Implementation Method: Detailed thermal analysis and design should be performed to ensure that the temperatures of all spaceflight components remain within their specified limits during the mission lifetime. To meet this objective, thermal modeling is required beginning at the project conceptual design stage and continuing through preliminary and detailed design stages and environmental testing. Test verified models are used to predict temperatures for the launch phase, and for mission operations. Design Phases During the conceptual design phase the temperature control system can be a major driver in defining the configuration, orientation and power requirements. Simplified calculations, rules of thumb, and experience with similar requirements are useful at this stage, but a computer model of the overall configuration and the location of major components provides the ability to compute component temperatures over the range of anticipated orbital environments and to be able to evaluate and respond quickly to proposed system trade-offs. In the preliminary and detailed design stages the computer models are expanded as more details of the overall system are firmed up. The models are used to support trade studies as needed and to develop and optimize the thermal control system design. Test Phase In preparation for thermal vacuum and thermal balance testing the computer models are modified to predict temperatures in the test environment and to provide the thermal analysis required to develop the test plan and to specify the test hardware. For thermal vacuum tests the models can be used to demonstrate that the test hardware can drive each component to the specified hot and cold temperature levels and to predict the transition times between hot and cold soak periods. The thermal balance tests are designed to verify the accuracy of the computer models and to demonstrate that the thermal control system functions as specified. Since it is often impractical to simulate the orbital environment, the models are used to develop equivalent environments that result in nearly the same temperatures in the test environment as are predicted for flight. If the test temperatures differ significantly from predictions for the test environment, the models are adjusted to try to match the test temperatures. These adjustme nts must have a plausible physical basis if the models are to be considered to be verified by test. Launch Phase For an Expendable Launch Vehicle (ELV) launch, the models are used to predict the payload temperatures from lift-off to orbit insertion. This may include transient heating from the nose fairing until fairing ejection and direct aerodynamic heating immediately followed ejection, solar and earth inputs, spin rate changes, deployment of booms and solar paddles, attitude changes for thruster firings, extended periods in the earth's shadow, etc. For an Space Transportation System (STS) launch, the payload models are placed in a model of the shuttle bay and run for a variety of cases, including (1) launch, (2) on orbit with the bay doors closed, (3) the open door configuration at selected attitudes, such as bay-to-earth, bay-to-sun, and bay-to-space, (4) payload on the remote manipulator system, (5) reentry, and (6) post landing with and without purge air. There are also safety related cases to be analyzed, such as a bay floodlight failed on and the vent door failed to open during reentry. Payload temperature grad ients at touchdown are needed for the analysis of landing loads. Flight Predictions The test verified computer models are used to predict temperatures in flight for use by ground stations for monitoring performance, for planning operations, for verification of the computer models using flight data, and for monitoring degradation of the thermal coatings. Special Purpose Models Reduced thermal models of instruments and other spaceflight hardware are often required by spacecraft thermal designers in order to limit the size of their all-up observatory computer model. The reduced models may be constrained to a small number of surfaces, nodes and couplings. Emphasis should be placed on the accuracy of the temperatures of critical components and the heat flow across the interface with the spacecraft. Thermal analysis of electronic boxes is performed to compute the temperatures and heat flows throughout the box from the mounting interface to the junction temperatures of semiconductors and other components as required. Special purpose computer programs have been developed to facilitate the modeling of circuit boards. STS thermal models, such as Orbiter Payload Thermal Integration Model (OPTIMOD), provide details for subdividing the shuttle bay into surfaces and nodes, adding external surfaces, such as the wings, tail, bay doors, and active thermal control radiators, adding internal structure as needed, and modeling the ascent, entry, and post-landing phases. Special purpose models are developed for providing added detail for a particular component or region of a larger model, such as computing temperature gradients and transient temperatures in thin films and windows. Others are developed for modeling the performance of thermal control louvers, heater pipes, capillary pumped systems, cryogenic instruments, passive radiative coolers, solid and liquid cryogen dewars, etc. Modeling Techniques The computer models are sets of finite difference equations which describe the heat transfer among small, isothermal elements or nodes which together represent the physical hardware. The number and location of these nodes are chosen based on accuracy requirements, convenience in working with complex shapes, and efficient use of engineering and computer time. For a spacecraft in earth orbit the equations are of the form: Heat Stored = Heat In - Heat Out The heat flow at each node is given by: [D] The result is a set of finite difference equations, one for each unknown temperature, with terms for the thermal mass, the heat absorbed on external surface nodes from sunlight, earth reflected sunlight (albedo), and earth emitted infrared radiation, the heat dissipated in electrical components, the heater power for thermal control, and conduction and radiation interchange between node pairs. Solutions are obtained using a general-purpose heat transfer computer program, such as Systems Improved Numerical Differencing Analyzer (SINDA). The bulk of the input data, which is the absorbed energy from the sun and the earth, and the radiation interchange factors are generated by programs such as Thermal Radiation Analyzer System (TRASYS) and Simplified Space Payload Thermal Analyzer (SSPTA). The steps involved in the development of a thermal model are shown in Figure 1. The initial step in the development of the geometric model. This is used in conjunction with the optical properties of the surfaces to generate radiative couplings between surface node pairs. Given the parameters defining the orbit and the orientation of the payload, the geometric model is also used to generate the absorbed solar, earth reflected solar and earth emitted infrared radiation on the external nodes. These data are then input into the heat transfer model for computing transient or steady-state temperatures . Any changes in the geometric model, the surface optical properties and the orbital parameters requires regeneration of the radiative couplings and the absorbed solar and earth radiation. [D] Figure 1. Thermal Model Development To ensure the accuracy of the models requires considerable care and skill, good engineering judgment and applicable experience. Care is required in checking the input data for errors and the caution and warning messages provided by the computer codes. It is very important to keep good records which show the sources of the input data and a log of the computer runs. Skill comes into play in knowing how to use the computer programs, in understanding the theory behind the calculations, and in being well versed in the pitfalls commonly experienced with each program. The experience and judgment comes into play in setting up the model, in checking the output for accuracy, and in interpreting the results. In using TRASYS or SSPTA, the geometric model should be plotted and checked for overlapping surfaces, for surface normals in the proper directions, for surfaces that are misplaced or mis-oriented, for unplanned gaps, for surfaces viewing the backsides of others, etc. The computation of radiative interchange factors, especially the radiative coupling to space should be checked for surfaces that have significant couplings to space but which do not view space. Where it is possible to do so, hand calculation or independent methods should be used to determine if the computed values are reasonably accurate. Similar checks should be made for calculations of absorbed sunlight. Steady state solutions should be checked to verify that the energy balance on each node is within required tolerances and that the heat flow to coupled nodes have reasonable values. Transient temperatures should be plotted to visually check: (1) if the temperature-time characteristics are as expected; (2) if any sudden or unusual variation has a physical explanation; and (3) that thermostats respond as required and that heaters are sized properly. Technical Rationale: The thermal design philosophy at Goddard Space Flight Center is that all temperature limits be met for worst case hot and cold combinations of possible orbital environments, spacecraft or instrument operating modes, and tolerances on all major thermal properties. These variations are stacked, that is each variable is combined in such a way that each contributes to the worst case condition to the extent that such combinations are possible within the mission requirements and constraints. For example, the worst case cold condition for a satellite in earth orbit would probably consist of the following: (1) the orbit oriented such that the percent time in sunlight is a minimum; (2) the spacecraft is oriented toward the sun in a direction that the absorbed sunlight is a minimum; (3) the internal power dissipation is at minimum predicted values; (4) minimum values are selected for the solar constant and the earth albedo factor and a value is selected for the equivalent black body temperature of the earth which is consistent with the assumed values of the solar constant and the albedo factor (see Reliability Preferred Practice Guideline No.GD-AP-2301); (5) minimum solar absorptances and maximum thermal emittances of the thermal coatings are selected; and (6) a value is assumed for the effective emittance or thermal conductance of the multilayer insulation blankets which contributes to the coldest condition. This philosophy is conservative to the extent that the worst case condition as defined above may be unlikely to occur. However, the experience with spacecraft and instruments that have been flown has been that many of the variables do occur in worst case combinations. Experience has also shown that temperatures in test and in flight often vary from predicted values, so that some conservatism is necessary to compensate for inaccuracies in the thermal models. References: quotSINDA/FLUINT, Systems Improved Numerical Differencing Analyzer and Fluid Integrator, Version 2.5, User's Manual,quot Martin Marietta, MCR-91-1393, December 1992. quotThermal Radiation Analyzer System (TRASYS),quot NASA JSC-22964, April 1988. quotOrbiter/Payload Thermal Integration Model (OPTIMOD),quot NASA JSC-22437, April 1987. NASA SP-8105, quotSpacecraft Thermal Control,quot May 1973. quotProgram Manual for the Simplified Space Payload Thermal Analyzer (Version 3.0/VAX,quot Arthur D. Little, Inc., ADL Reference C-89216, October 1986. Reliability Preferred Practice Number PD-ED-1204 Part Junction Temperature Reliability Preferred Practice Number PD-TE-1402 Thermal Cycling Reliability Preferred Practice Number PD-TE-1404 Thermal Test Levels Reliability Preferred Practice Number GD-AP-2301 Earth Orbit Environmental Heating |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
678 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Design Considerations for Selection of Thick-Film Microelectronic Circuits |  | Inadequate design and selecting non-established reliability components may impair the reliability of hybrid microcircuits. | This guideline provides information and guidance for the design of thick-film hybrid circuits. | JSC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2202 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: This guideline identifies design considerations and reliability requirements to assure reliable performance and to avoid cost overruns due to redesign and operational failures. Implementation Method: Component information. The design of thick-film microelectronic circuits requires information on specifying components with established reliability. The components used in thick-film microelectronic circuits are somewhat different from the sealed or encapsulated, fully tested discrete components used to fabricate circuits on printed wiring boards. The components fall into the categories of (a) thick-film resistors, (b) thin-film resistors, (c) ceramic capacitors, (d) semiconductors, and (e) thick-film conductors. Circuit partitioning. Several factors should be considered when partitioning the system into individual microelectronic circuits. Each of the circuits should be a separate and complete function which can be tested with the addition of a minimum number of external components, and should have the minimum number of input-output pins. If a system consists of two signal paths which must track, the partitioning should be done such that the corresponding circuits of each channel are in one thick-film microelectronic circuit. This will ensure that the circuit elements of both channels will be at the same temperature and therefore increase the tracking accuracy. Packages available. There are several package types that are currently available in industry. The packages that are used for space flight application shall meet MIL-H-38534 requirements. Power dissipation. The junction temperature is a function of the case temperature and the power dissipation within the package. The case temperature is a function of the internal power dissipation of the microelectronic circuit, the printed wiring board loading, the thermal impedances from the package case to the outside world, and the operating ambient temperature of the chassis. Thermal impedance of packages, substrates, and semiconductors all affect the thermal gradient from the junction to the outside world. Therefore, the choice of package and the distribution of power within the package will affect the maximum allowable power of the circuit with either a fixed maximum case or ambient temperature. Worst case analysis. A worst case analysis ensures that the circuit will function over the maximum operating temperature with the worst possible combination of component variables. The worst case analysis shall be performed in accordance with the applicable program requirements. The worst case analyses shall include the individual components. Before an actual worst case analysis is started, the following preliminary considerations must be made: Physical limitations. There are three factors to consider: (1) the number of required pin-outs must be available in the desired type of package and a key pin should be included in the pin count; (2) the number of components in the circuit shall not exceed the number of components specified as the maximum number that can go into that particular type of package, and (3) the use of non-established reliability components in the circuit design should be avoided. Power dissipation within the circuit. The worst case power dissipation within the circuit must be calculated. External factors. External factors affecting circuit performance must be identified before starting the worst case analysis; e.g., (1) the power supply tolerance should be known, (2) the worst case loading of the circuitís outputs must be considered, and (3) the decoupling requirements must be considered. Testing. Most hybrid microelectronic devices are custom made for their particular applications. However, the part operation should be precisely defined by electrical characteristics which include all necessary parameters with test conditions, parameter minima and maxima, and parameter typical values. All active and passive elements of the hybrid should have electrical characteristics derated according to the appropriate derating factors listed in MIL-STD-975 for NASA standard parts. Derating will increase the safety margin between the operating stress level and the actual failure level for the constituent hybrid parts and will provide added protection for system anomalies unforeseen by the application engineer. Dynamic trimming. The thick-film microelectronic circuits are dynamically trimmed using automatic laser trim system. Power supply settings, input conditions, and output requirements must be defined prior to dynamic trimming. All resistors involved in a trim must be referenced, along with the output reaction to the trimming of each resistor. Radiation Hardness Testing. The components used in the thick-film hybrids are required to undergo radiation hardness testing when radiation tolerances are specified in the detail specification, which may include dose rate and latchup, total dose, and neutron irradiation as applicable. Circuit quality level. The hybrid microelectronic circuits shall be screened to meet the requirements of MIL-STD-883, Class S or B depending on the program requirements. As a minimum, the following screening steps are essential in accordance with MIL-STD-883 applicable test methods, to ensure the quality and reliability. They are, (a) Die Visual Inspection, (b) Substrate Visual Inspection, (c) Element Evaluation, (d) Package Evaluation, and (e) Quality Conformance Evaluation including groups A, B, C, D, and E testings of MIL-STD-883 specifications. Technical Rationale: This document and JSC contractor paper, JSC 25471, provide the information and guidance to circuit designers for specifying devices which will be developed and produced as thick-film hybrid circuits. In order to ensure a reliable circuit at the lowest cost, there are several areas that require special consideration when designing a thick-film hybrid circuit. Use of these two documents should allow the engineer to spend less time researching standards and more time designing reliable microcircuits. References: JSC 25471, Electrical Design Considerations for Thick-film Microcircuits MIL-M-38510 Microcircuits, General Specifications for MIL-H-38534 Hybrid Microcircuits, General Specifications for MIL-STD-975 NASA Standards Parts List MIL-HDBK-978 NASA Parts Applications Hand Book MIL-STD-1772 Certification Requirements for Hybrid Microcircuit Facilities and Lines MIL-STD-883 Test Methods and Procedures for Microelectronics |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
677 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | High Voltage Power Supply Design and Manufacturing Practices |  | Impact of Nonpractice: Allowing High Voltage power supplies that have not been thoroughly tested for corona to operate in space has resulted in corona-caused shorts that disabled the power supply. | Practice: Thoroughly test high voltage power supply packaging on flight configured engineering models, in a simulated space flight environment, to evaluate corona effects. | GRC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1202; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Process controls on design, manufacturing, and testing operations reduce component failure rates and improve reliability. The goal is production of power supplies that will operate in space for the mission duration. Implementation Method: There are special requirements in packaging HV power supplies for space use. The power processor should be voltage-partitioned and the low voltage circuits should be separated from the high voltage circuits. This is usually done with a metal wall. There still will be signals transmitted between the sections. All grounds should be isolated to provide a means to predict the currents when transients or arcs occur. When capacitors discharge, there can be current flows of several hundred amperes. The low voltage section should be protected from these current and voltage surges. Table 1 shows recommended design practices used for an 11 kV CTS TWT power supply. All volumes must be vented. The pressure in any unvented volume will decrease gradually and result in corona or arcing. Allow for screens, RF traps, etc.; and count only the holes in the screens. Interior volumes, down to the capped nut plates, must also be vented. Table 1. High Voltage Power Supply Design Guidelines PHYSICAL LAYOUT Voltage Partitioning (Separate high and low voltage components) Isolated Grounds (Provide known current path for transients) Voltage Suppression (Suppress signal from high voltage to low voltage circuits) ELECTRIC FIELDS Solid Dielectric: DC Stress 50 Volts/MIL AC Stress 10 Volts/MIL Surface Creepage 8 Volts/MIL Air or Vacuum Gap 20 Volts/MIL VENTING >2 cm2 per 1000cc of enclosed volume (screens and RF traps reduce vent size), including: Capped nut plates Dielectric spacers Polyolefin shrinkable tubing High voltage connectors Figure 1 shows the fabrication methods used to build this supply. Round off all edges on metal as well as dielectric materials. Use anti-corona spheres. Void-free encapsulation is important. Remove excess RTV from bolts to keep vent paths open. Use shrink tubing in strips for hold downs, to avoid trapped air. Dielectric separators must be sized correctly for surface creepage. Anti-corona spheres should have a vent hole to eliminate voids in the solder. Dielectric inserts should be slotted to vent the interior volume. [D] Figure 2 illustrates the special construction methods used in the HV compartment for the equipment to operate in the thermal and vacuum environment of space. Table 2 shows the testing methods that should be used to check out the HV power supply. The glass epoxy boards should be scanned ultrasonically to check for density differences. The transformers and components mounted on the boards should be corona-tested. Corona discharges of less than 5 picocoulombs are allowed. Induced voltage in the dielectric testing should be done in vacuum at temperature per MIL-T-27. The corona tests should be repeated to detect internal degradation from the high voltage stress. Be careful to bake out the components at 65 degrees C for 72 hours in the vacuum chamber and cool the components down before the power supply is turned on. [D] Table 2. Testing Corona testing: Transformers Component Configuration on Boards <5 Picocoulombs Electric Testing: Induced voltage (twice-rated voltage) Dielectric withstanding (2.5 times rated AC and DC) Important to perform in vacuum at temperature Thermal Testing: Minimum of 10 temperature cycles at component level Minimum of 3 temperature cycles at box level Initial thermal-vacuum test preceded by bakeout of 65°C for 72 hours Ultrasonic Scanning of Glass Epoxy Boards (NASA TM X-73432) Technical Rationale: These design criteria were developed experimentally. The various component configurations, board layouts, and component assemblies were tested to 125% of expected working voltage in air, vacuum, and full operating temperature with a requirement that the corona inception measured less than 5 picocoulombs. An example of an early flight failure caused by corona was a short that developed between two pins of a high voltage connector. Gas trapped inside connector voids gradually decreased in pressure until corona discharge began to decompose the insulating material. When the insulating material thickness was reduced to the point that leakage started increasing, a carbon tree formed and a short occurred, disabling the experiment. This can be easily avoided by running corona tests on all high voltage parts to ensure that no gases are trapped in high voltage circuits. References: MIL-T-27, quotTransformers and Inductors (Audio, Power and High-Power Pulse), General Specification for,quot August 8, 1987. NASA CP 2159, quotSpacecraft Transmitter Reliability,quot September 1979. NASA TMX-3287, Lalli, Vincent R., Nueller, Larry A., and Koutnik, Ernest A., quotSystem Reliability Analysis Through Corona Testing,quot September 1975. Presented at Power Electronics Specialist Conference (sponsored by IEEE), Culver City, CA (June 9-11, 1975). NASA TMX-73432, Klima, S. J. and P. J. Riley, quotUltrasonic Evaluation of High Voltage Circuit Boards,quot June 1976. NAS3-17782, Cronin, D. L., quotModeling and Analysis of Power Circuits,quot TRW Systems Group, June 1975. NAVMAT P4855-1, quotNavy Power Supply Reliability Design and Manufacturing Guidelines,quot December 1982. Foster, W.M., quotThermal Test Report for the Space Acceleration Measurement System Circuit Boardsquot, NASA Lewis Code 6730 Internal Report, November 1987. | This practice has been used on Space Electronic Rocket (SERT) Tests I and II, Communication Technology Satellite (CTS), 30 cm Thruster Bi-module. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
680 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Design Checklists for Microcircuits |  | In many situations, new circuit designs may not adequately incorporate all the relevant past history from a wide data base of previous experience, and hence will not achieve the best possible performance and reliability. | This guideline provides checklists taken from Government-Industry Data Exchange Program (GIDEP) files to be used as a measure to avoid commonly experienced problems in transistor-to-transistor logic (TTL), complementary-metal-oxide-semiconductor (CMOS), and memory circuit design applications. | JSC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2203 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Use of this guideline will ensure continued improvement with the use of microcircuits in circuit designs by incorporating data from previously experienced problems into a design checklist. This will apply the experience base from the past and thus provide improved reliability for future space programs. Technical Rationale: Information gathered from a history base of known problem areas is presented in easy-to-use checklist form to be used by designers, etc. The checklists are separated into three categories, based on device technology (TTL, CMOS and memory). The guideline can then be used as a reference to avoid incorrect utilization of these component types in circuit design applications which may result in potentially poor reliability. TTL DESIGN CHECKLIST 1 Only gates from the same package should be connected in parallel. 2 Take note not to exceed fan-out limit (maximum number of circuits fed input signals from a single output terminal). 3 Check pin compatibility when using devices from different families or manufacturers. 4 Check manufacturer interchangeability for minor functional differences. 5 Maintain equal loading in ac and dc terms on multiple output devices with internal feedback. 6 The dynamic threshold of low-power schottky (LS) gates varies between 1.1 V and 1.4 V depending on circuit configuration; therefore, slow rise times (greater than 50 nanoseconds) will possibly cause pattern sensitivity. 7 Gates with outputs driving transmission lines should be situated close to the board periphery. 8 Consider full-range temperature effects on switching characteristics relative to design application. 9 Use pull-up resistors on devices with open collector gates. 10 Consider the frequency dependency of power dissipation when the operating frequency is greater than 1 to 2 MHz. 11 If decoded outputs from counters, particularly from ripple counters, are being used as clocks to drive counters or memory devices, the decoded outputs of interest should be examined for multiple pulses at counter transitions that might ambiguously operate the driven counters or memory devices, and corrective measures should be taken to non-ambiguously operate the driven circuits. 12 Take note that low-power, low-power Schottky, and Schottky TTL circuits are known to fail when exposed to 5 microjoules or more of electrostatic discharge (ESD) energy. 13 Consider "current dumping" effects when a multiple input gate is terminated to a single high impedance source such as a 150-ohm line. 14 All unused input pins should be tied to high- or low-logic levels, depending on the circuit application. When devices approaching their maximum speed for TTL are used, unused inputs should be "commoned" to used inputs rather than tied high; whereas for low-power Schottky devices with diode inputs, the unused ones can be directly connected to VCC. 15 Provide isolation for test points so that any foreseeable occurrence, such as shorting between, grounding or external excitation at the test points will not disrupt operational use of the circuit being monitored by the test points. 16 Consider potential problems involving the use of multiple flip-flops controlled by one or more asynchronous output. 17 Check interfacing parameters (fan-out, loading, and threshold) when using devices from different families. CMOS DESIGN CHECKLIST 1 Allow for hold-time and setup-time requirements of CMOS flip-flops, registers, and latches. Inputs to CMOS devices must be stable before and remain stable even after the active clock pulse edge. 2 Take adequate precautions to avoid ESD damage. 3 Account for possible incompatibilities with similar part numbers from different manufacturers when establishing parts lists. 4 Investigate the package choice/reliability tradeoff for each design application. 5 When using single-stage (unbuffered) multiple-input CMOS devices, consider that both dynamic and static performance of these circuits can deteriorate under certain logic conditions to the extent that logic systems display pattern sensitivity. 6 Protect signal inputs against overvoltage spikes and input currents exceeding ratings, i.e. many CMOS devices have ten milliamperes as the maximum allowable input current. Consider that if the overvoltage spike is greater than the supply voltage, the parasitic PNP or NPN transistors become forward biased and latch-up can occur. 7 Excessive current through switches results in latching and destructive breakdown; therefore, protective circuitry is essential. 8 Consider the noise margin when using 5-volt supply levels. CMOS has an order of magnitude less energy noise margin than TTL (approximately 0.4 nanojoules for CMOS and 4.0 nanojoules for standard TTL). 9 The power supply should switch on by itself first before signal inputs are applied, since damage may occur if the diode between input and VDD is forward biased. 10 Slowly rising or falling input signals can lead to multiple triggering, particularly if the supply voltage is poorly regulated, and also to higher supply (IDD) currents. 11 Maximum power dissipation of the device could be exceeded if input rise and fall times are greater than 15 microseconds, (depending on device type) especially using high current drivers with high supply voltages. 12 Terminate all unused inputs; a floating input can turn a CMOS device on, causing faulty operation and possible damage, and also uses increased power since both p- and n-transistors are partially conducting. 13 Ensure that interfacing parameters between CMOS and other logic families are correct, particularly with regard to loading and thresholds. 14 Keep interconnections short or use terminations, as long interconnections in high speed systems behave like transmission lines, which can cause reflections and ringing. 15 Do not use CMOS gates as linear amplifiers; this can destroy buffer gates, cause failure of the device to operate below 4 volts, and make supplier interchangeability even more problematical. 16 Avoid long, closely spaced, parallel traces on PCB's to minimize crosstalk. 17 Flip-flops with transmission gate inputs are particularly prone to malfunction if the inputs are driven above and below the supply voltages. This can occur when interfacing from other logic families and from distant boards. 18 Try not to design to typical values because of the large part-to-part process variations. In many cases guaranteed values are several orders of magnitude larger than typical values. 19 Reduce ground/power supply inductance (power/ground planes) and use sufficient decoupling capacitors, as simultaneous switching of multiple outputs causes noise and voltage drops on power supplies. MEMORY DESIGN CHECKLIST 1 Avoid using parts at their maximum supply voltage tolerance and/or at their maximum speed. In a large memory system, noise, loading, and skew problems result in reduced apparent working area and reduced effective speed. 2 Consider carefully the difficulty in "second sourcing" with memory components, since they are far more complex than standard medium scale integration components (MSI); and very few, if any, have identical replacements. 3 Avoid mixing several technologies within the same memory system. If this is done great care must be taken to ensure that at no time are the pins of any memory component pulled beyond the component's substrate voltage. 4 When read-only memories (ROM's) are used to replace wired logic gates, the outputs may show noise or extra transitions, since the ROM is not guaranteed to give a single output transition for a single input transition. 5 In the use of nichrome fused bipolar programmable read-only memories (PROM's) there has been evidence of fuses growing back after programming and of unblown fuses being subject to decay. Ensure that special freezeout tests and high voltage stressing have been carried out, and also consider the greatly delayed production cycles involved. 6 Take note when using PROM's that the programming operation on devices from the same family are not necessarily compatible. Examples are the 1602 and 1702 devices in which the programming operation forces "ones" to "zeros," and the 1602A and 1702A devices which force "zeros" to "ones." 7 Caution must be taken when using common bus lines not to allow more than one device to be enabled at a time. System noise and incorrect data problems could result, and depending on output drive capability, physical damage to the device could occur. 8 In order to minimize transmission line problems, the driver elements should be located as closely as possible to the memory elements, keeping the connecting printed circuit lines as short as possible. 9 Asynchronous input signals applied to a ROM should be permitted to change within an access time sufficient to meet setup and hold times, prior to clocking the output register. If this does not occur the contents of the output register may be completely unpredictable. 10 Periodically check PROM programming electrical specifications, since manufacturers often change their recommended programming method to improve programming yields. 11 Ensure the correct programming conditions (voltage, duration, etc.) when programming PROM's. 12 Ensure that shift register drivers have sufficient dumping capabilities, otherwise positive or negative spikes may be coupled from one clock to the opposite phase. Spikes may reach over the substrate voltage and activate parasitic substrated transistors and destroy data. 13 Memory products usually dissipate power at significantly higher levels per package than most large-scale integration (LSI) and MSI components. It is therefore very important that adequate cooling arrangements be made, because the power dissipation per unit area can approach an order of magnitude greater than ordinary TTL. 14 Allow in the design for the ROM/PROM access time differences from various parts of the array. Differences of four to one have been found for various address locations. 15 Take caution when using dynamic MOS shift registers (SR's) as low-speed power-saving circuits, since data can be lost if the SR clock speed is reduced instantaneously. The lower frequency limit applies only at high ambient temperatures and not at self-heated high-junction temperatures produced at high clock frequencies. 16 Take note that when using floating gate metal oxide semiconductor (MOS) PROM's, bit loss occurs under x-ray and nuclear radiation. In addition, problems of inadequate erasure due to poorly calibrated ultraviolet sources can arise. 17 Take caution when using MOS electrically alterable PROM's, since data loss can occur from cells subjected to greater than 109 accesses. Given an access time of 1 microsecond, the data could be lost within an hour if continuous reads are made from one location. 18 Power supply slew characteristics should be evaluated carefully. Two separate problems have been noted. One problem is that at switch-on, a slowly rising power supply may not initialize the random access memory (RAM) logic correctly so that a subsequent initializing procedure is required. Another problem is that sharp, small supply voltage changes that occur in normal memory system operation can cause data loss in some supplier dynamic memory products. 19 Operating temperatures have to be considered very carefully. Because of their complexity, memory components tend to be more sensitive to temperature extremes than other types of devices. 20 Consider that large MOS memory systems often require error correction and detection (the inclusion of "Hamming" error correction codes in the design). This approach improves the effective system reliability by two orders of magnitude, and the associated error indicators simplify scheduled maintenance. 21 Consider access time measurement criteria carefully. While some manufacturers measure access times to the VOL and VOH voltage levels, others measure access to the 1.5 voltage level for both high- and low-level outputs. Additionally, some suppliers specify two output loads in their dc characteristics, but measure access time against one output load. 22 Many dynamic RAM's require a substrate bias supply (VBB) to ensure correct operation. Unless this bias supply is raised before the main supply and dropped after the main supply, high currents may be drawn. Also, if the bias supply is reversed even in a transient mode, the parasitic substrate transistor will draw extremely high currents. Since the internal capacitances of the RAM are terminated to the substrate, very good transient bypassing is required. 23 Take care when using bipolar memory devices (e.g., many ROM/PROM devices) with PNP transistor low-power Schottky style inputs. It is important that the inputs not be pulled below ground until the PNP device is saturated; otherwise, very long access times will be observed. 24 Allow for input/output coupling features of static RAM's in the system design. Although possibly not shown on the write-cycle data published by the manufacturers, the input data may appear on the output during the write mode. References: MIL-M-38510 Microcircuits, General Specification for MIL-STD-975 NASA Standard Parts List MIL-STD-978 NASA Parts Applications Handbook MIL-STD-1547 Electronic Parts, Materials and Processes for Space and Launch Vehicles MIL-STD-1562 Lists of Standard Microcircuits |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
679 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Meteoroids & Space Debris |  | Impact of Nonpractice: As an example of noncompliance, consider a spacecraft bus, containing critical electronic parts, whose shear plate and thermal blanket are adjacent (i.e., not separated by the standoff which characterizes a suitable two-surface particle shield). The largest incident particle, namely that for which the area-fluence product is near unity (ref. Table 1) is then, for long-duration missions in low Earth orbit or in the inner solar system, capable of penetrating the electronics housing or of producing spallation from the inner surface. In either case a single impact introduces numerous fast-moving fragments into the electronics themselves, several electronic parts will be disabled simultaneously, and the probability is high that the subsystem's function will be severely compromised, resulting in mission failure if the subsystem is critical. Even if redundant assemblies are provided, they should not be packaged together, because one particle impact may destroy them both. Even if packaged separately, the likelihood of two impacts (of a penetrating particle) is only modestly smaller than that of one impact, so that redundancy is a far more expensive and less effective option than the provision of suitable particle impact shielding in the first place. An equally serious failure resulting from noncompliance is illustrated by the scenario, extensively investigated for the Galileo spacecraft, that a meteoroid penetration of the propellant tanks could result in loss of fuel, a consequent change in the spacecraft velocity vector, unintended reentry into the Earth's atmosphere (instead of the intended close flyby for gravitational assist), and widespread atmospheric dispersion of radioactive fuel from the RTGs (radioisotope thermoelectric generators). In this scenario, failure to provide adequate meteoroid protection could have both life-threatening and major legal consequences, albeit with small probability. An exceptionally thorough analysis, in which the velocity distributions and the time dependence of the meteoroid flux were used in addition to the appropriate analogs of the above equations, was needed to quantify this small probability. | Practice: Design spacecraft external surfaces to ensure 95 percent probability of no mission-critical failures from particle impact. | JSC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-EC-1102; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Reliability is greatly enhanced because the likelihood of serious mission degradation or spacecraft loss is significantly reduced. Implementation Method: Prepare design requirements which specify mean velocity, mass density, and mass distribution for the impacting particles in terms of the integral fluence. This fluence (sample units m-2) represents the expected number of impacting particles per unit area, above several different mass thresholds for the mission (using the worst case trajectory if more than one is contemplated). The design must then satisfy two separate requirements: (1) that the smallest penetrating particle have a probability of impact below 5%, using the product of fluence with vulnerable area and a Poisson distribution, and (2) that for smaller particles, of which many will impact any given spacecraft surface, the resulting degradation of surface properties (e.g., optical, thermal, dielectric) does not exceed allowable ranges for surface performance (considering, e.g., pitting, spallation, contamination, etc.). In practice, the first of these refers to a sum of probabilities over a variety of vulnerable spacecraft surfaces (each having specific values for area and threshold penetrating mass), allocated so as to make effective use of resources (e.g., shielding mass) and to achieve the desired probability for mission success. For this purpose, experience dictates that a two-surface configuration, of which the outer surface serves as the thermal blanket as well, provides the least massive meteoroid protection. Technical Rationale: For a given mission (specified in terms of geocentric and heliocentric positions as functions of time, for example), the environments comprising impacting solid particles are both independent of mission control and rather uncertain. The flux and fluence of such particles can be evaluated from suitable numerical models (here for space debris and for interplanetary meteoroids, although others may occur, e.g., for Saturn ring particles). The integral fluence typically decreases as mass increases according to a power law, illustrated here using the exponent a: [D] (1) Here F and F1 represent the integral fluences (sample units m-2) for particles with masses greater than m and m1 respectively, accumulated over the mission. Table 1 provides examples of such distributions (where the exponent is not necessarily constant over the range of masses of interest) and additionally specifies mean density and impact velocity. For large particles, the distributions represented by equation (1) or Table 1 imply that the exposed surface area As of a spacecraft subsystem has a probability [D] (2) that no particle larger than the mass ms (corresponding to the fluence F) will hit, where equation (2) is obtained assuming Poisson statistics for the particle impacts. If the surface is designed so that no particle of mass ms or larger, impacting at the mean velocity, can penetrate or lead to other component failure (e.g., by spallation), then the probability of no failure is also Ps (assuming that penetration leads to component failure with unit probability). When Ps is small for each subsystem (as is the case when the area-fluence product in eq. 2 is much less than unity), the sum [D] (3) represents the probability of failure (Pt) of the system, where ps is the conditional probability that the system fails when subsystem s fails. If the values of ps are not independent then equation (3) must be replaced by the appropriate combination of probabilities. Finally, the probability of mission success, considering particle impact alone, becomes (1-Pt), and design must proceed to ensure that this quantity exceeds the 95% probability cited above. To protect a subsystem against those large particles for which equation (2) applies, and for impact velocities larger than a few km/s, hypervelocity impact experiments show that a two-surface configuration (often named a bumper shield) prevents penetration far more effectively than a single surface of the same mass. This is so because the kinetic energy of impact leads to the vaporization (or liquefaction or disintegration) of the projectile when it hits the outer target surface; the momentum is thereby dispersed over a large area as the vapor expands in the space between the surfaces, and becomes less capable of rupturing the second surface than had the latter been hit directly. Typically a thickness of a few tenths of a millimeter, and a standoff distance of a few centimeters, suffice to prevent penetration of a spacecraft structural wall by a milligram particle arriving normally at 15 km/s. For a sample configuration, Figure 1 displays the threshold penetration mass as a function of impact velocity. Such a figure can be used to verify by analysis that the design does not fail for the mass necessary for equations (1) through (3) to provide the required probability; and a parametric set of such figures spanning a suitable design space can be used to select the design appropriate for a given spacecraft assembly. In this design process, the uncertainties in penetration threshold and the variability thereof with angle of incidence (Fig. 1 and related data are commonly presented for normal impact, oblique impacts being less well characterized) must be considered, possibly by application of margin to some measure of shield effectiveness (the use of Poisson statistics for probability of impact is intended to cover only environment uncertainties, not shielding ones). In many cases, thermal blankets of a single design and standoff will serve as an appropriate bumper shield for much of the spacecraft body. Analytic formulations for hypervelocity penetration, and for bumper spacing and other parameters, should be selected carefully for relevance to the specific impact regime (e.g., projectile speed, direction, density, etc.). The resulting design should be verified by testing whenever possible, and the tests should span or simulate the range of expected projectile sizes and velocities. For much smaller particles, the power-law distribution (eq. 1) ensures that the area-fluence product exceeds unity for most exposed spacecraft surfaces, and that numerous small particles will strike the surface. For surfaces which are shielded as described above, these smaller particles are of no consequence, except as they alter the thermal properties of the surface; the thermal control design must provide enough latitude that these changes do not lead to internal temperatures beyond the acceptable range for flight. For other surfaces, concern arises only if a few critical surface properties must be maintained; for example, structural integrity and magnetic cleanliness are not threatened by these small impacts. Among such critical properties, optical quality is often the most serious, as in lenses or mirrors whose performance can be degraded by pitting, erosion, or contamination. For such components, ad hoc solutions to the particle impact problem, possibly involving articulating covers, may be necessary if analysis demonstrates that the particle fluence represents a significant hazard to unprotected surfaces. Typically, if a specific fluence value is required for design purposes in these cases, a margin of a factor 2 is applied to the nominal values (e.g., Table 1) to account for the uncertainty in the environment of these smaller particles. Table 1. Integral fluence of cometary meteoroids as a function of particle mass for three subsets of the Galileo mission (columns two and three include interplanetary meteoroids near Jupiter, as focused by Jupiter's gravitational field). Particle Mass-M (grams) Integral Fluence(1) Received during Transit* (Particles-m-2 of mass greater than M) Integral Fluence(2) Received during Orbit** (Particles-m-2 of mass greater than M) Mission Integral Fluence(3) (Particles-m-2 of mass greater than M) 10-12 10-10 10-8 10-6 10-5 10-4 10-3 10-2 10-1 10-0 1.06 x 104 4.27 x 103 5.37 x 102 21.2 1.33 8.15 x 10-2 4.99 x 10-3 3.06 x 10-4 1.87 x 10-5 1.15 x 10-6 7.89 x 103 3.17 x 103 3.99 x 102 15.7 9.6 x 10-1 5.9 x 10-2 3.6 x 10-3 2.2 x 10-4 1.36 x 10-5 8.3 x 10-7 1.85 x 104 7.44 x 103 9.36 x 102 36.9 2.29 1.41 x 10-1 8.59 x 10-3 5.26 x 10-4 3.23 x 10-5 1.98 x 10-6 Mean relative speed (km/s) 15.9 15.9 15.9 Particle mass density (g/cm3) (cometary origin) 0.5 0.5 0.5 *Tabulated values envelope the Galileo transfer trajectories including VEEGA, delta VEGA 2 , delta VEGA 3 , and direct. ** Fluence resulting from JOI and the first 5 orbits of the Galileo 79-1 Tour, includes gravitational focusing from Jupiter. (1) 95% confidence environment - 2.0 x fluence spectra (2) 95% confidence environment - 5.6 x fluence spectra (3) 95% confidence environment - 4.4 x fluence spectra Figure 1. Meteoroid critical mass as a function of impact speed for the Cassini propellant tanks, including a bumper shield and fluid within the tanks. The lines are for different densities of the impacting meteoroid, with and without fluid in the tanks, and the power-law segments represent different regimes of failure. (Click image for a larger view) [D] | This practice has been used on Voyager | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
686 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Selection of Compatible Materials for use with Fluorine |  | Failure to use the design data presented in this guideline will result in unsafe systems and failures which are costly and potentially injurious to personnel and environment. | Use established design guidelines for selection of materials that provide safe operation when exposed to elemental fluorine and fluorine-oxygen (FLOX) mixtures. | GRC | 02/01/1999 | This Lesson Learned is based on Reliability Guideline Number GD-ED-2206 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The design data provides a list of materials and conditions which are compatible for use with fluorine. The use of this data by design engineers will result in the selection of materials for use with fluorine that can provide safe and reliable system operation. Implementation Method: Generally failures in systems using fluorine are caused by: (1) improper choice of materials and/or system components; (2) improper fabrication and assembly practices, (ref 1); and (3) improper system preparation and operating procedures, resulting in the presence of contaminants. This guideline applies design considerations to preclude failures caused by improper choice of materials. Design guidelines to address failure causes (2) and (3) are beyond the scope of this document (see Reference 1). The design considerations to be used in selection of materials for use in fluorine systems should consist of: Selection of materials based on property requirements for the application (e.g., strength, thermal properties, welding or brazing characteristics, etc). [Note: This design consideration represents standard design approach and is presented here for completeness only] Selection of materials that can be fabricated without introducing contaminants and/or entrapped voids. Consideration of effects peculiar to a fluorine environment (e.g., ignition temperature of material in fluorine, fluoride films and exposure to friction, moisture presence and compatibility with hydrogen fluoride, etc). The design considerations of (b) and (c) above are based on extensive test experience from liquid fluorine rocket testing conducted at LeRC, and from materials tests conducted at LeRC and other laboratories. References 1, 2, and 3 present material compatibility with liquid fluorine for metallic and nonmetallic materials, respectively. Table 1 below, extracted from reference 1 and presented here for purposes of illustration, lists the ignition temperatures and ignition delays for metals in fluorine. Table 1. Ignition Temperatures of Metals in Fluorine (a) Technique A Metal Wire diameter, in. Ignition temperature, °C Average ignition temperature, °C Max variation from average, percent Aluminum 0.010 0.016 ---- (a) --- Copper 0.0123 645 to 747 692 8.0 Iron 0.014 667 to 677 672 0.8 Molybdenum 0.0149 188 to 220 205 8.3 Monel 0.010 348 to 437 396 12.0 Nickel 0.008 0.0155 0.0154 0.0152 1168 1096 1219 1084 1162 6.0 Stainless Steel 302 0.020 570 to 796 681 13.0 Tungsten 0.0153 260 to 332 283 18.0 Table 1. Ignition Temperatures of Metals in Fluorine-Concluded (a) Technique B Metal Wire diameter, (in) Max wire temperature °C Ignition delay, sec Ignition temp range °C Activation energy, kcal/mole Copper 0.012 905 852 810 767 701 689 0.8 1.0 0.6 0.8 1.2 No ignition 689 to 701 39.5 Iron 0.014 730 676 648 644 618 1.0 1.6 2.0 2.2 No ignition 618 to 644 16.3 Nickel 0.015 1357 1306 1266 1253 0.6 1.2 0.6 No ignition 1253 to 1266 --- The data for Table 1 was obtained from tests using two techniques, techniques A and B. In technique A, an evacuated bomb was filled with gaseous fluorine at atmospheric pressure and the fluorine was increased in temperature by a heated wire. The temperature at which the wire burned is listed in the part of Table 1 for technique A. In technique B, the evacuated bomb was brought to temperature before fluorine introduction. The time required for the reaction to go to completion, the ignition delay, is listed in the part of Table 1 for technique B. In addition, Table 2 was produced from Reference 1 which shows an expanded list of materials and their reactive effects with fluorine. Reference 1 also includes the effects of the presence of water and corrosion, the effects of fluoride films and their characteristics, and specific reaction of fluorine spills. Table 2. Compatibility of Materials in Fluorine Aluminum and aluminum alloys An aluminum trifluorine (AlF3) film is formed on the surface of the surface of the metal or alloy. The melting point of aluminum is below its ignition point with fluorine gas. Iron, iron alloys, steels Ferrous and ferric films are formed at a higher rate and depth than other mild resistant metals. Reaction from moisture and hydrogen fluoride is also greater. Stainless steels Resistant to attack by hydrogen fluoride is greater than most mild steels. A fluoride film is formed with characteristics equivalent to Monel. The film becomes less stable at elevated temperature. Stainless steel welds behave similarly as the parent material. Nickel (A, D, and L), Nickel bearing alloys, & Monel Fluoride films are similar to that on aluminum, but are stable for use at high temperature (1200°F). Welding does not reduce the corrosion resistance of nickel or Monel if fluxes either are not used or are completely removed. Inconel, Illium, Illium "R", and Duranickel are less resistant than either nickel or Monel at higher temperatures but are generally similar to stainless steels. Copper Highly resistant to fluorine attack as are the copper alloys, red brass, and yellow brass. Cupric fluoride film is very stable in the presence of dry fluorine or dry hydrogen fluoride, but hydrolyzes readily in moisture to form hydrofluoric acid. Titanium Poor resistance to hydrogen fluoride. Liquid fluorine has the tendency to be highly reactive with titanium. Gaseous fluorine will attack titanium at temperatures above 300°F. Silver solder: Nicrobraze Recommended for most of the joining where welding is impractical or impossible. Connections made with this material have been highly reliable. Chromium Four fluorides are formed: 1) divalent, 2) trivalent, 3) tetravalent, and 4) pentavalent (3 an 4 are volatile). When chromium is reacted with fluorine below 300°F it forms a protective divalent fluoride film. Above 300°F, the fluoride is converted from a divalent to a volatile tetravalent fluoride form and loses its protective ability. Beryllium Behaves much the same way as nickel in fluoride film formation. Tantalum should not be used at temperatures above 150°F Lead Forms a nontenacious fluoride film. In passive exposure it has been used successfully as a seal or gasket material. Tin Reacts similarly to lead and can also be used for soft gaskets in cryogenic service. Rhodium, palladium, platinum Can be used on contact with fluorine at room temperature generally without attack. These metals are used in some equipment because they are inert to hydrogen fluoride. The list in the above table shows a variety of metals which are compatible to a certain degree in fluorine. Generally nonmetallic materials are incompatible with fluorine, with the exception of ruby and Teflon (see References 1 & 3). It should be understood by the designer that material selection is dependent on the environmental conditions. To assist the designer in developing a safe fluorine system, Table 3 lists recommended materials to be used under certain operating conditions. Table 3. Recommended Materials for High and Low Pressure Operations HIGH AND ATMOSPHERIC PRESSURE OPERATIONS Materials Preferred High Pressure: (>14.7-1500 psi.) Nickel or Monel More resistant to ignition than steel. These metals are preferred when handling pure fluorine under pressure. Monel piping can even be used at higher pressures than Nickel. Atmospheric Pressure: Copper, Iron, Stainless Steel, and Brass If the piping wall thickness is adequate, i.e., as in standard or extra-strong pipe, the material weight and surface area are large enough to eliminate spontaneous combustion. High & Low Pressure Connections: Welding, Flange joints Through experiments, welding has proved to be highly reliable in high and low pressure. Soft solder and fluxes should not be used, however. Flange joints are preferred when necessary, gaskets must be limited to soft metals, lead, tin, copper or aluminum. Valves Bellows-sealed valves generally can be used up to 100 psi., in 1-inch and larger sizes. The Hoke Monel needle valves or the Kerotest 440-A packed with Teflon or its equivalent have been successful. Metal-seated valves with Monel or aluminum-bronze seat-and-disk combinations have also been used successfully for low pressure valves. Technical Rationale: Certain effects peculiar to a fluorine environment need to be considered by the designer. Fluorine is a highly reactive oxidizing agent; it has the highest oxidation potential of all elements. Fluorine can react with practically all organic and inorganic substances with few exceptions. Exceptions include the inert gases, fluorinated compounds in their highest state of oxidization, and a few fluorinated polymers. Whether a substance will burn spontaneously in fluorine, or whether fluorine will replace an oxidant having a lower oxidizing potential, depends on the following conditions of exposure, (Reference 1): Initial temperature of the region. Reaction is initiated by reaching the ignition temperature or by providing activation energy from impact, friction, high flow, or reaction of contaminants. Initial pressure of the region. It has been found that ignition temperatures are lowered by increasing pressure. Thermal conductivity if the material is a solid. Combustion will not occur if heat of reaction can be removed by conduction and the temperature can be maintained below ignition temperature of material. Exposed surface area with respect to mass of the substance. Generally, surface reactions with most metals will form a fluoride film and inhibit further reaction. Large exposed surface-area-to-mass material forms (fine mesh screen, powered metal, etc.) can have surface reactions that are highly reactive and can increase temperatures to initiate combustion. Kinetic or static exposure. It has been found that kinetic energy from flow dynamics can contribute to activation energy for combustion. Fluorine concentration in the region. Reactivity increases with increased fluorine content of liquid or gaseous mixtures. Fluorine can react combustively with water depending on the size of water droplets. Ice will react combustively with liquid fluorine. In the presence of water, the fluorine will react to form hydrogen fluoride potentially resulting in corrosion. Therefore, the entry of water into the system in any form, even from non-dry purge gases or moisture laden air, is to be avoided. In addition to the selection of materials based on property requirements for the application (i.e. strength, thermal properties, welding or brazing characteristics, etc), the selection of materials for use with fluorine must consider the introduction of contaminants into the system and whether a given material will burn spontaneously in the presence of fluorine. Materials selected must be cleaned free of contaminants and fabricated without introducing contaminants and/or entrapped voids. The contaminant can be in the form of a material additive or foreign material (ice, moisture, grease, soil, etc.) which unintentionally enters the system. The contaminant can then react with fluorine and cause local temperatures to exceed the ignition temperature for that part of the system, resulting in failure. The presence of voids can lead to trapped contaminants that escape cleaning procedures and therefore must be avoided. References: Schmidt, H. W.: "Fluorine and Fluorine-Oxygen Mixtures in Rocket Systems," NASA SP-3037, 1967. Schmidt, H. W.: "Compatibility of Metals With Liquid Fluorine At High Pressures and Flow Velocities," NACA RM E58D11, 1958. Price Jr., H. G. and Douglass, H. W.: "Nonmetallic Material Compatibility With Liquid Fluorine," NACA RM E57G18, 1957. Slesser, Ph.D. Charles and Schram, Stuart R.: "Preparation, Properties, and Technology of Fluorine and Organic Fluoro Compounds," McGraw-Hill, New York, 1951. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
694 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Super Ni-Cd Spacecraft Battery Handling and Storage Practice |  | The impact of not following this practice would very likely be that flight batteries would be irreversibly degraded due to improper handling and preparation for launch. This could result in the failure of batteries to meet flight performance requirements and also possibly early catastrophic failures. | Flight projects assure reliable operation of Super Ni-Cd flight batteries through the implementation of appropriate handling and storage procedures. Such procedures minimize deterioration and irreversible effects. | GSFC | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1108; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Super Ni-Cd batteries are perishable and their reliability is directly related to prudent handling and storage procedures. The development and implementation of appropriate project-unique procedures based on a set of proven guidelines assure that the optimum performance of Super Ni-Cd batteries is not degraded due to inappropriate handling and storage. Implementation Method: The Super Ni-Cd cell is an advanced Ni-Cd cell design developed by Hughes Aircraft company. It is constructed of electrodeposited positive (nickel electrodes), and negative plates (cadmium electrodes). The separator material is an inert polymer impregnated zirconium cloth interleaved with the plates and serves to insulate the positive plates from the negative plates and retain the electrolyte. The interelectrode spacing was increased in the Super Ni-Cd design to permit greater than 4 ml/Ah of electrolyte. This is about 31 percent more electrolyte than in the conventional Ni-Cd cell. The plates are connected to the respective cell terminals which are attached to a cell cover and inserted in a steel case and welded shut. The electrolyte is normally 31 percent concentration of potassium hydroxide with Hughes Aircraft proprietary additives. It is added though the "fill tube" which is fitted with a pressure gauge. After the cell satisfactorily completes its manufacturing and acceptance testing, the fill tube is pinched off and welded closed. The manufacture of a hermetically sealed Super Ni-Cd cell is predicated on a delicate balance between the active material, the relative state-of-charge of the active material between the positive and negative plates at the time the cell is sealed, the amount of electrolyte placed in the cell at closure, the properties of the separator material, and the free volume allowed by the case design. The Super Ni-Cd cell, which has no free or excess electrolyte, is referred to as an "electrolyte starved" design. The primary prerequisite for a sealed-electrolyte starved cell to operate safely is that the positive plates be limiting on charge so that only oxygen is generated during overcharge. During charge some of the current is utilized in the generation of oxygen gas and when in overcharge, all the current is used in generating oxygen. This causes the cell pressure to increase to a level that is dependent on the recombination rate of oxygen at the negative electrode, the rate of diffusion of the oxygen through the separator, the amount of electrolyte in the cell, and the cell free volume. The cell pressure at 20 degrees C can typically be in the range of 50 to 65 PSIG. The negative plates of a cell contain approximately 50 percent more capacity than the positive electrode. Of this "excess" negative capacity, approximately 60 percent remains uncharged when the positive plates are fully charged. This uncharged material is referred to as "overcharge protection" and is required to prevent the plates from becoming fully charged and generating hydrogen gas. The remainder of the excess negative is in the charged state when the cell is fully discharged and provides over-discharge protection. It is referred to as precharge. On discharge, when the cell voltage drops below 1 volt, the positive plates are limiting, thereby leaving charged cadmium material to react with any residual oxygen when the cell is completely discharged. Typical pressure of fully discharged cells is 3 to 5 PSIG. A second reason for the positive plates to be limiting on discharge is to prevent the effects of negative capacity fading, which occurs during normal use, from causing losses in cell capacity. It is thought that capacity fading is related to the sizes of the cadmium crystals. It is most important that the overcharge protection is available for the entire life of the cell. Should the negative plates become fully charged, hydrogen gas is generated during overcharge and there is no effective mechanism within the cell for the recombination of H2 gas. If a cell is over discharged (potential reversed) H2 gas is generated at the positive electrode at a rate dependent upon the discharge rate. Because of the limited free space in a sealed cell, a cell that is reversed can quickly build up pressure and rupture the cell case or battery package. The Super Ni-Cd cell is a highly complex, interactive electro-chemical device where the present and future performance is totally dependent on its past history. This history includes the attributes and characteristics of the raw materials, the processing of these materials into components, the assembly of these components into a sealed cell, and all testing, handling, and storage. Consequently, a cell or battery is classified as perishable and treated accordingly. Since Super Ni-Cd batteries can be irreversibly degraded by improper use and handling, the following guidelines were developed for the use of battery engineers in developing project-unique Battery Handling and Storage Procedure and Requirement Documents. Guideline No. 1 - Flight batteries should be maintained charged in cold storage at a temperature of 0 degrees C (± 3 degrees C) and on trickle charge at a rate of C/100 until required for installation into the spacecraft for battery/spacecraft integration testing and for launch preparations. When a battery is placed in cold storage, it should be fully charged and wrapped with an anti-static bag and closed. This bag should be placed in another anti-static bag along with packets of desiccant. A battery stored by this method, up to three years after cell activation, is expected to provide several years of nominal performance in orbit. Guideline No. 2 - Flight batteries should not be subjected to extended spacecraft integration and test activities. The open circuit and intermittent use of Ni-Cd batteries during extended spacecraft integration and testing activities are known to significantly accelerate the degradation of batteries. Results from controlled tests have shown permanent and irreversible changes unlike anything observed after several years of spacecraft flight operations. Degradation is observed initially as an increase in cell overcharge voltage at low temperatures which is indicative of loss in overcharge protection. Also, NASA integration and testing use promotes significant cadmium migration. Both of these are recognized as the dominate wear-out mechanisms which determine battery life. Guideline No. 3 - Batteries that have been on open circuit for periods greater than 4 hours following a charge at a level of C/100, should be discharged for 5 minutes at a 1.0 amp rate and then subjected to a top-off charge before operations are resumed. The use of charged batteries after an open stand should be initiated with a 5 minute discharge at a 1.0 amp rate prior to initiating battery charge as defined above. Typically, the discharge is done with spacecraft load and in concert with the spacecraft ground power console. During normal cycling use, the battery is discharged followed by a recharge and some overcharge. In this mode, there is always a partial pressure of oxygen from the overcharge with oxygen recombination occurring at the negative electrode. In a relatively short time on open circuit, the oxygen recombines and the internal cell pressure returns to a vacuum. Charging cells that are fully charged in the absence of oxygen creates an "unnature" condition, since there is no oxygen available to react with the negative electrodes. Past experience shows that this technique reduces the effects of open circuit stand on performance. Guideline No. 4 - For short-term storage of up to 60 days, the flight battery may be stored charged and open-circuited with the temperature controlled at 18 degrees C (± 5 degrees C). A top-off charge is applied to the battery biweekly (every 3-4 days). Trickle charge at low rates is preferred to open circuit stand for a battery. There are degradation mechanisms associated with this storage method, but data from controlled tests indicate that this is much less detrimental than prolonged open circuit stand. Guideline No. 5 - The preferred operational temperature for Super Ni-Cd batteries is 18 degrees C (± 5 degrees C). The periods when the batteries are exposed to temperatures above 23 degrees C should be minimized. Under no circumstances should the battery temperature exceed 30 degrees C with the exception of non-operational periods during Thermal Vacuum Testing (e.g. Hot Balance) where the allowed temperature should not exceed 33 degrees C. When testing is performed off of the spacecraft, the batteries should be mounted on a thermal cooling cart to maintain the battery in the required temperature range. When installed in the spacecraft prior to launch, the battery temperature should be maintained by the use of dedicated cooling air directed onto the battery or its baseplate when possible. Battery temperatures should be monitored via sensors installed in the battery assembly. Guideline No. 6 - A battery stored at cold temperatures and on trickle charge for a period greater than 30 days should be "reconditioned" prior to placing it in use. The reconditioning cycle at 18 degrees C is defined as follows: Warm battery at room temperature for minimum of 16-24 hours Discharge the battery at C/2 constant rate until the first cell reaches 1.0 V Drain each cell with a 1 ohm resistor until each cell's voltage is less than .03 V or for 16 hours (+0/-1 hour) whichever occurs first. Recharge at C/20 rate for 40 hours (± 4 hours) Repeat steps (b) and (c) Recharge at C/10 rate for 20 (± 1 hour) Note! * Never short a Super Ni-Cd cell or battery * Monitor and maintain battery temperature at 18 degrees C (±5 degrees C) during the reconditioning cycle. Guideline No. 7- Batteries once removed from cold storage must be reconditioned every 30 days as described in Guideline No. 6. Guideline No. 8 - Flight batteries must be discharged and left on open-circuit stand during shipment. Batteries are packaged to control the temperature to 5 degrees C (± 5 degrees C). The shipping container is equipped with temperature recorders to provide assurances that flight batteries have not been exposed to temperatures exceeding 25 degrees C. Upon arrival at its destination, the battery is recharged and put on trickle charge. A Super Ni-Cd battery can deliver very high currents if shorted. High currents would create a safety hazard as well as destroy the battery due to the excessive heat that would be generated. Guideline No. 9 - The final reconditioning of flight batteries, using battery conditioning steps (b) thru (f) of Guideline No. 6, should be performed at least 14 days prior to spacecraft launch. Upon completion of the reconditioning, flight batteries are maintained on a C/100 trickle charge rate until launch. The reconditioning cycle restores the battery discharge voltage to "like new" condition by enhancing the formation of small cadmium crystals and electrolyte redistribution. A complete discharge establishes capacity balance for all cells within a battery. The low rate trickle ensures that the battery is maintained at full state of charge for launch. Guideline No. 10 - The design of flight batteries should include the following provisions for ground console interfacing with the batteries while integrated in the spacecraft. Signal lines for monitoring total battery voltage, charge and discharge currents, battery temperatures, and individual cell voltages Capability to charge and discharge the battery from the ground test console Capability to place a resistor across each individual cell Capability is provided to monitor the state of health of batteries and to discharge, charge, trickle charge and recondition batteries without powering up the spacecraft in order to meet guidelines to minimize degradation of the batteries. Guideline No. 11 - A log book should be maintained on each flight battery including the complete test histories of each cell, of the assembled battery, and of all integration and test and launch site activities. Each log book identifies the project and battery and individual cell serial numbers. Chronological (date and time) entries for all test sequences, summary of observations, identification of related computer stored records, malfunctions, names of responsible test personnel, and references to test procedures controlling all tests are recorded. Technical Rationale: Super Ni-Cd batteries can be damaged and irreversibly degraded through improper use and handling prior to launch. The guidelines provided above were developed over years of experience in the use, handling, and testing of Ni-Cd batteries. Following these guidelines ensures reliable operation of flight batteries by precluding irreversible degradation from handling and storage, and promoting the proper reconditioning and preparations for launch. References: GSFC-FAST AURORAL Snapshot Explorer (FAST) Super Ni-Cd Battery Handling Plan (FAST-PROC-004) of February 1994 | This practice has been used on: Solar Anomalous Magnetospheric Particle Explorer (SAMPEX) Fast Auroral Snapshot Explorer (FAST) Submillimeter Wave Astronomy Satellite (SWAS) Total Ozone Mapping Spectrometer (TOMS) X-Ray Timing Experiment (XTE) Tropical Rainfall Measuring Mission (TRMM) | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
693 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Earth Orbit Environmental Heating |  | Not considering the variations in the environmental thermal effects as described in this guideline will result in an incomplete thermal analysis. The temperature variation of the spacecraft could be grossly underestimated, thereby reducing its reliability. | Use the currently accepted values for the solar constant, albedo and earth radiation when calculating the heat balance of earth orbiters. This practice provides the heating rates for the black body case without consideration of spectral effects or collimation. | GSFC | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GD-AP-2301 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Consideration of the solar, albedo, and earth radiation thermal inputs, including seasonal variation with tolerances, is required to accurately predict the thermal environment of orbiting devices. Implementation Method: SOLAR CONSTANT The nominal solar constant value is 1367.5 W/m2. The variation of the earth-sun distance causes a ± 3.5% seasonal variation from nominal. The accuracy of the solar constant is taken as ± 0.5%. The following are the values for various seasons in the northern hemisphere. NOMINAL 1367.5 W/m2 WINTER 1422.0 W/m2 (NOM + 4.0%) SUMMER 1318.0 W/m2 (NOM - 4.0%) ALBEDO FACTOR* The nominal albedo factor is 0.30. The variation around the nominal should be ± 0.05. No variation during the sunlit portion of a given orbit should be assumed unless extremely light weight items are being considered. Programs that compute albedo energy should use 0.35 (hot case), 0.30 (nominal case), and 0.25 (cold case), respectively. *Note: Since earth temperature and albedo vary with latitude, as the orbit approaches either extreme of a polar or equatorial orbit, further study of the literature should be made. (see AIAA-87-1596) EARTH EMITTED ENERGY * The nominal earth temperature for earth emitted IR energy is 255 degrees K. This temperature produces a heating rate of 241 W/m2. A reasonable variation can be obtained by maintaining consistency using the following relationship between Solar, Albedo, and Earth Emitted Energy: Earth Emitted Energy = [(1-Albedo Factor)x Solar Constant] / 4.0 Table 1 shows the variations in Earth Emitted Energy that result from using the above recommended Solar and Albedo ranges. Software programs that compute Earth Emitted Energy should use the appropriate hot, nominal, or cold case Solar and Albedo values; and the corresponding black body Earth temperature to achieve an energy balance. REFERENCES FOR QUICK CHECKS OR SIMPLE CALCULATIONS Hand calculations should be made to verify that computer outputs of heating values for flat surfaces of known orientation and minimal reflected inputs from other surfaces are reasonable. Hand calculations also may be necessary when time does not permit a computer study. A check of incident Albedo energy to a flat plate at various altitudes and orientations can be made by using TN-D 1842 quotEarth Reflected Solar Radiation Incident Upon an Arbitrary Oriented Spinning Flat Plate,quot by F. Cunningham. Figures 1 through 9 show the orbit-averaged incident Earth and Albedo energies to an Earth-oriented flat plate at various altitudes and orbit/sun angles. Eclipse factors for elliptical orbits are provided in quotCalculation of the Eclipse Factor for Elliptical Satellite Orbitsquot, by F. Cunningham. A hand calculation of incident Earth Emitted Energy to a flat plate at various attitudes and altitudes also is possible. Figure 10 shows the instantaneous geometric shape factor for a planar surface as a function of altitude and attitude (h/R is the ratio of the orbit altitude to the Earth radius). The earth radius is 6,365 km. The incident Earth Emitted Energy is found by multiplying the shape factor times the black body emissive power at the earth temperature. For an altitude of 1,000 km and a flat plate whose normal is 90 degrees to the nadir (l= 90); h/R = 0.157, which gives a shape factor of 0.19. The Earth Emitted Energy incident on the plate is 0.19 x 241 W/m2or 46 W/m2. *NOTE: Since earth temperature and albedo vary with latitude, as the orbit approaches either extreme of a polar or equatorial orbit, further study of the literature should be made (see AIAA-87-1596). RECOMMENDED SOLAR AND ALBEDO RANGES* SOLAR CONSTANT (W/m2) ALBEDO FACTOR EARTH EMITTED ENERGY (W/m2) EQUIV. EARTH TEMP (°K) NOMINAL 1368 0.25 0.30 0.35 256 239 222 258 254 250 WINTER SOLSTICE 1422 0.25 0.30 0.35 267 249 231 262 258 253 SUMMER SOLSTICE 1318 0.25 0.30 0.35 247 231 214 256 251 246 *For use in Orbit Average Analyses EQUIVALENT SINK TECHNIQUE The equivalent sink technique can be used by replacing all surrounding surface radiant interchanges and the absorbed Solar and Earth energies to node i with a single radiation coupling to a single node at temperature T sink. To derive the equation for this sink temperature, first consider an energy balance at node i where all the inputs are treated as gross inputs and node i has a view to space of 1.0. (1) [D] From planetary flux program (TRASYS or SSPTA) From thermal program (SINDA) results obtained from Geometric Math Model (GMM) radiation exchange program Where: [D] Next consider the equivalent sink energy balance situation:[D] (2) [D] Solving (1) for [D] and setting equal to the right side of (2) gives: (3) [D] The equivalent sink for node i may be determined from the detailed thermal math model by determining the adiabatic temperature of node i when node i is disconnected from internal heat paths and heat dissipations. For a transient situation, node i must be an arithmetic node or a low mass node. Technical Rationale: Thermal analysis of an earth orbiting spacecraft requires the accounting of incident thermal energy from all external sources. The most significant external sources of energy incident on the spacecraft are the sun, the thermal radiation of the earth, and the solar energy reflected from the earth (albedo). The modification of the energy incident on the spacecraft due to the earth-sun distance variation, and the accuracy of the measurements of the solar constant, are of sufficient magnitude to be important parameters in performing a thermal analysis. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/09/2000
674 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Vacuum Seals Design Criteria |  | Incompatible O-ring elastomer and environmental elements, incorrect O-ring size, improper gland design (including rough surface finish), and inadequate O-ring lubrication may result in O-ring failure, joint leakage and ineffective vacuum seals. Leakage in vacuum seals can be detrimental to space crew, vehicles and equipment. | Well made, clamped, and temperature stabilized circular O-rings should be used in the design of reliable, reusable and long life seals in vacuum sealing applications. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-ED-1223 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Leak free flanges as well as low/undetectable outgassing of the elastomeric materials can be achieved at pressure levels as low as 10-8 Torr by using well made O-rings in a static vacuum seal environment. The use of O-rings has provided ease for running environmental tests on the ground using space simulation chambers. Implementation Method: The most common type of seal used for sealing vacuum systems is the O-ring. In order for any O-ring to be suitable for high vacuum service, it must have a very low vapor pressure at the service temperature. It must not have any components or materials which will vaporize at the pressures and temperatures to which the joint will be subject. Butyl, Buna-N and Fluorocarbon (Viton® A) rubber materials have been used to vacuum seal large chambers (15 foot and 25 feet in diameter) at LeRC. These materials can, in well made, clamped O-rings and under temperature controlled conditions, seal vacuum as low as 10-8 Torr. Small (6 foot diameter) and large (50 foot diameter) vacuum chambers have been successfully used on research programs at LeRC to simulate space pressure conditions and environment. Environmental testing, experiments, and pre-flight tests (all requiring large-volume vacuum environment) have been performed at LeRC in these chambers. For this pressure range, the following O-ring design considerations should be followed: Dimensional. To obtain the correct degree of compression for optimum O-ring sealing, careful consideration must be given to the size of the O-ring in relation to the size of the groove space into which the O-ring is being installed. Every groove has a slight gap (diametrical clearance) between the two mating surfaces forming the groove's internal cavity. It is important, therefore, for O-ring volume to be larger than the cavity, allowing seal compression to block the diametrical gap, preventing leakage and providing 25% compression in the O-ring. Butyl rubber has been tested in face type O-ring seals using grooves that provided 15%, 30% and 50% compression. For vertical O-ring applications (as a chamber), it is desirable to use an undercut groove similar to that shown in Figure 1. The O-ring is held firmly in place and has no tendency to drop out of the groove when the chamber is open. [D] Pressure. Total clamping pressure on the O-ring due both to the effects of vacuum on the parts being closed, and the effects of bolts or clamps used with the O-ring, should be approximately 800 pounds per lineal inch of O-ring. If the O-ring cannot resist increasingly high pressure, part of the O-ring will be forced (extruded) into the diametrical gap, causing tearing, pre-mature failure and leakage. To minimize O-ring movement and accompanying wear within the groove in face sealing, involving either internal or external pressure, the O-ring should always be seated against the low pressure side of the groove. The use of two O-rings on the chamber's sealing surface has proven successful in holding the required pressure applied on the 15 foot diameter seal as illustrated in Figure 2. The reason for the two O-ring design is that it is possible to pump out the space between the two O-rings. The effect of this technique is to make use of the outer O-ring for holding a relatively crude vacuum and subject the inner O-ring to only a small differential between the high vacuum system on its inner face and the partial vacuum on its outer face. As a result of this double pumped system, the leakage per O-ring can be greatly reduced. [D] Vapor Pressure. The O-ring must have a very low vapor pressure at the service temperature. It must not have any components which will vaporize at the pressures to which the joint will be subject. Resilient organic material such as Viton® A is most commonly used to produce and hold vacuum as low as 10-9 Torr. Temperature. The vapor pressure of most or all organic materials is proportional to temperature. It is therefore very important that O-ring's temperature be limited. The best of the materials must be held below 250°F, and for minimum outgassing an even lower temperature is recommended. For temperatures held below 65°F, it is possible to use carefully constructed O-ring joints at pressures as low as 10-9 Torr. Excessive heat, over time, degrades O-ring materials physically, and/or chemically, which may render them non-functional as seals. The O-ring temperature must be reduced to values between zero and -10°F during ultra vacuum operation. Surface. It is important that the groove surfaces be so ground and polished that no residual tool marks or scratches occur at right angles to the length of the groove. Even minute scratches can produce a leak, which is difficult to locate and repair. The mating flanges, which are flat and serve to compress the O-ring must have, at the point where the O-ring contacts them, an equally good finish. The surface finish in the O-ring groove and on the flat mating flange must be at least 32 micro inch and preferably 16 micro inch. Permeability. In vacuum applications, high material resistance to gas permeation is directly equated with low vacuum leakage of the O-ring. Butyl and Fluorocarbon excel as the most impermeable performers. Increased O-ring compression reduces permeability by increasing the length of the path the gas has to travel (width of ring) and decreasing the area available to the entry of the gas (groove depth). Increased compression also tends to force the rubber into any small irregularities in the mating metal surface, and thus prevents leakage around the seal. Vacuum Weight Loss. It is particularly important in many space and other vacuum applications that optical surfaces and electrical contact surfaces remain clean to serve their intended purpose. Some rubber compounds contain small quantities of oil or other ingredients that become volatile under high vacuum conditions and deposit as a thin film on all the surrounding surfaces. Table 1 indicates the weight loss of several compounds due to vacuum exposure. Where sensitive surfaces are involved, the higher weight loss compounds should be avoided. In the low weight compounds, the small amount of volatile material that is indicated is primarily water vapor which is not likely to deposit on nearby warm surfaces. Table 1. Weight Loss of Compounds in Vacuum Test Samples: Approximately 0.075 thick Time: 336 hours (two weeks) Vacuum Level: Approximately 1 x 10 -8 torr Room Temperature Compound Number Polymer Percent Weight Loss Compound Number Polymer Percent Weight Loss B612-70 C873-70 E515-80 E529-60 E692-75 L449-65 L677-70 N406-60 Butyl Neoprene Ethylene Propylene Ethylene Propylene Ethylene Propylene Fluorosilicone Fluorosilicone Nitrile 0.18 0.13 0.39 0.92 0.76 0.28 0.25 3.45 N674-70 P648-90 S455-70 S604-70 V747-75 V884-75 V894-90 Nitrile Polyurethane Silicone Silicone Fluorocarbon Fluorocarbon Fluorocarbon 1.06 1.29 0.03 0.31 0.09 0.07 0.07 Vacuum Seal Considerations. The rate of flow of gases from the pressure side to the vacuum side of a vacuum seal depends to a great extent on how the seal is designed. As mentioned earlier in this document, increasing the compression reduces the leak rate. Lubricating the O-rings with a high vacuum grease also reduces the leak rate significantly. The vacuum grease aids the seal by filling microscopic pits and grooves produced by small irregularities in the mating metal surface. The O-ring should first be cleaned to remove all dirt and foreign material utilizing a small amount of Alcohol on a cloth as a cleaning agent, and should be given a very thin coat of vacuum grease (i. e., Apiezon grease) applied by drawing it through fingers slightly coated with vacuum grease. It should be noted that vacuum grease should not be depended upon to provide any sort of vacuum seal. Vacuum Leak Approximation. The leak rate of a gas through an O-ring seal may be roughly approximated when the permeability of the gas through a particular material is known for the temperature at which the seal must function. The following formula is useful for this approximation: L ~ 0.7 F D P Q (1-S)2 L = Approximate leak rate of the seal,std. cc/sec. F = Permeability rate of the gas through the elastomer at the anticipated temperature, std. cc cm/cm2 sec bar. (example: Butyl's 2 permeability at 77°F with Acetylene is 1.26 x 10-8 std. cc cm/cm2 sec bar) D = Inside diameter of the O-ring, inches. P = Pressure differential across the seal, lb/in2. Q = Factor depending on the percent compression and whether the O-ring is lubricated or dry (from figure 3 below) S = Percent compression on the O-ring cross section expressed as a decimal (i.e. for 20% compression, S = 0.20) Note: This formula is a rough order of magnitude approximation and is based on the following assumptions: The cross section of a compressed O-ring is rectangular. The cross section area of a compressed O-ring is the same as its area in the free condition. The permeability rate of a gas through an O-ring is proportional to the pressure differential across the seal. [D] Static Seal Cross Section Calculation. To calculate correct cross section dimensions for static seals, list the gland depth and multiply by the minimum and maximum compression requirements (listed in Table A, Section 3 of Reference 5). For Inside Diameter (I.D., or hole diameter) calculation, list the diameter of the part the O-ring will be stretched over during installation, and reduce this figure by 1 to 5% to undersize the O-ring's I.D, allowing for stretch. Vacuum Feedthroughs. Many types of vacuum feedthroughs are available from suppliers as Varian Vacuum Products (Reference 6). They are designed for pressure as low as 10-11 Torr and provide leak-free performance in high and ultrahigh vacuum systems. With ceramic-to-metal seal construction, applications for these feedthroughs include: Instrument and Thermocouple Leads, RF Power Input, Coaxial Input, Mask and Substrate Handling, Target Movement, Liquid Cooling, High Voltage Conduction and High Current conduction. As an example for using one type of feedthrough, electrical circuits carried into and out of ultrahigh vacuum systems must be of ceramic-to-metal seal construction. A tight bond is made between a ceramic and a kovar transition sleeve which is then welded into the stainless steel of the vacuum vessels. The actual electrical feedthroughs come through the center of the ceramic insulator and are bonded to it by special bonding techniques to achieve gas tightness. It is important that electrical leads inside ultrahigh vacuum systems must be insulated by means of non-outgassing materials. These leads should be limited to ceramic beads since all of the elastomeric type insulating materials outgas a considerable amount in vacuum systems. Rotating Seals. O-rings are used as seals for rotating shafts, with the turning shaft protruding through the internal diameter of the O-ring. The inside surface of the O-ring is continuously exposed to friction generated heat from the rotating shaft. The most important factors to consider when designing rotating seal glands are frictional heat buildup, O-ring stretch, compression, application temperature limits, and shaft glandular machining. O-rings should be comprised of compounds featuring maximum heat resistance and minimum friction generating properties. To help minimize O-ring heat buildup, the following mechanical design safeguards should be considered where applicable: Reduce compression to 0.002 inch to minimize friction. Select the O-ring with the smallest possible cross section. Select an O-ring comprised of a hard, self-lubricating compound (such as graphite). Avoid applications requiring lower than -40°F, or higher than +250°F operating temperatures. Locate the gland as close as possible to the lubricating fluid and as far away as possible from the shaft support bearings. Assure that relative motion occurs only between the O-ring internal diameter and the rotating shaft, not between the O-ring and the gland. This can be accomplished by minimizing eccentric shaft rotation (machining shafts concentric to within 0.0005 inch TIR); by finishing shaft surfaces to 16 micro inch (for smooth, non-abrasive running); and machining gland surfaces to a rougher 32 micro inch (to discourage O-ring movement within the gland). Technical Rationale: Vacuum chambers (ranging from 6 to 50 feet in diameter) have been utilized at LeRC for over 30 years to simulate space conditions. The reliable, reusable, long lasting, and round configuration vacuum seals demonstrate the success of using rubber O-rings to vacuum seal these small and large chambers. Environmental testing, experiments, and pre-flight tests have been fruitfully conducted in these chambers in space simulated environment. These practices were gained from LeRC's experience with vacuum seals and sources listed in the references. References: Robert C. Finke, Arthur D. Holmes, and Thomas A. Keller, quotSpace Environment Facility for Electric Propulsion Systems Researchquot, NASA TN D-2774, Lewis Research Center, Cleveland, Ohio, May 1965. The Boeing Company, quotPractical Vacuum Systems Designquot, Seattle, Washington, 1962. The Boeing Company, quotUltra High Vacuum Theory and Designquot, Seattle, Washington, 1963. Parker Seals, quotParker O-Ring Handbookquot, ORD 5700, Parker Seal Group, O-Ring Division, Lexington, KY, 1991. Apple Rubber Products, quotSeal Design Catalogquot, Apple Rubber Products Inc., Lancaster, NY, 1989. Varian Vacuum Products, quotVarian Vacuum Products 1991/1992 Catalogquot, Lexington, Massachusetts, 1991. Donald J. Santeler, Donald W. Jones, David H. Holkeboer, and Frank Pagano, quotVacuum Technology and Space Simulationquot, NASA SP-105, Washington, D.C., 1966. quotStatic Cryogenic Seals for Launch Vehicle Applicationsquot PD-ED-1208. | This practice has been used since 1950 in operating vacuum chambers (such as the 15 foot diameter vacuum chamber addressed herein) with reliable and long lasting vacuum seals. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/08/2000
673 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Over-Speed Protection System for DC Motor-Driven Cranes |  | An increased potential would exist for a critical crane failure which could result in damage to flight hardware or serious injury/death to personnel. | DC drive motor over-speed detection using a voltage sensing relay. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-ED-1235 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: This design employs a simple method of providing protection against the effects of a crane operating at a higher than commanded speed while not introducing unwanted nuisance trips to the crane control system. This improves the reliability of the crane control system by preventing the crane from reacting to unwanted commands that are not operator initiated. The improvement allows the crane to be used with a higher degree of confidence that a critical failure will not result in damage to the load suspended from the load hook. Implementation Method: The design provides protection against damage to a load resulting from a crane drive system experiencing a speed increase caused by an unexpected input created by a failure of the electrical circuitry used to convey the operator stick input to the drive motors. The voltage sensing relay is set to detect a voltage that is larger than the normal operating voltage of the DC motors in the selected speed (slow, medium, or high). When this voltage is experienced, the relay will shut down the crane operation and set the brakes. For example, at KSC while performing stacking and mating operations of the Solid Rocket Motors (SRM), External Tank (ET), or Orbiter during Space Shuttle processing, the crane must be operated in the slow speed mode when within close proximity of a structure. The voltage sensing relay is active during this mode to prevent the shuttle components from impacting a surrounding structure as a result of a control circuitry failure. The relay is deactivated while operating in the medium or high speed modes because the critical load is not near an obstruction. This allows the crane to be operated with a higher degree of confidence and reliability that a critical failure will not result in damage or loss of critical flight hardware during stacking and mating operations. Technical Rationale: With a constant field/varied armature DC motor (more than one motor, the armatures wired in series) the voltage sensing relay coil should be placed in parallel to the motor armature(s) (see Figure 1.). The relay coil should be fed through a bridge rectifier to insure the input to the relay is consistent regardless of the voltage polarity and direction of current flow present in the armatures. The normally open relay contact should be wired in series with the power supplied to the crane and brake controls. When power is applied to the crane the contact should close and enable the drive control circuitry. The contact will remain closed when the voltage in the motor armature is below the predetermined threshold. When the limit is reached, approximately 115% of the full output of the speed range, the contact will open disabling the crane drive and setting the brakes to stop the crane. To avoid the crane shutting down when in the higher speed range, a time delay relay will be energized by the speed selector switch and by pass the voltage sensing relay. To prevent nuisance trips when the speed selector switch is repositioned from the higher to the lower speed range while the crane is moving, the time delay relay will disable the voltage sensing relay for a short predetermined time period when it is de-energized. [D] References: 69-K-L-11388: quotVehicle Assembly Building 250-Ton Bridge Crane #1 & #2 Electricalquot SAA09FY12-005: quotSystem Assurance Analysis of the 250-Ton Bridge Cranes at the Vehicle Assembly Building, High Bays 1, 2, 3 & 4quot 67-K-L-11348: quotVehicle Assembly Building 175-Ton Bridgequot Crane Electrical. SAA09FY12-006: quotSystem Assurance Analysis of the 175-Ton Bridge Cranes at the Vehicle Assembly Buildingquot | This practice has been used on the KSC Vehicle Assembly Building (VAB) 250-ton and 175-ton Bridge Cranes. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/08/2000
672 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Application of Ablative Composites to Nozzles for Reusable Solid Rocket Motors |  | Impact of Non-Practice: Not adhering to the proven practices for the design, manufacture, and testing of ablative composite materials could result in low material density, separation of fibers, and contamination. These defects could cause expensive scrappage and possible schedule delays. The ultimate impact of not adhering to precise in-process controls could be burn-through of the nozzle causing loss of mission, vehicle, and life. | Practice: Fabrication of ablative composite materials for solid rocket motor nozzles requires a precision, integrated, multi-disciplinary, multivendor approach to design and manufacture. Creation of the material requires stringent process controls during manufacture of the rayon fiber, weaving the rayon fiber into cloth, carbonizing the rayon cloth, impregnation of carbon cloth with resin and filler, wrapping the carbon-phenolic onto a mandrel to the proper thickness, curing, nondestructive inspection and final machining to the designed configuration. Environmental conditions and cleanliness levels must be closely monitored when bonding the ablative material to the metal housing. The critical material properties for acceptance of carbon cloth-phenolic prepreg material are cloth content, dry resin solids content, volatile content, carbon filler content, and resin flow. Use of certified and highly skilled tape wrapping operators, bonding technicians, machinists, and destructive and nondestructive testing personnel, is a must. | MSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1218; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Adhering to proven design practices and process controls during manufacture of ablative composite nozzle components will result in a high quality product with few rejects. Successful design and manufacturing of ablative composite materials for solid motor nozzles provides for proper transfer of the combustion gases from the burning propellant surface through the nozzle without damage to the metal structure. Use of a properly controlled manufacturing process will result in the proper density, percent resin content, compressive strength, interlaminar shear strength, thermal conductivity, coefficient of thermal expansion, and tensile strength. Implementation: The increased interest in carbon-phenolic composite materials at NASA is due to the use of these materials as the ablative materials in the Solid Rocket Motor (SRM) nozzle of the Space Shuttle and potential follow-on solid rocket motor upgrades. The practices discussed here are the current industry standards, and, however successful, much work is yet to be done. Most of the manufacturing practices have evolved by the trial and error method and could benefit greatly from further scientific investigation. Almost all of the nozzle materials and processes need continued research and development efforts as NASA strives for optimal performance from advanced materials. In the design of ablative nozzle components, considerable attention should be given to thermo-structural, thermochemical, process modeling and other computer predictive and analysis codes. Various computer based analytical and simulation programs are available and have been used successfully in characterizing ablative materials and their erosion, char, and thermal protection characteristics. Typical programs that have been used for this purpose are: Charring Material Ablator (CMA), Aerothermal Chemical Equilibrium (ACE), Momentum and Energy Integral Techniques (MEIT) (ACE and MEIT are used in conjunction with the CMA program), and PATRAN (geometry of nozzle, a general model for structural and thermal analysis). Computational Fluid Dynamics (CFD) is a discipline that is finding increasing usage in evaluating the exhaust flow in SRM nozzles and in determining potential heat transfer to nozzle components. These techniques are important tools for the designer who is applying ablative composites to solid rocket motor nozzles. [D] As shown on Figures 1 and 2, the aluminum structure of the SRM nozzle is protected from the heat of the expanding gasses by a series of carbon cloth phenolic rings backed up by glass or silica cloth phenolic rings. The glass and silica cloth phenolic backup rings are provided for structural, insulation, and galvanic corrosion protection. In lieu of one single ring, a series of rings is used for ease of manufacture and handling. Factors of safety for ablative carbon cloth phenolic vary between approximately 1.5 and 2.0 for erosion and are usually about 1.25 for char, depending upon the location of the ablative carbon cloth phenolic in the nozzle. Generally, the factors of safety in the entrance section of the nozzle are higher than in the exit section. The optimum angle between the plies and the flame surface in SRM nozzles using ablative carbon cloth phenolic has been proven to be between 30 degrees and 60 degrees, depending upon the location, contour and heating conditions at various sections of the nozzle. [D] Manufacture of Carbon Cloth: The carbon cloth used to fabricate composite solid rocket motor nozzles is impregnated with the binder or matrix prior to wrap and cure. This preimpregnated material is commonly called quotprepregquot in the composite industry. The diversity of the manufacturing process requires six different vendors before final material is produced. These vendors: 1) produce rayon thread; 2) weave cloth; 3) carbonize cloth; 4) produce resin; 5) produce carbon fillers; and 6) impregnate carbon cloth with resin and filler (production of prepreg). Constant monitoring of all phases of the manufacturing process is required to ensure satisfactory quality. The rayon thread is manufactured, then woven into cloth 60 in. wide. The rayon cloth is carbonized by slowly heating to 1000 deg. to 1500 deg. C in an inert atmosphere. Critical factors to be controlled in this process are the rate of temperature increase, time, and maintenance of an inert atmosphere in the oven. After carbonization, the carbon-cloth is impregnated by drawing it through a heated container of phenolic resin and carbon filler to form prepreg. Critical factors that must be carefully controlled in the preimpregnation process are temperature of the resin/filler mixture, tension and speed of the cloth through the resin/filler mixture, pressure on the roller to ensure penetration of resin into the cloth, oven temperature after impregnation to remove volatiles, and control staging of the resin. The prepreg should meet the uncured material acceptance test data properties shown in Table 1 and the cured material acceptance test data properties shown in Table 2. However, it should be pointed out that since the structural minimum - maximum properties shown on Table 2 vary by factors greater than 2 indicate that additional material, process and cure controls improvements are required to narrow the variation in material capabilities. Table 1. Uncured Material Properties of Carbon Phenolic Property Percent by Weight Retest Properties Percent by Weight 1/ Minimum Maximum Minimum Maximum Cloth content Dry resign solids Volatile content Carbon filler content Resin flow 47.0 32.0 3.5 8.0 10.0 60.0 37.0 6.0 16.0 20.0 — — 3.5 — 8.0 — — 6.5 — 23.0 1/ Procuring activity verification of potential extension of material shelf life after six months from date of supplier manufacture The prepreg material has a six-month shelf life from date of manufacture. Potential shelf life may be extended if the material meets the retest properties of Table 1. The prepreg tape rolls should be cut on a 45 deg. bias in widths of 3 in. and 12 in. The bias cut allows the cloth to stretch and conform to the different mandrels, and the narrow widths help avoid wrinkling and folding of the material during the wrapping process. The rolled prepreg is bagged with desiccant and stored in an environmentally controlled cold storage until it is required for processing. Glass Cloth Phenolic: The glass cloth phenolic shown in Figure 2 is used to provide structural integrity, a corrosion barrier, and insulation. It is fabricated in a manner similar to that of carbon cloth phenolic. The product should conform to the uncured material acceptance test data properties and the cured material acceptance test data properties shown in reference 5. Table 2. Cured Material Physical and Mechanical Properties of Carbon Phenolic (At Room Temperature Unless Otherwise Specified) Property Limits Minimum Maximum Density, grams per cubic centimeter (g/cc) Resin content, percent Compressive strength, psi (edgewise) warp direction fill direction Interlaminar double shear strength, psi Thermal conductivity, Btu/ft-hr-degrees F at 250 deg. F across ply with ply Coefficient of thermal expansion in/in-degrees F x 10 exp -6 at 400 deg. F across ply with ply Flexural strength, psi warp direction fill direction Tensile strength, psi (edgewise) warp direction fill direction 1.4 30.0 25,000 20,000 3,500 0.10 0.10 5.0 2.0 25,000 20,000 15,000 10,000 1.52 38.5 65,000 55,000 8,000 1.1 1.1 20.0 9.0 55,000 55,000 40,000 35,000 Silica Cloth Phenolic: The silica cloth phenolic shown in Figure 2 is also used to provide structural integrity, a corrosion barrier, and insulation. It is fabricated in a manner similar to that of carbon cloth phenolic. The product should conform to the uncured material acceptance test data properties and the cured material acceptance test data properties shown in reference 6. The silica cloth phenolic is a higher purity material than the glass cloth phenolic, and is only used in the cowl ring. Nozzle Ablative Composites Fabrication: The fabrication process for the components of the nozzle includes two tape wrappings and two machining operations. Because of the sensitive variables occurring during tape wrapping of the prepreg tape, a highly skilled operator is required who understands what is required when one of the variables changes. The critical manufacturing variables are heat input, cooling input, roller pressure, machine speed, and tape tension. There are many other random variables that play a less significant role. The material is wrapped onto a mandrel which has been machined to the desired contour of the component as specified in the manufacturing plan. Depending upon the component location, the first wrap could be either bias-cut carbon cloth phenolic, glass cloth phenolic, or silica cloth phenolic tape wrapped on the mandrel at a specified angle (which depends upon the nozzle component) to the centerline of the nozzle. Enough tape should be wrapped to provide machining stock and tag ends after cure. The tape wrapping process places the tape at the proper angle and debulks the tape material to minimize movement of the tape during cure. Debulking of the tape should be achieved by applying heat and pressure at the point of contact with the mandrel or the previous ply. Heat should be applied prior to wrapping to make the tape tacky. The pressure roller forces the fibers to nest and compact (debulk) within the resin/fabric matrix. CO2 is used to cool the resin to stop further cure, and dimensionally and thermally stabilizes the billet for further processing. All ablative components are cured in a hydroclave except the aft exit cone, outer boot ring, and the cowl, which are cured in an autoclave. After wrapping, the billet and mandrel are vacuum bagged for waterproofing, then installed in a hydroclave for final cure. Curing of the carbon-cloth liner requires a pressure of 1000 psi at 310 deg. F for a minimum of five hours. After the cure cycle, a test ring should be removed and tested to verify the properties of the cured carbon cloth phenolic. The carbon cloth is then machined to configuration. In preparation for the second wrap, a coat of phenolic resin is applied to the machined surface of the first layer of phenolic. The second layer of phenolic tape is wrapped at the desired angle to the nozzle centerline using the same process as described for the carbon-cloth phenolic. The component is vacuum bagged and cured in an autoclave at 250 psi at a temperature of 310 deg. F for approximately four hours. Carbon and glass rings should be removed and tested to verify properties of the cure. The billet is final machined, removed from the mandrel and x-rayed to verify absence of voids, delaminations and low density indications. Following x-ray, the machined component is ready for bonding to the metal housings. Bonding of the machined ablative component to the metal housing is accomplished in a clean environment and requires strict process control. Inspection, Destructive, And Non-Destructive Evaluation: A very important development in nondestructive testing that promises to help maintain the meticulous cleanliness required to ensure bonding of composites to adjacent metallic structures is computer controlled scanning of the metal surface with devices based on Optically Stimulated Electron Emission (OSEE) principle. Computer controlled contamination scanning (CONSCAN) is a system developed by MSFC using the OSEE technique for automated scanning of metal surfaces prior to critical bonding operations. The CONSCAN system provides the sensitivity and spacial resolution necessary when scanning large areas to ensure that surfaces are sufficiently free of contaminants that reduce bond strength. Scanning the surface with CONSCAN provides a map of surface contamination levels, which clearly identifies those areas that require further cleaning. Rescanning after the additional cleaning operation provides results of that recleaning. These data provide a permanent record of surface cleanliness levels. The data records may be used at a later date to help identify the specific process during which contamination occurred and to correlate surface cleanliness levels with subsequent debond locations. The carbon cloth prepreg, glass cloth prepreg, and silica cloth prepreg should be visually inspected to ensure that there are no broken fibers, voids, or lack of resin or filler. Coupons of these materials should also be tested to verify uncured and cured properties. After final machining of both glass cloth and carbon cloth wraps, the materials should be x-rayed to verify absence of voids, delaminations, and low density areas. Defects of this type may be cause for rejection and scrappage. An alcohol wipe may be performed on the finished surface. Collection of alcohol in a spot or line before drying, will indicate a crevice or void in the surface. The x-ray technician should be highly skilled in taking and reading the x-rays to avoid scrapping an expensive component due to erroneous low density indications. Low density indications could be caused by fiber ends not being flush with next butt end and the gap being filled with resin and filler, density variations, and interlaminar resin-rich areas. The tag ends and rings removed after curing should be used to verify mechanical properties. Tag ends and rings could also be used for plasma torch testing to verify the erosion rate and the factor of safety. Technical Rationale: Precision design and manufacturing procedures for ablative material for solid rocket motor nozzles have been developed over a period of 30 years. The design of the ablative material depends upon factors such as the solid propellant composition; combustion gas temperature, velocity and composition; and relative position of the material in the nozzle. Problems that have surfaced over the years were analyzed, improvements proposed; and, when approved through the NASA change board process, were designed, prototyped, ground tested and flown. Information for this practice was derived from a number of sources, including procurement specifications and manufacturing plans for the SRM and RSRM experimental studies, problem reporting and corrective action (PRACA) reports at MSFC, AIAA reports, and from personal interviews and telephone interviews with individuals from MSFC organizations and contractor organizations. References: Hall, William B.: quotStandardization of the Carbon-Phenolic Materials and Processes, Volume I, Experimental Studies,quot Professor of Chemical Engineering, Mississippi State University, August 31, 1988. Kelly, P. and Thompson, A.: quotAIAA 89-2661 Low Density Indications in Radiographs of Solid Rocket Motor Ablatives,quot 25th Joint Propulsion Conference, Morton Thiokol Inc., July 10-12, 1989. TWR-10341 (CD) Rev. D: quotManufacturing Plan for Space Shuttle Redesigned Solid Rocket Motor Project,quot Prepared by Morton Thiokol Inc., Manufacturing Engineering, NASA Contract NAS8-30490. TWR-10341 (CD) Rev C: quotManufacturing Plan for Space Shuttle Redesigned Solid Rocket Motor Project,quot Prepared by Morton Thiokol Inc., Manufacturing Engineering, NASA Contract NAS8-30490. STW5-2651F: quotGlass Cloth Phenolic, Preimpregnated Specifications,quot Morton Thiokol Inc., May 5, 1987. STW5-2652E: quotSilica Cloth Phenolic, Preimpregnated Specification,quot Morton Thiokol, Inc., August 13, 1987. STW5-3279A: quotCarbon Cloth Phenolic, Preimpregnated Specification,quot Morton Thiokol, Inc., May 8, 1987. MSFC: quotProblem Reporting and Corrective Action (PRACA) Systems,quot Run Dated Nov. 1, 1991, PRACA Record Numbers A07293, A08066, A09099, A11024, A11356, A11466, A12155, A12234, A12235, A12242, A12430, A12438, A13394, A09676, A09677, A10979, A11854, A11855, A11054, A11076, A11108, A11133, A11182, A11659, A11686, A12979, A13812. Nichols, R. L.: Solid Propulsion Integrity Program (improvements made through this program), ER41 Solid Propulsion Research and Technology Office, Marshall Space Flight Center, AL. Sutton and Ross: quotRocket Propulsion Elements,quot Fourth Edition, Wiley and Sons. Proceedings of Rocket Technology Subcommittees of The Chemical Propulsion Information Agency, 1989, 1990, 1991. | This practice has been used on Mariner Mars 64, Voyager, Galileo, Ulysses. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/08/2000
670 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Contamination Control Program |  | Instruments may not be capable of meeting their sensitivity, resolution, and other performance requirements if critical surfaces and components are not adequately protected from particulate and molecular contamination that can condense on cold optics and other components. | Apply a Contamination Control Program to those spacecraft projects involving scientific instruments which have stringent cleanliness level requirements. | GSFC | 02/01/1999 | This Lesson Learned is based on Reliability Practice Number PD-ED-1233 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: This practice enables spacecraft to meet these stringent cleanliness level requirements of state-of-the-art scientific instruments. It also serves to maintain the inherent efficiency and reliability of the instrument by minimizing degradation of critical surfaces and sensors due to undesired condensation of molecular and accumulation of particulate contamination layers. Implementation Method: General This Contamination Control Program and a number of its supporting technologies were developed to meet the stringent cleanliness specifications of the COBE state-of-the-art scientific instruments. These instruments operated at temperatures below 2 degrees Kelvin inside a dewar and required the most stringent surface level cleanliness specifications ever attempted by GSFC and perhaps NASA. These low temperatures required innovative contamination control measures to prevent condensation of outgassing materials on critical cold optical and non-optical surfaces. This program as defined in the following begins with the early design phases where cleanliness specifications are established and continues through the entire flight program where contamination of flight hardware is monitored and controlled from fabrication through integration and testing, transportation to and handling at the launch site, and the launch and early orbit phases as appropriate. The COBE stringent cleanliness specifications were initially met and maintained. Early observations from COBE show that the instruments are operating nominally. Optical scattering, principally caused by particulate and molecular contamination, is an order of magnitude smaller than originally budgeted with the spacecraft's contamination specifications. Cleanliness Specifications Establish cleanliness specifications during the early design phases. The most stringent cleanliness specifications are established as required for critical surfaces, usually cold surfaces such as optical surfaces, apertures, forebaffles, detectors, etc. These specifications are usually based on theoretical instrument performance degradation studies, contamination data from previous spacecraft missions, and in some cases from the space environment where cold optics can be coated with molecular layers of contamination from high-energy atomic oxygen bombardment or particulate contamination from micrometeoroid collisions with the spacecraft. Less stringent contamination specification requirements are established for less critical spacecraft and instrument surfaces and components. Stringent cleanliness specifications usually require the design of special contamination control domes and covers to protect critical surfaces during spacecraft qualification testing, transportation to and preparations for launch at the launch site, and during the launch and early orbital outgassing period. These domes and covers are deployed or detached from the spacecraft during the early orbits. Where appropriate, special instrumentation such as scatterometers or quartz crystal microbalances (QCM) are incorporated into the design of instruments to monitor contamination of critical surfaces or areas generated during spacecraft testing and launch activities. Selection and Testing of Materials Material selected for use in flight hardware is tested for its outgassing properties in accordance with ASTM E-595-77/84. Only materials that meet the criteria of ASTM E-595-77/84 [i.e., have a total mass loss (TML) < 1.0% and a collected volatile condensable mass (CVCM) <0.10%] are approved for use in a space environment. Instruments with more stringent contamination control specifications may require more stringent material selection criteria. Refer to related Reliability Preferred Practice No. PT-TE-1410, Selection of Spacecraft Materials and Supporting Vacuum Outgassing Data, for additional information on material selection and supporting vacuum outgassing data. Maintaining Clean Surfaces Spacecraft surface cleanliness levels are maintained throughout fabrication, integration, environmental qualification, and launch operations. These cleanliness levels are achieved through initial component level cleaning in a precision cleaning facility along with routine cleaning of the entire spacecraft. The cleaning facility is a 10,000 or better laminar-flow clean tent or clean-room equipped with an exhaust bench for chemical cleaning, an ultrasonic cleaning station, and contamination inspection stations. Standard cleaning procedures include a combination of thermal bakeouts, solvent rising, vacuuming, gaseous nitrogen blasting, vibration testing, and ultrasonic techniques. Flight components are required to undergo a thermal bakeout to reduce potential contamination due to outgassing. The following three inspection techniques are used to verify levels of cleanliness of flight hardware. First, the component is visually inspected using a minimum 100 footcandle intensity white light and a long wave black light to determine the presence of molecular and particular contamination. Second, tape lift samples are taken and analyzed to provide a statistical estimate of the total number and size distribution of particles per square foot present on the test sample. Third, molecular contamination levels are verified by analyzing a solvent wash using infrared and mass spectrometry techniques. These analyses verify that contaminants are within specified limits and provide data to help pinpoint the source of contaminant and whether material substitutions should be made. Contamination Control Procedures Special contamination control procedures are followed during component, subsystem, and spacecraft level flight environmental qualification test programs. These tests include thermal vacuum cycling, three axis vibration, acoustic bombardment, microphonics, and electromagnetic compatibility. Each test presents its own challenge for cleanliness control. An additional challenge is the transportation of the flight hardware from one test chamber or test facility to the next one. Each test chamber or test facility should be capable of maintaining a Class 10,000 or better environment and all test equipment and test fixturing brought into the test chamber or test facility is cleaned according to strict project procedures. During moves between test chambers or test facilities, the flight hardware is double bagged in clean antistatic nylon film. Once inside the clean area, the outer bag is removed and the environment is stabilized prior to removing the inner bag and exposing the flight hardware. If the test chamber or test facility is not a cleanroom, the bags remain on the flight hardware throughout the test. The bags are purged with Class 100 air conditioned atmospheric air to maintain thermal specifications on the flight hardware. A primary contamination control objective during thermal vacuum testing is to determine the possibility of the spacecraft self-contaminating its instruments during either launch or on-orbit. Secondary objectives are to (1) bake out the entire spacecraft during the first three days of hot-soak conditions, (2) measure the amount of condensed contamination throughout each phase of the test, and (3) determine the chemical makeup of the residue collected on cold surfaces in the chamber. This data is combined with a statistical on-orbit outgassing model of the spacecraft to determine an optimum outgassing period prior to deploying or removing contamination control covers from critical hardware. Contamination monitoring techniques used in the thermal vacuum testing include (1) the placement of quartz crystal microbalances around the spacecraft to provide a real-time means of measuring the quantity of outgassing contaminates throughout the testing, (2) the use of a residual gas analyzer to measure the types and quantity of gas molecules and their outgassing rates. Cold fingers, scavenger plates, and witness mirrors are used to collect contaminates that will condense on critical surfaces. The contaminates are analyzed using infrared and spectrometer techniques to identify the outgassing materials and their quantities. Primary contamination control objectives during vibration/acoustic testing are (1) to measure the generated debris and spacecraft self-contamination, (2) to analyze the effectiveness of contamination control covers, and (3) to assess the possibility of debris created during the launch reaching critical instrument surfaces. Contamination is monitored by placing witness plates containing nylon disks coated with transfer adhesive at critical locations usually at the same locations as the witness mirrors used in the thermal vacuum testing. The witness plates collect debris which is analyzed to identify the type and quantity of debris at the various locations of interest. In addition many tape-lift samples are taken at various locations. These samples can show the source and migration of debris. One source of debris generation that has been identified by this technique is scraping interaction between hardware. The problem is corrected by either separating the hardware or by installing an isolating layer of nylon or teflon material to provide a smooth surface that will not shed during launch. Contamination Control During Transport The spacecraft is transported to the launch site in a specially designed and built trailer to control the temperature, pressure, humidity, and cleanliness of the environment while protecting it from induced vibrations and stresses. The filtration system used in the transporter enables the pressure to stabilize at equilibrium during both takeoff and landing of transport aircraft. The spacecraft is completely covered and sealed inside two specially constructed Llumalloy-HSC bags prior to mounting the spacecraft inside an outer hard box which is a part of the transporter system. The acceptance tests of the bags include particle counts, tapelift samples, and rinse residue tests to ensure that the bags meet the project contamination specifications. A breathable air purge line equipped with a desiccant and a 2 micron particulate filter is inserted into the inner bag to provide positive pressure between the inner bags and the outer box. A thick outer bag equipped with three High Efficiency Particle Air (HEPA) filters is then placed around the double-bagged spacecraft and supported by a cage to add further weather protection. The HEPA filters protect the spacecraft from the incoming air supplied by a HVAC system which consists of dual air conditioner and heaters powered by diesel generators. The HEPA filter system and the outer bag ensure a less than Class 1000 environment around the spacecraft during transportation. Contamination measurements are again taken when the spacecraft is unbagged at the launch site to verify surface cleanliness levels. Contamination Control at the Launch Site At the launch site the spacecraft is placed inside a laminar-flow clean room or tent ranging between Class 100 to Class 1000 for final integration and launch preparations. The launch gantry which may have normal contamination levels of Class 100,000 must be carefully cleaned so as to lower the contamination levels to Class 10,000. The fairing of the launch vehicle is submitted to the same contamination levels and inspection techniques as the external surfaces of the spacecraft. The spacecraft is double bagged and purged with Grade C gaseous nitrogen during transportation to the gantry. The purge is then changed to conditioned air. The clean bags and the purge remain until just before the fairing is installed. A "shower" cap can be installed over the spacecraft to protect exposed instruments and dewars until the second half of the fairing is installed. Once the fairing is installed, an air-conditioned line containing a HEPA filter to maintain Class 100 air is connected. The air flow inside the fairing is sampled for 20 minute time periods to measure the air quality around the exposed spacecraft. Technical Rationale: A variety of instruments including the three state-of-the-art instruments flown on the COBE spacecraft require stringent surface level cleanliness control to protect critical surfaces and components from particulate and molecular contamination. The diffuse infrared background experiment (DIRBE) and the differential microwave radiometer experiment (FIRAS) flown on COBE operate at temperatures below 2 degrees Kelvin (-456.07 degrees F) inside the dewar. This requires stringent contamination control to prevent condensation of outgassing materials on critical cold optical components. The FIRAS is a modified Michelson interferometer that operates in the wavelength range from 0.1 to 10 mm to determine the spectrum of the cosmic background radiation. It utilizes a polished aluminum input skyhorn to direct cosmic radiation into the optical system. Particulate or molecular contamination in excess of level 300A would decrease off-axis rejection performance of the skyhorn and possibly destroy tiny elements inside the bolometer detectors. The DIRBE measures diffuse galactic radiation in the wavelength range from 1 to 300 microns. The first optical element in this off-axis Gregorian system is a super polished, gold-coated aluminum parabolic mirror that was cleaned and maintained at level 100A to minimize radiation scattering. The differential microwave radiometer instrument (DMR) flown on COBE has three individual receiver heads positioned around the periphery of the dewar to determine whether the cosmic background radiation is equally bright in all directions. The DMR antennas operate at wavelengths of 3.3, 5.7, and 9.6 millimeters, respectively to map the entire sky. The internal surfaces of the corrugated horns were protected from particulate contamination at all times to preserve the cleanliness of the horn throats and the switching mechanism that is used to calibrate each receiver on orbit. A particle of 80 microns in length would cause blockage in the horns and interrupt signal throughput. References: Barney, Richard D., "Contamination Control Program for the Cosmic Background Explorer", Journal of the IES, March/April 1991. "Selection of Spacecraft Materials and Supporting Vacuum Outgassing Data," Reliability Preferred Practice PT-TE-1410. | This practice has been used on Cosmic Background Explorer (COBE) and Extreme Ultraviolet Explorer (EUVE). | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/08/2000
671 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Demagnetization of Ferromagnetic Parts | Preferred Practice for Design & Test. External magnetic fields produced by spacecraft assemblies and subsystems can result in the contamination of science magnetometer data and the distortion of plasma wave and charged particle measurements. Also, on Earth orbiting and Jovian missions, the interaction of spacecraft dipole moments and the ambient field can result in disturbance torques that adversely affect attitude control systems. In those cases where the use of ferromagnetic material cannot be avoided, perform a complete demagnetization of the ferromagnetic parts, individually, prior to assembly. | Impact of Nonpractice: External magnetic fields produced by spacecraft assemblies and subsystems can result in the contamination of science magnetometer data and the distortion of plasma wave and charged particle measurements. On Earth orbiting and Jovian missions, the interaction of spacecraft dipole moments and the ambient field can result in disturbance torques which adversely affect attitude control systems. | Practice: In those cases where spacecraft science requirements or attitude control systems impose constraints on the magnetic characteristics of components and the use of ferromagnetic material cannot be avoided, perform a complete demagnetization of the ferromagnetic parts, individually, prior to assembly. | JPL | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1220; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: In an unassembled state, ferromagnetic parts can be exposed to stronger AC demagnetizing fields, as high as 60 mT (600 Gauss), thus assuring a lower level of remanent magnetization than can be achieved after the parts are mounted on assemblies. Attaining a low level of remanent magnetization minimizes the adverse effects of unwanted fields. In those cases where magnetic compensation may be required, the ability to apply high level fields to an unmounted part enables the utilization of techniques to stabilize the magnetic moment of the part. Implementation Method: The part being demagnetized is placed in a controlled AC magnetic field and rotated on all three of its axes as the field is exponentially increased and then returned exponentially to its lowest level. During this process, the ambient magnetic field must be reduced to near zero intensity (< 500 nT) while the parts are being demagnetized. This condition can be established either through the use of a triaxial coil system, to generate nulling fields, or by placing the parts in a magnetically shielded container. Effective demagnetization cannot be achieved in the presence of the earth's field (0.05 mT) because a significant number of magnetic domains will remain aligned along the ambient field vector and result in a residual dipole moment. After the demagnetization process is completed, the part and the assembly to which it is mounted should not be exposed to magnetic fields in excess of 2 mT. This control assures that any subsequent demagnetization of the assembly at 5 mT will be adequate. The size and configuration of the demagnetizing coil may vary depending upon the specific parts being treated. However, in most cases, a simple solenoid provides the adequate flexibility for such items as connectors, fasteners, and small parts. In some cases a commercial 60 Hz magnetic tape degausser can be used. For a solenoid, the wire size and number of turns are determined by the size of the AC source (voltage and current capacity). Series capacitors are used to tune the coil for resonance. The physical access to the center of the solenoid must be adequate to allow for the rotation of the part on all three of its axes while exposed to the demagnetizing field. At JPL two systems are in use to provide a near zero static magnetic field environment for high level demagnetization. For smaller test items, a double walled mumetal shield can, approximately 60 cm in diameter and 120 cm long, is used. Within the shield can, the AC demagnetizing field is generated by a solenoid. Larger test items are treated in a zero DC environment produced by a triaxial Helmholtz coil system having a maximum diameter of 3.6 meters. AC fields up to 10 mT are generated by a coil pair 2 meters in diameter contained within the triaxial system. Other demagnetizing solenoids and coils available for use include the following: 14 cm i.d. coil 42 cm i.d. coil 60 cm i.d. solenoid 116 cm i.d. Helmholtz Max. Field1 60 mT 50 mT 24 mT 0.6 mT Wire Size 20 AWG 20 AWG 10 AWG 10 AWG Windings 1 2 3 2/coil Turns 1600 1368 426 58/coil Ohms/Winding 30.5 25.7 3.1 0.8 L/Winding 506 mH 100 mH 57.5 mH 9.6 mH Series Capacitance 14 uf 80 uf 14 uf — Coil Construction 10 mT/amp 2.8 mT/amp 1.2 mT/amp .08 mT/amp Weight 4.5 kg 10 kg 5.3 kg 58 kg 1 230 volts at 60 Hz Technical Rationale: Ferromagnetic materials, such as the alloys of nickel and cobalt, are of concern because they exhibit hysteresis and have permeabilities which are dependent upon the ambient field strength and temperature. Parts made of these materials exhibit dipole moments which can create disturbance torques and also produce unwanted external magnetic fields. The demagnetization process has either of two objectives: first, to reduce the remanent dipole moment to its lowest practical level or second, to stabilize the moment with respect to the expected environmental extremes for temperature and field exposure. Because of the potential adverse effects of strong magnetic fields on electronic components, spacecraft assemblies are not exposed to demagnetizing fields in excess of 5 mT (50 Gauss). This level of demagnetizing field is based on the conservative assumption that the spacecraft hardware will not be exposed to magnetizing fields in excess of 1-2 mT. Frequently, in the process of fabrication, parts made of ferromagnetic materials are exposed to magnetic fields far in excess of 1-2 mT and, in some cases, are received in a saturated state. Ideally, the demagnetization process should remove the saturated remanence by a complete randomization of the domains in the material. However this typically requires a much higher field intensity than the 5 mT demagnetization field used on completed assemblies and subsystems. In those cases where demagnetization is not adequate, the magnetic moment of the part must be stabilized and compensation obtained through the addition of an equal but oppositely directed dipole moment (a permanent magnet). For this technique to be effective a strong magnetizing field must be applied to make sure that the ferromagnetic part is in a saturated state prior to compensation. This would not be practical to do with the part installed on a completed assembly. References: "Magnetic Field Restraints For Spacecraft Systems And Subsystems", N68-11295, Goddard Space Flight Center, Greenbelt, Maryland, February 1967 | This practice has been used on Mariner Mars 64, Voyager, Galileo, Ulysses. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/08/2000
669 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Structural Laminate Composites for Space Applications |  | Impact of Nonpractice: Failure to adhere to proven and acceptable practices in the design, manufacture, and testing of structural laminate composites will result in an unacceptably high rejection rate of fabricated composite parts. This rejection rate could be caused by unacceptable structural strength, delaminations, excessive (or inadequate) porosity, surface defects, inclusions, improper dimensions, or inadequate physical, thermal, or chemical properties as revealed in nondestructive testing or in destructive coupon testing. A high rejection rate could cause delays in the vehicle assembly, testing, and checkout process, and could possibly affect the launch schedule. Increased costs of manufacture would also result from a high rejection rate. | Practice: The creation of reliable structural laminate composites for space applications requires precision design and manufacturing using an integrated, concurrent engineering approach. Since the final material characteristics are established at the same time the part or subassembly is fabricated, part design, fabrication development, and material characterization must proceed concurrently. Because composite materials are custom-tailored to meet structural requirements of the assembly, stringent in-process controls are required to arrive at a configuration with optimum physical and material properties. | MSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1217; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Conscientious adherence to proven procedures in the design, manufacture, and test of aerospace structural composites will result in low rejection rates and high product integrity. In specific applications, successful composite design provides design flexibility, increased strength to weight ratio, dimensional stability under thermal loading, light weight, ease of fabrication and installation, corrosion resistance, impact resistance, high fatigue strength (compared to metal structures with the same dimensions), and product simplicity when compared to conventional fabricated metal structures. Implementation Method: Design Practices. The most important concept in deriving acceptable structural laminate composite parts is the multidisciplinary approach to design wherein the material composition, filament orientation, and fabrication procedures are custom tailored to the specific part configuration. From the beginning of design analysis to the completion and flight of composite components, the integration of material structure and formulation with configuration and environmental considerations is essential. More than in any other product manufacturing discipline, composite development requires the designer to simultaneously consider the following: configuration, operational environment, tooling, quality, reliability, safety, nondestructive evaluation, and material characteristics. The physical properties of structural laminate composites tend to deteriorate due to environmental conditions after manufacturing. Therefore, design requirements must include, to a greater degree than in conventional structures, the operational environment (transportation, prelaunch, launch) and the storage environment. The matrix or binder composition, filament composition and form, and the specific manufacturing procedures used will heavily influence the acceptability of the final integrated unit. Since the structural properties of the material are so strongly dependent upon the part fabrication process and tooling, design of the part and tooling configuration must be concurrent. This principle can be seen by comparing the conventional metals design, manufacturing, and testing procedure (Figure 1) with the corresponding cycle for structural laminate composites (Figure 2). [D] Figure 2 illustrates two important points: (1) part design and tool design go hand-in-hand; and (2) the manufacturing and fabrication process includes simultaneous production of the composite and fabrication of the structure. For structural space applications, composites must be designed properly and built properly. An important example of the need for laminate-unique considerations in the design process is that the design of the part and its manufacturing tooling include tag ends or trim area that must be removed and subjected to acceptance testing. It is common practice to use a safety factor of 1.5 for structural laminate composites. A safety factor of 2.0 is recommended for the materials located around fasteners. [D] The structural strength of the final design is dependent upon filament strength, matrix or resin strength, and fiber orientation (which should generally be in the direction of the applied force). The strength of the part is based on the interaction of fiber and matrix in a process that depends upon ply or layer thicknesses and percent of fiber volume. Typical fiber tensile strengths range from 200,000 to 800,000 psi while matrix tensile strengths range from 2000 to 5000 psi. When these two elements are combined into a graphite epoxy structural laminate, a composite tensile strength close to 98 percent of the uniaxial fiber strength is achievable. Part design must include the evaluation of coupon, section, and prototype tests in order to assure that part configuration/material interactions are taken into account in the final configuration. Structural algorithms using finite element methods are used early in the design process, and these are supplemented by results from tests of prototype parts. Graphite epoxy composite materials exhibit stress-strain relationships with less than 2 percent elongation and without the usual elastic-plastic behavior of metals. Where metals usually require only two design properties, modulus and Poisson's ratio, composite design will require five or more distinct directional variations of these properties. Thermal expansion properties can be designed so that zero expansion may be achieved, such as for optical benches. The resin used to bind the composite materials can typically absorb up to 5 percent by weight of water, which can affect dimensional stability of the composites. Ultraviolet radiation and atomic oxygen in space will increase aging and thereby decrease service life of the composite when left unprotected. This iterative and integral design process will ensure a successful structural laminate composite part or assembly design. Manufacturing Practices. The matrices and fibers for structural laminate composites can be applied to a mold sequentially or the filament can be preimpregnated with the matrix material. The latter is the more common practice for aerospace structural laminates. Developing the correct process flow prior to production is crucial to modern composite manufacturing. Critical factors in the manual or automated lay-up of composites are the indexing or orientation of the filament and the sequencing of layer application. Curing temperature, pressure, and ramp rates are critical as they affect the degree of cross-linking of the polymers in the matrix material, adhesion to the filaments, porosity, filament spacing, and resulting overall strength and integrity of the final part. Lifetime of preimpregnated materials is an important consideration because acceptable properties can only be maintained for ten days to one month at room temperature or a material-dependent range of six months to two years in cold storage. Timing of the preimpregnation process, therefore, is a critical factor in the planning of the manufacturing process. The manufacturing environment (humidity, temperature, and cleanliness) and the manufacturing process itself must be closely controlled to produce consistently acceptable products. Automation using statistical process control of composite fabrication methods may be the single most important advancement needed to foster the use of composites for aerospace applications. Testing and Nondestructive Evaluation Practices. Integral to the successful manufacturing process for aerospace structural laminates is the need for 100 percent in-process inspection, nondestructive testing, and coupon testing during the initial manufacturing phase. As inspection records are built up, the inspection requirements are reduced until only the problem areas are checked on each component. These problem areas should be defined by production results, design engineers, materials and process engineers, and shop fabricators. Early in the manufacturing process, filaments should be tested for tensile strength, strain rate, modulus of elasticity, density, diameter, stiffness, and surface morphology. Matrix rheology and mechanical performance must be characterized through chemical and physical testing. The preimpregnated material should be tested for resin content, flow rate, volatile content, tackiness, tack retention, and gel time. Filament count, filament spacing, drapability, and temperature exposure tests should also be conducted on the preimpregnated material. Coupons should be fabricated for each part to permit destructive tests (thermal, chemical, and structural) of the material which represents as closely as possible that which is included in the fabricated part. Wherever possible, part extensions should be trimmed off and tested to determine if the material meets strength, chemical, and thermal requirements. The final cured laminate composites should be tested for longitudinal compressive strength, longitudinal and transverse flex strength, longitudinal and transverse tensile strength, longitudinal and transverse shear strength, impact testing, and compression testing after impact testing. Nondestructive testing methods that may be used to verify absences of voids, delaminations, and low density areas are radiography, ultrasonics, thermography, eddy current, and acoustic emissions. Nondestructive tests that may be used to verify cleanliness for bonding composites to adjacent metallic structures are Fourier Transform Infra Red (FTIR) spectroscopy, Non-Volatile Residue (NVR) analysis, X-ray Florescence (XRF), and Ellipsometry. Nondestructive evaluation is an important inspection technique for determining defects without destroying the component. The typical evaluation (NDE) technique for detecting defects in composites are shown in Table 1. Development of accept/reject criteria should be accomplished during the manufacturing and testing phase prior to production phase of the composite component. Technical Rationale: Experience with structural laminate composites on the Space Shuttle External Tank, Space Shuttle Solid Rocket Motor Filament wound case, Advanced X-ray Astrophysics Facility, Solar X-ray Telescope, International Space Station, and related composite applied research and product improvement projects has included experience with graphite/phenolics, glass/phenolics, graphite/epoxies, and graphite/bismalemides. Table 1. NDE Techniques for Detecting Defects in Composite Materials Defect Composite Method X-Ray Ultrasonics Computer Tomography Alcohol Wipe Thermography Eddy Current Dye Penetrant Delaminations X X X X X Density Variations X X Resin Rich/ Resin Poor X X Voids X X X Crazing (Microcracks) X X X Wrinkles X X Conductive Materials X Both woven fabric and tape forms have been used as reinforcing materials. Research and applications of composite materials at MSFC and by its prime contractors and subcontractors have included many other types and applications of composites. Several of these, such as filament winding, and pultrusion, fiber placement, and automated tape laying, are being considered for future design practices. Since knowledge of structural graphite epoxy composites is constantly expanding, this practice may also be updated in the future to reflect emerging advancements. References: Agarwal, Bhagwan D. and Lawrence J. Broutman, Analysis and Performance of Fiber Composites, Second Edition, Wiley, New York, 1990. Dow, Marvin B., quotThe ACEE Program and Basic Composites Research at Langley Research Centerquot (1975 to 1986), NASA Reference Publication #1177, October 1987. quotDOD/NASA Structural Composites Fabrication Guide,quot Lockheed-Georgia Company, Air Force Materials Laboratory, Wright-Patterson Air Force Base, Ohio, 1979. Gause, Dr. Raymond L., quotA Noncontacting Scanning Photoelectron Emission Technique for Bonding Surface Cleanliness Inspection,quot NASA Technical Memorandum #100361, George C. Marshall Space Flight Center, February 1989. Jones, Robert M., Mechanics of Composite Materials, McGraw-Hill, 1975. quotPlastics for Aerospace Vehicles: Part I. Reinforced Plastics,quot Military Handbook 17A, Department of Defense, Washington, D.C., 1971. Schneider, Cecil W., quotLessons Learned on Composite Production Programs,quot Lockheed Aeronautical Systems Company, Marietta, GA, December 1991. Strong, Dr. A. Brent, quotFundamentals of Composites Manufacturing,quot First Edition, Society of Manufacturing Engineers, 1989. quotSpace Shuttle External Tank: Final Report,quot Composite Technology Group, Martin Marietta Michoud Division, 1984. | This practice has been used on Space Shuttle External Tank Composite Application Program, Space Shuttle Solid Rocket Motor filament wound case program, Advanced X-ray Astrophysics Facility (AXAF), Solar X-ray Telescope (SXT), Space Station Freedom, Solar X-ray Imager (SXI) and related composite applied research and product improvement projects. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/07/2000
667 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Common Review Methods for Engineering Products | Preferred Practice for Design & Test. Lacking clear standards for project and task review, and failing to conduct detailed technical reviews (DTRs) beforehand, design reviews have a tendency to emphasize formality and “packaging” at the expense of substantive assessment of content and depth of analysis. Conduct technical reviews to validate engineering designs using a common, consistent approach that has been proven to lead to reliable and quality products. These practices provide a common framework for planning, conducting, documenting, and evaluating the review process. | Impact of Non-Practice: Lacking clear standards for project and task review, and failing to conduct detailed technical reviews (DTRs) beforehand, design reviews have a tendency to emphasize formality and quotpackagingquot at the expense of substantive assessment of content and depth of analysis. | Practice: Conduct technical reviews to validate engineering designs using a common, consistent approach which has been proven to lead to reliable and quality products. A technical review is an evaluation of the engineering status of products and processes by an independent group of knowledgeable people. Although major technical reviews for a project differ in their content and timing, there are practices common to most reviews which may be defined to assure review success. These practices provide a common framework for planning, conducting, documenting, and evaluating the review process. | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1215.4; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Standards established for common review methods are presently supporting reliability assurance by emphasizing early detection and correction of deficiencies through the increased use of working level, peer reviews (detailed technical reviews) in preparation for major design reviews. The standards also assure that reviews are scaled in accordance with criticality, complexity, and risk, and that the review process is optimized to produce results of value to the mission. Implementation Method: The definition of common review methods essential to successful reviews reflects a need for effective planning and management of all technical reviews. Figure 1 provides an overview of the review process for a project responsible for an engineering product. The oval-shaped processes in Figure 1 are expanded in Figures 2 and 3. Review Planning: Review planning helps to ensure that the sponsoring organization is well prepared and that the anticipated results justify the significant resources to be expended in the review. The project (or task) manager prepares a review plan identifying the reviews to be held at the project, system and subsystem levels; their relationships to each other; when the reviews are to be held; and their major objectives. A carefully prepared, detailed statement of the objectives of the review and the success criteria for the product being reviewed provides the essential focus for the review process. Although each review is a milestone visible to high-level management, a review should be rescheduled if the work is not sufficiently mature or the prerequisites are not met. [D] The project manager scales the structure and formality of the review to the significance, complexity, and risk of the product. For smaller projects, reviews may be combined or eliminated to achieve the benefits of review at minimum expense. Factors considered in the review plan include: Total project duration. The number and timing of reviews should conform to the project schedule, but can be modified to match changes in project duration. Reviews should be considered whenever the project enters a new phase (viz, preliminary design, detail design, system test) or following a major change in requirements or resources. Level of inheritance. Projects that use inherited designs, hardware, or software should subject the items to inheritance reviews. This review may sometimes be substituted for, or included within, a preliminary design review (PDR) or critical design review (CDR). Sponsor-imposed reviews. Specific reviews required by the sponsor should be incorporated into the internal review plan and not duplicated. External reviews, such as independent readiness reviews (IRRs) and independent annual reviews (IARs), should be identified in the review plan and consolidated with equivalent internal reviews. Technical Complexity. Complex tasks involving critical technology may require multiple subsystem reviews as well as system-level reviews, and high risk components may require a focus on risk assessment and mitigation. Management Complexity. Activities with complex interfaces external to the project or task, such as contractor oversight or inter-organizational agreements, may require additional (or more rigorous and structured) reviews. Fully contracted tasks should defer to the contractor's in-house review practices to the maximum extent possible. Experience has demonstrated that perfunctory preparation is a precursor to poor performance. The selection and commitment of the review board is crucial to the success of the review. The board membership and review scope are defined in a review board charter. Board members are selected for their ability to objectively evaluate the products and processes to be reviewed. The scope should include all relevant technical concerns and related cost considerations, but exclude management issues such as implementation plans, schedules, and work breakdown structures. The essential focus for the review process is provided by a carefully prepared, detailed statement of the review objectives and success criteria for the product under review. Review objectives are stated in terms of specific product features-- for example, quotdoes the design satisfy the requirement for the 20-Gbit/s imaging data stream to have a 1.5-ns response time?quot Success criteria define measures of product readiness required to proceed to the next development step; if these criteria are not met, the review must be repeated. Essential prerequisites to the review-- timely distribution of review material to participants and completion of analyses and tests-- are also defined in advance. Figure 2 illustrates the review preparation process. [D] As an aid to review planning, Table 1 provides a standard review checklist, with items listed in the order they are performed. REVIEW ACTIVITY LEAD PERSON Generate project review plan. Project Manager Establish and document charter. Convening authority Establish and document scope, objectives, success criteria, and prerequisites. Responsible individual Select review board. Convening authority, responsible individual Announce schedule and agenda. Responsible individual Prepare for review: Schedule conference room Arrange for audiovisual equipment and support, refreshments Identify presentation team Develop presentation guidelines Hold presenters' meeting Assemble material to be reviewed, and distribute material to bard Generate presentation and backup material Dry run or story board presentation Update, produce, and print presentation material, and distribute it to the board Prepare slides and transparencies, and distribute them to the presenters. Responsible individual Study material prior to review. Board members Conduct review. Board chair Conduct post-review meeting: Identify key findings and recommendations Develop board consensus Draft board report. Board chair Consolidate and filter recommendations for action (RFAs) Board chair, responsible individual Accept RFAs as action items, advisories, or rejected items Identify critical action items. Responsible individual Complete and issue final board report. Board chair Submit metrics to the Office of Engineering and Mission Assurance. Responsible individual Prepare and issue RFA disposition plan. Responsible individual Approve disposition plan. Convening authority Approve action item closures. Responsible individual Review action item closures; provide feedback to responsible individual and convening authority. Board chair, selected board members Table 1. Standard Review Checklist Review Procedures: Reviews begin with the board chair's discussion of review objectives and instructions on desired audience participation, including who may generate a recommendation for action (RFA), and guidelines for keeping the review on schedule. The chair remains responsible for keeping the review within the scope, on the agenda, and on schedule. The goal of each presentation is to identify issues in the review to be solved outside of the review. Questions directed by the board members to the presenter should be phrased in an objective, neutral, and non-inquisitory manner addressing the product under review rather than the merits of the presenter. Once an issue has been sufficiently clarified, the chair summarizes the issue and assigns someone responsibility for writing an RFA. Presentations conclude with a summary of current work status, open issues and concerns, and future challenges. Effective resolution of technical issues by the review board requires prior analysis of design performance, including reliability, safety, security, and other product requirements. As a precursor to the design review, detailed technical reviews (DTRs) are recommended for important products to facilitate early detection and correction of design deficiencies. DTRs are informal, working-level, peer reviews intended to assess interface compatibility and to prevent propagation of deficiencies to later products. Like the formal design review to follow, organization of a DTR follows the steps of planning, scoping, team selection, materials distribution, conducting the meeting, and documentation of results. The primary differences are the greater technical depth provided by the DTR, the corresponding higher specialization of the small (commonly 2 to 3-person) review team, and the greater simplicity of the supporting documentation and reports. Review Follow-Up: A post-review board meeting is held to achieve consensus on key issues, findings, and recommendations. The board chair then consolidates all RFAs into a set of action items, which are filtered and prioritized to form the basis of the board's recommendations. A review board report is prepared listing the key findings and recommendations, any dissenting views, summary recommendations for action, and any advisories, actions items, and critical actions identified by the assigned responsible individual. The recommendations of the review board are advisory only, even though some projects may use the review results as the basis of their decision to proceed to the next step in product development. Figure 3 portrays the flow of review follow-up activities. Responsibility for tracking, resolution, and close out of action items rests with the responsible individual. After categorization of the board's recommendations into accepted action items, advisories, or rejected items, and an assessment of their criticality, this person submits a board recommendation disposition plan to the board chair for comment and to the convening authority for approval. Following each review, the responsible individual and the board chair provide metrics to the JPL Office of Engineering and Mission Assurance. These data on the cost, results, and identified benefits of the review are used to evaluate the annual trends of the JPL-wide review process as one aid to continuous improvement. [D] The review process concludes with the action item assignees completing their assigned actions and documenting the recommendations for action item closure. The responsible individual approves the written closures and distributes them to the convening authority and the review board members. Rationale: Experience has shown that the process of preparing for a review is highly valuable to a project-- even if the review is never held. Reviews provide the flight project manager with a knowledgeable and independent evaluation of products or processes, permitting a timely assessment of status and implementation of corrective action. However, reviews require planning, preparation, and follow-up. Definition of clear standards which apply to all reviews aids in training and guiding participants in the activities necessary to assure reliable engineering design. Related Practices: Preliminary Design Review, Reliability Preferred Practice No. PD-ED-1215.1 Hardware Review/Certification Requirement, Reliability Preferred Practice No. PD-ED-1215.2 Critical Design Review for Unmanned Missions, Reliability Preferred Practice No. PD-ED-1215.3 Subsystem Inheritance Review, Reliability Preferred Practice No. PD-ED-1262 References: JPL Standard for Reviews, Jet Propulsion Laboratory document D-10401 (Initial Issue), May 5, 1995. Reviews, Laboratory Policy 4-16. Reviews, JPL Standard Practice Instruction SPI 4-16-1. Special Reviews, Laboratory Policy 4-18. Accident, Incident and Mission Failure Reviews, JPL Standard Practice Instruction SPI 4-18-1. Management of Major System Programs and Projects, NASA Management Instruction NMI 7120.4A,B (and NHB 7120.5). Classification of NASA Payloads, NASA Management Instruction NMI 8010.1A, Appendix C. Technical Reviews, Department of Defense, Military Standard MIL-STD-1521B. | This practice has been used on Galileo, Magellan, and other flight projects. The comprehensive practice is being applied to Cassini, New Millennium, Mars Global Surveyor, Seawinds, and Mars 98. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/07/2000
668 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Pre-Ship Review | Preferred Practice for Design & Test. Pre-ship review ensures the completeness and readiness of each item of hardware and, if applicable, any associated software or firmware, prior to release for shipment to another facility. Pre-ship review of the fabricated item to be shipped is held at the supplier or NASA facility where the item was made and tested. | Evaluate the completeness and readiness of each item of hardware and, if applicable, any associated software or firmware, prior to release for shipment to another facility by performing a pre-ship review. | Practice: Prior to shipment of hardware or software, conduct a pre-ship review at the completion of the fabrication or build and testing of the item to be shipped. This review is scheduled as part of the overall technical review program as defined in a project review plan. Pre-ship review is held at the supplier or NASA facility where the item was made and tested. | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1215.5; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Pre-ship review ensures the completeness and readiness of each item of hardware and, if applicable, any associated software or firmware, prior to release for shipment to another facility. By imposing this requirement, any discrepancies or unresolved problems may be identified and corrected while the item remains under supplier purview. This review is beneficial because it provides an independent assessment of product readiness by knowledgeable people not directly involved in the fabrication and test activity. Implementation Method: The purpose of pre-ship review (PSR) is to determine whether the required work on a planned deliverable is complete and acceptable and, where applicable, whether the flight qualification criteria have been attained. This includes checking that all required analyses and tests were performed and that the data package contains all the required documentation. Action is taken to assess the actual performance of the item against the performance requirements. Differences between the designed versus the built hardware are identified, and any additional risks associated with the differences are assessed. Any liens, concerns, unresolved problems, and open issues with the hardware or software are cataloged, and plans to resolve such open issues and complete any unfinished work are assessed. PSR requirements may apply to system contractors, subcontractors, and NASA centers; they are held prior to shipment to an integration or installation facility, a NASA center, the sponsor, or the launch site. System contractor requirements are written to specify PSR and to pass the requirement down to subcontractors. The PSR is performed by a review board and is a customer-controlled review. The review board assesses the status of the deliverable item, recommends whether or not to ship it, makes an independent judgement of the risks, and identifies any concerns which would affect mission success. A representative of the receiving organization is usually present at the review. The planning and documentation process for pre-ship and other technical reviews is described in Reliability Preferred Practice No. PD-ED- 1215.4, Common Review Methods for Engineering Products. The review agenda specific to PSRs typically includes the items listed in Table 1. Table 1 - Pre-Ship Review Agenda Prepare Final Compliance Matrix. Explain any incomplete requirements. Review completeness of all drawing specifications, including incorporation of all engineering change requests (ECRs). Explain any drawings or specifications that are not complete. Determine the status of required analyses-- their completion or plans to complete, and identify any open issues. Discuss and classify any residual risks. Determine the completion status of hardware assembly and verify that the hardware reflects the final completed drawings. Explain each discrepancy in the as-built hardware. Determine the status of required tests-- their completion or plans to complete, and identify any open issues. Discuss and classify any residual risks. Specify the status of required documentation, including plans to provide any documents that are not complete and in the data package. Provide plans to resolve any assurance liens. Identify any ECRs that have not been implemented in the as-built product.. Identify any problem/failure reports (or equivalent, customer-approved, supplier report formats) on the subject hardware (including electrical and mechanical ground support equipment) or software, as well as on other equipment which could affect it. Provide the plans for resolution. Assess any quotred flagquot problem/failure reports (PFRs)-- problems, residual risks, and actions taken to manage the risk of an in-flight occurrence. Catalog any waivers of product requirements, including the risk assessment associated with each. Evaluate the readiness of hardware to be integrated with other hardware or the spacecraft. Assess the readiness to ship hardware, including the adequacy of shipping containers, shipping methods, shipping environment control, and monitoring. Identify special instructions for item handling, testing, and training. Review plans for supplier participation after shipment. A sample compliance matrix indicating the open item status of a sample subsystem is provided as Table 2. Table 2 - Galileo Orbiter Attitude & Articulation Control System (AACS) Compliance Matrix [D] * Details on work remaining were explained in the PSR package; Source: Reference 3 (Vol. 2, p XVI-E3) Technical Rationale: Pre-ship review provides a last opportunity for the supplier and the customer to review completion of development work before the product leaves the facility. Correction of liens after this milestone usually has a major schedule impact. The planned increase in supplier participation in NASA programs will likely cause an increase in hardware built at supplier sites. Effective pre-ship controls will help ensure the success of NASA outsourcing plans. Related Practices: Hardware Review/Certification Requirement, Reliability Preferred Practice No. PD-ED-1215.2 Common Review Methods for Engineering Products, Reliability Preferred Practice No. PD-ED-1215.4. References: quotJPL Standard for Reviews,quot Jet Propulsion Laboratory document JPL-D-10401, May 5, 1995. quotCassini Project: Spacecraft System Review Program,quot Jet Propulsion Laboratory document JPL-D-9926, December 1992. quotOrbiter Preship Review, (Book 2)quot Galileo Project, Jet Propulsion Laboratory document JPL-D-6358, May 10, 1989. quotLaunch Vehicle Review Milestones,quot NASA ELV OI-12, April 1994. quotRequirements and Procedures for Flight Project Forward Review within the Space Experiments Division,quot NASA SED OI-6700- 1, December 1989. | This practice has been used on Viking, Voyager, Magellan, Galileo, Atlas Centaur, Titan Centaur, and various instrument and space experiment projects. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/07/2000
662 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Uninterruptable Power Supply Systems (UPS) |  | An UPS cost should be weighted against the possible consequences of inadequate protection. Some of the consequences that should be considered are: Repair or replacement cost for damaged electronic equipment. Safety hazards that might result from a control system malfunction or loss of monitoring systems to alert personnel of hazardous conditions. Customer dissatisfaction over schedule slips due to lost information or equipment down time. Labor costs of inactive personnel and possible overtime expense. | Enhance system, subsystem, and component reliability by providing an uninterruptable power supply (UPS) system. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number GSE-3009 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Enhances mission reliability and prevents catastrophic mission failure. Use of UPS can prevent equipment damage by giving personnel time to safe a system or to provide power to critical equipment such as oxygen analyzers or emergency lighting until personnel can move to another area. In addition, UPS can be used to provide filtered AC power to equipment and eliminates disturbances in the power such as spikes, undervoltages (dips and sags), outage flicker, and transient noise which can affect system performance. This significantly increases reliability of electronic equipment using AC power. Implementation Method: UPS can be used where loss of power during an operation is considered critical or where loss of power may cause extensive equipment damage or data loss. Technical Rationale: An UPS typically does two things: (1) It either provides power to enable the safe shutdown of equipment and saving data to a nonvolatile medium, or (2) it provides power to equipment over the duration of fault/failure, enabling equipment to operate continuously. Safe shutdown is completed through embedded programming that communicates shutdown protocol to the user and/or initiates shutdown procedures automatically at the point of fault/failure. Continuous operation is primarily a function of load draw and battery type and size. There are a variety of end-user UPS applications, each with a specific price/performance demand. Some of these needs may be served best by a off-line UPS or an on-line UPS. Most UPS have intelligent features such as automatic battery check, automatic inverter check, AC volts in and out, battery alarm, internal temperature, alarm conditions of internal failures, and the number of power outages. The costs of implementing a UPS safety net can be minimized by choosing the right UPS topology and features for each application. In the networking environment, on-line UPSs are being assigned to critical processing and data traffic nodes, file servers, routers, etc. Off-line UPSs provide protection and power coverage to network printer/output stations, input/output terminals, and standalone PCS. Basically, an UPS system converts some or all of the AC power into DC for the battery and then back into AC power for the load. This double conversion has many variations; however, all of the designs incorporate an inverter to convert DC into AC. It is the inverter operation which defines an UPS as on-line or off-line. The inverter in an off-line UPS operates only when needed, conversely, the inverter in an on-line UPS operates continuously. An off-line UPS is inherently more cost effective than an on-line because the inverter is off most of the time. However, when switching from main power to battery power, known as transfer time, an off-line UPS stops providing power to equipment for a few milliseconds (typically up to 4ms). Most modern computer equipment can sustain a power switch time of up to 300ms, but some older equipment may shut down during the transfer time. An on-line UPS has no transfer time because the inverter continuously supplies battery power to the load whether the main power is active or not. An UPS must be served from a dedicated circuit unaffected by other loads, and the breaker serving the circuit must be provided with safeguards to prevent inadvertent or unauthorized turnoff. The UPS battery also requires monitoring; battery failure is the most common UPS problem. Life expectancy in small UPSs is only a few years due to the batteries which are replaced in accordance with the owners manual. Some UPSs contain self-diagnostics or other test features to provide personnel an indication of battery condition or component malfunction. By utilizing these features, problems can be detected before they announce themselves by failure of the unit to provide power. UPS are used at many locations throughout Kennedy Space Center. Some of the locations where UPSs are used are the Crawler Transporter, Orbiter Processing Facility, and Launch Processing System. Crawler Transporter The Crawler Transporter, Figure 1, is used to transport the Mobile Launch Platform and the space shuttle from the Vehicle Assembly Building to launch Pad A or B. [D] The UPS on the Crawler consist of the following major equipment shown in Figure 2. Ferroresonant Transformer Small Charger Batteries Inverter The Crawler Transporter contains a system that operates as an on-line reverse transfer system and has the following operating modes: Normal. Under normal operating conditions, the power path is shown by the black arrows in Figure 2. The load is powered by an AC supply line that has been filtered through a ferroresonant transformer. When AC on-line power is present, the small charger and inverter are normally off. The white arrows show the elements are connected to the system, but are not receiving power. If the battery charge falls below a predetermined level, the small charger will turn on and recharge the batteries. The ferroresonant transformer cleans up the raw line power; filtering out spikes, sags, surges, noise, lightning, and brownouts. Emergency. When AC line power fails or goes out of tolerance, Figure 3, the inverter turns on and supplies AC power from the battery source. The route of power is shown by the black lines. During the transfer process, the load never sees a break in the output of the system during transfer from normal AC line supply to inverter battery supply or back to line. Recharge. When AC power is restored, power flows to both the small charger and ferroresonant transformer. The inverter turns off and the small charger is turned on to trickle charge the batteries. Bypass. If the UPS must be taken out of service for maintenance the alternate AC power is not required since maintenance is done when no shuttle transport is taking place. If the UPS goes down during an transport operation, direct AC power or bypass is not fed into equipment because of voltage spikes and dips during operation. Instead, the Crawler is stopped until repairs are made or the unit is replaced. Power sustains the operation of the programmable logic controllers and the man machine interface units. The man machine interface units are cathode ray tube screens used by operators to control and monitor several crawler systems. If a power outage occurs during transport of the space shuttle, the Crawler Transporter propel and/or jacking system will automatically stop. The UPS provides power so that operators can obtain information from the various crawler systems and to determine what caused the Crawler to stop. This expedites the troubleshooting process by having the programmable logic controllers operational during a system anomaly. The Crawler has two means of AC power either through shore power or during operation where AC power is generated on board through a diesel engine and generator set. In either case, the UPS cleans the AC power from either source to provide power to sensitive electronic equipment such as programmable logic controllers and the man machine interface units. Filtered power precludes against possible equipment damage and provides a smoother operating system, thus improving system reliability. [D] [D] [D] Orbiter Processing Facility An UPS system is in the Orbiter Processing Facility High Bay 3 provide reserve power for 20 minutes to the oxygen deficiency monitors, hazard warning lights, emergency exit lights, environmental monitoring data system, and paging area warning system. The UPS in the Orbiter Processing Facility High Bay 3 consists of the following major equipment shown in Figure 4. The UPS operates as an on-line reverse transfer system shown in Figure 2 has the following modes: Normal. The critical AC load is continuously powered by the UPS inverter. The rectifier/charger derives power from a utility AC source and supplies DC power to the inverter, while simultaneously float charging the battery. The UPS also provides clean power to equipment by filtering out spikes, sags, surges, noise, lightning, and brownouts. Emergency. Upon failure of utility AC power, the critical AC load is powered by the inverter, which without any switching, obtains its power from the battery plant. There is no interruption in power to the critical load upon failure or restoration of the primary AC source. Recharge. Upon restoration of the utility AC source, the rectifier/charger powers the inverter and simultaneously recharges the battery. This is an automatic function and will cause no interruption to the critical AC load. Bypass. If the UPS must be taken out of service for maintenance or repair, the static switch will transfer the critical load to an alternate source without an interruption. The static switch is provided as a to draw-out assembly so that the static switch can be electrically isolated for maintenance. Once the load has been transferred to the alternate AC source, retransfer of the load is accomplished by automatically synchronizing the UPS and paralleling the inverter with the alternate AC source, allowing the inverter to ramp into the load and then disconnecting the alternate source. Off-Battery. If the battery only is taken out of service for maintenance, it is disconnected from the rectifier/charger and inverter by means of a Circuit Breaker. The UPS will continue to function and meet all of the steady state performance criteria specified herein except for the reserve time capability. Launch Control Center UPS The main Uninterruptible Power System (UPS) for the Launch Control Center (LCC) provides quality uninterruptible 208 VAC 60 Hz 3 phase power for electronic loads to distribution panels for the Record and Playback Subsystem (RPS), the Complex Control Subsystem (CCS), and the Checkout Control & Monitor Subsystem (CCMS). The UPS is critical because it supplies power to the CCMS which is required to safe the Space Shuttle critical systems. Examining the critical loads, half of the consoles operate off UPS 1 bus while the other half operate off UPS 2 bus. The individual racks operate either off both buses or the active operate off one bus and the standby operate off the other UPS bus. The UPS consist of the following major equipment: Uninterruptible Power Modules (UPMs) Power Processors including rectifier/chargers and inverters. UPM Battery Banks, one each per UPM plus one spare, including batteries and battery racks. UPS Bypass Output Switchboard, including system metering and system status displays. Vendor UPS Equipment The UPS is designed to operate as an on-line reverse transfer system in the following modes: Normal. The critical load bus is continuously supplied by the UPMs which derive power from the commercial AC source through a primary power supply system and simultaneously float charge the batteries. The UPMs filter AC power to sensitive electronic equipment. Emergency. Upon failure of the primary AC power, the critical load is supplied by the inverter portion of the UPM's, which, without any switching, shall obtain power from the storage batteries. There is no interruption to the critical bus upon failure or restoration of the commercial AC source. Upon restoration of primary AC power, the rectifier/charger power the inverters and simultaneously recharge the batteries. This is an automatic function and causes no interruption to the critical load. Bypass. If the UPS must be taken out of service for maintenance or repair of multiple internal failures, the static switch transfers the load to the alternate AC power without an interruption. The static switch is provided as a draw-out assembly so that the static switch can be electrically isolated for maintenance once the load has been transferred to the alternate AC power. (The static switch is also capable of providing fault clearing current to the load when the alternate AC power is available.) Retransfer of the load is accomplished by automatically synchronizing the UPS to the alternate source, paralleling the inverters with the alternate source, and then disconnecting the alternate source. Non-Redundant. If one of the UPM's is taken off-line, but the load demand does not exceed the capacity on the UPM's remaining on-line, the UPS will continue to furnish conditioned power from the inverters and operate in a non-redundant mode. Emergency and bypass modes shall operate as described above. NOTE: INPUT SOURCE IS TWO INDEPENDENT SOURCES, 1 FOR UPS 2nd FOR STATIC BYPASS INPUT. Basic Requirements of an UPS System Lightning and surge protection. The unit should meet the requirements of IEEE standard 587 Category A or B. These requirements require the unit to withstand surges of 6000 V without damage to itself, and preventing the surge from reaching the protected load. Isolation. The UPS should have grounding and bonding provisions to reduce neutral-to-ground noise to zero, thereby preventing common mode noise from reaching the protected equipment. Line noise can cause possible malfunction to equipment. Voltage regulation. Equipment voltage requirements must be maintained within the limits prescribed by the manufacturer. Continuous, no-break power. A true UPS continuously serves the load through the UPS support battery, and the load never sees a power break when utility power is lost. Some units are standby power systems, whereby the load is transferred to the UPS only when utility power is lost or deviates from prescribed power quality parameters. A continuous no-break power unit must be used if no power interruption, even of a momentary nature, can be tolerated by the load. Output power waveform. Electronic equipment and computers are designed with the assumption that input power is an AC sine wave. All UPSs transform DC battery power from a constant output, straight line, to a variable output, sine wave, or a reasonable approximation thereof. With some low cost units, a quotreasonable approximationquot may be an abrupt square wave. It is important to adhere to the requirements prescribed by the manufacturer of the protected equipment. Load rating basis. More than 90% of computer equipment employs input switching-mode power supplies. The UPS load rating should be based on a switching-mode power supply load, rather than some unrelated load such as lighting or motors. References: Valerie A. Price, quotUPS systems: Powering Up Process Performance,quot Intech, July 1994, pp. 38-41. Vladi Basch, quotFallacies and Facts of UPS Systems,quot Plant Engineering, June 3, 1993, pp. 72-74. SAA09UP05-001, quotSystem Assurance Analysis of the Uninterruptable Power Supply System at the Orbiter Processing Facility High Bay-3quot SAA09UP01-001, quotSystem Assurance Analysis of the Uninterruptable Power System (Exide) UPS 2, 2A, 3, 3A at the Launch Control Centerquot | This practice has been used on the Space Shuttle Program Ground Support Equipment, including the Crawler Transporter, Orbiter Processing Facilities and Launch Processing System. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/06/2000
659 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Redundancy in Critical Mechanical Systems |  | All other factors being equal, the elimination of redundancy in the system described in this practice would result in a considerably higher probability of failure, the identification of additional critical items and increased probability of loss of life. | The careful use of redundancy in Critical Kennedy Space Center (KSC) Ground Support Equipment (GSE) Mechanical Systems ensures reliable operation. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number GSE-3003 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The benefit of using dual redundancy in critical KSC Ground Support Equipment (GSE) systems is greater assurance of successful system operation during critical shuttle processing operations in the event of a single equipment failure that would otherwise possibly cause loss of life, vehicle or damage to a vehicle system. By designing in redundancy for critical operations, the system can fail to a quotfail-safequot condition and still achieve operational objectives. Implementation Method: The Orbiter Access Arm (OAA) is a critical GSE system located at Launch Complex 39, Pads A and B, Kennedy Space Center, Florida. The OAA is extended shortly after the shuttle arrives at the launch pad to allow personnel access to the shuttle to make the necessary preparations for launch. Shortly before launch, the astronauts will board the shuttle via the OAA. The OAA provides the only path of ingress and egress to the space shuttle crew cabin for the astronauts. Thus, this system becomes critical to the safety of the crew. A critical system, as it applies to KSC GSE systems, is a system whose loss of overall system function, or improper performance of a system function, could result in loss of life, loss of the shuttle vehicle itself, or damage to a shuttle system. In addition, systems that have been identified as critical must be designed to be fail-safe. Fail-safe design provides the ability to sustain a critical system failure without causing loss of life, loss of the shuttle vehicle, or damage to a shuttle system. This includes the capability to safe the systems and successfully terminate operations, or if required, to continue operations through to completion. Therefore, the OAA system must be able to sustain a failure and still be able to perform its function to completion of the operation. In the event of a single system failure, it must fail to a safe condition, meaning a single failure will not result in loss of life, loss of the shuttle, or damage to a shuttle system. The critical condition is encountered when the OAA is retracted away from the shuttle at T-7:30 minutes in the countdown in preparation for launch. Should an emergency arise, either on board the shuttle or on the launch pad, during the final minutes of the countdown after the OAA is retracted, the OAA will need to be re-extended to allow the astronauts to evacuate the area as quickly as possible. Extension of the OAA is essential to the astronauts safety, as it is the only path available to the crew in the event evacuation of the shuttle is required. The astronauts lives depend on the OAA extending when needed. The probability of 2 redundant components failing during a critical time period is much less likely than 1 component failing during the same period. In the case of the OAA, 2 completely redundant sets of valves, plumbing, and electrical controls are installed. Based on the classical probability theory, assuming no common cause failures, it can be shown that through using dual redundancy the reliability of a system can be increased 1 or more orders of magnitude. Thus redundant system design provides protection against a single failure causing a hazardous condition resulting in loss of life, destruction of a shuttle or damage to a shuttle system. Technical Rationale: Redundancy is defined as multiple ways of performing a function. There are several different types of redundancy used on KSC GSE systems. Depending on the requirements of the application, the type of redundancy to be used will vary. The two primary types of redundancy are described below: Operational or Active quotfully onquot Redundancy - Redundant elements, all of which are fully energized during the system operating cycle. Operational redundancy includes load sharing redundancy wherein redundant elements are connected in such a manner that, on failure of one unit, the remaining redundant elements will continue to perform the system function. Switching out the failed element is not required. Operational redundancy may be either full parallel or quotmajority votequot. Standby Redundancy - A redundant hardware item(s) that are non-operative until they are switched into the system on failure of the primary item(s). Switching can be accomplished by either automatic or manual means. Other categorization of redundancy include: Like Redundancy - Identical hardware items performing the same function. Unlike Redundancy - Nonidentical hardware items performing the same function. Safety features which provide protection for specific failure modes are considered as unlike redundancy for that failure mode; i.e. relief valves which provide protection against overpressurization after failure of a regulator Typically, KSC employs parallel, two component redundancy. It can be shown that the incremental reliability gain is greatest for the first redundant unit and decreases rapidly as more redundant units are added in parallel. Figure 1 provides an example of a basic block diagram of the hydraulic extend circuit for the Orbiter Access Arm (OAA) showing the use of redundancy in a critical shuttle ground support system. [D] A hydraulic reservoir fills 4 hydraulic accumulators. Only 2 accumulators are needed to ensure arm retract and extend, but 2 additional (redundant) accumulators are provided for fail-safe operation in the event of a leak. In the event of a major leak, the launch countdown will stop. If a major leak occurs during an emergency re-extend operation, the 2 redundant accumulators should supply enough hydraulic pressure to ensure full extension of the OAA. In addition, the hydraulic supply system is capable of supplying additional pressure if required. The ensuing discussion will address the primary system only. Design of the system minimizes the likelihood of a common cause failure. The accumulators provide hydraulic fluid to a pilot valve (Primary Hydraulic Extend Pilot Valve) and to the main hydraulic supply valve (Primary Hydraulic Extend Supply Valve). When commanded by LPS (Launch Processing System), the pilot valve supplies hydraulic pressure to the Primary Hydraulic Extend Supply Valve and to the Primary Hydraulic Extend Return Valve, thus opening both valves. Hydraulic fluid from the accumulators then flows thru the Primary Hydraulic Extend Supply Valve to the upper and lower OAA hinges. Each hinge is individually capable of rotating the OAA. Thus the hinges are redundant. Fluid exits the OAA hinges, and returns to the main hydraulic reservoir through the Primary Hydraulic Extend Return Valve. This discussion described the basic operation of the primary hydraulic extend circuit for the OAA. There is a secondary (redundant) set of valves as described above installed in parallel with the primary valves, that simultaneously operate. Operational redundancy ensures that the OAA will operate when needed. A single failure will not result in a catastrophic consequence. References: O'Connor, Patrick quotPractical Reliability Engineeringquot 2nd Edition, Wiley, 1985. | This practice has been used on the Space Shuttle Program, Ground Support Equipment. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/06/2000
661 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Redundancy Considerations for Ground Communication Systems |  | Incorrectly applying redundancy can result in higher cost and reduced MTBF. | Designing a fail-safe ground communication system requires attention to hardware and policy decisions. Ensuring a fail-safe system normally requires some use of redundancy. It also requires safe operating procedures. It further requires a reliable source of power. This practice considers what operating procedures are needed, what level of hardware redundancy is required, and backup power considerations. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number GSE-3007 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: In most instances it is not practical to be fail-safe at any cost. This practice provides guidelines on using redundancy only where it is required. Too much redundancy leads to failures resulting from increased complexity. Mean Time Before Failure (MTBF) is estimated as a function of the number of parts. Minimizing redundancy reduces the number of parts and therefore increases the MTBF. This practice illustrates how to design a system that satisfies the technical requirements but contains cost by minimizing the level of redundancy. Implementation Method: The Operational Intercommunication System - Digital (OIS-D) at the Vehicle Assembly Building (VAB) serves as the mechanism for discussing this practice. The OIS-D is a controlled access, multiuser, multichannel communications system used in support of vehicle test and launch operations. It is a fully digital system that provides 500 user channels of duplex voice communications. OIS-D equipment in the VAB interfaces with the Central Summing Network (CSN) in the Launch Control Center (LCC). OIS-D equipment in the VAB consists of the following: Group Processor Assembly (GPA) Racks Transmission Equipment (DTE) Rack Power Rack, D.C. Chargers, Battery Banks, Battery Disconnects, and D.C. Disconnects End Instruments (EI) The OIS-D will be referred to in the remainder of the report as the voice communication system. System Operation: The telephone system (Figure 1) provides a loose analogy to the voice communication system (Figure 2). The EI is a unit in which one connects a headset and dials up a voice channel. The user can talk and listen over this channel. As a communication device, the EI is analogous to the telephone. The EI is a user-operated, microcomputer-based, communication device. The GPA is the principal rack assembly of the voice communication system. Each GPA transmits and receives voice, status, and signaling data from its associated EIs. The GPA is analogous to a central office. It provides the interface between the End Instruments and the Central Summing Network (CSN). The CSN gathers information from multiple GPAs and sums the information for redistribution. The CSN is analogous to the toll office. [D] [D] Power Distribution: The voice communication system operates on a floating 48V DC power source. This power is first converted from 480V AC to 48V DC by a battery charger. It is then routed through circuit breaker distribution panels, and to battery banks where it is stored in case of a power failure. From there the power is distributed to the power supplies used by each chassis, and to the fans used for rack cooling, through power control modules that reside on each of the GPA racks. If 480V AC power fails, the battery banks supply 48V DC for a minimum of one hour. EI operating power (48V DC) is normally supplied by its associated GPA over the data transmission lines. The data transmission lines act as a medium for both the data transmission and power transmission to the EI. Redundancy Policy: The design must satisfy the Ground Support Equipment (GSE) Fail Safe requirement of NSTS 07700, Volume X. The requirement states that all GSE (except primary structure and pressure vessels) shall be designed to sustain a failure without causing loss of vehicle systems or loss of personnel capability. One of the requirements for support of hazardous operations is to have co-located EIs in areas of hazardous operations. The requirement for co-located EIs implies redundant EIs. Furthermore, the fail-safe requirement points towards a redundant implementation. That is, redundant GPAs, redundant power, and redundant Data Transmission Equipment (DTE). The data transmission equipment consists of Fiber Optic Transmitters (FO TX) and Fiber Optic Receivers (FO RX). The power requirements and data transmission equipment requirements are best satisfied through use of redundancy. The GPA requires additional consideration. Figure 3 is an implementation that utilizes redundant GPAs. For illustration purposes assume that each GPA can support four EIs (actually each GPA supports 119 EIs). This implementation satisfies the fail-safe requirement but it is very expensive. The GPA is the most expensive item in the system. Figure 4 introduces an alternative implementation. Observe that in this implementation neighboring EIs have different GPAs. Simply by requiring that co-located EIs have connections to independent GPAs eliminates the need for redundant GPAs. In the event of a failure, the operator could move to a neighboring EI and quotsafequot the system. Therefore Figure 4 is cost effective while also satisfying the fail-safe requirements. [D] [D] Both implementations were considered during the design of OIS-D. Many existing designs conform to Figure 3. The cost of the GPAs made the figure 3 implementation too costly for OIS-D. The Figure 4 implementation was acceptable to the design team because it fit within the cost profile of the system and satisfied the fail-safe requirements. In practice the system has proved to be very reliable. Technical Rationale: In attempting to determine if complete redundancy is needed or if policy decisions can be implemented to alleviate many of the fail-safe concerns, two questions need to be answered: Will it decrease cost? Will it improve the product? The answer to both questions is yes. Eliminating unnecessary redundancy reduces cost. The product is improved because the system MTBF increases with the removal of unnecessary redundancy. These are quantifiable justifications for the implementation of this practice. This practice should also be adhered to when designing Local Area Networks (LANs) and Wide Area Networks (WANs). References: SAA009CU08-026 (Revision A) - System Assurance Analysis of the Operational Intercommunication System - Digital at the Vehicle Assembly Building (VAB). | This practice has been used on the Space Shuttle Program, Ground Support Equipment including the Operational Intercommunication System — Digital (OIS-D) at the Kennedy Space Center. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/06/2000
660 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Flow Fuses for Elimination of Hazards in Pneumatic and Hydraulic Systems |  | Not incorporating flow fuses can increase risk of loss of life or damage to hardware. | To maximize system reliability (fail safe) through use of Flow Fuses when designing pneumatic or hydraulic systems for either facilities or ground support applications. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number GSE-3001 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The Flow Fuse, otherwise known as an Excess Flow Check Valve, inhibits media flow as a result of sensing a pressure differential which exceeds preset limits. Pressure differentials would be a result of downstream component failure, line rupture, a downstream component failure, line rupture or catastrophic human error. The Flow Fuse is essentially a Check Valve installed in the system such that flow is attempting to travel in the normally blocked direction. A mechanism enabled by pressure equilibrium causes the normal quotcheckquot function to revert to a quotbypassquot function. Upon sensing a shift in pressure differential which exceeds some calibrated setpoint (user defined), the quotbypassquot function is disabled and the valve immediately inhibits flow. The Flow Fuse has extremely rapid response characteristics (tests have proven 10-100 msec), can handle a wide range of applications (50-14000 psi), and has a long proven test and application history. The unique qualities of the Flow Fuse including multiple reset options (manual, automatic or remote), remote position indication and time delayed opening/closing features make the device adaptable to almost all applications where inadvertent expulsion of media could result in personal injury, loss of production or other catastrophic occurrences. Installation of Flow Fuses will provide extended downstream protection to personnel, equipment and/or facilities. The prime benefit provided by Flow Fuses will be the ability to produce near ideal quotfailsafequot designs. Flow Fuses, if used to their potential, will minimize the effects of hardware failure through systematic abatement of physical hazards. Additionally, inclusion of these devices will substantially lower failure recovery costs. Implementation Method: Flow Fuses should be installed in Pneumatic and Hydraulic systems for the prevention of loss of life, injury, or flight hardware damage due to expulsion of high pressure gaseous or liquid media. The designer should only implement these devices after a careful review of good safety review considerations. System analysis and subsequent modeling will reveal strategic points for the inclusion of Flow Fuses to maximize protection and provide system fault isolation. As an analogy, these devices will be installed much like circuit breakers used in electrical circuit design. In those applications, main breakers provide global overcurrent protection and branch circuit breakers provide secondary fault isolation (See Figure 1 quotFlo- Fuse Implementation Diagramquot). [D] Technical Rationale: Flow Fuses should be installed in Pneumatic and Hydraulic systems for the prevention of loss of life, injury or flight hardware due to catastrophic hardware failure or human error. These devices are appropriately selected through system modeling to match system operating parameters and installed within flexible or hard-lines as necessary. Flow Fuses should be utilized at both the system and subsystem level where they can serve as narrow field fault isolation devices. In contrast to manual hand valves or other manually actuated shut-off devices, Flow Fuses are automatically tripped and offer multiple reset options and monitor/control functions. Figure 2 depicts generic fluid distribution system uses and implementation methodologies. [D] References: NCSL 174-73, Naval Coastal Systems Laboratory quotTest and Evaluation of Flow Fuses for Use In Manned Pressure Chambersquot; by Clifford R. Holland, NCSL dated August 1973. Marotta Scientific Controls, Inc.; Product Correlation Sheet. Marotta Scientific Controls, Inc.; quotFLOW FUSESquot dated 23 November 1970 (White Paper). | This practice has been used on Ground Support Equipment at the Kennedy Space Center, specifically the Operations & Checkout Facility. The purpose is to prevent atmosphere oxygen depletion in underground tunnels should high pressure inert gas lines rupture expelling inert gases. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/06/2000
666 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Foreign Object Debris (FOD) Program at KSC |  | Since implementing a comprehensive FOD program, FOD incidents have decreased significantly from levels prior to the program. The lack of such a program can result in unacceptable performance of equipment, scrapping of otherwise usable hardware, expenditure of unnecessary resources, and possible schedule delays, or major penalties which could include loss of mission capability, injury to personnel or loss of life, and damage to, or loss of, the shuttle vehicle. | Enhance the Reliability of Flight Hardware Processing Systems by including in the Program a reliable Foreign Object and Debris (FOD) policy and related procedures for use during launch and landing operations, vehicle and payload processing, and maintenance activities at designated areas of Kennedy Space Center (KSC) and off-site landing facilities under KSC responsibility. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number GSE-3011 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Use of a FOD prevention program will minimize the possibility of damage or loss of flight hardware or injury to personnel due to lost items within the flight hardware elements, resulting in preservation of national resources. Implementation Method: FOD, as it is viewed at KSC, is defined as follows: Damage to, or malfunction of, a launch vehicle or payload caused by any foreign object(s) that are alien to flight systems. FOD may cause material damage or it may make the system or equipment inoperable, unsafe or less efficient. But what is FOD? FOD is somewhat ambiguous, because it varies depending on the situation. A paper clip on a desk is not FOD, because it is not foreign to that environment, but a paper clip in a commercial passenger jet engine or space shuttle main engine could prove catastrophic to either the flight vehicle, crew or both. FOD can consist of staples, paper clips, paper, particles generated from operations such as sanding, drilling and welding, liquids and chemicals, food, clothing, hair, insects, lost screws, nuts and washers, tools such as wrenches and screwdrivers, jewelry such as earrings, bracelets, watches and rings, eye glasses, plastic and rubber, tape, string, tie wraps, safety wire. Anything can be FOD if it is foreign to that environment. Its effect on the environment depends on many things, including a measure of luck. There are numerous facilities at KSC used for servicing and processing the Shuttle and its Payloads, External Tank (ET) and Solid Rocket Boosters (SRB's), and their various components. Each facility has its own unique tasks to perform, and associated hazards, both to the flight hardware and personnel. A FOD prevention program was implemented to improve the reliability of Space Shuttle processing. The primary goals of the FOD program is to: Provide a standardized approach, maintaining awareness, prevention, compliance and continued reinforcement. Ensure operational processing areas maintain a safe, clean, FOD-Free environment. The key to success is in a simple formula. AWARENESS + PREVENTION = COMPLIANCE. Figure 1 describes the attributes for each of these members. A FOD training program was established and a certificate of training is issued to each employee upon completion of the training. The employee signs the certificate as a pledge and personal commitment to help prevent Foreign Object Debris and Damage and to acknowledge their personal responsibility to the space program and flight safety. To attain a successful FOD program, total employee involvement is required. Everyone needs to be responsible. The SPC at KSC utilizes a 10 point plan to implement its FOD program. These 10 points are shown in Figure 2. The success of the FOD program has resulted in a decrease in incidents at the rate of approximately 50% per year. [D] [D] FOD Prevention Guidelines The following are general guidelines in establishing a FOD Prevention program, and can be tailored as needed to the specific requirements of particular work sites. Monitor in service tool Control Kits inventoried 100% each shift. Tooling, parts and equipment stored in a neat and orderly manner. Work area cabinets are maintained in a neat and orderly manner. No chemicals stored in cabinets. All chemicals and empty chemical bottles returned to the proper storage area. All quotHazardous Wastequot trash cans and FOD bags are emptied each shift. Work areas and work levels are clean and free of any debris. No wood, cardboard, bubble wrap, etc. Work area storage racks are maintained in a neat and orderly manner. No chairs on work stands or levels. Exception's are tethered chairs in approved areas. All equipment, tooling, trash cans, parts, etc., located above the floor level are tethered. All cables and flex hoses are routed and secured in an approved manner to prevent damage. All gloves, booties, razor blades, safety wire and miscellaneous items are disposed of in the proper manner. All paperwork turned in at the end of the shift. All emergency egress lanes are clear of any obstacles. Facility deficiencies are reported and recorded in the record log. All safety hazards reported to the supervisor immediately. All backup team members have taken care of assigned areas. Personal items such as watches, rings and eye glasses are either removed prior to entry to clean areas or are secured by taping or tethering. Definitions Clean As You Go - The practice of cleaning assigned tools, parts equipment, worksite, etc. (as practical), during and at the end of an assigned task, and/or shift, to promote flight safety and ensure that the areas remain safe, clean and FOD-Free. Designate Flight Hardware Operational Processing Area - Sites with flight hardware and processing activities in place in support of Shuttle Processing Operations. Site FOD Monitor - An individual in the flight hardware operational processing area designated to promote FOD awareness, check specific areas of responsibility for potential FOD and/or hazards, correct discrepancies and report open items to his/her supervisor for closure. Site FOD Prevention Office - A control center for management support, trend analysis, concerns committees, incident reporting, suggestions, and any other relevant items that meet the objectives of FOD prevention. Site FOD Team - A team consisting of the Site Manager and applicable representatives from other organizations, to perform FOD prevention walkdowns in the flight hardware operational processing areas. Site Manager - An individual who has primary responsibility for processing and/or maintenance tasks in an operational flight hardware processing area. Tool Control - The method used to ensure that tools are individually marked from other like items, identified to the user and storage location, and inventoried at the beginning and end of each task or shift. Work Area Rules - The requirements for ingress to and egress from the orbiter, external tank (ET), solid rocket booster (SRB), Space Shuttle Main Engine (SSME), and respective operational processing areas. General Requirements The procedures apply to all organizations that support flight hardware processing. The designated flight hardware operational processing areas will be maintained FOD free, clean, and safe at all times. There will be no abandoned debris, tools, parts, equipment, materials, chemicals, shavings, trash, flammables, contaminants, etc.; no ingress or egress obstacles; no unmarked or unidentified tools, parts, equipment, chemicals, etc.; no unsecured or untethered items above ground level; no unkempt areas; no hazards; nothing left in the area that does not have a specific purpose for work in process or functional requirement or is not stored properly. Only authorized personnel with valid requirements to perform work or surveillance will be allowed in the controlled work areas. Personnel entering into the designated flight hardware operational processing area will practice the quotclean as you goquot method, cleaning up assigned tools, parts, equipment, worksite, etc. as practical, during and at the end of the assigned task and/or shift. Organizations having possession of hardware inventories and/or tools and equipment will be responsible for those items and have a closed-loop tracking system, with tools and equipment traceable to location and user. The user is responsible for the physical location of all items carried into the flight hardware operational processing area and will be held accountable. Perform random inventory of toolbags upon ingress and egress of the flight element for compliance with the requirements. Report discrepancies. Each employee is expected to practice safety and good housekeeping habits and prevent FOD at all times in the designated flight hardware areas. Each operational processing area will have a FOD control board to hold clipboards for daily checklists and related FOD prevention data. FOD boards will be kept neat and clean. All personnel will view the KSC FOD Prevention Video and sign a personal commitment to quotClean As You Goquot. A copy will be on record in individual administrative files. Site Managers will be appointed by the Site Director. FOD prevention walkdowns will be scheduled on a regular basis in all operational processing areas by the Site Manager and the Site FOD Prevention Office. The Site Manager or delegate will attend all FOD prevention walkdowns. The work area will be checked for potential hazards and anything out of place that could potentially cause damage to flight hardware or injury to personnel. In addition to the scheduled walkdowns, daily walkdowns will be conducted by Site FOD Monitors. Site FOD Monitors will be selected for each shift at regular shift meetings, on a volunteer basis. Alternates will be appointed to cover absenteeism. Monitor duty will last for 1 month and will be in addition to normal work responsibilities. Before an employee can be selected for a second time, each work group member will have the opportunity to serve as Site FOD Monitor. Ensure that FOD prevention is stressed with subcontractors prior to award of contracts, have subcontractors sign a letter agreeing to follow the quotclean as you goquot method, and post a copy of this letter on the jobsite. Incentives As an incentive for good performance, rewards are given out. At SPC, the reward is a quotFOD Buster Chitquot. These chits are good for a $1 credit at the KSC cafeterias or mobile snack trucks. This provides positive reinforcement for the FOD program, and recognizes and encourages continued good performance. Organizations The Shuttle Processing Contractor is a member of National Aerospace FOD Prevention, Inc. The National Aerospace FOD Prevention, Inc. is a non-profit educational association. The organization's primary goal continues to be to promote awareness of the dangers of FOD and provide the aerospace industry with information on preventing foreign object damage to aircraft and aerospace vehicles with proven practices. Members are from military aerospace companies, as well as commercial aerospace companies, the various branches of the military itself, defense contractors and commercial business. A National Aerospace FOD Prevention Conference is held annually. The conferences have speakers on various topics, interactive learning sessions, and exhibitors. Member companies share their FOD program experiences, successes, and training programs with other with other members for the mutual benefit of all concerned. The annual conference promotes FOD prevention by keeping personnel who build or use aerospace products informed about the best practices in eliminating foreign objects. Topics discussed at the conferences and in the newsletter include Preventive Practices, Measuring Performance, Training, Material Handling and Parts Protection, House Keeping, Tool Accountability, Hardware Control, Lost Items, Hazardous Materials, Design Considerations, Assembly Operations, Reporting & Investigation. The National Aerospace FOD Board of Directors and the National Aerospace FOD Prevention Conference have been vital sources for disseminating current and effective FOD prevention ideas and techniques. Conclusions All flight hardware operational processing personnel are responsible for supporting the Site FOD Monitors and their supervisors to ensure the effectiveness of FOD prevention. Compliance will be monitored by random walkdowns conducted in addition to the scheduled walkdowns. The KSC/SPC FOD program has been successful. By involving all hands-on employees, the Shuttle processing operations FOD Prevention Program has been able to Lead by Example. Operational areas reflect pride in ownership, accountability and a safe, clean work environment. Awareness has significantly improved and Hazards have been reduced. Astronauts are reporting exceptionally clean Orbiters. Technical Rationale: A FOD program reduces costs in lost tools, damaged equipment, schedule impacts due to rework, and reducing unnecessary risks in a business that is inherently risky. References: National Aerospace FOD Prevention Newsletter - FAST, P.O. Box 5489, Pine Mtn., CA 93222 Kennedy Space Center Handbook for the Foreign Object Control Program - KHB 5330.10 | This practice has been used on the Space Shuttle Program as well as military and civilian aircraft operations. KSC use includes all processing areas: three Orbiter Processing Facilities (OPF's), Vehicle Assembly Building (VAB), Launch Pads 39 A & B, and others. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/06/2000
663 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Welding Practices for 2219 Aluminum and Inconel 718 |  | Impact of Nonpractice: Impact of nonpractice is depicted in abbreviated form in Table 2, which shows various defects and other conditions that can occur in welds of all three types included in this practice along with a few of the most prominent potential causes of these conditions. The impact of nonpractice can be seen by viewing each column to determine the conditions brought about by improper or inadequate adherence to approved and appropriate practices and procedures. Each row can be scanned to determine some of the likely potential causes of a given condition or defect. Greater detailed guidance on the causes and effects of improper practices can be obtained from the references, from welding manuals published by the American Society for Metals or American Welding Society, or by contact with NASA/MSFC engineers and technicians who have had experience with the given processes. Table 2. Welding: Conditions and Potential Causes Condition MOST PROMINENT POTENTIAL CAUSES (GTAW and VPPA on 2219 and EBW on Inconel 718) Improper Joint Design and Preparation Improper Atmosphere Control Improper Posthead Improper Heat Input Improper Tooling Improper Welding Procedure GALVANIC CORROSION X HOT CRACKING X X IMPERFECT BEAD SHAPE X X X X INCLUSIONS X X X LACK OF FUSION X X X X LACK OF PENETRATION X X X MICRO- FISSURING X X X MISMATCH (OFFSET) X PEAKING X X X X X POROSITY X X RESIDUAL STRESSES X X X X START/STOP DEFECTS X STRESS CORROSION CRACKING X X X | Gas Tungsten Arc Welding and Variable Polarity Plasma Arc Welding are preferred for joining 2219 Aluminum, and Electron Beam Welding is preferred for joining Inconel 718 in critical aerospace flight applications. | MSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1205; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Adhering to proven design practices and processing techniques for 2219 Aluminum and Inconel 718 will result in high performance joints, reduced weld defects, reduced weld repair costs, and reduced inspection costs. These practices, if conscientiously applied, will reduce the potential for galvanic corrosion, hot cracking, imperfect bead shape, inclusions, lack of fusion, lack of penetration, microfissuring, mismatch, peaking, porosity, residual stresses, start/stop defects, and stress corrosion cracking. Implementation Method: Three types of welding for two commonly used materials have been used predominantly at NASA/MSFC for the welding of aerospace hardware: (1) Gas Tungsten Arc Welding (GTAW) for 2219 aluminum; (2) Variable Polarity Plasma Arc Welding (VPPAW) for 2219 aluminum; and (3) Electron Beam Welding (EBW) for Inconel 718. In Gas Tungsten Arc Welding for 2219 aluminum, heat required to join the aluminum is generated through an electrical arc applied at the joint. An inert atmosphere of helium surrounds the arc to prevent oxidation during the welding process. The type of GTAW covered in this practice is direct current, straight polarity (DCSP) in which the torch serves as the negative electrode (cathode) and the work piece as the positive electrode (anode). In Variable Polarity Plasma Arc Welding for 2219 aluminum, an arc gas (argon) is constricted by an orifice in the torch so that it forms a narrow column of high density gas that carries the arc current. Current is reversed up to 20 percent of the time in a 20 to 25 microsecond cycle to provide a cleaning action to the work piece. Electron Beam Welding is performed in a vacuum and generates heat for fusing adjoining metals by impacting high kinetic energy electrons upon the work piece surface. [Definitions of selected welding terms applicable to the three types of welding are provided at the end of this section.] The three types of welding, along with distinguishing recommended practices for each, are shown in Table 1. Among the important practices that will aid in ensuring high reliability welds are welding in the proper position, use of high purity shield and plasma gasses, proper cleaning of the joint prior to welding, operator certification, and computer control of the welding process. The use of 2-percent thoriated tungsten electrodes for GTAW and VPPAW provides arc stability and increases electrode service life over that of standard tungsten electrodes. Important additional precautions for all three types of welding are use of rigid tooling to reduce weld joint deformation, nonmagnetic tooling to prevent skewing of the arc due to magnetic deflection, and correct and properly marked weld rod and wire. Automation is highly desirable for all three methods to maintain weld uniformity. If tack welds are used to temporarily hold adjoining parts in place, they should be consumed during the welding process. Specific characteristics, parameters, precautions, and criteria for each type of welding are described in the following three paragraphs: 1. Gas Tungsten Arc Welding (GTAW) (DCSP) for 2219 Aluminum As shown in Table 1, the flat (downhand) position is preferred for the best weld uniformity and penetration. Welding in the direct current, straight polarity (DCSP) mode while using high purity helium shield gas provides deep penetration without oxidation or contamination. (Welding in the alternating current mode is particularly suitable for welding thin aluminum as it produces less heat and provides good cathodic cleaning.) Pulsing of the weld current can be used to provide better control for some out-of-position welds. Minimizing the number of weld passes will decrease the tendency for distortion. A pointed tip electrode is used in GTAW. A positive torch quotlead anglequot is desirable for GTAW (DCSP) to provide preheating and more uniform melting. Lower energy inputs generally increase weld strength. GTAW (DCSP) is a preferred process for tack welding of aluminum. GTAW (DCSP) also can be used for welding steels (including stainless steel), titanium, magnesium (with care), and refractory metals. The 2219 aluminum is an excellent alloy for maximum strength in cryogenic applications with good weldability. Table 1. Weld Characteristics/Parameter/Criteria for Three Types of Welding CHARACTERISTIC OR PARAMETER RECOMMEND OR STANDARD PRACTICES GAS TUNGSTEN ARC WELDING (2219 Al) VARIABLE POLARITY PLASMA ARC WELDING (2219 Al) ELECTRON BEAM WELDING (INCONEL 718) Preferred Position Flat Vertical Flat Shield Gas Helium (99.999% Purity) Helium (99.999% Purity) Vacuum Plasma Gas N/A Argon (99.999% Purity) N/A Backing Required No No In Some Instances (1) Preferred Electrode 2% Thoriated Tungsten 2% Thoriated Tungsten (Tungsten Filament) Appropriate for Repair Yes Not Usually (2) Yes Cleaning Requirements Mechanical Removal of Oxide, Free of Hydrocarbons Mechanical Cleaning Not Required, Degrease Only Special Cleaning for Vacuum Requirements Used for Tack Welding Yes No Yes Computer Control Desirable Essential Desirable Most Prominent Potential Defects Oxide and Tungsten Porosity, Lack of Penetration or Fusion Undercut, Lack of Fusion Improper Seam Tracking, Microfissuring N/A: Not Applicable Notes: Backing bars are used for EBW in some instances to ensure full penentration without overshooting or to eliminate excessive spatter. VPPAW usually is employed in an initial manufacturing process since it is the most sophisticated method and the most adaptable to automation. Repair of larger seam welds may be appropriate for jobs of sufficient size warranting setup. [D] 2. Variable Polarity Plasma Arc Welding (VPPAW) for 2219 Aluminum Figure 1 shows three variations of plasma arc welding: (1) Straight Polarity; (2) Reverse Polarity; and (3) Variable Polarity. Variable Polarity Plasma Arc Welding retains the high heating capacity of the straight polarity process while offering the part cleaning feature of reverse polarity. A flat-tipped electrode is used in VPPAW. A minimum of reverse cycle time is required to keep electrode erosion low. As in the case of GTAW (DCSP), lower energy inputs generally increase weld strength and minimize distortion. Axial torch rotation to align the arc with the weld joint, and torch designs incorporating self-centering electrodes will compensate for electrode tip erosion and will provide greater accuracy in seam tracking and weld bead uniformity. A positive torch quotlead anglequot of 0 to 3 degrees is desirable for automated welding with VPPAW. Electromagnetic interference caused by the welding process will require shielding or distance separation of computer monitoring and control devices. High purity grades of both the plasma gas and the shield gas are required. VPPAW also can be used for welding steels, Inconel, and other metals. 3. Electron Beam Welding (EBW) of Inconel 718 EBW produces deep, narrow welds with parallel sides and a narrow heat-affected zone. It is performed in a vacuum in most aerospace applications, and a near-zero joint gap is required to ensure fusion of the parts. EBW provides minimum distortion because of low total heat input whether used on thick or thin sections; however, full penetration welds may result in excessive spatter. The vacuum environment requires special cleaning. The size of work to be welded is limited by the size of the vacuum chamber and configuration of the manipulator. While EBW can be used to weld almost any metal, it often is used on high melting point metals including the refractory metals requiring stringent control of oxides. EBW is suitable for welding dissimilar metals and parts of dissimilar mass. DESIGN CONSIDERATIONS FOR WELDED COMPONENTS As will be seen in quotImpact of Nonpractice,quot the concepts of a workable welded part design and a producible and inspectable weld joint configuration are very important to successful welding using any of the three processes described. The design of weld joints and of the special processes, tooling, and equipment needed to weld each configuration is best accomplished through use of a team approach in which the designer consults with materials, stress analysis, weld engineering, manufacturing, and inspection personnel as the welded design evolves. The process to be used to create the weld; the weld's fracture mechanics and fatigue properties in its planned environment; compatibility of the materials to be welded; the desired strength of the completed weld joint; and the method to be used to inspect the weld are among the many important factors that must be considered in weld joint design. Manufacturing, quality assurance, and design engineering personnel working hand-in-hand in this team approach will ensure reliable weld configurations. The need for this team approach cannot be overemphasized. Among the design practices for welding aerospace hardware are: (1) detailed consideration of fracture mechanics and fatigue effects, particularly in welding very thick materials to very thin materials; (2) designing, testing, and qualifying coupons of new weld configurations; (3) locating welds to avoid bending forces that concentrate stresses in the weld bead area; and (4) the design of joints that accommodate adequate visibility, tool access, and inspectability. Conscientious adherence to the team approach to weld configuration and process design will account for these and many other factors that will result in defect-free, inspectable, and reliable welds. NONDESTRUCTIVE EVALUATION OF WELDS In addition to visual inspection, there are a number of methods to inspect welds. These include x-radiography, ultrasonics, eddy current, dye penetrant, and magnetic particle inspection. Real-time inspection can be performed while the welding is being performed in automated systems that incorporate weld bead profiling, infrared detection, and x-ray image display graphics. Although x-radiography is suitable for detecting voids or discontinuities in the weld or the parent material, fine surface cracks often go undetected. Double-walled inspections by this method should be avoided. This method is limited by the welded part configuration because the film used to record the x-ray image must be placed to provide a suitable angle of incidence. Ultrasonics has some physical limitations due to thickness and angle of assembly of parts (angles less than 45 degrees cannot be effectively inspected using ultrasonics). Eddy current inspection, which measures induced current in the weld and parent material in the presence of a magnetic field, requires highly skilled technicians, but is a favored method of weld inspection for many weld NDE situations. Both the ultrasonic and eddy current methods are sensitive to most weld and parent material flaws. Real-time inspection and recording of NDE results, as is done with automated weld bead profiling, provides a permanent record of weld parameters as the weld bead is generated. Automated NDE techniques offer the advantage of on-site correction of welding operations before detrimental effects of inaccurate welding become excessively costly. Technical Rationale: The design and processing recommendations in this practice have evolved over several decades of fabricating large aerospace vehicles and related ground support equipment. Rationale is documented in greater detail in the standards, specifications, technical memoranda, and reports listed as references. General processes are included in References 1, 2, and 7 through 9. Specific experience on VPPAW is described in References 5 and 6. The effect of impurities in plasma arc welding gasses was explored in an in-depth contracted effort by the University of Texas at El Paso (Reference 4). The causes of and remedies for microfissuring of welded Inconel 718 are described in Reference 3. Work is continuing to further explore and document effective practices for welding automation and nondestructive testing procedures. This continuing work will be the basis for additional practices that may be submitted for publication at a later date. References: Publications that contain additional information related to the practice are: Nunes, Jr., A. C., quotA Comparison of the Physics of Gas Tungsten Arc Welding (GTAW), Electron Beam Welding (EBW), and Laser Beam Welding (LBW),quot NASA TM 86503, NASA/MSFC, August 1985. Yang, H. Q. and Przekwas, A. J., quotA Mathematical Model to Investigate Undercutting and to Optimize Weld Quality,quot CFRDC Report 4095/2, CFD Research Corporation, June 1990. Nunes, Jr., A. C., quotInterim Report on Microfissuring of Inconel 718.quot NASA TM-82531, NASA/MSFC, June 1983. McClure, John C., quotThe Effect of Impurity Gasses on Plasma Arc Welded 2219 Aluminum,quot NAS-8-37425, The University of Texas at El Paso, August 1989. Nunes, Jr., A. C., quotThe Variable Polarity Plasma Arc Welding Process: Its Application to the Space Shuttle External Tank - First Interim Report,quot NASA TM-82532, NASA/MSFC, June 1983. Nunes, Jr., A. C., quotThe Variable Polarity Plasma Arc Welding Process: Its Application to the Space Shuttle External Tank - Second Interim Report,quot NASA TM-86482, NASA/MSFC, November 1984. Schuerer, Paul H., quotWelding Aluminum Alloys,quot MSFC-SPEC-504C, NASA/ MSFC, November 1990. Schwinghamer, R. J., quotWelding: The Fusion Welding of Steels, Corrosion and Heat Resistant Alloys,quot MSFC-SPEC-560A, NASA/MSFC, June 1988. quotWelding, Electron Beam, Process for,quot MIL-W-46132, Department of the Army, February 1989. Definitions of Selected Welding Terms* arc welding (AW). A group of welding processes that produces coalescence of metals by heating them with an arc, with or without the application of pressure, and with or without the use of filler material. arc welding electrode. A component of the welding circuit through which current is conducted and which terminates at the arc. backing. A material or device placed against the back side of the joint to support and retain molten weld metal. The material may be partially fused or remain unfused during welding and may be either metal or nonmetal. defect. A discontinuity or discontinuities that by nature or accumulated effect (for example, total crack length) render a part or product unable to meet minimum applicable acceptance standards or specifications. downhand. A nonstandard term for flat position. flat position. The welding position used to weld from the upper side of the joint. The face of the weld is approximately horizontal. fusion. The melting together of filler metal and base metal (substrate), or of base metal only which results in coalescence. galvanic corrosion. Galvanic corrosion manifests itself in the accelerated corrosion of the more active metal (anode) of a dissimilar metal couple in an electrolyte solution or medium, and decreased corrosive effects on the less active metal (cathode), as compared to the corrosion of the individual metals, when not connected, in the same electrolyte environment. (MIL-STD-889B:7 July 1976) hot cracking. Cracking that develops during solidification. inclusions. Particles or fibers of foreign materials and substances in the completed weld. lead angle. Alignment of the welding device perpendicular (90 degrees) to the weld joint in the direction of travel would represent a zero lead angle. An increase of up to 3 degrees above 90 degrees in the direction of travel represents the recommended positive lead angle. microfissuring. The formation of small cracks in the weld metal or weld heat-affected zone within the grain boundaries or low melting constituent regions resulting from weld thermal stresses that can occur during welding. mismatch (offset). An unintended nonplanar match of parallel work pieces resulting from the welding process. peaking. An unintended angular displacement of the weld joint that can occur during welding. penetration. The depth a weld extends from its face into a joint, exclusive of reinforcement. porosity. Cavity-type discontinuities formed by gas entrapment during solidification. postheating. The application of heat to an assembly after welding. seam tracking. Alignment with respect to the joint of the welding device as it progresses along the interface between the two materials being joined. stress corrosion cracking. Failure of metals by cracking under combined action of corrosion and stress, residual or applied. tack weld. A weld made to hold parts of a weldment in proper alignment until the final welds are made. undercut. A groove melted into the base metal adjacent to the weld and left unfilled by weld metal. vertical position. The position of welding in which the weld axis is approximately vertical. weldability. The capacity of material to be welded under the imposed fabrication conditions into a specific, suitably designed structure and to perform satisfactorily in the intended service. weld axis. A line through the length of a weld, perpendicular to and at the geometric center of its cross-section. weld bead. A weld resulting from a pass. welder certification. Certification in writing that a welder has produced welds meeting prescribed standards. weld pass. A single progression of welding or surfacing along a joint or substrate. The result of a pass is a weld bead. *Adapted from American Welding Society, Inc.; Standard Welding Terms and Definitions; ANSI/AWS A3.0-85 | Programs That Certified Usage: Saturn I, Saturn V, Space Shuttle External Tank, and Space Shuttle Main Engine. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 03/06/2000
893 | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wilson - 0000000000 : NO@ADDRESS.GIVEN |  | Selection of Electric Motors for Aerospace Application |  | Failure to adhere to proven electric motor selection practices could cause shortened mission life, premature cessation of component or experiment operation, mission failure, and in extreme cases, loss of mission or life. | Careful attention is given to the specific application of electric motors for aerospace applications when selecting motor type. The following factors are considered in electric motor design: application, environment, thermal, efficiency, weight, volume, life, complexity, torque, speed, torque ripple, power source, envelope, duty cycle, and controllability. Brushless direct current motors have been proven to be the best all-around type of motors for aerospace applications because of their long life, high torque, high efficiency, and low heat dissipation. | MSFC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number PD-ED-1229 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Selection of the optimum electric motor for space flight operations results in a safe, reliable, effective, efficient, and economical electric motor power source for space flight. Brushless direct current motors provide the lightest weight alternative for most applications. Implementation Method: Four principal types of electric motors are suitable for in-space applications; AC Induction Motors, Brush Direct Current (BDC) Motors, Brushless Direct Current (BLDC) Motors, and Stepper Motors. Table 1 shows the most predominant applications for each type of motor. [D] Generally AC Induction Motors are used for constant speed applications where a fixed frequency power source such as 60 Hz or 400 Hz is available in the spacecraft. Typical applications are fans and pumps. Motor construction consists of windings on the stationary part of the motor and copper shorting bars on the iron laminations of the armature. The AC voltage applied to the windings induces a current in the armature of the rotor, creating a magnetic field. This field reacts with the field in the stationary part of the motor to create torque. These motors are rugged with no wear out mechanisms other than the bearings. The BDC motors use commutators and carbon brushes to apply current through the windings as the motor rotates. The BDC motor uses wound elements in the rotor and permanent magnets attached to a stationary stator ring. In a BDC motor, electrically separated motor windings are connected to the commutator ring. Current is carried by spring loaded brushes, through the commutator into the windings of the rotor. The current in the windings creates magnetic fields, which react with the stator's permanent magnetic field. These magnetic repulsion causes the rotor to rotate. This rotation causes the brushes to make and break connections through the commutator with different windings pairs. The moving magnetic field provides the torque necessary to rotate the motor's armature. The BLDC motor uses electronic commutation to control the current through the windings. The BLDC motors use permanent magnets on the rotor. The BLDC motors contains rotor position sensor electronics so that the power input wave form to the windings is in sequence with the proper rotor position. Motor efficiency is enhanced because there is no power loss in the brushes. In the BLDC motor, the stator is wound with electromagnetic coils that are connected in a multiphase configuration, which provides the rotating field, and the armature consists of a soft iron core with permanent magnet poles. Sensing devices define the rotor position. The commutation logic and switching electronics convert the rotor position information to the correct excitation for the stator phases. Sensing devices include hall-effect transducers, absolute encoders, optical encoders, and resolvers. The electronic controller can be separate or packaged with the motor. BLDC motors are preferred over BDC motors for most space environments. If BDC motors are used, the qualification of brush motors for the space environment is both expensive and time consuming. The advantages and disadvantages of the two types of DC motors are listed in Tables 2 and 3. [D] [D] Application gives the designer the intended use and could perhaps optimize an existing design. The no-load speed, stall torque, and the load point are used to establish the motor torque loadline. Knowing the no load speed and available voltage, the designer can establish an initial back EMF constant and the motor torque constant. The stall torque combined with the load point torque helps establish motor size. The duty cycle, temperature, and expected heat sinking are used with the motor size to determine the temperature rise of the motor. The design is optimized to meet the customer's requirements. Since the BLDC and stepper motors are the most predominant motors used for aerospace applications, an expanded listing of applications and requirements is shown in Table 4. [D] Stepper motors are a special case of BLDC Motors. Construction is identical except that they contain no position sensors. Excitation is sequentially applied to the windings, creating the rotating field to produce torque. The advantages are simplicity and compatibility with digital control schemes. Disadvantages are high continuous power dissipation and high ripple torque. The system designer typically requires the motor information listed in Table 5. [D] Technical Rationale: Selection of the appropriate motor for a given application permits more reliable operation, while minimizing weight, power consumption, and thermal dissipation requirements. References Sokira, Thomas J. and Wolfgang Jaffe: 'Brushless DC Motors Electronic Commutation and Controls,' Tab Books, Inc., Blue Ridge Summit, PA, 1990 Dang, Ngon T.: 'Overcoming Brushless DC Motor Limitations,' Electronic Products, Pgs. 63-67, July 1993 'Brushless DC Motor Handbook,' Inland Motor, Kollmorgen Corporation, Radford, VA 1989. | This practice has been used on Tethered Satellite System (TSS), Solar Max Mission (SMM), Infra-Red Telescope (IRT), Saturn 1B (S1B), Saturn V (SV), Skylab, High Energy Astronomy Observatory (HEAO), Lunar Roving Vehicle (LRV), Hubble Space Telescope (HST), Advanced X-Ray Astrophysics Facility (AXAF), and other MSFC projects. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/06/2000
664 | Raynor, Eric - 0000000000 : NO@ADDRESS.GIVEN | Raynor, Eric - 0000000000 : NO@ADDRESS.GIVEN |  | SOHO Mission Interruption Joint NASA/ESA Investigation Board |  | The Board has concluded that there were no anomalies on-board the SOHO spacecraft but that a number of ground errors led to the major loss of attitude experienced by the spacecraft. The Board finds that the loss of the SOHO spacecraft was a direct result of operational errors, a failure to adequately monitor spacecraft status, and an erroneous decision which disabled part of the on-board autonomous failure detection. Further, following the occurrence of the emergency situation, the Board finds that insufficient time was taken by the operations team to fully assess the spacecraft status prior to initiating recovery operations. The Board discovered that a number of factors contributed to the circumstances that allowed the direct causes to occur. FACTORS DIRECTLY CONTRIBUTING TO THE LOSS The Board has concluded that there were no anomalies on-board the SOHO spacecraft but that a number of ground errors led to the major loss of attitude experienced by the spacecraft. The first two errors were contained in predefined command sequences executed from the Ground System, while the last error was a decision to send a command to the spacecraft in response to unexpected telemetry. The sequence of these errors and their relationship to the triggered-ESRs are graphically depicted in Diagram 1. [D] Diagram 1. Failure Event Tree - Top Level (Click image for a larger view) This series of events was preceded by a routine calibration of the spacecraft's three roll gyros. As stated earlier, the gyros are not required during most of the mission. They are used for thruster-based activities such as momentum management, ISA, and ESR. Since the gyro calibration in the compressed timeline is immediately followed by the execution of momentum management, the previously employed procedure to despin the gyros at the end of the gyro calibration and to re-enable the on-board software gyro control function was not required. Following gyro calibration, Gyro A was specifically deactivated (despun) in order to conserve its life, while Gyros B and C remained fully active. Due to an omission in the modified predefined command sequence actually used, the onboard software function that activates the gyro needed by ESR was not enabled. This omission resulted in the removal of the functionality of the normal safe mode and ultimately caused the catastrophic sequence of events. Following the momentum management maneuver, Gyro B, which is used for fault detection, was erroneously left in its high gain setting, resulting in an indicated roll rate of 20 times greater than actual. The incorrect gain was due to an error in another predefined command sequence; this error resulted in an on-board fault detection output that triggered an ESR. This ESR, the 5th since launch, occurred at 7:16 PM EDT (23:16 UT), June 24, 1998. During ESR-5, the control Gyro A was not active because of the first error referenced above; however, there is no evidence or belief that any anomalous spacecraft behavior had occurred. As per design, the ESR event resulted in a reconfiguration of the gyros. Gyro A replaced Gyro C as the roll gyro used for the ESR thruster-based control mode, while Gyro B remained configured as the fault detection gyro. The error in Gyro B's gain was discovered and corrected, but the Gyro A despun status was not identified. After transitioning to the ISA mode as part of the normal ESR recovery sequence, the attitude control system began integrating the gyro drift rate bias associated with the still despun Gyro A. After 15 minutes, this resulted in roll thruster firings intended to null the apparent (but non-existent) roll attitude error. In less than one minute, the roll rate was sufficiently high to trigger the Gyro B based fault detection once again, resulting in ESR-6 at 10:35 PM EDT (02:35 UT), June 24, 1998. Although the spacecraft remained Sun-pointing within nominal limits and was therefore in a power-positive and thermally-safe attitude, the state of the spacecraft was precarious at this point in time. It had an anomalous roll rate and was depending on a deactivated gyro for roll control in both ESR and ISA modes. The personnel on the ground were not aware of either of these facts at that time. Gyro C was correctly configured to the ACU since the reconfiguration at ESR-5. Gyro B was active and on-line for fault detection, and it was correctly measuring the anomalous roll rate. A rapid decision was made that Gyro B was faulty because its output disagreed with the rate indicated by Gyro A. This decision led to the commanding off of Gyro B. During ESR-6 recovery, Ground Operations commanded the spacecraft to ISA mode. In ISA, the attitude control system resumed firing roll thrusters in an attempt to null the attitude error associated with the electrical rate bias term of the despun Gyro A. Gyro B and the associated fault detection were now inactive. The increasing roll rate eventually resulted in pitch and yaw Sun-pointing errors that exceeded a prescribed limit of five degrees, resulting in ESR-7 at 12:38 AM EDT (04:38 UT), June 25, 1998. Due to the gyroscopic cross-coupling torques caused by pitch and yaw thruster firings, and the absence of true roll rate indications, the ESR controller was no longer stable, and the spacecraft attitude diverged. The incorrect diagnosis of a Gyro B fault and the subsequent ground response to this diagnosis ultimately resulted in loss of attitude control, subsequent loss of telemetry, and loss of power and thermal control. Loss of telemetry occurred at 12:43:56 AM EDT (04:43:56 UT), June 25, 1998. It can not be determined whether this loss was a consequence of insufficient power or a loss of communication link caused by spacecraft attitude. At any time during the over five hour emergency situation, the verification of the spinning status of Gyro A would have precluded the mishap. For further information, a more detailed timeline summarizing the sequence of events leading up to the mishap is provided in Appendix C. A detailed fault tree analysis supporting the above scenario and the Board's conclusions has been performed by MMS and is on file. FACTORS INDIRECTLY CONTRIBUTING TO THE FAILURE: Ground Procedures (failure to control change; failure to perform risk analysis of a modified procedure set; Failure to comunicate change). Procedure Implementation (failure to properly respect autonomous Safe Mode triggers; Failure to follow the operations script; failure to evaluate primary and ancillary data; failure to question telemetry discrepancies) Management Structure and Process (Failure to recognize risk caused by operations team overload; failure to recognize shortcomings in implementation of ESA/NASA agreements; emphasis on science return at expense of spacecraft safety; Over-reliance of flight operations teams on ESA and MMS representatives; dilution of observatory engineering support) Ground Systems (Failure to resolve a critical deficiency report in a timely manner; failure to validate the planned sequence of events in advance) | The Board strongly recommends that the two Agencies proceed immediately with a comprehensive review of SOHO operations addressing issues in the ground procedures, procedure implementation, management structure and process, and ground systems. This review process should be completed and process improvements initiated prior to the resumption of SOHO normal operations. The recommendations are described below in detail. GROUND PROCEDURES An ESA and NASA review of the process for SOHO operational procedure change should be implemented forthwith. The review should critically assess the process from beginning to end. The review should include matters such as who can initiate a change, who agrees it should be made, how is the modification process monitored, how is it validated, how is it introduced into operations, how it is signed-off, how are the users of the procedure informed of the change, and how are users trained on the new version. All SOHO procedures modified since launch should be identified and subjected to a thorough review of the changes made and their verification and validation status. The review should be led by ESA and supported by MMS, NASA, and the FOT. This review should be completed before the resumption of routine operations. If there is any doubt about a procedure, it should be re-validated. PROCEDURE IMPLEMENTATION NASA should perform an immediate comprehensive audit of all ISTP on-going flight operations activities to assess conformance to contractual requirements addressing areas such as leadership, configuration management, roles/responsibilities, anomaly handling, and general procedure implementation and validation. The activities pertinent to SOHO should include ESA in the review. ESA and NASA should review the decision authority for real-time divergence from agreed upon ground or spacecraft procedures. In the event that a problem is encountered during any procedure execution, the decision authority for the subsequent action must be clearly defined. Spacecraft safety must never be compromised. It is critical that NASA should review the relevance of selected metrics to determine adequacy for contractor performance evaluation. MANAGEMENT STRUCTURE AND PROCESS ESA and NASA should review the allocation of their responsibilities for the operation of the SOHO mission, as defined in the STSP MOU, Program Plan, and SOHO Mission Management Plan. Assessment should be made as to how these responsibilities have been undertaken by both parties. Changes should be proposed and implemented where appropriate. In particular, ESA's responsibilities for the technical integrity and safety of the spacecraft and science instrumentation and NASA's responsibilities for Ground Segment infrastructure and the conduct of the mission in accordance with the approved Flight Operations Plan should receive critical focus. This review should be preceded by internal reviews in both Agencies and completed prior to return to normal operations. It is anticipated that the review should result in an improved Mission Management Plan. ESA and NASA should re-assess staffing to ensure it is commensurate with the complexity and criticality of the SOHO mission and consistent with the updated Mission Management Plan. The staffing should be strengthened as required. Surge capability should exist to support non-routine and contingency operations. NASA should perform a risk-based analysis of operations plans to determine the level of insight/oversight appropriate for joint, cooperative, and PI missions with special attention to accountability. GROUND SYSTEMS All operational timelines should be planned and validated well before implementation with proper attention to risk assessment and contingency planning. The operations scripts (the string of procedures used by the FOT) for other than routine science operations should be put under configuration control and any change formally approved by ESA and NASA. Each time such a script is changed, the whole script should be validated. Flight operations should verify response to spacecraft configuration changes and critical commands to ensure proper execution. Flight operations should verify configuration prior to initiating critical spacecraft activity to ensure it is consistent with planned events. ESA/ESOC should lead an independent assessment of the capabilities of the NASA SOHO simulator and provide recommendations for suggested maintenance and enhancements. The FOT should review the current database to ensure that all critical parameters are flagged as out-of-limits (and preserved) if they violate values as defined in the ESA provided satellite users manual. If possible, automatic monitoring should be extended to all telemetry. An ESA and NASA board should review all outstanding Ground System Problem Reports and the plans to close them. ESA and NASA flight operations personnel should be conversant with both the ESA and NASA systems to the maximum extent possible to form a more synergistic, integrated team. | HQ | 11/30/1999 | Contact with the SOlar Heliospheric Observatory (SOHO) spacecraft was lost in the early morning hours of June 25, 1998, Eastern Daylight Time (EDT), during a planned period of calibrations, maneuvers, and spacecraft reconfigurations. Prior to this the SOHO operations team had concluded two years of extremely successful science operations. A joint European Space Agency (ESA)/National Aeronautics and Space Administration (NASA) engineering team has been planning and executing recovery efforts since loss of contact with some success to date. ESA and NASA management established the SOHO Mission Interruption Joint Investigation Board to determine the actual or probable cause(s) of the SOHO spacecraft mishap. |  | N/A |  | Science | Public | Not Specified |  | 03/06/2000
665 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Oil-Free Vacuum Pumps in the LOX/LH2 Transfer System |  | All oil-sealed mechanical pumps backstream oil to some extent. As the oil becomes hot from the operation of the pump and the pressure falls into the molecular flow regime hydrocarbon vapors will rise from the pump. Surface creep will also occur right out of the pump itself with the oil reservoir within the pump acting as the source. In many cases, this constant surface flow of oil from the mechanical pumps are the greatest single source of hydrocarbons that can enter the vacuum chamber. Oil-sealed pumps can go into quothydraulic lockupquot if a power outage would occur and the pumps have to be constantly manned. The use of an oil operated type vacuum pump has disadvantages from both a cost and reliability stand point. A single vacuum jacketed section recently contaminated cost $4,031 when returned to the vendor for oil removal. This was the vendor's charge only, and did not include shipping, removal and replace or testing cost. | Oil-free pumping is the latest state of art in vacuum pump technology. At Kennedy Space Center, this technology is used to maintain approximate 650 sections of the LOX/LH2 vacuum jacketed transfer lines, at a pressure between 0-1000 Torr. This insures the capability to deliver cryogenic propellants on time and at a pre-defined temperature and pressure to the Shuttle vehicle. The use of oil-free pumps eliminates the risk of contaminating the LOX/LH2 transfer system (vacuum jacketed lines). It enhances the reliability of the vacuum pumping system. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number GSE-3010 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The major benefits for the use of oil-free vacuum pumps in the LOX/LH2 transfer system is that these pumps eliminate the danger of oil or oil molecule contamination and can be safely operated unmanned. This results in both cost saving and a reliability improvement in the pumping process. Implementation Method: The implementation of oil-free vacuum pumps has resulted in eliminating the danger of oil contaminants, increased reliability and has resulted in a reduced support costs. Technical Rationale: Oil-free pumps offer many advantages over the oil sealed pumps. The oil-free pumps are light-weight, truly portable, highly versatile, and the absence of fluids means the pump can be operated in any orientation - sideways or upside down. There are a number of considerations that affect the decision of whether to use an oil-free or an oil-sealed pump. First, and most important, is the determination of whether the application is sensitive to oil contamination. If it is determined that the application is oil sensitive, the next consideration is whether or not a foreline trap is sufficient to prevent the backstreaming oil from entering the process chamber in quantities that will cause contamination problems, if not then consideration should be given to use of oil-free pump. Oil-Sealed Type Pumps: The foreline traps (oil-sealed mechanical pump) is one type of pumping system that the LOX/LH2 system engineers considered for use in the LOX/LH2 transfer system vacuum jacketed lines. The following paragraphs discuss some of the characteristics of the foreline trap pump and figures 1, 2, and 3 show the creeping surface that can cause oil contamination. Foreline or roughing traps have been used for a number of years in an attempt to stop or reduce the oil backstreaming from oil-sealed mechanical pumps. Although they have had great commercial success in terms of number of units used, they have a number of problems that need be weighed carefully if they are to be considered as a method of stopping the pump oil from entering the chamber. Three types of foreline traps are commercially available: Condensation traps, Cryogenic Absorption traps, absorbent trapping medium Absorption traps, active surface trapping medium All have a potential problem that needs constant consideration. They have room temperature walls which will allow liquid oil to coat the inner surfaces and once the oil has passed through into the system side of the trap, it becomes a vapor source that can no longer be prevented from entering the system. The amount of time required for the surface oil to work its way through the trap will vary with the application. The best way of determining when oil is passing through is to occasionally remove the trap from the pumping line and placing a drop of water inside the tubulation on the system side to see whether it beads or spreads. Once oil is detected on the system side, itís time to solvent clean the trap or to bake out the entire trap, walls and all. The time to fully penetrate through the trap will be extended if the mechanical pump is shut off and the trap (fore or roughing line) is air released when the pump is not being used. [D] The LOX/LH2 System Engineers selected the oil-free type pump shown in figure 4, because this pump incorporates new vibration isolation techniques, new 3-stage pumping technology, simplified construction for easy maintenance and increased reliability. This type pump will probably have higher initial costs than an oil-sealed mechanical pump. Figure 4, shows a picture and Block Diagram of an oil-free pump. Oil-Free Pumps The following paragraphs briefly discuss some of the characteristics and advantages of an oil-free pump. Unique design: The key to this type pump performance is a unique three-stage design, which incorporates a molecular drag module backed by two customized diaphragm modules to provide a constant, dynamic flow of gas. Each module functions selectively in series, automatically carrying the pumping burden within its own pressure/flow envelope. As each successive stage acquires the primary pumping burden, the previous stage continues pumping in a support capacity. Entirely oil-free: Since no module uses pump fluids, roughing or backing with this type pump introduces no oil to backstream into a system. They require no traps, oil filtration accessories, or special oils as all mechanical pumps do. Since traps are unnecessary, oil-free pumps without a trap can deliver their full pumping speed. Mechanical pumps with traps inevitably experience speed losses. Clean, efficient backing: These type pumps provide highly efficient backing for turbo or diffusion pumps, improving their performance by providing a lower foreline pressure. In most cases, an oil-free pump will help achieve vacuum up to an order of magnitude higher than mechanical type pump. Versatile: Oil-free pumps will pump any gas, including hydrogen and helium, and any condensables, e.g., solvents or water vapor. They never load up with quotmemoryquot gases. Easy to use and repair: The oil-free pump requires no cryogenic or bakeout procedures. Because the molecular drag and diaphragm modules are separate, each can be easily repaired in the field or, if necessary, completely replaced. [D] References: KSC Problem Report Number S70-0817-00-001-0553, dated 5/9/89 | This practice has been used on the Space Shuttle Program, Shuttle Main Propulsion System (LOX/LH2),Ground Support Equipment. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 03/06/2000
696 | Harkins, Wilson - 202.358.0584 : wilson.b.harkins@nasa.gov | Harkins, Wilson - 202.358.0584 : wilson.b.harkins@nasa.gov |  | Spectral Fatigue Reliability |  | Failure to adequately consider fatigue in the design of structural and mechanical components subject to fluctuating loads may, at best, result in recurring costs for repair or replacement of components before their intended design life. At worst, a catastrophic failure, in terms of economic loss and loss of life, may result. Alternatively, outdated design practices which do not take advantage of modern methods of reliability analysis may result in overconservative and uneconomical structures and mechanisms. | A spectral (frequency domain) technique is used to estimate the design fatigue life and reliability of structural and mechanical components subject to randomly varying stress. | HQ | 01/31/1999 | This Lesson Learned is based on Reliability Guideline Number GD-AP-2303 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Consideration of fatigue reliability during the design process can assist in the prevention of failures of structural and mechanical components subject to fluctuating loads in service. Explicit consideration of the reliability of structural and mechanical components provides the means to evaluate alternative designs and to ensure that specified risk levels are met. Probabilistic fatigue analyses may also be applied to life extension of existing structures, and for problem assessment of in-service fatigue failures. Potential applications of this guideline to the Space Shuttle or International Space Station Alpha Programs include: landing gear, control surfaces, main engine components, auxiliary power unit components, external tank and solid rocket booster welds, pressure vessels, propulsion modules, and logistics modules. Implementation Method: A detailed discussion of the procedures for performing a spectral fatigue reliability analysis may be found in reference 1. A quotclassicalquot fatigue approach is described which utilizes the constant amplitude S-N curve characterization of a material's or component's fatigue resistance capability. The applied random loads are characterized by their power spectral density (PSD), and crack initiation locations (or hot spots) are determined by an analytical or experimental stress analysis. A structural dynamic analysis or test is used to determine the harmonic response function, H(w), which relates external loads to nominal internal stress. The mean or average fatigue life, T, is computed using either the Rayleigh [references 2, 3, and 4] or Single-Moment methods [references 5 and 6]. For high-cycle fatigue (high number of cycles) the uncertainty or randomness in the fatigue life due to the random loading is negligible (although load uncertainty is generally problem specific) [reference 2], but considerable uncertainty remains due to intrinsic metallurgical and geometric variations. In the usual deterministic fatigue analysis practice this uncertainty is accounted for by reducing the computed fatigue life by a quotscatter factorquot of 2 to 4 to determine the quotsafequot life. In a probabilistic approach the metallurgical and geometric variations are more rationally included by modeling them as random variables, using data from the S-N curve fitting and/or from the stress analysis. Sufficient data is necessary for statistical treatment (such as correlation analysis and distribution fitting) and is discussed in reference 1. However, even in cases for which sufficient problem specific data does not yet exist for rigorous statistical treatment, probabilistic risk assessment (PRA) methods may be used to construct distributions for the variables based on experts' opinions of the variables' range and likely values. Such an approach is useful as a first approximation until problem specific data becomes available and has the advantage of formally using the same quotexpert dataquot (engineering experience) that is usually only informally used in selecting the quotscatter factorquot. The resulting expressions for the distribution of the time to failure are generally not amenable to solution by analytic techniques. However, modern numerical structural reliability methods [reference 7] are available for solving these types of problems in several commercial software packages, such as PROBAN [reference 8], STRUREL, and NESSUS. These programs allow the characterization of any number of parameters in a problem as random variables. Usually this requires the characterization of the problem in the form of a mathematical expression or a computer subroutine which relates the input variables to some characteristic output variables which determine the failed or safe state of the system modeled. Simulation methods such as Monte Carlo, importance sampling, latin hypercubes, directional sampling, or axis-orthogonal sampling are also available in PROBAN. A Monte Carlo simulation approach to a Space Shuttle Main Engine fatigue problem is also described in reference 9. These methods are compared and their relative merits are discussed in reference 1. The results of a probabilistic fatigue analysis are usually expressed as the probability of failure as a function of time. For dealing with very high reliabilities, the reliability index, b, is often used as defined by: [D] An example of the change in reliability with time due to fatigue is given in Figure 1. The corresponding plot of reliability index as a function of time is given in Figure 2. The details of this example are given in reference 1. The expected or average time to failure for this example is 1265 seconds, at which time the reliability is 50% and the reliability index is zero. Also shown in Figures 1 and 2 are the times corresponding to the usual definition of quotsafe lifequot determined by using a scatter factor of 2 to 4. Using a scatter factor of 4 results in a safe life of 316 seconds, while a scatter factor of 2 gives a safe life of 632 seconds. Adoption of a reliability approach would allow specification of the safe life as the time at which the reliability or reliability index decreased below some minimum acceptable level. In this example that level was chosen to be the quot3-sigmaquot level, at which the reliability is 99.865% or the reliability index is 3.0. This results in a safe (or allowable) life of 869 seconds, a 37% increase in allowable life compared to the scatter factor of 2 life, and a 175% increase compared to the scatter factor of 4 life. The conservatism inherent in the deterministic scatter factor approach is illustrated more clearly in Figure 2. In this example a scatter factor of 2 corresponds to a reliability index of 5.6, while a scatter factor of 4 corresponds to a reliability index of 11.2. Fatigue Reliability Index as a Function of Time [D] [D] Use of a probabilistic method allows the uncertainty in fatigue life or time to failure to be more explicitly accounted for than is possible in the quotscatter factorquot approach. Sensitivity analysis methods are also available in some of the commercial software packages, allowing the uncertain input variables to be ranked according to their contribution to the uncertainty in the resulting life estimate. This enables a more timely and cost effective design optimization by identifying the most important input parameters upon which resources should be concentrated to gain the greatest increase in life. This approach naturally leads to a design risk assessment and requires the development and selection of a specific criteria for defining acceptable risk or probability of failure. The acceptable risk value should be specified in the appropriate program requirements, but the selection process is a program and policy issue which is beyond the scope of this guideline. Some guidance is available from the various national civil structural requirements codes that have been formulated to provide reliability indices of 3 to 5, depending on the importance of the structure and the consequences of failure [reference 7]. This method is primarily useful as a design evaluation or optimization tool and cannot easily be used to evaluate the remaining life of an in-service component unless instrumentation (such as strain gages, accelerometers, or load cells) is in place to allow collection of data on the actual performance of the component. In cases where the necessary in-service data is available, this method may prove very useful for extending the life of the component or structure beyond its original predicted service life. If inspection of the component or structure by a non-destructive evaluation (NDE) method is feasible, the probabilistic fracture mechanics method described in the companion guideline is more useful for estimating damage and remaining life of in-service components than the fatigue analysis method. A measured crack length provides information about the in-service state of the structure, and the probabilistic fracture analysis may be updated following the inspection to this new information. If inspection is not feasible, the fracture mechanics method has no particular advantage over the fatigue method for in-service assessments. Technical Rationale: The potential loss of strength in structural/mechanical components due to the cumulative damage effect of fluctuating applied loads is well known. Spectacular failures have resulted from fatigue since the beginning of the industrial revolution. The danger of fatigue in new applications, however, has not always been adequately considered in the design process and continues to be a concern to this day. A classic example is the British Comet airliner, which was one of the first aircraft to employ an aluminum-skin, pressurized fuselage. The loss of three aircraft and many lives in 1953 and 1954 occurred before the potential for fatigue in this application was understood. Results from the theory of stochastic process and modern structural reliability methods enable the design engineer to assess the expected fatigue life of structural and mechanical components subject to randomly varying loads, and to estimate how the probability of failure of the component increases over time. The application of these data will enable optimal designs to be achieved which balance the initial costs of design and fabrication against the expected costs of repair, replacement, and/or failure. References: NASA Contractor Report, Larsen, C.E., quotProbabilistic Fatigue and Fracture Mechanics Analysis for Structural/Mechanical Reliabilityquot, To be released, 1994. Crandall, S.H., and Mark, W.D., Random Vibration in Mechanical Systems, Academic Press, New York, 1973 Miles, J.W., quotOn Statistical Fatigue Under Random Loadingquot, Journal of Aeronautical Sciences, Vol. 21, 1954, pp. 753-762 Wirsching, P.H., and Light, M.C., quotFatigue Under Wide Band Random Stressquot, Journal of the Structural Division, ASCE, Vol. 106, No. ST7, July, 1980, paper 15574, pp. 1593-1607 Lutes, L.D., and Larsen, C.E., quotImproved Spectral Method for Variable Amplitude Fatigue Predictionquot, Journal of Structural Engineering, ASCE, Vol. 116, No. 4, April, 1990, paper 24612, pp. 1149-1164 Larsen, C.E., and Lutes, L.D., quotPredicting the Fatigue Life of Offshore Structures by the Single-Moment Spectral Methodquot, Probabilistic Engineering Mechanics, Vol. 6, No. 2, June, 1991, pp. 96-108 Madsen, H.O., Krenk, S., and Lind, N.C., Methods of Structural Safety, Prentice-Hall, Englewood Cliffs, NJ, 1986 PROBAN-2: Example Manual, Report No. 89-2025, A.S Veritas Research, Hovik, Norway, August, 1989 Sutharshana, S., et al., quotProbabilistic High Cycle Fatigue Failure Analysis Applicable to Liquid Propellant Rocket Enginesquot, Proceedings of the AIAA/ASME/ASCE/AHS/ASC 31st Annual Structures, Structural Dynamics and Materials Conference, April, 1990 Reliability Preferred Practice Guideline Number GD-AP-2304: Fracture Mechanics Reliability |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/04/2000
697 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Active Redundancy |  | The designer should consider redundancy for reliability improvement of critical components having low reliability for which a single failure could cause loss of a system or one of its major functions, i.e. loss of control, unintentional release or inability to release space hardware, failure of space installation systems, or harm to the crew. Building a flight assembly that has low reliability can cause problems in qualification and acceptance testing, launch preparation and flight activities, schedule delays, and budget overruns. | Use active redundancy as a design option when development testing and reliability analysis show that a single component is not reliable enough to accomplish the function. Although active redundancy can be applied to various types of mechanical and electrical components and systems, the application detailed in this practice illustrates an approach using a Traveling Wave Tube amplifier in a space flight application. | GRC | 01/31/1999 | This Lesson Learned is based on Reliability Practice No. PD-ED-1216; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Provides multiple ways of accomplishing a function to improve mission reliability. Implementation Method: The decision to use redundant design techniques should be based on analysis of reliability and test data. Redundancy may prove to be the only available method when other techniques of improving performance (e.g., better components, additional derating, simplification, software debugging) have been exhausted or when methods of item improvements are shown to be more costly than duplications. The use of redundant equipment can allow for repair with no system downtime. Some situations exist in which equipment cannot be maintained (e.g., communication satellites), in which case dormant redundant elements may be a necessary approach to prolong operating time. The application of redundancy is not without penalties. It will increase weight, space, complexity, and time to design, fabricate, assemble, and test. It may also increase costs; however, the costs may be recovered by the increased reliability. Thus, safety and mission reliability is gained at the expense of adding more items to test. The increase in testing time may be reduced by making improvements in the components such as the use of more reliable parts, more derating, design simplification, and software improvements. The incorporation of redundancy into a design must take into account quotcheckable redundancy.quot It is important to be able to functionally test the redundant elements prior to mission start. If this capability is not present, the benefits of redundancy may be defeated by the uncertain functionality. However, if the designer takes into account built-in test planning, inclusion of test points, and packaging, the benefits of active redundancy will be retained. Technical Rationale: As an example, consider how redundancy was used in the transmitters of the Communications Technology Satellite (CTS). The component failure data for the basic nonredundant configuration of the Traveling Wave Tube (TWT) is shown in Table 1. CTS TWT Component Failure Data [D] K A= application factor =>engineering adjustment for use application The TWT serves as the final output stage and driver for the 200W transmitter. Most space applications require long operating times for earth/satellite communications. Therefore, reliability without maintenance is a major design and manufacturing concern. (The analysis used in this example assumes that the failure rates are constant over time and, therefore, the calculations are used as engineering estimates.) For the nonredundant circuit, the approximate total failure rate is given by: Failure Rate=l~ 27.4x 10 -6 failures / hour This rate is then adjusted by an operating factor based on engineering judgement to take into account the space environment, Kop: l total=lK op= (27.4 x 10 -6)(0.33) = 9.04x10 -6 failures / hour Using a mission time of 17,520 hours (2 years, the CTS performance goal), the approximate reliability for the nonredundant configuration is: R = e-ltotalt= e- (9.04 x 10-6)(17,520) R = 0.85 For the simple, redundant configuration, the approximate reliability is: Rs= 1- (1-R1)(1-R2),whereR1= R2= 0.85 Rs= 0.98 Obviously, the use of redundancy can greatly enhance the transmitter reliability and give high confidence that the two year CTS performance goal will be met. However, there are additional considerations that need to be taken into account. Specifically, we need to address the additional components added by the redundancy, such as switches, sensors, and/or activators. In this case, two switches are added in order to activate the redundancy (see Figure 1).The first switch is a coaxial transfer switch with a failure rate of 1.1 x 10-6. The second switch, a waveguide transfer switch, has a failure rate of 1.5 x 10-6. These are the only two components added due to the redundancy. The command receiver/decoder needs to operate in order to activate the switches. However, if it fails, the whole spacecraft would fail whether the redundancy is present or not. Therefore, the following additional calculations need to be made: lSWI= 1.1 x 10-6 leqTWT= 1.15 x 10-6 (sinceR = 0.98) lSW2= 1.5 x 10-6 Switched Redundant TWT Block Diagram [D] lRED=lSW1+leqTWT+lSW2= (1.5 + 1.15 + 1.1) x 10-6=3.75 x 10-6 RRED= 0.94 Therefore, the total Reliability of the redundant system is approximately 0.94. This is still a big improvement over the single component reliability of 0.85. The success of the CTS spacecraft demonstrated this improved reliability as all CTS transmitters operated beyond their performance goal of 2 years. Both the advantages and disadvantages of redundancy should be considered prior to its use. To repeat, the disadvantages of using redundancy to solve a reliability problem are increased weight, cost, and complexity. Additions of back-up systems and/or lower level items add the weight and cost of the additional hardware. This weight and cost may be reduced by the application of piece part redundancy. A more harmful effect may be increased complexity which would negate the reliability improvement. For example, sensing, activation, and switching hardware added to use the redundant component may reduce the overall reliability lower than that of the simple string. There are many cases where deliberate redundancy provides reliability improvement with cost reduction. It does not necessarily follow that simple redundancy is the cost effective way to compensate for low reliability. The design engineer has the responsibility to determine what balance of redundancy alternatives is the most effective to use. In the trade-off process, it may be determined that redundancy, by the duplication of hardware, may impact the cost of preventive maintenance. This is a significant factor in life cycle cost considerations for equipment worth. Redundancy may be practical if a designed item is readily available, and more economical than redesign. However, redundancy may be too expensive if the item is costly, or too heavy if spacecraft limitations are exceeded. These are all trade-offs which the designer must consider. References: Dillard, R.B., Reliability for the Engineer, Book Two, Martin Marietta Corporation, 1973. quotElectronic Reliability Design Handbook,quot MIL-HDBK-338-1A, October 1988. Klion, Jerome, A Redundancy Notebook, Rome Air Development Center, RADC-TR-77-287, December 1987. Lalli, Vincent R. and Speck, Carlton E., quotTraveling-Wave Tube Reliability Estimates, Life Tests, and Space Flight Experience,quot NASA TM X-73541, January 1977. quotReliability Modeling and Prediction,quot MIL-STD-756B, November 1981. | This practice has been used on Space Acceleration Measurement System (SAMS), Communication Technology Satellite (CTS), Atlas/Centaur, and Titan. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/04/2000
654 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Assessment and Control of Electrical Charges |  | Impact of Nonpractice: Adverse effects of electrostatic charges on space vehicle design, development, test and operation sometimes have been serious. Such effects include inadvertent ignition of electroexplosive devices, spurious triggering of electronics, and damage to insulating materials. The ignition, by electrostatic discharge, of the final stage solid rocket motor of the Delta launch vehicle for the Orbiting Solar Observatory spacecraft during test operations killed three men in 1964. Electrostatic discharges previously had ignited a similar motor without loss of life. In addition, failures of several vehicles after launch have been attributed to electrostatic discharges. Electrostatic discharges in the atmosphere can have adverse effects on launch operation. NASA SP-8084, revision of June 1974, gives models that should be applied to electrostatic problems. The lightning strikes on Apollo 12, shortly after liftoff, caused major disturbances to on-board electrical systems. Fortunately, most of the effects in this case were of a temporary nature and the mission was able to continue. To be effective, a program to minimize the hazards of the electrostatic discharges must be instituted early in the design phase and must consider all aspects of the design, test, launch, and operations of the launch vehicle, spacecraft, and experiments. | Practice: Provide protection against electrostatic charges, discharges, and lightning strikes by shielding and bonding space systems, structures, and their components in accordance with Standard Payload Assurance Requirements (SPAR-3) for GSFC Orbital Projects. This reliability practice does not cover Electrostatic Discharge (ESD) control due to an energetic space plasma environment. | GSFC | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1210; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The Earth's space environment (geospace) is uniquely comprised of dynamic and complex regions of interacting plasmas, ionized particles, magnetic fields and electrical currents. Proper grounding/bonding of the space vehicle's shell and its electronic equipment can provide protection against lightning strikes in geospace, and also can eliminate or control most of its internal electrical and electrostatic hazards. This results in lower failure rates and significant reliability and safety enhancement of space systems and space vehicles. Implementation Method: For space vehicles all sections of the vehicle's outer shell should be bonded together to permit large quantities of electric charge to distribute across the shell by conducting paths. The bonded shell of the space vehicle then acts as an electrical shield to protect internal structures from lightning and atmospheric electricity. Ground wires should be used for individual systems when appropriate. Wires should be adequate to carry a surge without mechanical damage. NASA has established lightning protection requirements for design, and procedures to demonstrate that these requirements are implemented for the Space Shuttle program in NASA document NSTS 07636, which is a subtier to NSTS 07700, Volume X. NSTS 07636 defines the conducted current lightning environment for design, and imposes the requirements that the design must satisfy to ensure the protection of the Space Shuttle from the direct and indirect effects of lightning. A practical approach to lightning protection problems is presented in the appendices of NSTS 07636, which are: Appendix A, "Conducted Current Lightning Environment"; Appendix B, "Lightning Strike Zones"; Appendix C, "Test Waveforms and Methods"; Appendix D, "Methods for Estimating the Internal Induced Voltage and Current Environment"; Appendix E, "Analysis Methodology", and Appendix F, "Lightning Bonds". Bonding and grounding requirements are defined in MIL-B-5087B(ASG), "Bonding, Electrical, and Lightning Protection for Aerospace Systems". Table 1 provides typical classifications for electrical bonds from that document. TABLE 1. Electrical Bond Classes of Application1 CLASS APPLICATION MIL-B-5087B(ASG) REFERENCE PARAGRAPH A Antenna installation 3.3.1 C Current path return 3.3.2 H Shock hazard 3.3.3 L Lightning protection 3.3.4 R Rf potentials 3.3.5 S Static charge 3.3.6 1Where a single bond is used to serve two or more classes of application, the design shall conform to the most critical requirement of bonding. Class L bonding requirements are designed to achieve protection against lightning discharge current carried between the extremities of an airborne vehicle without risk of damaging flight controls or producing sparking or voltages within the vehicle in excess of 500 volts. These requirements are based upon a lightning current waveform of 200,000 amperes peak, a width of 5 to 10 microseconds at the 90% point, not less than 20 microseconds width at the 50% point, and a rate of at least 100,000 amperes per microsecond. Test requirements are described in MIL-STD-1757A, "Lightning Qualification Test Techniques for Aerospace Vehicles and Hardware" (The term "aerospace vehicles" includes fixed/variable wing aircraft, helicopters, missles, and spacecraft.) This document presents a set of standard test waveforms and techniques for lightning qualification testing of aerospace vehicles and hardware. The test waveforms presented in this document are intended to reproduce the significant effects of the natural environment and are therefore independent of vehicle type or configuration. The tests include high voltage and high current physical damage tests of fuel, structural and electrical hardware, as well as indirect effects associated with lightning strikes to externally mounted electrical hardware. The capability to test hardware and design concepts in a lightning environment has been very limited in the past. However, there are presently test facilities that are able to generate and simulate the levels of voltage, current and charge transfers typical of lightning phenomena. Therefore full scale, full threat lightning tests that meet the requirements of MIL-STD-1757A and NSTS 07636 are now available. Technical Rationale: LIGHTNING ENVIRONMENT. The currents in a lightning flash are conveniently separated into three categories: Return stroke surges with peak currents of up to 200,000 amps or more and with durations on the order of tens of microseconds. Intermediate currents of up to 10,000 amps or more and with durations on the order of milliseconds. Continuing currents of up to 1000 amps and with durations on the order of hundreds of milliseconds. Intermediate and continuing currents are primarily responsible for damage such as hole-burning while return stroke currents mainly produce explosive effects and indirect effects. There are also currents associated with subsequent return strokes and there are phases of return strokes characterized by rapid rates of change. These categories are represented by idealized waveforms designated A,B,C,D, and H. These waveforms and their mathematical definitions are described in Appendix A of NSTS 07636E. The accumulation of electrostatic charges on the electrically isolated bodies could lead to a number of results that might affect the success of a space mission. Breakdown occurs when the electric field exceeds the dielectric strength of the medium. Charge then crosses the dielectric between oppositely-charged bodies. Heat and electromagnetic energy are emitted with the passage of the charge. Besides the electric field strength imposed on the medium, the occurrence and severity of the discharge depend on system geometry and secondary discharge effects. The gaseous medium that surrounds the components of a space vehicle is particularly vulnerable to breakdown in altitudes around 30 km. The dielectric strength of the atmosphere passes through a minimum at the reduced pressures associated with those altitudes. The various field strengths that might be present on the space vehicle can cause atmospheric breakdown. Breakdown could still be possible at much higher altitudes or even in orbit because of residual gases and outgassing materials in the space vehicle that could increase the localized gas pressure until it reached the breakdown region. Air launched spacecraft such as Pegasus must minimize tribo-electric charging even during fair weather. This is done by conductive surfaces and/or discharge wicks. This is of particular concern when composite fairings are used. Breakdown of the gaseous medium occurs when the electric fields on the vehicle are strong enough to break apart the atoms or molecules of the medium into ions and electrons that then move according to the voltage gradient. If recombination takes place before the ions or electrons impinge on their respective electrodes, the breakdown is considered a partial one and is designated corona. If the gaseous ions impinge on both electrodes, then breakdown of the dielectric between them is complete and is referred to as arcing or an arc discharge. References: NASA, "Space Shuttle Lightning Protection, Test and Analysis Requirements", NSTS 07636, REV. E, Sept. 27, 1990. "Assessment and Control of Electrostatic Charges", Space Vehicle Design Criteria Environment, NASA SP-8111, May 1974. NASA, Guidelines for Standard Payload Assurance Requirements (SPAR) for GSFC Orbital Projects, NASA SPAR-3, March 1990. DOD-MIL-HDBK-263, Electrostatic Discharge Control (ESD) Handbook for Protection of Electrical and Electronic Parts, Assemblies and Equipment. DOD-STD-1686, Electrostatic Discharge Control (ESD) Control Program for Protection of Electrical and Electro Assemblies and Equipment. MIL-B-5087B(ASG), "Bonding, Electrical, and Lightning Protection, for Aerospace Systems", Amendment 3, Dec. 24, 1984. MIL-STD-1757A, "Lightning Qualification Test Techniques for Aerospace Vehicles and Hardware", July 20, 1983. NFPA-78, "Lightning Protection Code of the National Fire Protection Association", Adopted by the American National Standards Institute (ANSI) as ANSI/NFPA-78. IEEE 4-1978, "Standard Techniques for Dielectric Test", Institute of Electronic Engineers (IEEE). Langley, M.E., "Lightning Test Capabilities", Trip Report, Wendover, NV, Thiokol Corp., Wendover Test Facility, NASA MSFC CS21(90-355), Aug. 24, 1990. | Programs That Certified Usage: Apollo, Space Shuttle, All GSFC Flight Programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/03/2000
657 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Critical Design Review for Unmanned Missions | Preferred Practice for Design & Test. In the absence of a Critical Design Review (CDR), potential problems with adverse impacts on the subsystem, system, or project may not be identified in a timely manner. This oversight may later result in a condition having a significant effect on quality, reliability, capability, schedule, or cost. Conduct a formal CDR of hardware, software, and firmware at the subsystem and system levels. Schedule the review prior to the start of subsystem fabrication and assembly to assure that the design solutions satisfy the performance requirements established in the development specifications. Establish this review as a standard reliability engineering practice for flight hardware. | Impact of Non-Practice: In the absence of a CDR, potential problems with adverse impacts on the subsystem, system, or project may not be identified in a timely manner. This oversight may later result in a condition having a significant effect on quality, reliability, capability, schedule, or cost. | Practice: Conduct a formal Critical Design Review (CDR) of hardware, software, and firmware at the subsystem and system levels. Schedule the review prior to the start of subsystem fabrication and assembly to assure that the design solutions satisfy the performance requirements established in the development specifications. Establish this review as a standard reliability engineering practice for flight hardware. | JPL | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1215.3; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: The Critical Design Review (CDR) provides increased assurance that the proposed design, and the planned manufacturing and test methods and procedures, will result in an acceptable product, with minimal project risk. Implementation Method: Responsibilities The responsible project or task manager defines the need to conduct a formal review and initiates action by contacting the convening authority (generally, the next higher management level). The convening authority, in consultation with the responsible manager, appoints the review board and a chair and defines the board charter and schedule. The CDR ensures that all design considerations have been adequately incorporated and that all engineering analyses have been completed. Results of engineering model tests are presented to demonstrate that the hardware and software can be built to perform as planned. In addition, plans are presented for fabrication and testing, including qualification and acceptance. The review board, under direction of the chair, conducts the review and prepares a written report to the responsible manager on the findings and recommendations. The responsible manager then prepares a written response to the convening authority addressing the disposition of the review board findings and recommendations. The convening authority reviews and approves these dispositions. CDR Agenda The following items and issues are addressed at the CDR, where applicable: Functional description and block diagram. Functional requirements and compliance of the design, presented in matrix format with traceability references. Disposition of subassembly/subsystem Preliminary Design Review (PDR) action items. Compliance of the design with accuracy requirements. Compliance of the design with interface requirements. Compliance of the design with mass requirements. Compliance of the design with power requirements. Compliance of the design with memory requirements. Compliance of the design with environmental requirements. Compliance of the design with project Single Point Failure (SPF) policy. Compliance of the design with maintainability requirements. Status and plans for electronic piece part acquisition. Make or buy decisions and rationale. Compliance with project requirements for inherited hardware and software. Consideration of inheritance review results. Plans for compliance with spares requirements. Status of plan for meeting quality assurance requirements, procedures, and workmanship standards. Status of plan for meeting software assurance requirements. Status or results of plan for meeting reliability analyses requirements. Status or results of plan for meeting safety analyses requirements. Status of plan for meeting documentation requirements. Status of plan for meeting support equipment requirements. Status or results of plan for meeting structural analysis requirements. Status or results of plan for meeting thermal analysis requirements. Fabrication, assembly, and test schedule and constraints. Status or results of plan for meeting calibration requirements. Plans for compliance with testability requirements. Qualification (protoflight) test requirements and implementation plans. Acceptance test requirements and plans. Manufacturing and test facility requirements, availability and acceptability. Certification status and plans. Hazardous operations facility requirements, availability and acceptability. Certification status and plans. Results of detailed peer reviews, conclusions, and implementation plans. Technical Rationale: The CDR provides for the assessment of the design and fabrication plans by a group of knowledgeable persons not directly involved in the activity being reviewed. A formal review can focus many years of experience on the subject at hand. The CDR aids the responsible manager in evaluating the quality of the work and in making important decisions, including those concerning completion of critical milestones and resolution of identified issues. The review process should aid in the identification of problems and the evaluation of design approaches and options. Related Practices: Preliminary Design Review, Reliability Preferred Practice No. PD-ED-1215.1. Subsystem Inheritance Review, Reliability Preferred Practice No. PD-ED-1262. Common Review Methods for Engineering Products, Reliability Preferred Practice No. PD-ED-1215.4 References: JPL Standard Practice Instruction (SPI) 4-16-1. Guidelines for Planning and Conducting Formal Reviews, Jet Propulsion Laboratory document JPL D-10401 (Office of Engineering and Mission Assurance). Technical Reviews and Audits for Systems, Equipment and Computer Software, MIL-STD-1521 (USAF). | Programs That Certified Usage: The CDR process has been used on all JPL-managed projects and science instrument tasks, including Ranger, Mariner, Voyager, Galileo, Magellan, Topex/Poseidon, Mars Observer, Microwave Limb Sounder, Wide Field Planetary Camera, and numerous other science instruments. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/03/2000
655 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Preliminary Design Review | Preferred Practice for Design & Test. One or more potential problems that could result in an adverse impact on the system, subsystem, or project might not be identified in a timely manner. This oversight might later result in a condition having a significant effect on quality, reliability, capability, schedule, or cost. Conduct a formal Preliminary Design Review (PDR) at the system and subsystem levels prior to the start of subsystem detail design, to assure that the proposed design and associated implementation approach will satisfy the system and subsystem functional requirements. | Impact of Nonpractice: One or a number of potential problems which could result in an adverse impact on the system, subsystem, and/or project might not be identified in a timely manner. This oversight might later result in a condition having a significant effect on quality, reliability, capability, schedule, and/or cost. | Practice: Conduct a formal Preliminary Design Review (PDR) at the system and subsystem levels prior to the start of subsystem detail design, to assure that the proposed design and associated implementation approach will satisfy the system and subsystem functional requirements. | JPL | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1215.1; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: The Preliminary Design Review (PDR) will provide for increased assurance that the proposed design approach, and the manufacturing and test implementation plans, will result in an acceptable product, with minimal project risk. Implementation Method: The responsible project/task manager defines the need for, and initiates the action for conducting a formal review by contacting the convening authority (generally the next higher management level). The convening authority, in consultation with the responsible manager, appoints the review board and a chair, and defines the board charter and schedule. The review board, under direction of the chair, will conduct the review, and will prepare a written report to the responsible manager of the findings and recommendations. The board may elect to use the JPL Recommendation For Action form (RFA) to document recommendations, which are advisory and are not direction to the manager. The responsible manager will prepare a written response to the convening authority addressing the disposition of the review board findings and recommendations for action. The convening authority will review and approve these dispositions. PDR Agenda. The following items and issues should be addressed at the PDR. (It should be noted that all items may not apply in all cases, and that additional items may apply in some cases.) Functional description and block diagram Functional requirements and compliance of the design Subassembly/subsystem Functional Requirements Review Action Items and disposition Accuracy requirements and compliance of the design Interface requirements and compliance of the design Mass requirements and compliance of the design Memory requirements and compliance of the design Environmental requirements and compliance of the design Project single point failure (SPF) policy and compliance of the design Reliability requirements and compliance of the design Safety requirements and compliance of the design Maintainability requirements and compliance of the design Electronic piecepart requirements and compliance of the design Make or buy decision and rationale Inherited hardware/software and compliance with project requirements Spares requirements and plans for compliance Quality Assurance requirements and plans for compliance Software Assurance requirements and plans for compliance Reliability analyses requirements and plans for compliance Safety analyses requirements and plans for compliance Documentation requirements and plans for compliance Support equipment requirements and plans for compliance Structural analysis requirements and plans for compliance Thermal analyses requirements and plans for compliance Calibration requirements and plans for compliance Testability requirements and plans for compliance Qualification test requirements and plans for compliance Acceptance test requirements and plans for compliance Development schedule and constraints Long-lead parts requirements and procurement plans Manufacturing and test facility requirements, availability, and acceptability Environmental test facility requirements, availability, and acceptability Hazardous operations facility requirements, availability, and acceptability The PDR allows for an assessment of the design and plans by a group of knowledgeable persons not directly involved in the activity being reviewed. A formal review can focus many years of experience on the subject at hand. Technical Rationale: The PDR aids the responsible manager in evaluating the quality of the work, and in making important decisions, including those concerning completion of critical milestones. The review process should aid in the identification of problems, and the evaluation of design approaches and options. References: JPL Standard Practice Instruction (SPI) 4-16-1. JPL D-363 Guidelines for Planning and Conducting Formal Reviews. | Programs that Certified Usage: The PDR process has been used on all JPL-managed projects and science instrument tasks, including Ranger, Mariner, Voyager, Galileo, Magellan, Topex/Poseidon, MLS, WFPC, and numerous other science instrument tasks. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/03/2000
656 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Hardware Review/Certification Requirement | Preferred Practice for Design & Test. Hardware Review/Certification Requirement (HR/CR) reviews are potentially capable of discovering hardware defects, deficiencies, or deviations prior to delivery of the hardware. Consequently, if the HR/CR review is not conducted, any defects, deficiencies, or deviations that may have been uncovered by the Review Board will either go undetected or will have to be detected by some other means at a time subsequent to delivery. If the hardware problems go undetected, then a mission failure may occur. If the hardware problems are detected late, then serious schedule impacts could result and the cost of correcting the hardware defect could be affected. Conduct an HR/CR review prior to the delivery of flight hardware and associated software to evaluate and certify that the hardware is ready for delivery and that it is acceptable for integration with the spacecraft. | Impact of Non-Compliance: HR/CR reviews are potentially capable of discovering hardware defects, deficiencies, or deviations prior to delivery of the hardware. Consequently, if the HR/CR review is not conducted, any defects, deficiencies, or deviations that may have been uncovered by the Review Board will either go undetected or will have to be detected by some other means at a time subsequent to delivery. If the hardware problems go undetected, then a mission failure may occur. If the hardware problems are detected late, then serious schedule impacts could result and the cost of correcting the hardware defect could be affected. | Practice: A Hardware Review/Certification Requirement (HR/CR) Review is conducted prior to the delivery of flight hardware and associated software to evaluate and certify that the hardware is ready for delivery and that it is acceptable for integration with the spacecraft. | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1215.2; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The Hardware Review/Certification Requirement (HR/CR) provides a structured review process for assessing the status of flight hardware and screening for unresolved defects prior to delivery for integration. Implementation Method: After flight hardware has been designed, undergone unit level reviews, fabricated, integrated, and tested, a review board is convened to review the status of the hardware and to certify that the hardware is ready for delivery and is acceptable for mating with the spacecraft. The Project System Engineer/Instrument Manager is selected to chair the review. Other members of the review board include the Hardware Division Representative, the Quality Assurance Engineer, the Software Assurance Engineer, The Environmental/Reliability Engineer, and the Product Assurance Manager. The agenda and the scope of the review board is generally defined by the HR/CR form shown as Figure 1. Using the HR/CR form as a checklist, the design engineer responsible for the hardware being reviewed addresses the following: The hardware performance and requirements compliance status. That all requirements have been met, or that any requirements that have not been met are covered by approved waivers. That all documentation is current and complete, and includes all approved waivers and Engineering Change Requests (ECRs). That all analyses required to validate environmental requirements have been completed, documented, and approved. That all tests required to qualify the hardware have been successfully completed. That the hardware is acceptable for integration with the spacecraft. If the members of the review board or other participants have any concerns about the flight readiness of the hardware, anyone may write a Request for Action (RFA) against the hardware. These RFAs are reviewed by the Project and a response is prepared. After all RFAs are closed, the board certifies that the hardware is ready for delivery and flight by signing the HR/CR form. Technical Rationale: A structured review following a predetermined checklist such as the HR/CR form provides a mechanism for the responsible design engineer to review the status of the hardware and verify that the hardware is in compliance and ready for delivery and spacecraft integration. This process is enhanced by having a review board whose members have not been responsible for the design, fabrication, and testing of the hardware. Board members from the reliability engineering area and the product assurance area can focus this expertise on the completed product. Additionally, the board is able to take a fresh look at the hardware production cycle and to ask questions until they are satisfied that all necessary steps have been completed and that the hardware is acceptable for integration. Related Practices: Common Review Methods for Engineering Products, Reliability Preferred Practice No. PD-ED-1215.4. [D] Figure 1. Hardware Review / Certification Requirement Form | Programs That Certified Usage: Voyager, Galileo, and all other JPL developed Class A, B, and C spaceflight hardware. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/03/2000
658 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Grounding Practices for Aerospace Hardware |  | Impact of Non-Practice: The impacts of failure to adhere to proven and acceptable grounding practices for the design and fabrication of electrical and electronic parts are: (1) potential damage to delicate space flight systems, subsystems, components and experiments; (2) creation of sparks or overheated components or connections, creating a fire hazard or a thermal imbalance that cannot be counteracted by environmental control systems; (3) danger to ground or flight crew personnel from electrical shock; or (4) damage to vehicle, payloads and ground systems due to atmospheric lightning. Ultimately, lack of proper grounding could cause death due to electrical shock or mission failure due to excessive heating, shorts, or fire. | Practice: Electrical grounding procedures must adhere to a proven set of requirements and design approaches to produce safe and trouble-free electrical and electronic circuits. Proper grounding is fundamental for reliable electronic circuits. | MSFC | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1214; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Grounding procedures used in the design and assembly of electrical and electronic systems will protect personnel and circuits from hazardous currents and damaging fault conditions. Benefits are prevention of potential damage to delicate space flight systems, subsystems and components, and protection of development, operations, and maintenance personnel. Implementation Method: System Grounding Requirements and Design Approaches: The design of electrical and electronic systems should comply with the following as a minimum: (1) a ground reference plane should be established that will hold the grounds for all systems, subsystems, equipment metallic components, surfaces, and electrical and electronic parts at the potential of the base structure; (2) within equipment, power should have dedicated returns; (3) except for a single-point reference, all electrical signal and power grounds should be electrically isolated from each other, and each separately derived electrical system should be electrically connected to structure at only one point; and (4) a dedicated power return should be used except where necessary to support system requirements. The grounding within electrical or electronic enclosures is at the discretion of the circuit designer. The following design approaches should be considered for the design of these systems: (1) within equipment, conditioned electrical power should be DC-isolated from chassis and structure except at a single point; (2) within equipment, the single-point reference should be routed external to the equipment for termination to ground, or routed directly to the chassis for termination; (3) the control power bus return should be independent of the primary electrical power return and should be referenced to the return system at a single point; (4) secondary and tertiary electrical power should be single-point grounded and should be returned to that single reference ground point; (5) when all single-point grounds are not terminated to chassis or structure, secondary and tertiary electrical power should be dc isolated by a minimum of 1 megohm; (6) power conversion performed to supply conditioned power to several devices or functions should reestablish a single-point ground reference for the serviced equipment or functions; (7) equipment should not depend on other equipment for reference or grounding, either signal or power, unless it is also dependent upon the other equipment for its power; (8) signal circuits with frequencies below 2 MHz, with interfaces external to equipment, should be balanced and isolated from chassis; (9) all returns and references should be brought out of equipment on individual connector pins; (10) shield connections should be made to connector shells or to connector pins that are, or will be, grounded when mated; (11) single-ended circuits with the lowest frequency component equal to or above 2 MHz should be coupled by coaxial cable with the shield terminated 360 degrees at each end; and (12) external to an equipment, single-ended electrical signals should be prohibited for signal frequencies below 2 MHz except where electrical isolation is maintained. [D] Schematic Examples: An example of grounding implementation concepts is shown on Figure 1. This figure reflects the stated grounding requirements and design considerations and shows two feeder, cabling and load configurations. At frequencies below 2 MHz (Figures 1 and 2), the emphasis is on circuitry requiring internal grounding with interfaces to external equipment. For frequencies equal to and above 2 MHz, the emphasis is on external connections between equipment and the proper grounding of shielding to prevent electromagnetic coupling. Single-Point/Multiple-Point Grounding: Although the establishment of a ground reference plane requires a single-point ground, the actual practice of complying with this requirement in a system design is controversial. Modern electronic systems seldom have only one ground plane and, to reduce potential interference, as many ground planes as possible are sometimes used. From Figure 2, a grouping of ground planes connected by the shortest route back to a system ground point where they form an overall system potential reference, could be called a single-point ground system. However, problems with this scheme arise when interconnecting shielded cabling is used having significant lengths with respect to the wavelength of signal frequencies and parasitic capacitance exists between equipment housings or between subsystems and the grounds of other subsystems. It can be argued that a quotmultiple-pointquot ground system, which bonds each subsystem or equipment as directly as possible to a low impedance equipotential ground plane, can minimize these electromagnetic interference problems. An example of such a system is shown in Figure 3 where each subsystem is connected directly to a common ground plane, ideally a flat, equipotential plate. In practice, the selection of a grounding scheme is dependent on the highest significant operating frequency of low-level circuits relative to the physical separation of the equipment. As shown in Figure 4, single-point grounding works best at low frequencies and small dimensions and multiple-point grounding works best at high frequencies and large dimensions. For transitional situations, one or the other may perform better as shown in Figure 4. For this crossover region, hybrid grounds perform best when portions of the low-frequency systems use single-point grounds and the high-frequency portions use multiple-point grounds. Shock Prevention: Proper grounding protects personnel from accidental contact with metallic elements that may have hazardous voltage potentials due to system faults or accidental contact between energized elements and equipment chassis, frame or cabinet structure. Case voltage rise is limited to reduce currents to levels that do not produce adverse reactions and possible secondary effects. Typically, case voltage rise is limited to prevent hazardous currents. Table 1 summarizes the alternating and direct currents and their shock effects. Table 1. Summary Effects of Electrical Shock Alternating Current (60Hz) Direct Current (DC) Reaction (mA) 0.5-1 1-3 3-21 21-40 40-100 > 100 (mA) 0-4 4-15 15-80 80-160 160-300 > 300 Perception Surprise Reflex action Muscular inhibition Respiratory block Usually fatal Bonding: The integrity of interconnected conductive elements is ensured by electrical bonding, a process in which components or modules are electrically connected to provide a low-impedance conductor. Bonding practices should comply with MIL-STD-5087B or with SSP 30245. Bonding procedures require the use of specified clamps, standard parts, bolt and screw attachments, washers and materials to ensure consistent bonding of equipment under various temperatures and corrosion environments. The use of jumper cables is discouraged except across movable vibration or thermal isolation joints. Surface preparation for bonded joints should begin by removing all anodic film, grease, paint, lacquer, or other high-resistance properties from the faying surfaces. A typical bonding hardware configuration is shown in Figure 5. The use of scrapers, abrasives or chemical cleaning methods to provide a clean, smooth bonding surface is dependent on the type of joint (i.e., metal-to-metal, metal-to-nonmetal or nonmetal-to-nonmetal). Example bonding impedances for selected bonding classes are shown in Table 2. [D] [D] Table 2. Example Bonding Impedances and Bonding Class Bonding Class Impedance A (Antenna installation) H (Shock hazard) R (RF potentials) S (Static charge) DC resistance < 2.5 milliohms DC resistance < 100 milliohms DC resistance < 2.5 milliohms Impedance < 100 milliohms up to 1 MHz <1 ohm (conductive structure) < 1000 ohms (composites) < 1000 ohms (conductive subassemblies) 1 ohm (pipe and hose) [D] Cabling/Connector Grounding: Cabling extending outside grounded enclosures is vulnerable to radiated emissions if cable lengths are a significant portion of the wavelength of the systemís highest operating frequencies. Adequate shielding and grounding are required to ensure proper system operation. Figure 6 shows typical grounding practices for shielded cabling and connectors. Shield terminations at connectors are gripped by the connector back shell to provide a low impedance 360 degree connection. Soldered connections are not recommended due to the difficulty in repair and wiring changes, and the use of foil in some cable shielding. Where cabling enters enclosures, the box connector or partition penetration in Figure 6 may be used. For cabling where the overall shield ends in a terminal strip, the termination may look like the configuration shown in Figure 7. [D] [D] [D] Technical Rationale: Through many years of designing and fabricating electrical circuits and electronic devices for launch vehicles, experiments and payloads, the Marshall Space Flight Center has developed procedures and techniques for designing reliable and safe aerospace electronic systems. Design criteria were built upon a solid foundation of industry and government practices. Military standards were used at the outset, and procedures unique to the space program were added as refinements. Practical experience reflected in the standard procedures and techniques resulted in reliable circuits that presented minimum hazard to personnel and equipment. Related Practices: Reliability Preferred Practice No. PD-ED-1202, quotHigh Voltage Power Supply Design and Manufacturing Practices,quot Lewis Research Center. Reliability Preferred Practice No. PD-ED-1210, quotAssessment and Control of Electrical Charges,quot Goddard Space Flight Center. Reliability Preferred Practice No. PD-ED-1206, quotPower Line Filters,quot Goddard Space Flight Center. References: SSP 30240 Revision A, quotSpace Station Grounding Requirements,quot September 1991. MSFC-SPEC-521B, quotElectromagnetic Compatibility Requirements on Payload Equipment and Systems,quot August 15, 1990. MIL-STD-461C, quotElectromagnetic Emission and Susceptibility,quot August 1986. MIL-STD-462, quotElectromagnetic Interference Characteristics,quot July 1967. MIL-STD-463A, quotDefinitions and System of Units, Electromagnetic Compatibility Technology Interference,quot June 1966. MIL-STD-5087B, quotBonding, Electrical and Lightning Protection for Aerospace Systems,quot Amendment 3, December 24, 1984. Denny, Hugh W., quotGrounding for the Control of EMI,quot 1983. White, Donald R.J., quotElectromagnetic Interference and Compatibility,quot Vol.3, quotA Handbook on EMI Control Methods and Techniques,quot 1973. SSP 30242 quotSpace Station Cable/Wire Design and Control Requirements for Electromagnetic Compatibility, quotSeptember 1991. SSP 30245 quotSpace Station Electrical Bonding Requirements,quot September 1991. | Programs That Certified Usage: Saturn I, IB and V launch vehicles, Space Shuttle Solid Rocket Booster, International Space Station, MSFC-developed payloads and experiments. | N/A |  | Aeronautics Research | Public | Not Specified |  | 03/03/2000
651 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Environmental Test Methods for Ground Support Equipment |  | The difficulty of designing equipment to meet the design specification is greatly compounded when the specification includes requirements excessive to the actual service environment. | Defines test methods for determining the capability of ground support equipment (GSE) and other facility hardware to function when exposed to the natural and induced environments peculiar to the prelaunch and launch conditions at Kennedy Space Center (KSC). Provides guidelines for the preparation of detailed test procedures and for the preparation of the environmental test portions of design specifications. | KSC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number GSE-3006 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The test methods described herein specify conditions obtainable in the laboratory that will give test results similar to actual service conditions. Implementation Method: Design and Testing Considerations. The basic purpose of this practice is to provide a guide to uniform testing of Ground Support Equipment (GSE) and other facility components to assess the ability of the hardware to withstand the environmental stresses it will encounter during its life cycle and to ensure that plans and test results are adequately documented. Tests should be conducted to the maximum extent practicable to ensure operational suitability of the item for the anticipated environmental conditions to be encountered during its required usage. Consideration should be given to natural and induced environments and to combinations and sequences of stresses. The environmental conditions to which GSE is exposed in the KSC area vary considerably by virtue of its location on the center. The environmental conditions of computer equipment installed in an air-conditioned, sound-absorbent room on vibration-isolated floors is negligible compared to the severe conditions a holddown system experiences; i.e., the daily natural environments and the blast of the launch vehicle during lift-off. Designing or testing all equipment to the most severe of these conditions is impractical and expensive. Design and testing should be accomplished with both the actual environmental and reliability requirements in mind. KSC-STD-164 may be used as a guide to define test conditions. Testing Procedures. Test Requirements. - The anticipated environmental conditions should be carefully considered before determining which tests are to be conducted. Generally, only those conditions that reflect launch and prelaunch usage of the test item should be considered. Where possible, data should be obtained on actual operating and field environments to which the GSE will be exposed to aid in the test selection process. When considering the applicable environmental conditions, combined environmental testing should also be considered as a means for more closely simulating service conditions, and in fact, may be the only method of attaining valid test results. Test Sequence. - Those tests that require the successful operation of the test item during exposure to the environment should normally be conducted first, and those tests where the test item remains static throughout the environment should be conducted last. In either case, the test should be conducted in the order of the likely severity on the item; the least severe being conducted first. Unless otherwise stated in the test requirements, the following sequence is recommended; Electromagnetic interference Low temperature High temperature Temperature shock Acoustics Vibration Shock Humidity Rain Icing Solar radiation Fungus Salt fog Sand and dust Explosion Lift-off blast Receiving Inspection. - Prior to conducting any tests, the test item should be subjected to a receiving inspection. This inspection should be made to determine conformance with applicable drawings and specifications to the extent possible without disassembly of the test item. When quality acceptance tests are specified, they should be conducted as part of the receiving inspection. Functional Test. - The functional test is the means by which it can be determined whether or not the environmental tests are adversely affecting the performance capabilities of the test item. Because the functional test is required to monitor the very "pulse" of the test item, it is obvious that it must be comprehensive enough to include all possible aspects which could affect the operation of the item. The determination of what checks to make as part of the functional test requires a good understanding of the operation and application of the test item and its possible failure modes. Prior to conducting a functional test, the functional parameters to be monitored should be specified and should include allowable limits on permissible degradation. Installation in Environment Facilities. - The test item should be installed in the test facility at ambient conditions in a manner that will simulate service usage. Install instrumentation in, on, or around the item as required by the test. Plugs, covers, and inspection plates used in service should remain in place. When mechanical or electrical connections are not used, the connections normally protected in service should be adequately covered in the same manner as service usage. The test item should then be functionally tested to determine that no malfunction or damage was caused due to faulty installation or handling. The requirement to conduct a functional test following installation is applicable only when a functional test is required during exposure to the specified environments. Frequency. - Functional tests should be conducted at least three times before and after each test environment. If the functional test performed after an environmental test is satisfactory, the test item should be qualified for the succeeding environment without further testing, provided (1) the succeeding test is started within 72 hours after the previous functional test and (2) installation changes are not required. When a test environment simulates conditions under which the test item would be required to operate during service, the item should be functionally tested at least three times during the test environment. Characteristic Tests. - Tests to establish the basic design characteristic of the item are also required. These tests should not be confused with the functional-type test which is repeated throughout the test program. Characteristic tests are conducted once, generally prior to the environmental tests, unless they are destructive in nature. Examples of characteristic tests for pneumatic components may include proof test, flow test, surge test, and the burst test which is destructive. For electrical components, characteristic tests may include voltage drop test, ampere test, resistance test, and repeatability test. Life Cycle Reliability Testing. - Testing is conducted to provide statistical data for determining the reliability of the test item with a reasonable degree of confidence. Failures that would occur "once-in-a-thousand" are looked for in the life-cycle test. After exposure to all the environments the item would normally be exposed to during use with no deterioration of operation found, the life-cycle test can provide a valid method for determining reliability. Failures that occur due to wearing out of parts beyond service life expectancy must not be considered a design failure, but may be considered for establishing maintenance time periods. The number of life cycles to be conducted should be established by the testing agency. Documentation. - The environmental tests required for a particular hardware item should be documented in a test plan or test requirements document. Inspections, data requirements, test tolerances, functional tests, and installation requirements should be indicated along with any deviations from the standard tests established herein. KSC-DF-107 may be used as a guide in preparing the plan. The testing agency should develop a detailed test procedure based upon the test requirements specified in the test plan. Test results should be documented, approved, and published in accordance with KSC-STD-128. Test Methods. Electromagnetic Interference. - The electromagnetic interference test is performed to determine if the electronic or electrical equipment under test will exhibit malfunction or degradation in performance when subjected to undesired external signals. Electrical and electronic equipment includes components that are susceptible to malfunction from external electromagnetic interference. Such interference can change the calculations of a computer, alter the sequence of planned commands of computer programs, and cause recorders to erroneously indicate that a function occured, failed, or even altered the time of the recording function. Components, such as solenoid valves, power contacts, and signal relays that are not susceptible to malfunction from external electrical interference, generate transient pulses when deenergized. These impulses may exceed the normal operating voltage ratings of much associated connecting circuitry as well as transmit electromagnetic interference to external electronic circuits. Low Temperature. - The low temperature test is performed to determine the operational performance of the item at low temperatures which might be encountered during its life cycle. The test item should be functionally tested during exposure to ascertain whether or not the environment causes degradation of performance. Some of the difficulties which may result from low temperature exposure are binding due to differential contraction of parts, loss of resiliency of gaskets, and congealing of lubricants. Testing to this environment is applicable to components not installed in a temperature controlled environment. High Temperature. - The high temperature test is performed to determine the operational performance of the item at high temperatures that might be encountered during its life cycle. The test item should be functionally tested during exposure to ascertain whether or not the environment causes degradation of performance. High temperature conditions may cause permanent setting of packings and gaskets, binding of parts due to differential expansion, and cracking or bulging of rubber and plastic. This test is applicable to components that are not installed in a temperature controlled environment. Temperature Shock. - The temperature shock test is performed to determine the effect of an anticipated sudden change in temperature on the operational performance of an item. Cracking or rupturing of materials (particularly valve seats) due to changes in material characteristics and dimensions is the principal difficulty to be anticipated. A thermal shock is experienced when (1) gases expand upstream or immediately downstream of a pneumatic component, (2) hydraulic fluid is forced through restrictions at high flow, and (3) when cryogenic fluids are used in items that are not gradually chilled down. Acoustics. - The acoustic test is performed to determine the effects on performance that acoustics will have on GSE and other facility hardware located at or near the launch pad at the time of launch vehicle holddown and lift-off. In an acoustic noise field, pressure fluctuations impinge directly on the equipment providing a distributed type of dynamic load. Broadband spectra of these loads contain resonance frequencies of most, if not all, structural components of equipment. The resulting resonant vibration is generally different from that which occurs when excitation is applied only at discrete points. Further, components that are effectively isolated from a mechanical transmission of vibration from the supporting structure will be excited directly. Electronic chatter at friction-held contacts, chafing of wires, cracking and collisions of printed circuit boards, and malfunction/failure of waveguides and Klystron tubes are examples of acoustically induced problems. Acoustic! test specifications provide guidance for the performance of acoustic tests on GSE or other facility hardware. Acoustic tests are subject to restraints imposed by the capabilities of existing test facilities. Vibration. - Vibration test specifications provide guidance for the performance of vibration tests on GSE or other facility hardware used to support the launch of a space vehicle. These specifications apply to a vibration environment occurring during a launch for the purpose of providing criteria for acceptance and qualification of GSE. The extent of concern is limited to equipment located on and in the proximity of the launch pad, generally within a 300-meter (1000-foot) radius of the launch pad. Shock. - The launch of a space vehicle generates pressure acoustic environments that do not contain shocks. A pressure pulse generated by some engines at the time of ignition does not induce as a response a distinct vibration shock, rather it results in a transient vibration with peak amplitudes that are substantially lower than the peak vibration during a lift-off period. True vibration shocks occurring during a launch are true anomalies caused by collisions between structural elements and by bottoming of vibration isolators. High shocks can be generated by a hard bottoming of vibration isolators that do not have snubbers and that involve metal-on-metal impacts. Whenever possible, the cause of shocks should be corrected rather than trying to qualify equipment for an operation in the shock environment by testing. Exceptional shock occurrences covered by these specifications are those that cannot be corrected by a structure/isolator redesign or by moving equipment to another location free from shocks. Because there are exceptions, test specifications, testing procedures, and tolerances should be handled on a case-by-case basis. Humidity. - The humidity test is performed to determine the resistance of equipment to the effects of exposure to a warm, highly humid atmosphere such as that encountered in the KSC area. This is an accelerated environmental test, accomplished by the continuous exposure of the equipment to high relative humidity at an elevated temperature. These conditions create a vapor pressure, which is the force behind moisture migration and penetration. Corrosion is one of the principal effects of humidity. Hygroscopic materials are sensitive to moisture and deteriorate rapidly under humid conditions. Many materials lose their functional utility and physical strength and change their important mechanical properties. Insulating materials that absorb moisture may lose their insulating properties. Rain. - The rain test determines the resistance of GSE to the effects of exposure to rainfall rates that are encountered in the KSC area. The rain test determines the capability of equipment or component seals to resist water intrusion and determines the efficiency of protective covers or cases designed to shield the item from rain. Icing. - The icing test is conducted on GSE that is susceptible to the formation of ice on its external surface. This formation can occur during the normal operation of cryogenic systems and during the normal operation of pneumatic systems that require high flow rates and large pressure drops across individual components. Ice will also form on component surfaces that are physically located within the thermal gradient of these systems. For this reason, when selecting components for this test, the moisture and temperature conditions must be considered in relation to the proximity of the component to the system. Each component subjected to this test must be selected judiciously and its physical location must be adequately defined. Damage that can be expected from the accumulation of ice is mechanical binding or sticking, short circuiting of the electrical wiring, and sealing of the vent ports. Solar Radiation (Sunshine). - The solar radiation test is performed to determine the effect of solar radiant energy on equipment. Solar radiant energy causes heating of equipment, photo degradation (such as fading of fabric colors), and cracking of paints, natural rubber, and plastics. The solar radiation test is applicable to any item of equipment that may be exposed to solar radiation during service and that is constructed of materials that may be adversely affected by this environment. Fungus. - The fungus test is performed to determine the susceptibility of GSE to fungus attack and to ascertain the detrimental effects that are incurred when such equipment is subjected to the test environmental condition. During the normal growth of fungi, there is an enzymatic secretion that accelerates a chemical transformation of organic substances. Once attacked, most organic materials will be destroyed by the fungi. Many minerals are also destroyed by these spores. Fungi affect insulation, wood and wood derivatives (paper), some types of seals, lens coatings, as well as many other types of materials. This is an accelerated environmental test; therefore, the temperature and moisture condition are specified to support rapid growth of fungi and accelerated deterioration of materials. Salt Fog. - The salt fog test is performed to determine the resistance of equipment to the effects of a salt atmosphere. The expected damage from exposure to salt fog is primarily corrosion of metals, although in some instances salt deposits may result in clogging or binding of moving parts. This is an accelerated environmental test; therefore the specified concentration of moisture and salt is greater than that found in normal service. Sand and Dust. - The sand and dust test is performed to determine the resistance of equipment to blowing fine sand and dust particles. Because of their abrasive character, sand and dust can affect items into which sand may enter. Sand and dust can also cause parts to bind and can interfere with electrical contacts. Due to the high sand concentrations of the soils at KSC, dust will not be part of this test. The sand and dust test is applicable to those items that are exposed to wind-blown sand conditions common in the KSC area. This is an accelerated accelerated environmental test; therefore the conditions are more severe than those found in normal service. Explosion. - The explosion test is conducted to determine the explosion-producing or explosion-containment characteristics of hardware when operated in a hazardous location. Explosions may be initiated by mechanical or electrical sparking, flashes, temperature, or chemical reactions. Hardware can be placed into one of two categories: (1) intrinsically safe or (2) explosionproof. GSE and other facility hardware located near propellant storage or fueling areas may be considered in a hazardous location due to the possible exposure to high-atmospheric concentrations of hydrogen and hypergol propellants. Dust ignition requirements are not considered to be applicable to GSE or other facility hardware; therefore, dust ignition will not be part of explosion testing. Lift-Off Blast. - The lift-off blast test is performed to determine the effects of rocket engine exhaust on GSE and other facility hardware at the time of launch vehicle holddown and lift-off. The detrimental effects of a blast are due to extremely high temperatures and pressure and the erosion characteristics of the rocket engine exhaust plume. The extent of damage depends on the exposure time, velocity of exhaust gases, type of propellants, and most importantly, the location of the item in relation to the rocket engine exhaust. Blast conditions may cause erosion of hardware surfaces, loss of protective coatings, permanent set or binding of parts, cracking or bulging of rubber and plastic due to high temperatures, and bent or deformed material due to the pressure load. The lift-off blast test should only be performed on those hardware items that cannot be shielded or protected from the lift-off environment. Technical Rationale: The environmental conditions to which equipment is exposed varies considerably by virtue of its location. Designing or testing all equipment to the most severe of these conditions is impractical and expensive. To ensure that reliability goals are met, design and testing must be accomplished with both the actual environmental and reliability requirements in mind. References: KSC-STD-164 Environmental Test Methods for Ground Support Equipment. MIL-STD-810 Environmental Test Methods and Engineering Guidelines. KSC-STD-128 Preparation of Test Reports. KSC-DF-107 DE Technical Documentation Style Guide. KSC-DE-512-SM Guide for Design Engineering of Ground Support Equipment and Facilities for Use at Kennedy Space Center. KSC-STD-G-0003 Qualification of Launch Support and Facility Components. | This practice has been used on the Space Shuttle Program, at the Kennedy Space Center, Launch Complex 39 Ground Support Equipment. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/02/2000
652 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Combination Methods for Deriving Structural Design Loads Considering Vibro-Acoustic, etc., Responses | Preferred Practice for Design & Test. The probability of structural failure during launch will be increased, particularly for secondary structure. Design primary and secondary structural components to accommodate loads which include steady-state, transient dynamic, and vibro-acoustic contributions at liftoff. | Impact of Nonpractice: The probability of structural failure during launch will be increased, particularly for secondary structure. | Practice: Design primary and secondary structural components to accommodate loads which include steady-state, transient dynamic, and vibro-acoustic contributions at liftoff. | JPL | 01/31/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1211; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: The probability of structural failure during launch and landing is significantly reduced. Implementation Method: Loads due to various sources (steady-state acceleration, transient dynamic, vibro-acoustic) may be computed separately. Then use one of the combination methods listed below to derive the combined load. For acoustically sensitive components, direct acoustic load should be included as well. Technical Rationale: Vibration which causes structural loads can be classified as follows (see Table 1): Vibration due to transient events (liftoff, staging, etc.), typically below 60 Hz, including steady-state acceleration; Random vibration transmitted through mechanical interfaces, typically from 20 to 2000 Hz; Random vibration caused by direct acoustic loading on the surface of the structure, typically from 50 to 10,000 Hz. For primary structure, the steady-state and transient loads typically dominate the vibro-acoustic loads, and the latter are often ignored in practice. For secondary structure, however, the vibro-acoustic loads can be comparable to, or larger than, the steady-state and transient loads. Acoustically sensitive components may have loads which are dominated by their response to direct acoustic excitation. Because the transient and vibro-acoustic loads can be of comparable magnitude, and both are present simultaneously at liftoff, it can be unconservative to design the structure to the transient and vibro-acoustic loads separately. A number of methods are available for assessing the combined load. The following methods are considered acceptable. Method 1: Coupled Transient Analysis with Base Drive Random Depending on the launch vehicle, coupled transient analysis predicts structural loads up to 60 Hz, although in most cases the frequency cutoff is much lower (35 Hz for STS liftoff). Forcing functions for these analyses are adjusted, based on flight data, to assure that the loads envelop the actual flight loads (including transient and mechanically transmitted random vibrations within the frequency range of analysis). Above the cutoff frequency of the coupled transient analysis, mechanically transmitted random vibration loads may be computed using base drive random analysis of the payload structure. The base vibration is specified in terms of power spectral densities of the acceleration in each direction. If possible, the analysis should be performed using input accelerations corresponding to the time of peak transient loads, rather than the maximum random vibration over the entire flight. Accelerations in different directions should be considered uncorrelated, and may be applied simultaneously or one direction at a time. A higher level of damping is acceptable for the random analysis than for the coupled transient. Common practice is to use 3 times the RMS (3 sigma) as the peak load prediction. Peak loads from the coupled transient and base drive random analyses may be combined by a root-sum-square (RSS) approach. When direct acoustic loading on the payload structure is non-negligible, it may be combined with the above load using an RSS approach. Methods for predicting acoustic loading include finite-element based approaches, which are limited to low frequency predictions, and statistical energy methods, which are limited to higher frequency predictions. Method 2: Mass Acceleration Curve A typical mass acceleration curve (MAC) is shown in Figure 1. The MAC is an upper bound acceleration level for all components of a given mass, regardless of location, orientation, or frequency. Applicability is limited to appendage masses up to 500 kg, with frequencies up to approximately 100 Hz. Such a curve can be derived based on analytical and flight data, and includes the effects of both transient and mechanically transmitted random vibration. That is, the load predicted by the curve is already a combination of transient and random vibration. When direct acoustic loading is non-negligible, it may be combined with the MAC load using an RSS approach. Method 3: Coupled Transient Analysis with Modal MAC It is generally accepted that base drive random analysis can be very conservative, because it does not account for impedance effects. These effects can be very significant for the payload modes with large effective mass. An approach which accounts for impedance in an approximate way is based on application of the MAC to the modes of the payload structure. Each mode of the payload may be assigned an acceleration level based on its effective mass. The acceleration level is taken from a curve similar to Figure 1, but the modal MAC is typically lower in level than the MAC which applies to physical appendage masses. Physical loads corresponding to each mode are then derived by scaling the mode shape according to this level. The combined load is obtained as the RSS of the transient load with the modal loads above the transient cutoff frequency. It can be seen that this method is the same as Method 1, except that the base drive random approach is replaced by an RSS of modal loads scaled to the modal MAC. As in the previous two methods, when direct acoustic loading is non-negligible, it should be computed by an appropriate acoustic analysis method, and combined with the transient and random load using the RSS approach. Table 1. Sources of Structural Loads Type of vibration Frequencies (Hz) Types of Analysis From To Steady-state: Transient Vibration 0 60 Coupled transient MAC Mechanically transmitted random 20 2,000 Base drive random Modal MAC Direct acoustic 50 10,000 Finite element (low frequency) Statistical engergy (high frequency) [D] | Programs That Certified Usage: Viking, Voyager, Galileo | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/02/2000
653 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Shielding of Power, Signal and Control Cables |  | Impact of Nonpractice: The absence of high performance cable shielding frequently results in cross interference which degrades hardware operation and can obliterate scientific data. These problems can usually be identified in ground testing, but correcting them by retrofitting flight hardware is very difficult and expensive. Therefore, it is important that cable shielding be included in the early design of hardware. Significant interference problems can occur on orbit that were not corrected during ground testing or were not found due to hardware interference situations that could not be exactly duplicated during ground testing. Also, deterioration or partial failure of components and parts can result in increased levels of radiated emissions. Hardware that is susceptible to these radiated emissions can exhibit problems such as microprocessor resets, false or inaccurate engineering data readouts, unintentional mode changes, and noisy or lost scientific data. Cable shielding minimizes these interference problems by isolating hardware from radiated emissions. Numerous EMC tests at GSFC have demonstrated that unshielded cables and wires such as power leads, thermistor, and thermostat leads pick up radiated emission signals and re-radiate them from all areas of a payload. Additionally, the signals are often conducted inside shielded boxes. These tests have also shown that signal and control leads should have 60 dB or more of shielding effectiveness; whereas, most commercial shielded cable has only 30 to 40 dB of shielding effectiveness. | Practice: All wiring harnesses, cables, and wires on payloads, instruments, subsystems, and components are well shielded, including the use of connector types that provide tight EMI back shells or other means for attaching shields. This practice assumes that all efforts have been made to develop a design which requires minimum shielding. | GSFC | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1213; from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: High performance shielding on wiring harnesses, cables and wires minimizes radiated emissions from hardware that could be picked up by itself or other hardware and interfere with proper operation. Shielding also minimizes the sensitivity of hardware to radiated emissions, from itself or other hardware, that could interfere with proper operation. Implementation Method: Cable shielding that can provide 60 dB or more of shielding effectiveness is used to meet the radiated emission and the radiated susceptibility requirements of GSFC's General Environmental Verification Specification for STS & ELV Payloads, Subsystems, and Components (GEVS-SE). This document contains a baseline for demonstrating by test the satisfactory performance of hardware in the expected mission environments. Connector types should be selected that provide 60 dB or more of shielding, and provide an appropriate method for attaching cable shields and maintaining a low impedance path to chassis or structure ground. Soldering shields to the back of connectors is not a good practice since many cables use both an aluminum foil shield and a braid shield. Also, soldered connections make repairs and wiring changes very difficult. Good practice is to use a solid back shell that tightly grips the shield all the way around and provides complete 360 degree shielding. Cable shields should not be attached to connector pins and grounded on the inside equipment chassis or boxes since this enables shields to conduct outside emissions into the box, and inside emission to the outside, and can cause radiated emission problems. Chassis or box mounted connectors should have a conductive gasket between the mounting surface of the connector and the chassis or box in order to provide an EMI tight seal. The mating surfaces of the connector and the chassis or box should be clean and highly conductive. Technical Rationale: The practice provides a basis for the selection of cable shields and connector types that enable equipments to comply with the References 1 and 2 EMC requirements. Additionally, the proper selection of cable shielding and connector types significantly reduces the possibility of electromagnetic compatibility problems. Related Practices: Power Line Filters - Practice No. PD-ED-1206. EMC Guidelines for Payloads, Subsystems and Components - Guideline No. GT-TE-2401. References: General Environmental Verification Specification For STS & ELV Payloads, Subsystems, And Components (GEVS-SE). Shuttle Orbiter/Cargo Standard Interfaces Document (JSC 07700 Volume XIV Attachment 1 (ICD 2-19001). | Program Which Certified Usage: All GSFC Flight programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/02/2000
649 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Identification, Control, and Management of Ground Support Equipment (GSE) Critical Items |  | Failure to adhere to these guidelines for ground processing operations could create operational delays, increase operational costs, decrease the effectiveness of failure management, and could ultimately lead to a system failure which could result in loss of life/vehicle or damage to a vehicle system. | Identify potential critical items early in projects for Ground Support Equipment (GSE) as an input to hardware and software design activities. Perform Failure Modes and Effects Analysis (FMEA) for "as built" configuration GSE identifying Critical Items. Prepare Critical Items Lists (CIL's) and present the resulting risks to management for acceptance. Use CIL's to initiate control of the risks associated with the critical items and to request a waiver or deviation from program requirements. | KSC | 02/01/1999 | This Lesson Learned is based on Reliability Practice number GSE-3005 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Early identification of potential critical items will provide valuable inputs to design engineering for their avoidance and/or elimination. Critical Items Lists (CIL) provide management with design acceptance rationale for those critical items which could not be eliminated, and identify test and inspection controls to minimize the probability of a failure. Implementation Method: Background GSE at KSC includes equipment and facility systems used to test, checkout, process, handle, and transport Space Shuttle flight hardware at the launch and landing sites. Equipment used at other sites that is common to that used at the launch and landing sites is also included. Prior to conducting the FMEA a criticality assessment is performed to assess each system function. If loss or improper performance of the function, without regard to available redundancy, could result in loss of life/vehicle or damage to a vehicle system the system is assessed as critical. FMEAs are performed on the hardware associated with the critical functions. The only exceptions are functions assessed as critical due to failure of passive components, such as certain types of structural components. The Failure Modes and Effects Analysis (FMEA) is performed at the lowest level necessary to identify: 1) Single Failure Points (SFP's) which if failed could cause loss of life/vehicle or damage to a vehicle system; 2) The combined effect of two like or unlike redundant items which could result in loss of life/vehicle; 3) SFP's in safety or hazard monitoring systems whose failure modes assume the hazardous condition being monitored or combated has already occurred. The FMEA and resulting CIL can be used not only as a check of the systems design for reliability, but can also be used as a driver for the systems design to reduce or eliminate critical items and/or implement value added maintenance design features. The FMEA/CIL process plays a key role in reliability management. Reliability management is the activity involved in assuring that proper performance of the system/equipment and completion of maintenance procedures will minimize the risks associated with the identified failure modes. Reliability management coordinates the analysis of design, development, manufacturing, testing, maintenance, and operations to assure that the system output will support the prescribed program interface/function. Reliability Management is accomplished through the formulation of reliability plans, the performance of system/equipment design analysis, the support of classical reliability analysis activities, and project/system team participation using concurrent engineering methodologies. The principal outputs of the FMEA/CIL process are the CIL's. Critical Items and Retention Rationale Specific lessons have been learned that will enhance the value of identifying potential critical items early in high-technology, multi-disciplinary aerospace programs and projects. Critical items are identified through the conduct of a FMEA. The FMEA process involves the analysis of each active component (hardware or software element) in a complex system to a specified level, for each possible failure mode. The determination of the "worst case" failure effect of that failure on vehicle systems and/or personnel safety is then determined. If the item could fail in a mode which could directly result in loss of life/vehicle and/or damage of a vehicle system, the item is designated as a critical item and categorized according to the severity of the failure effect. SFP's in designated safety or hazard monitoring systems, whose failure modes assume the hazardous condition being monitored or combated has already occurred, are also identified as critical items. The FMEA is most effective when it is performed concurrently with the design process and maintained throughout the life of a program or project. It is the policy of NASA not to permit the retention of SFP's in design unless special conditions result in the application and approval of a waiver or deviation from the Space Shuttle Program (SSP) Configuration Management Requirements. Retention of a SFP requires that a CIL sheet be prepared which identifies the item, Criticality Category, Function, Failure Mode, Failure Cause(s), Failure Mode Number and Failure Effect. The CIL sheet also provides the Acceptance Rationale which describes the components design, test, inspection, failure history, and operational use. The elements of the Acceptance Rationale, as described below, include safety margins, prevention measures, and maintenance/operational procedures which will ensure that the critical item will not fail in the critical failure mode. The Acceptance Rationale forms the basis for management acceptance of GSE which contains critical items. Design Rationale: Design rationale identifies design features and/or margins that have been provided in the design of the hardware or software element which minimize or eliminate the probability of occurrence of the failure mode and/or reduction or elimination of the potential causes of the failure mode. Test Rationale: Test rationale includes specific tests which are accomplished to detect failure modes and/or causes during acceptance and periodic certification. If turnaround checkout testing is accomplished via Operational and Maintenance Instructions (OMI's) the details of the test, frequency, and OMI number are included. Inspection Rationale: Inspection rationale addresses specific inspection methods,procedures, tools, and techniques which are performed on a pre-operational and/or post-operational basis to determine whether or not the critical failure modes have occurred. Inspections which minimize the probability of encountering failure modes and their potential causes are also included. Tear-down analysis is excluded as a means for inspection. Failure History: Failure history includes data on previously reported failures and corrective actions for the critical item in the critical failure mode(s) as found in the Problem Reporting and Corrective Action (PRACA) database. Reference is also made to the PRACA database for current data on test failures, unexplained anomalies, and other failures experienced during ground processing activities. Operational Use: Corrective action that would either prevent the particular mode or mitigate it's effect once it has occurred is included as part of the retention rationale. The time required to take the corrective action (timeframe) is also provided. The CIL sheet is presented to project management for approval/acceptance of the risk associated with the critical items and subsequently to the Program Requirements Control Board (PRCB) with the waiver request (CR). The waiver request identifies the failure modes which do not meet the fail safe requirement from NSTS 07700, Volume X. The fail safe requirement specifies that all GSE (except primary structure and pressure vessels) shall be designed to sustain a failure without causing loss of vehicle systems or loss of personnel capability. Suggestions for Effective CIL Implementation based on KSC experience Correlation of FMEA results with Fault-Tree Analyses and Hazard Analyses: The FMEA/CIL data can serve as an input to the hazards analysis process. The hazards analysis uses fault trees and is basically a top down approach. It focuses on human errors and considers multiple unrelated failure modes which the FMEA/CIL ground rules out. Use of the CIL sheets to initiate risk management controls: Preparation of the CIL sheet can be used as an opportunity to coordinate with the cognizant engineering organizations to develop and agree upon appropriate maintenance procedures and operational processes to assure control of the risks associated with the critical items. Subsequently the CIL can be used to initiate closed loop tracking of the test and inspection controls. Use of FMEA/CIL to develop test and checkout procedures: FMEA/CIL developed early in design projects can be used as input to develop test procedures, inspection requirements, operational procedures, and trouble shooting guides. The component level analysis performed in the FMEA and the detailed reporting of critical items provides specific information regarding failure scenarios with defined system reactions and expected personnel corrective action. CIL's should be implemented in a way that would not impact important program milestones or create unnecessary work-around in the areas of cost, schedules, or system performance. Example Uses of FMEA/CIL Use of FMEA for early identification of critical items: The design process for the 325 Ton Bridge Crane installed in the Vehicle Assembly Building at KSC utilized the FMEA process to identify potential critical single failure points in both hardware and software systems. As potential single failure points were identified the reliability engineer coordinated with the NASA and vendor design engineers. The design engineers were made aware of the failure effects, alternative designs were considered, and solutions were implemented. The FMEA process continued through test and acceptance of the equipment with the resulting design having no single failure points. Use of CIL sheets to identify risk to management: The CIL process was utilized during the analysis of the extensible and auxiliary access platforms in the VAB. The analysis was initiated by a design study that indicated that a substantial number of platforms were equipped with hinges that may fail under dynamic loading. Reliability engineering analyzed the systems and identified critical single failure points which, if failed, could allow a platform to fall causing a cascading effect of one platform upon another and resulting in the overloaded hinge scenario as described in the design study. The CIL sheets were used to advise management of the risks associated with platform operations. During presentation of the CIL sheets, Reliability Engineering also made recommendations for alternative fail-safe equipment. Management was able to assess the risks, accept interim controls and identification of new CIL items, and initiate implementation of corrective action. Use of CIL sheets to initiate test and inspection controls: The CIL process has been used at KSC to manage the risks associated with cranes and hoists which, if failed, could cause loss of life or vehicle. CIL sheets for critical gear systems/components identify test and inspection requirements which are performed in a close-looped tracking operations and maintenance process. Performance of a periodic load test at rated load, verifies the operational integrity of the gear system and periodic ferrographic analysis of the gear lubricant is used to document wear trends and to assist in predicting future failure. Technical Rationale: Extensive analytical work on existing and emerging programs relative to failure identification, management, and control has resulted in well documented, rigorous procedures for the treatment of critical items. Concurrent engineering approaches to program engineering and management have included attention to more details earlier in the design process and at a much lower level than previously attained. Assurance of success means the elimination or reduction of potential failure modes. Elimination or reduction of potential failure modes can only be achieved through the conscientious application of FMEA, critical item identification, and prudent engineering management. The advantages of the FMEA/CIL process are that it: (1) Systematically identifies all credible failure modes and causes; (2) permits a focus on critical SFP's and levels of redundancy; (3) provides management with risk acceptance rationale for critical failure modes/causes; (4) initiates control of critical items, associated procedures, and processes; and (5) provides a single, agreed-to listing of all critical items associated with a given project. References: National Space Transportation System Critical Items List, Shuttle Program Critical Items List, Kennedy Space Center Ground Support Equipment, NSTS 08399, Book 4, Revision A, Lyndon B. Johnson Space Center, Houston, TX, November 28, 1988. Problem Reporting and Corrective Action System Requirements, NSTS 08126, Lyndon B. Johnson Space Center, Houston, TX, April 7, 1994. Requirements for the Preparation and Approval of Failure Modes and Effects Analysis (FMEA) and Critical Items List (CIL), NSTS 22206, Revision D, Lyndon B. Johnson Space Center, Houston, TX, December 10, 1993. Space Shuttle Flight and Ground System Specification, FMEA/CIL Deviation and Waivers, NSTS 07700 Volume X, Book 5, Revision K, Lyndon B. Johnson Space Center, Houston, TX, October 9, 1992. Space Shuttle Program Configuration Requirements, NSTS 07700 Volume IV, Lyndon B. Johnson Space Center, Houston, TX, November 23, 1994. NASA Reliability Preferred Practice PD-ED-1240, Guideline for the Identification, Control and Management of Critical Items. | This practice has been used on all programs at the Kennedy Space Center. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/01/2000
650 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Fail Safe Firex/Deluge System |  | This system serves two purposes. It prevents a single failure from rendering the FIREX system inoperative and helps prevent the occurrence of an inadvertent operation of the FIREX Deluge System. | Incorporation of prudent design techniques results in reliable Firex/Deluge System Design Practice for Elimination of Single Point Failures and Unsolicited Operation. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number GSE-3002 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: This design standard incorporated a fail safe practice that prevents the two potential failures inherent to a water protection system: Lack of water flow when required Inadvertent water flow when not required. Implementation Method: This design implements a practice which might be considered as excessive due to the added expense of the additional water valves and their associated controls. However, applied in an appropriate situation this configuration could prove to be very cost effective. The appropriate application for this design would be where the protected materials are susceptible to ruination from water damage. The loss incurred from fire damage and the lack of fire extinguishing capability is well understood. This configuration provides added security to the user that the system will be available when required. Not as evident is the susceptibility to damage as a result of an inadvertent activation or failure. This arrangement provides the security that a single failure will not result in a water deluge potentially destroying the property it was designed to protect. Technical Rationale: The basis for this configuration is the series-parallel arrangement of the water valves shown in Figure 1. An adequate flow of water should be available to the user through any of the paths involving the ARM and ACTIVATE valves, i.e. all that is required is one ARM valve and one ACTIVATE valve to open (see figure 1 to show available water paths). The valves should be pneumatically or hydraulically controlled through electrically positioned solenoid valves. Each water valve should have its own controlling solenoid valve. The ARM solenoid valves should be controlled open by two parallel redundant controlling devices (relays, programmable logic controllers, etc.) and the ACTIVATE solenoid valves should be controlled open by two other parallel redundant controlling devices. Local and remote valve actuation should be provided with separate ARM and ACTIVATE switches. These arrangements insure that a single failure will not prevent water flow when required or initiate water flow when not desired. [D] References: KSC-STD-F-0004C: Standard for Fire Protection Design for Facilities, John F. Kennedy Space Center, NASA. SAA09SY03B-001: System Assurance Analysis of the Pad Water System at LC-39 Pad B & MLP-1, -2. 79K40019: LOA Facility Water Pad B SMS/EMCD. 80K55529: LOA Facility Water MLP 1, 2, & 3 SMS/EMCD. | This practice has been used on the Space Shuttle Program, Ground Support Equipment, KSC Launch Complex 39 Pad B Payload Changeout Room Firex/Deluge System KSC Mobile Launch Platform (-1, -2, -3) Hydrazine Service Area Firex/Deluge. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 03/01/2000
645 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Optical Fiber Cable Terminations Techniques and Procedures |  | Impact of Nonpractice: Failure to select approved materials and to follow the fabrication and inspection procedures of this practice can result in limited initial performance and further significant degradation during space flight. This degradation could result in mission failure. | Practice: Apply approved requirements and assembly techniques and procedures in the termination of optical fiber cables used in spaceflight applications. | GSFC | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-EC-1110 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: This practice ensures the performance reliability of optical fiber cable assemblies by requiring the selection of optical fiber cable components that have been tested and approved for spaceflight use and by specifying approved assembly and acceptance inspection and test procedures. Implementation: The termination of optical fiber cables used in spaceflight applications is performed in accordance with the GSFC approved training document, Ref. 1, which defines approved material requirements and detailed assembly techniques and procedures. Ref. 1 is used by engineers, senior technicians and those involved in training personnel in the techniques of terminating optical fiber cable. The procedures defined in the Ref. 1 training document are applicable to the following items from the MIL-STD-975 NASA Standard Electrical, Electronic, and Electromechanical Parts List, (NSPL), and the GSFC Preferred Parts List-20, (PPL-20): MIL-T-29504/4&5 Type II adhesive Optical fiber termini manufactured by Amphenol/Bendix and used in MIL-C-38999 Series III connectors OC-1008 optical fiber cables manufactured by Brand-Rex This procedure may not be applicable to other types of optical fiber cable and termini which may require different stripping techniques, polishing steps, tools, materials, and assembly instructions, all of which must be documented and controlled when spaceflight hardware is assembled. Personnel are cautioned about the use of parts from manufacturers not specified in the procedure as the use of those parts could result in unreliable cables. Other manufacturer's parts may be used, however, provided they are tested at GSFC, meet GSFC performance requirements, and are interchangeable with approved parts as determined by GSFC. Ref. 1 provides lists of approved materials required by the procedure including part numbers, manufacturer/source, and specifications. Also included is a list of equipment required by the procedure including model/part number and manufacturer or source. The assembly of an optical terminus onto an optical fiber cable is performed in the following four steps: Step 1- Equipment Parts, Preparation and Pre-cleaning This step ensures that all tools, materials, and equipment are checked against required part numbers, labeled, calibrated, and cleaned as required. The cleanliness of all parts which come in contact with the adhesive is critical to a reliable bond and end product. All parts which come in contact with the adhesive, including all dispenser parts and mixing pans, as well as the fiber and connector to be bonded, must be thoroughly cleaned with appropriate solvents before bonding. Note that some dispensers used for medical applications are internally coated with silicone for ease of dispensing. Silicone can mix with the adhesive and produce an unreliable bond. After cleaning is performed, care must be taken not to re-contaminate cleaned items by inadvertent contact with dirty surfaces. Also, equipment and setup information, tool part numbers, material lot numbers and other data are recorded in the certification logs in order to provide traceability in the event of problems. Step 2- Optical Fiber Cable Preparation and Stripping The optical fiber outer jacket, strength member, inner jacket, and fiber coating components are prepared for the bonding process by stripping and cleaning and are inspected for correct stripping dimensions before bonding. Cracks, nicks, cuts, excessive chemical strip wicking, or other potential damage to cable components including the fiber and the strength member are inspected after stripping and prior to bonding in accordance with an in-process inspection criteria. Required data including acceptance inspection is recorded in the certification log. Chemical stripping is used to remove the acrylate fiber coating since the fiber can be nicked inadvertently even by trained operators when mechanical stripping is used. Nicks in the fiber are very difficult to detect, and an undetected nick could result in a latent defect which may not become apparent for a considerable length of time. Chemical stripping solutions as well as other chemicals or materials may be limited life items (i.e., their potency may be reduced over time) and are marked, controlled, and handled to ensure that expired chemicals are not used for assembly of spaceflight hardware. Step 3- Terminus To Cable Bonding The optical fiber cable is bonded to the terminus and the excess glass fiber is cleaved in preparation for terminus polishing. Care is exercised to ensure that the temperature-controlled ovens are stabilized at the required temperatures, the stripped cable ends are clean, and that the epoxy does not spill out onto any parts of the terminus except the rear barrel. Cleanliness is critical to a reliable bond and end product. Mixed adhesive systems are degassed (i.e., by use of a centrifuge) before they are applied to optical fibers and connectors to minimize the potential for fiber breakage due to bubbles or voids in the adhesive surrounding the fiber. The proper weighting, mixing, and curing of adhesive systems are critical to a reliable product. Detailed instructions on weighting proportions and tolerances, number of mixing cycles or mixing time, and cure time and temperature with time and temperature tolerances (cure schedule) are included in the engineering documentation. The pot life or working life of an adhesive is determined as a function of temperature. The engineering documentation includes requirements for the adhesive's shortest pot life or working life for the temperature range specified during adhesive application. After connector bonding, inspection criteria is defined in the engineering documentation for the fiber and cable as well as the connector to ensure reliable connectorization. Data such as adhesive lot numbers, room temperature and humidity, and pot life are recorded in the certification log for traceability in the event of problems with the adhesive. The glass transition temperature (Tg) of the adhesive used to bond an optical fiber to an optical connect, contact, substrate, or other piece part is at least 10 degrees C greater than the maximum temperature that the optical assembly will be subjected to, including test and storage temperatures. The Tg of an optical fiber adhesive is controlled to minimize optical performance variations caused by the potential movement of the bonded fiber within the optical assembly after temperature cycling. Step 4- Bonded Terminus Polishing Polishing of a terminus bonded to a cable is accomplished in three stages; course hand polishing and a two step machine fine polishing procedure. Refer to the polishing procedures in Ref. 1. The connector assembly is inspected for excess adhesive on the fiber endface and other parts of the connector, as defined in the engineering documentation, which could interfere with proper operation of the connector. Excessive adhesive on the connector endface can flake off over time and create contamination which can affect performance. Excess adhesive on other connector parts can prevent springs and other mechanisms from operating properly or fitting properly together. The optical fiber is back-lit using a flashlight from the opposite end of the cable assembly without touching the fiber when inspecting a finished fiber optic connector for cracks in the fiber. The polishing process produces a "flat" polish and the use of an interferometer is recommended to measure the profile of a fiber endface. The amount of fiber protrusion and the amount of fiber undercut is specified in the engineering documentation. Physical contact connectors, angle polished connectors, or other specialized polished endfaces have specific requirements for endface finishing. The amount of fiber protrusion, amount of fiber undercut, connector endface geometry parameters and tolerances, such as flatness, radius of curvature, vertex offset, or angle, as a minimum, are specified in the engineering documentation. Final Polish Verification Visual examination of the polished, bonded terminus is performed to ensure that the finished termination is of high optical quality and free of unacceptable defects, such as chips, contamination, cracks, scratches, pits, or hackles. A 200X hand held microscope is used and because of the high magnification, the microscope lens and terminus adapter and the polished terminus must be clean. Loose debris or dust is removed by using dry nitrogen. Care is used to insure that lenses of the microscope and the polished terminus are not scratched. Cleaning and inspection is accomplished in accordance with the step by step procedures of Ref. 1. Acceptance Criteria The following define the acceptance criteria: The terminus must have a smoothly polished face and glass fiber free of visible scratches and imperfections which affect optical performance or reliability. No visible scratches on the terminus ceramic face. No fiber edge chips, scratches, pits, or hackles. No contamination. No fiber cracks or cracks anywhere in the ceramic ferrule. No excess epoxy around the fiber or spots of apoxy anywhere on the ceramic face. Optical Performance Verification The optical fiber cable has been terminated on both ends and conforms with all acceptance criteria up to this point. Optical performance verification is performed by conducting a power loss measurement in accordance with a test setup and the procedure defined in Ref. 1. The first step is to perform power loss measurements without the optical fiber cable in the test setup to establish reference measurement values. The second step is to insert the cable to be verified into the test setup without changing anything else in the test setup and repeating the power loss measurement. The difference in the two power loss measurements, is the power loss of the optical fiber cable. Power Loss Acceptance Criteria Power losses of -1.0 dB per terminus or -2.0 dB per cable is the acceptable value for the two termini of each completed cable. In addition acceptable cable length losses for cables less than 34 feet long is 0.1 dB. Acceptable cable length losses for cables longer than 34 feet are based on -0.003 dB per foot of cable length. Cables that fail the power loss acceptance criteria may be repaired by cleaning or additional fine polishing of an terminus or by replacement of a defective terminus if the cable length permits replacement of a terminus. Connector Installation A terminated optical fiber cable is installed into a MIL-C-38999 connector before it is used in a spacecraft harness assembly. The optical fiber terminus is installed into the connector in the same way that a wire contact is installed. Care is exercised to ensure that the termini ends are not touched, contaminated, or scratched during installation. Standard contact extraction tools for the MIL-C-38999 connector are used if the termini are to be removed from the connector. Mechanical strain relief backshells are used as appropriate. Socket termini have springs which allow for movement inside a connector when optical termini are mated together. Care is exercised to ensure that the strain relief allows for a slight movement of all socket termini cables in the harness. Optical fiber cable connector terminations are inspected and cleaned if necessary before each mate. Under no circumstances are 100 mate and demate cycles exceeded without cleaning the fiber optical termination to ensure consistent optical performance. Dust caps which are non-outgassing in laboratory or room environments are used as covers for optical assemblies. Vinyl dust covers are not used. Technical Rationale: The use of components, materials, and techniques used in the fabrication of optical fiber cables that have not been tested and approved for spaceflight use could result in significant loss of performance during the mission. Outgassing of contaminates in space can be a serious problem with optical fiber systems. Also, space radiation can cause significant loss in performance of certain optical fibers. Nicks in the small and fragile glass fiber can result in latent optical defects and failures. References: GSFC Document No. 733-FO-29504-TERM-TRAINING Entitled "Optical Fiber Cable Termination Procedures For Spaceflight Applications Using MIL-T-29504 Optical Fiber Termini" | Programs That Utilize Practice: GSFC X-Ray Timing Explorer Mission (XTE); GSFC Tropical Rainfall Measuring Mission (TRMM) | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/01/2000
647 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Solar Flare Proton and Heavy Ion Modeling for Single Event Effects | Preferred Practice for Design & Test. Non-use of the updated JPL solar flare proton and heavy ion models could force designers to over-design, based on the predictions from the Adams worst case model which predicts unrealistically high single event effects. Formulate an energetic particle environment model for calculating single event effect rates by utilizing the JPL statistical models for solar proton, alpha particle and heavy ion fluence. This predicted rate, which is a function of cumulative probability, is a useful measure when specifying shielding thickness to protect susceptible components, employing mitigating software, or both to reduce the risk to an acceptable level. | Impact of Nonpractice: Non-use of the updated JPL solar flare proton and heavy ion models could force designers to over-design, based on the predictions from the Adams worst case model (ref. 6) which predicts unrealistically high single event effects. | Practice: Operational spacecraft can experience adverse effects from impinging high energy radiation. A single event upset (SEU) occurs when a single particle, usually a heavy ion or proton, deposits enough charge at a sensitive node in a microcircuit to cause that circuit to change state. In general, these effects are temporary and appear as "soft failures" such as anomalous bit flips or spurious commands. In extreme cases, latch-up can occur and result in the destructive failure of the part. The practice is to formulate an energetic particle environment model for calculating single event effect rates by utilizing the JPL statistical models for solar proton, alpha particle and heavy ion fluence. This predicted rate, which is a function of cumulative probability, is a useful measure when specifying shielding thickness to protect susceptible components, employing mitigating software, or both to reduce the risk to an acceptable level. Note that this assessment does not consider concentration of particle radiation due to the Earth's magnetic field, (ref. 1), and factors which are not influenced by shielding thickness, such as GCR (Galactic Cosmic Rays). | JPL | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-EC-1105 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Shielding thickness can be realistically assessed by considering the cumulative probability of component failure due to radiation of solar particles. Implementation Method: JPL computer codes (ref. 2 & 3), simulate the transport of ion fluxes determined from the particle models through specified shielding thicknesses of aluminum to obtain resultant spectra. These spectra are used to calculate device single event effect rates when applied to the laboratory measured cross sections. For low linear energy transfer (LET) threshold devices, proton upset cross sections vs. energy are used to determine upset rates from the proton energy spectra. For higher LET threshold devices the measured upset cross section vs. LET is used with the Heinrich flux for heavy ions to determine single event effect rates. Technical Rationale: Penetrating ions create ionization tracks in silicon components. The heavier ions produce denser ionization tracks. Disposition of the created charge, which depends on the electric field configuration within the device, can lead to the following effects: Recombination without single event effects, Single event upsets, Device latch up, and Spurious signals. Measurements of proton solar event fluences and alpha particle solar event fluences have been obtained for many solar flares. Organizing these data in a statistical manner according to cumulative probability of occurrence for a specified particle event fluence level constitutes the proton and alpha particle models. Solar flare heavy ion data are more difficult to obtain because the lower flux levels and the need for mass discrimination requires more sophisticated instrumentation. The paucity of available data creates the need for a heavy ion model based on solar abundance's. A solar heavy ion model (ref. 4) has been constructed based on the work of Breneman and Stone (ref. 5) who analyzed heavy ion data from 10 solar flares between 1977 and 1982. It has been assumed that the average alpha fluence is predictable from the heavy ion model relative to the other ion species. However, the proton fluence is not predictable from the heavy ion model. The heavy ions are normalized to the alpha particle probability of occurrence fluence levels by requiring that the integrated alpha fluence level from the heavy ion model match the fluence level from the measured alpha statistical distribution model. Complete ion flux spectra are specified in this manner. These spectra can be introduced into transport software to determine shielding requirements and software to determine single event effect rates. Related Practices: Environmental Factors, Practice No. PD-EC-1101 References: SSP 30425 (SSP Natural Environment Definition), Chapter 6. Feynman, J., Spitale, G., Wang, J., Interplanetary Proton Fluence Model: JPL 1991, Jet Propulsion Laboratory IOM 5217-92-23, February 6, 1992. Spitale, G., Feynman, J., Wang, J., Solar Alpha Particle Model: Progress and Problems, Jet Propulsion Laboratory IOM 5217-92-60, March 5, 1992. Croley, D.R., Solar Flare Heavy Ion Model, IEEE Transactions on Nuclear Science, June 22, 1992. Breneman, H., Stone, E. (1985). Solar and Photospheric Abundance from Solar Energetic Particle Measurements, Astrophysical Journal, 299, L57-L61. Adams, et. al., (1981). Cosmic Ray Effects on Microelectronics, Part I: The Near-Earth Particle Environment. NRL Memorandum Report 4506, Naval Research Laboratory, Washington, D.C. | Programs That Certified Usage: Cassini, Multi-Angle Imaging Spectroradiometer (MISR), Atmospheric Infrared Sounder (AIRS), NASA SEP Technology Application Readiness (NSTAR), Hermes, Advanced Composition Explorer (ACE), Mars Missions. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/01/2000
646 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Power Line Filters |  | Impact of Nonpractice: The absence of power line filters frequently results in cross interference, which disrupts the proper operation of hardware and can obliterate science data. These problems usually can be identified in ground testing; however, correcting them by retrofitting flight hardware is very difficult and expensive. Therefore, it is important that power line filters be included in the early design of hardware. Significant interference problems can occur on orbit that were not found in ground testing due to unexpected ground loops or to hardware interface situations that could not be duplicated exactly during ground testing. Also, deterioration or partial failure of components and parts can result in increased levels of noise on power and ground buses. Hardware that is susceptible to conducted emissions can exhibit such problems as microprocessor resets, false or inaccurate engineering data readouts, unintentional mode changes, and lost or noisy scientific data. Power line filters minimize these interference problems by isolating hardware from conducted noise on power lines. | Practice: Power line filters are designed into power lines (power buses) at the inputs to payloads, instruments, subsystems, and components. | GSFC | 02/01/1999 | This Lessons Learned is based on Reliability Practice No. PD-ED-1206 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Power line filters minimize the flow of conducted noise currents on power buses emanating from hardware that could interfere with the proper operation of other hardware also operating on the same power buses. Additionally, power line filters minimize the flow of noise currents on power buses into hardware which could interfere with the proper operation of that hardware. Implementation: Power line filters are used to meet the Conducted Emission and Conducted Susceptibility Requirements of GSFC's General Environmental Verification Specification for STS and ELV Payloads, Subsystems, and Components (GEVS-SE). This document contains a baseline for demonstrating by test the satisfactory performance of hardware in the expected mission environments. Technical Rationale: The problems of Conducted Emission and Conducted Susceptibility have been widely recognized for many years. The EMC community and the Department of Defense have collaborated in preparing and in continually reviewing and updating a widely used set of EMC design and test requirements designated MIL-STD-461, 462, and 463. These requirements have been tailored for specific spaceflight application and incorporated by the GSFC into the GEVS-SE document along with specific requirements defined in the Shuttle Orbiter/Cargo Standard Interfaces Document (JSC 07700 Volume XIV Attachment 1 (ICD 2-19001). References: General Environment Verification Specification For STS and ELV Payloads, Subsystems, and Components (GEVS-SE). Shuttle Orbiter/Cargo Standard Interfaces Document (JSC 07700 Volume XIV Attachment 1 (ICD 2-19001). | Programs That Certified Usage: All GSFC flight programs. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/01/2000
648 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Design Review Checklists for Space Shuttle Ground Support Equipment (GSE) |  | Failure to use a checklist during the design phase could result in an R&M issue or consideration being overlooked. This could have an impact on the final reliability. Also, making reliability improvements later than the design phase, such as in the prototype or production phase, would result in a much greater increase in cost for the improvement than if the change were done earlier. | The use of a checklist which delineates specific reliability and maintainability (R&M) considerations during design reviews ensures that no critical R&M consideration will be overlooked during the design phase of a project. | KSC | 01/31/1999 | This Lesson Learned is based on Reliability Practice number GSE-3004 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefit: Adherence to a design review checklist ensures that reliability and maintainability (R&M) issues, including those requirements necessary to meet the R&M specifications, are considered early in the design phase of a project when the cost is minimal for making changes. This will provide the highest reliability for the minimum cost. Implementation Method: The technical checklist is prepared by Reliability and Maintainability Engineering to ensure that all R&M considerations and issues have been taken into account during the design phase of GSE. The checklist is formatted for ease of use by all engineering disciplines involved. A question format can be used to ensure that critical factors are not overlooked. The following is a list of some of the issues to be considered during a design review: Preliminary Design Review Identification of critical equipment Program plans Preliminary test plans Progress of the design Reliability allocations and predictions Redundancy requirements Maintenance concept: Repair level Stock provisions Built-in-test features Predictions Intermediate Design Reviews Reliability analyses: Allocations Predictions FMECA, FMEA Failure data Growth test data Production assurance data Vendor data Critical Design Review Subsystem and component specifications Test plans and procedures Critical component identification and evaluations Final design configuration Reliability analyses: Predictions Stress Analysis FMECA, FMEA Worst Case Analysis Test results; Environmental and Operational At KSC, LSOC R&M Engineering has developed a checklist to cover reliability, maintainability, safety and quality assurance issues for Space Shuttle GSE development. This checklist is used during the design phase of the GSE projects. R&M concerns and requirements for the Shuttle program are addressed in the checklist and brought to the attention of design and project engineering. Technical Rationale: The checklists have resulted from operational experience with the Shuttle Program. The document which incorporates the checklist also includes a cross reference which relates items on the Reliability and Maintainability Checklists to Shuttle Program requirements. The table of contents of the document has been included with this practice. A sample is also included of some of the items from the Reliability, Quality, Maintainability and Safety Checklists. There are in excess of 60 pages of checklist items which actually comprise the Checklists for Reliability, Quality, Maintainability, and Safety. The format and the topics addressed in the checklist will also work for other applications and the checklist is designed to be tailored to meet the specific needs of the individual programs. The complete checklist is contained in reference 2. PROCEDURE FOR PERFORMING SPC DESIGN REVIEWS, S&R-P-003 TABLE OF CONTENTS (Reference Only) INTRODUCTION 1.0 PROGRAM REQUIREMENTS 2.0 GROUND SUPPORT EQUIPMENT DESIGN REQUIREMENTS 3.0 REFERENCE DOCUMENTS 4.0 RELIABILITY & QUALITY ASSURANCE DESIGN REQUIREMENTS 4.1 GENERAL 4.2 DESIGN FOR RELIABILITY 4.3 BASIC RELIABILITY DESIGN PRINCIPLES 4.3.1 Design Simplicity 4.3.2 Redundancy 4.3.3 Derating 4.3.4 Environmental Design 4.3.5 Self-Healing Items 4.3.6 Parts Selection and Control 4.4 RELIABILITY & QUALITY ASSURANCE DESIGN REVIEW CHECKLIST 5.0 MAINTAINABILITY DESIGN CHARACTERISTICS 5.1 GENERAL 5.2 MAINTAINABILITY DESIGN GUIDELINES 5.2.1 Electrical/Electronic Equipment Design 5.2.1.1 Cables and Connectors 5.2.1.2 Miniaturization And Modular Design 5.2.2 Mechanical Equipment Design 5.2.3 Fluid Equipment Design 5.2.4 Interchangeability 5.3 MAINTAINABILITY DESIGN REVIEW CHECKLIST 6.0 SAFETY DESIGN REVIEW CHECKLISTS 6.1 GENERAL 6.2 SAFETY DESIGN GUIDELINES 6.3 DESIGN SAFETY CHECKLIST TABLES Table 1 Shuttle Program RM&QA Requirements for Ground System Design Table 2 Shuttle Program RM&QA Technical Requirements and Criteria for GSE Design Table 3 Reliability Design Review Checklist Table 4 Quality Assurance Design Review Checklist Table 5 Maintainability Design Review Checklist Table 6 Generic Hazard Checklist Table 7 Design Safety Checklist [D] [D] [D] [D] References: Reliability Engineering for Electronic Design, Norman F. Fuqua, Marcel Dekker, Inc. 1987, pp. 365-366. Lockheed Space Operations Company, Procedure for Performing SPC Design Reviews, S&R-P-003. | This practice has been used on the Space Shuttle Program, Ground Support Equipment. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 03/01/2000
644 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | Ni-Cd Conventional Spacecraft Battery Handling and Storage |  | The impact of not following this practice would very likely be that flight batteries would be irreversibly degraded due to improper handling and preparation for launch. This could result in the failure of batteries to meet flight performance requirements and also possibly early catastrophic failures. | Flight projects develop and implement handling and storage procedures for Ni-Cd flight batteries when applicable to minimize deterioration and irreversible effects on flight performance due to improper handling and storage. The procedures described in this practice are specifically for Conventional Ni-Cd batteries and are not necessarily applicable to Super Ni-Cd batteries. | GSFC | 02/01/1999 | This Lessons Learned is based on Relibility Practice number PD-EC-1103 from NASA Technical Memorandum 4322A, NASA Reliability Preferred Practices for Design and Test. Benefits: Ni-Cd batteries are perishable and their ability to satisfactorily complete mission life is directly related to prudent handling and storage procedures. The development and implementation of appropriate project-unique procedures based on a set of proven guidelines assure that the optimum performance of Ni-Cd batteries is not degraded due to inappropriate handling and storage. Implementation: The Ni-Cd cell is constructed of positive plates (nickel electrodes), negative plates (cadmium electrodes), and a separator material that is interleaved with the plates and serves to insulate the positive plates from the negative plates and retain the electrolyte. The plates are connected to the respective cell terminals which are attached to a cell cover and inserted in a steel case and welded shut. The electrolyte is normally 31 percent concentration of potassium hydroxide and is added though the "fill tube" which is fitted with a pressure gauge. After the cell satisfactorily completes its manufacturing and acceptance testing, the fill tube is pinched off and welded closed. The manufacture of a hermetically sealed Ni-Cd is predicated on a delicate balance between the active material, the relative state-of-charge of the active material between the positive and negative plates at the time the cell is sealed, the amount of electrolyte placed in the cell at closure, the properties of the separator material, and the free volume allowed by the case design. The aerospace Ni-Cd cell, which has no free or excess electrolyte, is referred to as an "electrolyte starved" design. The primary prerequisite for a sealed-electrolyte starved cell to operate safely is that the positive plates be limiting on charge so that only oxygen is generated during overcharge. During charge some of the current is utilized in the generation of oxygen gas and when in overcharge, all the current is used in generating oxygen. This causes the cell pressure to increase to a level that is dependent on the recombination rate of oxygen at the negative electrode, the rate of diffusion of the oxygen through the separator, the amount of electrolyte in the cell, and the cell free volume. The cell pressure at 20 degrees C can typically be in the range of 50 to 65 PSIG. The negative plates of a cell contain approximately 50 percent more capacity than the positive electrode. Of this "excess" negative capacity, approximately 60 percent remains uncharged when the positive plates are fully charged. This uncharged material is referred to as "overcharge protection" and is required to prevent the plates from becoming fully charged and generating hydrogen gas. The remainder of the excess negative material is in the charged state when the cell is fully discharged and provides over-discharge protection. It is referred to as precharge. On discharge, when the cell voltage drops below 1 volt, the positive plates are limiting, thereby leaving charged cadmium material to react with any residual oxygen when the cell is completely discharged. Typical pressure of fully discharged cells is 3 to 5 PSIG. A second reason for the positive plates to be limiting on discharge is to prevent the effects of negative capacity fading, which occurs during normal use, from causing losses in cell capacity. It is thought that capacity fading is related to the sizes of the cadmium crystals. It is most important that the overcharge protection is available for the entire life of the cell. Should the negative plates become fully charged, hydrogen gas is generated during overcharge and there is no effective mechanism within the cell for the recombination of Hydrogen gas. If a cell is over discharged (potential reversed) Hydrogen gas is generated at the positive electrode at a rate dependent upon the discharge rate. Because of the limited free space in a sealed cell, a cell that is reversed can quickly build up pressure and rupture the cell case or battery package. The Ni-Cd cell is a highly complex, interactive electrochemical device where the present and future performance is totally dependent on its past history. This history includes the attributes and characteristics of the raw materials, the processing of these materials into components, the assembly of these components into a sealed cell, and all testing, handling, and storage. Consequently, a cell or battery is classified as perishable and treated accordingly. Because Ni-Cd batteries can be irreversibly degraded by improper use and handling, the following guidelines were developed for the use of battery engineers in preparing project-specific Battery Handling and Storage Requirement Documents: GUIDELINE NO. 1 - Flight batteries should be maintained in a discharged and shorted condition and stored at cold temperatures when not required for "critical" spacecraft testing. The electrochemical activity is at a minimum in the discharged state and when stored at the optimum storage temperature of 0 degrees C. A battery, stored discharged and shorted up to three years since cell activation, is expected to provide several years life of nominal performance in orbit. GUIDELINE NO. 2 - Flight batteries should not be subjected to extended spacecraft integration and test activities. The open circuit and intermittent use of Ni-Cd batteries during extended spacecraft integration and testing activities are known to significantly accelerate the degradation of batteries. Results from controlled tests have shown permanent and irreversible changes unlike anything observed after several years of spacecraft flight operations. Degradation is observed initially as an increase in cell overcharge voltage at low temperatures which is indicative of loss in overcharge protection. Also, integration and testing use promotes significant cadmium migration. Both of these are recognized as the dominate wear-out mechanisms which determine battery life. GUIDELINE NO. 3 - The use of charged batteries after an open stand should be initiated with a 3 to 5 minutes discharge prior to initiating battery charge. Typically the discharge is done with spacecraft load and in concert with the spacecraft ground power console. During normal cycling use, the battery is discharged followed by a recharge and some overcharge. In this mode, there is always a partial pressure of oxygen from the overcharge with oxygen recombination occurring at the negative electrode. In a relatively short time on open circuit, the oxygen recombines and the internal cell pressure returns to a vacuum. Charging cells that are fully charged in the absence of oxygen creates an "unnatural" condition, since there is no oxygen available to react with the negative electrodes. Past experience shows that this technique reduces the effects of open circuit stand on performance. GUIDELINE NO. 4 - During periods when the battery is not needed to support spacecraft test and operations, it should be maintained on a low rate trickle charge, (C/100). Trickle charge at low rates is preferred to open circuit stand for a battery. While there are degradation mechanisms associated with trickle charge, data from controlled tests indicate that this to be much less detrimental than open circuit stand. GUIDELINE NO. 5 - Cooling should be provided to maintain battery temperatures at about 18 degrees C during spacecraft integration and test operations. Exposures to elevated temperatures accelerate cadmium migration and separator breakdown which depletes the overcharge protection in the cells. Since the rate of separator degradation increases by a factor of 3 for every 10 degree C rise in temperature, strict adherence to this guideline is advised. GUIDELINE NO. 6 - A battery stored discharged and shorted for a period greater than 14 days should be activated with a "reconditioning cycle" prior to placing it in use. The reconditioning cycle is performed at 20 degrees C and is defined as follows: Recharge at C/20 (C/*** indicates recharge or discharge rates in terms of "name plate" battery capacity, e.g., C/20 = 1/20 of the capacity listed on the battery nameplate) for 40 hours (+/- 4 hours) Discharge at C/2 constant current rate until the first cell reaches 1.0 volts. Drain each cell with a 1 ohm resister to less than 0.03 volts. Short each cell for a minimums of 4 hours Recharge battery at C/20 constant current rate for 40 hours (+/- 4 hours) GUIDELINE NO. 7 - Charged batteries should not stand on open circuit for more than 14 days. Charging should be initiated only after implementing Guideline No. 3. When cells are on open circuit "self discharge" occurs which results in the formation of large cadmium crystals. Controlled tests have shown capacity loss of just under 1% per day at 23 degrees C and about 1.5% at 35 degrees C. The self discharge rate of each cell is not identical, consequently after extended periods of open circuit, there can be an appreciable capacity loss and capacity divergence between cells in a battery. This can be remedied by discharging the battery as described in Guideline No. 3 and trickle charging the battery several hours to bring all cells into balance. GUIDELINE NO. 8 - A battery should be "reconditioned" if it has been on open circuit, subjected to intermittent use, i.e., open circuit, trickle charge, occasional discharge, etc., for a cumulative period of 30 days. Reconditioning is effected by performing the following sequence at 20 degrees C: Discharge at C/2 constant current rate until the first cell reaches 1.0 v/c. Drain each cell with a 1 ohm resistor until each cell's voltage is less than .03 V/C. Short each cell for a minimum of 4 hours. Recharge battery at C/20 constant current rate for 40 hours (+/- 4 hours). Repeat steps a, b, and c. Charge battery at C/10 constant current rate for 16 hours ( +/- 4 hours). Repeat steps a, b, c, and f. Exercising the active material by periodic discharge of each cell followed by a low charge helps retard permanent change in the crystal structure of the cadmium electrodes and forces electrolyte redistributions within the cell. The less frequent the reconditioning cycles, the less effective the reconditioning cycle is in restoring the discharge voltage of a battery. GUIDELINE NO. 9 - Flight batteries should be discharged and cells shorted during shipment. Batteries should be packaged to exclude humidity and control temperatures to 5 degrees C (+/- 5 degrees C) and the shipping container should be equipped with temperature recorders to provide assurances that flight batteries have not been exposed to temperatures exceeding 25 degrees C. A Ni-Cd battery can deliver very high currents if shorted. High currents would create a safety hazard as well as destroy the battery due to the excessive heat that would be generated. Elevated temperatures enhance the rates of electrochemical reaction and separator hydrolysis. GUIDELINE NO. 10 - The final reconditioning of flight batteries should be performed at least 14 days prior to spacecraft launch. Upon completion of the reconditioning, flight batteries should be kept on low rate trickle charge until launch. Use the reconditioning sequence defined in Guideline No. 8. The reconditioning cycle restores the battery discharge voltage to "like new" condition by enhancing the formation of small cadmium crystals and electrolyte redistribution. A complete discharge establishes capacity balance for all cells within a battery. The low rate trickle ensures that the battery is maintained at full state of charge for launch. GUIDELINE NO. 11 - The design of flight batteries should include the following provisions for ground console interfacing with the batteries while integrated in the spacecraft: Signal lines for monitoring total battery voltage, charge and discharge currents, battery temperatures, and individual cell voltages. Capability to charge and discharge the battery from the ground test console Capability to place a resistor and a shorting plug across each individual cell Capability must be provided to monitor the state of health of batteries and to discharge, charge, trickle charge and recondition batteries without powering up the spacecraft in order to meet guidelines to minimize degradation of the batteries. GUIDELINE NO. 12 - A log book should be maintained on each flight battery including the complete test histories of each cell, of the assembled battery, and of all integration and test and launch site activities. Each log book should identify the project and battery and individual cell serial numbers. Chronological (date and time) entries for all test sequences, summary of observations, identification of related computer stored records, malfunctions, names of responsible test personnel, and references to test procedures controlling all tests should be recorded. Since Ni-Cd batteries are perishable, their ability to satisfactorily complete their mission life is directly related to their storage, their ground use, and handling. Historical performance information is required to ensure their flight worthiness at launch time. The referenced document provides additional details concerning the degradation mechanisms of Ni-Cd cells and how these mechanisms are affected by improper ground handling. The reference also includes a synopsis of Ni-Cd cell design and evolution over 30 years of space flight on GSFC satellites along with a chronological review of key elements which influenced the current design of the Ni-Cd cells. Technical Rationale: Ni-Cd batteries can be damaged and irreversibly degraded through improper use and handling prior to launch. The 12 guidelines provided above were developed over many years of experience in the use, handling, and testing of Ni-Cd batteries. Following these guidelines ensures that flight batteries are not irreversibly degraded and have been properly reconditioned and prepared for launch. References: Handbook For Handling And Storage Of Nickel Cadmium Batteries: Lessons Learned - NASA Reference Publication 1326 - February 1994. | GSFC Programs That Used Practice: Solar Maximum Mission (SMM); Landsat; Earth Resource Budget Satellite (ERBS); International Ultra-violet Explorer (IUE); Cosmic Background Explorer (COBE); Gamma Ray Observatory (GRO); Tracking and Data Relay Satellite System (TDRSS); National Oceanic & Atmospheric Administration/Television Infrared Observation Satellite (NOAA/TIROS); Geostationary Operational Environmental Satellite (GOES); Upper Atmospheric Research Satellite (UARS); Extreme Ultraviolet Explorer (EUVE) | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/18/2000
643 | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN | Harkins, Wil - 0000000000 : NO@ADDRESS.GIVEN |  | NASA Preferred Reliability Practices; Design and Test Practices for Aerospace Systems; Environmental Factors |  | Failure to perform a detailed life cycle environment profile can lead to overlooking environmental factors whose effect is critical to equipment reliability. If these factors are not included in the environmental design criteria and test program, environment-induced failures may occur during space flight operations. | At the onset of the design process, identify the operating conditions that will be encountered during the life of the equipment. | GRC | 01/31/1999 | This Lessons Learned is based on Reliability Practice NO. PD-EC-1101 from NASA Technical Memorandum 4322A, NASA Preferred Reliability Practices for Design and Test. Benefits: Each of the identified environmental factors requires consideration in the design process. This assures that adequate environmental strength is incorporated into the design to ensure reliability. Implementation Method: To ensure a reliability-oriented design, determine the needed environmental resistance of the equipment. The initial requirement is to define the operating environment for the equipment. A Life-Cycle Environment Profile, containing this information, should be developed. A Life-Cycle Environment Profile is a forecast of events and associated environmental conditions that an item experiences from manufacturing to retirement. The life cycle includes the phases that an item will encounter such as: handling, shipping, or storage prior to use; disposition between missions (storage, standby, or transfer to/from repair sites); geographical locations of expected deployment; and platform environments. The environment or combination of environments the equipment will encounter at each phase should be determined. All deployment scenarios should be described as a baseline to identify the environments most likely to be associated with each life cycle phase. The following factors should also be taken into account: Hardware configuration. Environment(s) that will be encountered. Platform/hardware interfaces. Interfaces with other equipment. Absolute and relative duration of exposure phase. Probability that environmental condition(s) will occur. Geographical locations. Any other information that will help identify environmental conditions that may impact the item. The steps in developing a Life-Cycle Environment Profile are as follows: Describe anticipated events for an item of equipment, from final factory acceptance through terminal expenditure or removal from inventory. Identify significant natural and induced environments or combination of environments for each anticipated shipping, storage, and logistic event (such as transportation, dormant storage, stand-by, bench handling, and ready modes, etc.). Describe environmental and stress conditions (in narrative and statistical form) to which equipment will be subjected during the life cycle. Data may be derived by calculation, laboratory tests, or operational measurements. Estimated data should be replaced with actual values as determined. The profile should show the number of measurements used to obtain the average value of these stresses and design achievements as well as their variability (expressed as standard deviation). This analysis can be used to: develop environmental design criteria consistent with anticipated operating conditions, evaluate possible effects of change in environmental conditions, and provide traceability for the rationale applied in criteria selection for future use on the same program or other programs. A listing of typical environmental factors is included in Table 1. Table 1: Environmental Coverage Checklist (Typical) Natural Induced Albedo, Planetary IR Clouds Electromagnetic Radiation Electrostatic Discharge Fog Freezing Rain Frost Fungus Gravity, Low Hail Humidity, High Humidity, Hight Ice Ionized Gases Lightning Magnetics, Geo Meteoroids Pollution, Air Pressure, High Pressure, Low, Vacuum Radiation, Cosmic, Solar Rain Salt Spray Sand and Dust Sleet Snow Temperature, High Temperature, Low Wind Acceleration Chemicals Corona Electromagnetic, Laser Electromagnetic Radiation Electrostatic Discharge Explosion Icing Magnetics Moisture Nuclear Radiation Shock, Pyro, Thermal Space Debris Temperature, High, Aero. Heating, Fire Temperature, Low, Aero. Cooling Turbulence Vapor Trails Vibration, Mechanical, Microphonics Vibration, Acoustic Technical Rationale: Given the dependence of equipment reliability on the operating conditions encountered during the life cycle, it is important that such conditions be identified accurately at the beginning of the design process. Environmental factors that strongly influence equipment reliability are included in Table 1, which provides a checklist for environmental coverage (typical). Concurrent (combined) environments may be more detrimental to reliability than the effects of a single environment. In characterizing the design process, design/test criteria must consider both single and/or combined environments in anticipation of providing the hardware capability to withstand the hazards identified in the system profile. The effects of typical combined environments are illustrated in a matrix relationship in Figure 1, which shows combinations where the total effect is more damaging than the cumulative effect of each environment acting independently. For example, an item may be exposed to a combination such as temperature, humidity, altitude, shock, and vibration while it is being transported. The acceptance to end-of-life history of an item must be examined for these effects. Table 2 provides reliability considerations for pairs of environmental factors. Each environmental factor that is present requires a determination of its impact on the operational and reliability characteristics of the materials and parts comprising the equipment being designed. Packaging techniques should be identified that afford the necessary protection against the degrading factors. In the environmental stress identification process that precedes selection of environmental strength techniques, it is essential to consider stresses associated with all life intervals of the equipment. This includes operational and maintenance environments as well as the pre-operational environments, when stresses imposed on the parts during manufacturing assembly, inspection, testing, shipping, and installation may have significant impact on equipment reliability. Stresses imposed during the pre-operational phase often are overlooked; however, they may represent a particularly harsh environment that the equipment must withstand. Often, the environments to which systems are exposed during shipping and installation are more severe than those encountered during normal operating conditions. It is probable that some of the environmental strength features that are contained in a system design pertain to conditions that will be encountered in the pre-operational phase rather than during actual operation. Figure 1: Effects of Combined Environments [D] (Click image for a larger view) Table 2: Various Environmental Pairs High Temperature and Humidity High Temperature and Low Pressure High Temperature and Salt Spray High temperature tends to increase the rate of moisture penetration. The general deterioration effects of humidity are increased by high temperatures. Each of these environments depends on the other. For example, as pressure decreases, outgassing of constituents of materials increases; as temperature increases, outgassing increases. Hence, each tends to intensify the effects of the other. High temperature tends to increase the rate of corrosion caused by salt spray. High Temperature and Solar Radiation High Temperature and Fungus High Temperature and Sand and Dust This is a man-independent combination that causes increasing effects on organic materials. A certain degree of high temperature is necessary to permit fungus and microorganisms to grow. However, fungus and microorganisms cannot develop above 160°F (71°C). The erosion rate of sand may be accelerated by high temperature. However, high temperature reduces sand and dust penetration. High Temperature and Shock and Vibration High Temperature and Acceleration High Temperature and Explosive Atmosphere Since both environments affect common material properties, they will intensify each other's effects. The degree to which the effect are intensified depends on the magnitude of each environment in combination. Plastics and polymers are more susceptible to this combination than metals, unless extremely high temperatures are involved. This combination produces the same effect as high temperature and shock and vibration. Temperature has minimal effect on the ignition of an explosive atmosphere but does affect the air-vapor ratio, which is an imporant consideration. Low Temperature and Humidity High Temperature and Ozone Relative humidity increases as temperature decreases, and lower temperature may induce moisture condensation. If the temperature is low enough, frost or ice may result. Starting at about 300°F (150°C) temperature starts to reduce ozone. Above about 520°F (270°C), ozone cannot exist at pressures normally encountered. Low Temperature and Solar Radiation Low Temperature and Low Pressure Low Temperature and Salt Spray Low temperature tends to reduce the effects of solar radiation and vice versa. This combination can accelerate leakage through seals, etc. Low temperature reduces the corrosion rate of salt spray. Low Temperature and Sand and Dust Low Temperature and Fungus Low temperature increases dust penetration. Low temperature reduces fungus growth. At sub-zero temperatures, fungi remain in suspended animation. Low Temperature and Shock and Vibration Low Temperature and Acceleration Low Temperature and Explosive Atmosphere Low temperature tends to intensify the effects of shock and vibration. However, it is a consideration only at very low temperatures. This combination produces the same effect as low temperature and shock and vibration. Temperature has minimal effect on the ignition of an explosive atmosphere but does affect the air-vapor ratio, which is an important consideration. Low Temperature and Ozone Humidity and Low Pressure Humidity and Salt Spray Ozone effects are reduced at lower temperatures but ozone concentration increases with lower temperatures. Humidity increases the effects of low pressure, particularly in relation to electronic or electrical equipment. However, the actual effectiveness of this combination is determined primarily by the temperature. High humidity may dilute the salt concentration and could affect the corrosive action of the salt by increasing the coverage, thereby increasing the conductivity. Humidity and Fungus Humidity and Sand and Dust Humidity and Solar Radiation Humidity helps the growth of fungus and microorganisms but adds nothing to their effects. Sand and dust have a natural affinity for water and this combination increases deterioration. Humidity intensifies the deteriorating effects of solar radiation on organic materials. Humidity and Vibration Humidity and Shock and Acceleration Humidity and Explosive Atmosphere This combination tends to increase the rate of breakdown of electrical material. The periods of shock and acceleration are considered too short for these environments to be affected by humidity. Humidity has no effect on the ignition of an explosive atmosphere but a high humidity will reduce the pressure of an explosion. Humidity and Ozone Low Pressure and Salt Spray Low Pressure and Solar Radiation Ozone meets with moisture to form hydrogen peroxide, which has a greater deteriorating effect on plastics and elastomers than the additive effects of moisture and ozone. This combination is not expected to occur. This combination does not add to the overall effects. Low Pressure and Fungus This combination does not add to the overall effects. Low Pressure and Sand and Dust Low Pressure and Vibration Low Pressure and Shock or Acceleration This combination only occurs in extreme storms during which small dust particles are carried to high altitudes. This combination intensifies effects in all equipment categories but mostly with electronic and electrical equipment. These combinations only become important at the hyperenvironment levels, in combination with high temperature. Low Pressure and Explosive Atmosphere Salt Spray and Fungus Salt Spray and Dust At low pressures, an electrical discharge is easier to develop but the explosive atmosphere is harder to ignite. This is considered an incompatible combination. This will have the same effect as humidity and sand and dust. Salt Spray and Vibration Salt Spray and Shock or Acceleration Salt Spray and Explosive Atmosphere This will have the same combined effect as humidity and vibration. This combinations produce no added effects. This is considered an incompatible combination. Salt Spray and Ozone Solar Radiation and Fungus Solar Radiation and Sand and Dust This combination is similar to but more corrosive than humidity and ozone. Because of the resulting heat from solar radiation, this combination probably produces the same combined effect as high temperature and fungus. Further, the ultraviolet in unfiltered radiation is an effective fungicide. It is suspected that this combination will produce high temperatures. Solar Radiation and Ozone Fungus and Ozone Solar Radiation and Shock or Acceleration This combination increases the rate of oxidation of materials. Fungus is destroyed by ozone. These combinations produce no added effects. Solar Radiation and Vibration Sand and Dust and Vibration Under vibration conditions, solar radiation deteriorates plastics, elastomers, oils, etc., at a higher rate. Vibration might possibly increase the wearing effects of sand and dust. Shock and Vibration Vibration and Acceleration This combination produces no added effects. This combination produces increased effects when encountered with high temperatures and low pressure in the hyperenvironmental ranges. Solar Radiation and Explosive Atmosphere This combination produces no added effects. Environmental stresses affect parts in different ways. Table 3 illustrates the principal effects of typical environments on system parts and materials. High temperatures impose a severe stress on most electronic items, since it can cause catastrophic failure (such as melting of solder joints and burnout of solid-state devices). High temperature also causes progressive deterioration of reliability due primarily to chemical degradation effects. It is often stated that excessive temperature is the primary cause of poor reliability in electronic equipment. In electronic systems design, great emphasis is placed on small size and high part densities. This generally requires a cooling system to provide a path of low thermal resistance from heat-producing elements to an ultimate heat sink of reasonably low temperature. Solid-state parts are rated in terms of maximum junction temperatures. The thermal resistance is usually specified from this point to either case or to free air. Specification of the maximum ambient temperature for which a part is suitable generally is not a sufficient method for part selection, since the surface temperature of a particular part can be greatly influenced by heat radiation or heat conduction effects from nearby parts. These effects can lead to overheating, even though an ambient temperature rating appears not to be exceeded. It is preferable to specify thermal environment ratings such as equipment surface temperatures, thermal resistance paths associated with conduction, convection, and radiation effects, and cooling provisions such as air temperature, pressure, and velocity. In this manner, the true thermal state of the internal components of temperature-sensitive components can be determined. Reliability improvement techniques for high temperature stress include the use of heat dissipation devices, cooling systems, thermal insulation, and heat-withstanding materials. Low temperatures experienced by electronic equipment can cause reliability problems. These problems usually are associated with mechanical system elements. They include mechanical stresses produced by differences in the coefficients of expansion (contraction) of metallic and nonmetallic materials, embrittlement of nonmetallic components, mechanical forces caused by freezing of entrapped moisture, stiffening of liquid constituents, etc. Typical examples include cracking of seams, binding of mechanical linkages, and excessive viscosity of lubricants. Reliability improvement techniques for low temperature stress include the use of heating devices, thermal insulation, and cold-withstanding materials. Table 3: Environmental Effects Environment Principal Effects Typical Failures Induced High Temperature Thermal aging: Oxidation Structural change Chemical reaction Insulation failure; Alteration of electrical properties. Softening, melting, and sublimation Structural failure. Viscosity reduction/evaporation Loss of lubrication properties. Physical expansion Structural failure; increased mechanical stress; increased wear on moving parts. Low Temperature Increased viscosity and solidification Loss of lubrication properties. Ice formation Alteration of electrical properties. Embrittlement Loss of mechanical strength; cracking, failure. Physical contraction Structural failure; increased wear on moving parts. High relative humidity Moisture absorption Selling, rupture of container; Physical breakdown; Loss of electrical strength; Loss of mechanical strength; Interference with function; Loss of electrical properties; Increased conductivity of insulators. | Programs That Certified Usage: Space Electronic Rocket Test (SERT) I and II, Communication Technology Satellite (CTS), ACTS, Space Experiments, Launch Vehicles, Space Power Systems, and Space Station Freedom. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 02/18/2000
642 | Narvaez, P - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Narvaez, P - 0000000000 : NO@ADDRESS.GIVEN |  | "Non-Magnetic" Materials May Become Magnetized | Although stainless steel material is generally assumed to be non-magnetic, it is possible for a stainless steel propellant tank to become residually magnetized, either from “working” the material into its shape or from an external magnetic field. The associated dipole moment imparted roll torque to a commercial communications satellite, resulting in mission failure. Do not rely solely on the known magnetic properties of constituent material(s), and take steps to control residual magnetization of flight hardware. | A spacecraft component may possess a significant magnetic moment despite the non-magnetic characteristics of the constituent materials. In this case, the stainless steel tanks were magnetized either during fabrication or by subsequent magnetic exposure. Magnetic contamination is a mission critical risk on spacecraft with magnetic sensitive instrumentation or subjected to magnetic environments during flight. | When determining the magnetic properties of an end product by analysis, do not rely solely on the known magnetic properties of the constituent material(s). Consider factors that may have changed the original magnetic characteristics, including the fabrication method and the shape, length, and mass of the end item. Also, consider exposure to external fields that may magnetize materials during fabrication and handling. Steps to control residual magnetization of flight hardware may include: a) imposition of a limit on residual dipole moments (e.g., degauss to less than 5 A-m2), b) performance of magnetic testing on end items, c) implementation of controls to maintain a magnetically clean ambient ground environment, and d) monitoring of spacecraft field exposure with magnetic sensors attached to the spacecraft during handling and ground transportation. | JPL | 01/13/2000 | An unanticipated roll torque was imparted to a commercial communications satellite launched in 1989. This torque mandated excessive thruster corrections by the attitude control system until the propellant was prematurely exhausted, resulting in mission failure. Subsequent magnetic characterization tests performed on an engineering model of the large stainless steel propellant tanks revealed that the tanks could be easily magnetized during or after fabrication. The dipole moment of a magnetized tank would interact with the earth's magnetic field. This force would attempt to align the spacecraft with magnetic north, like a compass needle, producing the observed roll torque and requiring excessive attitude corrections by the thrusters. Testing showed that once magnetized, the tank would be capable of retaining a residual field that produces a dipole moment much greater than the 580 A-m2 required to produce the observed torque. The satellite's two stainless steel propellant tanks had been substituted for titanium tanks due to schedule deadlines. Since stainless steel material is generally assumed to be non-magnetic, no magnetic testing was performed. However, it is possible for the stainless steel sheet metal to become residually magnetized, with an associated moment, either by working it into the tanks' hemispheric shape or by exposure to an external magnetic field. As a corrective measure, this moment can be reduced significantly (to approximately 5 A-m2) after manufacturing by subjecting the tanks to a 40 Gauss alternating field and by monitoring subsequent exposure. Additional Keyword(s): Helmholtz coil, demagnetization, magnetic compatibility, attitude control, mission operations Reference(s): Magnetic Test Results of Engineering Model Propellant Tank, P. Narvaez, Jet Propulsion Laboratory IOM 5219-89-341, October 17, 1989. Roll Torque Anomaly Review Committee Findings, K. P. Bhat, August 21, 1989. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.1 ("Engineering Practices: Materials, Processes, and Contamination Control"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.10.1.2 ("System EMC/EMI Design"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 02/07/2000
641 | Rutledge, Pete - 0000000000 : NO@ADDRESS.GIVEN | Rutledge, Pete - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Climate Orbiter Mishap Investigation Board - Phase I Report |  | The MCO Mishap Investigation board (MIB) has determined that the root cause for the loss of the MCO spacecraft was the failure to use metric units in the coding of a ground software file, quotSmall Forces,quot used in trajectory models. Specifically, thruster performance data in English units instead of metric units was used in the software application code titled SM_FORCES (small forces). A file called Angular Momentum Desaturation (AMD) contained the output data from the SM_FORCES software. The data in the AMD file was required to be in metric units per existing software interface documentation, and the trajectory modelers assumed the data was provided in metric units per the requirements. During the 9-month journey from Earth to Mars, propulsion maneuvers were periodically performed to remove angular momentum buildup in the on-board reaction wheels (flywheels). These Angular Momentum Desaturation (AMD) events occurred 10-14 times more often than was expected by the operations navigation team. This was because the MCO solar array was asymmetrical relative to the spacecraft body as compared to Mars Global Surveyor (MGS) which had symmetrical solar arrays. This asymmetric effect significantly increased the Sun-induced (solar pressure-induced) momentum buildup on the spacecraft. The increased AMD events coupled with the fact that the angular momentum (impulse) data was in English, rather than metric, units, resulted in small errors being introduced in the trajectory estimate over the course of the 9-month journey. At the time of Mars insertion, the spacecraft trajectory was approximately 170 kilometers lower than planned. As a result, MCO either was destroyed in the atmosphere or re-entered heliocentric space after leaving Mars' atmosphere. The Board recognizes that mistakes occur on spacecraft projects. However, sufficient processes are usually in place on projects to catch these mistakes before they become critical to mission success. Unfortunately for MCO, the root cause was not caught by the processes in-place in the MCO project. A summary of the findings, contributing causes and MPL recommendations are listed below. These are described in more detail in the body of this report along with the MCO and MPL observations and recommendations. Root Cause: Failure to use metric units in the coding of a ground software file, quotSmall Forces,quot used in trajectory models Contributing Causes: Undetected mismodeling of spacecraft velocity changes Navigation Team unfamiliar with spacecraft Trajectory correction maneuver number 5 not performed System engineering process did not adequately address transition from development to operations Inadequate communications between project elements Inadequate operations Navigation Team staffing Inadequate training Verification and validation process did not adequately address ground software | Verify the consistent use of units throughout the MPL spacecraft design and operations Conduct software audit for specification compliance on all data transferred between JPL and Lockheed Martin Astronautics Verify Small Forces models used for MPL Compare prime MPL navigation projections with projections by alternate navigation methods Train Navigation Team in spacecraft design and operations Prepare for possibility of executing trajectory correction maneuver number 5 Establish MPL systems organization to concentrate on trajectory correction maneuver number 5 and entry, descent and landing operations Take steps to improve communications Augment Operations Team staff with experienced people to support entry, descent and landing Train entire MPL Team and encourage use of Incident, Surprise, Anomaly process Develop and execute systems verification matrix for all requirements Conduct independent reviews on all mission critical events Construct a fault tree analysis for remainder of MPL mission Assign overall Mission Manager Perform thermal analysis of thrusters feedline heaters and consider use of pre-conditioning pulses Reexamine propulsion subsystem operations during entry, descent, and landing | HQ | 11/30/1999 | The Mars Climate Orbiter (MCO) Mission objective was to orbit Mars as the first interplanetary weather satellite and provide a communications relay for the Mars Polar Lander (MPL) which is due to reach Mars in December 1999. The MCO was launched on December 11, 1998, and was lost sometime following the spacecraft's entry into Mars occultation during the Mars Orbit Insertion (MOI) maneuver. The spacecraft's carrier signal was last seen at approximately 09:04:52 UTC on Thursday, September 23, 1999. |  | N/A |  | Science | Public | Not Specified |  | 12/01/1999
638 | Smith, Claude - 0000000000 : NO@ADDRESS.GIVEN | Smith, Claude - 0000000000 : NO@ADDRESS.GIVEN |  | DC-XA Clipper Graham Mishap Investigation Board Report |  | Contributing causes of the mishap were as follows: Design of the system for gear stowage required technicians to break the integrity of the helium brake line after integrity had been already verified. No other check was conducted to reverify the integrity of the system after disconnection and reconnection of the line was completed. Landing gear stowage was never identified as a critical process. No special steps were taken to ensure the readiness of this system for flight. During the gear stowage process, there was no record of checking off steps or evidence of cross-checking of work by another person. Distraction or interruption of the mechanical technician during gear stowage operations may have contributed to the nonconnection of the brake line. The design of the DC-XA vehicle and operational procedures were driven by rapid development and low cost. Accordingly, a minimum number of personnel were involved in operations. Also, design was single string, and there was just one flight test vehicle. There was strong reliance on good people but not a lot of margin for human error afforded by the vehicle preparation process. Rapid Prototyping Guidelines or implementation thereof for the DC-XA may have gone too far in the direction of sacrificing quality and reliability. This rapid prototyping concept should be revisited from an operations perspective. | Critical procedural steps should be identified during systems design and flagged as critical in vehicle operations procedures. Then, independent verification of all critical steps should be performed during execution of operations procedures. NASA should perform a handover design review when any program is transferred from another agency. The quotrapid prototypingquot philosophy was cited as the rationale for employing minimal written procedures. The concept should be revisited from an operations perspective. Prelaunch processing documentation and data tapes should be kept as historical records for each flight at least until a mission is completed and degree of mission success is understood. Up-to-date hazardous materials information should be supplied to the appropriate hazardous response agencies at the start of any flight program in the future. | HQ | 07/29/1996 | On July 31, 1996, at 13:15 MDT, NASA successfully launched and flew the Clipper Graham, DC-XA, vehicle for the fourth time. Following an uneventful takeoff, the Clipper Graham flew for 104 seconds reaching an altitude of 4100 feet and traveling 2800 feet up range before returning to the concrete landing pad, successfully completing all test objectives. Ninety-eight seconds into the flight and at approximately 400 feet, the DC-XA computer commanded landing gear deployment. Over the next five seconds, three of the four legs successfully deployed. Four seconds after the gear deploy command, landing gears 1 and 4 deployed within one-tenth of a second of each other. Then, landing gear 3 deployed one full second later. Landing gear 2 never deployed. Descending from 400 feet, the spacecraft landed safely on three of its four legs. When the weight-on-gear indication was received at 13:17:27 MDT, the engines terminated as programmed and at 13:17:29 MDT, the vehicle toppled toward the position of landing gear 2. Upon impact, the vehicle was destroyed in a series of three explosions spaced over the next 90 seconds. The first explosion at 13:17:30 MDT ignited the composite shell and the avionics rack. At 13:17:40 MDT, ten seconds after the initial explosion, the fire suppression system began dispensing water. A second explosion of liquid oxygen from the aluminum-lithium tank rocked the mishap scene ten seconds after the first explosion. The fire suppression system shut down after the tank ran out of water but before complete fire extinction. Approximately 1 minute after the second explosion, the hydrogen tank exploded. This third explosion scattered the composite material from the aeroshell and hydrogen tank over the mishap scene. The Clipper Graham DC-XA vehicle was totally destroyed by ground impact and ensuing explosions and fires. The vehicle struck the ground on the corner of the vehicle at the undeployed landing gear 2. The upper two-thirds of the composite aeroshell, aluminum-lithium liquid oxygen tank, composite liquid hydrogen tank, composite intertank, avionics, nose cone, and parachute recovery systems were destroyed during the three explosions and ensuing fire. Parts of landing gears 3 and 4 were melted in the fire as well. Landing gears 2 and 1 mechanisms were damaged during the tip over and ensuing fires and explosions. The lower one-third of the vehicle aeroshell, containing the throttlable RL-10 engines and the auxiliary propulsion system, were charred and covered with soot. The RL-10 engines and auxiliary propulsion system were the only items appearing to be recoverable. Videotapes of the flight and still photographs of the wreckage showed that landing gear 2 failed to deploy. This failure was also evident in the helium supply pressure time history. NASA analysts at Kennedy Space Center (KSC) performed a helium pressure decay study and showed the loss of helium to be greater than expected after the start of gear deployment. Also, they estimated the diameter of the hole in the pneumatic system that would be required to achieve the observed helium pressure decay rate. This analysis indicated that if the brake line was disconnected during landing gear deployment, the decay rate would be equivalent to that which was recorded by the flight instrumentation. Also, post mishap inspection found the landing gear to be stowed and the pneumatic brake line not connected. Therefore, the primary cause of the vehicle mishap was that the brake line on the helium pneumatic system for landing gear 2 was not connected. This unconnected brake line prevented the brake mechanism from being pressurized to release the brake and resulted in landing gear 2 not extending. The vehicle became unstable upon landing, toppled onto its side, exploded, and burned. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 11/02/1999
639 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | DS1 Ion Engine Shut-Down Anomaly (1998) | Shortly after the successful demonstration of solar electric propulsion (SEP) aboard Deep Space 1 began, the xenon ion engine shut down unexpectedly-- likely due to a “grid short.” Although the engine was later restarted using other procedures, immediate use of a “grid clear circuit” was deemed as too risky. Since grid shorts are likely to occur during future missions that use SEP technology, conduct further study of grid clear circuits and provide a pre-planned operational procedure for detecting and clearing critical anomalies, including SEP grid shorts. | The quotgrid clearquot approach to recovery from a solar electric propulsion (SEP) grid short, a failure mode that is likely to occur during an extended mission, requires additional evaluation before it can be judged as an acceptable risk. | Provide a pre-planned operational procedure for detecting and clearing time-critical and mission-critical anomalies, including SEP grid shorts. Perform a study to determine how well grid clear circuits work. The study should identify the amount of current needed to clear grid shorts caused by various materials. Ensure that downlinked data on the operational condition of SEP systems include measurements of the current to the grids, and the voltage between them, to permit in-flight analysis of a possible grid short. | JPL | 10/13/1999 | The Deep Space 1 (DS1) mission successfully demonstrated the use of an ion engine as a primary spaceflight propulsion system. A few minutes after startup in November 1998, DS1's xenon ion engine shut down unexpectedly. The problem was believed to be a quotgrid short,quot a common problem in ion propulsion. Repeated attempts to restart the engine that same day were unsuccessful. Solar electric propulsion (SEP) imparts a small thrust by passing ions through two closely spaced, charged grids (Figure 1). Should a loose conductive flake bridge the gap between the positive and negative charged grids, it could short the grids leading to automatic shutdown of the engine. Molybdenum flakes commonly peel off the grids late in the ion engine's life. Given the early occurrence of the DS1 anomaly, however, it is possible that a conductive contaminant was introduced during assembly or launch operations. [D] DS1 Xenon Ion Engine Ion propulsion systems in commercial satellites incorporate a quotgrid clear circuit,quot like a patio bug zapper, that is believed to be capable of clearing grid shorts by producing a brief high current that eliminates the conductive source. DS1 was designed with a relatively low power version of this circuit. After the anomaly, DS1 operators executed preplanned low risk contingency evaluation procedures. It was decided not to take the risk associated with the immediate use of the quotgrid clear circuit.quot Approximately two weeks after the engine shutdown anomaly, an engine start planned for evaluation purposes resulted in successful engine operation. Activities during this two-week period are believed to have induced thermal cycling of the grids which removed the short. Since this early anomaly, engine operation has been normal. Additional Keyword(s): debris, contamination, fault protection, New Millennium, short circuit, NSTAR, Mission Operations | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph5.17.1 (quotManagement Practices: Risk Managementquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 11/02/1999
640 | Landano, M - 0000000000 : NO@ADDRESS.GIVEN; Ross, R - ; Oberhettinger, D - | Landano, M - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate Venting Analysis for the WIRE Spacecraft (1999) | Past analyses of electronic, mechanical, and optical hardware performance have sometimes focused on steady state characteristics to the exclusion of known transients. As indicated in the Wide-Field Infrared Explorer (WIRE) mission loss scenario, spacecraft venting configurations designed for steady state flow rates may experience large unexpected blow-down impulses, or even nominal cryogen flows sufficient to cause mission loss or degradation. Secondly, the inability of the WIRE spacecraft to counteract accelerated venting rates suggests a marginal attitude control system authority. Third, the unavailability of definitive cryostat temperature data during the anomalous venting period hampered early, real-time identification of the root problem (premature cover deployment). Consider all venting mission sequences, plus the possibility of unplanned worst-case venting scenarios, in the spacecraft system design. Design the thrust neutralizing capability of the attitude control system to encompass transient venting-induced torque. Ensure that the electronics monitoring spacecraft health supply data during critical operational sequences. | Past analyses of electronic, mechanical, and optical hardware performance have sometimes focused on steady state characteristics to the exclusion of known transients. As indicated in the WIRE scenario, spacecraft venting configurations designed for steady state flow rates may experience large unexpected blow-down impulses, or even nominal cryogen flows sufficient to cause mission loss or degradation. The inability of the WIRE spacecraft to counteract accelerated venting rates suggests a marginal attitude control system authority. The unavailability of definitive cryostat temperature data during the anomalous venting period hampered early, real-time identification of the root problem (premature cover deployment). | Consider all venting mission sequences, plus the possibility of unplanned worst-case venting scenarios, in the spacecraft system design. The thrust neutralizing capability of the attitude control system should be designed to encompass transient venting-induced torque. Ensure that the electronics monitoring spacecraft health supply data during critical operational sequences. | JPL | 10/20/1999 | Shortly after separation of the Wide-Field Infrared Explorer (WIRE) spacecraft from the launch vehicle, venting of the secondary cryogen tank was commanded, as planned, to dissipate the heat absorbed by the cryogen since termination of ground cooling. Venting this small amount of hydrogen gas was expected to induce some tumbling of the spacecraft. This tumbling was also expected to be quickly dampened by the attitude control system as the solid hydrogen reached equilibrium with the low space-ambient temperature. Instead, the spacecraft was observed to be tumbling too fast to be countered by the reaction wheels and magnetic torquers--an out-of-control condition. A NASA review board determined (reference 1) that an error in the design of the pyro electronics caused premature release of the telescope cover when the secondary cryogen tank was vented. The cover release permitted a large heat load into the cryostat that caused greater and more prolonged cryogen venting then expected following the transient associated with secondary vent actuation. A "T" fitting had been placed at the vent outlet to balance the thrust induced to the spacecraft by the gas flow expected from the planned venting sequence. However, design analysis did not consider the torque effects of worst case transient flows caused by one side of the "T" pointing directly at a connector (added as a late design modification during integration). The combined applied torque to the spacecraft from the initial secondary vent transient and the effects of early cover release was greater than the attitude control system capability. An independent analysis performed by a member of the WIRE JPL Review Board (reference 1, appendix E, p. 91) indicated the possibility that the normal secondary vent actuation transient could have exceeded attitude control capability. This could significantly impact early science return since it would take many days to reestablish a stable spacecraft attitude. Venting analyses performed during the design phase considered only the steady state cryogen flows expected during primary mission science pointing. However, the premature release of the instrument cover, and resultant boil-off of the cryogen required for telescope operation, was determined by the review board to be the direct cause of the WIRE mission loss (references 1 and 2). It was also determined that the design characteristics of the cryogen tank vent outlet prevented timely control of spacecraft attitude following the cover release anomaly, and the venting-induced torque deterred any productive efforts to save the mission. Additional Keyword(s): WIRE failure, thrust vector, thrust neutralizer, telemetry, angular velocity, roll rate, magnetic torquer, spacecraft spin, torque rod, impingement, subsystem and instrument development Reference(s): WIRE Mishap Investigation Board Report, NASA, June 8, 1999. Transient Performance of the WIRE Pyro Electronics, Lesson Learned No. 0634, August 12, 1999. | JPL has referenced the lesson as supporting Paragraph 4.9.4.2 ("System Fault Protection Design: Fault Detection - Deviation from Expected Behavior"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Science | Public | Not Specified |  | 11/02/1999
637 | Card, Michael - 0000000000 : NO@ADDRESS.GIVEN | Card, Michael - 0000000000 : NO@ADDRESS.GIVEN |  | Wide-Field Infrared Explorer (WIRE) Mishap Investigation Board |  | The WIRE Mishap Review Board has determined that the telescope instrument cover was ejected earlier than planned and at approximately the time the WIRE pyro electronics box was first powered on. The instrument's solid hydrogen cryogen supply started to sublimate faster than planned, causing the spacecraft to spin up to a rate of sixty revolutions per minute over the twelve hours following the opening of the secondary cryogen vent. Without any solid hydrogen remaining, the instrument could not perform its observations. The root cause of the WIRE mission loss is a digital logic design error in the instrument pyro electronics box. The transient performance of components was not adequately considered in the box design. The failure was caused by two distinct mechanisms that, either singly or in concert, result in inadvertent pyrotechnic device firing during the initial pyro electronics box power-up. The control logic design utilized a synchronous reset to force the logic into a safe state. However, the start-up time of the Vectron crystal clock oscillator was not taken into consideration, leaving the circuit in a non-deterministic state for a time sufficient for pyrotechnic actuation. Likewise, the startup characteristics of the Actel A1020 FPGA were not considered. These devices are not guaranteed to follow their quottruth tablequot until an internal charge pump quotstartsquot the part. These uncontrolled outputs were not blocked from the pyrotechnic devices' driver circuitry. There has been no evidence or indication of any component failure although component failures were considered in the investigation. A significant contributing cause of the anomaly was the failure to identify, understand, and correct the electronic design of the pyro electronics box. Design errors in the circuitry, which controlled pyro functions, were not identified. The pyro electronics box design was not peer reviewed, and other system reviews conducted by the instrument design organization did not focus on the electronics box. At the time the Systems Design Review was conducted for WIRE the design of the pyro electronics box was not completed. It is the assessment of the WIRE Mishap Investigation Board that a peer review held during the design process, by people with knowledge of and expertise regarding pyro circuit design would have identified the turn-on characteristics that led to failure. A large number of failure scenarios were evaluated during the investigation to determine the cause of the cover ejection. These included; pre-launch, launch, powered flight, separation, software, operations, design and component reliability faults. Based on comprehensive, systematic review of data, it was determined the cover was most likely ejected at the time the WIRE pyro electronics box was turned on due to a transient condition that exists in the pyro electronics during startup. This transient condition is the direct result of the non-deterministic initialization of a Field-Programmable Gate Array (FPGA) that controls both the arming and firing circuits in the pyro electronics. Although some design attention was given to the startup behavior of the FPGA, the design contained unidentified idiosyncrasies that triggered the cover ejection. The system design did not contain sufficient start-up lockout protection or independent provisions to prevent the FPGA startup operation from propagating to the firing circuits. The anomalous characteristics of the pyro electronics unit were not detected during subsystem or system functional testing due to the limited fidelity and detection capabilities of the electrical ground support equipment. Post-flight circuit analyses conducted as part of the failure investigation have predicted the existence of the anomaly and it has been reproduced confidently using engineering model hardware. | Independent, separate pyro inhibits should be considered for mission critical events, particularly if all pyro functions can be simultaneously armed and enabled. Hence, activitation of a pyro event would require two separate actions - one separate action to enable the inhibit and another to fire the pyros. This approach would preclude spurious transient pyro firings during turn-on and preclude sympathetic firings induced by sneak path and/or crosstalk/magnetic field interactions that may occur in cabling. Testing only for correct functional behavior should be augmented with a significant effort in testing for anomalous behavior, especially during intitial turn-on and power-on reset conditions. Peer reviews should be required by Project Management and held as often as necessary. Peer reviews should consider the heritage capability and limitations of the support equipment to be used for testing the flight design. Project review board members should consistently penetrate the system and subsystem functional design and implementation to expose risk areas, particularly where multiple/complex interfaces exist. Reviews should fully define spacecraft and payload interface requirements, and have a cognizant systems person from each program element review the other persons' test program and payload/spacecraft simulators for fidelity. System and subsystem engineers should consistently evaluate functional designs and implementation to expose risk areas, particularly where multiple/complex interfaces exist. Projects with multiple components, i.e. spacecraft bus and a separate instrument, require complete team coopoeration, openness, and the ability to penetrate and understand each other's design responsibilities in a timely manner. | HQ | 10/20/1998 | The Wide-Field Infrared Explorer Mission objective was to conduct a deep infrared, extra galactic science survey. The Wide-Field Infrared Explorer was launched on March 4, 1999, and was observed to be initially tumbling at a rate higher than expected during its initial pass over the Poker Flat, Alaska, ground station. After significant recovery efforts, WIRE was declared a loss on March 8, 1999. |  | N/A |  | Science | Public | Not Specified |  | 11/02/1999
635 | Nebrig, John - 0000000000 : NO@ADDRESS.GIVEN | Nebrig, John - 0000000000 : NO@ADDRESS.GIVEN |  | MSFC Building 4672 Pressure Reducing Statin Grayloc Clamp Removal |  | Work documentation (work orders and baseline drawings) should reflect the current system configuration. During the investigation, it was found that: The temporary configuration change to the gaseous hydrogen system was initiated on multiple work orders and by different individuals. There was no single document that documented the temporary system configuration. The procedure for performing the work was written using a drawing that had not been updated to show the actual system configuration. Verbal field direction was given when it was discovered the system was not configured per the work order. Incorrect Grayloc clamp removal techniques were used. Upon pressure release, the Grayloc clamp, blind hub, and seal ring became projectiles that had the potential to cause significant personnel injury. | Develop procedures for temporary change configuration control of high-pressure systems. The overall work process should be included in one work authorization document. Re-emphasis to all personnel that current procedures be followed. If the work order is not written to reflect the current system configuration, stop work, revise work order, and have the work order properly reviewed prior to continuing work. Write a procedure for proper Grayloc removal and installation and train technicians to the procedure. | MSFC | 08/17/1999 | On June 29, 1999, personnel were removing a Grayloc blind hub that had been used to temporarily isolate a portion of the gaseous hydrogen system. As a result of a sudden release of 2800 psig gaseous nitrogen, sand and debris kicked up from the concrete pad and caused minor injury to two technicians. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 09/29/1999
636 | Nebrig, John - 0000000000 : NO@ADDRESS.GIVEN | Nebrig, John - 0000000000 : NO@ADDRESS.GIVEN |  | Incorrectly Installed Fitting |  | Identification and installation of fittings requires detailed attention. During the investigation, it was found that the appearance of the 1/2" NPT female port was tapered. The NPT female port had a tapered/finished area on the port face very similar to an AN port face. Careful inspection of the fitting and port is required. | Retrain all technicians in the identification and installation of pressure fittings. Review the close call at the next safety meeting. | MSFC | 07/14/1999 | On 7/12/99, a mechanic was performing a verification leak test (using a 2900 psig gaseous nitrogen pressure source) of a 1/2" hand valve when an incorrect fitting blew out. The mechanic erroneously installed a 1/2" AN male fitting into the 1/2" NPT female port of the valve body. The fitting was attached to a high pressure flex hose when the failure occurred. This flex hose had Kellum restraints that prevented damage to equipment and injury to personnel. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 09/29/1999
634 | Landano, M - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - ; Herring, E - | Landano, M - 0000000000 : NO@ADDRESS.GIVEN |  | Transient Start-up Performance of the WIRE Pyro Electronics (1999) | Due to a transient effect, the Wide-Field Infrared Explorer (WIRE) telescope aperture cover was unintentionally ejected when the WIRE pyro electronics box was first powered. The cryogen subsequently vented, resulting in mission loss. Pyro electronics design, such as the use of pyro inhibits, must consider transient effects known to occur upon powering of the pyro electronics. Conduct detailed, independent technical peer reviews of the system design, and electronics power turn-on characterization tests that can detect anomalous behavior such as subtle transient events. | Pyro electronics design must appropriately consider transient effects known to occur upon powering of the pyro electronics. Pyro inhibits should be considered for mission critical events, particularly if all pyro functions can be simultaneously armed and enabled. Activation should require two separate and independent actions-one to override the inhibit (referred to as quotARMquot or quotSAFE/ENABLE-ENABLEquot), and another to fire the pyros. Detailed, independent technical peer reviews are essential to assess the integrity of the system design, including an evaluation of the system and mission consequences of the detailed design and implementation: Technical peer reviews for all design elements should be encouraged by project management. Peer reviews should consider the capability and limitations of the support equipment to be used for testing the flight design. Peer review board members should consistently penetrate the system and subsystem functional design and implementation to expose risk areas, particularly where multiple or complex interfaces exist. Ensure adequate fidelity of test and simulation equipment to detect subtle transient events where appropriate. Perform electronics power turn-on characterization tests, particularly for applications involving irreversible events, that include testing for anomalous behavior. Testing of power turn-off characteristics may also be important in some applications. | See lesson(s) learned. | JPL | 08/11/1999 | The Wide-Field Infrared Explorer (WIRE) was declared a loss only a few days after launch. A NASA review board (reference 1) determined that the telescope aperture cover was unintentionally ejected prior to spacecraft attitude stabilization when the WIRE pyro electronics box was first powered. Without the thermal protection provided by the cover, the solid hydrogen cryogen essential for operation of the telescope rapidly sublimated and vented. The mission loss is attributed to a pyro electronics box design that did not allow for the known transient performance of components. The control logic design utilized a synchronous reset to force the logic into a safe state. However, the start-up time of the crystal clock oscillator was not taken into consideration, leaving the circuit in a non-deterministic state for a time sufficient for pyrotechnic actuation. Likewise, the startup characteristics of the field-programmable gate arrays (FPGAs) were not considered. The FPGAs were not guaranteed to follow their quottruth tablequot until quotstartedquot by an internal charge pump. The electrical transients initially generated by the FPGAs were not blocked from the driver circuitry of the pyros. Prompted by the failure investigation, circuit analysis and test showed that the turn-on transients are sufficient to produce spurious signals that latch-up the control logic to a state that can issue commands to fire cover release pyros. These anomalous characteristics were not detected during subsystem or system functional testing due to the limited fidelity and detection capabilities of the electrical ground support equipment. There was no system-level end-to-end test in an as-flown configuration. [D] WIRE Pyro Electronics Startup Characteristics The design error was exacerbated by the failure of a detailed technical review to penetrate the electronic design of the pyro electronics box. Detailed peer review did not extend to the box and its interfaces with the spacecraft. The Mishap Investigation Board concluded that a peer review, held by knowledgeable people, would have identified the turn-on characteristics that led to the failure. Additional Keyword(s): WIRE failure, WIRE instrument electronics (WIE), cover deployment, pyrotechnic device, pyro arming, pyro firing, pyro circuit, qualification test, test equipment, spurious logic, transient analysis, inadvertent actuation, stray current, sneak circuit, SAFE/ENABLE-RESET, management and planning, system development, subsystem and instrument development, system integration and test Reference(s): WIRE Mishap Investigation Board Report, NASA, June 8, 1999. Informal Design Reviews Add Value to Formal Design Review Processes, Lesson Learned No. 0582, September 26, 1997. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.16 (quotManagement Practices: Reviewsquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.8.2 (quotFlight Electronics Hardware System Design: Hazard Controls - Visibility Into State of Safety Inhibitsquot), and Paragraph 4.3.4.3 (quotPower/Pyrotechnics Design: Pyrotechnic Function - Enabling of Pyrotechnic Functionsquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Science | Public | Not Specified |  | 08/26/1999
629 | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | Fan Screen/Filter Maintenance Considerations for Space Flight Applications |  | When designing airflow systems for use aboard the shuttle the following items should be considered for air inlet filters: The filters should be designed oversized so that they will still perform satisfactorily when 50% blocked. To expedite maintenance, the filter should be designed to be easily replaced or easily removed to facilitate cleaning. If the filter is not designed to be replaced, then it should be sized and designed to facilitate cleaning. Filters need to be sized large enough from a human factors standpoint to allow crew members to have (hand or finger) access. Filter cleaning should not be based on having the crew use duct tape to adhere to or remove attached debris. This is both inefficient and ineffective. | See lesson(s) learned. | ARC | 07/20/1999 | During the STS-90 flight, one of the experiment habitats located in the shuttle Middeck area experienced a mild over-temperature condition. Post-flight evaluations revealed that the habitat's air inlet filter was partially clogged restricting airflow into the cooling system. Human hair, lint, and miscellaneous debris clogged the filter. Further investigation revealed that many air filters in the Middeck area are similarly blocked and that most payload developers count on the crew to perform daily cleaning of these filters. In order to minimize the impact of the debris and to allow for proper airflow, several design considerations were identified. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 08/02/1999
632 | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | Designs for in-flight mating of sealing surfaces |  | In the microgravity environment it is difficult for crew members to mate and attach sealing surfaces together unless the attachment mechanism assists the crew in applying a load to hold the surfaces together. Designs that help in this attachment include: Screw thread lids, where the screw thread can be started before the seal starts to compress. Cam-lock devices, where the mechanism can be positioned and engaged and then the cam mechanism assists in applying a force to compress the seal. The use of clamps, where the clamp can be positioned and engaged and then a screw thread can be utilized to supply the force to compress the seal and hold the surfaces together. It should be noted that while screw threads are recommended to provide a mechanical advantage to help mate these surfaces, that friction alone (at the screw thread interface) should not be relied upon to hold the components together. | See lesson(s) learned. | ARC | 07/20/1999 | During the STS-90 flight, there was a repeated need to access the specimens contained within the Animal Enclosure Modules. The operation to gain access required the mating of equipment and covers that had seals (and sealing surfaces) designed to contain contaminants and particulates. The attachment mechanism to hold these mating surfaces together were simple quarter turn fasteners designed to simplify attachment. In flight, it was discovered that the crew had a difficult time pressing the mating components together (to compress the seals) and engaging the fasteners at the same time. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 08/02/1999
631 | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | Human Factors Design Consideration for Space Flight |  | Given the crucial role of the crew-hardware interface in accomplishing science objectives, specific attention must be paid to human factors and ergonomic principles. All hardware (even if previously qualified) must be subjected to a crew applied loads analysis or evaluation for the new application. Hardware to be used by the crew should be evaluated for the maximum load that the crew could apply, as opposed to loads applied in a nominal position. The front-end application of ergonomic principles into designs would maximize crew performance and minimize design rework. Design guidance can be found in: NASA-STD 3000 NASA-STD-50005 | See lesson(s) learned. | ARC | 07/20/1999 | During the STS-90 fight, a hold-down strap used to secure an experiment habitat during in-flight operations broke. While the strap used was identical to those used to secure crew members during sleep periods, the strap was not able to withstand the loads that the crew member could apply from a hunched/pulling position. The strap was never designed to hold the maximum loads that a crew member could apply. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 08/02/1999
630 | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | Space Flight Thermal Test Considerations |  | When performing ground based thermal testing of space flight hardware, care has to be taken to remove the effect of natural hot air convection. One of the most practical ways to accomplish this is to perform the thermal tests in an oven or thermal chamber where the overall environmental temperature can be raised to be the maximum temperature allowable. In this way, the effect (both heat load and performance) of the hardware being tested can be identified and evaluated. | See lesson(s) learned. | ARC | 07/20/1999 | When performing ground based functional testing of space flight hardware, it is difficult to perform accurate thermal testing. This is because natural hot air convection is present during ground based testing, and it is not a factor in the microgravity environment of space flight. There have been several instances where this factor has been forgotten and where the resultant thermal testing was not representative of the in-flight conditions. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 08/02/1999
633 | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | Need for functional performance testing |  | It is essential to perform functional verification testing of space flight hardware prior to final hardware acceptance. This testing should include: Test to ensure operational reliability for the full mission duration. Tests to characterize that the system will have acceptable performance under worst-case conditions. This can be a combination of conditions such as: highest temperature environment; highest power output, cooling filters partially blocked, cooling fan failure; etc. Tests to verify end-to-end compatibility that would include: physical and electrical interfaces; data signal compatibility; operational access; and crew interaction. Tests to verify compatibility with the microgravity environment on-board the KC-135. With limited microgravity periods, these tests cannot fully verify functional performance in a sustained microgravity environment, however, they can be used to demonstrate validity of concept and crew interface compatibility. | See lesson(s) learned. | ARC | 07/20/1999 | In support of obtaining flight certification for space flight experiment, there is a requirement and it is standard practice to perform both safety and verification testing. A similar requirement to provide functional performance testing does not exist. Functional performance testing is left to the discretion of project management or to the payload element developer. Ames Research Center has found that the performance of full functional performance testing helps to characterize hardware parameters, identify weak design and circumvent potential in-flight anomalies. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 08/02/1999
628 | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | Fan Screen Placement Considerations for Space Flight Applications |  | While it is important to have air filters on the air-inlet to space flight hardware (to facilitate cleaning), it is equally important to have a filter directly in front of any internal fan blades to protect the fans from debris (regardless of source) during in-flight operations. Not only will this protect the fans from debris caused by external sources, but it will allow the fans to remain operational if any of the internal components become loose (or float free) during the launch. | Place a filter directly in front of all fans used in space flight operations. | ARC | 07/20/1999 | During the STS-90 flight, two of the internal air circulation fans within the Research Animal Holding Facility (RAHF) failed to operate. To successfully complete the mission, an in-flight procedure was utilized to maintain the required air flow. Upon landing and recovery, an investigation was conducted to determine the cause of the failed fans. A small (approximately 6.0 X 0.5 X 0.1 inch) cloth/velcro strap was found to have been ingested into the RAHF air flow, and was eventually pinched between the fan blade and the rotor housing causing the fan to stop. The cloth strap came loose from another piece of stowage hardware and was apparently ingested into the RAHF through an opening while one of the removable rodent habitats was being removed or replaced. While the RAHF has an inlet filter over the main air inlet to the unit (that would have stopped this strap), it does not have a filter directly in front of the circulation fans that would catch any debris in the system, regardless of source. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 08/02/1999
627 | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN | Zimmer, Dave - 0000000000 : NO@ADDRESS.GIVEN |  | Criticality of Hardware Refurbishment Process |  | It was discovered that during the refurbishment process for the air pump, that a different material was utilized for an internal pump component that resulted in increased rotational friction and a failure to meet the specified operational life requirement. Insufficient detail and documentation was supplied for the refurbishment process. | When developing or evaluating a hardware refurbishment process, care must be taken to ensure that the refurbishment will comply with the specified basic design requirements for the part or component with regards to: Dimensional tolerances Material specifications and properties Assembly processes Acceptance testing | ARC | 07/20/1999 | Shortly after launch of STS-90, some of the motors/air-pumps associated with the aquatic habitats exhibited an increased power draw indicating either motor or pump failure. To successfully complete the mission, an in-flight procedure was utilized to cross-link each habitat to an operational air pump. Upon landing and recovery, an investigation was conducted of the failed motor/air-pump assemblies to determine why some units failed while others performed normally. The investigation determined that all of the units that operated properly were original equipment manufacture units, and the units that failed had all been refurbished. |  | N/A |  | Aeronautics Research, Science, Exploration Systems | Public | Not Specified |  | 08/02/1999
626 | Acord, A - 0000000000 : NO@ADDRESS.GIVEN | Acord, A - 0000000000 : NO@ADDRESS.GIVEN |  | Inadvertent Powering of the Deep Space 2 Mars Microprobe (1998) | During final assembly of the Deep Space 2 (DS2) Mars Microprobes, each of the two flight probes was inadvertently powered. The design of the mechanical switches was found to permit inadvertent ground paths during assembly, which could cause loss of mission due to undetected battery depletion prior to launch. System design must address hardware performance during assembly and test as well as during flight. Safing devices should be operational throughout assembly and test operations. Design analyses such as FMEA, SCA, and FTA must examine the electrical implications of mechanical/packaging design decisions. | Design analyses should include (a) Failure Modes and Effects Criticality Analysis (FMECA) and sneak circuit evaluation for potential electrical issues, and (b) Fault Tree Analysis (FTA) for potential mechanical issues. These analyses must be conducted in an integrated manner at the system level to ensure that the electrical implications of mechanical/packaging design decisions are understood. System design planning and processes must address hardware performance during assembly and test as well as during flight (the DS2 electronic switch design was almost impossible to assemble without an anomaly). Where the use of safing devices is required, the system design and assembly/test procedures must accommodate their use throughout assembly and test operations. | See lesson(s) learned. | JPL | 06/20/1999 | During final assembly of the Deep Space 2 (DS2) Mars Microprobes, each of the two flight probes was inadvertently powered. [D] When Mars 98 lander reaches Mars and the DS2 probes are released from the lander cruise ring, a MOSFET electronic switch will apply battery power to each probe. This switch, whose design heritage is unclear, is to be operated only once during the mission. Two mechanical switches are used to provide hold-off bias voltage to prevent the electronic switch from turning on until the probes are released. Both mechanical switches must be activated to power the probes, which then remain powered unless all system power is lost. Although a safing plug keeps the electronic switch biased to the off condition during early phases of assembly, the design required its removal well before the completion of electrical assembly. The overall system implementation included the following deficiencies and vulnerabilities that were not well understood and were not adequately accounted for in the system design, the Failure Modes and Effects Criticality Analysis (FMECA), and assembly planning: The electronic switch design permitted the probes to be powered if any of the wires connected to the mechanical switches were even partially connected to ground. An estimated resistance to ground of 1.5 megohm or less is sufficient to turn on the switch. The anomaly investigation determined that even the body resistance of the assemblers connecting the wires was sufficient to cause this very sensitive electronic switch to turn on. The design of the mechanical switches allowed an unintentional ground path to the probe aeroshell. This would inadvertently power the probes during assembly, causing loss of the DS2 mission due to an undetected battery depletion prior to launch. The design did not permit the safing plug to remain installed throughout electrical assembly. The electronic switch circuit design required external power while the batteries were being connected. Following completion of the anomaly investigation, design changes were made to electrically isolate the mechanical switches and retain the safing plug in place during electrical installation of these switches. Procedures were changed to require extreme care to avoid stray resistances due to handling following removal of the safing plug. Additional Keyword(s): Power Switch, Design for Testability, Design for Manufacturability, Inherited Design, Sneak Circuit Analysis (SCA), System Integration and Test, Hardware Fabrication and Test, Hardware Safety, System Development Reference(s): JPL Problem/Failure Report (PFR) No. Z48923, November 8, 1998. | JPL has referenced the lesson as supporting Paragraph 4.12.8.2 (quotFlight Electronics Hardware System Design: Hazard Controls - Visibility Into State of Safety Inhibitsquot), and Paragraph 4.9.2.1 (quotSystem Fault Protection Design: Fault Protection Response - Fault Protection Prioritiesquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 07/30/1999
623 | Ensign, Charles - 0000000000 : NO@ADDRESS.GIVEN | Ensign, Charles - 0000000000 : NO@ADDRESS.GIVEN |  | Tethered Satellite System De-integration Process Lesson Learned |  | Failure to maintain adequate configuration control for flight hardware hazardous items nearly resulted in personnel being exposed to live category B ordnance. | Configuration Control should clearly detail the status of all hazardous items for the entire de-integration process. An ISR has been submitted to change the Engineering Configuration List to include a field to identify hazardous items. This will encompass all flight hardware including hardware not scheduled for re-flight. | KSC | 06/02/1999 | The Tethered Satellite System (TSS) Satellite Support Assembly (SAA) was inadvertently scheduled for delivery to the Florida Space Institute prior to de-integration of live ordnance. The scheduled delivery resulted from a request for donation of the SAA following utilization of TSS on STS-75. During offload operations of the SAA at Cape Canaveral Air Force Station (CCAS), a technician recognized six NASA Standard Initiators (NSI's) still installed on the hardware. The NSI's were all examined and determined to be "live" category B ordnance with Faraday caps installed. Explosive Ordnance Disposal (EOD) personnel then removed the six devices for proper disposition. The remainder of the satellite equipment was subsequently closely examined to verify there were no other hazards. No personnel were exposed to the live NSI's. The event was classified as a "Close Call" and entered into the Incident Reporting Information System (IRIS) database for review and implementation of corrective action(s). The cause of this incident was determined to be inadequate configuration control of flight hardware during the de-integration process. This resulted in a loss of accountability for hazardous items integral to the design. This is a situation particular to flight hardware not scheduled for re-flight. Hardware scheduled for re-flight (unlike TSS) possess adequate configuration control of hazardous items. |  | N/A |  |  | Public | Not Specified |  | 06/07/1999
625 | Vanek, Charles - 0000000000 : NO@ADDRESS.GIVEN | Vanek, Charles - 0000000000 : NO@ADDRESS.GIVEN |  | Lewis Spacecraft Mission Failure Investigation Board |  | The Board found that the loss of the Lewis Spacecraft was the direct result of an implementation of a technically flawed Safe Mode in the Attitude Control System. This error was made fatal to the spacecraft by the reliance on that unproven Safe Mode by the on orbit operations team and by the failure to adequately monitor spacecraft health and safety during the critical initial mission phase. The Board also discovered numerous other factors that contributed to the environment that allowed the direct causes to occur. While the direct causes were the most visible reasons for the failure, the Board believes that the indirect causes were also very significant contributors. Many of these factors can be attributed to a lack of a mutual understanding between the contractor and the Government as to what is meant by Faster, Better, Cheaper. These indirect contributors are to be taken in the context of implementing a program in the Faster, Better, Cheaper mode: Requirement changes without adequate resource adjustment Cost and schedule pressures Program Office move Inadequate ground station availability for initial operations Frequent key personnel changes Inadequate engineering discipline Inadequate management discipline The Board strongly endorses the concept of "Faster, Better, Cheaper" in space programs and believes that this paradigm can be successfully implemented with sound engineering, and attentive, and effective management. However the role changes for Government and Industry are significant and must be acknowledged, planned for and maintained throughout the program.Since these roles are fundamental changes in how business is conducted, they must be recognized by all team members and behaviors adjusted at all levels. The Board observed an attempt during the early phase of the Lewis Program to work in a Faster, Better, Cheaper culture, but as the Program progressed the philosophy changed to business as usual with dedicated engineers working long hours using standard processes to meet a short schedule and skipping the typical Government oversight functions. | Based on observations from the Lewis Program, the Board offers the following recommendations in order to enhance mission success in future programs performed under this new paradigm: Balance Realistic Expectations of Faster, Better, Cheaper. Meaningful trade space must be provided along with clearly articulated priorities. Price realism at the outset is essential and any mid-program change must be implemented with adequate adjustments in cost and schedule. This is especially important in a program that has been implemented with minimal reserves. Establish Well Understood Roles and Responsibilities. The Government and the contractor must be clear on the mutual roles and responsibilities of all parties, including the level of reviews and what is required of each side and each participant in the Integrated Product Development Team. Adopt Formal Risk Management Practices. Faster, Better, Cheaper methods are inherently more risk prone and must have their risks actively managed. Disciplined technical risk management must be integrated into the program during planning and must include formal methods for identifying, monitoring and mitigating risks throughout the program. Individually small, but unmitigated risks on Lewis produced an unpredicted major effect in the aggregate. Formalize and Implement Independent Technical Reviews The internal Lewis reviews did not include an adequate action response and closure system and may have received inadequate attention from the contractor¹s functional organizations. The Government has the responsibility to ensure that competent and independent reviews are performed by the Government, the contractor, or both. Establish and Maintain Effective Communications A breakdown of communications and a lack of understanding contributed to wrong decisions being made on the Lewis program. For example the decision to operate the early on orbit mission with only a single shift ground control crew was not clearly communicated to senior TRW or NASA management. The Board believes that, especially in a "Faster, Better, Cheaper"program these working relationships are the key to successful program implementation. Although this report necessarily focused on what went wrong with the Lewis Program, much also went right due to the skill, hard work, and dedication of many people. In fact, these people completely designed, constructed, assembled, integrated and tested a very complex space system within the two-year goal and probably came very close to mission success. | GSFC | 02/11/1998 | The Lewis Spacecraft was procured by NASA via a 1994 contract with TRW, Inc., and launched on 23 August 1997. Contact with the spacecraft was subsequently lost on 26 August 1997. The spacecraft re-entered the atmosphere and was destroyed on 28 September 1997. The Lewis Spacecraft Mission Failure Investigation Board was established to gather and analyze information and determine the facts as to the actual or probable cause(s) of the Lewis Spacecraft Mission Failure. The Board was also tasked to review and assess the "Faster, Better, Cheaper" Lewis spacecraft acquisition and management processes used by both NASA and the contractor in order to determine if they may have contributed to the failure. The investigation process used by the Board was to individually interview all persons believed to have had a substantial involvement in the Lewis spacecraft acquisition, development, management, launch, operations and the events that may have led to the eventual loss. These interviews were aimed at not only understanding the facts as they occurred but also at understanding the individual perceptions that may have been instrumental in the decisions and judgments as made on this Program. |  | N/A |  | Science | Public | Not Specified |  | 06/04/1999
624 | Forgrave, J - 0000000000 : NO@ADDRESS.GIVEN; Farguson, C - ; Oberhettinger, D - | Forgrave, J - 0000000000 : NO@ADDRESS.GIVEN |  | Design, Test, and Inspection of Semi-Rigid RF Cables (1997) | The Sea Winds test program demonstrated that semi-rigid coaxial RF cable failures are difficult to avoid. Semi-rigid RF cable failures often cannot be detected by visual examination. During inspections following vibration test of the Sea Winds SES, hairline cracks were missed several times. Testing of protoflight models (PFMs) may permit only in-situ visual examination of components, while structural mass model (STM) tests typically allow cables to be removed from the unit for close examination. After a cable assembly passes environmental test, a second “identical” cable may fail due to minor differences in manufacture and installation. Consider using flexible cable. Where semi-rigid cabling is preferred, the lesson recommends standardization of cable receiving inspection, assembly, and installation. It also suggests several cable installation and test measures. | The Sea Winds test program demonstrated that semi-rigid coaxial RF cable failures are difficult to avoid. Consider using flexible cable. If the design decision is to use semi-rigid cabling, provide ample strain relief loops, structurally join the two cable mounting points so that the load path does not go through the cable, and ensure that the natural frequency of the cable does not match the resonant frequency of the support structure. Stress and fatigue analysis should be performed on the cables to establish margin. Semi-rigid RF cable failures often cannot be detected by visual examination. During inspections following vibration test of the Sea Winds SES, hairline cracks were missed several times. When inspecting semi-rigid cables after vibration testing, use a magnifying glass with very good lighting, and look very carefully for cracks. During thermal vacuum testing of semi-rigid cables, carefully monitor RF output signals for signs of signal drift that may indicate a cracked cable. Consider conducting several thermal cycles to increase the likelihood of crack detection. Testing of PFMs may permit only in-situ visual examination of components, while STM tests typically allow cables to be removed from the unit for close examination. Where funding and schedule permits, structures joined by semi-rigid cables should be tested in a developmental model, such as an STM, that facilitates cable removal and inspection. After a cable assembly passes environmental test, a second quotidenticalquot cable may fail due to minor differences in manufacture and installation. To the extent feasible, cable receiving inspection, assembly, and installation should be standardized so that test results on one cable are valid on subsequent articles. | See lesson(s) learned. | JPL | 06/02/1999 | The Scatterometer Electronics Subsystem (SES) for the Sea Winds spacecraft featured six semi-rigid coaxial radio frequency (RF) cables spanning two independent structures within the SES. After two cables failed during the initial SES vibration test, four additional cycles of redesign and test were required before the cables were judged acceptable. Two of the five tests were performed on SES protoflight models (PFM) and three on structural mass models (STM). Each of the six cables required varying degrees of redesign, including changes to cable material, strain relief, mounting configuration, and bonding, that impacted the Sea Winds schedule. [D] The process of cable redesign and retest is complicated by lack of repeatability. Minor uncontrolled variations in cable manufacture, routing, and mounting; JPL quotimprovementsquot in the cable configuration; and differences between the PFM and STM units, alter the dynamic characteristics of the test article. Furthermore, cracks in semi-rigid cables are very difficult to detect while they are installed. Cable failures may not be visually detected until the cables are removed from a test model, but they cannot easily be removed for inspection without damaging the cables and invalidating the vibration test results. If a cable failure was not detected and the SES was launched with a cracked cable, thermal transients could widen that crack, and the resulting signal attenuation could cause loss of science data. Additional Keyword(s): developmental model, coaxial cable, coax cable, waveguide Reference(s): JPL Problem/Failure Report No. SWD075 J. Forgrave and C. Farguson, quotConcerns Regarding Q-SCAT/Sea Winds SES Semi-Rigid Cable Qualification Status,quot JPL IOM 5052-98-045 of 3/1/98. C. Kuo, quotFatigue Analysis if SES's Coax Cables,quot JPL IOM 352G: 98:025/CPK of 5/11/98. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.8 (quotEngineering Practices: Project and System Level Functional Verification and Validation - Verification and Validationquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 8.3.7.1. (quotFlight System Verification and Validation Design: System Assembly, Integration and Test: System Environmental Verification - Environmental Exposure Fault Isolationquot), and Paragraph 9.3.2 (quotFlight System Flight Operations Design: Flight Hardware Maintenance - Thermal Cyclingquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 06/04/1999
622 | Acord, A - 0000000000 : NO@ADDRESS.GIVEN; Moore, W - ; Oberhettinger, D - | Acord, A - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Obsolescent Test Facilities Pose Risk to Hardware (1997) | Cassini: At the beginning of Assembly, Test, and Launch Operations (ATLO), vibration testing of the massive Cassini spacecraft was performed using facility test equipment that was barely up to the task. Powering an aged power amplifier for a shaker resulted in multiple failures of the test equipment, including board fires. Proactively perform periodic test facility maintenance and upgrade, and validate the current performance of the environmental test facility prior to use. | Test facilities may deteriorate between periods of use and may not be fully ready for the next major test program. Lack of full readiness may be especially risky when testing near the limit of the environmental equipment capability, or with resource-constrained projects that may lack the time and funding to correct deficiencies. | If NASA Centers are to maintain the capability to support environmental testing of multiple small missions, it is important that they proactively perform periodic test facility maintenance and upgrade. Moreover, provide procedures for validating and documenting current performance of the environmental test facility prior to use. It is always a good practice to verify environmental test equipment readiness and set-up with appropriate simulated hardware prior to flight hardware testing. This should be done early enough to avoid impacting project schedules. | JPL | 05/21/1999 | At the beginning of Cassini Assembly, Test, and Launch Operations (ATLO), the readiness and condition of the JPL Environmental Test Laboratory equipment was poorly understood. Vibration testing of the massive Cassini spacecraft was performed using facility test equipment that was barely up to the task. Proof mass vibration tests had to be aborted due to instrumentation problems. Since not all elements of the standard instrumentation suite were needed, various test instruments were uncoupled until the configuration provided a workable subset. The amplifier used to drive the shaker was approaching the end of its useful life during the Cassini proof mass vibration tests. The power amplifier includes 3000 power transistors on 10 circuit boards. Several days were spent getting the amplifier operational. Powering the amplifier resulted in multiple failures of the test equipment, including board fires. The resultant uncontrolled shutdown of the shaker would have posed a significant risk had the test been conducted on flight hardware. The Cassini project had to devote resources for repairing and upgrading the test facility so that the flight spacecraft could be tested. Additional Keyword(s): system safety, test instrumentation, dynamics test, acoustic test, test planning, test-induced failure, Management and Planning, System Integration and Test, Hardware Fabrication and Test Reference(s): Cassini Spacecraft Assembly, Test, and Launch Operations (ATLO) Final Report, Volume I, JPL Document D-15701, May 15, 1998, page 151. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.3 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 05/24/1999
620 | Jungewaelter, Jan - 0000000000 : NO@ADDRESS.GIVEN | Jungewaelter, Jan - 0000000000 : NO@ADDRESS.GIVEN |  | Indoor Freon 113 Spill |  | When accepting inherited systems, carefully consider the application and associated hazards of each part. Fluid release should always be considered a "credible hazard." Freon may be considered a relatively benign substance by personnel accustomed to handling much more toxic chemicals, but it can impose a great hazard in a closed environment, and/or in large quantities under high pressure. | Perform a risk analysis on Freon containment systems with special consideration given to the greatly increased cost of Freon loss since original installation. Ensure flexible systems are secured against pressure force differentials. Ensure personnel understand the scope of safety reviews and can recognize potential out-of-scope conditions. Ensure all tools are identified and included in safety reviews. | WSTF | 04/08/1999 | Upon closing a Shuttle AC Motor Valve during a cycling test, the pressure force differential across the valve deformed the Teflon interface a1dapter for a butt joint at the valve outlet port. The valve slipped free at the inlet port and approximately 160 gallons of Freon 113 was sprayed into the room at 250 psig and 56 gpm. Employees there immediately evacuated the room and suffered no ill effects. There was no equipment damage, but the Freon and productivity losses were costly. Flow benches and tooling for several components were supplied together by the original equipment manufacturer (OEM) to transfer repair operations of these components to WSTF. Safety reviews, subsequent modifications, and personnel training for the motor valve addressed only a valve using a slip joint upstream and a butt joint downstream to facility lines. No other configuration of this valve was known to the reviewers or specifically identified by the OEM to WSTF. An engineer new to the project received a valve with a smaller diameter outlet port for which the OEM had used the adapter to make the butt joint with the facility line. Because the adapter was already available among the tooling, the new project engineer believed it had been included in the system reviews, when it had not been. The OEM, in addition, had recently changed the material from which the adapter was made, from stainless steel to Teflon, to avoid scratching the valve, but transferred ownership prior to using the Teflon adapter and realizing its potential for failure. Losses and hazards were maximized because the supply valve to the Freon tank was inaccessible, being in the direction of spray, and there was no isolation valve on the supply tank. In addition, the emergency instructions did not explicitly address significant Freon leakage. |  | N/A |  |  | Public | Not Specified |  | 04/15/1999
619 | Margolies, Don - 0000000000 : NO@ADDRESS.GIVEN; Smith, Elizabeth - | Margolies, Don - 0000000000 : NO@ADDRESS.GIVEN |  | Management & Planning, Production/Fabrication/Development |  | The ACE project approach was to stick to design where "good is good enough" and not allow hardware changes just for the sake of "improvement". A reasonable schedule with key milestones was established with heavy emphasis on maintaining it. The ability to reallocate funds as needed was crucial to keeping the mission on target. The management arrangement was innovative and resulted in a 3-way nexus of centers, the GSFC for project management, the California Institute of Technology (CIT) for the payload development and the Johns Hopkins University JHU Applied Physics Laboratory (APL) for the spacecraft development. Each center had enough power and independence that aided in reaching solutions and working out difficult situations. Specific techniques used during the execution of ACE included: Maintain full and open communications with all project peers in up, down and sideways directions. Foster team approaches by being open, honest and frank in discussions with team members. Place heavy emphasis on schedule maintenance and design to cost. Delegate development responsibility in order to facilitate effective results and maximize resources. Provide adequate reserves to APL and CIT managers to use, as they deem appropriate. Define project/instrument descope options early in the program and develop a plan to implement them in a timely manner. Decide very early in the program to use the same core hardware and software system for Integration and Test (I&T), mission operations and the science data center to provide for greater efficiency, cost savings and better trained operations personnel. This has become the model for many subsequent missions. Establish a review board of technical experts, primarily in the payload area, who are not project staff. Retain the same people on the board for the duration of the development phase. This board worked in an open and trusting environment with the CIT Payload Management office, the Instrument Development Teams, APL and the GSFC Project Office. The board had a very significant impact on the ability of a number of ACE instruments to be successfully completed on time and within budget. Form the Flight Operations Team (FOT) early in the development phase so as to: Include FOT key personnel in the early phases of the spacecraft development in order to assist in the formulation of systems operations concepts and to influence the operations (and test) philosophy. Include FOT personnel in the I&T process (e.g., as test conductors) in order to help in procedure preparation and problem identification, receive the best kind of on the job training, and to be synergistic with the APL I&T team. This approach paid big dividends. Coordinate project reviews in conjunction with other NASA centers. Use a dual Chairman approach in the implementation of these reviews so as to reduce the total number of reviews needed. Always remember who the customer is. | See Lesson(s) Learned. | GSFC | 04/09/1999 | The primary objective of the Advanced Composition Explorer (ACE) Project was to determine and compare the elemental and isotopic composition of several distinct samples of matter, including the solar corona, the interplanetary medium, the local interstellar medium, and galactic matter. The Goddard Space Flight Center (GSFC) and the National Aeronautics and Space Administration (NASA) Headquarters Office of Space Science (OSS) undertook the ACE mission development including the execution phase. The GSFC agreed to launch ACE no later than December 1997 on a not-to-exceed cost basis. The end result was that the mission's actual cost was considerably less than the limit and the launch date was earlier than projected. |  | N/A |  |  | Public | Not Specified |  | 04/14/1999
618 | Kestel, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Kestel, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Ruptured Paint Drum Incident |  | Paint waste generators need to be aware of the potential for reaction between polyurethane and latex-based paint compounds. Precautionary warnings will be added to the technical instructions for paint waste streams. The routine practice of overpacking paint waste drums into salvage drums will be discontinued at KSC. This will facilitate detection of pressure buildup within drums. Salvage drums for paint wastes will be scrutinized to determine defects to the inside packaging. The new Waste Management Handbook, KHB 8800.7B, includes a requirement for generators to annotate salvage drums to alert personnel of bulging containers. Any salvage drums that contain bulging drums will be monitored for pressure. The use of gauges and/or relief valves on suspect drums is being examined. | See Lesson(s) Learned. | KSC | 05/13/1998 | A bulging 55-gallon drum of paint wastes from Cape Canaveral Air Station, which had been overpacked into an 85-gallon salvage drum, ruptured while in storage at an offsite hazardous waste storage facility in Emelle, Alabama. Pressure had built up inside the drum to the point where both the inside drum and recovery drum burst, propelling the drum 26 feet in the air, at which point it dented the roof and spilled hazardous waste into the containment area. The incident occurred late at night and no personnel were injured or exposed. Primary Cause: The waste stream contains a mixture of solvent-based paints and cleanup solvents. None of the vapor pressures of the waste components were great enough to cause failure of the drum. The pressure build-up was likely due to a chemical reaction producing a gaseous product. Polyurethane paint components of the waste stream contain isocyanate compounds, which react with water to produce carbon dioxide. Although there were no accounts of water-based paints being added to the drum, the generator also uses latex paints, and some may have been accidentally added to the drum. The drum was routinely opened and closed during waste accumulation allowing release of the pressure. It was only when the drum was sealed for storage that pressure increased to deform and eventually rupture the drum. Contributing Factors: The bulging condition of the drum was first noticed at the onsite CCAS hazardous waste storage facility. The drum was overpacked into an 85-gallon recovery drum to correct the container condition deficiency, but the facility operator was unaware that the drum was continuing to build pressure. The 85-gallon salvage drum then obscured the condition to the hazardous waste shipper, transporter, and offsite receiving facility. |  | N/A |  |  | Public | Not Specified |  | 04/12/1999
613 | Whitnah, Miles - 0000000000 : NO@ADDRESS.GIVEN | Whitnah, Miles - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Booster, Bonding Material Process |  | RSRM joint cleaning wipe was replaced with an aqueous-based solvent that was determined to be inappropriate for the expected joint interface surface temperatures. | Emulating the flight conditions, perform finite testing and analysis of any manufacturing, material and process changes. | HQ | 04/20/1997 | To meet environmental requirements, a program decision was made to change the Pressure Sensitive Adhesive used in the J-flap of the segment of the Shuttle Reusable Solid Rocket Motor (RSRM) and the solvent used in the joint cleaning process. A new Pressure Sensitive Adhesive was acquired and a solvent-based cleaning wipe was replaced with an aqueous-based joint cleaning process. Post flight analysis of the RSRM flight article revealed greater than expected erosion, sooting and heat effects on the insulation interfaces. |  | N/A |  |  | Public | Not Specified |  | 03/31/1999
615 | Whitnah, Miles - 0000000000 : NO@ADDRESS.GIVEN | Whitnah, Miles - 0000000000 : NO@ADDRESS.GIVEN |  | Shuttle Hatch Opening Anomaly |  | Post-flight inspection found that the hatch anomaly was traced to the hatch actuator internal mechanism. Per inspection, it was determined that one of the two screws fasteners for the clutch housing retainer had inadvertently backed out and was wedged between the first stage planetary gear and the ring gear. | Validate where specified self-locking inserts are required. In addition specify torque values. | HQ | 04/20/1997 | In preparation for a scheduled Extra Vehicular Activity (EVA) during STS-80, the crew discovered that they were unable to open the airlock outer hatch. |  | N/A |  |  | Public | Not Specified |  | 03/31/1999
614 | Whitnah, Miles - 0000000000 : NO@ADDRESS.GIVEN | Whitnah, Miles - 0000000000 : NO@ADDRESS.GIVEN |  | GSE Test Rig Installation |  | Hatch support GSE had been installed incorrectly (90 degrees from correct position). | Design and fabricate GSE support equipment so that it can be installed only in one way, with no options. | HQ | 04/20/1997 | While performing a functional retest of a Shuttle hatch movement, following a hatch actuator R&R, the GSE support structure failed. As a result, the hatch hinges and hinge arm mechanism were potentially subjected to the full unsupported weight of the hatch. |  | N/A |  |  | Public | Not Specified |  | 03/31/1999
617 | Raby, Lorraine - 0000000000 : NO@ADDRESS.GIVEN | Raby, Lorraine - 0000000000 : NO@ADDRESS.GIVEN |  | Test Stand 116 Liquid Oxygen Fire Mishap Investigation |  | The purpose of lessons learned is to provide a global overview of what value-added engineering design and testing practices can be obtained from studying this mishap. In addition, improvements in other processes are also pointed out. The lessons learned are not intended to be additional "recommendations," however, their application is certainly intended to be implemented as good engineering practice. The board, in most cases, related the lessons learned to their findings and recommendations where applicable, however, they did not feel constrained by them. The lessons learned are as follows: All components proposed for use in high pressure systems should have demonstrated functionally in an application and environments comparable to their intended use. If the above is not feasible, the component design drawing should be fully assessed or the system should be tested under appropriate conditions in an inert environment and disassembled and inspected prior to use in oxygen environments. Chairpersons of Design Reviews, ORIs, etc., should make sure that review documentation accurately reflects the hardware under review. Prospective suppliers should be required to provide historical data to verify their qualification to supply components for the specified environment and intended use. Performance Specifications for purchases of high pressure components must include requirements for demonstrated capability in the media and environment in which the component is to be used. Extreme caution should be exercised when a significant discrepancy exists between expected and actual test data. Testing should not proceed until the discrepancy has been explained to the satisfaction of appropriate discipline experts, and the test team deems it acceptable to proceed. | See Lesson(s) Learned. | MSFC | 12/18/1998 | At approximately 4 p.m. on June 7, 1996, a liquid oxygen fire occurred in the "A" Leg of the LOX feed system for the 750k lb. position of Test Stand 116 located in the East Test Area of MSFC. The fire occurred as the "A" Leg engine shutoff valve reached the "20T open" position while closing after completion of the fourth of a series of six planned set point tests. These test were being conducted to provide data for establishing the correct throttle valve setting for subsequent planned hot fire testing of a 650k lb. Thrust Chamber Assembly provided by Rocketdyne. At the time of ignition, the "A" Leg shutoff valve had closed far enough to permit it to take control of the LOX flow from the venturi. The LOX fire started in the seat region of the valve, progressed from the engine shutoff valve outlet to the test article within 120 ms, and burned for approximately 25 seconds. For the first 8 seconds, the fire was fed by high pressure LOX. The fire partially consumed the lower part of the engine shutoff valve body, the two elbows and straight pipe section that connected the engine shutoff valve and the test article. The test article, all instrumentation devices, hydraulic fluid lines, control wires and cables on the stand were destroyed. The hydraulic fluid fire primarily charred pipe insulation and coated the test stand and its equipment with soot. |  | N/A |  |  | Public | Not Specified |  | 03/29/1999
616 | Raby, Lorraine - 0000000000 : NO@ADDRESS.GIVEN; Pepper, Rhonda - | Raby, Lorraine - 0000000000 : NO@ADDRESS.GIVEN |  | Building 4777 Impeller Tip Failure |  | Don't anodize thin aluminum impeller blades. | See Lesson(s) Learned. | MSFC | 10/14/1998 | Water flow pump impeller blade tips failed during testing at MSFC's Inducer Test Loop (ITL). All three inducer tips were discovered missing during inspection of the pump. An investigation team determined that impeller tip failure was caused by degradation of aluminum impeller material (caused by anodizing and/or heat treat) and/or high impeller dynamic flow forces. |  | N/A |  |  | Public | Not Specified |  | 03/29/1999
612 | Slonski, J - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Slonski, J - 0000000000 : NO@ADDRESS.GIVEN |  | Fault Protection of Wax Thermal Actuator Applications (1998) | Eighteen days after launch of Deep Space 1, a spurious signal issued by the power distribution logic re-powered the primary heaters on the wax thermal actuators that had been used to release the DS1 solar arrays. The resulting short-circuit current could easily have damaged the power subsystem and jeopardized the mission. Power distribution circuitry should be designed to preclude inadvertent powering of wax thermal actuator heaters. Wax actuator circuitry should be designed to prevent a failure that leaves actuator heaters powered for an excessive period of time. | Wax thermal actuators have failure modes that can cause collateral damage. | Power distribution circuitry should be designed to preclude inadvertent powering of wax thermal actuator heaters. Wax thermal actuator drive circuitry should be designed to prevent a failure that leaves actuator heaters powered for an excessive period of time. | JPL | 03/03/1999 | [D] Wax thermal actuators are high reliability devices used to trigger spacecraft deployment mechanisms. Following launch, the Deep Space 1 (DS-1) solar arrays were released by powering the primary heaters in four high output paraffin (HOP) actuators. The HOP heaters were powered for three minutes and, as designed, the HOPs activated in 70-90 seconds after the heaters were powered. The secondary heaters in the HOPs were not powered. Eighteen days later, a spurious signal issued by the power distribution logic re-powered the primary HOP heaters. After ten minutes of heating, telemetry indicated a short in a HOP that caused the current to increase by approximately 6 amps. Over the next few minutes, all four primary heater circuits failed open, and evidence derived from telemetry indicated that at least three of the four primary heaters bridged to their corresponding secondary heaters. A trace rated for only 1.6 amps in the power distribution circuit board could easily have been damaged by the short-circuit current of 6 amps. Had this resulted in an open circuit in the power distribution board instead of the HOP, the mission could clearly have been jeopardized. Additional Keyword(s): Wax Actuator, HOP Actuator, Electrical Short, Pyro Reference(s): JPL Incident Surprise Anomaly (ISA) No. Z50426 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.8.4 (quotSafety and Mission Assurance Practices: Systems Safetyquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.3.4.4 (quotPower/Pyrotechnics Design: Pyrotechnic Function - Duration Limitingquot), and Paragraph 4.9.4.2 (quotSystem Fault Protection Design: Fault Detection - Deviation from Expected Behaviorquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/15/1999
610 | Powers, Charles - 0000000000 : NO@ADDRESS.GIVEN; Smith, Elizabeth - 0000000000 : NO@ADDRESS.GIVEN | Powers, Charles - 0000000000 : NO@ADDRESS.GIVEN |  | Long-Term Life Testing of Spacecraft Components |  | Accelerated life testing can lead to incorrect lifetime predictions if the failure modes are not understood. Instrumentation and high data rates during a life test can provide an understanding of component behavior and can lead to effective screening techniques. | Use accelerated life testing cautiously because failure modes can change between accelerated and operating conditions. If accelerated life testing is your only choice, make sure you understand the failure mechanisms of your component. Thoroughly characterize your components prior to life testing. You can conduct a meaningful life test with a small quantity of well characterized parts. Instrument as much as you can during a life test and use automation for monitoring a life test. Also, take lots of data during the life test. Perform a thorough post life test analysis of your components. | GSFC | 02/02/1999 | Since 1980, the Materials Engineering Branch has been involved in operational life testing of spacecraft components. These include encoder lamps and light emitting diodes, calibration lamps, signal amplifiers and support bearings for scanning mechanisms. Many of these life tests were initiated to demonstrate that life sensitive components would meet mission lifetime requirements. Several of the life tests were also used to determine the cause of in-flight failures of components. Besides demonstrating that a component would meet mission lifetime requirements, these life tests also determined useful lifetime and long-term behavior of components. In some cases, the behavior of a component at the beginning of life was used to develop screening techniques to select longer lived parts. Reference(s): 1009454main_0610.pdf by Chuck Powers, 10/21/98 (PDF File) |  | N/A |  |  | Public | Not Specified |  | 03/02/1999
611 | Baisley, R - 0000000000 : NO@ADDRESS.GIVEN; Shaw, L - ; Oberhettinger, D - | Baisley, R - 0000000000 : NO@ADDRESS.GIVEN |  | Evaluate Launch Vehicle and Services Requirements (1997) | Careful planning for the acquisition of launch services and interface definition and control is an important success factor for cost and schedule constrained flight projects. Tailor the launch services contract to meet project-specific needs, and consider other elements that historically accompany this type contract, prior to finalizing the agreement. Make minimal or no changes to the basic launch vehicle after the spacecraft interfaces with the launch vehicle have been established. | Determine the need for all elements that historically accompany a launch services contract prior to finalizing the agreement. Tailor the launch services contract to meet project-specific needs. Make minimal or no changes to the basic launch vehicle after the spacecraft interfaces with the launch vehicle have been established. Early analyses and identification of unique requirements may preclude significant cost growth. | See lesson(s) learned | JPL | 02/19/1999 | Careful planning for the acquisition of launch services and interface definition and control is an important success factor for cost and schedule constrained flight projects: Launch service contract stipulations are sometimes retained in a subsequent contract without adequate consideration of their suitability to the applicable flight project. "Unnecessary baggage" is a likely consequence of a rush to arrange flight services. In contracting for launch services, the Cassini project accepted the launch service contractor's standard arrangement. This contract retained launch service contractor responsibility for total launch vehicle/space vehicle (LV/SV) compatibility and performance. The level of contractor involvement with the spacecraft side of the interface, with an absence of clear decision making authority, was perceived to result in a duplication of effort, negatively influencing project morale. Independently, NASA subsequently directed JPL flight project offices to lead all efforts to ensure mission success. Once the launch services contract is finalized, changes that affect the hardware configuration will likely result in increased program costs. For example, Cassini launch safety analyses indicated the need for changes to LV/SV hardware and interfaces. Additional Keyword(s): Configuration Management, Configuration Control, Mechanical Interface, Control Drawing, MICD, Spacecraft Integration Reference(s): Cassini Spacecraft Assembly, Test, and Launch Operations (ATLO) Final Report, Volume I, JPL Document D-15701, May 15, 1998, pages 153-4. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.5.4 ("Launch Services"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/01/1999
609 | Moore, W - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Moore, W - 0000000000 : NO@ADDRESS.GIVEN |  | Develop and Test the Launch Procedure Early (1997) | During the terminal countdown for the first attempted launch of Cassini, spacecraft telemetry channels indicated a false alarm condition that delayed verification of spacecraft readiness for launch, and contributed to a delay on the first launch day. The anomaly was traced to erroneous telemetry documentation. Develop and release the launch procedure early enough for comprehensive testing prior to launch. Rigorously test and verify all telemetry channels and their alarms, and ensure documentation such as telemetry definitions is kept up to-date. | All spacecraft related launch operation procedures should be demonstrated multiple times prior to shipment. | Develop and release the launch procedure early enough for comprehensive testing prior to launch. Rigorously test and verify all telemetry channels, and their alarms, that will be used during launch and flight. Ensure documentation such as telemetry definitions is kept up-to-date. | JPL | 01/14/1999 | During the terminal countdown for the first attempted launch of Cassini, spacecraft telemetry channels indicated a false alarm condition that delayed verification of spacecraft readiness for launch, and contributed to a delay on the first launch day. In planning for Cassini launch activities, the RED-ALARM strategy was to set critical measurement alarms for telemetry values differing from those expected at liftoff. As expected, pre-launch conditioning generated a number of red alarms, most of which cleared as the spacecraft was brought to the final liftoff state. However, two red alarms did not clear, resulting in the false alarm conditions. This anomaly was traced to erroneous telemetry documentation: the SAFE/ARM logic states for the two channels whose alarms did not clear were found to be reversed in the data dictionary. The Cassini launch procedure was developed late in the Assemble, Test, and Launch Operations (ATLO) process, and alarm testing with correct parameters was not done. Also, testing of these particular alarms prior to actual launch was not possible at KSC due to safety considerations. The Mars Pathfinder (MPF) project developed their launch procedure early, and subjected it to rigorous, multiple tests during their 18-month ATLO. In this case, additional testing had negligible cost and schedule impact since it was conducted in conjunction with other testing to gain operating hours. Additional Keyword(s): Launch Readiness Review, Operations Readiness Review, Configuration Management, Interface Control Reference(s): Cassini Spacecraft Assembly, Test, and Launch Operations (ATLO) Final Report, Volume I, JPL Document D-15701, May 15, 1998, page 151. JPL Problem/Failure Report No. Z44319, October 13, 1997. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.2 ("Engineering Practices: Telecommunication Design"), Paragraphs 6.14.2.3 and 6.14.2.4 ("Engineering Practices: Project and System Level Functional Verification and Validation - Verification and Validation"), Paragraph 6.18.6 ("Engineering Practices: Mission Operations System Development"), and Paragraph 6.3.4 ("Engineering Practices: Mission Operations - Spacecraft Health and Safety, and Performance Analysis"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 01/27/1999
608 | Wirth, J - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Wirth, J - 0000000000 : NO@ADDRESS.GIVEN |  | Consider Language Differences When Conveying Requirements to Foreign Partners (1997) | When communications are phrased ambiguously, foreign partners who use English as a second language may misinterpret requirements. In the case of the Huygens probe, a requirement specifying the memory location of probe science data confused the European Space Agency. The use of a diagram would have helped. Hence, when working with foreign partners, document requirements in terms that describe the intent very clearly. | It is especially important when working with foreign partners to document requirements in terms that describe the intent very clearly; include graphics where possible. | See lesson(s) learned. | JPL | 01/20/1999 | The Huygens probe was the European Space Agency's (ESA's) contribution to the joint NASA/ESA Cassini/Huygens mission, and it represented the first medium-sized mission of ESA's long-term space science program. This venture required a high degree of collaboration between NASA and ESA's industrial partners in 14 European countries where 10 different languages are spoken. [D] ESA Industrial Partners for the Huygens Probe Control of subsystem interfaces always requires effective interaction between engineers. The complexity of the Cassini/Huygens interfaces increased the need for clear and unambiguous communication. Since most Europeans use English as a second language, requirements that are clear to JPL engineers may be misinterpreted by foreign partners. When the wording is vague, a requirement or specification may be interpreted many ways. For example, a requirement called for two copies of probe science data to be stored in each of two memory partitions on the dual solid state recorders. Read correctly, this requirement called for a total of eight storage locations, but the lack of a diagram illustrating these assignments confused ESA. Additional Keyword(s): Interpretation, Interface Control, Configuration Management, Joint Venture, International Partners Reference(s): Cassini Spacecraft Assembly, Test, and Launch Operations (ATLO) Final Report, Volume I, JPL Document D-15701, May 15, 1998, page 155. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.4.6 (quotManagement Practices: Project Organization, Roles and Responsibilities, Internal Communications, and Decision-Makingquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 01/26/1999
621 | Combes, Larry - 0000000000 : NO@ADDRESS.GIVEN | Combes, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Post Mission Hardware Drop Incident (1998) | CHeX: In 1998 the CHeX space flight hardware was damaged due to a drop caused by failure of the lift fixture during transfer of the cryoprobe to a support structure. CHeX: Implement positive means of assuring lift fixtures are assembled in the same configuration as proof-tested. Assure operators and supervisors are trained to perform critical lifts. | The same care that is provided during pre-flight operations should be given to flight hardware after completion of its mission. Assure that lift fixture design and lift procedures are fail-safe. Implement positive means (tagging and tethering) of assuring lift fixtures are assembled in the same configuration as proof-tested. Assure operators and supervisors are trained to perform critical lifts, including pre-operational inspections. Implement the buddy system, or provide adequate supervision, while handling critical hardware. | See lesson(s) learned | JPL | 01/01/1999 | The CHeX space flight hardware was damaged at a collaborating university during disassembly and testing after completion of the mission. The cryoprobe, a high value component of the experiment hardware, was dropped approximately 18 inches onto a concrete floor causing significant repairable damage. The drop was caused by failure of the lift fixture during transfer of the cryoprobe to a support structure. Review of the mishap revealed that the lift fixture design was structurally adequate, with load carrying capability of the vertical axis dependent on a double lock-nut system. Prior to the operation, the unassisted lift fixture operator did not detect that the lock nut was missing and that the remaining nut was close to disengagement. This nut did disengage, allowing the flight hardware to drop. The fixture design and test planning were not robust enough to reasonably preclude flight hardware damage. Contributing to the mishap was a failure to follow NASA critical lift procedures for flight hardware, including: Inadequate fail-safe design of the lift fixture. Improper assembly of the lift fixture. Inadequate pre-operation inspection of the lift fixture. Inadequate supervision of the operator. Additional Keyword(s): Human Factors, Crane, Hoist Reference(s): CHeX Hardware Failure Review, 7941:TL-98-007:tl NSS/GO-1740.9B, NASA Safety Standard for Lifting Devices and Equipment, Nov. 1991 LLIS Number 0267 (JPL #11-115), TOPEX/POSEIDON Near-Drop Incident LLIS Number 0273 (JPL #11-113), Solar Array Drive (SAD) Drop | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 01/01/1999
607 | Clark, K - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Clark, K - 0000000000 : NO@ADDRESS.GIVEN |  | Handling and Storage of Flight Spares | White spots, identified as “mealing,” were observed on 10 spare Mars Observer circuit boards, withdrawn from long term storage for use on Mars Global Surveyor. Although the cause of the defects was not established, the handling and warehousing of these flight spares may not have been consistent with their status as potential flight hardware for future projects. Treat flight spares as though they are going to be flown. | The care given to the handling and warehousing of flight spares is not always consistent with their status as potential flight hardware for future projects. | Treat flight spares as though they are going to be flown. Storage of any duration should be maintained under a controlled environment; especially low humidity (typically 30 to 50 percent) and room temperature or less. | JPL | 12/09/1998 | White spots were observed on ten, conformally coated, electrical power subsystem (EPS) printed wiring assemblies. The anomaly was noted when the boards, built as Mars Observer (MO) spares, were withdrawn from long term storage for use as Mars Global Surveyor (MGS) flight hardware. [D] Mealing of MO Spares The spots were identified as quotmealing,quot which involves significant levels of ionic contaminants concentrated primarily at the interface between the conformal coating and the substrate material. Exposure to warm, damp conditions is known to promote the growth of mealing. This growth can cause electrically conductive paths along interfacial surfaces, or between components and traces. Speculated contributors to the problem are: The ionic contaminants may have been imbedded during board manufacture, or at some later time such as during cleaning prior to conformal coating. Moisture normally present within the fiberglass board substrate might also migrate to the interface. Exposure to excess humidity during the 3 years the coated boards were warehoused may have caused atmospheric water vapor to permeate the conformal coating and reach the interface, or prevent dissipation of the moisture from within the board. The ten boards were reworked to remove mealing and eliminate potential electrical anomalies. Narrow strips of conformal coating were removed from critical areas followed by cleaning of the exposed board laminate and touch-up of the conformal coating. Additional Keyword(s): Contamination, Corrosion, Inherited Hardware Reference(s): MGS Problem/Failure Report (PFR) No. Z20617 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraphs 6.12.2 and 6.12.5.5 (quotEngineering Practices: Protection and Security of Flight Hardwarequot), and Paragraph 6.13.1.1 (quotEngineering Practices: Design and Verification for Environmental Compatibilityquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/14/1998
606 | Jungewaelter, Jan - 0000000000 : NO@ADDRESS.GIVEN | Jungewaelter, Jan - 0000000000 : NO@ADDRESS.GIVEN |  | High Pressure Steam Strainer Failure |  | Careful consideration of the effects of failure must be made before using cast iron parts in steam systems. Employees should be trained and prepared to recognize symptoms of unique hazards. If conditions like water hammer are significant operational concerns, procedures and personnel training should specifically address how to recognize (look/listen for) the warning signs. In contracting, be careful of "slimming down" technical specifications for performance-based results. | Assess the use of materials in steam systems to ensure that they are not subjected to stresses in excess of the allowable. Ensure that the effects of catastrophic failure due to non-ductile materials, like cast iron, are considered. Ensure performance-based specifications are sufficiently detailed to address all allowable stresses, including operating conditions. Identify potential hazards associated with material substitution. Ensure employees can recognize warning signs of hazards unique to a system. | WSTF | 12/10/1998 | A four inch-diameter cast iron strainer in a 225 psig steam line failed catastrophically, releasing high pressure steam and hurling strainer pieces and attached parts in the equipment building. The steam and projectiles weighing up to 50 lbs. posed life-threatening hazards; however, they caused only minor damage to the steam piping and surrounding equipment. Two employees opening a steam supply valve nearby were not injured. The failure was caused largely by the inappropriate use of material for the strainer. The strainer was manufactured from gray cast iron to ASTM Specification A 126 Class B. A stress analysis was performed by the A&E contractor assuming cast steel construction. The principle stress at the strainer position would not exceed the maximum allowable stress for steel but would for cast iron, as specified in ASME B31.1 (1995 edition). Repeated water hammer effects during operations hastened eventual strainer failure. Upon acceptance of the strainer, material criticality associated with analysis was not recognized as a determining factor in component acceptability. Operating and performance parameters (pressure and temperature) were the principle considerations. Also, the hazard analysis did not address steam line rupture resulting from steam flashing or water hammer. It is common within NASA and industry to dismiss catastrophic failure potential of ASME code-compliant pressure systems as non-credible, given intrinsic safety factors. Procedural problems combined with some malfunctioning steam traps caused the part to be subjected to significant water hammer during system startup. Employees were not instructed explicitly in how to recognize water hammer symptoms. |  | N/A |  |  | Public | Not Specified |  | 12/10/1998
605 | McCalman, Mark - 0000000000 : NO@ADDRESS.GIVEN | McCalman, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | LOX Barge Pumping Operations; Retaining Screw and Wear Ring |  | Adequate LOX pump hardware and operations procedures, safeguards and baseline data must be in place to assure that all risks to people, facilities, equipment, or missions are identified and mitigated. Manufacturer's recommended procedures should be integrated into SSC procedures when possible. | Ensure that procedures associated with the LOX barge operations include the following: Use wear rings for one time use only. (Present method of staking screws prevents proper installation of the retaining screws if a previous stake mark(s) exists.) Develop a "standard recommended time" during which the pump is allowed to cavitate without turning off the motor, Prohibit personnel access on the barge while any LOX pump is running, A briefing to include the potential hazards and site-wide experience with this operation for all involved personnel. Inspect all LOX barge pumps to verify that the retaining screws on the wear rings are properly installed and staked. Replace multiple use wear rings and ensure that the cases have proper bolt hole configurations. Develop a vibration baseline and analysis for the LOX barge pump motors and LOX barge pumps while coupled to the motor. Investigate and implement improvements on retaining screw design that positively holds the screws to the wear ring. Consider the following: Improve surface finish of inside surface of the aluminum housing to at least a 125 rms for smooth flow of LOX. Repair existing deficient discrepancy holes on the pump housings that do not meet specifications. Improved pump-to-motor coupling. Issue a GIDEP Parts Advisory on the potential of additional counterbore mounting holes on pump casings. | SSC | 11/16/1998 | During LOX transfer operations in preparation for a Space Shuttle Main Engine (SSME) test (904-362) on the B-1 test stand, a LOX pump (barge #1, pump B) over pressurized, initiating a fire on barge #1. The fire was extinguished and mishap investigation procedures were initiated. The primary cause (determined by the board) was the backing out of a retaining screw during LOX pump B operations. Further investigation highlighted the following: SSC's procurement (post 1988) of pump casings with configurations that were not per design (beveled area around retaining screw area), and Wear rings for the pump are re-used after pump rebuild if no evidence impeller to wear ring wear exists. The incident caused no injuries; however, damage to equipment including the barge, motors, lines, and decking is estimated at approximately $250,000. In addition, the pending SSME test was cancelled and rescheduled. |  | N/A |  |  | Public | Not Specified |  | 12/10/1998
604 | Montague, Ronald - 0000000000 : NO@ADDRESS.GIVEN | Montague, Ronald - 0000000000 : NO@ADDRESS.GIVEN |  | Microchip Susceptibility to Ionizing Radiation Emitted by Environment, Materials Used in Production and Processing of Computer Hardware |  | Some microchip technology is getting more and more miniaturized, making previously used ionizing radiation controls obsolete. In contrast, some experts indicate that true nanotechnology processors are not as susceptible. | Ensure that materials used in processing and manufacture of microchips do not emit ionizing radiation which may damage the microchips during manufacture or test of microchips or electronic systems. Known examples of such materials are lead solder, silica molds, and phosphoric acid used for etching. The materials may be used actively like solvents) or passively (like molds). Materials may be used in direct manufacture, test, maintenance, etc. Parts used in the manufacture of electronic systems utilizing microchip technology must also be scrutinized as potential radiation sources which may damage microchips. Where microchips will be susceptible to environmental radiation, ensure that design trade studies consider trade-offs such as additional weight from additional shielding, additional cost of radiation hardening of commercially available microchips, etc. | JSC | 11/11/1998 | The following was originally published by New Scientist magazine and picked up by Reuters. Two different JSC engineers have indicated that these radiation issues can cause concerns for NASA systems. The article is quoted verbatim. (from New Scientist/Reuters) Microchips are growing smaller, but their diminishing size exacts a price. Tiny circuits are vulnerable to radioactive interference that could cause a simple blip in your cell phone or a far more serious kind of crash, New Scientist magazine reported Saturday. When chips are miniaturized, they require less electrical charge to store each bit of information. Those decreased voltages also mean that the chips are less prepared to cope with low-level ambient radiation. "Unfortunately, the price we pay for smaller chips is as each chip has less voltage to work with and less charge, it can be more sensitive to some of these soft error events," said Robert Bauman, manager for embedded memory and analog reliability at Texas Instruments. Radioactive interference can come from neutrons in the atmosphere or from the materials used in building the computer equipment, such as lead solder, silica molds, and the phosphoric acid used for etching. Those materials all emit radioactive alpha particles. "There is no simple solution to these things, we need to work with the materials-technology people to insure that the equipment contains fewer radioactive impurities," said Chand Viswanathan, professor of electrical engineering with the School of Engineering & Applied Science at the University of California at Los Angeles. Most PCs now use microchips with transistors between 330 and 250 nanometers across. The next generation of microprocessors should shrink to below 180 nanometers, making them more susceptible to interference. A nanometer is one-billionth of a meter, roughly one-hundredth the width of a human hair or the size of one bacterial cell. Aircraft systems could face the worst problems of all, because the risk of interference goes up with the altitude. "When you are flying five or six miles up, you're subject to more cosmic radiation effects," Viswanathan said. Texas Instruments has been working on the problem for almost a decade. "When you're doing your system design, whether it's memory or high performance DSP, it's important to have this radioactivity problem in mind as you're designing it. None of these problems are insurmountable," Bauman said. "There's always a solution. The question is, what's the cost of solving it, and what's the cost if you don't solve the problem?" Bauman said. "The risk depends on the applications and the acceptable error rate-you have to factor that in. The best case is to design the system so there's no error." One solution would shield the equipment from potential radiation, but that could prove impractical since some shields would have to be 10 feet thick. Equipment could also be placed in a basement, Bauman suggested. Another solution might be for designers to harden the chips against the effects of radiation, Viswanathan said. "The bottom line is, because it entails knowing nuclear physics, engineering, and so many varied disciplines, it's not obvious to most people that it's a problem," Bauman said. (from NanoSpace 98) Scaled Silicon MOS is not nanotechnology. In contrast, recent measurement by the Naval Research Laboratory and Texas A&M show that nanosized quantum devices (Nanoelectronics) are extremely radiation tolerant and have the potential to lower power and increase speed in advanced signal processing and storage space systems. This was briefed at the NanoSpace 98 conference last week. For details on the nanosized quantum devices, contact Steven Watson of SAIC at (281) 244-1747 or Gary Frazier of Raytheon Systems at (972) 344-3634. |  | N/A |  |  | Public | Not Specified |  | 11/16/1998
603 | Stell, C - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Stell, C - 0000000000 : NO@ADDRESS.GIVEN |  | DC-DC Converter Applications (1995) | Several JPL flight projects obtained low cost, commercial quality, hybrid DC-DC power converters from a single vendor that proved unsuitable in some intended applications. Hybrid power supplies are complicated and difficult to analyze. Worst Case Analysis (WCA) techniques, if applied to just the hybrid, may not be sufficient to identify application sensitivities to external interfaces, and/or to identify non-linear interactions that may occur within the hybrid. | Hybrid power supplies are complicated and difficult to analyze. Worst Case Analysis (WCA) techniques, if applied to just the hybrid, may not be sufficient to identify application sensitivities to external interfaces, and/or to identify non-linear interactions that may occur within the hybrid. | The following activities are recommended to verify the suitability of a hybrid power supply application: Involve a power supply engineer in the selection, application, analysis, and test of hybrid power supplies. Conduct worst case analysis on all hybrid power supply applications including internal and external circuitry. Utilize the supplier's specification limits, the user's environment (line, filter, load, temperature, radiation, life) with appropriate margin, and the internal part manufacturer's tolerances. Retain the results of WCA computer modeling for analysis of future applications. Conduct parts stress analysis (PSA) assuming worst case conditions. This permits future users of the power supply to merely update the analysis if warranted by changes in the converter design or changes in worst case conditions. Conduct thermal analysis, including minimum heat sink bond area. Assume worst case conditions and document the results for future updates as needed. Thoroughly test power supplies considering: Output voltage regulation Efficiency Standby power consumption Output voltage ripple Output voltage turn-on overshoot Input voltage variation Input inrush current Load current transient response Load current transient cross regulation Input common mode current Differential input current | JPL | 10/22/1998 | Several JPL flight projects obtained low cost, commercial quality, hybrid DC-DC power converters from a single vendor which proved unsuitable in some intended applications. The sensitivity of this family of converters to load, ground, and input/output power conditions was not evident in the vendor documentation. Specific DC-DC power converter design limitations involved several different failure mechanisms including: Use of a sync circuit external to the converter frequently coupled noise into the internal pulse width modulator (PWM), keeping the power FET (field effect transistor) saturated, which led to its eventual failure. [Reference (1)] Imbedded electromagnetic interference (EMI) filters in most of these converter designs lacked a damping resistor; the resulting instability kept the FET saturated until it failed. [Reference (2)] The startup capabilities of these converters were insufficient for the Mars Pathfinder (MPF) mission worst case cold temperature. Slow input voltage rise time resulted in failure of the converter to turn on due to PWM regulator latch-up. A JPL tiger team was able to resolve these problems through external and/or internal design changes with significant schedule and budget impact. Also see Reference (3) for related vendor issues. Additional Keyword(s): Parts Procurement Reference(s): JPL Problem/Failure Analysis Reports (PFARs) No. 6419, 6978, and 6950 GSFC Failure Analysis Report (FAR) No. FA78126 "Commercial Electronic Parts Supplier Evaluation," JPL Lesson Learned No. 9-121. C. B. Stell, "Off the Shelf Power Converter Unit Electrical Performance Evaluation, Jet Propulsion Laboratory, February 2, 1998. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5.8 ("Safety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisition"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.3.3.2 ("Power/Pyrotechnics Design: Power Generation - Power Demands"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/28/1998
602 | James, S - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | James, S - 0000000000 : NO@ADDRESS.GIVEN |  | Commercial Electronic Parts Supplier Evaluation (1995) | The Mars Pathfinder project experienced initial workmanship problems with hybrid DC-DC power converters from a vendor who supplies primarily low cost commercial parts. Working closely with the vendor to improve manufacturing processes and quality, the project was able to obtain some acceptable parts. Maintenance of an approved supplier list, including performance of supplier quality surveys, is increasingly important as JPL projects transition from military specification parts, to commercial specification parts where manufacturing processes may not be well documented or controlled. | Maintenance of an approved supplier list is increasingly important as JPL projects transition from military specification parts, to commercial specification parts where manufacturing processes may not be well documented or controlled. | Project planning should include sufficient budget for the performance of supplier quality surveys. The JPL electronic parts procurement process should develop and maintain an approved supplier list and a vendor rating system to foster new suppliers and identify vendor technical and delivery problems. Such a rating system should be updated periodically incorporating results of testing programs, GIDEP alerts and JPL internal parts bulletins. Projects should utilize quality survey results and the vendor rating system. | JPL | 10/01/1998 | The Mars Pathfinder (MPF) project experienced initial workmanship problems with hybrid DC-DC power converters from a vendor who supplies primarily low cost commercial parts. Working closely with the vendor to improve manufacturing processes and quality, the MPF project was able to obtain some acceptable parts. This successful MPF experience led the Seawinds, QuickScat, Deep Space 1, Stardust, and Mars 98 projects to purchase similar converters from this vendor. However, vendor process changes since MPF led to significant quality problems with the production lots for these projects. A JPL tiger team was formed to address these quality problems. Significant project costs were incurred in resolving the issues and reworking the converters. The JPL electronic parts procurement practice had been to check the date when the vendor was last surveyed by JPL Quality Assurance. Where no recent survey had been performed, the project funded a new on-site vendor survey. This review of vendor manufacturing processes, procedures, and controls resulted in approval, conditional approval, or disapproval of the vendor. Despite the increased utilization of low cost commercial quality parts, this JPL practice has fallen into disuse due to small projects' budget constraints. Additional Keyword(s): Quality Audit, Supplier Audit | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.14.6 ("Management Practices: Acquisition and Surveillance"), Paragraph 7.1.4 ("Safety and Mission Assurance Practices: Mission Assurance Management"), and Paragraph 7.5.6 ("Safety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisition"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/14/1998
600 | Clark, K - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Clark, K - 0000000000 : NO@ADDRESS.GIVEN |  | Continuous Capture of Lessons Learned During Project Lifecycle (1996) | Capture of lessons learned throughout the project life cycle is generally more efficient and effective than waiting until project development is completed. Throughout the flight project lifecycle, maintain a cumulative list of lessons learned, including technical/management issues and significant events. | Capture of lessons learned throughout the project life cycle is generally more efficient and effective than waiting until project development is completed. | Throughout the flight project lifecycle, maintain a cumulative list of lessons learned, including technical/management issues and significant events. At appropriate times, publish significant lessons learned which capture the knowledge gained throughout the project lifecycle. | JPL | 09/03/1998 | At the end of the Mars Global Surveyor (MGS) project, management identified and documented significant project lessons learned. Although this process was successful in identifying important lessons, collecting and organizing the material was arduous at this late date. Management could not assure that all candidate lessons were identified because project staff members were in job transition, and staff recollection over the entire project history had faded. In contrast, the Mars Pathfinder (MPF) project used a different approach. Throughout the project an ongoing list of potential lessons learned was maintained. During the quiescent MPF cruise period, project management made time to review the list and related documentation. They prepared a comprehensive summary of the lessons learned issues, emphasizing the importance of innovative management techniques, concurrent engineering/teaming practices, and spacecraft architectures to this low cost, rapid development flight project. Information transfer seminars on MPF lessons learned were sponsored by senior Project staff and widely attended by JPL personnel. Reference(s): B. Muirhead, MPF Lessons Learned-Volume 1, April 17, 1997. B. Muirhead, MPF Lessons Learned-Volume 2, April 28, 1997. JPL D-15553, Lessons Learned Process, July 1998. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.22.1 ("Engineering Practices: Flight Hardware Logistics") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/11/1998
601 | Cherniack, E - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Cherniack, E - 0000000000 : NO@ADDRESS.GIVEN |  | Need for Power Subsystem Spares (1998) | Galileo and Deep Space 1 failures during ground test and integration damaged power subsystem modules, demonstrating the importance of an adequate supply of these spares. Since power subsystem modules are particularly susceptible to damage during ground test, project sparing policy -- even for low cost missions-- should allow for unplanned consumption of spacecraft power subsystem modules. | Power subsystems are particularly susceptible to damage during ground test that is likely to deplete the spares inventory. | Project sparing policy -- even for low cost missions-- should allow for unplanned consumption of spacecraft power subsystem modules during test and integration. | JPL | 09/10/1998 | Innovative, low cost approaches to NASA spaceflight missions may include a reduced inventory of flight hardware spares. However, experience throughout JPL flight project history illustrates the importance of an adequate supply of spare power subsystem modules. Both the Galileo and Deep Space 1 projects sustained major damage to power subsystem modules or assemblies due to spacecraft equipment failures during ground test and integration. Since high voltage and current exist in power subsystems, failures that affect power equipment tend to cause more hardware damage than other electrical failures. Occasionally during ground test, short circuits occur which char spacecraft power subsystem components or vaporize modules to the extent that they are unrepairable. If this occurs close to the launch date, acquisition of replacement units may be impossible without impacting the launch schedule. Additional Keyword(s): PPS, Power Module, Power Converter Unit, PCU, GLL, DS1 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.1 ("Management Practices: Spares, Testbeds, and Models"), and Paragraph 6.9.2 ("Engineering Practices: Flight Hardware Logistics"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 09/11/1998
599 | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN; Deligiannis, F - ; DiStefano, S - ; Oberhettinger, D - | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN |  | In-Flight Management of Rechargeable Batteries (1992) | Performance problems with NiCd rechargeable batteries, which drastically affected the lifespan of several military satellites, led JPL to review existing battery management techniques. Optimized in-flight battery management practices were recommended. Also, use of a Taguchi Design Of Experiments approach reduced the number of battery test conditions from 1,024 to 16. | Optimized in-flight battery management practices can result in significant improvement in performance of rechargeable batteries, such as NiCd. See the reference or call its author(s) for more detail. Use of "Taguchi Methods of Robust Design" as a Design Of Experiments approach reduced the number of battery test conditions from 1,024 to 16. | See Lessons Learned above. | JPL | 08/27/1998 | In recent years, performance problems with onboard nickel cadmium (NiCd) rechargeable batteries drastically affected the lifespan of several Department of Defense satellites. NiCd batteries are currently used for an entire class of NASA observatory spacecraft, including TOPEX, Extreme Ultra-Violet Explorer (EUVE), Upper Atmosphere Research Satellite (UARS), and Gamma Ray Observatory (GRO). NASA postulated that optimizing onboard battery performance could extend the life of these batteries, and thus the potential life of the spacecraft. JPL was asked to review existing NiCd battery management techniques to determine their effectiveness in achieving optimal flight performance. A ground battery testbed was created to evaluate the operational parameters affecting battery life, including peak charge current and depth-of-discharge. Environmental factors such as battery operating temperature were also considered. Three existing NiCd batteries were evaluated. The experimental protocol made use of the "Taguchi Methods of Robust Design" techniques and applied them to determine the optimum management of battery operation. Testing confirmed that a change in battery management practices reduced the cell-to-cell voltage variations (in this case by 96 percent), which significantly improved the performance of this battery type. Reference(s): J. Blosiu, F. Deligiannis, S. DiStefano, "Optimization of Battery Operation Management Using Robust Design.," (JPL Technical Paper). | JPL has referenced the lesson as supporting Paragraph 4.1.3.3 ("Flight System Design: Design Robustness - Graceful Degradation"), and Paragraph 4.3.3.6 ("Power/Pyrotechnics Design: Power Generation - Secondary (Rechargeable) Batteries") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/01/1998
598 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN; Whittlesey, A - | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Protect Against Corona Discharge and High Voltage Breakdown (1960's-Present) | JPL flight projects since the 1960s-- Ranger 6, Mariner Mars, Viking 2, Voyager, Galileo, NSCAT, Magellan, and Mars Observer-- have a history of susceptibility to corona when exposed to regimes of critical pressure during ground test and flight. Design, test, and operational procedures are listed that may address spacecraft hardware susceptibility to corona-induced damage caused by either flight or ground environments. | Hazardous corona events can be induced by both flight and ground environments. Examples include: Passage of a spacecraft through a critical pressure region of the atmosphere following launch. Partial pressurization of a spacecraft in space due to gas leaks from propulsion systems, batteries, etc. Engine firings in vacuum or near vacuum which cause plume wrapping. Changes in vacuum chamber test facility pressurization which expose powered flight hardware to the critical pressure region. Electric fields from low voltage circuitry, such as pyrotechnic device firing circuits. | Spacecraft hardware susceptibility to corona-induced damage should be addressed in subsystem design and in test and operational procedures. Ensure that ventable products will be vented overboard in spaceflight instead of venting within any enclosures, including blankets. The following design measures for corona avoidance on high voltage circuits, summarized from Reference (1), were recently used in the Multi-Angle Imaging Spectroradiometer (MISR) instrument program (Reference (2)): Avoid venting into regions of intense electric fields, such as the vicinity of power supplies and power wiring. Ensure that all critical voltage regions are properly vented. Use insulation materials of high dielectric strength. Insulating materials with strength greater than 300 volts/mil and a relative dielectric constant less than 5 are preferred. For high voltages, use only connectors that have been tested to work in the critical pressure region. Also, use only soldering terminals rated for high voltage. Physically isolate the high and low voltage circuits. Test the circuits that may be subject to voltage breakdown and/or corona discharge. Where the above design measures cannot be accommodated, take protective actions (e.g., power such circuitry off prior to encountering critical pressure regions) during testing and flight to avoid damage. | JPL | 07/22/1998 | JPL flight projects have a history of susceptibility to corona when exposed to regimes of critical pressure during ground test and flight: Ranger 6 (in-flight): During launch the camera was inadvertently powered. In addition a nearby enclosure was insufficiently vented for boost pressure decay. As the spacecraft passed the critical pressure region, a corona discharge occurred, disabling the camera system. The result was a complete loss of imaging data. 1971- Mariner Mars (ground): During acceptance testing, it was found that a lack of RF breakdown margin at critical pressure necessitated costly design changes. 1971- Mariner Mars (in-flight): Unexpected battery venting caused a brief critical pressure region around the high voltage Canopus star tracker, resulting in a corona discharge. The arc caused a ground-loop current spike that resulted in the permanent loss of 22 telemetry channels in the Flight Data Subsystem (FDS). 1976- Viking 2 (in-flight): The Viking Lander's downlink failed while on the surface of Mars. This suggested that the high voltage power converter developed a corona discharge and high voltage breakdown while in the critical CO2 pressure region present near the surface of Mars. [D] 1976- Voyager (ground): Design verification disclosed voids in certain capacitors which could bleed down to critical pressure after long exposure to vacuum, and could lead to a corona discharge. 1988- Galileo (ground): The vendor's vacuum chamber was purged with dry nitrogen while the extreme ultraviolet (EUV) instrument was powered. This produced a critical pressure region, corona discharge, and failure of the EUV high voltage power supply. 1989- NSCAT (ground): Windings added to a traveling wave tube amplifier (TWTA) transformer for test purposes, resulted in increased voltage in the primary windings, which triggered a corona discharge. 1989- Magellan (in-flight): The pyrotechnic firing which separated the solid rocket motor, used for Venus Orbit Insertion, resulted in a plasma arc, a ground current loop, and destruction of a significant amount of spacecraft memory. 1990- Mars Observer (ground): Due to inadequate insulation of the TWTA, a corona discharge occurred at critical pressure during evacuation of the vacuum chamber. Additional Keyword(s): Electrostatic Discharge Reference(s): JPL D-8208, Design and Fabrication Requirements, Section 3.9: quotHigh Voltage Requirementsquot, Rev. C, March 15, 1997. A. Whittlesey, quotMISR Corona Issues,quot JPL IOM 5215-94-75 (MISR DFM # 380), March 17, 1994. quotProceedings of the Second Workshop on Voltage Breakdown in Electronic Equipment at Low Air Pressures on March 5-7,1969,quot JPL TM-33447, June 30, 1970. quotRF Breakdown in Mariner Mars '71 RFS Components and Circuits,quot JPL Lesson Learned No. 3-115; JPL Problem Failure Report (PFR) No. 100789. quotHigh Voltage Capacitor Used in Voltage Doubler Circuits for Space Applications,quot JPL Lesson Learned No. 3-117. quotTraveling Wave Tube Amplifier on Martian Surface: Failure Due to Corona,quot JPL Lesson Learned No. 3-119; Viking Incident Surprise Anomaly (ISA) Report No. 15643, October 13, 1976. JPL Galileo PFR No. 44450. JPL NSCAT PFR Nos. 52102 & 52103. JPL Mars Observer PFR No. F0745. JPL Magellan PFR #52235. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.4 (quotEngineering Practices: Protection and Security of Flight Hardwarequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.10.1.1 (quotSystem EMC/EMI Design: General - EMC Approachquot), and Paragraph 4.12.2.3 (quotFlight Electronics Hardware System Design: Electronic Packaging - High Voltage Designsquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 08/07/1998
597 | Schuster, Ludwig - 0000000000 : NO@ADDRESS.GIVEN | Schuster, Ludwig - 0000000000 : NO@ADDRESS.GIVEN |  | Monitoring of On-orbit Spacecraft Health and Performance During Early Mission Checkout |  | Continuous monitoring of spacecraft health is essential during the early orbit and operations checkout phase, lasting typically 30-90 days. This is critical if anomalies are present or if the spacecraft has inherent design, power or orbital parameter limitations that must be corrected in real time or near real time in order for the spacecraft to survive. | Ensure that initial on orbit health monitoring of new spacecraft be continuously undertaken by ground station personnel and that any critical life threatening on orbit anomalies be resolved as expeditiously as possible. This includes ensuring that this segment of the operations phase has adequate program resources. | HQ | 07/10/1998 | During the critical initial on orbit operations and checkout phase, ground station personnel did not monitor the Lewis spacecraft continuously for anomalies. This was accepted based on a false belief that the spacecraft had a stable safe-mode that it would switch to automatically if anomalies were not immediately corrected. (In the Lewis implementation, the safe-mode was neither stable nor robust.) The situation was further exacerbated by the fact the spacecraft was in an interim (low altitude) orbit which had high drag and short on-station communications intervals and for which the designers had not carried out modeling. |  | N/A |  |  | Public | Not Specified |  | 07/28/1998
596 | Schuster, Ludwig - 0000000000 : NO@ADDRESS.GIVEN | Schuster, Ludwig - 0000000000 : NO@ADDRESS.GIVEN |  | Insufficient Understanding and Agreement on "Faster, Better, Cheaper" Mission Implementation |  | "Faster, better, cheaper" programs are inherently susceptible to adverse effects due to changes in scope. These programs are also susceptible to perturbations in continuity of commitment and key personnel. | Provide agency level guidance for structuring "faster, better, cheaper" programs. Enter into "faster, better, cheaper" agreements with necessary foresight to eliminate the need for contract modifications. When modifications are unavoidable, recognize the seriousness of the change to the basic approach and ensure the changes include appropriate resource adjustments. Make clear agreements on roles and responsibilities of contractor and government personnel part of the contract. Tailor government insight to match the risk. Any contract for space flight should allow for at least one major technical review involving government experts. Also, consider the inclusion of a "process review" at the beginning of the performance period to ensure understanding by all parties concerning roles, responsibilities, baselines, and risk items. | HQ | 07/13/1998 | Serious programmatic difficulties arose during the period of performance on the Lewis Mission. These difficulties can be traced to Insufficient Understanding and Agreement on "Faster, Better, Cheaper" Mission Implementation. |  | N/A |  |  | Public | Not Specified |  | 07/28/1998
595 | Schuster, Ludwig - 0000000000 : NO@ADDRESS.GIVEN | Schuster, Ludwig - 0000000000 : NO@ADDRESS.GIVEN |  | Misapplication of Heritage Systems, Subsystems and Validation Tools on the Lewis Spacecraft |  | Use of a proven design system in a new application does not ensure success and does not relieve the design activity from carrying out (independent) technical peer reviews and comprehensive assurance processes and validation. | Ensure uniform treatment of all systems and subsystems in technical and management reviews regardless of heritage. Require comprehensive independent peer reviews on all subsystems and systems. | HQ | 07/13/1998 | The Lewis implementation had a flawed attitude control system (ACS) design and simulation deriving from technically invalid application of a design from an earlier mission. This misapplication ultimately led to the spacecraft failure when the system encountered an untested instability during a "safe hold." |  | N/A |  |  | Public | Not Specified |  | 07/28/1998
593 | Reeves, G - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Reeves, G - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Pathfinder Avionics and Flight Software Architecture (1997) | The Mars Pathfinder (MPF) avionics and flight software development effort focused on producing a software architecture that would contribute to lower operations cost and minimize the overall project cost. This lesson summarizes MPF success factors, including use of an extra powerful flight computer and a standardized backplane and bus. | Use of a powerful computer (20 MIPS) with large memory for margin management provided flexibility in software development for MPF. Consider use of a commercial standard backplane (e.g., VME) and avionics standard bus (such as MIL-STD-1553) to allow the fast development of realistic test environments using commercial hardware and software. The early MPF risk assessments prompted the use of an essentially single string avionics design, which resulted in a great reduction in the complexity of the software. A multitasking execution model permits parallel development of separate modules and is supported by a variety of commercial products. Purchase a commercial operating system (kernel) rather than developing one in house. Select a mature flexible implementation language, with mature development tools, such as the C language. The MPF project combined the Command Data Subsystem (CDS) and Attitude Control Subsystem (ACS) hardware and software functions in one processor. This greatly simplified hardware design, ground and flight software design, system implementation, and integration and test. Consider using software system analysts to directly produce flight code, instead of just writing software specifications and handing them to a flight software team to code. | See Lessons Learned | JPL | 06/18/1998 | The Mars Pathfinder (MPF) avionics and flight software development effort focused on producing a software architecture that would contribute to lower operations cost and minimize the overall project cost. Additional Keyword(s): Software Life Cycle, Life Cycle Cost, Concurrent Engineering Reference(s): Glenn Reeves, "Mars Pathfinder Flight Software Lessons Learned," April 28, 1997. "Mars Pathfinder Flight Software Development Process," JPL Lesson Learned No.10-105, June 4, 1998. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.3 ("Engineering Practices: System Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 06/25/1998
594 | Herring, Ellen - 0000000000 : NO@ADDRESS.GIVEN | Herring, Ellen - 0000000000 : NO@ADDRESS.GIVEN |  | ACE SEPICA Micro-machined Silicon Valve On-orbit Anomaly |  | Inconsistencies in Ground Testing vs. On-Orbit Configuration: Ground testing should mirror on-orbit configuration to the maximum extent possible. Ground hardware should undergo test program as similar as possible to flight units (e.g, thermal, vibration, acoustical, etc.). For those areas that can not be made to be consistent with on-orbit configuration and/or pre-mission flight unit test program, analysis should be performed to justify and/or extrapolate test results to the on-orbit environment and flight units. Use of COTS Products Beyond Recommended Design/Operations: The need to use a small, commercially made valve was emphasized and recommended by an independent Review Team very early in the program. The choice of the selected valve was driven by what was available in the marketplace, and by spacecraft constraints, cost, and schedule. In order to meet instrument needs, it was necessary to operate the valve outside of manufacturer's recommendations. COTS products should be carefully chosen to be consistent with system defined specifications. Testing or analysis should be performed to identify and understand risks, to the COTS as well as to the mission goals, associated with operating COTS in other than recommended manner. Use of Emerging Technology: The selected valve was an immature, emerging-technology product line and was available through only one vendor. The original vendor is no longer producing the valve and has no remaining in-house expertise to support on-orbit anomaly analysis and resolution. Risk is expected when dealing with emerging technology; however, the customer should attempt to mitigate these risks by fully investigating the stability of the supplier, the future market of the product, and the future availability of engineering analysis support. COTS Workmanship: Pre-mission analysis indicated inconsistent workmanship on the 3 analyzed valves. Risk mitigation was put in place on the customer side by a filtering, selection process complemented by an extensive ground test program. Additional effort should be considered to mitigate risk by partnering with the vendor to improve vendor workmanship prior to customer delivery to provide a higher quality product and/or to include an opportunity for customer inspection before a non-recoverable process (e.g., final sealing) is performed. On-orbit Mitigation: Although the valves were recognized as a high risk element of the instrument development, no analysis was performed on a low-cost, possibly degraded, on-orbit gas control mechanism to fall back on in case of on-orbit valve failure. Given overall mission constraints, this was consistent with the approach taken for ACE. However, it is generally recommended that pre-mission analysis should include evaluation of most probable failures and the identification of low cost, degraded on-orbit back-up approaches that could result in continuing science taking in a potentially degraded mode at marginal cost. Consequence of Additional Risks of Faster, Better, Cheaper (FBC) Mission Environment: In order to meet the spacecraft limitations, cost, and schedule envelope to fly in the FBC environment, Projects must at times accept higher risk associated with emerging technology, non-space qualified parts, and/or COTS products. Failures, likely to become more frequent in this paradigm, should be expected, accepted, and built upon as a resource to mitigate future mission risks. Required emerging technology such as these low power, low mass micro-valves should be identified to NASA technology programs as a technology to be selected for future initiatives to allow some level of test, verification, and improvement prior to operational flight. | See Lessons Learned | GSFC | 06/17/1998 | The SEPICA instrument, one of 9 instruments flown on the ACE Mission, uses isobutane gas as part of its particle detection scheme. Three proportional counters, one associated with each of SEPICA's 3 detectors (1-high resolution, 2-low resolution), were to be held at a constant pressure by the use of a Commercial-Off-The-Shelf (COTS) bi-metallic micro-machined silicon valve assigned to each of the detectors. Following one month of flawless operations, detector operations indicated pressure being maintained slightly higher than pressure set point. It was thought that this state could be attributed to a loss of valve seat tightness or to a fundamental shift in valve baseline response. Approximately 6 months following launch, pressure in the high resolution detector totally decayed to zero at a rate consistent with that of a normal closed-valve rate. Analysis of the pressure decay and the inability to command the valve seems to indicate that the valve associated with this detector is in a closed state and there exists a lack of ability to flow required current across the system to open the valve. Although unproven, analysis seems to indicate the failure is within the valve. Impact of this failure to mission and instrument science is minimal due to a combination of the availability of high resolution data obtained earlier in the mission, the continuing availability of the other 2 SEPICA low resolution detectors, and the availability of complementary science from other ACE instruments. Although pre-mission analysis did indicate inconsistent workmanship in the chosen COTS valves, it was determined that these COTS valves were the only acceptable design approach given mission limitations (e.g., power, mass, etc.) and that the risk mitigation approach to select the best valves through instrument team-led filtering process and the performance of extensive ground testing was consistent with the mission/instrument class (i.e., mission was Class C and instrument suite was Class D). Considerable experience was gained in extensive pre-launch and post-launch ground testing which was performed at on-orbit thermal and vacuum conditions. However due to safety concerns, the majority of life testing on the spare unit at the University of New Hampshire was performed with nitrogen, rather than the on-orbit isobutane gas. The use of nitrogen did not necessarily fully simulate effects in the on-orbit configuration due to the different properties from the on-board gas. Post-anomaly evaluation also indicated that, although the spare gas system had undergone some level of vibration test, the valves had been replaced afterward. The flight valves that are being tested in the spare have not been vibrated at all and, therefore, may not be an adequate model of the on-orbit valves. The valve manufacturer did supply recommended valve operational boundaries (e.g., duty cycle, power, etc). In some of these areas, the on-orbit valves were operated on or near the manufacturer's recommended boundaries and, in the area of duty cycle, the valves were operated outside of the manufacturer's documented recommendations with verbal confirmation from the manufacturer that the out-of-boundary conditions should be acceptable. The selected valve was a commercial product, is no longer produced by the vendor, and vendor-expertise is no longer available. No on-orbit back-up/redundancy to control the gas flow, possibly in a degraded fashion, in case of failure of the valves was developed or contemplated. |  | N/A |  |  | Public | Not Specified |  | 06/24/1998
592 | Gacek, Joseph - 0000000000 : NO@ADDRESS.GIVEN | Gacek, Joseph - 0000000000 : NO@ADDRESS.GIVEN |  | Conformal Coating as Moisture Protection of Electronic Circuitry in Micro Gravity |  | Post flight testing determined that water, resulting from moisture produced during the smoldering process, provide an apparent electrical coupling between pins 9 and10 of the integrated circuit responsible for temperature compensation. The condition was repeated in the laboratory, producing the same results as those encountered in flight. Water on the card connector contacts likewise produced similar results. Increasing thickness of conformal coating on the circuit board to twice that originally used verified water no longer caused the coupling problem between the integrated circuit pins 9 and 10. Additionally, circuit board and chamber connectors were sealed with RTV to prevent water incursion. Conformal coating nominally used as a contamination and flammability barrier does not necessarily provide an effective electrical barrier. The need for electrical isolation should be considered in the selection of the conformal coating material and method of application, especially in humid applications. | Where condensation is anticipated in an experiment conducted in micro-gravity, it is imperative that sufficient encapsulation of electronic circuitry is used to prevent incursion of water into the electrical components. Additionally, tests should be performed to verify that moisture does not introduce detrimental coupling between, or within electronic components. | GRC | 06/17/1998 | The Microgravity Smoldering Combustion protoflight unit was flown on the STS69 shuttle mission. Resulting flight data indicated anomalous readings from two thermocouples. Both channels had noticeable noise, and readings, which were higher than anticipated for the condition. Since the igniter algorithm uses this information to initiate igniter shut-off the igniter was shut off prior to establishing desired conditions in the foam for smoldering completion. | The re-flight on STS-77 with the additional conformal coating and added encapsulation produced expected temperature values, and provided nominal test information. | N/A |  |  | Public | Not Specified |  | 06/18/1998
591 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Pyrovalve Blow-by May Interact Violently With Propellant (1993) | Two satellites with different propulsion system designs were lost in 1993 and 1994 when blow-by from pyrovalves interacted violently with propellants. To prevent detonation of fuel due to the compression of hydrazine and its ignition by pyrovalve blow-by, use non-pyrotechnic valves or a zero blow-by pyrovalve design, or fire a pyrovalve only when there is a vacuum downstream of the valve. | Blow-by from pyrovalves can interact violently with propellants in propulsion systems. | To prevent detonation of fuel in propulsion systems due to the compression of hydrazine and its ignition by pyrovalve blow-by: Use non-pyrotechnic valves such as latching valves, or Use a zero blow-by pyrovalve design, and/or Fire a pyrovalve only when there is a vacuum downstream of the valve. | JPL | 05/13/1998 | Two satellites with different propulsion system designs were lost in 1993 and 1994. Limited telemetry was received on the incidents. Subsequent failure investigation focused on possible propulsion feed system design flaws. In both cases, pyrovalves were used to isolate the hydrazine supply until the satellite was separated from the launch vehicle. [D] In accordance with a common design practice for engine feed systems, two pyrovalves were placed in parallel to provide redundancy. With the hydrazine tank isolated, pressurized fuel was present upstream of the pyrovalves (e.g., Point A), but only a dry nitrogen quotpad gasquot at low pressure downstream of the pyrovalves (e.g., Point B). On one spacecraft it was unclear what the gas composition was and whether it was totally vented through the thruster prior to the priming event. During priming of the hydrazine system, the primary pyrovalve was fired to charge propellant lines leading to the engine. When the propellant reached the thruster valves and stopped, it produced a pressure surge. Under certain conditions, this surge could cause exothermic decomposition of the fuel, and tests were conducted to assess if the prevalent conditions were conducive to exothermic decomposition. This particular failure mode was never observed during the failure investigations. However, when the backup pyrovalve was fired a second later during one test, the blow-by of hot gas into the lines between Points A and B detonated the decomposed fuel; this then breached the fuel lines on both sides of the backup pyrovalve. The tests did not exhibit this detonation failure mode when, just prior to firing the backup pyrovalve, the pad gas was evacuated to leave a vacuum downstream of both pyrovalves. Reference(s): GIDEP Advisory No. GH-P-94-01, quotPyrovalve, Titanium, 1/2quot, Normally Closed Single Initiates,quot Revised May 1, 1995. |  | N/A |  |  | Public | Not Specified |  | 06/16/1998
590 | Reeves, G - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Reeves, G - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Pathfinder Flight Software Development Process (1997) | Mars Pathfinder (MPF) flight software development departed from strict adherence to then existing institutional software standards in order to produce software that would contribute to lower operations cost and minimize the overall cost to the project. Innovations included early software planning, getting software and hardware together early, avoiding excessive use of CASE tools, and development of a “Flight-Like Test Set” for early unit and integration testing | Establish a software implementation plan early that outlines the basic strategy, including reviews, standards, processes, schedule, and deliverables. Get software and hardware together early in the development cycle, with hardware-software integration performed by the flight software team. Using the flight software team to identify integration problems is efficient, since it is the party responsible for fixing them. Make early, conscious, engineering decisions on the applicability of computer-aided software engineering (CASE) tools. Beyond basic software development planning, their use can consume resources and prove counterproductive. Develop a quotFlight-Like Test Setquot (FLTS) for early unit and integration testing. The MPF FLTS test set (shown below) was comprised of commercial hardware and simulation software assembled by the flight team members. Both the spacecraft and FLTS used a standard VME bus and software architecture, thus avoiding any duplication of effort. [D] MPF Flight-Like Test Set (FLTS) Provide the flight software team with a dedicated flight software testbed equipped with engineering model hardware. Such a testbed permits development and checkout of flight software in parallel with development of electronics and sensors. The MPF project avoided the overhead associated with strict adherence to documentation and coding standards since no inheritance by future projects was planned. However, project(s) inheriting this software have since encountered problems due to limited documentation. | See Lessons Learned | JPL | 06/03/1998 | Beyond meeting mission requirements, the Mars Pathfinder (MPF) flight software development effort focused on producing software that would contribute to lower operations cost and minimize the overall cost to the project. This cost consciousness necessitated the establishment of low cost software development processes compatible with short duration missions. These new processes did not require strict adherence to then existing institutional software standards. Additional Keyword(s): System Architecture, Software Life Cycle, Rapid Prototyping, Concurrent Engineering Reference(s): Glenn Reeves, quotMars Pathfinder Flight Software Lessons Learned,quot April 28, 1997. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.3.1 and 5.7.4 (quotManagement Practices: Spares, Testbeds, and Modelsquot), and Paragraph 6.11.3 (quotEngineering Practices: Software Development - Development, Maintenance and Acquisition Practicesquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.11.1.4 (quotFlight Software System Design: Compatibility with COTS Toolsquot), in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 06/09/1998
589 | Milburn, Julia - 0000000000 : NO@ADDRESS.GIVEN | Milburn, Julia - 0000000000 : NO@ADDRESS.GIVEN |  | Utility Vehicle Incident |  | Vehicles not designed as personnel carriers should not be used for personnel transportation. | Use special vehicles only for intended and designed use. Assure all drivers of vehicles are trained in proper use of utility vehicles. | MSFC | 06/04/1998 | On May 16, 1998, MSFC held an quotOpen Housequot for the public. During the event an elderly woman fell from the rear of a NASA owned and operated utility vehicle, hitting her head on the pavement. The visitor was taken to the hospital and fortunately released with no serious injuries. An investigation determined that the woman requested the vehicle driver to take her to another location within the Center. She sat on the rear bed of the vehicle. When the vehicle moved forward she slipped off. The utility vehicle is a 4 wheel skooter with a small flat bed manufactured by Cushman (see photos below). |  | N/A |  |  | Public | Not Specified |  | 06/08/1998
588 | Kestel, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Kestel, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Booster (SRB) Holddown Post Incident |  | OSHA standards are inadequate for space operations. Organizations that move very large, heavy, critical, or high-value hardware/equipment need to review training requirements and adjust certification criteria where appropriate. A standardized set of minimum certification requirements for all KSC operators would be helpful in ensuring a uniform proficiency level. Housekeeping requires continuous vigilance. Obstacles can cause abnormal maneuvering and/or load shifts that affect stability. The entire path of movement needs to be clear. Figure 1. Original Pallet/Handling Configuration Figure 2. Redesigned Pallet | Shipping/handling pallets and containers for large/bulky items should be designed to provide adequate restraint of a load during movement (see figure 2). Adequate procedures/training should be developed for handling critical and high-value ground support equipment and other equipment. Operators must maintain situational awareness of the task to be performed, load management factors, and the environment (obstacles, weather, terrain, etc.). Supervisors should exercise judgment when assigning tasks. If tasks are hazardous, critical, high value, or new/infrequent, supervisors should assign the task by experience or should provide experienced trainers. Organizations that move very large, heavy, critical, or high-value hardware/equipment need to review training requirements and adjust certification criteria where appropriate. A standardized set of minimum certification requirements for all KSC operators would be helpful in ensuring a uniform proficiency level. Obstacles can cause abnormal maneuvering and/or load shifts that affect stability. The entire path of movement needs to be clear. | KSC | 05/12/1998 | On October 8, 1997, a 7,000-pound Solid Rocket Booster Holddown Post (HDP) slid off a forklift while it was being moved up a slight ramp into the low bay of building M7-505 at the Launch Equipment Test Facility (LETF). Neither damage to the holddown post nor injuries to personnel occurred during this near miss. Root Causes: Design: The less than optimal design of the shipping/handling pallet and the load restraint configuration of the HDP provided a minimal margin for stability (see figure 1). Procedure: The forklift operator's lack of attention to the HDP configuration and good forklift operating practices contributed to the unstable conditions. Environment: Storage of equipment in the rollup door area hindered the forklift's approach and contributed to the improperly angled entry into the area. |  | N/A |  |  | Public | Not Specified |  | 05/28/1998
587 | Kestel, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Kestel, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | High Pressure Incident |  | High pressure systems need to be operated by qualified employees and new high pressure sources evaluated prior being ordered/used. Work-arounds create new/unexpected hazards to employees. All employees need to have a single and easy to access source of safety information on high pressure systems. | Require all NEW USAGE requests for high pressure gas sources be approved in writing by Safety Dept. Require all employees likely to come in contact with or be near compressed gas systems to be trained every three years on high pressure gas hazards and precautions. Require that all work-arounds and repairs for flight hardware processing systems, beyond the expected routine return to print / configuration , be formally documented on the appropriate approved work authorization procedures (PR, RODS, or FWR). All deviations from approved processes on Safety Reviewed systems shall be formally documented and approved by Safety Dept. Particular attention must be applied to work-arounds which have potentially hazardous consequences. These should always be documented with a WAD and approved by Safety. Improve existing Safety Procedures to include more information on compressed gas safety requirements such as regulator selection criteria and design requirements. | KSC | 05/12/1998 | Recently a Close Call involving the unintentional over-pressurization of a low pressure system designed to operate at less than 150 p.s.i.g. The system was opened to a pressure of 2300 p.s.i.g. for a fraction of a second until a shop air hose, rated for 300 p.s.i.g., ruptured into two sections. It was fortunate that no one was hurt as the potential for serious injury was very real. The sequence of events was started with a work-around that was initiated to replace the shop air (which was out of specification) in the LubeLok spray booth with compressed air from a supplied Manifold K-bottle Rack. The engineer in charge misread the Rack's pressure gauge and quotassumedquot the output pressure was 160 p.s.i.g. when what he had read off the gauge (see picture) was 160 BAR, approximately the equivalent of 2300 p.s.i.g. Root Causes: Failure to pay attention to details because no one involved took the time to correctly observe the high pressure indicated on the gauge. (see picture) Lack of training and failure to take time to understand the Manifold Rack's design which would have revealed that there was no pressure regulator built into the Rack system. Failure to develop detailed work authorization documents to perform work on a Safety Reviewed system that processes Flight Hardware and which requires quotmaterial specificationsquot. No gauge or pressure indication visible from control valve. |  | N/A |  |  | Public | Not Specified |  | 05/28/1998 | Safety & Mission Assurance
586 | Kuberry, R - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Kuberry, R - 0000000000 : NO@ADDRESS.GIVEN |  | Verify Vendor Certifications of Commercial Equipment (1996) | A commercial reference antenna used to test the Cassini-to-Probe RF link wrongly indicated that the spacecraft and probe antenna polarizations were both incorrect. The GSE reference antenna was then tested against other antennas of known polarization and found to be mislabeled. The functional attributes of vendor provided equipment cannot be assumed to match specifications, particularly when an item is to be used as a reference standard. Assure independent testing of critical features of commercial instrumentation, review interface control documents and drawings, and conduct spacecraft-level tests of all telecom interfaces. | The functional attributes of vendor provided equipment cannot be assumed to match specifications, particularly when an item is to be used as a reference standard. | Assure adequate independent testing of critical features of any commercial instrumentation used in a test of flight or critical hardware. Continue present practice of reviewing interface control documents and drawings to determine whether they adequately define and control interface conflicts between subsystem and spacecraft elements. To prevent gaps in system-level interface control and monitoring, conduct spacecraft-level tests, where practical, of all telecom interfaces, including polarization. | JPL | 04/23/1998 | JPL required the use of a reference antenna to verify the Huygens Probe to Cassini high gain antenna (HGA) RF link. A test had been developed to use right and left-circular polarized (RHCP and LHCP) antennas to verify the polarization of both the Probe and HGA antennas, used for the transfer of science data during the probe's descent to the surface of Titan. JPL purchased an off-the-shelf RHCP conical log spiral antenna for this test; the vendor provided a calibration certificate which certified the candidate ground support equipment (GSE) antenna to be right-circular polarized. When the commercial antenna was used as a reference standard during a spacecraft-level RF compatibility test, it indicated that the spacecraft and probe antenna polarizations were both incorrect. When further investigation between international partners could not substantiate this indication, the GSE reference antenna was tested against other antennas of known polarization and found to be mislabeled. The product featured a biwire winding which effectively reversed the polarization to LHCP, resulting in a left polarized emission from an apparently clockwise-wound spiral antenna. The manufacturer revealed that the antenna labeling was not in accordance with accepted standards, and that the product had been marketed as RHCP for over 10 years. Since the antenna had been used in EMC testing mostly as a broadband source or receiver, users were rarely concerned with polarization. As shown in Figure 1, the physical appearance of the reference antenna structure - a clockwise helix - supports the standard definition of RHCP, but the electrical performance indicates LHCP. [D] A Typical Conical Log Spiral Antenna Additional Keyword(s): COTS, Receiving Inspection Reference(s): Cassini Problem/Failure Report No. Z23529, October 21, 1996. K. Kellogg & W. Moore, quotProbe-Spacecraft Antenna End-to-End Failure Investigation Report,quot JPL IOM 3360-96-14, October 17, 1996. Lesson Learned #11-121, Ground Support Equipment Failure Caused Damage to SEASAT-A | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.2 (quotEngineering Practices: Project and System Level Functional Verification and Validation - Verification and Validationquot), in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 05/04/1998
585 | Muirhead, B - 0000000000 : NO@ADDRESS.GIVEN; Clark, K - ; Oberhettinger, D - | Muirhead, B - 0000000000 : NO@ADDRESS.GIVEN |  | Staff Continuity Enhances Low Cost, Rapid Development Projects (1996) | The low cost, short duration Mars Pathfinder and Mars Global Surveyor projects featured lean engineering teams. This provided several advantages, but made it critical to retain team members from the beginning to the end of the project. Obtain the commitment of high-level management to foster an environment that encourages team members to remain throughout the project lifecycle and with rotating assignments, as appropriate. | Experience on Mars Pathfinder and Mars Global Surveyor projects showed that retaining project team members from the beginning to the end of the project improved continuity of design, ATLO, and mission operations at lower cost. | Obtain the commitment of high-level management to foster an environment which encourages team members to remain throughout the project lifecycle and with rotating assignments, as appropriate. | JPL | 04/09/1998 | The Mars Pathfinder (MPF) and Mars Global Surveyor (MGS) flight projects pioneered JPL's transition to low cost, short duration, spacecraft development efforts. The projects featured lean engineering teams and required continual shuffling of team members between high priority tasks. The Assemble, Test, and Launch Operations (ATLO) phase advanced relatively smoothly for both projects, largely because almost all subsystems entered ATLO accompanied by the original design team complement. Project management understood the importance of these missions to JPL's future, and the potential impact of high turnover on project schedules. In addition to maintaining the flight project knowledge base, team continuity provided some additional benefits: Relatively inexperienced staff were assigned major responsibilities as they demonstrated their abilities, enhancing the value of available staff resources. Shuffling of the existing team among high priority tasks within the project provided a variety of experience for team members. Reliance on a small core staff required individual subsystem engineers to bridge interfaces, improving the understanding of the overall system and establishing relationships with the JPL technical divisions and the aerospace community. Reduced turnover of key technical personnel facilitates the assessment and control of mission risk. The potential downside to this staffing arrangement featuring lean team continuity involved the: Greater need for early identification of staff qualification and performance problems, and for immediate remedial action by Project management. Risk of staff burn-out and limitations to career mobility. Additional Keyword(s): Retention, Collocation, Personnel Phasing, Project Planning, Schedule Risk Management Reference(s): Muirhead, B., "Mars Pathfinder Lessons Learned - Volume 2," JPL MPF-100-97-LL2, April 28, 1997 Clark, K., Mars Global Surveyor Lessons Learned, April 4, 1997. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.12 ("Management Practices: Project Staffing and Destaffing") in the Jet Propulsion Laboratory standard, "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 04/27/1998
584 | Whetsel, C - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Whetsel, C - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Global Surveyor (MGS) Aerobraking Extra Burn Anomaly (1997) | Following Mars encounter, an unintended repetition of MGS's Aerobraking Maneuver #5 occurred after the intentional burn. Installation of a new version of the ground data system software one day earlier than planned without adequate review of the consequences of the schedule change caused an incompatibility between ground and flight software. Configuration control procedures must ensure that the spacecraft and sequence teams are properly notified of changes to planned ground software updates affecting the spacecraft. In particular, uplink sequences must be consistent with memory partitions onboard the spacecraft. | Configuration control procedures must ensure that the spacecraft and sequence teams are properly notified of changes to planned ground software updates affecting the spacecraft. In particular, uplink sequences must be consistent with memory partitions onboard the spacecraft. | Prior to implementing any change in command and control software, verify that the configurations of ground and flight software are compatible. Provide a method for identifying the time-criticality of any flight software configuration change. When approved mission plans must be changed in real time, review and reconsider all factors which were weighed in developing the original plan. Software design and implementation should minimize the possibility of accessing onboard stored command sequences at inappropriate times. Development and use of flight and ground software should be closely coordinated from the very beginning and throughout the life of the project. | JPL | 03/04/1998 | Missions using aerobraking employ atmospheric drag to reduce the spacecraft orbit period and lower its apoapsis altitude. The technique requires tight control both on the attitude pointing of the spacecraft while in the atmosphere, and especially on the altitude during each aerobraking drag pass at periapsis (the orbit's closest approach to the planet). Targeting periapsis altitudes is critical to assure that the proper orbital conditions are achieved. The periapsis altitude is controlled by periodically performing small propulsive aerobraking trim maneuvers (ABMs) one-half of the orbit period earlier. This places the spacecraft at the other side of the orbit, near apoapsis, the point in an orbit at which the spacecraft is at furthest distance from the planet. A portion of the Mars Global Surveyor (MGS) spacecraft memory was allocated and managed as storage space for command sequences and programs uplinked from Earth, such as aerobraking maneuvers. These sequence loads are typically created by the flight project's sequence team with inputs from the spacecraft and science operations teams. Extra Burn Anomaly. An unintended repetition of MGS Aerobraking Maneuver #5 occurred after the intentional burn on November 12, 1997. The planned maneuver's objective was to decelerate the spacecraft 0.1 meters per second (m/s) to enable an aerobraking pass 17 hours later. This maneuver executed as expected. [D] Aerobraking Operations Approximately 3 hours later, the spacecraft unexpectedly repeated the aerobraking maneuver, imparting an additional delta-v to the spacecraft. To avoid a deeper penetration into the Martian atmosphere, the flight team designed, uploaded, and successfully commanded a third quotantidotequot maneuver, which counteracted the effect of the unplanned second maneuver. Although the mission impact of this incident was limited to expenditure of propellant in the 0.5 m/s remedial burn, occurrence at another time could have been mission catastrophic. The cause of the incident was traced to an incompatibility between ground and flight software. A new version of the ground software had been installed in the ground data system one day earlier than planned without adequate review of the consequences of the schedule change. This new software had been redesigned to improve programming and command efficiency. Certain memory partitions were reassigned in on-board memory, and this software package needed to be installed on the ground system at the previously agreed to time relative to the command uploads. Due to the address changes, the recently executed Aerobraking Maneuver #5 was loaded into the partition originally intended for the next science sequence. Hence, when the spacecraft command data subsystem (CDS) executed quotNext Sequence,quot the Aerobraking Maneuver #5 sequence was still present in memory, and it was performed instead of the science sequence. Reference(s): JPL Incident/Surprise/Anomaly (ISA) Number Z44658, November 23, 1997 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.5 (quotEngineering Practices: Mission Operations - Critical Events and First-Time Eventsquot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/13/1998
582 | Clark, K - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Clark, K - 0000000000 : NO@ADDRESS.GIVEN |  | Informal Design Reviews Add Value to Formal Design Review Processes (1996) | A study supports the premise that informal peer review is valuable in ensuring that the appropriate level of technical penetration is attained during interrogation of designs. Refocus formal design reviews towards more programmatic issues and implement informal technical peer reviews staffed by competent designers and engineers who are not all directly involved in the design being reviewed. | Informal system and lower level design reviews can result in a superior design process which enables formal project reviews to be more focused on programmatic issues. | Refocus formal design reviews towards more programmatic issues and implement informal technical peer reviews staffed by competent designers and engineers who are not all directly involved in the design being reviewed. | JPL | 09/26/1997 | A JPL study of inflight problems (see reference below) on Voyager I and II, Magellan, and Galileo (up to late 1993) revealed that 40% would likely have been identified by better technical penetration in reviews of the detailed designs performed well before launch. An additional 40% (for a total of 80%) might also have been found by similarly in-depth reviews. As a result, JPL adopted the informal peer review process in order to ensure that the appropriate level of penetration was obtained by technical personnel qualified to adequately interrogate the designs. Informal peer reviews were conducted for the Mars Pathfinder, Mars Global Surveyor, and Cassini projects. Formal presentations were de-emphasized. Informal, but in-depth, discussions of requirements and designs were a more typical activity. Over the course of these projects, JPL review board membership was composed of technical peers with recent, directly applicable, subsystem experience. Peer reviewers were selected based on their knowledge of what questions to ask, how to probe an issue, and when an answer is satisfactory. Since formal reviews emphasize verification of the project status and attainment of milestones, their chief benefit lies in the investigative work performed in preparation for the review. In contrast, informal reviews feature detailed value-added engineering analysis, problem solving, and peer review. Reference(s): JPL D-11381, Flight P/FRs and the Design Review Process | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.1.1 ("Management Practices: Life Cycle") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.1 ("Flight System Design: General") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/03/1998
583 | Clark, K - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Clark, K - 0000000000 : NO@ADDRESS.GIVEN |  | Test Contingency Planning Should Consider Facility Power Interruptions (1996) | During a regional public service power outage, an unplanned facility power loss occurred during system level thermal-vacuum test of the Mars Global Surveyor. This resulted in a slight inflow of external unfiltered air into the propulsion system through its Ground Support Equipment (GSE) pressure control system -- a potential contamination concern. Test contingency plans and FMEAs for ground support equipment should consider responses to facility power interruptions. Test facilities should have devices to maintain a safe spacecraft environment in the event of a facility power loss. | Unplanned power interruptions during thermal-vacuum test may cause air backflow and possible contamination and/or damage of flight hardware. | Consider appropriate responses to facility power interruptions when developing test contingency plans and failure mode and effects analyses (FMEAs) for ground support equipment. Consider equipping test facilities with GSE devices which maintain a safe spacecraft environment in the event of facility power loss. | JPL | 02/17/1998 | [D] MGS Prepared in Vacuum Chamber for System-Level Testing Propulsion systems are normally kept at a net positive pressure. During a regional public service power outage, an unplanned facility power loss occurred during system level thermal-vacuum test of the Mars Global Surveyor (MGS). This resulted in a slight inflow of external unfiltered air into the propulsion system through its Ground Support Equipment (GSE) pressure control system -- a potential contamination concern. Examination of the propulsion test equipment GSE revealed that an open port on its vacuum pump relief valve allowed a small amount of room air back through its cold trap. Had a separate GSE solenoid valve been included immediately downstream of this vacuum pump, the propulsion system would have been safe in the event of total facility power failure. Because the backflow rate into the propulsion system was small and the cold trap temperature was not compromised, there was little concern for contamination. Gas sampling confirmed that there had been no significant contamination of flight hardware. Backup power was restored within one minute, and the system resumed operation as designed. Reference(s): Problem/Failure Report No. B0PE10 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 (quotEngineering Practices: Protection and Security of Flight Hardwarequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/03/1998
581 | Chamrad, Edward - 0000000000 : NO@ADDRESS.GIVEN | Chamrad, Edward - 0000000000 : NO@ADDRESS.GIVEN |  | Unstable Small Electronic Dynamic Load Banks Over Long Couple Distances |  | Load banks must be evaluated during development and test for reliable performance at coupling lengths equal to or greater than intended in the final test or operational configuration. | If use of this type of load bank is required, it is recommended that further evaluation to determine at what length coupling does the load bank performance become erratic. Also, it should be tested with the actual coupling required prior to utilization as a critical load. The reporter has reverted to use of resistive load banks with no recurrence of this phenomenon. | JSC | 12/22/1997 | During testing of a electrical power generating device known as a "fuel cell" it was discovered that the electronic dynamic load bank went into oscillations and became very unstable when an attempt was made to utilize it as a "load" for the fuel cell. During post test evaluation it was discovered that when these load banks are long coupled to the power supply their performance is erratic. When short coupled they perform as programmed. The question becomes at what length coupling does the problem occur. Presently evaluations were only made at three lengths: five (5) feet, twenty (20) feet, and forty feet per lead. At five feet no problems were noted, at twenty feet and forty feet the load bank was unstable. Research of available literature concerning this load bank does not reveal this problem. Consultations with the manufacturer indicated they were aware of some problems associated with small dynamic load banks using long coupling leads and that this is a characteristic of this type of load bank (small electronic dynamic load banks). This instability has been observed in small electronic dynamic load banks; larger dynamic load banks do not seem to exhibit this phenomenon, and resistive load banks are not prone to this phenomenon. The correlation of this phenomenon to the couping length is still under investigation. A Government-Industry Data Exchange Program (GIDEP) alert has been recommended. |  | N/A |  |  | Public | Not Specified |  | 01/30/1998
580 | Keprta, Sean - 0000000000 : NO@ADDRESS.GIVEN | Keprta, Sean - 0000000000 : NO@ADDRESS.GIVEN |  | Adherence to Manufacturer's Recommendations and to Established Procedures for Hazardous Operations (Plastic Cryogenic Tissue Storage Vial Burst Hazard) |  | Read and implement manufacturer's warnings on products. PPE must be worn when required and must fit the tasks to be performed. Periodic reviews of hazard analyses are capable of revealing any inconsistencies between planned operations and manufacturer's recommendations, protective safeguards, etc., prior to commencement of operations. | Hazard analyses be performed and updated, periodic safety reviews be conducted with all personnel working in the area, and standard operating procedures be checked against the warnings (including updates) provided by equipment vendors. Manufacturers tend to update warnings in their literature, both in catalog and on the data sheet shipped with the equipment when they discover hazards not previously known; such literature needs to be reviewed systematically for such new information. Identify and use suitable protective equipment to allow handling small cryogenic vials that might burst when removed from storage. | JSC | 01/12/1998 | A small plastic vial stored in liquid nitrogen burst while laboratory workers were inventorying and transferring vials from one dewar to another. During the transfer a vial burst, causing superficial cuts on the hands of two laboratory workers. The vial manufacturer had updated catalog and shipping documents to alert customers that the vials were not recommended for storage in the liquid phase of cyrogenically stored nitrogen. Instead, the manufacturer recommends that the vials be stored only in the gaseous phase of cryogenic nitrogen. The seal on the vials is not adequate to protect against seepage of liquid into the vial which could then burst following removal from the liquid unless adequate precautions were taken to allow the liquid to evaporate and escape slowly. Workers were not wearing the selected PPE at the time of the mishap. The PPE had been removed because it was too bulky to permit manipulation of the small vials. This directly exposed the personnel to low temperature hazards as well as the burst hazard from the cryogen stored vials. |  | N/A |  |  | Public | Not Specified |  | 01/16/1998
579 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Avoid Inadvertent quotHotquot Mates or Demates of Connectors (1996) | During integration and test of Mars Global Surveyor, the mating configuration for a power connector permitted a pin to short to ground. Use “scoop-proof” power connectors. Where possible, avoid mating or demating any powered connector, whether powered externally or by a spacecraft battery. | Where possible, avoid mating or demating any powered connector, whether powered externally or by a spacecraft battery. Use scoop-proof power connectors. quot Scoop-proof quot means that the connector's long shell design prevents inadvertent cocking of the mating plug connector into the mating receptacle. Such cocking can occur in other connector designs, causing physical damage to the pins or electrical shorting. [D] In the event of connector "mismates," scoop-proofing will also preclude the inadvertent partial electrical mating of differently keyed connectors. Positively isolate the power source or follow appropriate spacecraft battery discharge procedures whenever connectors are being mated or demated. | See Lessons Learned | JPL | 12/17/1997 | While mating two electrical power connectors during integration and test of the Mars Global Surveyor (MGS) Electrical Power Subsystem (EPS), a pin on one connector came into contact with the backshell (at spacecraft ground potential) on the other connector. Spacecraft external power was disconnected at the time, but the batteries were charged. A short occurred between a solar panel power return pin and the backshell. The event caused a transient energizing of the power system. The pin was isolated from spacecraft ground by a remote power switch. The shorting of the pin to ground provided a current path around the remote power switch, allowing the batteries to energize the power bus to no more than 22 volts. This short probably existed for only a few milliseconds and did not power any loads connected to the bus. The incident was attributed to the connector mating configuration-the exposed position of a corner pin during a slightly twisted entry. This event caused no damage to flight hardware due to the adequate surge rating of the blocking diodes and inductors. The corrective action was to add a test cable to the positive side of the battery allowing battery voltage to be interrupted prior to and during cable mating or demating. Where use of the test cable was not feasible (e.g., during spacecraft acoustic test), the solution was to discharge the battery prior to any mate/demate which could cause a turn-on transient. Reference(s): MGS Problem/Failure Report No. B0RE5V A related lesson is recorded in Magellan Battery Fire, Lesson Learned #4-112 (NASA LLIS #386) | JPL has referenced the lesson as supporting Paragraph 4.3.1.1 (quotPower/Pyrotechnics Design: General - Power System Grounding/Fault Tolerancequot) in the JPL standard quot Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles), quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 01/08/1998
578 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN; Lord, D - | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Cassini-Huygens Probe On-Pad Cooling Incident (1997) | After Cassini was mated to the launch vehicle, excessively high velocity cooling airflow blew insulation particles into the Descent Module. The responsibility for supplying cooling to the probe on the launch pad had been informally transferred from ESA to JPL without adequate control of the on-pad interface. Require that program decisions affecting interfaces automatically trigger a review of the need to change the IRD or ICD. Ensure that the verification methodology is thorough and considers responsibilities as well as requirements. | The Cassini-Huygens Probe review board identified a solution to each of two Interface Requirements Document (IRD)-related problems: The probe IRD was not updated when the responsibility for probe cooling was split between organizations. The specification compliance matrix failed to identify an inconsistency across the interface. End-to-end responsibility for elements within a given interface should reside within a single organization. Specifically, one single individual should be assigned responsibility for on-pad cooling (purge source, to purge outlet, to thermally controlled elements). | Require that program decisions affecting interfaces, whether made at the working group level or at program reviews, automatically trigger a review of the need to change the IRD or Interface Control Drawing (ICD). Ensure that the verification methodology is thorough and considers responsibility statements as well as requirements. | JPL | 12/10/1997 | On August 28, 1997, after the Cassini spacecraft was initially positioned on the launch pad and mated to the Titan IVB/Centaur launch vehicle, a cooling incident occurred which affected the Huygens Probe. During ground operations, cool air is injected into the probe to prevent internal heat build-up and damage to probe hardware. Prior to movement to the launch pad, cooling was provided without incident by a JPL cart. At the launch pad, cooling air was provided by the facility and routed to the probe through a diverter box provided by JPL, as shown in Figure 1. After mating Cassini to the launch vehicle, cooling air was supplied to the probe at approximately 0.26 kg/s (35 lbs/min). This air was routed to the descent module via the European Space Agency (ESA)-furnished ducting whose configuration and effects were not fully communicated. This produced a high-velocity airflow in the vicinity of internal probe insulation. It was later determined that the desired flow in that configuration was 0.04 kg/sec, and the air flow was adjusted accordingly. [D] Figure 1. Worst Case On-Pad Configuration To assess potential damage from the high airflow, a borescope was used to inspect the area inside the Descent Module (DM) in the vicinity of the air inlet. A tear approximately 5 cm long was seen on a Kapton blanket, along with evidence of foam insulation particles. The spacecraft was removed from the launch pad and returned to the Payload Hazardous Servicing Facility (PHSF) for removal and more detailed inspection of the probe. The probe was cleaned, repaired, re-verified, reinstalled on the spacecraft, and transported back to the launch pad. These unplanned activities resulted in a delay of seven days in the scheduled launch of the Cassini-Huygens mission. A failure review board concluded that, although ESA originally had responsibility for providing cooling air to the probe, the responsibility for supplying cooling to the probe on the launch pad was informally transferred from ESA to JPL without adequately defining and documenting nor implementing the resulting new interface requirement. Thus, no unambiguous assignment of responsibility for interface control existed. In addition, the internal probe cooling configuration at the launch pad, prior to backshell close-out, was changed without adequate review and coordination. These two factors resulted in excessive cooling air velocity within the DM, which caused the damage. Additional Keyword(s): Test & Launch Operations, Requirements Documentation Reference(s): JPL Problem/Failure Report No. Z44098 Cassini-Huygens Probe On-Pad Cooling Incident: Report of Formal Review Board, JPL Document D-15158, October 24, 1997 Probe Interface Requirements Document (IRD) PD-699-080 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.6 ( Engineering Practices: System Engineering) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 7, JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 12/16/1997
577 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN; Lord, D - | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Verify CAD/CAM Software Compatibility Between Organizations Before Proceeding to Hardware Fabrication (1995) | The Cassini Telemetry and Control module failed during functional bench test. This was due to an electrical trace errors generated during the apparently successful translation of PWB circuit design data from JPL CAD software to vendor CAD software. To prevent undesirable rework on flight hardware, this lesson suggests several steps to verify the net list, the vendor software compatibility, and the PWB. | Electrical trace errors may be generated during the apparently successful translation of PWB circuit design data from JPL CAD software to vendor CAD software. Such incidents on future "faster, better, cheaper" projects could have a significantly adverse effect on cost, schedule, quality and reliability. | To prevent undesirable rework on flight hardware: Use automated design checks or manual methods to verify the fidelity of the net list to the schematic prior to PWB design. Initially verify the compatibility of vendor CAD/CAM software generated interconnects with JPL circuit design net list CAD files before committing to PWB fabrication. Where cost and schedule allow, use a prototype PWB for complete verification via extensive continuity checking or functional testing of a populated board. | JPL | 11/17/1997 | Printed wiring boards (PWBs) for JPL spacecraft flight control systems are produced in the following sequential steps using specialized computer-aided design (CAD) software programs: Schematic Capture. A schematic diagram--a functional representation of the circuit design -- is produced by the JPL circuit designer using one CAD tool. Net List. A functional representation of the PWB interconnections may be generated by a different JPL organization using the same or a different CAD tool. The schematic is compiled to produce a "net-list," which identifies each set of nodes (i.e., set of pins on piece parts) to be electrically connected to form a "net." PWB Design. This net-list is transferred to a PWB design vendor along with physical descriptions of the piece parts. The PWB design vendor may use another CAD program to define the physical PWB layout, including placing and routing. PWB Artwork. Data files from this CAD program are then sent to an artwork vendor who may use yet another CAD program to create the PWB artwork. PWB Fabrication. The artwork and a fabrication drawing are sent to a PWB fabrication vendor to construct the PWB. Errors may be introduced in each step without any indication of CAD/CAM software incompatibility. The Cassini Telemetry and Control (T&C) module failed during functional bench test in June 1995. Inspection of artwork prepared by the PWB artwork vendor revealed three nodes connected to three other nodes in contradiction to the schematic diagram. The errors occurred in the conversion of the net-list, prepared by JPL using one CAD program, to the vendor artwork, which utilized a different CAD software program. Node reference numbers possessing common "suffixes" were interpreted as common nodes without discriminating between the differing "prefixes." The incorrect interconnection of certain gate outputs caused contention-type failures, disabling the telemetry processing circuitry. The corrective action performed by JPL was to rework the stray node connections with trace cutting and haywires, and to replace many parts which may have been damaged when the T&C module was powered for test. Additional Keyword(s): PWB Miswire Reference(s): JPL Problem/Failure Report No. 61810 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.17.2 ("Hardware Development") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 11/21/1997
575 | Lamonde, Brian - 0000000000 : NO@ADDRESS.GIVEN; Wheeler, Dave - | Lamonde, Brian - 0000000000 : NO@ADDRESS.GIVEN |  | Numerically Controlled (NC) Milling: Removal of Machine Debris |  | Removal of debris or waste must be verified during any automated or manual machining process. | Consider programming the milling sequence to allow for tabs (or other waste material) to be detached and verified as removed before making additional passes with mill.Verify that machining waste/debris will not accumulate or become entrapped in the product, tooling, or equipment and result in a hazardous condition during the machining operation.Ensure that training, procedures and instructions properly highlight this operational hazard. | JSC | 04/14/1997 | During the machining and removal of tooling tabs located in a small closed pocket on a bulkhead, one of the loose tabs became entrapped in an adjacent corner. The end mill subsequently struck this loose tab, causing ti eject, resulting in damage to the product. The damage was found to include a bent rib and an approximately 2-inch crack The operator was trained but inexperienced in this particular machining operation.Cutter path verifications using software simulations are useful for detecting most types of part / tooling collision programming errors, but they cannot anticipate how detached tabs (or other waste material or debris) may fall into the a pocket, tooling, etc., and be struck by the mill. On any automated (or manual) machining process, detached parts or debris must be accounted for so they do not hamper the process.Cost of rework estimated at $10K.Lesson Submitted from the Boeing International Space Station (ISS) Lessons Learned Database:from Boeing ISS dated 4/14/97, was entitled "NC Programming: Tooling Tab Removal"from Boeing ISS dated 4/15/97, was entitled "Bulkhead Damaged During Final N/C Milling" |  | N/A |  |  | Public | Not Specified |  | 10/31/1997
576 | Horn, Jim - 0000000000 : NO@ADDRESS.GIVEN; Martin, Matt - ; Clinton, Walter - | Horn, Jim - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Mechanical Stops to Restrict/Prevent Equipment Rotation/Movement |  | Use of limit switches or position indicators are better alternatives to mechanical stops to preclude excessive mechanical movement. | Limit switches and position indicators are better suited to provide the primary means to stop or limit movement of a rotating / moving device. System drives should not be designed or programmed to operate when a mechanical stop is engaged. Mechanical stops should be utilized only if excessive movement or rotation will result in damage to the hardware or fixture or result in unacceptable operational hazards. | JSC | 08/01/1996 | When a test fixture was commanded to rotate, the rotation machinery was actuated but the fixture failed to rotate. Visual inspection of the fixture revealed deformation and damage of several fixture components. The drive system had a mechanical stop in place to prevent over-rotation of the fixture cradle. Subsequent analysis indicated that the drive system had sufficient torque capability to overload the drive train should the drive train operate after the mechanical stop was engaged. Damage to the test fixture was estimated at $20K. Lesson Submitted from the Boeing International Space Station (ISS) Lessons Learned Database: From Boeing ISS dated 8/96, was entitled "Rotating/Moving Equipment Mechanical Stops" |  | N/A |  |  | Public | Not Specified |  | 10/31/1997
574 | Clark, Kevin - 0000000000 : NO@ADDRESS.GIVEN | Clark, Kevin - 0000000000 : NO@ADDRESS.GIVEN |  | Eliminate Potentiometers from Flight Critical Position Indicators (1995) | Potentiometers (pots) are low reliability items. Yet Mars Global Surveyor used 8 pots for confirming solar panel deployment that were non-essential, yet a single failure could have jeopardized the mission. Eliminate potentiometers from deployment designs unless intermediate position readings are essential and the spacecraft lacks a redundant sensor. | Eliminate potentiometers from deployment designs unless: Intermediate position readings are essential, and The spacecraft lacks a redundant capability for measuring deployment mechanism position. | See Lesson(s) Learned | JPL | 07/31/1997 | Mars Global Surveyor incorporated eight potentiometers (pots) used to confirm the position of the solar panels following their deployment away from the main body of the spacecraft. This event was the only time the eight potentiometers were needed in the mission. For each solar panel, the design permitted one of the two inherently low reliability devices to fail without losing the ability to ascertain mechanism position. If a potentiometer failed before launch, and a decision was made not to repair it, this could result in a mission critical single point failure. The flight computer would assume that the solar array had not been deployed and issue commands to reinitiate the deployment sequence. If this occurred at a late phase of the aerobraking maneuver, the mission could be jeopardized. The pots proved nonessential since body rate data generated in flight by the Attitude and Articulation Control Subsystem (AACS) provided quite accurate measures of solar panel deployment position. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5.5 ("Safety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisition") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.5.5 ("Flight Electronics Hardware System Design: Interfaces - Restricted Usage"), and Paragraph 7.1.4 ("Flight Scenario Design: Time Critical Sequence Priorities"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/29/1997
573 | Clark, K - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Clark, K - 0000000000 : NO@ADDRESS.GIVEN |  | Power Bus/GSE Sneak Paths May Energize Spacecraft in the Ground Test Environment (1995) | Due to the Mars Global Surveyor electrical power system design, a sneak path through GSE energized the spacecraft power bus, even though spacecraft battery power was disconnected. Locate the power interrupt on the positive side of the power system, design electronic subsystems and GSE for testability, and design circuits and interfaces to avoid sneak paths. | With certain spacecraft power designs, sneak paths through GSE may energize the spacecraft power bus, even with spacecraft battery power disconnected. | Locate the power interrupt (e.g., the Main Enable Plug) in the positive side of the power system with appropriate safety features. Design electronic subsystems and GSE for testability; design circuits and interfaces to avoid sneak paths which energize the spacecraft when it is intended to be in an unpowered configuration. | JPL | 08/07/1997 | The Mars Global Surveyor (MGS) electrical power system (EPS) design featured a switch on the negative leg of the battery for interrupting battery power. When this switch was opened to place the EPS (and thus the spacecraft) in the unpowered state, a blue light on the ground support equipment (GSE) power bus monitor remained lit, indicating that the spacecraft power bus was still energized. Examination of the design revealed that a residual voltage of almost 2 volts could be expected due to sneak paths both through the GSE grounding system and within the spacecraft telemetry system. Telemetry and control circuitry in the battery charger assembly (BCA), power supply electronics (PSE), and signal conditioning units (SCUs) provides multiple high impedance paths that bypass the main enable plug and the remote power switch and are manifested only in the ground test environment. In this specific design, these paths are necessary for normal flight operation of the power subsystem and command and data handling (C&DH) subsystem, but constrain pre-launch testability. The MGS design criteria define the circuit as "unpowered" with a voltage of less than one volt; a higher voltage could have caused: A stressed or blown spacecraft fuse which could have remained undetected. Inadvertent powering of the spacecraft bus without the knowledge of the test crew due to ground equipment. Burnt connector pins caused by scooping of the "D"-type connector shell during mate or demate. Reference(s): PFR #B0JK79 | JPL has referenced the lesson as supporting Paragraph 4.12.10.1 ("Flight Electronics Hardware System Design: Verification - Testability"), and Paragraph 4.3.2.1 ("Power/Pyrotechnics Design: Power Distribution - Load Removal") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/22/1997
572 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Damage to Bipropellant Main Engines from Premature Oxidizer Depletion (1997) | Premature depletion of one propellant can occur in bipropellant systems if engine and component acceptance test data are not properly considered when determining the flight propellant loads. Oxidizer depletion may be difficult to detect from accelerometer readings. The lesson suggests methods for (1) determining flight propellant loads and consumption and (2) determining the onset of oxidizer depletion and triggering burn termination. | Premature depletion of one propellant can occur in bipropellant systems if engine and component acceptance test data are not properly considered when determining the flight propellant loads. The level of dissolved gases in the oxidizer should also be considered. For nitrogen tetroxide/hydrazine engines similar to those intended for use in future planetary missions, oxidizer depletion may be difficult to detect from accelerometer readings because of (a) the residual thrust of the hydrazine operating in monopropellant mode and (b) random slugs of oxidizer which may continue to be ingested by the engine for tens of seconds after the first bubbles are ingested. | For bipropellant propulsion systems, ensure that supplier data on engine and engine component acceptance tests are used properly in determining the flight propellant loads and that consumption data are available to mission planners for use in accurately predicting the onset of oxidizer depletion. Be sure to verify the level of helium or nitrogen pressurant gas saturation in the propellants. If a method that time averages the reduction in acceleration from steady state values is used to determine the onset of oxidizer depletion and to trigger burn termination, select an appropriate threshold deceleration value based on actual test data. | JPL | 07/17/1997 | The first in a series of commercial geosynchronous satellites experienced abnormal operation of the bipropellant main engines following initial pressurization of the propellant tanks. Subsequent analysis of contractor test data on engine flows, previously unavailable to the customer, indicated an actual engine mixture ratio slightly higher than the ratio used to determine the propellant loading. This resulted in the depletion of the oxidizer about one minute prior to the end of the final burn required to place the spacecraft on station. The extremely large monopropellant burns required to compensate for the absence of oxidizer may reduce the mission life. The spacecraft was provided with two methods to detect oxidizer depletion: (1) a single accelerometer reading indicating acceleration below a manually set threshold and (2) multiple readings of acceleration values which are time-averaged at 60 percent below the last steady-state value. With the latter method active during the final burn, the depletion was not detected by the onboard software because the average acceleration did not drop below the 60 percent threshold. Severe line pressure oscillations, indicative of intermittent ingestion of oxidizer bubbles, indicated the main engines were still firing. The engines were allowed to operate in this abnormal mode for about 30 seconds before shut down was commanded by ground control to minimize engine damage. Additional Keyword(s): Engine Flow Test Data |  | N/A |  |  | Public | Not Specified |  | 10/22/1997
570 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | SCUBA hose failure |  | Color coding of similar connections is an effective method to ensure the correct assembly prior to use. | Color coding of similar connections is an effective method to ensure the correct assembly of equipment prior to use. Use only SCUBA regulators with different size fitting for high and low pressure outlets. Color code high and low pressure hoses for identification. Test to verify correct assembly. | JSC | 09/23/1997 | The low pressure buoyancy compensator flex hose failed when it was inadvertently attached to the high pressure port of the SCUBA regulator. When the diver opened the SCUBA bottle for a pre dive check the hose failed causing minor injuries to the diver. |  | N/A |  |  | Public | Not Specified |  | 10/21/1997
571 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Intergranular Corrosion of Austenitic Steels due to Nitriding/Heat Treating; Controls for hazardous liquid/vapor vent lines; Response to anomalous conditions during a hazardous test. |  | Improper heat treatment of stainless steel fittings used in systems containing corrosive fluids may sensitize the fitting materials to intergranular corrosion and cause leaks. Vapor vent lines for hazardous liquid systems must be designed to accommodate potential leaks of liquid into the lines. Using three-way solenoid valves to open hazardous fluid systems to vent for pressure transducer calibration introduces an unnecessary leak path and increases risk. | Periodically inspect and replace effected fittings in corrosive use. Use stainless steel fittings made of material other the 316 type stainless steel for hazardous fluid systems. ): Modify the system to enable it to safely accommodate component failures which could result in a liquid flow to the vent system. One design of the system which should be considered is a liquid trap capable of containing the amount of liquid which could potentially leak. | JSC | 09/23/1997 | There was an inadvertent release of nitrogen tetroxide (N2O4) at JSC on April 21, 1994 at Approximately 11:20 am. The release occurred in the Thermochemical Test Area (TTA) during the preparation phase of a simulated altitude test of a small bi-propellant rocket engine. The immediate trigger event was the failure of a three-way solenoid valve. This failure enabled liquid oxidizer (N2O4) to flow in a vent line and the oxidizer burner stack (which was used as a control device to burn off small amounts of N2O4 which might leak or be released from the system). As the system was being charged to the desired operating pressure of 800 psig, the leak rate increased and the burner stack was filled with liquid oxidizer and saturated oxidizer vapor. The system was initially charged to 850 psig, instead of the desired pressure of 800 psig, and was vented to reduce the pressure. Venting resulted in the release of a small cloud of oxidizer from the burner stack. Although this was an indication of anomalous system operation it was mistakenly attributed to an improper setting on the methane supply valve for the N2O4 burner, and test was continued. Other indications that the system was not operating properly were available in the control room, but were not noticed or were misinterpreted. A subsequent attempt to raise system pressure to 800 psig for the test caused the release of a large oxidizer cloud and percolated liquid oxidizer from the burner stack onto the ground area surrounding the burner, resulting in a spill. Subsequent to this incident, several fittings started leaking. Two fittings were successfully tightened, but attempts to tighten the third led to an increase in the leak rate. This fitting ( a mechanical Parker- type flareless, single ferrule fitting) was removed and sent to the materials laboratory for analysis. Leakage was attributed to the collapse of the ferrule component. The ferrule had clearly lost all of its functional integrity and separated into small fragments. All surfaces showed evidence of severe intergranular attack. Chemical analysis identified the ferrule as a 316-type stainless steel. Metallographic examination of a sample piece confirmed that gross intergranular corrosion attack of the ferrule material occurred. In addition, the examination suggested that the grain boundary sensitization may have occurred in the material, increasing the susceptibility of the ferrule to intergranular corrosion. Examination of other fittings removed from the system also revealed at least slight amounts of intergranular corrosion. Discussions with the manufacturer indicated that at least some of the ferrules had been nitrided, a process which may require extended times at temperatures of from 480 degrees C to 590 degrees C. Since austenitic stainless steels becomes susceptible when subjected to temperatures from 480 degrees C to 815 degrees C, the subject ferrules may have inadvertently become susceecptible during the nitriding process. |  | N/A |  |  | Public | Not Specified |  | 10/21/1997
569 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Interface Control and Verification | Problems occurred during Mars Pathfinder spacecraft integration and test due to out-of-date or incomplete interface documentation. The problem of communicating design details and changes across interfaces is a common industry problem. Employ a dedicated ICD engineer, ensure proper notification of interface changes, and avoid maintaining separate in-house and vendor ICDs. | The problem of communicating design details and changes across interfaces--mechanical, electrical, and informational--is a pervasive common thread across JPL projects and throughout industry. Assignment of full responsibility for interface control coordination to a single engineer, in conjunction with weekly Project Engineering Team reviews, results in an acceptable and cost effective engineering change control process. Mechanical Interface Control Drawings (MICDs) at all levels require periodic verification of accuracy and compatability, especially prior to any hardware fabrication. | Employ a dedicated engineer to assure that the hardware being built matches the ICDs. Ensure that cognizant engineers verify consistancy between their hardware and the MICDs/ assembly drawings, and provide proper notification of interface changes. Use vendor ICDs where applicable, but do not maintain two sets. | JPL | 10/09/1997 | The Mars Pathfinder (MPF) project operated under cost and schedule constraints. It employed new approaches for interface definition and control which produced both good and bad results. In simplifying the expensive serial engineering change request (ECR) process, a dedicated JPL interface control drawing (ICD) coordinator was responsible for change control and for assuring that interface changes were approved by cognizant engineers. In addition, the Project Engineering Team met weekly to review all changes. Problems occurred during MPF spacecraft integration and test, however, due to out-of-date or incomplete interface documentation: Electrical connector discrepancies were found between the MPF main wiring harness (delivered in July 1995) and 7 connectors on circuit boards in the Attitude and Information Management (AIM) subsystem. Investigation showed that the main wiring harness was built in accordance with MICDs which had not been updated after interfacing circuit board connectors were changed. This resulted in a connector mismatch--non-mating male-to-male and female-to-female connections. No power subsystem cabling was involved, and the discrepancies were corrected by retrofitting the cabling, or in some cases the boards, before any damage had occurred. For some hardware items, it was discovered that JPL and vendors had each prepared MICDs independently. Additional Keyword(s): Electrical Interface Control Drawing (EICD), Mechanical Interface Control Drawing (MICD) Reference(s): Muirhead, B., Mars Pathfinder Lessons Learned Presentations, April 17, 1997. Mars Pathfinder Problem Log, IR 043306. Mars Pathfinder ATLO Data Package JPL Common Threads Workshop Summary Report, JPL D-13776, May 31, 1996. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.6 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/16/1997
568 | Clark, K - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Clark, K - 0000000000 : NO@ADDRESS.GIVEN |  | Battery quotPoppingquot During ATLO (Assembly Test and Launch Operations) Due to Horizontal Mounting | During Mars Global Surveyor system test, it was discovered that horizontally mounted nickel-hydrogen battery cells are subject to electrolyte pooling in a 1 g. environment. This can damage the cells; high charge rates (and temperatures) increase the likelihood of damage. Some measures to prevent battery popping (rapid oxygen-hydrogen recombination under fast charge conditions) are recommended for nickel-hydrogen batteries during any ground phase. | A nickel-hydrogen battery design where the cells are mounted on their sides (i.e., horizontally), instead of in the vertical position shown in Figure 1, increases the potential for electrolyte quotpoolingquot in a 1 g. environment and for possible damage to cells. High charge rates (and temperatures) increase the likelihood of battery popping. | For nickel-hydrogen batteries, take precautions against battery popping during any ground phase: Reduce the charge rate as the batteries approach full charge. To minimize the likelihood of pooling, ensure that battery cells contain no excess electrolyte. Mount batteries to minimize electrolyte pooling in a 1 g. environment. | JPL | 08/27/1997 | Mars Global Surveyor (MGS) carries two nickel-hydrogen (NiH2) battery assemblies: one mounted to the +Y and one to the -Y propulsion module. Each assembly consists of eight 20Ahr NiH2 common pressure vessels (CPVs) in a honeycomb composite enclosure mounted on an aluminum baseplate. During MGS system test, shortly after installation of the batteries on the spacecraft, an intermittent popping or snapping sound issued from both batteries. This noise was most likely caused by oxygen-hydrogen (H2/O2) recombination in the battery under the fast charge rate conditions normally present throughout the charge cycle. H2/O2 recombination is a natural chemical process which occurs mostly during the late charge and early discharge stages of NiH2 battery operation. Audible popping occurs during H2/O2 recombination when a large enough oxygen bubble is allowed to form on an electrode plate inside the cell stack before it can recombine with hydrogen. When this bubble finally does recombine, a popping sound results. Such popping may induce significant damage to cell plates and may reduce battery cycle life. This phenomenon was exacerbated by the MGS practice of mounting and testing the battery on its side (i.e., horizontally) in a 1 g. environment. Instead of remaining fully contained within the porous electrodes, a small amount of the liquid electrolyte was drawn by the force of gravity to the bottom of the horizontal CPV. The liquid pressure from this pooling of electrolyte promoted the formation of oxygen bubbles large enough to recombine violently. Such pooling cannot occur in a zero g. environment. Use of the flight batteries was judged to represent a low risk to MGS mission success. X-ray inspection showed that the popping had caused some deformation of the cell plates. However, charge retention testing showed no degradation in battery performance, and the item features a heritage design and robust capacity. [D] Figure 1. NiH2 CPV Positioned Vertically (only the upper of two stack sets is shown) Additional Keyword(s): Battery Charging Reference(s): Problem/Failure Report No. B0M9XU Walker, S., Battery Noise Anomaly Close-Out Engineering Analysis, September 26, 1996 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.8 ( Engineering Practices: Design and Verification for Environmental Compatibility. ) in the Jet Propulsion Laboratory standard Flight Project Practices, Rev. 7, JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/10/1997
567 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Provide Software Checks On All Spacecraft Command Constraints (1997) | The Command and Control Subsystem for a commercial satellite lacked software command constraint checks. A gyro sensitivity setting that was incompatible with on-orbit testing of the thrusters resulted in a severe spin. Recommendations involve allowable command parameters, walk-throughs of critical mission command sequences, and use of a system testbed facility. | In keeping with "faster-better-cheaper" and multiple-flight mission operations support, commercial satellite service providers may operate spacecraft without a detailed list of flight operations command constraint checks. Instead of extensive ground simulation, the first of multiple crafts to be launched may serve as the flight test article. | Allowable command parameters should not permit exceeding spacecraft design capability. A walk-through of the design, implementation, and verification for critical mission command sequences, with certification by appropriate cognizant engineers, should be a required procedure. Use of a system testbed facility to simulate all spaceflight operations is encouraged. | JPL | 04/09/1998 | As a commercial geosynchronous satellite achieved its approximate final orbit, on-orbit testing was initiated to check out the on-board electronics suite. In one test, ground controllers rolled the satellite slightly off of its normal attitude relative to Earth to check the attitude recovery loops. The proper response was for the satellite thrusters to automatically fire a short burst to roll it back. In this instance, however, the satellite responded by firing the thrusters and continuing to fire until the satellite went into a flat spin. The centripetal forces induced by a flat spin can cause structural damage. The cause of this incident has been attributed to the failure of ground controllers to change the gyro sensitivity settings prior to initiating the test. The satellite gyros have two sensitivity settings—fine (0.6 degrees/sec.) and coarse (5.0 degrees/sec.). The gyros had earlier been set to fine sensitivity for the transfer orbit, and ground control neglected to change them back to the coarse setting for this test. To check the attitude recovery loops, ground control commanded 1 degree/sec. of roll. This roll rate exceeded the sensitivity of the gyros, inducing saturation of the attitude control electronics (they could not recognize any level above 0.6 degrees/sec.) and resulted in a severe spin. Command and Control Subsystem designers did not incorporate software command constraint checks: such checks would have prevented thruster firing with an incompatible gyro sensitivity setting. A contributing factor may have been human fatigue: multiple mission support was combined with this mission»s ambitious checkout schedule. Additional Keyword(s): Production-line Satellites | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.7.3.1 ("Management Practices: Spares, Testbeds, and Models"), and Paragraph 6.3.5.1 ("Engineering Practices: Mission Operations - Critical Events and First Time Events"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.4.4.6 ("Information System Design: Commanding and Sequencing - Commanding Reliability"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/09/1997
566 | Messore, Peter - 0000000000 : NO@ADDRESS.GIVEN | Messore, Peter - 0000000000 : NO@ADDRESS.GIVEN |  | Tethered Satellite System 1 Reflight (TSS-1R) Failure |  | The TSS-1R Mission Failure Investigation Board made several observations in the course of the investigation. Among these are that: the tether failure is not indicative of any fundamental problem in using electrodynamic tethers; there was a significant amount of scientific data secured from the flight, before the tether separated; the science, engineering and support teams were highly competent, motivated, and committed to the experiment; electrostatic charge build-up could be an issue in the future; the documentation provided by the project to the Board was appropriate; the tether configuration was affected by the winding loads on the reel; the load paths of the composite tether are complex; closed areas with a favorable pressure-distance combination (Paschen's Law) can cause arcing if not vented. The TSS-1R Mission Failure Investigation Board finally observed that the long time span between the fabrication of the hardware and the flight missions increased the exposure of the hardware to contamination and damage. | The TSS-1R Mission Failure Investigation Board made the following recommendations: use rigid standards for fabrication and handling of the high voltage cable; ensure that the deployer path is free of debris; reduce, through design and operations, the possibility of arcing; conduct electrical integrity tests as close to the flight date as possible; conduct high fidelity tests on critical subsystems; strengthen the integrated systems development approach. | MSFC | 05/19/1996 | On February 22, 1996, the STS-75 Space Shuttle Columbia was launched at 53/20:18 GMT. The orbiter was inserted into a 296 km (160 nautical mile) orbit at an inclination of 28.5 degrees. The crew consisted of 7 members, including commander, pilot, 3 mission specialists, 1 payload commander, and 1 payload specialist. The TSS-1R payload was a reflight of TSS-1 in 1994, where deployer mechanism problems limited the tether deployment to slightly less than 300 m. The planned duration of the flight was 14 days. The payload bay configuration consisted of the Tethered Satellite System (TSS) experiments, two U.S. Microgravity Lab pallets (USMP-3), Orbiter Acceleration Research Experiment (OARE) pallet, and Extended Duration Orbiter (EDO) pallet. Deployment of the satellite began at 56/20:46 GMT. On 57/01:29:26 GMT, at a tether length of 19.7 km, the satellite tether broke within the 12 m deployer boom, and the satellite separated from the orbiter. The rate of tether deployment was under control of the science computer. At the time of the tether separation, the deployment rate was being ramped down, per timeline, in preparation for halting at 20.7 km tether length. The tether deployment rate was approximately 1 m/s when it separated. There were no injuries and no damage to the orbiter or its subsystems due to the tether break. The orbiter was located at 2 degrees N latitude and 100.4 degrees W longitude, and was at an altitude of 296 km (160 nautical miles) at the time of tether break. The TSS-1R experiments were in the passive mode, with no current flowing in the tether. The tether had an electric potential of -3500 VDC with respect to the orbiter ground, as planned, during this mode. Telemetry from the orbiter and the satellite was operating prior to, during, and after the tether separation. Video imagery of the tether was available after the separation, but no video coverage exists showing the break itself. Video and still photography were taken during the mission of the failed end of the tether within the boom. The tether remaining in the boom was rewound on the reel during the mission. Post flight inspection of the tether end showed it to be charred, with an apparent final tension failure of a few strands of Kevlar. The TSS-1R Mission Failure Investigation Board established that the tether failed as a result of arcing and burning of the tether, leading to a tensile failure after a significant portion of the tether had burned away. Pictures of the frayed tether end The arc started in the Lower Tether Control Mechanism (LTCM), resulting in a 1 A current discharge to orbiter ground in the LTCM. This event occurred during a passive mode of science operations, with -3500 VDC on the tether conductor. The arc continued intermittently for 9 s, as the breached part of the tether traversed at 1 m/s through the remaining deployer mechanisms and into the 12 m deployer boom, where the space plasma provided the current return path. This arcing produced significant burning of most of the tether material in the area of the arc. The nominal load on the tether, 65 N (15 lb.), finally separated the tether at the burn location, while it was within the deployer boom. The upper tether section was pulled through the Upper Tether Control Mechanism (UTCM), away from the orbiter at a speed of 3 m/s, due to tether dynamics and the satellite movement away from the orbiter. The lower section of the tether remained within the boom, and was recovered after the flight. The arc initiated at a breach in the FEP insulation layer of the tether. Pressure within the LTCM, the proximity to a ground plane at the LTCM entry pulley, and the high voltage on the conductor, provided the favorable environment based on pressure-distant relationships (Paschen's Law)* for the conductor to arc through the breach in the tether insulation. Although the damaged area of the insulation was destroyed due to burning, the TSS-1R Mission Failure Investigation Board found sufficient evidence from test and analysis to establish foreign object penetration, or damage to the FEP insulation layer in manufacturing or handling, as the probable cause of the breach of the insulation layer. See the following videos: [D] The satellite and tether moving away from the shuttle [D] Scan of the boom with the slack tether in the shuttle cargo bay Manufacturing and inspection records show that the tether fabrication task was very difficult, and that numerous problems were encountered in the extrusion and braiding processes of this very long tether. The fabrication of the tether was carried out in a normal manufacturing shop environment. Metallic and non-metallic contamination was found within the FEP insulation layer of the flight tether, including the 9 m that had gone through the lower deployer mechanisms prior to the failure. Non-metallic and metallic contamination was also found between the Nomex and insulator layers of several samples of flight tether. EDS analysis revealed foreign material near the failed end. In addition to the contamination found within the tether, debris was found in several locations within the deployer mechanism. Metallic debris, large enough to breach the FEP, was found in the LTCM, the deployer boom assembly, and the reel housing. In the LTCM, a small piece of very fine silver plated wire, aluminum shavings, and unidentified non-metallic debris were found. Small metallic shavings were found attached to the back of small screw holes in the boom assembly. Damage to the copper conductor was found in both the returned flight tether, and in a section of qualification tether examined after a special spark test. This damage appeared to have taken place during fabrication of the tether. The final wind of the tether onto the flight reel was at a tether tension of 50 N. This results in high compression forces on the tether layers deep within the reel. The TSS-1R Mission Failure Investigation Board calculated that compressive forces at the layer where the tether breach was located, were as high as 35 N/mm for several days after the winding process. This compressive force is more than sufficient to force small debris through the insulation layer of the tether. The TSS-1R Mission Failure Investigation Board found one contributing cause was that the degree of vulnerability of the tether insulation to damage was not fully appreciated. A second contributing cause was high voltage effects on the insulator itself. Concern over the environment inside the LTCM led to the analyses involving Pashcen's Law relating voltage break down propensity as a function of the pressure-distance parameter. * - In 1889 Paschen introduced a generalization to the complex subject of gas break down in the law bearing his name. This law states simply that in a uniform field the sparking potential of a gas depends only upon the product of the gas pressure and the electrode separation. The TSS-1R Mission Failure Investigation Board was able to conclusively eliminate several major areas as causal. They included: Satellite Hardware and Operations Core Science Equipment and Operations Hardware and Operations of the Experiments Mission Operations (Ground and Flight) Induced Loads (static or dynamic) Pyrotechnic Tether Cutters Heating of the Tether During Commanded and Controlled Current Flow Design Changes Made to TSS-1 Aging of the Components (shelf life) Micrometeoroid or Orbital Debris Collision Electrical Storm Activity Reference(s): TSS-1R Mission Failure Investigation Board - Final Report, May 20, 1996. |  | N/A |  |  | Public | Not Specified |  | 10/01/1997
563 | Bopp, Charles - 0000000000 : NO@ADDRESS.GIVEN | Bopp, Charles - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Connectors |  | By not having ample cable length, excessive stress was applied to the threaded electrical connections causing misalignment. This left a false impression of thread engagement to be observed. Proper mating of the connection was wrongly assumed when tightening due to a cross-threading effect. | Implement electrical and/or mechanical modifications that will ensure proper electrical connection. Emphasize in the work authorizing documents specific procedures including verification steps to follow to prevent electrical connection mismating. Technicians performing tasks involving 480 VAC should not attempt to energize such a circuit unless they are absolutely sure the connection is positively made. Technicians should contact the responsible engineer, supervisor, safety engineer, etc., for back up verification if and/or when any doubt should arise concerning integrity of the connection. Issue a shop safety bulletin regarding the potential hazards associated with 480 VAC systems. Technicians should be educated on high voltage hazards and proper electrical connection techniques. | SSC | 09/08/1997 | A routine hookup and pump testing was being attempted on LOX barge #5 by Test Complex technicians. They were working under a process plan and standard operating procedure as required. The testing was necessary to functionally check the system after repair was performed. The technicians encountered difficulty in making a threaded electrical connection between the 480 VAC shore power cable connector and the LOX barge receptacle. The cable was insufficient in length to make a comfortable hookup. They pulled on it attempting to gain range by decreasing the slack in the line. Although they were successful in mating the connectors, the weight and angle of the cable applied undue stresses. The lead technician was under the impression the connection was adequate due to the fact the associated retaining nut felt to tighten by hand. A strap wrench was therefore used to further tighten the nut. When power was applied to energize the system, a high current arc was produced within the connection. The forces exerted by this arc resulted in the connector plug being forcefully ejected free from the receptacle. This action caused the connector plug to come in contact with the barge access ramp. The chain holding the associated aluminum connector plug moisture/dust cap was severed. The cap was then propelled and struck a technician working nearby behind the ear. |  | N/A |  |  | Public | Not Specified |  | 09/10/1997
565 | McGown, Matthew - 0000000000 : NO@ADDRESS.GIVEN | McGown, Matthew - 0000000000 : NO@ADDRESS.GIVEN |  | Mobile Crane/Preventive Maintenance |  | Failure to thoroughly inspect the mobile crane prior to use may result in damage to equipment, property, and loss of life. Failure to provide scheduled maintenance activities leads to the deterioration of equipment. | Inspect all mobile cranes to verify that each unit has a "Positive Mechanical Block (PIN)" in place before usage. Paint proof test due dates on the side of all mobile crane. This will facilitate confirmation of certification due dates. Establish a daily log to document visual inspection of certification due date. Establish monthly recall list of all lifting devices one month prior to proof test expiration. Ensure safety department continues to monitor all lifting devices regularly for current proof load certification. Remind all relevant SSC personnel of the importance for preventive maintenance/certification and following established procedures. Ensure that appropriate levels of heavy equipment are available to support a variety of site-wide projects. | SSC | 09/11/1997 | The mobile crane was holding a 20 foot section of 36" diameter pipe while a section of handrail was being removed. Removal of the handrail was necessary in order to remove the section of pipe. While the crane was in operation, one of the crane's outriggers "leaked down", and caused a brief uncontrolled movement of the pipe. No damage occurred to the equipment, and property surrounding the crane. Most importantly, there were no injuries to personnel. The crane was not equipped with a "Positive Mechanical Block (PIN)" system. Subsequently, it was found that the crane had not been proof load tested for over a year. |  | N/A |  |  | Public | Not Specified |  | 09/10/1997
562 | Beazley, Harold - 0000000000 : NO@ADDRESS.GIVEN | Beazley, Harold - 0000000000 : NO@ADDRESS.GIVEN |  | Testing With Removable Shrouds in the LaRC 8-Foot High Temperature Tunnel |  | When an object is ejected into the tunnel air stream, the mass of the object is as critical as its aerodynamic shape. Flight trajectories may vary significantly from their theoretical trajectory. | Ensure that the mass of objects and their credible trajectories are considered prior to placement into the tunnel for testing. | LaRC | 09/04/1997 | A model under test in the tunnel required the use of a removable shroud to insulate a sensor from heating while the model was being injected into the tunnel flow. Once the model was in the tunnel flow and was ready to collect data, the shroud was released from the model and ejected from the diffuser of the tunnel. The first test used a metal shroud that had been designed with air dams to ensure that it was not aerodynamic. The metal shroud was of sufficient mass and was ejected from the tunnel at sufficient velocity to cause the shroud to travel a long distance placing personnel in its potential path at unacceptable risk. A "catcher screen" was install but was not successful in capturing the metal shroud. The metal shroud was replaced with a wooden shroud. The wooden shroud provided the needed heat protection for the sensor and upon release, tumbled, contacted the diffuser walls of the tunnel and disintegrated. The pieces of the wooden shroud either came to rest before reaching the catcher screen or were captured by the catcher screen |  | N/A |  |  | Public | Not Specified |  | 09/04/1997
559 | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN |  | Redundant Verification of Critical Command Timing (1995) | When a new mission software release was uploaded to the spacecraft, the inflight upload failed to include a software patch that had been written to fix a defective countdown timer. Because an independent “watchdog timer” was planned, but never implemented due to constrained project resources, the thrusters continued to fire after the desired shutdown time and the mission was terminated. Recommendations centered on the need for rigorous software configuration management, a watchdog timer to terminate operations, and testbed verification of in-flight software updates. | Maintain a rigorous software configuration management program. Provide flight software with an independent watchdog timer to terminate operations which exceed the specified maximum time duration. Whenever possible, verify in-flight software updates in a testbed. | See Lesson(s) Learned | JPL | 05/29/1997 | Flight software for a recent mission included a safety feature in which the flight computer initiated a command sequence for enabling the thrusters. It also started a countdown timer which limited the duration of the burn. Flight software contained a known defect: whenever numerical computations produced an overflow, the calculations generated false results. When interplanetary mission software was uploaded following conclusion of the first science objective of the mission, the upload failed to include a software patch which had been written to fix the defect. When the thrusters were enabled for a spacecraft pointing maneuver, the flight computer performed calculations which generated a numeric overflow. A floating point interrupt occurred, and the processor generated erroneous commands affecting various spacecraft functions, including the propulsion subsystem and the countdown timer. With this timer not functioning, the thrusters continued to fire after the desired shutdown time. The 15-minute ground response to the fault allowed the loss of too much fuel to continue the mission. An independent watchdog timer*, redundant with the countdown timer, was planned but never implemented due to constrained project resources. Contributing Factors: Inadequate Operational Configuration Management. The functions of configuration management and software performance analysis and repair lacked adequate staffing. Inadequate Redundancy Design and Overflow Detection. Spacecraft hardware and software did not provide redundancy checking on the performance of software, such as fault protection monitors, to detect, diagnose and recover from an overflow condition. Insufficient Processing Capability. The spacecraft computer was selected chiefly for its physical attributes -- principally mass and radiation tolerance -- rather than for its computational power. The decision to omit a watchdog timer was influenced by this hardware limitation. Lack of Post-Launch Anomaly Analysis and Software Repair Capability. Only a single software development and simulation model was available for use by the flight project, and it was used continually after launch to generate flight sequences. This meant that the model was unavailable to generate software revisions to fix known bugs, so various software patches had to be uploaded throughout the mission. * Watchdog Timer: A software module which works in conjunction with a hardware time limiter to anticipate periodic receipt of a system health indication and, in the absence of such indication, initiates a system restart, interrupt, or return to a prior state. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.15.2 ("Engineering Practices: Configuration Management - Implementation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.11.1.1 ("Flight Software System Design: General - Software Architectural Design") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 08/13/1997
560 | Gounley, R - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Gounley, R - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Scan Platform Anomaly at Ida Encounter (1993) | A scan platform anomaly occurred shortly before Galileo's encounter with the asteroid Ida. Because the Galileo architecture did not provide for revolving, short-term storage of downlink data, ground control lacked insight into the cause of the incident. Missions should continuously buffer at least a small amount of high-rate telemetry as it is being downlinked at a lower rate. Storage of high-rate data for the period immediately preceding and following a fault would assist mission analysts in diagnosis of the problem. | Establish "First, do no harm" as the overriding principle guiding both fault protection design and the ground response to in-flight anomalies. Where it is not practical to record and downlink all telemetry, future missions should continuously buffer a small amount of high-rate telemetry as it is being downlinked at a lower rate. Should a fault occur, high-rate data for the period immediately preceeding and following the fault could be stored for later retrieval. This would assist mission analysts in real-time diagnosis of the problem. | See Lesson(s) Learned | JPL | 06/05/1997 | A scan platform anomaly occurred 5 hours before Galileo's August 1993 encounter with the asteroid Ida. During a quiescent period in scan platform activity, it unexpectedly jerked. The fault response sequence interpreted the high rate of scan platform motion as a spacecraft gyro error and turned off the gyros. The flyby continued in cruise mode, using star-based platform pointing. Although the low data rates available from the low gain antenna provided poor insight into spacecraft condition, ground control received indications of at least 5 more incidences of unexpected platform motion during quiescent periods over the next few hours. Ida encounter continued successfully with the gyros off and with no further signs of the anomaly. No conclusive explanation was found despite extensive ground testing and analysis and attempts to recreate the anomaly on the spacecraft. Consistent x-axis data from both gyros suggested that gyro hardware failure was improbable. Analysis did reveal that the anomaly would have aborted the imaging sequence had the additional power drawn during the slew been enough to cause an undervoltage condition. Instead, the first level fault protection (gyros off) allowed the sequence to continue imaging Ida. After the science data had been safely recorded and before the gyros were required, ground control was able to command them back on. This conservative, "first, do no harm" approach proved successful. The Galileo architecture did not provide for revolving, short-term storage of downlink data, which would have been useful in compensating for low telemetry data rates. Galileo telemetry provided data needed to troubleshoot the anomaly only once every two hours. Running intermittently, the tape recorder failed to capture any of the scan platform jerks. Subsequent to the Galileo era, some low data rate missions are being designed to provide for some storage of transient data to improve fault visibility to ground control. Additional Keyword(s): System Design, Transient Event Recording Reference(s): ISA 04013G | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.4.3 ("Engineering Practices: Mission Operations - Spacecraft Health and Safety, and Performance Analysis") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.4.6.1 ("Information System Design: Telemetry Visibility - Visibility of S/C Status") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 08/13/1997
561 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN; Kunstmann, G - | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager Plated - Through Hole Failures (1976) | During initial testing of multi-layer circuit boards for Voyager, defective copper plating was found to have caused cracks in the barrels of plated-through holes. Recommendations involve monitoring of fabrication processes, performance of thermal cycling screening tests, and use of test coupons. | If circuit board fabrication specifications or processes fail to provide for copper plating of the proper thickness and ductility, internal interconnect failures (such as cracks in the barrels of plated-through holes) may occur after only a few thermal cycles. Since this incident, research has indicated that the frequency of barrel cracking increases with increasing aspect ratio of the PTH (depth/diameter) as well as with decreasing barrel wall thickness. | Manufacturing, fabrication, and assembly processes employing complex technology require constant monitoring, auditing, and review of the appropriate process parameters despite repeated past successes. Even minor changes in processes or materials can result in the product falling below acceptable standards. Efforts must be made to increase the consistency and margin of all processes to preclude defects due to production variations. Thermal cycling screening tests should be performed on unpopulated printed wiring boards regardless of process maturity. Circuit board manufacturing processes should continue to use test coupons to determine individual board acceptability. | JPL | 07/30/1997 | In January 1976, a problem became evident during initial testing of the earliest Command & Control Subsystem (CCS) subassemblies for Voyager. Detailed testing revealed multiple, often intermittent, functional failures. The failures were traced to the multi-layer boards (MLB's), specifically the plated-through holes (PTH's). [D] The extent of the problem was determined by subjecting selected subassemblies to a detailed sequence of resistive measurements and temperature cycling. The sequence was designed to stress the PTH's without over-stressing the components installed on the MLB's. MLB fabrication documentation, test history, and theoretical analyses were reviewed. Failure analysis of hard failures, PTH's that exhibited early signs of failures, and PTH's which had appeared acceptable, revealed PTH copper plating that was marginal -- too thin and of insufficient ductility. This incident involved Viking board designs inherited by Voyager. The Voyager boards were fabricated 3-4 months later in a follow-on contract in which the same contractor presumably used the same specification and process. However, micro-photographs of the Voyager boards showed insufficient plating, and metallurgical tests showed insufficient ductility. A metallurgical test was subsequently performed on one of the earlier Viking boards: it showed the copper to be more ductile. Reference(s): quotMJS MLB Failure Investigation Report,quot June 1976. Voyager Problem/Failure Report No. 36970, Jet Propulsion Laboratory, opened 04/13/76, closed 01/18/77. Gibbel, M., quotSummary of JPL Printed Circuit Board Failures,quot Jet Propulsion Laboratory Document TETA-029, October 1995. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.3.3 (quotSafety and Mission Asssurance Practices: Quality Assurancequot) in the Jet Propulsion Laboratory standard quotFlight Project Practices, Rev. 7,quot JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 08/13/1997
558 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Migration and Differential Draw Between Multiple Propellant Tanks (1997) | Use of multiple tanks for a given propellant can introduce the potential for propellant transfer between tanks and cause unexpected shifts in spacecraft inertial properties and/or reduction of useable propellant. Where a propellant is stored in multiple tanks, design an appropriate set of pyro valves and latch valves to control propellant migration and differential draw. | Use of multiple tanks for a given propellant can introduce the potential for propellant transfer between tanks and cause unexpected shifts in spacecraft inertial properties and/or reduction of useable propellant. | Where a propellant is stored in multiple tanks, design an appropriate set of pyro valves and latch valves to control propellant migration and differential draw. | JPL | 07/17/1997 | Serious drawbacks have emerged from the propulsion subsystem design on a series of geosyncronous satellites impacting the on-orbit lifespan of a recent mission. The design uses four separate tanks for the hydrazine load, with a separate check valve for each tank in the pressurization system. Following each orbit-raising maneuver, and until the final burn, this results in propellant transfer from those tanks with check valves having the highest reseat pressures to the tanks with check valves having the lowest. Since orbit raising on this specific mission was done while spinning, this moved the spacecraft spin axis closer to the fuller tanks, which may have resulted in yet further propellant transfer. Differential heating or cooling of the tanks can add to the propellant migration problem. In addition to changing spacecraft dynamics, this transfer of mass may limit the spacecraft's on-orbit life because pressurant gas instead of propellant will be drawn from the first tank to be depleted, leading to early engine shutdown. For interplanetary spacecraft with a similar configuration, such as the Mars 98 lander, propellant transfer or differential draw during cruise may cause dynamic imbalance and/or reduction of useable propellant. Additional Keyword(s): Bipropellant Propulsion Systems |  | N/A |  |  | Public | Not Specified |  | 08/07/1997
557 | Bishop, D - 0000000000 : NO@ADDRESS.GIVEN | Bishop, D - 0000000000 : NO@ADDRESS.GIVEN |  | Test Requirements for Online Maintenance-Free Batteries (including Uninterruptible Power Supplies) |  | "Maintenance-Free" terminology is misleading; batteries do lose fluid. Manufacturer recommendation to perform a battery bank capacity test semiannually had not been performed consistently and reviewed. | Perform load tests (including battery bank capacity) as recommended by manufacturer and record the load and decay rate. Establish a replacement program to minimize battery failure potential; suggested guideline is when 50% capability is reached. The batteries should be replaced when the 'low level indicator' (usually set by the vendor) is activated (typically at about 50% battery capacity.) Personnel inspecting and servicing the UPS electrical and battery components should be protected with face shield, gloves, and acid apron. | JSC | 07/21/1997 | A "maintenance-free", lead acid battery, of the set in a Uninterruptable Power Supply (UPS) cabinet, exploded during normal operations. The investigation determined that the 6 year old cell was dry and failed internally; other batteries cells were found void of liquid, as well. Battery condition /capacity was not observable, due to the configuration with continuous supply of normal facility power keeping the batteries charged. Note: When contacting originator, please refer to Lessons Learned ER-LL-97-01 |  | N/A |  |  | Public | Not Specified |  | 07/22/1997
556 | Messore, Peter - 0000000000 : NO@ADDRESS.GIVEN | Messore, Peter - 0000000000 : NO@ADDRESS.GIVEN |  | Space Weather Media Blitz |  | Space weather has come to people's attention with the loss of the AT&T Telstar 401 satellite in January, and this seemed a reprise of that event, but with greater media play. The public noticed space weather reports. The media did not listen to the qualifiers that NASA interviewees attempted to put into their interviews. "This is the first time we have flown a telescope capable of seeing the phenomenon" got changed to "We have never seen anything like this before", allowing the inference that this would be the biggest event of all time. | ISTP (International Solar-Terrestrial Physics Project), including SOHO and NOAA will have procedures in place for the next event to coordinate information to the media. Also, media folks excited by NASA reports about solar events will be encouraged to confer with NOAA/SEC if the story involves likely terrestrial effects. If you have media interviewers, we suggest you encourage them to consult the Space Environment Center Home Page (www.sec.noaa.gov) for its assessment. This site took 142,000 hits on April 9, and includes statistics on how skillful are the Center's predictions. Both the NOAA and NASA public affairs officers will be engaged from the beginning of the media interest in future events. Some portions of the media have expressed embarrassment at the degree to which they inflated the story and missed the point that these were spectacular observations, because there were new sensors in orbit to see an ordinary event in new ways. There is some hope that educational efforts currently underway with the media will result in maintaining the increased sensitivity to solar-terrestrial observations and events, while ensuring more balanced and correct reporting next time. | GSFC | 04/07/1997 | On April 7, 1997 a solar flare occurred with an associated coronal mass ejection and a "coronal Moreton wave." These phenomena were seen in new and spectacular ways by instruments aboard the NASA/ESA SOHO spacecraft. NASA, ESA, and NRL scientists queried by the media were excited, and their excitement about the new observations led to media reports that a massive ejection had left the Sun (true), it would hit the Earth (highly probable), at a certain time (wrong), and cause damage and outages to technical systems (highly unlikely.) Meantime, NOAA's Space Environment Center (SEC), utilizing primarily the same types of data with which we have become familiar over the last several solar cycles, regarded the flare (C6 in soft x-rays and 3N in H-alpha) to be ordinary, the coronal mass ejection to be the expected garden variety, time of transit to Earth through slow solar wind to be long, and the terrestrial effects likely to be unremarkable. The unprecedented media saturation and attention gives to this event, and the "NASA predictions" (which NASA scientists did not make) appearing as an official government warning, caused many systems operators to be severely shaken, As on example, NOAA's Space Environment Center had a call asking if 747s scheduled to fly across the Atlantic should be kept on the ground at the predicted time of arrival of the storm. This lessons learned document appeared in the June 1997, International STEP Newsletter, Vol. 3, No. 2 and was written by: Ernest Hildner, Director, SEC Art Poland, Project Scientist, SOHO Nicola Fox, ISTP |  | N/A |  |  | Public | Not Specified |  | 06/24/1997
555 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Breathing air system/CO2 wash out |  | Significant air flow is required to adequately wash out the CO2 in a space suit. | Determine flow requirements for adequate CO2 wash out for space suit operations. Have warning systems for low flow conditions. Develop detailed control procedures and provide training and certification for breathing air console operators. | JSC | 06/17/1997 | During an Extravehicular activity training exercise involving pressurized operations in a Extravehicular Mobility Unit, the subject suffered symptoms of high concentrations of CO2. The primary cause of the physiological symptoms experienced in the training exercise was insufficient air flow to remove carbon dioxide from the facial area of the helmet in the space suit. |  | N/A |  |  | Public | Not Specified |  | 06/19/1997
554 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Recognizing and Controlling Thermal Hazards During Test Planning and Test Conduct |  | All potential hazards must be communicated to the test team (including the test subject) to enable them to identify and control the hazards. | Conduct integrated hazard analysis for all of the test systems and communicate this information to the test team for their awareness and control. EVA tools should be designed for low thermal conductivity to reduce the thermal hazard. | JSC | 05/28/1997 | During a thermal vacuum test with a subject in a space suit, the test subject received frost bite on his finger tips, while handling EVA (Extravehicular Activity) tools at -120 degrees F. Under specific conditions the subject in the space suit gloves can be subjected to low temperatures. The Extravehicular tools required difficult functional operation, resulting in extensive handling /contact time. The EVA tools had high thermal conductivity. The Space suit gloves have minimum insulation in the finger tip areas for increased touch and grasp capabilities. The ensuing investigation revealed that the test team had a low awareness that this hazard existed and that it needed to be controlled. |  | N/A |  |  | Public | Not Specified |  | 05/29/1997
553 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Communicating System Requirements |  | Positively Verify System and Component Specifications and Requirements Rather than Rely on Assumptions Derived from Professional Knowledge of Past Practices. | Always provide specific instructions to other organizations when you are requesting support or returning equipment. All materials installed in sensitive systems (such as oxygen systems) must be approved by competent technical authorities. Some organizations have the necessary expertise in house; other organizations should consult with experts such as the JSC Manufacturing, Materials, and Process Technology Division (mail code EM) or the White Sands Test Facility Laboratories Office either to review the materials or provide a referral to an alternate technical resource. Organizations that require gas sampling of potentially hazardous systems should ensure that approved procedures are available for the task and that employees are trained in the proper operation and hazards of the systems. The cleaning facility must be made aware of the required filter element type by each requester seeking an assembled filter housing for use in sampling procedures. The filter type/material should then be indicated on the paperwork and/or marked on the assembly provided to the requester. When uncertain about system requirements, treat it as a critical system! | JSC | 05/27/1997 | A particulate sampling filter was ruptured during use due to excessive differential pressure. The filter was in use in an oxygen system, and the Quality Assurance technician recording the sampling results noted that the failed filter element was not the type required for the procedure, as it was incompatible with the sampling being performed. The failed filter was not the type required by the users. The users had received the filter housing "cleaned and ready for service" from another organization. The type of filter element installed was not considered an issue, because both organizations used only one type of filter and presumed that it was the same type. The users thought that the filter was Teflon, which was normal for their use. The actual filter element was cellulose ester. In addition to being incapable of handling the differential pressure, cellulose ester filters are not recommended for use in oxygen service by the manufacturer. Manufacturing, Materials, and Process Technology Division (EM) has recommended a maximum service pressure of 20 psia for cellulose ester filter elements in oxygen service. |  | N/A |  |  | Public | Not Specified |  | 05/29/1997
552 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Potential Electrical Shock Hazard Involving Light Poles on Streets and in Parking Lots |  | Supplementary electrical grounding protection for streetlamp structures must be periodically verified. | All personnel should understand the electrical shock hazard presented by an energized light pole. Therefore, do not touch street or parking lot light poles! Immediate interim measures are being implemented, as follows: new ground rods are being installed on each light pole on-site, a temporary means of insulating the base of each pole is being examined a preliminary report has been requested that will make recommendations for permanent repair or replacement of the existing exterior lighting system. | JSC | 05/21/1997 | Several randomly sampled exterior street and parking lot light poles were found to have defective electrical grounds that could result in a potentially lethal electric shock hazard if the pole is touched by a person. The hazard is primarily a result of two conditions: The original design of the power distribution circuit lacked an equipment grounding conductor even though the installation met the National Electric Code at the time. The normal breakdown over time of the materials utilized in the supplemental ground rod which was installed to correct the original design deficiency. The poles are energized primarily at night, but can be remotely energized for testing and repair during daylight hours. Certain power distribution system failure modes may result in an energized light pole. While it is unlikely to have a combination of a defective grounding condition and a power system fault, the condition can be lethal if the pole becomes energized. However, the shock hazard can be precluded by the installation of an upgraded supplemental ground to the earth. |  | N/A |  |  | Public | Not Specified |  | 05/22/1997
550 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Oxygen-Deficient Atmospheres |  | Cryogenics are capable of displacing air, resulting in unbreathable, Oxygen-deficient atmospheres. | Follow your organization's procedures for handling of cryogenics. Operations with liquid nitrogen should only be performed using the buddy system and by experienced and qualified personnel familiar with the hazards and safety precautions. Resist the urge to rush in and rescue a downed co-worker; 60% of the confined space fatalities happen to the would-be rescuer. If rescue is necessary, use proper protective/breathing equipment. Confined Space Entry requirements and procedures must be followed when working with nitrogen in areas that are not well ventilated. Improve visibility through the use of portable ventilation fans to disperse the vapor cloud surrounding the operation with necessary. Consider use of portable oxygen monitors when working around cryogenic fluids. | JSC | 05/07/1997 | Two technicians were transferring liquid nitrogen from a vendor tanker to a tank trailer. Near the end of the operation, visibility was severely limited due to fog caused by venting nitrogen, leading to a decision to shut down the operation until the visibility improved. While shutting down the transfer operation, the technicians became unconscious due to lack of oxygen but recovered with no ill effects after being rescued by the tanker drivers. Technicians were wearing PPE for protection against frostbite, spills, etc., but did not include equipment to detect lowered oxygen levels or to supply breathing air. At JSC there are a large number of nitrogen containers. The areas surrounding the larger, permanent containers do not normally present pockets in which to trap nitrogen; however, on still days there could be oxygen-deficient areas near the connection the vent, or the 90% fill valve. The smaller portable containers (dewars) could be located in potentially confined areas, also presenting the potential for an oxygen-deficient atmosphere. | Safe Alert 1995 SA95013; NASA-JSC Mishap Report 950045 | N/A |  |  | Public | Not Specified |  | 05/14/1997
551 | Sinclair, Susan - 0000000000 : NO@ADDRESS.GIVEN | Sinclair, Susan - 0000000000 : NO@ADDRESS.GIVEN |  | Electric Power Off Button Design |  | Human factors and site analysis are important considerations when designing or modifying facilities and equipment. | Consider human factors when designing and installing power/equipment on/off switches/buttons. The EPO button was red and had a red sign above it - similar in appearance and coloring to exit buttons. The sign color has been changed to a color different than red to avoid confusion. An extra clip has been added to the button cover of the EPO buttons to make it more difficult to inadvertently push the button or to unconsciously lift the cover and push the button without being fully aware that it is an EPO button. | JSC | 04/18/1997 | An electric power off (EPO) button for computers was located in a room that required a button to be pushed to exit the room. An individual mistook the EPO button for an exit button and inadvertently cut off the power to the computers in the room. Had this happened during a flight or critical simulation a great deal of data and monitoring could have been lost. |  | N/A |  |  | Public | Not Specified |  | 05/14/1997
542 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Use of RGA Quadrupole Mass Spectrometer for Leak Detection |  | It is possible to not have a 5:1 ratio of N2 to O2 in a vacuum chamber that has a steady leak, when there is a cryopump running that will preferentially pump the O2. | When using gas ratios based on a quadrupole mass spectrometer (RGA) to tell you if you have a leak (i.e., looking for 5:1 ratio between N2 and O2), make sure you do not have a pump running that is pumping one gas preferentially (such as an ion pump or cryopump). | LaRC | 04/01/1996 | On the MIDAS project, leak detection for the vacuum chamber was done both by helium "sniffing" using the RGA, and also by checking the N2 to O2 ratio to see if there was a steady air leak present. In one case, this ratio did not indicate a leak, because the cryopump was preferentially pumping oxygen. | When using gas ratios based on a quadrupole mass spectrometer (RGA) to tell you if you have a leak (i.e., looking for 5:1 ratio between N2 and O2), make sure you do not have a pump running that is pumping one gas preferentially (such as an ion pump or cryopump). | N/A |  |  | Public | Not Specified |  | 05/05/1997
541 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Vacuum System Load and Ion Pump Selection |  | If a complete tally of all vacuum loads is not done before a pump is selected, the pump chosen may be over- or under-powered for the job. | For vacuum systems, plan the load that will be on the pumping system by calculating all the surface areas of all materials exposed to the chamber, figuring the pressure load due to those materials based on their condition and tabulated values of outgassing (can be found in several references). Add in loads due to leak rates. Then add some safety factor, and any de-rating of the pump necessary for temperature, power available, or aging, before selecting a pump for the chamber. | LaRC | 02/01/1996 | On MIDAS, an ion pump was purchased to be the maintaining pump on a chamber before all vapor and leak loads within the chamber were calculated (or measured). This resulted in the ion pump being at its maximum pumping capacity during normal operation. |  | N/A |  |  | Public | Not Specified |  | 05/05/1997
544 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Early EMI Testing At Component Level |  | When you have a part that is a possible suspect for EMI, always test it separately for EMI as early as possible, rather than waiting and testing the whole payload and finding out then that you have to change one component. This can be an informal test in a local facility, and not require money, excessive procedures, or time. | See Lesson(s) Learned field for Recommendation(s) | LaRC | 04/01/1996 | MIDAS EMI testing was only done at the experiment assembly level, and when problems were found it required extensive re-work. |  | N/A |  |  | Public | Not Specified |  | 05/05/1997
543 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | EMI Filter Selection |  | An EMI filter may not perform as well when it is not matched with the power converter it is meant to operate with. | When designed for EMI 'cleanliness', power converters and EMI filters should be matched: bought from the same company and in the same series. | LaRC | 04/01/1996 | The original EMI filters on MIDAS were not matched with the power converter, and were not successful in keeping the EMI below the required level. |  | N/A |  |  | Public | Not Specified |  | 05/05/1997
547 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Requirement for Stalled-Rotor Power in Worst-Case Thermal Analysis |  | Worst-case thermal analyses must include locked-rotor conditions of any moving parts. | Whenever the thermal analysis is supposed to be worst case, or include component failure, make sure that any fans or rotating parts included stalled failure power (power that a stalled rotor draws), and not just a normal worst-case maximum power. | LaRC | 06/01/1996 | On the MIDAS project, thermal analysis for the Shuttle locker payload was performed without the fan in the locked rotor condition (maximum heat dissipation). |  | N/A |  |  | Public | Not Specified |  | 05/05/1997
548 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Habitable Compartment Offgassing Test for Shuttle Middeck Payloads |  | All Shuttle middeck payloads have to have the habitable compartment offgassing test done on them (LaRC payloads MACE, GPPM, MIDAS had this done at White Sands) -- check with JSC Safety if unsure. It is possible to send a mock-up unit only, that only includes the same non-metallics as are in the flight payload, but does not have to be operational. | Plan your offgassing test early, and determine if you can send a mock-up or whether you have to send a flight-like item. | LaRC | 04/01/1996 |  |  | N/A |  |  | Public | Not Specified |  | 05/05/1997
545 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Ion Pump Recommendations: Baking, Ion Gauge Use |  | If a system is baked with the ion pump off, the contaminants driven off of the chamber walls during baking may be driven into the pump, and it will then take quite a while to be able to restart it. If the system is not baked sufficiently, then the act of turning on a vacuum ion gauge will drive so much water off the walls of the chamber and gauge that the ion pump may not be able to continue running. | Ion pumps like to run as much as possible. If one is having problems or not stabilized, keep running it. Also, if you bake a system with an ion pump on it, keep the ion pump running during the bake. Bake the system to get water off the walls (especially if you will be running an ion gauge). | LaRC | 04/01/1996 | The MIDAS ion pump was at the top of its load rating when it was pumping the vacuum chamber. When the chamber was baked, the ion pump went out of range, so once the pump was turned off during this bake, on a prototype unit. This is not recommended for optimum pump operation. Also, when the ion gauge was operated, the pump would go out of range, which was due to water being forced off the walls. |  | N/A |  |  | Public | Not Specified |  | 05/05/1997
546 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Venting Design for Small Pressure Changes |  | Even if pressure changes will be extremely small, have vent holes designed in everything by CDR. | It is easier to design venting into the system in the first place than answer questions about what the maximum pressure change might be, and re-design parts to include venting later. | LaRC | 04/01/1996 | The MIDAS experiment was designed for one atmosphere pressure, and thus venting was not seen as a requirement and was not designed in. However, the specified minimum and maximum pressures on Shuttle and Mir would have produced a potential maximum pressure difference of 4 psi in the worst case. Venting was back-designed into the system after the fact, when this was determined. |  | N/A |  |  | Public | Not Specified |  | 05/05/1997
549 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Utilize Project Web Page |  | Web page archival can be beneficial for the project in terms of communication (both internal and with other centers and HQ), helpful in getting industrial partners, and facilitates transition of personnel since past history is documented. | Whenever possible, keep an archival of project information available electronically - might include requirements documents, procedures, drawings, materials lists, lessons learned, design decisions, analysis performed, photos, lists of publications, and historical or background information. Access to parts of this information can be restricted if necessary. | LaRC | 03/01/1997 | MIDAS instituted a Web page of all project information -- documents, photos, drawings, and an appeal for commercial partners. |  | N/A |  |  | Public | Not Specified |  | 05/05/1997
538 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Place Wire Paths, MLI Blankets And Other "Soft" Items On Assembly Drawings |  | Soft items which do not seem capable of creating interferences may actually lead to crucial conflicts which are only caught in assembly or testing because they were not shown on assembly drawings. | Always indicate wire paths and MLI blankets on top-level assembly drawings and anywhere else appropriate, to help identify potential interference and obstruction problems before assembly starts. | LaRC | 05/01/1996 | Several wire bundles and MLI blankets were not explicitly shown in the MIDAS top-level assembly drawing. This made it difficult to assemble the materials list, and also allowed a blanket interference to go unnoticed since the blankets were not shown on the top-level drawing. |  | N/A |  |  | Public | Not Specified |  | 05/03/1997
535 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Design of Bonded Parts for Cryogenic Temperatures |  | When parts have different coefficients of thermal expansion (CTEs), the shrinkage created when they are taken down to cryogenic temperature will not only produce a shear stress in the epoxy bonding them together, but it can also produce bending stresses if the mounting design is not carefully planned for cryogenic temperatures. | When a bond will be taken to cryogenic temperatures, carefully evaluate all possible stress conditions. This includes those that could be caused by a part being at its maximum tolerance for dimension or position, which could cause it to impinge on another part when cooled. | LaRC | 11/01/1996 | On MIDAS, thin ceramic boards (1-inch x 1-inch x .030-inch thick) were bonded to a 1-inch hollow copper cube. The bond was cured at 75C, and then the assembly was cooled to 75K for operation. It was found that some boards would shatter for what seemed like no reason, even though an identical procedure was used for ones that survived many cycles undamaged. It was eventually found that the stresses on the boards were intimately related to their exact mounting configuration. If the boards were mounted on the cube such that two edges were in contact, the shrinkage created by taking the assembly down to cryogenic temperatures caused the edges of the boards to push on each other and stressed the boards to failure at the edges. Thus, testing the epoxy by bonding substrates to flat copper test pieces was not sufficient to ensure a successful bond. | When the MIDAS cube was assembled with the boards not in contact, so that no stresses would be produced during shrinkage, the boards did not shatter during cooldown. | N/A |  |  | Public | Not Specified |  | 05/03/1997
536 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Clean Room Certified Adhesive Tapes: Silicone vs. Acrylic |  | Clean room certified adhesive tape 5413 looks just the same as clean room certified adhesive tape 1205, but 5413 contains a silicone-based adhesive that is not compatible with vacuum work. 1205 has an acrylic adhesive that can be baked to reduce outgassing. | Carefully evaluate proper tape to use for each situation, and take steps to ensure that incorrect tape cannot be used. | LaRC | 05/01/1996 | Clean room certified adhesive tape 5413 was used inadvertently in construction of multi-layer insulation (MLI) blanket for a vacuum chamber (instead of clean room certified adhesive tape 1205). The two tapes look virtually identical and are packaged similarly. | Clean room certified adhesive tape 1205 used for MLI; bakeout and pumpdown times much reduced. | N/A |  |  | Public | Not Specified |  | 05/03/1997
537 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | O-Ring Manufacture for Vacuum Sealing |  | The best O-ring seal is attained with a commercial O-ring or one with a 45° angle joint. Do not assume that a fabrication shop will put a 45° joint in automatically -- they may have no way of knowing that you are going to use it for vacuum use. | For O-rings that must make a good vacuum seal, buy them commercially or make sure the person making them is going to put a good 45° angle on the joint -- butt joints will leak. | LaRC | 05/01/1996 | O-ring manufactured on MIDAS for vacuum seal was made with butt joint instead of 45° angle joint. | Commercial O-rings gave a much better seal than ones fabricated with butt joint. | N/A |  |  | Public | Not Specified |  | 05/03/1997
539 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Safeties on Man-Accessible Panels |  | Everything that is accessible to astronauts or ground crew must have safeties designed in to guard against inadvertent activation. | Design safeties into everything on a panel that is accessible to astronauts -- covers on breakers, etc. | LaRC | 05/01/1996 | Front panel of a locker designed for use on Mir and Shuttle did not originally have safeties on breakers. |  | N/A |  |  | Public | Not Specified |  | 05/03/1997
540 | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN | Amundsen, Ruth - 0000000000 : NO@ADDRESS.GIVEN |  | Hermetic Connector Purchasing/Shipping |  | If you do not specify on your purchase order for hermetic connectors, it is possible that they will be shipped with the inserts loose. | When ordering hermetic connectors, make sure you specify that they are to be shipped with the inserts installed. | LaRC | 02/01/1996 | On MIDAS, the hermetic connectors purchased were not specified on the LaRC PR to be shipped with the inserts installed, and thus the inserts had to be installed by project personnel. This is a tedious procedure, and one that can cause damage to the connectors. |  | N/A |  |  | Public | Not Specified |  | 05/03/1997
534 | Lewis, Philip - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Philip - 0000000000 : NO@ADDRESS.GIVEN |  | Materials Compatibility: Verifying Design Acceptability Prior to Manufacture and Distribution of Hardware |  | Material incompatibility issues, as well as material compatibility reviews, should be conducted and approved prior to the shipment of any flight hardware. | Review of the MIUL's must be accomplished by knowledgeable personnel (such as Materials & Processes experts) familiar with the hazards of the working environment. | JSC | 04/11/1997 | Space Station Oxygen quick disconnects (QD's) used silicon grease in the flow path of moderate to high pressure oxygen. The auto ignition temperature for this grease is 500 degree Fahrenheit and with pressures of 200 psia and above, adiabatic compression could have caused this grease to ignite, resulting in a catastrophic event on board. The material rating of the silicon grease stated in the Material Identification Usage Agreement (MIUL) was for 30% or less Oxygen concentrations at 14.7 psia or lower pressures, and not that of 100% O2 at elevated pressures. The vendor failed to observe that the test environment used to determine the MIUL rating as listed in the Materials and Processing Technical Information System (MAPTIS) did not match the actual operational environment. The error was caught by NASA materials and process engineers and representatives of Safety, Reliability, and Quality Assurance, but not before some of these QD's had already been shipped for installation in Node 1. |  | N/A |  |  | Public | Not Specified |  | 04/16/1997
533 | Clark, K - 0000000000 : NO@ADDRESS.GIVEN; Oberhettinger, D - | Clark, K - 0000000000 : NO@ADDRESS.GIVEN |  | Concurrent Engineering Benefits for Low Cost, Short Duration Missions (Teaming of Disciplines) (1996) | Planned NASA missions will require rapid design and development techniques to reduce costs and shorten schedule times. Mars Global Surveyor represented a transitional project that provided several concurrent engineering lessons. Lessons learned involve reliability engineer collocation with designers, effective teaming with industrial partners, and formation of competent concurrent engineering teams. | Collocate reliability engineers with designers. Maximize teaming between industrial partners and JPL by meeting requests for direct JPL support with identified JPL strengths. Establish a JPL project organization which reflects the industrial partner's functions to provide significant economy in communication, technical interchange, and reporting. Provide concurrent engineering teams with the right mix of technical disciplines to review the development approach and monitor progress. |  | JPL | 03/27/1997 | NASA envisions smaller, cheaper, and more frequent space and Earth science missions with highly specific goals. Many of these missions will require new types of spacecraft that will be created using rapid design and development techniques to reduce costs and shorten schedule times. Spacecraft and instrument designers will evaluate design options in an environment in which the engineering and design of flight and ground systems can be done concurrently. Mars Global Surveyor (MGS) represents a transitional project which provided several concurrent engineering lessons: Collocation of a dedicated reliability engineer with the designers significantly increased communication and facilitated rapid resolution of reliability issues. Design analyses and their review were focused and efficient. The industrial partnership between JPL and the prime contractor was very effective. Much of the effort JPL typically spends on oversight was instead dedicated to direct partner support in many important areas (e.g., parts, gyros, structures, solar array). A JPL project organization which generally mirrored that of the industrial partner improved communication, technical interchange, and reporting. Insufficient concurrent engineering between the electrical and mechanical engineering disciplines led to specific issues. Numerous problems were encountered with High Gain Antenna (HGA) encoder design and with electrical and packaging processes. The inherited Dual Temperature Controller (DTC) was misapplied, resulting in failure and complete redesign. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.3 ("Engineering Practices: System Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 04/04/1997
532 | Stanford, John - 0000000000 : NO@ADDRESS.GIVEN | Stanford, John - 0000000000 : NO@ADDRESS.GIVEN |  | Improper Facility Planning and Utilization |  | Before locating people in an area specifically not designed for Personnel occupancy, conduct a joint review by appropriate Facilities Engineers and Environmental (Occupational) Safety and Health Engineers. | Assure that the problem of using facilities not originally designed for human occupancy receives a review by top level management. Assure that the health and well being of the occupants receives top priority during initial planning. Have Facilities Engineers and Safety and Health Engineers prepare options to relieve the problem and present to top management as part of an overall site strategy for personnel relocation. Refer (for review) any other such planned move to the appropriate Facility Configuration Management official. | JSC | 03/21/1997 | Due to overall dwindling budgets and severe cutbacks in operational budgets, onsite space is being used whenever possible to house personnel and operations to avoid renting offsite space. In this instance, personnel were located in sections of two buildings designed for main frame type computers. People began to complain about headaches and other ailments as well as the conditioning of the air in these locations. Carbon dioxide concentrations in these areas were evaluated and found to exceed the 1000 ppm recommended by the American Society of Heating, Refrigerating, and Air Conditioning Engineers, Inc. (ASHRAE). ASHRAE 62-1989, "Ventilation for Acceptable Indoor Air Quality". Carbon dioxide concentrations exceeding 1000 ppm indicate insufficient make-up air and the possibility of build up of other indoor contaminants. |  | N/A |  |  | Public | Not Specified |  | 04/04/1997
531 | Clem, Daniel - 0000000000 : NO@ADDRESS.GIVEN | Clem, Daniel - 0000000000 : NO@ADDRESS.GIVEN |  | Reporting Close Calls is Important |  | If someone had reported the first close call, the second one may not have happened. Promptly reporting close calls and taking corrective action prevents injuries. | Emphasize the importance of reporting close calls. Make it easy for employees to report close calls. | JSC | 03/30/1997 | An employee walked into a board with nails that was sticking out of the back of a pickup truck. The employee only suffered minor cuts and scratches to the face, but could have injured an eye. Someone else had almost ran into this board earlier, but no one reported the close call. After the close call was finally reported, action was taken to remove the hazard. |  | N/A |  |  | Public | Not Specified |  | 04/03/1997
514 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Intensity-Modulated Fiber Optic Microphone for Obtaining Measurements of Pressure Fluctuations in Hypersonic Flow Fields |  | The recent availability of high-temperature optical fibers makes the intensity- modulated fiber optic microphone a promising instrument for obtaining measurements of pressure fluctuations in hypersonic flow fields. | For a complete description of an intensity-modulated fiber optic microphone, see the paper, "Fiber Optic Sensor for Measurements of Pressure Fluctuations at High Temperatures", by Allan J. Zuckerwar, NASA Langley Research Center. The paper appeared in the ICIASF '89 Record. | LaRC | 08/02/1994 | The measurement of pressure fluctuations in hypersonic flow fields is much more demanding on dynamic pressure sensors than in traditional acoustical applications. Essential sensor specifications for measurement of pressure fluctuations in hypersonic flow are small size (<0.02 in.), height temperature (20000F), frequency response (200 kHz), and 0.01-10 PSI dynamic range. The recent availability of high-temperature optical fibers makes the intensity-modulated fiber optic microphone a promising instrument for obtaining these measurements. Small sensor size is desirable to obtain high frequency response and to reduce spatial averaging errors due to the finite size of the sensor. In order to minimize the correction factors needed to account for the latter, it is desirable to have a sensor diameter at least as small as 0.02 in. For measurements in hypersonic flow. One of the predominant considerations in hypersonic flow is the high-temperature environment to which the sensors will be exposed. Thus, materials used to fabricate such sensors must be stable in the attendant environment. Sensors whose transduction is based on a material (piezoelectric, piezoresistive, magnetostrictive, etc.) Cannot meet the high-temperature requirement with current technology. The condenser microphone has an inherent small-size limitation due to loadings by cable capacitance; further, if a polarization voltage is used, then the necessarily close proximity of the preamplifier to the microphone cartridge will preclude operation at high temperatures. The recent availability of high-temperature optical fibers makes the intensity-modulated fiber optic microphone a promising instrument to fulfill the above requirements. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
511 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Placement of Aluminum Oxide Grit on Tape Aft of Nose on a NASP Forebody Model Caused Boundary Layer Transition |  | Placing various size aluminum oxide grit on one inch wide kapton tape, two inches aft of the nose on a NASP 17-inch forebody model, caused boundary layer transition. | A more detailed investigation to quantify the effects of roughness, simulated using aluminum oxide grit, will be conducted in the 31-inch mach 10 tunnel. | LaRC | 07/27/1994 |  |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 04/02/1997
513 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Moisture Contamination from the Initial Electronically Scanned Pressure (ESP) Systems Module Destroyed all Remaining ESP Modules |  | The reference cavities for all ESP modules are connected to a common vacuum source; if this common vacuum source becomes contaminated with moisture from the initial ESP module all remaining ESP modules can be destroyed. | Ensure that high pressure tubes are correctly connected to the proper high pressure module ports by maintaining thorough tube labeling and verifying that tubes are labeled correctly after every instrumentation change. Examine tubing paths between measurement orifices and sensor ports, looking for potential interfaces with fluids other than dry, clean, inert gas. Always leak check sensors with vacuum only. | LaRC | 07/29/1994 |  |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
512 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Increased Understanding of the Effects of Lightning Strikes on Aircraft |  | NASA LaRC research has significantly increased understanding of the effects of lightning strikes on aircraft. | Information concerning this project is contained in the article, "Aircraft Jolts from Lightning Bolts", authored by Felix L. Pitts and Bruce D. Fisher of NASA Langley Research Center, et al., In the July, 1988 Institute of Electrical and Electronics Engineers (IEEE) Spectrum. | LaRC | 07/29/1994 | Since 1960, the NASA Langley Team has flown a NASA-owned F-106B airplane through thunderstorms about 1500 times at altitudes between 5000 and 40000 feet (1500 to 12000 meters). The airplane, lightning-hardened and outfitted with special instruments, was hit by lightning 714 times. Ground-based NASA RADARs located across the Chesapeake Bay on Wallops Island, Va., Were used to guide the airplane into the upper, and most electrically active, regions of thunderstorms. Considerable attention was paid to protecting the crew during these potentially dangerous missions. When lightning strikes an airplane, it may take more than a second before the extremely fast and interactive electromagnetic effects die away. Currents between 10000 and 200000 amperes may flow through the airplane's metal skin, setting up electromagnetic fields that may propagate into the airplane's interior through open apertures, diffusion, or other mechanisms. Among other significant findings, this research produced data that was the first to actually capture an airplane in the act of triggering a lightning flash. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
502 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | External Thermal Barrier (ETB) Retainer as a Potential Single Point Failure |  | The Safety Analysis Report (SAR) System failed. If the ETB retainer had been identified as a potential single point failure, preventive measures could have been taken to prevent this mishap. | This mishap was formally investigated, the failure causes identified, and actions recommended to be taken to prevent a like occurrence. | LaRC | 07/08/1994 | The National Transonic Facility (NTF) is a transonic wind tunnel primarily intended to provide a high Reynolds Number test capability for aerodynamic research and the development testing of commercial and military aircraft configurations. On 1-18-89, the NTF experienced a Type A mishap, resulting in irreparable damage to all 25 fiberglass fan blades, significant damage to the upstream nacelle region and minor damage to tunnel internals downstream of the fan. The mishap was initiated by local failure (due to fatigue and fracture damage) of the External Thermal Barrier (ETB) retainer, resulting in high energy release of damage causing metallic parts. The Mishap Investigation Board determined that one factor contributing to the mishap was the failure of the Safety Analysis Reporting System. The ETB was not treated as a critical assembly or as a critical item of the ntf drive system (i.e. It was not recognized as a single point failure which could result in a Type A mishap). There were no inspection or maintenance requirements developed for the ETB retainer. A Safety Analysis Report (SAR) was not performed by either the contractor or NASA. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
501 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Adequate Procedures and Safeguards |  | Adequate procedures and safeguards must be in place to assure that all foreseeable risks to people, facilities, equipment, or missions are identified and mitigated. | Specifically, the unauthorized leak testing was stopped. In general, Langley Handbook 1740.5, governing procedures for working with oxygen clean systems, is in production. | LaRC | 07/08/1994 | On or about January, 1993, the LOX/LN2 System (an Oxygen Clean Environment) of the LaRC 7" High Temperature TUNNEL Was leak checked using K-Bottle nitrogen. At Langley Research Center, only personnel from the Fluid Systems Section of the Operations Support Division are authorized to work on oxygen clean systems. Personnel doing the leak testing were not from the Fluid Systems Office. When Fluid Systems Section personnel became aware of the leak testing, they questioned the use of K-Bottle nitrogen from the standpoint of system contamination. While the LN2 furnished for use in K-Bottles is over 99% pure, the K-Bottle itself, unless specifically tested and posted with appropriate paperwork attesting to that fact, is assumed to be contaminated with rust, hydrocarbons, and/or various other contamination-causing particles. Langley Handbook 1740.5 governs working with oxygen clean systems. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
503 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Periodic Evaluation of Blade Sets |  | Periodic and thorough evaluation, to include NDE, is in order for blade sets that have been in use for extended periods of time. | As a result of a blade failure incident, an aggressive blade inspection program, to include NDE, was implemented. During normal tunnel shutdown, a certain percentage of blades were pulled and thoroughly examined. Over a set period of time, this program insured inspection of all blades. New blades were equipped with frangible tips. There have been no subsequent catastrophic blade failures. | LaRC | 07/08/1994 |  |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
500 | Cockrell, C - 0000000000 : NO@ADDRESS.GIVEN | Cockrell, C - 0000000000 : NO@ADDRESS.GIVEN |  | Fasteners |  | Torque is not a sufficient measure to assure that joints are assembled with the proper preload. | While making threaded joints assure that all threads are clean before torquing fasteners. See Description of Driving Event for critical information. | LaRC | 10/19/1992 | For critical applications either run tests to develop actual torque-preload relationship, or use tables which were developed using the actual fastener material, joint material, and lubrication and/or locking system. On January 15, 1991 a failure occurred in the 8 foot transonic pressure tunnel during testing of a model wing with attached flap. During the test run, the flap peeled away from the wing, broke free, and proceeded down the tunnel. Extensive damage resulted. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
522 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Consider Stress Combinations During Design Analysis, also, do not Tap and Thread Acrylic Materials that will be Under Load |  | There are two lessons from this incident: During design analysis, stress combinations must be considered Do not tap and thread acrylic materials that will be under load. | The following recommendations resulted from the investigation of this incident: Frame the test section door. Combine stresses in the loads analysis. Do not drill, or tap and thread, acrylic door material. In the loads analysis, consider the vibration effects on the water tunnel when opening the jet exit facility and the water tunnel at the same time. | LaRC | 08/12/1994 | On 5-2-85, a mishap occurred at the water tunnel at Building 1234. While the tunnel was filled with water for leak checks, the test section door detached from the test section, resulting in 3500 gallons of water escaping the tunnel and the building. Significant damage resulted to the test section door, model support mechanism, test section, flow channel, and the honeycomb flow straighteners. The cause of the accident was the prying action between the door and the adjacent wall. This prying action, which was not considered in the design analysis, created stresses in the lucite door material beyond its flexural strength. There were other errors in the door design, to include: stresses were not combined (however, in the analysis performed - prying action not included - the material strength would have been sufficient for the loads considered). Acrylic materials should not be tapped and threaded (manufacturers recommend use of oversize bolt holes, grommets, and washers to minimize stress from through bolting) as was done with the test section door; and, framing, which could have provided for the load, was not used. The tunnel critical design review stipulated that, due to the effects of vibration, the water tunnel and the jet exit facility should not be run simultaneously. Effects of the jet exit facility vibrations on the water tunnel were not considered in the analysis. | Investigation Board recommendations to fix the problem were adopted. | N/A |  |  | Public | Not Specified |  | 04/02/1997
520 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Investment Casting Process for Producing Net-Shape, Superconducting Ceramics |  | Using an investment casting process developed by NASA LaRC personnel, it is now possible to produce net-shape, superconducting ceramics. | The production of net-shape superconducting ceramics, using the NASA LaRC developed process, has been demonstrated. | LaRC | 08/05/1994 | An investment casting process has been developed to produce net-shape, superconducting ceramics. In this work, a factorial experiment was performed to determine the critical process parameters for producing cast YBA2CU307 ceramics with optimum properties. The process employed YBA2CU307 powders dispersed in organic carrier liquids and foundry molds developed at, and patented by LaRC. The slips were poured into the molds as in traditional slip casting operations, however, instead of removing the casting from the mold, the molds were destroyed, leaving a cast ceramic shape. The most reliable organic carrier for the YBA2CU307 powder was found to be an acetone/menhaden fish oil system. The analysis of variance results indicate that careful control of the various casting variables is critical in controlling both the density and porosity of cast YBA2CU307 ceramics. As density and porosity are indications of the current carrying capacity of the superconductor, the optimization of the critical process parameters to produce superconductors with both high densities as well as a porous network permitting the uniform uptake of oxygen throughout the cast superconductor, is of great importance. These results indicate that the properties of cast superconductors may be controlled by understanding the effects of traditional ceramic processing variables such as the particle size distribution of the cast powders and the sintering temperature, as well as their interaction. This work was cited in the August and September 1992 issues of the American Ceramic Society Bulletin. The NASA-Langley Research Center contacts are S.A. Wise and M.W. Hooker, telephone number (757) 864-8068. A full report of this process is contained in the paper "Effects of Process Variables on the Properties of YBA2CU3O7-X Ceramics Formed by Investment Casting", authored by M.W. Hooker, T.D. Taylor, and H.D. Leigh, Department of Ceramic engineering, Clemson University, Clemson, SC 29634-0907; and S.A. Wise, J.D. Buckley, P. Vasquez, G.M. Buch, and L.P. Hicks, NASA-Langley Research Center, Hampton, VA 23681 |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
518 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Successful Prototype Reel Mechanism for use in the Gateway Tether Experiment |  | Tethered system technology has advanced to the point where an apparently successful prototype reel mechanism has been constructed for use in the Gateway Tether Experiment. | Test results show that: The prototype reel mechanism performs satisfactorily compared to simulations. Deployment and retrieval rates appear adequate for space-based systems. Length errors were within acceptable limits. The Yo-Yo damping scheme was shown to be successful. | LaRC | 08/03/1994 | The Gateway Tether Experiment (GATE) is a single tether satellite system that will develop and test control technology for a tethered system. Originally a free flying tethered system released from a gateway special canister on the orbiter, the system is now one experiment in the Tether Dynamics Explorer (TDE) series launched by a Delta II. The system consists of a Delta II second stage and subsatellite connected by a single tether. The subsatellite contains a motorized reel mechanism that will be the primary means of control actuation. A prototype reel mechanism has been constructed for use in the GATE system and ground tested. The reel mechanism consists of a spool and a level wind mechanism that are driven by independent stepping motors. The spool is designed to hold 1.8 km of 0.075 cm diameter tether. A paper, "Ground-based Implementation and Verification of Control Laws for Tethered Satellites", by David A. Gwaltney (NASA Langley Research Center) and Michael E. Greene (Auburn University) was published in the Journal of Guidance, Control, and Dynamics in the edition of January-February, 1992 (pages 271-273). The paper contains system equations and discusses testing and testing results. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
517 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Failure of a Parachute Recovery System During a Drop Test |  | Teflon cloth wrapped around the suspension lines to expedite extraction of the folded lines, jammed closed the canopy compartment lockoff flaps and caused failure of the recovery system. | The committee investigating the mishap recommended that prior to use with future models, parachutes procured by NASA-LaRC should be checked for appropriate and safe design; definitive specifications should be included with every parachute ordered by NASA-LaRC; and, any instance of change to parachute packing or repacking procedures, or to the parachute design, should require NASA-LaRC approval prior to implementation. | LaRC | 08/01/1994 | During a drop test at the NASA Plum Tree Island Test Facility, a model was severely damaged due to failure of its parachute recovery system. The failure of the recovery system resulted from teflon cloth jamming closed the canopy compartment lockoff flaps. The teflon cloth had been wrapped around the suspension lines to expedite extraction of the folded lines. The parachute contractor design personnel chose to add the cloth because its lubricating effect on the suspension lines and the resultant lowering of the force required to extract the lines. The information concerning the design change and lower opening force was transmitted to the research project engineer by telephone conversation. Significantly, no confirming strip-out load tests were performed with the teflon wrapped lines prior to using them in an actual test. The primary finding of the investigation committee was that teflon cloth jamming prevented the bag from opening and the canopy extracting. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
516 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Working in the Proximity of Energized Electrical Sources |  | Prescribed procedures should be followed and extreme caution exercised when working in the proximity of energized electrical sources. | Several actions were taken due to this mishap. They included issuance of a safety alert, procedures' reviews, and briefing high voltage technicians on the importance of maintaining safe distance from a high voltage source. | LaRC | 08/02/1994 | On 7-2-91 a LaRC electrical technician was seriously injured while preparing to check a 22kV nitrogen filled power cable in an electrical substation. When the technician came in proximity to an energized switchgear electrical terminal, an arc initiated, jumped to the technician's hand, passed into his arm, and exited from various parts of his lower body as well as from a key ring hanging from his belt. Langley Handbook (LHB) 1710.6, "Electrical Safety", defines safe distances for approaching exposed energized circuits. The LaRC investigation determined that the injured technician was less than the LHB 1710.6 mandated 3 feet from the injury causing energized electrical source. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
519 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Acoustic Emission for Detection of Damage Mechanisms |  | the use of acoustic emission for the detection of different damage mechanisms such as fiber breakage, matrix cracking and plastic deformation, and fiber-matrix debonding in these composites has been published. | NASA TM 107742, entitled, "Monitoring Damage Growth in Titanium Matrix Composites Using Acoustic Emission", has been published. | LaRC | 08/03/1994 | NASA TM 107442 entitled, "Monitoring Damage Growth in Titanium Matrix Composites Using Acoustic Emission", has been published. This work was coauthored by J.G. Bakuckas (National Research Council Research Associate), W.H. Prosser, and W.S. Johnson and is the result of collaborative research between different LaRC offices. The publication describes the use of acoustic emission for the detection of different damage mechanisms such as fiber breakage, matrix cracking and plastic deformation, and fiber debonding in these composites. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
521 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Inspection Oversights Led to Model Failure |  | Inspection oversights ultimately led to model failure as well as failure of the test being run. | Facility personnel were counseled on the importance of quality workmanship and, most importantly, on the need for a team effort relative to model inspections. All facility personnel involved have dedicated themselves toward insuring that this type of failure does not happen again. | LaRC | 08/12/1994 | On 11-12-92, research runs were being conducted in the unitary wind tunnel. During one test run, the downstream wood fairing on the model side mount splitter plate came loose and was destroyed as it went down the tunnel. The tunnel was not damaged, however, there was damage to some instrumentation tubing as well as lost research time. Although damage was relatively minor, this failure is significant because it was preventable. Subsequent investigation of the cause of the failure showed that not all of the required fasteners had been installed in the wood fairing, thus causing it to fail. In spite of the fact that the model was inspected more than once prior to the research runs being made, none of the inspectors noticed the missing fasteners. These inspection oversights ultimately led to model failure as well as the failure of the test being run. The damaged instrumentation tubing was replaced. A new wood fairing, this time secured by all required fasteners, was made by the LaRC model shop. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
515 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | High-Temperature Strain Gage |  | Excellent results are being obtained with the NASA Langley Research Center developed high-temperature strain gage on various NASP high-temperature test articles. | NASA Langley Research Center representatives have traveled to Pasadena and to Upland, California to confer with representatives of two firms with respect to commercial utilization of Langley developed strain gage technology. | LaRC | 08/02/1994 | High-temperature strain gage development in GWP Number 29 at NASA Langley was the topic of a paper presented at the annual NASP Technology Review Conference in Monterey, California, April 13-16, 1993. The talk highlighted the Langley developed high-temperature strain gage, focusing on the excellent results being obtained with this gage on various NASP high-temperature test articles. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
523 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Failure in the 16' Transonic Tunnel During Testing of a Lockheed Designed Powered Turboprop Model |  | Model integrity criteria should be developed and appropriate publications updated to require design consideration of blade loss, encapsulating parts, accounting for dynamic loads and/or instabilities, and the identification of dynamic characteristics by analysis and/or tests. | Based on the above findings, the investigating committee made the following recommendations: LaRC should develop model integrity criteria and update LHB 1710.15 to require design consideration of blade loss, encapsulating parts, accounting for dynamic loads and/or instabilities, and the identification of dynamic characteristics by analysis and/or tests. At least one reviewer of the model integrity report should be familiar with loads and instabilities of rotating systems. For each test, prepare and document test procedures including inspection requirements (for example, bearings) and operating checklists, and conduct wind-on and wind-off rehearsals. Instrument for, and record dynamic and static loads data during testing necessary to insure model integrity and correlate these measurements with predictions used in analysis. For future high risk tests, consider installing screening to protect the wind tunnel fan blades. | LaRC | 08/23/1994 | On October 29, 1985, a failure occurred in the 16' transonic tunnel during testing of a Lockheed designed powered turboprop model. The model failed while being tested at mach 0.8. The model propeller, spinner, balance, and air motor separated from the model nacelle and impacted the tunnel fan blades. The separated model components were irreparably damaged and all except one of the tunnel fan blades were damaged. The investigating committee found the most probable cause of failure to be high dynamic loading due to loss of one or more prop blades. It was also found that: The model design approach attempted to eliminate blade loss as a credible failure mode. The consequence of blade failure was not considered by Langley, Lewis, or Lockheed. | After this incident, Lockheed made modifications to insure containment of all parts within the model should blade failure occur. After modification, a verification test proved the model capable of sustaining "blade out" conditions. | N/A |  |  | Public | Not Specified |  | 04/02/1997
524 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Torque Value on Screws After Repeated Applications of a Thread-locking Compound |  | It is impossible to predict torque value on screws after repeated applications of "a thread-locking compound". | The "thread-locking compound" Corporation has provided information that screws should not be reused after having "a thread-locking compound" applied; further, a tap should be run into the female threads to clean them prior to a new screw being installed. | LaRC | 08/23/1994 | On 1-15-91 a failure occurred in the 8' Transonic pressure tunnel during testing of a model wing with attached flap. During the test run, the flap peeled away from the wing, broke free, and proceeded down the tunnel. Extensive damage resulted. It is hypothesized that reuse of screws having repeated applications of a thread-locking compound caused the east most flap bracket screws to either lose or never obtain proper preload. Under test conditions the screws loosened, then the east most flap bracket was lost, load was shifted to the flap fitting, the flap fitting sheared, and failure occurred. Of special significance is the fact that a thread-locking compound is always used on the screws that attach the flap brackets to the wing. These screws were reused for all tests and no special effort was made to clean them. The flap bracket screws had received an application of a thread-locking compound approximately thirty minutes prior to final installation in the wing, resulting in dried, but undisturbed, thread-locking compound on the screw threads. Further, an additional coating of a thread-locking compound was applied to the flap bracket screw threads just prior to their actual installation. Torque values shown on drawings were given for a preload of 50% or proof load based on dry threads. It is impossible to predict the actual torque on the bracket under the conditions indicated. The thread-locking compound corporation has provided conflicting information. One individual stated that screws should not be reused after having a thread-locking compound applied; further, a tap should be run into the female threads to clean them prior to a new screw being installed. Other representatives said they had no information about reusing screws. To achieve prescribed torque values, however, prudence would seem to dictate a more conservative approach to the use of a thread-locking compound as well as to the cleaning of threads. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
525 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Acceptance Testing, Inspection, and Securing of Air Lines |  | There are two lessons learned as a result of this event: Thoroughly inspect, prior to acceptance, work done by outside contractors. Secure tubing in support channels by clamping on both sides of the fittings. | To preclude future incidents such as this, it is recommended to: Inspect, before acceptance, work done by outside contractors. Secure tubing in support channels by clamping on both sides of fittings. Use fittings only where necessary (on the failed fitting line, distance between fittings ranged from inches to feet. It appeared as if fitting placement was determined in some cases by length of tubing available, not by where fitting was actually needed). Always let facility personnel know you are in their building, what you will be doing while there, and where you will be located. | LaRC | 08/23/1994 | On 1-20-93, contractor technicians were tracing a 1/4" stainless steel air line in Building 1247E. The line, part of the 5000 PSI air system, was in an overhead support channel and the technician was tracing it with his fingers while standing on a 4' step ladder. While tracing the line, the pressure of the technician's fingers was sufficient to cause the line to separate at a union fitting. The tubing was clamped into the support channel on one side of the fitting and this section of tubing held fast. On the other side of the fitting the tubing was not clamped into the channel; on this side, after separation, a section of line approximately 10' long whipped into the air and became lodged in other piping in the area. Damage was minor (a 1/4" plastic water line was severed) and there were no injuries. Fortunately, neither technician was in the path of the loose tubing. Had they been, serious injury could have occurred. It appears that the cause of the fitting separation was the result of improper assembly of the union. A "bite" ferrule in the fitting failed to secure the stainless steel tubing in the union. Thus, the line was only secured by air pressure. Movement of the line for any reason would have been sufficient to cause joint separation. | This incident has been documented and a record made of it. Appropriate personnel have been made aware of it. | N/A |  |  | Public | Not Specified |  | 04/02/1997
528 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Improperly Conceived Acceptance Tests and Original Specifications |  | Improperly conceived acceptance tests and original specifications led NASA Langley Research Center to accept parts, which failed in use. | When used, the output of two transducers became very erratic while a third one leaked water through welded seams in the transducer case. | LaRC | 10/05/1994 | In preparation for a test in the tow tank, Naval Underwater Systems Center personnel, who operate the facility under an MOU, sought the recommendations of IRD for the purchase of thirteen wet/wet pressure transducers with amplified outputs. The IRD recommended manufacturer was Druck and the appropriate specifications for transducers in their product line were provided to NUSC personnel. When the PR reached purchasing, the facility was informed that a GSA contract manufacturer would be the supplier. The GSA contract manufacturer was contacted by both NUSC and the instrument support section, IRD, since the needed items were not part of the GSA contract manufacturer's product line. The GSA contract manufacturer gave assurances that they could custom build the transducers to the required specifications. Twelve of the ordered thirteen transducers were delivered more than two months behind schedule and the thirteenth one-two weeks later. All the transducers passed acceptance tests and met or exceeded the original specifications. The first time the facility introduced a wet test medium (fresh water) into the transducers, the output of two transducers became very erratic and a third leaked water through welded seams in the transducer case. The two with erratic output were returned to the GSA contract manufacturer. The leaking transducer cannot be sent back without shutting down the in-progress test. Before the PR went out, ISS advised purchasing of the questionable quality of the GSA contract manufacturer's products, but according to purchasing, because of the GSA contract system, the GSA contract manufacturer had to be the supplier. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
526 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Magnetic Field Distribution in the Magneto-Optic Imaging Instrument |  | In the magneto-optic imaging instrument, a distribution of strong magnetic field exists in between two conducting sheets, while no measurable field strength exists above the magnetic current sheet. | The distribution of flaw-induced normal magnetic field component in the magnetic-optic imaging instrument has been measured between the test object and the current sheet as well as at locations above the current sheet. | LaRC | 08/25/1994 | One of the most important elements for the further improvement of the performance of the magneto-optic imaging instrument is to quantify the contribution of each different mechanism to the obtained image. More experiments were recently performed using a single-layer thick pancake pickup coil so that the distribution of flaw-induced normal magnetic field component may be measured between the test object and the current sheet, as well as at locations above the current sheet. The test used magnetic current sheet, which has very strong skin depth attenuation. As expected, a distribution of strong magnetic fields exists in between the two conducting sheets; no measurable field strength exists above the magnetic current sheet. Further experiments are being conducted with the new pickup coil to establish a firm theoretical base. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
527 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Producing a Symmetrically Smooth Time Base for Celestial Photography |  | A symmetrically smooth time base for celestial photography can now be produced for standard 60 Hz power. | A certificate and cash have been awarded for the disclosure and innovation entitled "Sidereal Rate Generator," LAR-14350-1. | LaRC | 08/25/1994 | Two Langley Research Center employees, Brad Leighty and John Franke, received a certificate and cash award for the disclosure of innovation entitled "Sidereal Rate Generator," LAR-14350-1. This circuit was developed to produce a symmetrically smooth time base for celestial photography from standard 60 Hz power. Normal time is based on the position of the sun. There are approximately 365.25 solar days in the year. A sidereal day is the average time between meridian crossings by a star. There are approximately 366.25 sidereal days in a year. This circuit multiplies standard 60 Hz power cycles and divides by a slightly different number in order to produce a signal that approximates sidereal time with an error of only about 1.8 seconds per year. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
529 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Evaluation of the Fire Watch Surveillance Period |  | Although this fire happened some time ago, there were no personnel injuries, and damage was relatively minor, there were some significant lessons learned: Sparks and hot chips generated during the cutting operations apparently came to rest in a hidden area, created a hot spot, and, approximately 90 minutes after cutting operations were completed, the hot spot ignited into a full fire. Fire watches normally cease one hour after cutting operations are ended. Under certain circumstances, such as those found in this situation, existing procedures may be inadequate to insure no fire hazard remains. Therefore, each job should be individually evaluated to make sure the fire watch surveillance period is sufficient. Security measures should cover entry of emergency personnel to controlled/limited access areas. Unnecessary delays can significantly increase fire damage. In this incident, use of material stored in ready access for the covering of electronic equipment in the event of fire prevents water damage. Readiness of this type of material could have benefit in other facilities should a fire occur. Standpipe system bosses in the Building 1268A complex weren't long enough for the most effective use in fighting this fire. Subsequently, an additional 50' of hose has been added to each standpipe location. | Fire watches normally cease one hour after cutting operations are ended. Under certain circumstances this period of time may be inadequate to insure no fire hazard remains. Therefore, each job should be individually evaluated to make sure the fire watch surveillance period is sufficient. | LaRC | 10/06/1994 | On 8-5-83 a fire occurred in Building 1268A. The fire, which ignited on the building roof, caused no personnel injuries and resulted in damage under $5,000. The fire was the result of cutting torch operations required in the removal of a number of steel i-beams located next to a wood structure. This fire occurred although all reasonable fire prevention measures had been used to protect the facility. | Fire prevention at LaRC continues to receive high priority. | N/A |  |  | Public | Not Specified |  | 04/02/1997
510 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Limitations of Classical Plate Theory for Composite Materials Caused by Neglecting the Effects of Shear Deformation and Rotary Inertia |  | The lack of agreement between theory and experiment at the higher frequencies demonstrates the limitations of classical plate theory for composite materials caused by neglecting the effects of shear deformation and rotary inertia. A Higher Order Plate Theory (HOPT) using these effects to predict the dispersion behavior was in much better agreement with the experimental measurements. | This work has been published in the technical paper "Propagation of Flexural Mode AE Signals in GR/EP Composite Plates", by W. H. Prosser and M. R. Gorman, NASA LaRC. | LaRC | 07/27/1994 |  |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
509 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Velocities of Acoustic Emission Signals in a Thin-Walled Graphite/Epoxy Tube in Agreement with Classical Plate Theory |  | Velocities of acoustic emission signals induced by means of lead breaks in a thin-walled graphite/epoxy tube were found to be in agreement with classical plate theory. | For a detailed presentation of this work, see the paper, "Extensional and Flexural Waves in a Thin-Walled Graphite/Epoxy Tube", by John Dorighi (Mechanical Engineering Student, University of Colorado, Boulder, Colorado 80309-0424) and William H. Prosser, NASA Langley Research Center, Hampton, Virginia 23665; and, Michael R. Gorman, Aeronautics and Astronautics, Naval Postgraduate School, Monterey, California 93943. The paper appeared in Vol. 226, No. 14/1992, Journal of Composite Materials. | LaRC | 07/25/1994 | Simulated acoustic emission signals were induced in a thin-walled graphite/epoxy tube by means of lead breaks (Hsu-Nielson Source). The tube is of similar material and layup to be used by NASA in fabricating the struts of space station freedom. The resulting waveforms were detected by broad band ultrasonic transducers and digitized. Measurements of the velocities of the extensional and flexural modes were made for propagation directions along the tube axis (0 degrees), around the tube circumference (90 degrees) and at an angle or 45 degrees. These velocities were found to be in agreement with classical plate theory. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
506 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Documentation to Determine whether or not a Product Contains Hazardous Substances |  | Because something has always been done that way doesn't necessarily mean that it is being done properly. When necessary documentation exists, in this case an MSDS, to determine whether or not a product contains hazardous substances, use it. | In order to prevent recurrences of potential exposure to MIL-7808-H, a non-hazardous oil will be used in all similar models for all future tests. | LaRC | 07/12/1994 | On 1-28-93, during normal testing in the Model Preparation Area (MPA) of the 16' Transonic tunnel, oil from a turboprop simulator model was vented into the atmosphere. The vented oil was MIL-7808-H, the same type as used in past model tests. The turboprop simulators have no oil scavenging system, therefore, it is standard practice to vent oil from the simulators. When preparing to clean instrumentation fouled with the vented oil, it was determined that MIL-7808-H oil contains Tricresylphosphate, a hazardous substance absorbable through the skin and capable of causing paralysis. After LaRC Environmental Health Personnel were contacted to determine proper protective measures, the MPA room was cleaned of all residual oil. There were no personnel injuries resulting from this incident. | A non-hazardous oil is now being used in testing. | N/A |  |  | Public | Not Specified |  | 04/02/1997
505 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Failure in a CPU Consisting of Two Boards could be due to Oxidation on the Connecting Pins |  | When a failure occurs in a CPU consisting of two boards, connected by pins to form one unit, failure could simply be due to oxidation on the connecting pins. In many cases, disassembly, or merely, flexing the board, will correct the error. Moving the pins, either by flexing or disassembly, removes the oxidation. | Backup limit switches are in use on each device that exceeded movement limits. The watch dog timer will shut down sequencer "C' if proper operation is not achieved within the first few seconds after start up. These two actions will prevent damage if there is a future sequencer failure. | LaRC | 07/12/1994 |  |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
504 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Improper Handling of a Test Item Ultimately Resulted in Test Failure |  | Improper handling of a test item likely contributed to overstressing a fitting pin, leading to a tensile fracture of the pin and its subsequent failure, which ultimately resulted in test failure. | Proper handling procedures were subsequently observed and there was no further failure attributed to this cause. | LaRC | 07/12/1994 | On January 15, 1991, a failure occurred in the 8' Transonic pressure tunnel during testing of a model wing with attached flap. During the test run, the flap peeled away from the wing, broke free, and proceeded down the tunnel. Extensive damage resulted. It is hypothesized that the east wall flap fitting pin was damaged when the flap was allowed to bend during installation. These pins are stainless steel and approximately 0.38" square. They are inserted into square holes in the tunnel side plates. When the model was installed, the flap was lifted to complete the attachment, was left unsupported during the attachment process, and deflected in the center. This deflection could have caused the square flap fitting pin to become overstressed. The Metallic Materials Branch did, in fact, identify an area of tensile fracture related to a single load incident, but was unable to conclusively establish when the fracture occurred. In any case, engineering should strive to use the lowest stress concentration configuration feasible. In this instance, a round pin on the flap end fitting would have reduced the stress concentrations from the level present on the square pins and perhaps prevented test failure. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
507 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Prevention of LaRC T-38 Canopy Failures |  | It is possible to prevent LaRC T-38 canopy failures using existing modifications. | The investigation committee made four recommendations: The JSC devised warning horn modification should be added to N511NA (done) Preflight procedures should include a post canopy closure checkoff by ground service personnel (done) JSC procedures for canopy operation should be incorporated into Langley T-38 pre-flight procedures (done) Pilot sensitivity should be raised as to the nature of the T-38 canopy locking problem history and the need to ensure canopy lock prior to takeoff (done). There have been no subsequent canopy failures on N511NA. | LaRC | 07/13/1994 | On 10-15-90 the T-38 Aircraft (N511NA) belonging to LaRC was on a local training flight. At the time of rotation, the rear canopy separated from the aircraft, damaging both the canopy and the vertical stabilizer. The pilot made an uneventful landing. The canopy loss was most probably caused by the failure of the external handle force input to complete latching of the canopy hooks. There is also strong circumstantial evidence that the canopy latching mechanism contains a design deficiency. JSC has fathered two T-38 canopy locking modifications. One modifies the outer access door for the external canopy handle and was on N511NA at the time of the canopy failure. The other modification includes a warning horn which sounds if either canopy switch indicates an unlatch and the throttle is moved past 96%. This modification was not on N511NA at the time of canopy failure. | Since the LaRC T-38 was appropriately modified, there have been no canopy failures. | N/A |  |  | Public | Not Specified |  | 04/02/1997
530 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Flux Measurements Providing Information on the Source/Sink Distribution of O3 and CH4 over Regions of Alaska |  | Airborne CO flux measurements over the Yukon-Kuskokwim Delta (YKD) indicate low negative flux values over the coastal areas, while some positive fluxes were observed in the inland, sparsely forested regions. Analyses indicate the possibility of in situ photochemical destruction/production of CO. Tundra surfaces are estimated to be responsible for approximately 32% of the total deposition loss of O3 poleward of 60 degrees north. Data from the airborne O3 flux measurements made during this study indicate similar values of RC for the Alaskan North Slope (ANS) and YKD. | In situ airborne measurements of the turbulent flux and mean values for O3, CO, and CH4 were obtained in the boundary layer over the YKD and ANS regions in Alaska. The flux measurements provided information on the source/sink distribution of O3 and CH4 over these selected areas. | LaRC | 10/07/1994 | In situ airborne measurements of the turbulent flux and mean values of O3, CO and CH4 were obtained in the boundary layer over selected wetland systems in Alaska. These measurements were obtained in July-August 1988 as part of the NASA Global Tropospheric Experiment Program's Arctic Boundary Layer Expedition. The flux measurements obtained from this study provide information on the source/sink distribution of O3 and CH4 over the Yukon-Kuskokwim Delta (YKD) and Alaskan North Slope (ANS) regions of Alaska. The source/sink distribution over the YKD is qualitatively correlated with surface vegetation type, identified from multispectral scanner imagery. Direct measurements of the spiral variation in the CH4 source strength were obtained over the YKD. The CH4 source strength over the YKD ranged from 2.5 to 85 MG M-2 D-1 during a flux survey flight which spanned a considerable portion of the YKD, a spatially averaged, seasonally adjusted source strength of 51 MG M-2 D-1 was established for the YKD. Indirect CH4 flux estimates obtained over tundra were estimated to be 44 TG/A based on: the spatially averaged source strength obtained over the YKD current estimates of the global coverage of tundra assuming a similarity between other tundra areas and that of the YKD. |  | N/A |  |  | Public | Not Specified |  | 04/02/1997
499 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Pressure Verification During Pressure Systems Operations and Maintenance |  | Verification of pressure status is critical when working on energized systems. | Always assume a pressure system is under pressure until otherwise verified. Verify that it is unpressurized and then recheck the verification. Look for valves in the system that may be open or closed, giving an erroneous verification. Obtain the drawings and configuration control documents. Take the time to review the documentation, drawings, or schematic. Consult local experts for pressure system configuration and requirements. When performing general maintenance tasks: Energized systems require lockout/tagout prior to performing maintenance. Read and honor the warning signs while conducting your work. Be concerned for the safety of your co-workers and act accordingly. Stop the task if you encounter a potential hazard and check with your supervisor. Do not take chances! | JSC | 12/09/1996 | A maintenance team was removing a gate valve from a high pressure (5000 pounds per square inch) nitrogen trailer at the fill end of the trailer. After the valve bolts were removed and the employee tapped on the valve to loosen it, the valve flew off and hit one of the maintenance employees. The employee was thrown 15 feet through the air and against an I-beam, resulting in a fatality. Preliminary information indicated that the system was not under pressure and the valve gauge reading was zero pressure. [This event occurred during work external to NASA but includes information that is pertinent to NASA operations.] |  | N/A |  |  | Public | Not Specified |  | 03/31/1997
498 | Stanford, J - 0000000000 : NO@ADDRESS.GIVEN | Stanford, J - 0000000000 : NO@ADDRESS.GIVEN |  | Job Hazard Analysis for Warehouse Operations |  | Performing job hazard analyses for new tasks or jobs or ones with major modifications can identify hazards and provide information for corrective actions to eliminate or control those hazards. | Relocate storage racks in this and similar buildings so that there is extensive distance between storage racks and suspended heaters and their service lines. Items that are to be stored below suspended heaters are never to be stored over one tier high. Mark all gas supply lines to suspended heaters in warehouses in a highly visible and prominent fashion with yellow caution banners. ALL ABOVE RECOMMENDATIONS HAVE BEEN IMPLEMENTED. | JSC | 11/21/1996 | A JSC forklift operator struck and broke a 3/4 natural gas supply line servicing a suspended forced air gas heater in Building 422. The operator was moving a material pallet from the top shelf of storage bin. As he was backing the forklift to lower the load, the extended mast of the forklift struck the natural gas line. Due to the escaping gas, operations were shut down and the facility evacuated. Root cause was the failure to perform a job hazard analysis and eliminate or control those hazards. The layout of storage in close proximity of suspended heaters should have been corrected. Also, scars and scratches on this and other gas lines and heaters is evidence of pervious physical contact. |  | N/A |  |  | Public | Not Specified |  | 03/31/1997
496 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Improper Welded Joints in Rocket Engine Combustion Chamber (1995) | A defective weld in the combustion chamber of the Mars Global Surveyor main engine resulted in destruction of the engine within the first few seconds of test. Conduct a thorough external and internal inspection of rocket engine combustion chambers, paying particular attention to welded joints, prior to hot fire testing. | Conduct a thorough external and internal inspection of rocket engine combustion chambers, paying particular attention to welded joints, prior to hot fire testing. |  | JPL | 03/13/1997 | In the first test firing of a Mars Global Surveyor (MGS) main engine, the engine was destroyed within a few seconds. The combustion chamber had exceeded the maximum allowable temperature, causing parts to melt and rendering the engine unusable. Internal examination with a boroscope revealed an annular extrusion in the combustion chamber due to overpenetration of weld material in the joint between the injector and the chamber. The MGS main engine injector fits over the head end of the combustion chamber; the two parts are attached with a weld about the circumference of an overlapping joint. Vendor use of an incorrect weld schedule produced an annular ridge, which interfered with the flow of boundary layer cooling fuel within the chamber. This disturbed flow resulted in an untenable thermal condition. A boroscopic examination of the chamber prior to the test firing would have revealed the defect. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.3.3 ("Safety and Mission Assurance Practices: Quality Assurance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/25/1997
497 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Propulsion Valve Contamination Sources in Vendor Test Facilities (1995) | The Cassini/Mars Global Surveyor thruster high pressure latch valve was redesigned to use a Kel-F seal instead of Teflon. Because the harder plastic has less ability to seal around small particles, particulate contamination in the helium gas can cause random leakage. Use high purity helium for pressure testing and for flight consumables, and establish contamination control procedures. | Propulsion system valve designs remain vulnerable to gas leakage over the course of multi-year missions. Hard plastic seals such as Kel-F are nearly as sensitive to contamination as metal-to-metal seals. Examine propulsion valve vendor test facilities for sources of potential test article contamination-particularly by hydrocarbons. Establish contamination control procedures for qualification test of propulsion valves. Flush the test article with freon to remove any hydrocarbon deposits. As part of these procedures, the qualification valve should be subjected to at least 5 times as many mechanical/thermal cycles as expected in flight without detecting excessive leakage. Establish contamination control procedures for both flight hardware and ground support equipment. Use high purity (medical application) helium for pressure testing and for flight consumables. |  | JPL | 03/13/1997 | During thermal cycle test of the Cassini/Mars Global Surveyor thruster high pressure latch valve -- the final test in the valve qualification program -- an unacceptable rate of valve leakage was detected. Disassembly of the valve revealed particulate and hydrocarbon contamination. Examination of the vendor test fixture disclosed that the 4000 psi test pressure had been attained using a compressor that included a non-operational, contaminated "cold trap." Under these conditions, the room temperature test permitted compressor oil to contaminate the valve assembly allowing accumulation of debris on the valve seat. The valve seat had been redesigned during the Cassini project to use a Kel-F seal instead of Teflon. A harder plastic able to withstand higher pressure and temperature than Teflon, Kel-F has less ability to conform and seal around small particles. Cleaning and reassembling the test article was only partially successful in stopping leakage during a second thermal cycle test. It was the consensus that this hard Kel-F plastic seal is subject to random leakage due to particulate contamination in the helium gas used in test and in flight. Reference(s): Cassini PFR B33135 Contractor memo no. 1.3-TM-237, "High Pressure Latch Valve Qualification Closure", June 11, 1996. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 ("Engineering Practices: Materials, Processes, and Contamination Control"), and Paragraph 6.12.3 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/25/1997
494 | Shovlin, Mike - 0000000000 : NO@ADDRESS.GIVEN; Zander, Ken - | Shovlin, Mike - 0000000000 : NO@ADDRESS.GIVEN |  | Verification of Baseline Configuration before Modification, Upkeep of Maintenance and Operational Logs, Operation Condition Effects, Upkeep Documentation, Safety System Checks |  | Configuration must be baselined and accepted before modification to understand design, identify all necessary changes, assess effects on whole. Incomplete data recording and maintenance of operational logs resulted in incomplete determination of effects. Abnormal operating conditions producing effects that are unanticipated or can not be explained should be investigated prior to continuing testing. Review of documentation found errors or deficiencies on operational and maintenance logs. Safety equipment should be used prior to any test or review for safety of operation, adequate warning, and/or understanding of operation. | Ensure that the configuration is defined and verified before modifying. Document adherence to operating procedures with defined procedures for data recording of maintenance and operational logs. Test for abnormal operating conditions and determine rational for results before proceeding. Define procedures for keeping reference documentation current, and complete. Investigate procedures: Check performance of safety equipment prior to installation (note procedures for Safe Operation, Shut Down, and Alarm). | ARC | 05/05/1989 | On January 25, 1984, the National Geotechnical Centrifuge, located at NASA Ames Research Center, experienced a catastrophic failure of the 18,000 horsepower drive motor thrust bearing. The failure permitted the 100 ton drive motor armature to drop, the centrifuge to stop, and resulted in extensive electrical and mechanical damage. Repairs may take one year, and cost estimated at $550,000. |  | N/A |  |  | Public | Not Specified |  | 03/10/1997
495 | Zander, Ken - 0000000000 : NO@ADDRESS.GIVEN | Zander, Ken - 0000000000 : NO@ADDRESS.GIVEN |  | Systems Engineering, System Safety and R&QA Program Integration, Operational Safety and Performance, Risk Management, and Facility Safety Inspections |  | Procedures for effective systems engineering on safety issues are lacking. System safety and R&QA omitted for project design decisions results in design deficiencies and possibly manufacturing defects affecting safety. The user/operator community does not understand the design constraints on the system imposed by issues of safety and risk management. Cost control does influence performance, safety and reliability. Modifications to facility design contained specific configurations that serve to abate previous safety inspection hazards. | Define procedures to ensure effective systems engineering. Assign review and approval authority to system safety and R&QA on project design decisions. Involve the user/operator community in the design decision process regarding safety and operational safety issues. Institute cost control systems for safety and reliability. Check all aspects of facility design construction and operation against modification. | ARC | 02/28/1983 | December 9, 1982, the 80 x 120 foot wind tunnel at the Ames Research Center was undergoing commissioning/shakedown testing when Vane Set 5 collapsed destroying the vane set, the fan blades of all six drive motors, and damaging the tunnel itself. |  | N/A |  |  | Public | Not Specified |  | 03/10/1997
493 | Zander, Ken - 0000000000 : NO@ADDRESS.GIVEN | Zander, Ken - 0000000000 : NO@ADDRESS.GIVEN |  | Transitory Negative/Positive "G" Force Effects, Flight Policy, Fact Sheet Material, Upkeep of Pilot Flight Manual, Aircraft Modification Safety Analysis, Flight Data Recorders, Emergency Escape Decisions |  | Lack of knowledge/awareness of the effects of negative "G" forces may have contributed to the crash. No supervision of flight, suggests oversight function could have identified need for preflight training. Fact sheet material not clearly defined in function may have resulted in directive material being interpreted as advisory. Review of flight manual indicated possible lapse in updating material or in pilot training or both. Modifications made to aircraft may not have been reviewed/approved by safety, even though made for safety and flight reasons. Board review of accident was less effective because there was no flight data recording to evaluate. Flight managers must emphasize importance of adherence to emergency escape decision altitudes at preflight for high angle of attack maneuvers. | Include information on incapacitation or disorienting effects of transitory "G" forces on pilots, in all aircraft operations documentation. Maintain management oversight of research support and proficiency flights. Clearly define fact sheet information for pilots as advisory or directive. Institute adequate procedures to assure pilot's flight manuals reflect current training. Develop procedures that require written approval for modification of research aircraft involving safety to flight. Equip all agency aircraft with flight data recorders. Develop procedures to ensure review of emergency escape decision altitudes at preflight. | ARC | 04/18/1989 | A fatal accident involving the Ames/EFRF T-37B Jet Trainer (NASA 807) occurred east of California City, CA. at approximately 1:15 P.M. (PST) on November 8, 1982. NASA pilot Richard E. Gray was killed. The aircraft was totally destroyed by ground impact and fire. There were no other personnel injuries and no other property damage. Every attempt to establish probable cause has been unsuccessful. In the course of the research support flight, T-37B entered a spin resulting in an uncontrolled flight condition, and the pilot delayed ejection until a successful ejection was no longer possible. |  | N/A |  |  | Public | Not Specified |  | 03/10/1997
492 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo High Gain Antenna (HGA) Failure (1991) | The Galileo spacecraft High Gain Antenna (HGA) was to open like an umbrella, but it never reached the fully deployed position. The failure was attributed to an inherited design of the rib retention mechanism. Recommendations involved the design of preloaded mechanisms, lubricant selection and use, hardware robustness, and fault tolerant design of one-shot, non-redundant, mechanisms. | Design changes intended to improve the reliability of inherited hardware may introduce new failure mechanisms. The mission impact of such design changes may best be understood through a "physics of failure" approach to reliability analysis. Failure physics issues relevant to antenna support bearings, for example, may include oxidation, cold welding, galling, static and sliding friction, lubrication transfer, Hertzian contact stresses, and plastic deformation, as well as operational issues such as long-term storage, ground handling, the mission environment, and mission duration. | In the design of preloaded mechanisms, consider the potential for high contact stresses on pin/socket interfaces to destroy the integrity of the lubricant film. Take into account the potential for lubricant effectiveness to decrease over time. Due to its high wear rate in air, carefully evaluate the use of molybdenum disulfide drylube on a mechanism that will be tested or operated under non-vacuum conditions. Hardware should be inheritently robust or redesigned to accommodate major changes in spacecraft system design, changes in spacecraft handling or the mission profile. Inheritance, design and peer reviews should fully consider the effect of such changes on known failure mechanisms. One-shot, non-redundant, mechanisms should be designed for simplicity and fault tolerance-particularly where the mechanisms are preloaded prior to long-term storage, or where they endure extended periods under atmospheric and vacuum conditions prior to actuation. | JPL | 01/16/1997 | In April 1991, the Galileo spacecraft executed a deployment sequence which was to open the High Gain Antenna (HGA) like an umbrella, but it never reached the fully deployed position. A formal failure investigation attributed the failure to the design of the rib retention mechanism. According to this scenario, the most likely failure mechanism is friction in the pin/socket interface on the antenna rib midpoint restraint. Preloading of the ribs when the antenna was stowed at the factory damaged the ceramic coating on the pin engaged by the V-groove socket; the coating served to retain the molybdenum disulfide dry lubricant. Accumulated stresses from vibration testing, rib preloading, four cross-country trips, and the post-launch ignition of the upper stage further dispersed the lubricant film. The resulting friction caused asymmetrical deployment, resulting in restraining forces which further reduced the torque available from the deployment drive system. The HGA was largely inherited from an antenna developed for the Tracking Data Relay Satellite (TDRS) system. JPL design changes included substitution of two conical Inconel pin sockets with one conical and one V-groove Inconel socket. Selection of an Earth orbital antenna design, even though proven in that application, was not fully consistent with the Galileo mission. Inheritance and other design reviews failed to reveal the existence of high surface stresses. In addition, a lessons learned on Voyager II to use spring assisted mechanical deployments was not followed. The deep space mission subjected the redesigned antenna to environmental conditions not encountered by TDRS in Earth orbit, and the VEEGA mission profile instituted after Challenger extended both the duration of those conditions and the time to deployment. Galileo illustrates the difficulty of reproducing the spaceflight environment in the ground test of large and complex mechanisms, even when full design review and environmental testing are undertaken. Flight antenna deployment test failed to disclose the problem because (1) vacuum test was performed without the vibration-induced relative motion between the pins and sockets and (2) oxides and contaminants present during ground test on the bare titanium pins lubricated the mechanism. Similarly, ambient ground tests did not reveal the failure mode due to the lower coefficient of friction of the titanium pin/socket interface in air. Additional testing of the deployment mechanism would only have worn out the deployment drive system. Work-arounds using the Low Gain Antenna, new data compression techniques, and the spacecraft's recorder are expected to meet 70 percent of the mission objectives. Reference(s): "Galileo HGA Deployment Pin Walkout Analysis Final Report," JPL D-9932, July 1992 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6 ("Engineering Practices: Inheritance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.2.3.4 ("Mechanical Configuration/Systems Design: Mechanisms - Use of Kick-Off Springs for Assured First Motion") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/07/1997
490 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Electric Shock Hazard - Russian 220v AC Circuits |  | Electrical problems been attributed to the lack of verification of a proper ground of 220V AC power outlets. | To prevent mishaps, the following actions may be taken: Adequate grounding of electrical outlets should be verified prior to connecting any equipment to a power source. If adequate grounding from the facility outlets cannot be verified, an independent ground to earth ground should be installed. | JSC | 12/24/1996 | International travelers should be prepared to deal with grounding problems that have been experienced by NASA personnel. As an example, several personnel have been electrically shocked while working at the Star City Training Complex and other Russian facilities. Improper or compromised grounding of 220v AC circuits has been found in these reported cases. [While highly unusual for 220v, this event is known to occur in American facilities on occasion.] Verification of grounds has been difficult in some cases, prompting the need for installation of independent ground to earth grounds. Reference(s): NASA JSC Safe Alert dated, 10/27/95 |  | N/A |  |  | Public | Not Specified |  | 02/26/1997
491 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | High -Voltage Hazard |  | It is imperative that the workers be fully informed of the hazards of the energized electrical systems before working around them. | Conduct physical inspections of all work areas to identify hazardous areas and operations. Closely control all restricted access areas to prevent mishaps which might be precipitated by untrained individuals. All personnel must be knowledgeable and fully capable of understanding the full meaning and message intended by caution, warning, and danger signs. Take time to review the risks of a job or work site before approving or beginning any job. Ensure proper procedures have been provided to address hazardous operations and involved personnel are aware of the procedures and all identified hazards. Never work on or near energized equipment unless you have the proper training and protective equipment. | JSC | 12/24/1996 | Support contractor personnel contacted high voltage with a paint scraping knife while preparing a cable tray for painting in a facility / building transformer enclosure, causing a flash fire. Two of the worker¹s clothing caught fire and nearby combustibles were ignited. Two workers sustained burns to their hands and faces when one of the workers inserted the knife in a vent/drain slot. This accident did not result in permanent disability or death but the potential is evident. Reference(s): NASA JSC Safe Alert dated, 11/01/95 |  | N/A |  |  | Public | Not Specified |  | 02/26/1997
488 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Vacuum Pump Outlet Hazard |  | Restriction of vacuum pump discharge may cause rupture of exhaust components. | Install a wire cage around the pump outlet line discharge or replace the open exhaust fitting with an extension drilled with holes along the side as well as an open end. This will prevent inadvertent blockage of a single port that may lead to over pressurization of the oil mist separator jar. | JSC | 01/01/1997 | Technicians were performing a maintenance operation on a Mazak CNC milling machine vacuum pump when a glass oil mist separator bowl burst. The subject bowl was attached to the discharge of a 3 hp Gast pump. This particular pump has the capability of producing 15 psi at the outlet if restricted. The rated pressure of the glass bowl is 5 psi, which is clearly marked with a warning regarding breakage. Prior to the incident, the pump had undergone overhaul and, after reinstalling the pump, the technicians operated it in order to circulate its lubrication oil. Once oil circulation was verified, the pump was restarted and the glass oil separator bowl ruptured. Fortunately, no one was injured by the broken glass. The technicians performing the task stated that there was no known restriction in the discharge piping downstream of the separator. It should also be noted that an identical separator is installed on the inlet of the vacuum pump. The incident prompted an investigation of other similar installations in the facility. The result was that a total of 3 machines are using the same oil separator configuration as the subject machine. These separators are factory installed and are standard equipment on these type of machines. To prevent injury from unanticipated glass fragmentation due to overpressurization of the oil separator, maintenance management personnel decided to install a wire cage around the pump discharge. |  | N/A |  |  | Public | Not Specified |  | 02/18/1997
489 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Shocking Surge Protector |  | Physical contact with energized equipment and power sources should be performed only when the operation is clearly visible to the operator. | Never attempt to insert or remove an electrical plug into or from an energized receptacle or power strip that you cannot clearly see. This can easily lead to injury from shock by touching (or having jewelry touch) energized electrical components. Periodically check your power strips and cords that are not easily seen to ensure that they are not damaged, nicked, or separating. Deenergize the devices to check them thoroughly if you can not clearly see them. Carefully remove all objects that have stayed in one place on the floor for any period of time. This is especially true of items that sit on tile floors and can become "Stuck" from floor maintenance. It can be very difficult to remove stuck items without damaging the item or the floor tiles. | JSC | 01/01/1997 | An employee received an electrical shock while unplugging a printer from a 6 receptacle power strip surge protector. The surge protector was located behind some furniture, on the floor, and out of sight of the employee unplugging the printer cord. The surge protector had apparently become stuck to the floor from floor maintenance, the plastic case had separated, and energized electrical components were exposed. When the employee reached back to unplug the cord, he they received a shock from the exposed components. |  | N/A |  |  | Public | Not Specified |  | 02/18/1997
486 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Conduct Post Test Examination of Lot Acceptance Hardware for Incipient Failures (1993) | During lot acceptance test of ten Mars Observer pyro valves, none failed. Yet, post-test examination showed that each of these valves had sustained erosion (burning) of about 50 percent of their threads. A study showed that some firings result in the pyro being ejected from the valve body at speeds of approximately 200 m/s, which could damage critical hardware. Users of NSIs should be alerted to this possibility. Acceptance or qualification testing should include post-test examination of inferred margin or incipient failure modes. The use of titanium in pyrotechnic applications should be avoided. | Successful lot functional acceptance tests may not detect incipient failure modes without post-test examination. Explosive initiators produce hot, reactive products which may create ejecta ranging from tiny debris particles to portions of the valve body, especially in the presence of titanium which is a highly reactive metal. | Alert users of NSIs to the possibility of damage from ejected initiators. Parts and materials lot acceptance or qualification functional testing should include post-test examination to look for signs of inferred margin or incipient failure modes and should include destructive testing if necessary. The use of titanium in pyrotechnic applications should be carefully reviewed or avoided due to its highly reactive nature. | JPL | 12/19/1996 | As part of the Mars Observer mission failure investigation, the acceptance test lot of the Mars Observer pyro valves were examined for thread erosion. The pyros were suspect because of tests that had been made on European Space Agency (ESA) pyro valves and initiators, which showed that some firings result in the pyrotechnic initiator being ejected from the valve body at speeds of approximately 200 m/s. The pyro valves and NASA standard initiators (NSIs) used aboard Mars Observer were designed to the same specifications, though they were not identical to the ESA hardware. During lot acceptance test, none of the ten pyro valves tested had failed-- all fired, and none ejected their initiators. Following the Mars Observer failure, examination showed that each of these valves had sustained erosion (burning) of about 50 percent of their threads. The erosion was caused by combustion of the titanium thread material with the combustion products of the initiator. This examination was not required in the original lot acceptance test of the parts. Were the thread loss to cause ejection of an initiator, severe damage to the spacecraft wiring, propellant tanks, and other critical hardware could result. For example, one of the Mars Observer initiators was located such that it would impact the monomethylhydrazine (MMH) propellant tank if it were ejected. The JPL Mars Observer Special Review Board considered a failed pyro valve charge initiator to be a potential cause of the loss of the Mars Observer mission. Reference(s): "Report of the Mars Observer Mission Failure Investigation Board," (Coffey report), December 31, 1993. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.2.3.9 ("Mechanical Configuration/System Design: Mechanisms - Mechanisms Cycle Life Design Margins"), and Paragraph 4.2.5.6 ("Mechanical Configuration/System Design: Structural Design - Structure Design Criteria for Actuators"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 01/24/1997
484 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Adoption of an Earth-Orbital Propulsion System Design for a Planetary Mission (1993) | To reduce costs, the Mars Observer propulsion and other subsystems followed design practices more common to earth-orbiting satellites than to planetary missions. Consider contractor experience in bipropellant spacecraft propulsion system design in source selection. To manage risk on one-of-a-kind developments, assure thorough technical oversight of contractors with limited experience in the design of interplanetary spacecraft. | The differences in the operating environment between Earth-orbiting and interplanetary missions may be very significant and must be considered very early in the project design. It is unrealistic to assume that contractor experience with earth-orbiting spacecraft is directly applicable to design of interplanetary spacecraft. | Consider contractor experience in bipropellant spacecraft propulsion system design in source selection. To manage risk on one-of-a-kind developments, assure thorough technical oversight of contractors with limited experience in the design of interplanetary spacecraft. | JPL | 12/12/1996 | The Mars Observer propulsion system, like much of the Mars Observer spacecraft, followed design practices more common to earth-orbiting communications satellites than to planetary missions. This was consistent with the plan to reduce costs by mandating maximum use of industry practices. A significant weakness of the Mars Observer propulsion system was in the design of the pressurization system, which regulates propellant tank pressures during main engine maneuvers. For conventional earth-orbiters, where the pressurization system is used for apogee boost to establish the proper orbit, the pressurization system is required to function for only a few days following launch. Typically, the pressurization system is then isolated from the propellant tanks. This mission duty cycle makes such spacecraft essentially impervious to regulator leakage and the effects of propellant vapor diffusion within the pressurization system. This is not true of planetary missions such as Mars Observer, which require high propellant flow rates years after launch. With the Earth-orbital design, the Mars Observer propulsion system had inadequate flexibility in pressurization system isolation and marginal control of propellant vapor migration. This design limitation may have contributed to the loss of the Mars Observer mission. Of three likely propulsion-related scenarios identified by the JPL Mars Observer Special Review Board, two could be attributable in part to inadequate review and consideration of the differences between earth-orbiting and planetary propulsion applications. These potential causes were (1) propellant reaction leading to pressurization system line rupture and (2) tank rupture due to regulator leakage. Reference(s): "Report of the Mars Observer Mission Failure Investigation Board," (Coffey report), December 31, 1993. "Mars Observer Loss of Signal: Special Review Board Report," JPL Publication 93-28, November 1993. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6 ("Engineering Practices: Inheritance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.7.1 ("Flight System Design: Propulsion System Design"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Science | Public | Not Specified |  | 01/24/1997
485 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Isolate the Propulsion Pressurization System from the Propellant Tanks (1993) | The “most probable cause” of the Mars Observer mission failure was identified as migration of substantial amounts of nitrogen tetroxide oxidizer upstream through the check valves where it condensed on the cold tubing. When the pressurization sequence was executed upon Mars encounter, the liquid oxidizer may have mixed rapidly with fuel in the lines and detonated. The recommendations included (1) preventing hazardous propellant vapor migration and (2) performing thermal analysis of pressurization systems to identify incipient conditions for propellant condensation. | Interplanetary missions should provide a means to positively isolate the pressurization system from the propellant tanks when high flow rates are not required, or ensure that the effect of propellant vapor migration into the pressurization system is benign. When check valves leak propellant vapors, lower temperatures upstream may cause propellant vapor condensation in the pressurization system. Perform thermal analysis of pressurization systems to identify incipient conditions for propellant condensation. | None | JPL | 12/12/1996 | The Mars Observer propulsion system design was inherited from an Earth-orbital application and incorporated a pressurization system employing helium to maintain the propellant tanks at a constant pressure. Regulation of propellant tank pressure prevents the tanks from rupturing, which would likely cause loss of the spacecraft. As gases are exchanged, pressure regulators and check valves prevent propellant and oxidizer from entering the pressurization system and causing a hypergolic reaction. Although nominal leakage through regulator check valves is anticipated, the pressurization system is fully isolated from the oxidizer tank early in an Earth-orbital mission following achievement of final orbit. For a Mars mission, however, high propellant usage is not required until months after launch, and substantial amounts of nitrogen tetroxide (NTO) oxidizer may migrate upstream through the check valves. Since the Mars Observer pressurization plumbing was cold for much of the cruise, liquid or gaseous NTO migrating through the check valves could have condensed on the cold tubing. When the pressurization sequence was executed upon Mars encounter, liquid NTO could have mixed rapidly with monomethylhydrazine (MMO) fuel in the pressurization lines. The resulting combustion could have ruptured the tubing, venting the helium pressure tank, damaging Mars Observer or inducing an unrecoverable spin. The Mars Observer Special Review Board identified this scenario as the "most probable cause" of the mission failure. Additional Keyword(s): Bipropellant Propulsion System, Propellant Vapor Diffusion Reference(s): "Adoption of an Earth-Orbital Propulsion System Design for a Planetary Mission," Lesson Learned No. 1-110. "Report of the Mars Observer Mission Failure Investigation Board," December 31, 1993. | JPL has referenced the lesson as supporting Paragraph 4.7.4.2 ("Propulsion System Design: Safety - Use of Passive Isolation in Bi-Propellant Systems"), and Paragraph 4.8.2.8 ("System Thermal Design: Temperature Control Design Performance - Propellant Vapor Migration"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  | Science | Public | Not Specified |  | 01/24/1997
487 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Long Term Materials Compatibility in Propulsion Systems (1993) | This lesson provides several examples of incompatible materials in propulsion systems that posed a major risk to Cassini and Mars Global Surveyor, and may have led to the loss of Mars Observer. Propulsion system components should be tested for long term chemical compatibility with propellants. Heritage systems should be requalified for mission environments for which they were not originally intended. | Propulsion pressurization system components suitable for missions where the system is isolated after a few days may not be suitable for interplanetary missions. Swelling of non-metallic components upon exposure to propellant vapors can result in propulsion system malfunction even if no chemical incompatibility exists. | Propulsion system components should be tested for long term chemical compatibility with propellants. The test should be performed by JPL or a qualified contractor if the component manufacturer lacks experience with propellants. Heritage systems should be requalified to verify their functionality in mission environments for which they were not originally intended. | JPL | 01/16/1997 | Incompatible materials in propulsion systems have posed a major risk to recent missions: Tungsten Carbide Ball Material: During JPL qualification test of the original candidate Cassini pressure regulator, the tungsten carbide/nickel regulator ball was tested for compatibility with nitrogen tetroxide (NTO) and monomethyl hydrazine (MMH). Exposure to the NTO oxidizer for 28 days caused substantial corrosion of the ball, and a surface roughness corresponding to a 42% increase in surface area. Another regulator design was therefore installed on Cassini; use of the original design would have caused serious pressurant leakage and possible system contamination problems. Flow Restrictor Braze Material: The pressure sensing ports in the pressure regulators contain flow restrictors which allow the regulator to sense and respond to downstream pressure changes. During the Cassini and MGS regulator heritage reviews, it was discovered that the MO restrictors contained a copper-bearing (AMS-4774) braze and a wax lubricant, neither of which are compatible with NTO propellant vapor. Neither of these materials were listed on the materials list for the regulator. Long term exposure to this vapor could potentially produce enough corrosion products to plug the restrictor orifice, which would likely lead to an inability to sense the downstream pressure and failure to regulate tank pressure. Such extensive exposure of the same regulator to propellant vapors would not normally occur on an Earth-orbital mission where pressurization is only required for a short period immediately following launch. These materials were eliminated in the MGS and Cassini regulator design. One of the credible hypotheses which had earlier been posed for the loss of the MO spacecraft was the plugging of identical flow restrictors due to long term reactions of propellant vapors with an unspecified incompatible material. Teflon Swelling: When the Galileo spacecraft executed 3 large delta V maneuvers with the main 400 Newton engine, restricted helium flow through the check valves caused significant pressure drops in the propellant tanks. The pressurization system is designed to hold the tank pressures constant during propellant flow. Pressure regulator performance was found to be nominal, but the flight propellant tank pressure data indicated significant degradation of both the fuel and oxidizer check valves. Ground tests have shown that swelling of the TFE Teflon valve bushing and PFA Teflon seal due to months of oxidizer exposure duplicates the flight behavior of the oxidizer check valve. Additional Keyword(s): Heritage Hardware, Mars Observer (MO) | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 ("Engineering Practices: Materials, Processes, and Contamination Control"), and Paragraph 6.6 ("Engineering Practices: Inheritance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.7.1 ("Flight System Design: Propulsion System Design - General") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 01/24/1997
483 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Free Dive Hazard |  | Always use the buddy system during free dives at any depth. | To prevent further mishaps, many actions can be taken: Do not hyperventilate prior to free dive. The buddy system should be used during all water operations. A qualified person, whose only task is to watch over all water operations, should be required to provide lifeguard services. A briefing on the medical aspects of diving should be held. Procedures should be reviewed to determine if they follow accepted diving industry practices for safety, training, SCUBA operations, management and record keeping. Personnel should be trained in emergency response and life saving skills. | JSC | 12/12/1996 | During a swimming skills test at an underwater training facility, an experienced dive instructor lost consciousness during a free dive (with mask and fins). The dive instructor was positioning a weight at the bottom of the pool when he lost consciousness. He was observed by his co-workers and the trainee, who was sent to retrieve him to the surface. Once on the surface, the instructor¹s condition was assessed and cardio-pulmonary resuscitation (CPR) was started. CPR was ceased after five or six compressions when the instructors breathing and heartbeat began. The most likely cause of the incident was thought to be shallow water blackout, or more correctly, breath-hold blackout. Although this is an uncommon event, shallow water blackout potentially can cause serious injury or death in as little as six feet of water. One of the greatest concerns of breath holding during a free dive is unconsciousness during ascent. When the diver descends, the air in his lungs is compressed, raising the oxygen partial pressure. This partial pressure increase of oxygen (PPO2) satisfies the bodies oxygen demand during descent and while on the bottom. During ascent, the remaining partial pressure of oxygen is reduced rapidly as the hydrostatic pressure on the body lessens. If the partial pressure of oxygen drops below 11 percent (83.6 mmHg) unconsciousness may result. This danger is increased when hyperventilation has eliminated normal body warning signs of CO2 accumulation. |  | N/A |  |  | Public | Not Specified |  | 01/08/1997
508 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Determining the Angle of Impact of an Object on a Thin-Walled Structure through Analysis of Acoustic Waves |  | Through analysis of the acoustic waves which result from impact, it is now possible to determine the angle of impact of an object on a thin-walled structure. | A patent was granted on 3-2-93 to William H. Prosser, NASA Langley Research Center, Hampton, Virginia, 23665; and, Michael R. Gorman, Aeronautics and Astronautics, Naval Postgraduate School, Monterey, California, 93943 for this method of measurement. | LaRC | 01/01/1994 | Currently, only one method is available for determining an object's angle of impact against a structure: high speed photography. This method requires a great deal of equipment and produces data, which requires a great deal of time to analyze. Presently, the acoustic emission technique is being used to assess damage caused by the impact of an object. As now used, this technique does not provide information concerning the angle of impact. However, a patent was granted on 3-2-93 for a method for determining the angle of impact of an object on a thin-walled structure through analysis of the acoustic waves which result when the object impacts. Transducers are placed on and in the surface of the structure which sense the impact waves caused in the structure. The waves are recorded and saved for analysis. For source motion normal to the surface, the antisymmetric mode has a large amplitude while that of the symmetric mode is very small. As the source angle increases with respect to the surface normal, the symmetric mode amplitude increases while the antisymmetric mode amplitude decreases. Thus, the angle of impact is determined by measuring the relative amplitudes of these two lowest order modes. |  | N/A |  |  | Public | Not Specified |  | 01/01/1997
482 | Milam, Laura - 0000000000 : NO@ADDRESS.GIVEN | Milam, Laura - 0000000000 : NO@ADDRESS.GIVEN |  | Test Delays Due to Late Set-up of Instrument Ground Support Equipment (GSE) |  | Allowing Instrument teams to arrive with their GSE just prior to testing can cause delays. Meanwhile, the clock is ticking and the marching army costs mount. The process of tearing down GSE and relocating the racks of equipment can cause unexpected failures and anomalies. | When scheduling I&T activities, allow adequate margin for Instrument teams to arrive, unpack and test their GSE. These activities should be completed in parallel with other activities and should be line items on the I&T schedules. Less complicated GSE needs at least a full day for setup and test. For more complicated set-ups allow at least 2 or 3 days. Instrument teams should allow for this extra time in their travel budgets. Make actual measurements for cable lengths from Spacecraft GSE locations to the Instrument GSE locations, and put measurements in an approved document such as an ICD. Allow extra length in cabling in case of location change. | GSFC | 11/07/1996 | During laboratory system level integration and testing for a GSFC satellite at a contractor's facility, testing was delayed or reordered because of problems with the Instrument GSE. The Instrument teams arrived the same day that the testing was to start, and when the GSE was hooked up, there were problems. The ensuing troubleshooting process caused delays in the start of testing. In some instances, the test procedure was reordered to workaround the problem. |  | N/A |  |  | Public | Not Specified |  | 11/13/1996
480 | Gonzales, Luis - 0000000000 : NO@ADDRESS.GIVEN | Gonzales, Luis - 0000000000 : NO@ADDRESS.GIVEN |  | Landsat Program, Multispectral Scanner (MSS), Technology Development |  | The overselling of the Multispectral Scanner (MSS) data capability and the emphasis on applications during Phase II and III made it very difficult to gain support for advancing the sensor and data processing technology. While serious definition studies were conducted early in Phase III, the actual development of an advanced sensor (TM) did not start until late in this phase. Also, no serious advance development was initiated on the next generation sensor: i.e. electronic scanners. | Too much emphasis on applications greatly retarded innovative advanced technology development. | GSFC | 11/07/1996 | The Landsat program was one of the first NASA programs to develop and introduce a major new capability with a broad commercial, public service, and scientific potential. Therefore, the insights to be gained from this twelve-fifteen years of experience might be of value not only in guiding the future research, development, and test (RD&T) activities in land remote sensing but also to other programs. The Landsat program and the related R&D programs to develop techniques for extracting useful information from Landsat data have been very successful. However, this success has raised a new set of questions; for example, how and in what form is the technology and capability to be exploited? By whom, the government or private sector? Should the operational capability be internationalized? What is NASA's future role in land remote sensing? With the proper planning NASA should have been in a position to have better answers to these questions. |  | N/A |  |  | Public | Not Specified |  | 11/13/1996
481 | Milam, Laura - 0000000000 : NO@ADDRESS.GIVEN | Milam, Laura - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate Exchange of Information Between Test Shifts |  | To assure efficient and accurate testing, proper communications must occur between test shifts. Written instructions should be kept in a single designated place. Logbook entries should be recorded in a consistent format. Adequate information is essential for troubleshooting during testing. | The information in the shift leader's logbooks needs to be expanded. It should include personnel on shift; a brief description of any events or tasks that occurred; the serial number of any problem or test anomaly report filed; the beginning and completion time of any test procedure and detailed shift carryover instructions. | GSFC | 11/07/1996 | During laboratory system level testing for a GSFC satellite at a contractor's facility, there was a lack of information exchanged between test shifts. Consequently, test instructions were not accurate or not passed to the proper personnel, information pertaining to problems was incomplete, test delays occurred and personnel were confused about their responsibilities. The lack of information also made it difficult to reconstruct events which occurred prior to and after anomalies. |  | N/A |  |  | Public | Not Specified |  | 11/13/1996
479 | Davis, Bill - 0000000000 : NO@ADDRESS.GIVEN | Davis, Bill - 0000000000 : NO@ADDRESS.GIVEN |  | XTE Instrument Problems |  | There is no such thing as a low risk heritage detector. Each detector is one-of-a-kind and should be treated as a high risk item with an appropriate amount of contingency and a good risk mitigation plan. In addition, the XTE detector problem clearly showed the value of flight spare detectors (even if degraded) which can remain on the Observatory to maintain the Mission schedule while other detectors are reworked and qualified in parallel. | When developing Mission schedules plan enough schedule and cost contingencies to allow for multiple iterations in the integration of flight detectors with the spacecraft. | GSFC | 11/06/1996 | The XTE Instrument Development Team experienced monumental problems with the development of the three small proportional counter detectors used in the All Sky Monitor Instrument. This was completely unexpected since the proportional counters were presented by the Instrument Development Team as low-risk heritage detectors that were nearly identical to detectors that had previously flown many times. As it turned out, the heritage vendor was unsuccessful in fabricating a working detector. After an exhaustive search by the Instrument Development Team, a second vendor was located in Finland. It took the new vender over a year to fabricate, test, and deliver the required three flight and one spare detector. Unfortunately, all of the detectors degraded after delivery and they needed multiple rework cycles of several months each to get acceptable flight detectors. The XTE Program Management Team was able to maintain the Mission schedule by installing degraded flight and/or spare detectors on the spacecraft during Observatory integration, testing, and launch site activities. The flight detectors were finally installed at the launch site. |  | N/A |  |  | Public | Not Specified |  | 11/07/1996
473 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | Storage Battery Explosion |  | Batteries stored on a charger can explode during use if overcharged. | Use automatic current limiting or timed circuit chargers when charging batteries. Operators should be aware of safe practices and proper battery charging instructions. | GRC | 07/26/1993 | A battery that was left on a charger over the weekend was used to start a gasoline power generator. This battery was connected in series with another battery and the connection on the negative post was hand tightened. When an attempt was made to start the generator, the battery exploded on approximately the fifth click of the starter solenoid. No damage was done to any equipment or facilities and no one was injured. The most probable cause of the accident was the severe overcharging of the battery (64 hours at 20 amp/hour). This charging created hydrogen, which combined with air or oxygen and an ignition source to form the explosion. One source of ignition could have been the loosely attached connection to the battery terminal. Another possible source may have been an internal short at the battery plates, distorted by the severe overcharge condition. |  | N/A |  |  | Public | Not Specified |  | 11/06/1996
474 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | Telephone System Failure |  | Lack of voice communications can have serious impact on the operations of a center and its safety services. | Prepare a contingency plan to standardize communications procedures for use during certain emergency situations. | GRC | 08/11/1993 | A new telephone system went into a total failure condition and remained that way for 10 1/2 hours. This failure resulted in the entire lab being without telephone service, external calls, internal calls and VMX service. The investigative team concluded that a switch failure caused the system breakdown. A contingency plan containing emergency procedures for a telephone system collapse was created. |  | N/A |  |  | Public | Not Specified |  | 11/06/1996
476 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Learning Zero-G Skills |  | Insufficient amount of time given to the payload crew to perform initial experiments in Zero-G can result in incomplete experiments. | Allot extra time during the experiment learning curve for the development of the payload crew's Zero-G skills. | GRC | 06/12/1995 | One of the first United States Microgravity Laboratory (USML-1) pre-mission timeline constraints addressed the number of hours that a crew member could be scheduled for payload operations. For the first four shifts of the missions, crew members could only be scheduled for 70% of the available time. For the remaining shifts of the mission, 90% of their time was available for experiment operations. The crew's comments indicated that this constraint was very valuable in preventing fatigue and supported the period of time during which space adaptation was occurring. However, because of the learning delay, experiments were unable to achieve science objectives during initial runs. As a result of this mission, it was recommended to continue the use of the timeline constraint for crew utilization and include more time early in the mission for a learning curve for the crew's Zero-G skills. |  | N/A |  |  | Public | Not Specified |  | 11/06/1996
475 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | Fit Check of Flight Hardware |  | Canister fit problems can result in significant overtime and delays. | Conduct a fit check of new flight hardware in full flight configuration prior to shipment to KSC. | GRC | 11/08/1993 | During ground operations at KSC, the first United States Microgravity Laboratory (USML-1) experienced canister fit problems with the LiOH flight storage containers. This resulted in significant overtime and nearly caused delay of the orbiter move to the Vehicle Assembly Building (VAB). The cause of the problem was that a fit check of the canisters in container foam was not done in the flight configuration at Huntsville, Alabama. |  | N/A |  |  | Public | Not Specified |  | 11/06/1996
477 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | IRT Fan Blades |  | Modification of IRT fan blades can result in more accurate data or higher test section airspeeds. | Replace the original IRT fan blades with a modified set of spares. | GRC | 06/12/1995 | In the gathering of test data for IRT fan blades, data was extrapolated for test section airspeeds greater than approximately 200 mph using the 20% air blockage models. A desire was expressed for more accurate results of higher test section airspeeds ranging up to 350 mph using the 20% air blockage models. A temporary method was found which would provide the desired airspeed at a relatively low cost. This new method consisted of replacing the original fan blades, installed in 1944, with a modified set of spares. The modification included reshaping the blade hubs to an increased angle of attack of 5 degrees. The modified fan blade's performance with a reasonable stall margin was calculated to have increased the test section airspeed from 190 mph to 245 mph using the 20% air blockage model. In addition, the drive motor, rated at 5000 hp, only required 2400 hp at 300 mph and maximum rpm. The modified fan blades will take advantage of the remaining horsepower with no alterations of the motor. | Tests were completed using the modified fan blades and their performance was found to be better than initial expectations. | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 11/06/1996
478 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Transmit Antenna Adjustment Limits vis Bi-axial Drive Assembly - ACTS |  | Friction is not sufficient to maintain precise alignments of mechanical attachment-type joints during any type of loading, especially launch loads. | Matched drill alignment joints with body-bound bolts or drill and pin joints after assembly. | GRC | 06/12/1995 | The transmit antenna on the Advanced Communications Technology Satellite (ACTS) has the capability to traverse in both elevation (north-south) and azimuth (east-west) directions in order to adjust the alignment between the transmit and receive antennas. The adjustment was to be accomplished by using a bi-axial drive assembly mounted between the transmit antenna and the spacecraft. The bi-axial drive assembly consists of two axial drive mechanisms mounted orthogonally. Each drive mechanism contains a stepper motor capable of rotating a minimum of 0.30 degrees in either direction, in steps of 0.0075 degrees +/- 0.0015. The structural joint between the bi-axial drive assembly and the transmit antenna was designed to accommodate final adjustments for final positioning or alignment of the transmit antenna. The joint was held by friction with shims via four bolts through large holes to allow for adjusting or shifting of the transmit antenna for final RF alignments. The mechanical joint between the bi-axial drive assembly and its mounting to the spacecraft allowed the transmit antenna to shift locations during launch aboard STS-51. The four bolts did not maintain the proper preload and the joint slipped during launch loading. This has reduced the available design adjustment range for the ACTS transmit antenna. |  | N/A |  |  | Public | Not Specified |  | 11/06/1996
470 | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Connectors - Scout Program |  | Unmated or mismated electrical connectors can be the cause of functional problems. | Minimize connector cycling. Visually re-inspect connectors prior to mating. Verify that all applicable connectors have been mated prior to proceeding with testing. Tapered socket entry should be considered as a feature of the connector design. | GRC | 07/22/1994 | Various times throughout 1960-1975, functional problems were encountered because a set of connectors were unmated or contacts in the connector were deformed as a result of misalignment during mating. The unmated connector condition was the result of deviating from normal processing. Break of inspection sheets were added to applicable logbooks to alert test technicians and engineers of the unmated connectors. When the connector was remated, the condition was verified on the break of inspection sheet. Deformed contacts were often the result of slightly bent pins or the misalignment of pin and socket at the time of mating. Tapered socket entry reduced this problem. Misalignment of replaceable contacts was sometimes caused by wire routing at the rear end of the connector. If inspectors had performed a visual examination of both connectors prior to mating, misalignment of contacts would have been greatly reduced. Further information can also be obtained by contacting the Reliability and Quality Division of Loral Vought Systems at P.O. Box 650003, Dallas, TX, 75265-0003 or calling (214) 603-1000. | Possible failures were reduced because the contact alignment condition cannot be visually verified after mating, and functional tests may not always detect bent pin problems, such as electrical shorts to other circuits. | N/A |  |  | Public | Not Specified |  | 11/01/1996
468 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | Operation Training for KSC Personnel |  | Mission schedules can be disrupted if contingency time is not allowed for training on new mission-support hardware. | Plan for the training of KSC personnel on new hardware. | GRC | 11/08/1993 | During ground operations at KSC, the first United States Microgravity Laboratory (USML-1) did not allow contingency time for the development and installation/test of new hardware. Delivery of a new Payload General Support Computer-Data Display System (PGSC-DDS) did not support the scheduled start of systems test. Also, training was not planned for the Master Memory Unit (MMU) tester and the PGSC unit tester. |  | N/A |  |  | Public | Not Specified |  | 11/01/1996
469 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | Special Tests at KSC |  | Special payload tests can disrupt major ground operations test activities and schedules unless separated from the major ground operations test. | Provide extra contingency time in the KSC ground operations schedule for the completion of any special tests. Avoid any last-minute additional or special ground processing / operations during MST day. | GRC | 11/08/1993 | During ground operations at KSC, the first United States Microgravity Laboratory (USML-1) took longer than projected to perform a special module acoustical test. This occurred on the last Mission Sequence Test (MST) day and caused the MST time slice to be shortened. MST days are scheduled as full 12-hour test days and have no room for special tests. |  | N/A |  |  | Public | Not Specified |  | 11/01/1996
472 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Replaceable Contacts in Electrical Connectors - Scout Program |  | Electrical connector contacts with replaceable pins or sockets may not function properly from damage caused by the mating processes. | Perform a push test prior to mating to detect and screen for unlocked contacts where the connector has replaceable contacts. | GRC | 06/13/1995 | Recessed electrical contacts in connectors, with replaceable pins or sockets, were observed as a result of a functional failure or during visual examination. The contacts were either not properly locked or became unlocked in the connector insert. During connector mating, the mating contact would push the contact backwards. Improper locking was often the result of deformed or broken retention clips. The Scout Program fabricated a set of push test tools. These tools have the proper mating contact and permit the application of an appropriate force on the contact in an assembled connector. After initial wiring and modifications of the electrical connector, a push test was performed on each contact in the connector. Contacts and connectors failing the push test were rejected per established procedures. | This test significantly reduced the problem of recessed contacts in electrical connectors and decreased costly replacement in the field. | N/A |  |  | Public | Not Specified |  | 11/01/1996
471 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Contamination from Failures caused by Fluid Filters - Scout Program |  | Fluid filters can be a source of contamination if they are dirty or fail structurally. | Perform a high pressure flush on safety-critical filters prior to their addition into a system. Avoid manufacturing processes which can damage filters during fabrication. | GRC | 06/13/1995 | A number of H2O2 motor valves in the H2O2 fuel system of the Scout Missile experienced leakage due to contamination of the valve's teflon seats. Failed parts analysis revealed minute stainless steel particles embedded in the teflon seats. This contamination prevented complete closure at the poppet to seat interface. Examination of the contamination exposed particles larger than 20 micron. Each valve was protected at the fuel inlet by a 15-20 micron filter. An extensive failure investigation discovered that the contamination was being induced by the stainless steel filter itself. Fabrication of the filter was accomplished by press fitting an inner ring into a larger diameter ring after inserting the meshed screen circular filter. This technique essentially sandwiched the screen between the two rings. Bi-sectioning of several filters revealed that the frayed ends of the meshed filters screen were being temporarily trapped between the rings. Subsequent high pressure fuel flows usage dislodged the particles and the resultant contamination. Since the contamination was being released behind the filter, the filter was ineffective. |  | N/A |  |  | Public | Not Specified |  | 11/01/1996
462 | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN |  | Motor/Igniter Shelf Life - Scout Program |  | Vehicles with solid rocket motors older than the shelf life recommended by manufacturers can be launched. | Maintain extensive files related to rocket motor component's weight, age, in-process testing, ballistic performance, and inspection. Update and analyze for effects on motor structural and ballistic performance. | GRC | 07/25/1994 | Motor information was routinely tabulated during the manufacture of solid rocket motors. This information was furnished by the motor vendor (or obtained by resident representatives) from in-process propellant mechanical and ballistic properties testing. Typical properties included stress, strain, density, liquid-strand burn rate, propellant burn rate from subscale motor testing, and peel strength. Once logbooks were available, other parameters were tabulated. Typical properties were motor assembly total weight, propellant weight, case weight, linear weight, insulation weight, igniter propellant weight, igniter assembly weight, and nozzle assembly weight. Post-flight motor performance information was tabulated for all flights (some fourth stage motors were not instrumented). Information items included thrust and chamber pressure. From these items were calculated Isp, total impulse, web burnout time, total burn time, and the pressure integral. Beginning in 1984, age related information was accumulated for the solid rocket motors to aid in engineering evaluation of motor shelf life. Typical information accumulated from storage site inspections, return-to vendor inspections, or launch site receiving inspections which included propellant shore a hardness, radial slot width measurements, and visual inspections of the propellant grain surface and bond lines. As a result of the evaluation of motor shelf life, the Scout Program has been launching vehicles with motors that are well beyond the shelf life established by the motor manufacturer. Motor production to replace aging motors is costly. Use of the tabulated age related information allowed engineering and quality/reliability personnel to extend motor shelf life. New production was not required. Inventory motors could be flown. Further information can also be obtained by contacting the Reliability and Quality Division of Loral Vought Systems at P.O. Box 650003, Dallas, TX 75265-0003 or calling (214) 603-1000. | The maintenance of extensive data files related to rocket motor information resulted in cost savings during motor production, a higher reliability of pre-flight motor performance predictions, and use of older motors. | N/A |  |  | Public | Not Specified |  | 10/25/1996
465 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Crimped Electrical Connections - Scout Program |  | Manufacturers' Recommendations for crimped connector settings are not always correct and can result in inadequate crimp conditions. | Perform frequent periodic sample pull tests on crimped connections. | GRC | 06/13/1995 | Functional failures were attributed to varying resistance values through crimped electrical connections (contacts, splices, terminals). The variation was from several milliohms to open circuits. Microscopic examination of the cross-section of the crimped area revealed either insufficient crimping or excessive deformation of the wire strands. Samples of the various combinations of crimp connections (connector pins, connector sockets, terminal lugs, or splices) and wire gauges were made using various crimp tools and settings. Cross-sectioning of these samples indicated that the manufacturers' recommended settings and positioners did not always provide the best crimp conditions. Pull test results on similar crimp connections correlated with the cross-section conclusions. In 1975 the Scout Program established its own crimping standard, which specified the crimp tool model, contact positioner, and setting (if applicable) for each connection type (manufacturer and part number), single or double leads, and stranded wire gauge. Crimping on solid buss wire was not considered acceptable. All applicable personnel were trained and certified on crimping and assembling contacts on connectors. Each day a specific crimp tool (serial number, model) was used, two samples of the specific anticipated combination (contact part number, wire gauge(s)) were made and each sample was subjected to a pull test. Both samples had to meet the established pull test requirements, which were based on the wire gauge capability. After meeting the pull test, the production hardware contacts were crimped. If a sample failed, then the tool was rejected per established procedures. Similar crimp contact controls have been imposed on applicable vendors and subcontractors. | Improved requirements significantly reduced the problem of unstable circuit resistance through crimped electrical connections. | N/A |  |  | Public | Not Specified |  | 10/25/1996
463 | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN |  | Atlas Booster Engine Precision Regulator - Atlas/Centaur Program |  | Reworked screws can be the cause of decayed precision regulator output if rework instructions lack requirements for set screw torquing and verification by a quality inspector. | Provide corrective action to prevent the stem screw from undesired rotating, improve system margins, improve data evaluations, and improve quality processing. | GRC | 07/25/1994 | On March 25, 1993 an Atlas/Centaur launch vehicle (AC-74, Atlas1) inserted a Hughes UHF follow-on spacecraft into orbit with an apogee altitude of 4,967 nmi instead of the targeted nominal of 9,098 nmi. Although functioning normally, the satellite was declared a loss by the Navy due to the unacceptable orbit. The investigation team concluded that the precision regulator in the booster engine system failed. The output pressure of this regulator controls the output power level of the booster engine, which caused the decline in thrust. This failure was caused by the stem screw rotating and decaying the output of the precision regulator. This precision regulator had been reworked twice during its build to repair excessive vent port leakage. The first authorized rework required loosening and retorquing the set screw. The set screw has been redesigned so that it is custom made for each mission. The length of each screw is predetermined and inserted so that rotation is impossible to achieve. Further information can be found in the AC-74 Anomaly Investigation Summary Report. | With the redesign of the set screw, there have been no further failures of this type. | N/A |  |  | Public | Not Specified |  | 10/25/1996
464 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Payload Activation |  | Payload activation may require considerably more time than the pre-mission scheduled time to allow for the crew to acclimate to zero-g. | Reserve more time on first shift for payload activation. | GRC | 06/12/1995 | The first United States Microgravity Laboratory (USML-1) pre-mission timeline approximated 20 minutes for the payload crew to activate the payload. Since extra time was necessary for the crew members to adjust to zero-g, the actual payload activation time was approximately 55 minutes. In future flights it is suggested that more time is allotted on the first shift for payload activation. |  | N/A |  |  | Public | Not Specified |  | 10/25/1996
466 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Nozzle Aging - Scout Program |  | Nozzle aging experience indicates nozzles can have age related problems. | Include nozzles and related components in shelf life surveillance programs. | GRC | 06/14/1995 | During the visual receiving inspection process of the fourth stage Altair IIIA motor for a 1984 launch from the Wallops Flight Facility, a delamination was found in the silica phenolic exit cone liner. A similar delamination was found in a nozzle being processed for a Vandenberg Air Force Base launch. An immediate visual, ultrasonic, and radiographic inspection of the remaining inventory of silica phenolic exit cone liner nozzles found one other nozzle that was suspect. The same inspections were completed concurrently for inventory nozzles that included graphite phenolic exit cone liners. No delamination indications were found in the carbon phenolic exit cone liners. The delamination was determined to be a moisture related problem associated with silica phenolic. A monitoring program was established for the remaining silica phenolic nozzles and carbon phenolic nozzles. This monitoring consisted of storing the nozzle assemblies in the Dallas Scout Logistics Area, monitoring humidity, and attaching gages to one of the carbon phenolic nozzles and a dissected nozzle piece to measure strain on a periodic basis. Visual, ultrasonic, and radiographic inspections were completed at Dallas just prior to shipment to verify that a flightworthy nozzle would be shipped to the field site. | Continued monitoring of the silica phenolic or graphite phenolic exit cone material in the Altair IIIA nozzle revealed no other delamination. This meant that a production was not required and inventory nozzles could be flown. | N/A |  |  | Public | Not Specified |  | 10/25/1996
467 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Centaur RL10 Rocket Engine Check Valve - Atlas/Centaur Program |  | If the check valve on the Centaur RL10 rocket fails to close, an ingestion of air can occur. Solidification of this air will prevent the engine turbopump from rotating causing engine failure. | Change the design process to include a cause/effect methodology. Conduct corrective action to prevent air ingestion. Improve system margins with several procedural changes. | GRC | 06/14/1995 | On August 22, 1992 an Atlas/Centaur Launch Vehicle (Atlas 1, Launch AC-71) carrying a Hughes Galaxy I-R Spacecraft was destroyed in flight. The Centaur C-1 engine had failed to achieve full thrust, resulting in an uncontrolled tumble of the vehicle. The guidance system, sensing that the vehicle had not achieved proper acceleration, shutdown both engines and instituted a restart sequence. Once again the C-1 engine failed. Full thrust was achieved by the C-2 engine both times. In lieu of the C-1 thrust failure the vehicle was destroyed by the range safety officer. To start reliably, the RL10 engine requires proper fuel and oxidizer pressure at its pump inlets and the fuel and oxidizer pumps to be at the proper cryogenic temperature. The engine temperature results from a two-stage chilldown process. The prelaunch chilldown is provided by ground dewars supplying pressurized helium. Each RL10 engine receives the flow of helium through a check valve. These valves should close when the flow is terminated to prevent further flow of any gas through the engine via the chilldown ducts exiting the vehicle. The state of the chilldown check valve was not monitored. As a result, the check valve of the C-1 engine was not closed and an ingestion of air occurred which eventually caused the engine to fail. The investigation team also concluded that AC-70's failure is due to the same cause as AC-71. For more information on AC-70, see AC-70 Anomaly Investigation Summary Report. Further details on the AC-71 failure are found in the AC-71 Anomaly Investigation Summary Report. | Changes were made to the failure analysis process of flight anomalies. | N/A |  |  | Public | Not Specified |  | 10/25/1996
409 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager Gyro Swap During Launch Phase (1977) | Because the Voyager 2 failure protection logic was unnecessarily enabled during launch, transient gyro outputs triggered a series of alarming “gyro swaps.” Careful attention should be given to preclude the possibility of spurious inputs triggering unwanted events when the protection logic is enabled. | It is suggested that failure protection logic be enabled only when the protected components or subsystems are required for spacecraft operation. Careful attention should be given to preclude the possibility of spurious inputs triggering unwanted events when the protection logic is enabled. | The gyros were not used for attitude control until just before separation from the Centaur. Thus, the failure protection logic function was not needed until that time. To prevent a recurrence of the Voyager 2 experience, the failure protection logic was disabled on Voyager 1* during periods of launch vehicle thrusting. * Voyager 1 was launched after Voyager 2. | JPL | 06/24/1996 | (Relevant Historical Lesson(s) Learned) Voyager 2 experienced gyro control problems during launch because its failure protection logic was enabled. Attitude control required data about all three spacecraft axes: roll (R), pitch (P), and yaw (Y). The three 2-axis gyros on Voyager provided data, respectively, about the R-P, P-Y, and Y-R axes. Thus any two gyros together provided the required three axis data, plus a fourth, redundant set of data about an axis common to both gyros. The third gyro acted as backup. The gyros, not needed until just before separation from the Titan/Centaur, were left "on" and thus warmed up during launch to ensure immediate readiness. The failure protection logic, also left enabled during launch, sensed failure by comparing the output of the axis common to both controlling gyros. If not equal, the "back-up" replaced one controlling gyro. If still not equal, the gyros were switched again. Continued inequality among all possible gyro pairs caused the logic to look elsewhere for the problem. It was understood a priority that the gyro output would "saturate" during launch, and that this saturation output would be at equal limiting values, thus ensuring a valid logic comparison. Instead, however, the output oscillated significantly, causing a mis-comparison. Telemetry then indicated the series of "gyro swaps" as the failure protection logic attempted unsuccessfully to pair gyros having equal output. This led Mission Operations to suspect a major failure on Voyager 2. | JPL has referenced the lesson as supporting Paragraph 4.9.2.1 ("System Fault Protection Design: Fault Protection Response - Fault Protection Priorities") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/16/1996
460 | Bott, J - 0000000000 : NO@ADDRESS.GIVEN | Bott, J - 0000000000 : NO@ADDRESS.GIVEN |  | Glass Cased Components Fractured as a Result of Shrinkage in Coating/Bonding Materials Applied in Excessive Amounts (1963) | Shrinkage during the curing of hard set, epoxy based, conformal coating caused cracked glass cases in many axial lead diodes in Ranger and Mariner flight computers. The lesson recommended investigating coating and bonding material properties, avoiding excessive amounts of coating, and performing post-cure inspection. | Unnecessary or excessive application of materials used for coating or spot bonding may have unexpected side effects. Materials used for coating and spot bonding applications may have unexpected side effects. Thermosetting epoxies and others which cure to a hard, inelastic consistency may have destructive side effects, i.e. shrinkage, outgassing, unusual viscosity characteristics, tacky surfaces, etc. Some coating/bonding materials go through a low viscosity watery state during the cure cycle, which can lead to slumping of the material, allowing it to run into unintended locations where its presence was not anticipated. | Investigate the properties of any coating or bonding materials being considered for use with respect to vulnerabilities in the intended application, particularly with respect to new materials for which there is no prior use history. Avoid the use of excessive amounts of coating or bonding materials, and specify the thickness and configuration to be used for applications. Perform a post-cure inspection of the coating/bonding material to verify thickness and configuration. | JPL | 10/03/1996 | Microscopic inspection under 10X magnification of a completed Ranger Central Computer and Sequencer (CC&S) Subsystem revealed a relatively large number of cracked glass cases in axial lead diodes. The fractures frequently extended lengthwise along the glass case from lead entry to lead exit at the opposite end. The fractures usually occur at the edge of heavy accumulations of hard set epoxy based conformal coating and/or spot bonding materials used to secure the components to substrates. The problem was found to re-occur with several similar types of coating/bonding materials then and still available. This problem necessitated the development of a new process to soften the coating/bonding material, and stripping the material away from hundreds of glass diodes. A large number of fractured diodes were replaced. The problem was also evident in other subsystems which had been built prior to discovery of this problem. Subsequent investigations into other applications where these materials were used revealed the existence of cracked glass diode cases in a Mariner Attitude Control (AC) Subsystem under construction at another contractor. The source of the cracked glass problem was traced to an .8% Shrinkage factor during the cure cycle in the coating/bonding material, which also had very good adhesive properties. Contraction in a heavy application of the hard set coating or spot bonding material which enclosed 50% or more of the diode case diameter literally pulled the glass case apart. Those which do not fracture during the cure cycle may be assumed to be severely stressed, and possibly subject to failure under subsequent environmental exposure, including acceptance testing and flight exposure. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/11/1996
458 | Montague, Ronald - 0000000000 : NO@ADDRESS.GIVEN | Montague, Ronald - 0000000000 : NO@ADDRESS.GIVEN |  | Coordination of Facilities Operations Between Facility Users and Providers of Support (e.g., maintenance) Services |  | Coordination of discrete operations in a facility is needed to preclude the deactivation of required emergency systems especially during a hazardous operation or test activity. Coordination must be an integrated process involving at least one person knowledgeable in the facility's planned day to day operations. | A single point of contact for each JSC facility was implemented to ensure that all operations in the facility (including access)are controlled and managed to ensure appropriate coordination of operations. This point of contact is described in the Facility Manager Functions covered by a human resources letter dated 11/30/94. Pre- and post-test fire technicians' checklists for Bldgs 32 and 33 have been generated. The use of emergency information signs must be in accordance with emergency action plans to preclude misleading information or direction being implemented. Fire alarm system disarming procedures now require an advance approval of a request from the Facility Manager and from work control prior to activation and deactivation of such systems. The procedures for these requests are JJMU-1001, Fire Suppression System Arming Checklist and JJMU-1004 Fire Suppression System Deactivation Checklist. | JSC | 09/17/1995 | During an engineering test, organizations external to the test organization were performing maintenance activities in the test vicinity. Welding was being performed in a test facility, which resulted in the deactivation of the facility's fire alarm bells during the first few days of a test. This condition was discovered by chance observation and not during inspection nor during normal pre-test activities. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
457 | Montague, Ronald - 0000000000 : NO@ADDRESS.GIVEN | Montague, Ronald - 0000000000 : NO@ADDRESS.GIVEN |  | Safety Engineering Analysis of Low Hazard Systems Interfaces with High Hazard Systems |  | Low hazard systems must be addressed by supporting safety engineering analyses (failure modes and effects, hazard analysis, etc.) to identify vulnerabilities at the interface with high hazard systems. Such analyses will identify the need for additional and/or modified controls. | Include other organizations in emergency drills and enact responses to emergency scenarios. Notifying supporting areas of hazardous materials usage including attachment of a Hazardous Materials Statement to the Area Notification Memo. Obtain test management training on JSC site emergency procedures and organizational response. Prepare emergency kits to retreat to if driven from primary test areas. Incorporate failure modes and effects analysis and/or hazard analysis to check fluid interfaces, freeze points, and rupture areas including effects of failure. Permanently amend operational checklists to restrict personnel access above 2nd level during testing. Amend test facility guidelines (including those for test build-up) to discuss relief valve rules pertaining to safety and human factors. ALL ABOVE RECOMMENDATIONS HAVE BEEN IMPLEMENTED. | JSC | 09/17/1995 | During repressurization of a test chamber, ammonia in a test article heat exchanger froze resulting in rupture of the exchanger. The rupture caused pressure to build up in a second test support unit. This second unit had a pressure relief valve, which was released when the pressure exceeded the upper limit, spilling ammonia into the work environment. The facility had to be evacuated. The root cause of this mishap was failure to treat "low hazard" systems, when connected to ammonia systems, as ammonia hazard systems. Had this been done, the design of the relief valve would have been configured to preclude direct venting of the valve into the facility work environment. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
455 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Nonmetallic Materials Certification |  | Vendor's materials certification processes must specify recertification for substitute materials. | In critical applications, physical properties testing must be accomplished to assure that materials substitutions are acceptable. | JSC | 08/19/1991 | A flight life support system battery leaked when a vendor substituted the certified material with a substitute in the manufacturing of the relief valves and the electrolyte decomposed it. The vendor certification was for the original material only. Substitute materials generally require recertification prior to use. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
456 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | High Electrical Current |  | Circulation pump heated to approximately 240 degrees F with pressure increase in reservior and accumulator. | Flight procedures must state pump not be operated longer than 60 seconds at a time when no outlet pressure is present. | JSC | 05/09/1991 | Electrical test determined no electrical shorts to case. However, an internal direct short was detected. Attempts to restart pump should not be less than 60 seconds elapsed time. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
449 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Migration of Conductive Contaminates in an Electrical Switch in Zero "G" |  | Excess wear led to migration of conductive contaminates into electrical contacts. High (off limits) temperatures were required to open contacts. | Test electrical components at expected vibration levels to establish usable life limits. | JSC | 12/15/1990 | APU 2 Fuel Pump Heater was cycling high during flight. Detailed analysis of the thermal switch showed extreme wear from the switch bi-metal disc and case. Large amounts of conductive contaminates were found. Analysis showed that they came from the disc and case. It is concluded that excessive vibration caused the wear and in zero gravity particles were free to migrate into the electrical contacts, resulting in a higher disc deflection to open the thermostat contacts. The result is a higher heater turn off temperature. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
450 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Emergency Procedure Training for Critical Operations/Areas |  | Personnel working in critical equipment areas with no training in emergency procedures resulted in a delayed response causing additional damage. | Train personnel working on critical systems in emergency procedures to reduce the response time for emergencies. | JSC | 04/04/1991 | While installing electrical cables into a conduit in the Johnson Space Center Mission Control Room, the conduit was displaced from its mounting, and then contacted and broke a chilled water line. A portion of the room was flooded. The installation procedures did not include details for using sufficient lubrication on the cables being pulled through the conduit. Also, no cautions or warnings were provided to alert the electricians to take additional precautions to prevent accidents in a high value, mission essential area. Other factors that increased the extent of damage included; (1) An emergency plan that did not include water leaks, and (2) No information was available to the maintenance or operations personnel on the location of or access to shutoff systems. The investigation board recommended correcting the deficiencies in the work procedures, emergency plans, and Mission Control allowable work policies. Also recommended was increased training of personnel to include these improvements. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
451 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Distributor Conformance Certification |  | Errors in a distributors materials conformance certification resulted in use of incompatible material used to assemble quick disconnect. | Request a copy of manufacturers material lot certification along with distributors conformance certification when purchasing materials. | JSC | 07/03/1991 | When a quick disconnect was checked for compatibility with hydrazine the "O" seal disintegrated. It was found to have been made of material other than the required Ethylene-Propylene Rubber (EPR) material. The distributor had provided a certificate of conformance traceable to a seal manufacturers lot number. Upon a request for the manufacturers certificate of conformance they could not provide traceability for 40 pieces of a lot of 500 seals. They provided traceability for 460 of the seals. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
453 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | Smoke Alarm Procedure Verification |  | Ground and flight self testing procedures for smoke alarm must match to perform accurate self test activation during flight. | Verify ground and flight testing procedures have the same requirements. | JSC | 07/31/1991 | Flight deck (left side) smoke detector failed self test. Ground procedures specify alarm must sound within 120 seconds. Flight procedures specify alarm must sound with 15 to 25 seconds after activation. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
454 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | Assembly of Vacuum Vent Valve |  | Improper torquing of the Waste Collection System (WCS) vent valve knob retention screw caused the knob to work its way off the shaft. | Add mandatory inspection point to procedure to verify mechanical stop mounting screws are properly torqued. | JSC | 07/30/1991 | The excessive torque problem was due to improper assembly. The mechanical stop mounting screws were loose permitting the mechanical stop to move away from the housing toward the control housing. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
452 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Failure Analysis Investigation |  | Failure analysis of a component in a system did not consider the effects of the failure on the system. | Evaluate the effect of a component failure on the system when investigating the failure of a component in a system. | JSC | 07/11/1991 | The failure analysis of a temperature probe for a cryogenic hydrogen system was investigated by instrumentation systems engineering for effects on the instrumentation system (loss of output from one temperature sensor which is minor). The potential effects of the defective weld (piece of the probe entering the liquid hydrogen system) was not recognized till later as catastrophic. |  | N/A |  |  | Public | Not Specified |  | 09/30/1996
448 | Bryant, Paul - 0000000000 : NO@ADDRESS.GIVEN | Bryant, Paul - 0000000000 : NO@ADDRESS.GIVEN |  | Fusing Element Failure resulting from Test Integration, Test, Pyrotechnic Devices, PYRO, Electrical Explosive Devices, EED, Command Circuit, Drive Circuit |  | EED I&T tests can appear to be successful while concurrently damaging the fusing element so that subsequent EED firing is impossible. If fusing resistor damage is not found, the result could be a launch with one or more dead EED channels. | An obvious recommendation is that the status of the fusing element be verified after the last EED live fire test, before launch, which would stress the fusing element. Another recommendation would be NOT TO USE THIS DESIGN. If it is desired to break all connections to the power source then this could be done with an arm and a prearm single pole elements in each leg of the design or with double pole elements. Best of all options would be to not use this kind of ground fire pulse design AND check the status of fusing element after each use of the circuit and prior to launch. It is crucial that for any designs like that shown the fusing element be checked at least once before launch and after the last test that would stress the fusing element. | GSFC | 09/11/1996 | Recently on a Goddard Space Flight Center (GSFC) spacecraft program, a contractor had concluded successful live fire tests on the EEDs (Electrical Explosive Devices, also called Pyros). Subsequently it was found that the live fire tests had not only fired the EEDs but had also damaged the drive circuit. The damaged component was the EED circuit fusing element. This component would not provide sufficient energy to fire an EED when required during the mission. This then could have resulted in failure to fire EEDs during the mission. GSFC engineering had mandated that the drive circuit be tested after the live fire test. This drive circuit test was to demonstrate the drive circuit vitality. Fortunately, the mandated tests were done, the damaged parts found and appropriate corrective measures taken. The last paragraph of this document contains a test recommendation to preclude launching with a "dead" EED system (typical I&T EED tests may appear to be successful but the typical test can actually damage the EED drive circuit). This paragraph was written as an executive summary with the last paragraph being the summary recommendation. The other paragraphs provide more detailed information on the problem. Early concerns about the Pyro circuit design included unconventional EMI shielding, unconventional EED firing via a ground pulse, firing current sustained after initiation, overcurrent protection by using a resistor (current-time curves were not available from the contractor), and the safing plug location that precludes verification of EED status. The Contractor maintained that the design was the same as that used repeatedly on all of their programs. (It was subsequently discovered that the fire pulse design has not been consistent on their programs.) The contractor also maintained that the design minimized hazard risks and therefore was acceptable. They were insistent that since they had already fabricated the assemblies a change to the design would substantially impact the program. GSFC insisted that as a minimum after any EED test firing, the Contractor must conduct a test to verify the resistance value of the EED fusing resistors. No change was made by the contractor to alter the unconventional EED firing via a ground pulse. [D] During the tests to verify the resistance value of the EED fusing resistor, it was discovered that in one channel the fusing resistor value was 15 times the required value. Therefore, the fusing resistor would no longer activate a flight installed EED. When the assembly was opened, the resistor was found to be charred. Evidence points to this being a result of EED firing via a ground pulse and the EED establishing an internal path to ground that resulted in a sustained current until the pre-arm/arm path was interrupted by fusing resistor failure. Another fusing resistor was also discolored but had the correct resistance value. The discolored resistor was then further tested to confirm that it could provide additional adequate fire pulses. The Contractor did limited testing and confirmed that the discolored (but correct resistance) fusing resistor was capable of repeatedly providing fire pulses with adequate energy. This result appears to confirm that a measurement of resistance value was adequate to determine drive circuit functionality. The mechanism for the damage appears to be the ground firing pulse combined with the known effect of EED shorting to case during discharge. The enclosed figure is a simplified diagram of the ground firing pulse configuration. The prearm and arm contacts are closed or opened by ground command for extended periods. The duration of positive voltage application is mostly dependent upon intervening operations. However, a minimum duration on the order of a few hundred milliseconds would be expected from the contractor's implementation. The fire pulse is a 40 ms ground activation pulse. If the prearm and arm commands are executed, the EED only needs the fire pulse ground connection to initiate. Once the fire pulse occurs then a "sneak" circuit can occur internal to the EED by either the bridge wire shorting to the EED case or by a low resistance plasma path to the case (information seems to indicate that this kind event occurs in about 4 percent of EEDs). If this happens, high current will flow until either the fusing resistor opens or the prearm or arm functions are deactivated. A short duration fire pulse on the positive voltage side would not have caused fusing resistor damage. If the fire pulse were placed on the positive side of the circuit instead of the ground side a high surge current could still occur but only for the duration of the 40ms fire pulse instead of the much longer duration of the prearm and arm relays. |  | N/A |  |  | Public | Not Specified |  | 09/19/1996
443 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | High Voltage Electric Circuits |  | Personnel injury and hardware damage can result if inaccurate drawings are used for preparation of power switching instructions. | Assure that approved drawings (verified, accurate and complete) are used to prepare power switching instructions or any maintenance procedure. | GRC | 11/16/1992 | During the removal of power to a transformer prior to it being serviced, an accidental 2400 Volt line to ground short circuit was created resulting in minor injury to a technician and minor hardware damage. The major contributing factor to this mishap was the use of a drawing that was not adequately checked after additions and changes had been made to the system. The secondary factor was that the technician did not test the voltage on the line side of the potential transformer compartment to verify that the bus was in fact de-energized. |  | N/A |  |  | Public | Not Specified |  | 09/13/1996
442 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | Pre-Run Checklists |  | Research and/or operation engineers may overlook important test set-up operations unless they are included and emphasized in the pre-run checklist. | Include all important test set-up operations in pre-run checklists with special emphasis on instrumentation and meter settings for alarm and shut down. | GRC | 11/13/1992 | A roof fire occurred in Cell 23 of Building 35. An Accident Review Team concluded that the cause of the fire was the inoperability of the water quench system used to cool the hot combustion gases exiting the test section. The problem was that the ACROMAG Transmitter was not plugged in and had remained closed. It did not regulate the appropriate amount of quench water for a given hot exhaust temperature. The quench water system had facility alarm and shutdown meters which monitored exhaust gas temperatures downstream of the quench spray station. The high limits for these meters were set too high (800 and 860 degrees F, respectively) and should have been set at 650 degrees F. These meters were designed to monitor the exhaust gas temperatures and shutdown the fuel system if the limits for the exhaust gas temperatures were exceeded. |  | N/A |  |  | Public | Not Specified |  | 09/13/1996
444 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Connectors |  | Differently keyed connector halves can be partially mated and cause arcing and short circuiting. | Use scoop-proof connectors for future applications where interchangeability is possible and provide for greater visibility of battery connectors to prevent mismate. | GRC | 07/30/1993 | During mating of the Magellan Spacecraft connectors within the forward equipment module (a confined space with limited visibility), the technician observed sparks, flames, and smoke. The primary cause was the inadvertent mating of at least two pins of the spacecraft harness connector P2 to connector J3 of Battery 1. The mismate of these connectors created an electrical short circuit within the J3 connector that, using the energy stored in the battery, produced the damage on Battery 1, connector P2 and the battery thermal blanket. |  | N/A |  |  | Public | Not Specified |  | 09/13/1996
447 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Component Anomalies Log - Scout Program |  | Components may have anomalies that are within specification and which later become the source of other problems. | Responsible system engineers should maintain a log for all components, which have anomalies that are within specification. | GRC | 06/12/1995 | At the Loral Vought Systems in Dallas, Texas prior logbook test data history was evaluated as part of a normal failure investigation. During this review a trend in data was sometimes observed that indicated a prior drift or shift towards an out-of-tolerance condition. The Scout Program initiated a test data monitoring program on selected assemblies. Design, quality and/or reliability engineers reviewed the test data after each retest on the assembly or vehicle level. The appropriate engineer maintained supplementary notes. The list of assemblies to be monitored grew as additional parameters were identified. Typical parameters monitored were: Spin-up time, mass unbalance and null voltages on gyros Receiver and transmitter frequencies on beacon transponders Output frequencies of voltage controlled oscillators Resistance measurements on relay assemblies Discharge times at constant current on rechargeable batteries De-spin time on bearings This practice has been in place since the beginning of the Scout Program in 1960. | Because of this monitoring, many failures were prevented by rejecting the identified assembly prior to flight failure or by the early detection of potential out-of-tolerance parameters. This evaluation of test data resulted in attaining a higher reliability of flight performance and prevented costly component replacement in the field. | N/A |  |  | Public | Not Specified |  | 09/13/1996
446 | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN | Terlep, Judy - 0000000000 : NO@ADDRESS.GIVEN |  | Postlanding Power-Up of Spacelab |  | Insufficient notification of the latest flight procedure changes to the KSC-Payloads Group can lead to inaccurate tracking of Spacelab's configuration following landings. | Ensure that monitoring, emergency procedures, and personnel are available for all landings regardless of the planned landing configuration for Spacelab. | GRC | 06/12/1995 | The first United States Microgravity Laboratory (USML-1) located in the Spacelab of the shuttle (STS-50) was not continuously monitored due to insufficient notification of the latest flight procedures. The contingency flight procedures allow for Spacelab power-up in the event of system low temperature and power-down when the orbiter proceeds to ground cooling. Due to an anomaly with the orbiter ammonia boiler system, the flight procedures were altered the day before landing with the decision to power-up Spacelab. The flight procedures were altered again on the landing day with the decision to leave Spacelab powered after the orbiter proceeded to ground cooling. The Spacelab was left in this condition when the orbiter was turned over to KSC. Since KSC-Payloads Group was not informed of the condition, they did not monitor Spacelab's activation nor the several hours of power-on operation. |  | N/A |  |  | Public | Not Specified |  | 09/13/1996
445 | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN |  | O-Rings for Critical Seal Locations - Scout Program |  | In critical seal locations and/or large number usage, O-Rings should be 100% inspected per MIL-STD-413B to avoid any leakage. | Apply criteria from MIL-STD-413B regarding inspection and shelf life usage. Allow a time period, after assembly, before testing components with dynamic O-Rings and soft seats to allow for permanent setting to take place. Avoid seals made of elastomers which are susceptible to compression set for long term use or storage. | GRC | 07/22/1994 | In the time period of 1960-1975, a generic problem was encountered on several Scout Vehicle components containing elastomer O-Rings. During the Scout Production Procurement, components such as regulators and hydraulic actuators were a source of problems due to leakage after initial acceptance tests. An extensive investigation and long surveillance period determined the cause of the leakages to be the O-Ring set. The type of set used was not the well-known permanent set of an elastomer, but rather a much shorter time duration. This was to allow the elastomer to seat in its permanent position in the groove, allow distribution of lubricant, etc. Corrective action was to allow a time period after component assembly and acceptance testing. Further information can also be obtained by contacting the Reliability and Quality Division of Loral Vought Systems at P.O. Box 650003, Dallas, TX, 75265-0003 or calling (214) 603-1000. | Fewer problems and failures of components utilizing elastomers. | N/A |  |  | Public | Not Specified |  | 09/13/1996
441 | Bott, J - 0000000000 : NO@ADDRESS.GIVEN | Bott, J - 0000000000 : NO@ADDRESS.GIVEN |  | Contamination of the Mars Observer Spacecraft by Environmental Conditioning (1992) | The exterior of MO was found to be dirty after the spacecraft had been mated to the launch vehicle. The air conditioning piping or the nitrogen purge system were the likely sources of the contamination. Similarly, deterioration of the nitrogen delivery system for Topex at a contractor facility produced heavily contaminated output. Use gas use supplies only from known, proven sources, investigate the gas supply source and delivery system, and test gases at the source and at the point of delivery. | Air and Nitrogen supplies are often a source of particulate and/or fluid contaminants. Piping and other types of delivery systems may also be sources of contamination. JPL's past experience has shown that certifications on the purity of delivered Nitrogen supplies are not always reliable. JPL's past experience also has shown that although initially certified, Nitrogen at the point of usage can be contaminated. | Where chemically pure gas supplies are a requirement, use only supplies from known, proven sources, particularly sources for Nitrogen. Investigate and qualify delivery systems, as well as sources of gas supply. Test and qualify gases at the point of delivery to sensitive equipment, as well as at the source. | JPL | 08/23/1996 | When the Mars Observer (MO) spacecraft was installed on the launch vehicle at KSC, an air conditioning duct and a Nitrogen purge system were installed at access points to the shroud over the MO spacecraft. Following activities associated with a hurricane, a payload cable inspection showed the spacecraft's external surfaces to be heavily contaminated with particulate matter. This led to delay of the launch, and removal of the spacecraft to the preparation facility for cleaning. The source of the contamination was never identified with certainty, but available evidence pointed to piping in the air conditioning system as the most probable source of the contamination, with the Nitrogen purge system also a possible source. Following replacement of piping in the air conditioning system, a purge of both piping systems, and the addition of a Nitrogen filter, the problem did not re-occur. On the TOPEX project, a similar event was averted at a contractor's facility, after a resident JPL QA representative requested a particle count on the output of a Nitrogen delivery system. The output was found to be heavily contaminated, which necessitated the use of a newly cleaned and tested purge cart. Although pure Nitrogen was manufactured on-site, the delivery system included passage through an aged distribution system, whose interior had deteriorated. Reference(s): PFR #54717 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 ("Engineering Practices: Materials, Processes, and Contamination Control"), and Paragraph 6.12.3 ("Engineering Practices: Protection and Security of Flight Hardware"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.2.2.11 ("Mechanical Configuration/System Design: Configuration - Contamination Avoidance"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 08/23/1996
439 | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN | Oberhettinger, D - 0000000000 : NO@ADDRESS.GIVEN |  | Avoid Use of PFPE-based Lubricant on Moving Surfaces of Titanium (or Other Highly Reactive Metal) Bearings (1993) | A rotating prism motor aboard the TOPEX spacecraft experienced a sudden in-flight failure due to the use of perfluoropolyalkyether (PFPE) based lubricant on titanium bearings. Pure titanium debris produced by spalling of the motor shaft chemically reacted with the fluorocarbon-based lubricant, causing polymerization of the lubricant. Avoid the use of PFPE-based lubricants on titanium or other highly reactive bearing surfaces. | A state-of-the-art spacecraft lubricant, with high performance characteristics throughout the operating temperature range and low vapor pressure, may be vulnerable to polymerization. In such cases, and where thin film lubrication conditions prevail, a more stable lubricant than PFPE-based lubricant should be used on moving titanium bearing surfaces. Regardless of the bearing lubricant used, metallic particle contamination of bearings is likely to affect bearing lifespan. Bearing designs which reduce the amount of bearing play may reduce debris generation. | Avoid the use of PFPE-based lubricants on titanium or other highly reactive bearing surfaces in spacecraft applications. Mitigate the risk of bearing failure by design measures which prevent the generation of metallic wear particles or which control the amount and migration of debris. | JPL | 07/19/1996 | Following an April 1993 in-flight failure of an Upper Atmosphere Research Satellite (UARS) Earth Sensor Assembly (ESA), the vulnerability of identical ESAs aboard the TOPEX spacecraft was investigated. UARS experienced a sudden in-flight failure of the ESA rotating prism motor attributed to the use of perfluoropolyalkyether (PFPE) based lubricant on titanium bearings. Pure titanium debris produced by spalling of the motor shaft chemically reacted with the fluorocarbon-based lubricant, causing polymerization of the lubricant. In the presence of debris, bearing race-to-ball friction produces enough heat for the titanium to react with the lubricant, given that titanium is very reactive when exposed. The degradation mechanism consists of two steps: (1) the reaction of PFPE molecules with freshly exposed titanium particles to form an acid followed by (2) the reaction of the acid with unreacted PFPE molecules, resulting in cleavage of their molecular bonds. This failure mechanism was confirmed in a life test performed by GSFC on a spare UARS ESA motor. The PFPE oil was suspected of causing problems in at least seven units identical to the TOPEX ESA. Reference(s): "UARS ESA-1 Failure Study," Martin Marietta Corp., August 3, 1993. "TOPEX Earth Sensor Motor Review," June 23, 1994, ITHACO, Inc. "TOPEX/Poseidon Earth Sensor Assembly (ESA) Operation," Fairchild Space & Defense Memo No. 968:TOPEX:94-032 to Mark Fujishin (JPL), August 19, 1994. |  | N/A |  |  | Public | Not Specified |  | 06/20/1996
440 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Radio Frequency Assignments (~1976) | Delays to the SEASAT-A project demonstrated the need to prepare and submit requests for radio frequency assignments during the conceptual stage of a project. | Preparation and submission of radio frequency review material should be accomplished in the conceptual stage of a project. | Preparation and submission of radio frequency review material should be accomplished in the conceptual stage of a project. | JPL | 07/19/1996 | (Relevant Historical Lesson(s) Learned) The Office of Telecommunications Policy (OTP) in cooperation with the Office of Management and Budget (OMB) has established a procedure for the review of telecommunications systems for frequency availability and electromagnetic compatibility. Late transfer of SEASAT-A project responsibility to JPL resulted in delayed preparation and submission of the requisite review material. The choice of the Synthetic Aperture Radar (SAR) frequency especially was questionable for a few months. Frequency management personnel from several government agencies performed in "Tiger Team" fashion to coordinate authorization of a specific frequency. Direct project impact was the delay in knowing this important parameter and the concomitant delay in the detailed design of the SAR. Additional Keyword(s): Conceptual Planning, RF Assignments | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 5.2 ("Management Practices: Planning") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 05/09/1996
438 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager Photopolarimeter Subsystem (PPS) Filter & Analyzer Wheel Step Problems (~1977) | Palladium is a particularly efficient catalyst for the formation of polymers. Palladium in the potentiometer wiper contacts on the Voyager Photopolarimeter Subsystem formed a frictional polymer that prevented the stepping of both the analyzer and filter wheels. Catalytic material, including palladium-containing substances, should not be utilized in designs for sliding wipers, relay contacts, etc. | Careful consideration must be given to material choices and system designs in spaceflight hardware. | In particular, palladium-containing substances (or other catalytic material) should not be utilized in future designs for sliding wipers, relay contacts, etc. to avoid a repetition of this problem. | JPL | 07/19/1996 | (Relevant Historical Lesson(s) Learned) The Voyager Photopolarimeter Subsystem on both S/C-31 and S/C-32 has a history of analyzer and filter wheel stepping problems. The problem was discovered late in the test program before launch. The problems persisted in Flight with the analyzer wheel becoming unsteppable. Filter wheel could be stepped marginally, but that was also given up. Numerous in-flight operational fixes were tried without success. Failure analysis by the PPS Diagnostic Working Group has traced the probable cause of this anomaly to formation of an insulating "frictional polymer" on PPS potentiometer wiper contacts. Such a polymer can be formed by the sliding action of metals in the presence of small quantities of almost any organic molecule. This polymer formation reaction was noted as early as 1958 by the Bell System in researching relay failures. Palladium is a particularly efficient catalyst for this reaction - unfortunately, the PPS wipers are made of a palladium substance. Additional Keyword(s): Contamination, Electrical Contacts Reference(s): ISA's 1392, 1420, 1677, 1720, 1899 (Also see PPS ISA's for VGR-2 Encounter) | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.1 ("Engineering Practices: Materials, Processes, and Contamination Control: Practices") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.2.2.11 ("Mechanical Configuration/System Design: Configuration - Contamination Avoidance") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 05/02/1996
426 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Surveyor Rocket Motor Almost Fired (~1965) | To prove that electrical connections were properly made, a test of motor control circuits was included after fueling and pressurization of tanks. Had slightly higher pressure been present in the fuel tanks when the pilot valve for the motor control was activated, rocket firing could have injured observers and destroyed the spacecraft. Functional tests must be carefully screened against a standing policy that at least two protective elements are included to prevent irreversible action. | Functional tests must be carefully screened against a standing policy that at least two protective elements are included to prevent irreversible action. | Exceptions to including at least two protective elements should be even more carefully reviewed, and generally not allowed. | JPL | 07/12/1996 | (Relevant Historical Lesson(s) Learned) To prove that electrical connections were properly made, a test of motor control circuits was included after fueling and pressurization of tanks. Commands were issued and executed which "clicked" the solenoid pilot valve for Surveyor motor control. Subsequent analysis exposed the fact that the motors could have fired if slightly higher pressure had been present in the fuel tanks. The test observer listening for clicks could have been badly burned and the spacecraft destroyed. Additional Keyword(s): Safety, Hazardous Test, Redudant Protective Elements | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 04/25/1996
430 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Permeability, Swelling and Solvent-Stress-Cracking Polymeric and Elastomeric Materials (1977) | During fabrication of the TIROS-N Microwave Sounding Unit, connector cleaning fluids penetrated to the interior of the chassis. This caused severe swelling of the conformal coating material and the subsequent fracture of electronic components, dissolution of polyurethane insulation on the magnet hookup wire, and removal of component identification markings. To preclude detrimental results, care should be exercised in the selection of fluids to be used with or in the presence of polymeric and elastomeric materials. | Most polymeric and elastomeric materials are permeable and are subject to swelling and solvent-stress-cracking when exposed to some fluids. | To preclude detrimental results, care should be exercised in the selection of fluids to be used with or in the presence of polymeric and elastomeric materials. | JPL | 07/15/1996 | (Relevant Historical Lesson(s) Learned) During the fabrication of the Television Infrared Observation Satellite (TIROS-N) Microwave Sounding Unit, fluids used to clean chassis mounted connector penetrated around and through the connectors to the interior of the chassis causing severe swelling of the conformal coating material and the subsequent fracture of electronic components, dissolution of polyurethane insulation on magnet hookup wire and removal of component identification markings. Additional Keyword(s): Connector Cleaning, Polymers Reference(s): PFR #2649 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.4 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 04/11/1996
434 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Rusty Integrated Circuits (~1973) | During the Viking program, rust spots were observed on the gold-plated Kovar lids of a number of flat pack ICs. The cause was suspected to be chlorine from the lead tinning operation, and various polymeric coatings failed to prevent further corrosion. Following the use of any chlorinated product, a thorough and complete cleaning to remove all residual chlorine contamination is a necessity. | Corrosion, once started, is extremely difficult to stop. | Following the use of any chlorinated product, a thorough and complete cleaning to remove all residual chlorine contamination is a necessity. | JPL | 07/17/1996 | (Relevant Historical Lesson(s) Learned) During the Viking program, rust spots were observed on the gold-plated Kovar lids of a number of flat pack Integrated Circuits (I.C.) used in electronic equipment. Although the source was not clearly identified, chlorine apparently initiated the corrosion. The chlorine is presumed to have been within activated solder flux residues from the lead tinning operation. In some cases, the corrosion penetrated through the I.C. lid and was a potential cause of I.C. failure. Although various polymeric coatings were applied over the metallic coatings to interrupt the corrosion cycle, they were all permeable enough to permit water through to the Kovar surface and the corrosion continued. Reference(s): PFR 32492 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.4 ("Engineering Practices: Materials, Processes, and Contamination Control: Practices") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 04/04/1996
420 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | VO'75 Pressure Regulator Leakage and Work-Around Procedures (~1976) | The pressure regulator in the Viking Orbiter Propulsion Subsystem started leaking following a pyro firing that occurred prior to the near-Mars TCM. Likely causes were corrosion or residue from propellant migration or pyro valve blowby, or particulate contamination. Recommendations included using separate regulators for the fuel and oxidizer sides, incorporating a bellows in the pyro valve to eliminate blowby, and adding a isolation valve between the regulator and propellant tank. | The micro-scale effects of long-term propellant exposure should be investigated in order to better critique regulator design. | Design corrective measures of propulsion pressurization subsystems which should be considered are: using separate regulators for the fuel and oxidizer sides incorporating a bellows in the pyro valve to eliminate blowby adding a isolation valve between the regulator and propellant tank to minimize propellant migration into the regulator | JPL | 07/08/1996 | (Relevant Historical Lesson(s) Learned) The pressure regulator in the Viking Orbiter-1 (VO-1) Propulsion Subsystem, after having performed without incident through the completion of the near-Earth midcourse Trajectory Correction Maneuver (TCM), leaked when 265 days later it was brought back on-line by the opening of an explosive valve which had isolated the regulator and propellant tanks from the pressurant tanks through the coast period prior to the near-Mars Trajectory Correction Maneuver. The regulator leakage was detected by virtue of a continual rise in the fuel and oxidizer tank pressures. Propellant tank pressure data show that the regulator had been leak-tight up to the end of the near-Earth Trajectory Correction Maneuver, when the pressurant isolation pyro valve was actuated closed. The near-Mars TCM burn duration was lengthened considerably and an additional unscheduled TCM made. This relieved pressure and increased ullage. After Mars Orbit Insertion (MOI) the regulator was valved off from the pressurant supply. It was elected not to isolate the regulator immediately, then re-open for MOI. The VO-2 approach sequence was also revised, but differently. The pressurant supply was left isolated until MOI, the TCM being made in "blow down" mode. An analysis of telemetry data ruled out: a scratch in the regulator poppet or seat, and housing weld failure. Remaining possibilities are: 1) corrosion and/or residue formation in the regulator circuit - due to propellant migration and/or pyro valve blowby, and 2) particulate contamination. Additional Keyword(s): Material Compatibility, Propellant Feed System Reference(s): IOM 344S-76-258, September 14, 1976, "Pressure Regulator Failure Analysis, VO'75 Propulsion Subsystem, PFR 35408," G. Yankura to F. C. Vote | JPL has referenced the lesson as supporting Paragraph 4.7.4.3 ("Propulsion System Design: Safety - Use of Gas Regulator") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 04/04/1996
412 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager-Power Subsystem Coded Commands Interface with the Computer Command Subsystem (CCS) (~1975) | Because, the interface circuit between the Voyager CCS and Power subsystems was not electrically isolated, spacecraft system noise prevented reliable commanding from CCS to Power. This was not discovered until system-level test, and circuit modifications were difficult. Lesson recommendations pertain to system level requirements, design, and early compatibility testing for interface circuits. | The system test phase is too late to discover hardware interface incompatibilities after subsystems have completed qualification testing. | Coded interface circuits should employ isolated power supply and grounding schemes. System level requirements must be generated for the design of grounding of interfaces. Compatibility tests, using representative equipment (prototype or breadboard) should be conducted as early as possible for subsystems having new, or complex interfaces. Where noise immunity is critical, injection of noise on the signal lines may be necessary to demonstrate that adequate margin exists. These tests (and the design/analysis that precedes them) should account for the fact that differences will exist between subsystem and system configurations. The noise characteristics in the lab may be different than the system configuration, for example. | JPL | 06/26/1996 | (Relevant Historical Lesson(s) Learned) A digital, coded interface was utilized on Voyager for the first time, at JPL, for transferring basic commands between CCS and Power. It was not until the Proof Test Module Spacecraft System Test Phase, in the Spacecraft Assembly Facility, that an incompatibility appeared that prevented reliable commanding from CCS to Power. The problem was caused by spacecraft system noise that resulted in spurious triggering of interface circuit elements. Circuit modifications, in this case, were troublesome. This configuration was adopted late in the subsystem design phase. For simplicity, an existing power supply was used for this circuitry which resulted in the signal return being common with the spacecraft 30V power return. Additional Keyword(s): Electrical Isolations Reference(s): Voyager PFR 39934, 39935, 39940, 39948 SSEF #343.2 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.6 ("Engineering Practices: System Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.10.1.1 ("System EMC/EMI Design: General - EMC Approach") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 04/04/1996
429 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Low Strength Solder Joints (~1975) | In the process of reflow soldering flat pack leads to printed circuit boards during the Voyager program, it was discovered that a high phosphorous content in the plating process for the Kovar leads can weaken solder joints. Evaluate the effects of phosphorus when soldering or welding nickel plated surfaces. | A high phosphorous content in the plating process can weaken solder joints. | Evaluate the effects of phosphorus when soldering or welding nickel plated surfaces. | JPL | 07/15/1996 | (Relevant Historical Lesson(s) Learned) While in the process of reflow soldering flat pack leads to printed circuit boards during the Voyager program, small black spots were observed on some leads of various CD 4000 series flat packs. Analysis revealed the solder surface of the leads to be poorly wetted, caused by a high phosphorus content in the plated surface, and the solder joints to be substantially weakened. (Some joints when barely touched, fell apart). As a result, suspect flat packs were replaced, wherever found. The Kovar leads of the flat packs are electroless nickel plated to provide a solderable surface. The plating process, which also coplates elemental phosphorus, begins to plate a poor solder surface when the phosphorus content exceeds approximately 7% by weight. Since the nickel depletes at a faster rate than the phosphorus, it is necessary to monitor the plating solution and maintain an acceptably low level of phosphorus. Also, when a poor solder is found to exist as a result of excess phosphorus, platers will usually overplate with tin to regain a solderable surface. This overplate when exposed to the mechanical and thermal stresses of lead forming and reflow soldering will crack and pull away from the phosphorus rich nickel plate below. Reference(s): Part Failure Analysis Report Log 2624 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10.1 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/28/1996
437 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Damaged Capped Inserts (~1976) | Oversized mounting screws caused apparent damage to capped inserts in a Voyager transponder. When designing or reworking hardware employing capped inserts, it is critical to verify that correct screw lengths are specified and used. | Oversized mounting screws can damage capped inserts. | When designing or reworking hardware employing capped inserts, it is critical to verify that correct screw length is specified and used. | JPL | 07/17/1996 | (Relevant Historical Lesson(s) Learned) During a Voyager Radio Frequency Subsystem (RFS) transponder filter capacitor rework, a noise was noted in the Proof Test Model (PTM) subassembly. On opening the power converter interface module, some of the mounting insert caps were found loose inside and others were partially pushed out from the insert ends. A dimensional check showed the mounting screws used may have an interference fit in length. A second possibility exists that longer screws were used at some earlier installation. Fastener inserts used in flight equipment are usually of the capped variety (closed at the bottom) when used in a thru-mounting design. This is done to prevent metallic particles being deposited in the electronics where they can cause electrical shorting or other problems. See also: In-flight failure, "Receiver 1 Power Converter Failure on Voyager 2" which was likely caused by this event. Additional Keyword(s): Tolerance Stackup Reference(s): PFR #40215 Voyager Structure Subsystem | JPL has referenced the lesson as supporting Paragraph 8.3.3.3 ("System Assembly, Integration and Test: System Functional Verification - Mechanical Clearances") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/28/1996
421 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager II Instrument Boom Deployment Anomaly (1977) | The Voyager II Science Boom failed to indicate, by microswitch, that it had deployed completely. The design of deployment mechanisms should consider susceptibility to jamming by foreign objects. Deployment clearance verification testing should be repeated if any related changes are incorporated. | Ideally, deployment verification procedures should be performed on a completely assembled spacecraft subsequent to its final buildup. Mocked-up areas of critical clearance may be used, but their use introduces some risk. | Avoidance of susceptibility to jamming by foreign objects should be a specific consideration in design of deployment mechanisms. Deployment clearance verification testing should be repeated if any related changes are incorporated. | JPL | 07/08/1996 | (Relevant Historical Lesson(s) Learned) On August 21, 1977, the Voyager II Science Boom failed to indicate, by microswitch, that it had deployed completely. Analysis of the spacecraft dynamics during jettison of the expended Solid Rocket Motor (SRM) case indicated that the science boom folding strut was not locked and that the boom momentarily refolded due to impulse from the SRM case separation. Subsequent star mapping using the scan platform-mounted TV cameras ascertained that the boom was within a tenth of a degree of the fully deployed position. Exhaustive tests were conducted to assess candidate causes. The possibilities investigated included equipment interferences, jamming by foreign matter, and excessive friction or binding due to low temperature phenomena. Some discrepancies were discovered, but a specific probable cause could not be identified. Additional contributing factors may have resulted from late incorporation of a number of cabling, thermal blanket, and external surface configuration changes. Reference(s): JPL Problem Failure Report (PFR) 41010/NASA Experience Bulletin No. 14 | JPL has referenced the lesson as supporting Paragraph 8.3.3.2 ("System Assembly, Integration and Test: System Functional Verification - Deployments and Articulations"), and Paragraph 4.2.2.9 ("Mechanical Configuration/Systems Design: Configuration - Design Deployables for Test"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/21/1996
428 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Electroexplosive Device Degradation with Time (~1975) | In selecting squibs stored from the Viking Orbiter 1975 program for use in the Voyager 1977 mission, it was found that moisture sealed within the squibs at the time of manufacture had combined with the boron ignition mix to produce boric acid and corrosion. The manufacture of hermetically sealed squibs must preclude the presence of moisture prior to hermetic sealing. Flight quality squibs in bonded storage must receive periodic resistance checks to detect degradation. | The manufacture of hermetically sealed squibs must preclude the presence of moisture prior to hermetic sealing. | Flight quality squibs in bonded storage must receive periodic resistance checks to catch any degradation as it may occur. This is especially critical if squibs are inherited from past projects. | JPL | 07/12/1996 | (Relevant Historical Lesson(s) Learned) Flight qualified electroexplosive devices (squibs) stored from the Viking Orbiter 1975 program were selected for use in the Voyager 1977 mission. A twenty-eight day temperature soak resulted in increased bridgewire resistance for six of the ten samples. This was considered to be indicative of an incipient failure, the possible opening of the bridgewire with subsequent failure to fire upon command. Dissection of the squib which showed the greatest resistance increase revealed corrosion along the top of the bridgewire. None of the Voyager 1977 squibs built to the same specifications by the same manufacturer exhibited this resistance increase in similar testing. The phenomenon was attributed to moisture sealed within the squibs at time of manufacture, which combined with the Boron ignition mix to produce boric acid. Slow corrosion probably occurred with the passage of time. Selected squibs with no bridgewire resistance change were flown on Voyager. Additional Keyword(s): Contamination, Pyrotechnic Reference(s): Voyager PFR 37909 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.10 ("Engineering Practices: Materials, Processes, and Contamination Control") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/21/1996
394 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager Scan Platform Problems | Near the end of the Voyager 2 Saturn encounter, the scan platform azimuth actuator seized, causing a scan platform pointing error that resulted in a loss of some data. Recommendations involved the need for life cycle testing of critical rotating mechanical equipment, and attention to factors that could cause increased drive torque requirements for rotating elements used in a space environment. | Life cycle testing of rotating mechanical equipment used in a space environment can aid in design verification, and can enable analysis of in-flight faults. | On mission critical rotating mechanical equipment, life cycle testing should be performed under realistic conditions to obtain a reasonably accurate life-time forecast prior to final design acceptance and flight qualification. For design of rotating elements used in a space environment, care should be taken on those facets of the design which could contribute to increased drive torque requirements with continuing use. For precision mechanisms containing moving parts which are susceptible to binding in the presence of particulate matter or fluid contaminants, the use of bonding agents for locking devices should be tightly controlled. This particular application used nylon, Solithane and Stycast for the purposes of screw locking and wire harness bonding. Post assembly cleaning and inspection for contaminants are critical elements in the fabrication process. Properly applied, nylon, Stycast and Solithane are stable compounds. All of these materials however, are highly productive of particulate contamination when abraded or disturbed. Rework, such as breaking free a screw head which is bonded in place, or cutting a Stycast spot bond away, tends to produce large quantities of very small particles which must be subsequently located and removed. A set of spare spacecraft hardware should be maintained in the flight configuration and within specification to enable detailed analysis of suspected causes of in-flight faults and validation of proposed corrective actions or workarounds. | JPL | 05/30/1995 | The Voyager 2 scan platform, on which are mounted the spacecraft cameras and several science instruments, is rotated in elevation and azimuth by actuators. Near the end of the Voyager 2 Saturn encounter, the scan platform azimuth actuator exhibited an anomaly. This anomaly was evidenced by the azimuth actuator seizing, causing a scan platform pointing error that resulted in a loss of some data. Through a series of ground commands, the problem was alleviated to the extent that the scan platform could perform its function. A prototype scan platform actuator was life-tested in a laboratory and it failed after approximately the same total number of slewed degrees as the flight unit. Upon disassembly of the test actuator, the problem was determined to be a design flaw in the actuator shaft bearing and gear lubrication system. In addition, dissimilar metal electro-chemical reactions produced corrosion. There was also debris build-up due to a lack of relief ports resulting in the deposition of this debris on the drive gear bearing assembly. For details, refer to "Voyager Engineering Improvements for Uranus Encounter" by Howard P. Marderness. | JPL has referenced the lesson as supporting Paragraph 4.2.3.9 ("Mechanical Configuration/Systems Design: Mechanisms - Mechanisms Cycle Life Design Margins"), and Paragraph 4.2.5.6 ("Mechanical Configuration/Systems Design: Structural Design - Structure Design Criteria for Actuators") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/14/1996
433 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager - Power Subsystem Power Distribution Flight Relay Procurement (~1975) | Voyager's discovery of defective component lots in welded module assemblies led to a re-procurement of the flight relays. For procurement of parts with a prior history of problem/failures, evaluate the design and workmanship of the current production and determine the need for JPL inspections and special screening tests. | The discovery of defective component lots in welded module assemblies or at any point subsequent to completion of flight hardware fabrication results in major program impacts. There are unavoidable schedule slips due to the re-procurement and replacement of parts and welded modules. Flight hardware quality is jeopardized by the resulting rework and retest effort. The pre-cap visual inspection alone on a densely packed relay provides little insight into the quality of its individual subassemblies. Screening tests are not 100% effective in elimination of defective units. | Procurement of parts with a prior history of problem/failures should be specifically re-evaluated prior to re-use on a subsequent flight program. Both design and workmanship of the current production output should be evaluated to establish the quality of the product and the critical points in the manufacturing process where JPL inspections should be negotiated into the purchase order. Special screening tests and/or additional special burn-in tests may also be warranted. | JPL | 07/17/1996 | (Relevant Historical Lesson(s) Learned) During flight welded module fabrication (2) 3SBM relay failures occurred. One relay failed due to a shorted coil, the other failure was due to a broken weld. Subsequent JPL failure analysis on (14) additional flight relays showed failed conditions in one or more of the armature positioning welds. An investigative team visited the vendor to review the failures and the relay manufacturing process/Quality Assurance (QA) controls. The welding process suffered from a component "fit" problem, worn welding fixtures and an absence of weld schedules. The coil lead operation had no instructions that precluded the possibility of coil shorts. The QA coverage lacked a systematic method of keeping records and employing corrective action. Based on the deficiencies found in the manufacturing process and the inability to cull defective relays in a non-destructing manner from the existing flight lots, a re-procurement of flight relays was initiated. The modifications to the fabrication process include: (a) component part inspection prior to kitting, (b) development of weld schedules and weld inspection criteria, and (c) JPL inspection points established at critical stages of relay fabrication. NOTE: This component was selected from the JPL Preferred Parts List. Additional Keyword(s): Wire Welding Reference(s): PAR's 36074, 36841, 36861; Part Failure analysis Reports 2494, 2496, 2603, 2622; IOM #342-76-B-028, Johnson, H. L., "Disposition and Status of MJS'77 Power Subsystem 3SBM Relay Problems," 5 February 1976. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph7.5.6 ("Safety and Mission Assurance Practices: Electronic Parts Reliability, Application and Acquisition") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/07/1996
419 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | SEASAT-A Synthetic Aperture Radar Coherent Leakage (1978) | The SEASAT-A Synthetic Aperture Radar system end-to-end gain was instable due RF leakage that varied with the sensor gain state and with temperature. Use of prototype models and diagnostic RF system analysis and modeling are effective in identifying microwave design susceptibilities to RF leakage. | Test programs must be designed to uncover operating problems. | Diagnostic Radio Frequency system analysis and modeling are effective in identifying microwave design susceptabilities to RF leakage. They need to be scheduled early enough to allow the necessary design modifications to be accomplished. In addition, use of prototype models offers the opportunity to uncover problems without subjecting flight hardware to jeopardy. | JPL | 07/08/1996 | (Relevant Historical Lesson(s) Learned) The SEASAT-A Synthetic Aperture Radar (SAR) system end-to-end gain varied anomalously during measurements made just prior to SAR shipment to the SEASAT system contractor. Tests to resolve the anomaly traced the cause to the presence of leakage in the sensor signal output which was coherent with the Data Link carrier. (The Data Link in the SAR system is, in effect, an Intermediate Frequency (IF) strip, which converts the radar signal to offset video after transferring the radar signal, with reference signals, through an S-band link.) Phasing and amplitude of the leakage varied with the sensor gain state and with temperature, thereby causing variations in the Data Link resultant carrier level. These variations perturbed the unity gain level required of the system. The system was designed for a fixed known relationship between signal and carrier levels. To alleviate the problem, the sensor was removed from the satellite, and the leakage as attenuated by application of conducting tape. This did not eliminate the effect, but reduced it to acceptable levels. The leakage subsequently remained within these acceptable levels. Additional Keyword(s): Communication Link, Design Verification, Spacecraft Radar Reference(s): SEASAT P/FR 1287 R. L. Horttor/B. L. Huneycutt, et al, "SAR Engineering Assessment Report." | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.4.11 ("Engineering Practices: System Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 02/29/1996
427 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Okonek, Joseph - 818 354-9300 : Joseph.J.Okonek@jpl.nasa.gov |  | SEASAT-A Synthetic Aperture Radar (SAR) Data Link Power Amplifier (1977) - (Revised) | A crack in an RF circuit ceramic substrate was revealed by a potentially mission catastrophic loss of output power during thermal-vacuum test of a sensor module. This crack was due to substrate weakening caused by use of a dental drill used for circuit tuning (by removing conductor material) during the final amplifier assembly process. Microwave RF circuit design that involves the practice of flight unit tuning by removal of conductive material, such as by use of abrasive or cutting tools, should be compatible with the substrate and circuit material, the packaging design, and other relevant factors. The Lesson Learned and Recommendations section in this 1977 lesson learned were revised in 2006 to reflect current practice in the use of abrasive and cutting tools to tune RF circuits. | The tuning of RF circuits using abrasive or cutting tools to remove conductive material from the boards may cause mission critical damage that is not easily detectable. | Microwave RF circuit design that involves the practice of flight unit tuning by removal of conductive material, such as by use of abrasive or cutting tools, should be compatible with the substrate and circuit material, the packaging design, and other relevant factors. Post-tuning inspection is mandatory. | JPL | 01/01/1996 | (Relevant Historical Lesson(s) Learned) The SEASAT-A Synthetic Aperture Radar (SAR) Data Link suffered a 25-dB loss in output power during the Sensor Module Thermal Vacuum Test. This failure would have been catastrophic in flight, causing loss of all SAR data. The cause of the failure was a crack in an RF circuit ceramic substrate. The crack opened the DC bias supply to an RF amplifier. Structural analysis of the substrates showed weakening caused by use of a dental drill used for circuit tuning (by removing conductor material) during the final amplifier assembly process. This process inevitably removed some substrate material, by gouging or cracking the substrate. Without this initial damage, the substrate material would have survived the expected thermal environment. Tuning of the flight RF circuit was done without benefit of new artwork. Because of cost and schedule pressures, design changes were made on the brassboard model and implemented on the flight model without benefit of a prototype. (A similar failure had occurred 8 months before during SAR System Thermal Vacuum Test. The earlier failure was originally attributed to an open solder joint in a bias circuit. In hindsight, the actual cause was probably a cracked substrate. At the time of the earlier failure, Voyager launch priorities precluded the assembly of the team, which made the diagnosis of the later failure.) Additional Keyword(s): Fabrication Technique, Environmental Test, Spacecraft Radar Reference(s): SEASAT P/FRs 1275, 3388 |  | N/A |  |  | Public | Not Specified |  | 02/29/1996
402 | Bott, J - 0000000000 : NO@ADDRESS.GIVEN | Bott, J - 0000000000 : NO@ADDRESS.GIVEN |  | Solderability Problem with Solder Plated Terminals (~ 1990) | Multi-year storage and aging of solder plated terminals for TOPEX and ASTROS circuit boards affected their solderability. Consider aging and solderability factors, and perform solderability tests, before installing solder plated terminals. | Solder plated brass terminals have a limited shelf life after initial manufacture or reprocessing. Surface deterioration may set in after approximately two years in an air ambient environment. Failure to take aging and solderability factors into account before installing solder plated terminals may have serious consequences. | Use fresh stock when installing solder plated terminals. Evaluate date codes on packages of terminals to be used. Return residual stocks of solder plated brass terminals to controlled stores, or discard them on completion of the project. Perform solderability tests on any lot of solder plated terminals prior to use. Avoid installing solder plated terminals until immediately prior to populating the printed wiring board, if possible. | JPL | 04/19/1996 | TOPEX Microwave Radiometer (TMR) Solder plated terminals supplied to a contractor for installation in TMR multilayer boards failed solderability tests, prior to installation. These terminals were found to have exceeded their useful shelf life, (typically 2 years), and were replaced with new ones. Removal and replacement of these terminals after installation would have meant severe penalties in terms of added costs, schedule slippage and/or potentially destructive rework. ASTROS Instrument When previously built printed wiring board assemblies were removed from long term storage (more than 5 years) for use in new construction, surface deterioration on solder plated terminals necessitated the use of activated (type RA) fluxes to obtain acceptable solder joints. Such acid based fluxes are not normally used due to potential for long term corrosion. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.17.9.1 ("Engineering Practices: Hardware Development - Electronic Packaging/Cabling Design and Fabrication") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 02/08/1996
397 | Ervin, G - 0000000000 : NO@ADDRESS.GIVEN | Ervin, G - 0000000000 : NO@ADDRESS.GIVEN |  | Viking Spacecraft Anomalous Power Turn-On | While on the launch pad, Viking experienced an anomalous power turn-on that resulted in a total discharge of the spacecraft batteries. Failure analysis had not detected that discrete failure of a relay located in support equipment could have caused the problem. All interfaces with the spacecraft should be subject to failure mode analysis, status indicators or alarms should be used, and the spacecraft should not be left unattended unless periodic monitoring is conducted. | Failure mode analysis can disclose potential fault scenarios and indicate prudent preventive action. Periodic monitoring of spacecraft can provide detection of anomalous conditions. | All interfaces with the spacecraft should be subject to failure mode analysis. Since it is difficult to anticipate all failure modes, use should be made of indicators or alarms to provide verification of operational performance or mode status. The spacecraft should not be left unattended unless periodic monitoring is conducted. The periods to be used and the parameters to be monitored should be based on an analysis of the conditions under which the spacecraft is left unattended. | JPL | 06/07/1995 | While on the launch pad, a Viking Spacecraft experienced an anomalous power turn-on during a period when the spacecraft was unattended. The power turn-on resulted in a total discharge of the spacecraft batteries. The most probable cause was induced current resulting from local lightning strikes on the seven miles of cable between the support equipment located in Building AO and in the Launch Complex Trailer at the launch pad. Spacecraft internal power "ON" is accomplished by energizing a motorized switch in the spacecraft, which then connects the spacecraft batteries to the power bus. The induced current caused a relay located in the support equipment to connect an emergency battery to the spacecraft motorized switch, which then initiated the power turn-on. Analysis conducted during the investigation disclosed that a possible discrete failure of the relay would have caused the same problem. This failure analysis was not performed prior to the incident. After the deep discharge, the Viking Spacecraft batteries were no longer flight certified and had to be replaced at a considerable expenditure of resources. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.5 ("Safety and Mission Assurance Practices - Reliability Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.5.1 ("Flight Electronics Hardware System Design: Interfaces - Flight-Support Equipment Interfaces"), and Paragraph 8.2.3.2 ("Flight System Verification and Validation Design: Pre-Delivery Verification - System Level: Launch Site Support Equipment") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 01/26/1996
411 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Inability to Perform Inflight Checkout of Viking Lander RF Power Amplifier in High-Power Mode (~1975) | Inflight checkout of the Viking Lander relay link transmitter posed the risk of overloading and zenering input transistors in the Orbiter relay receiver. A system design must include requirements for “testability” and inflight test requirements should be considered in selection of telemetry data points. | A system design must include requirements for "testability." Test requirements may create "abnormal" operating modes which are easy to overlook during the design of individual elements of a system. Accurate analysis of the coupling of RF energy between systems physically close to one another, over other than free-space paths, may be intractable, particularly in the presence of adjacent "structure." | Inflight test requirements should be considered in selection of telemetry data points. On Viking, the overall "system" problem was exacerbated because the Orbiter, the Lander, and the Viking Project were each the responsibility of different organizations. (The Galileo Orbiter and its Probe are a similar composite system, in which interactive RF effects need to be carefully assessed.) Early system decisions as to which tests will be necessary are needed to make correct recommendations regarding testability and test operating modes. | JPL | 06/26/1996 | (Relevant Historical Lesson(s) Learned) The Viking Lander relay link transmitter has selectable power output levels of 1, 10, and 30 watts. Inflight checkout of the Lander system was to include operation at each of the power levels. Prior to launch, Orbiter and Lander telecom analysts identified the planned checkout as a problem. With the Lander attached to the Orbiter during interplanetary flight, the separation between the Lander relay transmitting antenna and the Orbiter relay receiving antenna was small enough that the Orbiter relay receiver was subject to overload and possible zenering of input transistors at 30 watts. Prelaunch antenna tests were limited by available modeling capability (use of 1:5 scale; half of the bioshield) and VO-1/VL-1 mated tests were accomplished under non-flight conditions (Orbiter relay antenna stowed, noisy environment). An inflight test was devised, in which the 1-watt mode was tried and the effect on the available Orbiter relay receiver telemetry points noted. The receiver signal strength telemetry (AGC) was "saturated." An input current telemetry channel, responding to the large overloads was "calibrated" at one watt, and on the basis of this, the 10-watt level was deemed safe and was exercised. However, parameter tolerance buildup resulted in too large a risk of relay receiver damage for the 30-Watt checkout to be tried. Because of the absence of testing and the criticality of the Mars-descent data, the initial mission design requirement for 30 watts during descent was re-examined. As a result of this work, the (small) risk of data loss due to atmospheric fading was accepted. Descent was at 10 watts, and subsequent relay passes from Mars' surface were at 30 watts. Additional Keyword(s): Margins, Subsystem Interaction, Antenna Pattern, Communication Link, RF Measurement, Test Methods Reference(s): Viking Project Document VFT-022, "Viking Orbiter System, Primary Mission Performance Report," June 15, 1977. (see section of Relay Radio Subsystem, pp. II-37 to II-39.) Viking Flight Team memo OTAU-15240-FHJT, "Recommendation Against 30-watt Lander UHF Transmitter Checkout," Jim Taylor to R. A. Ploszaj, February 11, 1976. VFT Memo FPAG-15642-EAE, "RCE 10 Watt Mode in Descent for Mission 1," E. A. Euler, 3/18/76 | JPL has referenced the lesson as supporting Paragraph 4.1.7.2 ("Flight System Design: General - Operability - Design for In-Flight Characterization") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 01/25/1996
410 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Radio Frequency Interference Caused by Multiple Viking Spacecraft in Deep Space Station Antenna Beamwidth (1976) | Mutual interference among the two Viking Orbiters and the two Viking Landers caused a loss of downlink carrier lock and telemetry data several times during the Viking extended mission. The Viking experience showed that the types and magnitude of interference can be adequately analyzed (or determined by test) and that the resulting operational constraints can be adequately specified. | The situation of two deep space vehicles in the same ground station antenna beamwidth results in possible mutual RF interactions not present with ordinary single-spacecraft tracking. The Viking experience showed that the types and magnitude of interference can be adequately analyzed (or determined by test) and that the resulting operational constraints can be adequately specified. | Although the Viking situation continued for more than two years, there are shorter periods when vehicles from different projects (for example, Voyager and Galileo) may be less than a few tenths of one degree from one another, as seen from a station. This potential interference must be properly accounted for in each project's frequency allocation process and mission design. On Viking there was no operational software available either within the Project or the Deep Space Network to use routinely to predict when such interference would occur. It was therefore necessary to preclude the possibility of interference (by forbidding ranging during critical spacecraft data return sequences) by operational rule. Also, it was necessary to accept occasional interferences and to acquaint the real-time operations people to the "signature" of these interferences. | JPL | 06/24/1996 | (Relevant Historical Lesson(s) Learned) The potential for mutual interference among the two Viking Orbiters (on Deep Space Network (DSN) channels 9 and 20, with 'backup' on 16) and the two Viking Landers (both on DSN channel 13) was recognized during the link design and test phase. Multiple vehicle interferences can occur when modulation on the carrier of one Viking channel produces sideband energy, which extends into a second channel. In particular, discrete spectrum ranging produces sideband centered about 516 kHz clock and its harmonics, and the orbiter high rate telemetry produces sideband energy centered about 240 kHz subcarrier and its harmonics. Compatibility testing was accomplished at Compatibility Test Area 21 (CTA 21). This testing identified the most severe (likely) interference condition as false uplink RF acquisition by and out-lock vehicle of the uplink sideband intended for a second vehicle during range acquisition. Loss of downlink RF from the first vehicle would also be experienced at the station, due to the vehicle's shift from one-way to two-way mode. Several other conditions, involving degradation of the RF carrier tracking, ranging link delay measurements, and telemetry signal-to-noise ratio, were also identified. The results of the analysis and testing were stated in a recommendation not to fly the backup channel 16 and in various mission rules as to when ranging acquisitions would be possible. Ranging modulation interference to a one-way Orbiter occurred several times during the Viking Extended mission. Downlink carrier lock and telemetry data were lost as predicted. Additional Keyword(s): Multiple Mission Planning Reference(s): JPL letter 339-FVS;fv Fred Stuhr to Mr. H. R. Kowitz of Viking Project Office of the Langley Research Center of NASA, Oct. 4, 1974, reporting the CTA-21 test results. "Deep Space Network to Viking Orbiter Telecommunications Performance During the Viking Extended Mission, Nov. 1976 Through Feb. 1978", in DSN Progress Report 42-45, March and April 1978, F. H. J. Taylor. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.2.4 ("Engineering Practices: Telecommunication Design") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Science | Public | Not Specified |  | 01/18/1996
404 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Traveling Wave Tube Amplifier on Martian Surface: Failure Due to Corona (1976) | When commanded to switch on, TWTA No. 1 on Viking Lander 2 failed to produce an S-band RF downlink, probably due to RF breakdown of the high-voltage power converter. High-voltage circuits designed to operate within the Martian atmosphere require special design precautions, such as insulation from ground potential, to avoid corona or other forms of high-voltage breakdown. | High-voltage circuits designed to operate within the Martian atmosphere require that special design precautions be taken to avoid corona or other forms of high-voltage breakdown. | The TWTA has numerous high-voltage areas needing protection from ground potential, by means of either insulated wire or potting compound. Note: The Martian atmosphere consists mainly of 95% carbon dioxide and about 3% argon. The ambient pressure at the Lander site is 7.2 millibars, corresponding to an Earth pressure of 5.2 torr. This constitutes a very critical pressure region in an atmosphere of "active" gasses. (Experimental experience with electrostatic discharge indicates that carbon dioxide produces corona at a voltage 19% lower than required for air, and argon at a voltage 60% lower than air.) Corona breakdown in Martian atmosphere could occur as low as 50 volts. The TWTA power converter has output voltages ranging up to 2 kV. The failure analysis concluded that somewhere in the TWTA system, a high-voltage point developed a gap between itself and circuit ground which then filled with Martian air. Lack of precise telemetry data from the Lander made it impossible to define the breakdown area any closer than the TWTA No. 1 as a whole. Power converter corona RF noise could have found its way into the ranging system via the radio system or power line pickup. | JPL | 04/26/1996 | (Relevant Historical Lessons Learned) Traveling Wave Tube Amplifier (TWTA) No. 1 on Viking Lander 2 failed to produce an S-band RF downlink when commanded "ON" October 13, 1976. The most probable failure model is that the high-voltage power converter developed a corona breakdown. A subsequent attempt to operate this TWTA during the extended mission late in 1978 also failed to produce downlink. From Martian day one (SOL 1) after Lander 2 touchdown, TWTA No. 2 had been used and it had performed very well. On SOL 33, the link was switched to TWTA No. 1 because it ran cooler than No. 2, and the increasing solar angle was beginning to raise the Lander ambient temperature. TWTA No. 1 produced normal carrier and telemetry sidebands; however, the ranging subcarrier was suppressed by noise by 6 to 8 dB. These symptoms continued from SOL 33 to SOL 38. On SOL 39, no signal was observed at the Deep Space Stations after the TWTA "ON" command. Subsequent telemetry via the UHF relay link (not involved) showed the TWTA bay temperature did not make its usual climb. The TWTA went through its 90-second cathode warm-up period, and the failure must have occurred shortly after the high-voltage was programmed to come on. Other failure mechanisms examined and discarded include: sequence error, spurious signals on the uplink from the stations, "power-on" switch failures, exciter spurious signals, and command link failure. It was concluded the failure was within TWTA No. 1. Reference(s): Viking Incident Surprise Anomaly Report No. 15643 (dated 13 Oct. 1976) JPL IOM 3363-76-059, "Narrative on the Viking No. 2 Lander TWTA Failure," Lloyd Derr to Lee Randolph, 29 Oct. 1976 | JPL has referenced the lesson as supporting Paragraph 4.12.2.3 ("Flight Electronics Hardware System Design: Electronic Packaging - High Voltage Designs") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 01/04/1996
436 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Receiver 1 Power Converter Failure on Voyager 2 (1978) | A Voyager telemetry failure was attributed to over-length screws that caused conductive end-caps to contact areas not sufficiently coated by conformal coating. The lesson provides recommendations for design of captivated inserts, QA monitoring of assembly, application of conformal coatings, and planning of ground activities. | Effects of both plus and minus component tolerances must be examined in design. Telemetry measurements can be used to detect imbalances between the chassis-supply and chassis-return voltages, such as would be caused by the original Voyager short. | Tolerancing of screw length normally is examined to ensure adequate penetration. For captivated inserts, buildup of tolerances in the other direction becomes important. Captivated inserts should be designed so that conductive pieces of the insert are retained and will not fall into the electronics. Assembly of spacecraft bays should be closely monitored by the Quality Assurance organizations to verify that only screws of the proper length are used. The application method for conformal coating relied on to prevent electrical shorts must not leave uncoated conductors. Procedures governing required or planned ground activities and their interaction with stored on-board quotautomaticsquot must be carefully established and used. | JPL | 07/16/1996 | (Relevant Historical Lesson(s) Learned) Voyager 2 Receiver 1 operated normally from launch until an inadvertent activation of the on-board command loss routine switched it out and put Receiver 2 into use. Receiver 2 would not lock to the uplink to receive a command to stop the loss routine, and it later was found to have a shorted loop capacitor. Twelve hours later, the routine again selected Receiver 1. The Voyager flight team, knowing the spacecraft was already on the High-Gain Antenna (HGA), transmitted a series of HGA select commands to stop the routine without having any other effect on the spacecraft. The first command of the series was received and stopped the routine. Several receiver telemetry channels began changing unexpectedly between two subsequent HGA select commands, and within 11 seconds the receiver power converter had failed; this was one-half hour after Receiver 1 had been turned back on. Anomalous telemetry data occurred in other subsystems during the receiver failure, with several indications in the photopolarimeter and an in crease in radio frequency noise in one channel of the harmonic radiation experiment of the planetary radio astronomy instrument. The Voyager document, quotVoyager 2 Command Receiver 1 Failure Analysis,quot details the telemetered failure indications and measurements from the other subsystems sent at the same time. It also hypothesizes a failure model fitting all the observations and based on confirming laboratory testing of Voyager assemblies, subsystems, and instruments. Additional Keyword(s): Surveillance, Captive Inserts, Conformal Coatings, Mission Operations Reference(s): Project Document 618-817, quotVoyager 2 Command Receiver 1 Failure Analysis,quot Arthur G. Gussner, Oct. 1979 Voyager Incident Surprise Anomaly (ISA) 1783, and Voyager P/FR 41029 Receiver Failure Model: The hypothesized failure model asserts that a resistive short from the 30-volt return line to chassis existed somewhere in the spacecraft at the time of the receiver failure. This first short had no effect on operation by itself and could not be detected by telemetry. Then a short to chassis occurred in the receiver, intermittent during the first three seconds and then continuous. This second short completed the short circuit and caused the receiver fuses to open. The location of the short outside the receiver is unknown. The short in the receiver, by itself, would not have caused the failure. The receiver short is believed to have been caused by a metal particle from a captivated insert contacting areas not sufficiently coated by the solithane conformal coating. The inserts are steel, constructed with a disk captivated in the end of the insert to prevent metal shavings from the screw or the insert from entering the electronic housing. The receiver short is believed to have been caused by the conductive end-caps that were pushed out of the inserts by over-length screws when the transponders, containing the receivers, were assembled to the spacecraft bay outer shear plates. As shown in the diagram, if the screw installed in the insert is too long, the captivated metal disk is pushed loose and a quotdonutquot of the insert is pushed loose with it. (The screws may have been too long through tolerance buildup in design, or wrong-length screws could have been inserted during assembly by error.) An examination of Voyager residual hardware revealed that the brush-on solithane conformal coating did not cover all areas, especially areas such as the edges of component leads where they were lap-soldered to circuit traces, bends in leads, the tops of horizontal leads, the edges of etched circuit traces, and the perimeters of transistor cans. [D] | JPL has referenced the lesson as supporting Paragraph 4.3.1 (quotFlight System Design: Power/Pyrotechnics Design - Generalquot) in the JPL standard quotDesign, Verification/Validation and Operations Principles for Flight Systems (Design Principles),quot JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 11/03/1995
418 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Command Feedthrough Problem on Voyager X-Band Downlink (~1975) | Since Galileo used inherited Voyager transponders, the mission also inherited the problem that an uplink carrier suppression that is optimal for command purposes tends to degrade X-band telemetry. The lesson describes link accommodations successfully implemented by both Voyager and Galileo. | With a strong uplink, the command performance requirements can be met with much less than optimum uplink carrier suppression. Some phases of a mission may not require a two-way coherent link. Changes in link configuration require verification through end-to-end performance tests. | Voyager uses a carrier suppression of 0.54 dB for the 64-meter stations compared to 3.0 dB for the 26-meter stations. The requirement for two different modulation levels does complicate mission operations. In noncoherent modes, the downlink frequency reference is derived from an on-board oscillator. Phase jitter in the loop VCO is acceptable under these conditions. Future projects, including Galileo, need to develop careful mission design to accommodate conditions such as command feedthrough where hardware modification is not considered feasible. Voyager command feedthrough parameters were established for the subcarrier frequency and bit rate used. Galileo will require similar tests for its bit rate of 32 bps, even though transponder design and command subcarrier frequency remain unchanged. 1995 Update: Missions presently in design at JPL use a 16 kHz command subcarrier to accommodate command feedthrough effects. | JPL | 07/08/1996 | (Relevant Historical Lesson(s) Learned) The design of phase-locked loop transponders for Deep Space missions is such that the loop is sensitive to uplink modulation components within its bandwidth. In the two-way coherent mode of operation, the frequency reference for the downlink carriers is the loop Voltage-Controlled Oscillator (VCO). On Voyager, the command subcarrier at 512 Hz and the command data at 16 bps modulated on the subcarrier produce a residual phase jitter in the loop VCO when optimum Deep Space Network command carrier suppression factors are used. The downlink carrier jitter degrades the telemetry demodulation process; this effect was imperceptible for S-band downlinks in the past. Command feedthrough was first observed on the experimental X-band transmitter (XTX) downlink on Mariner Venus-Mercury 1973 (MVM'73); however, Voyager was the first mission with the primary telemetry link at X-band. Voyager found that optimum (for command) uplink carrier suppression destroyed X-band telemetry. The Galileo telecommunications system includes inherited Voyager transponders; therefore, Galileo can expect the same command feedthrough problems as have been experienced on Voyager. Galileo does not plan to "fix" the problem because the resources to do so are deemed excessive relative to the inconvenience of accommodating to it. The required accommodations (for both Voyager and Galileo) are described below. Additional Keyword(s): Communication Link, Signal Degradation, Spacecraft Commanding, Tracking Loop Filter Reference(s): JPL IOM 3395-79-013, "Project Galileo Strategy to Accommodate Command Feedthrough Effects," R. L. Horttor, 25 January 1979 | JPL has referenced the lesson as supporting Paragraph 4.5.5 ("Telecommunications System Design: Telecommunications System Margins") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 11/02/1995
417 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | High-voltage Capacitor Used in Voltage Doubler Circuits for Space Applications (~1978) | Voyager circuit design verification showed that capacitors that were appropriate for use at atmospheric pressures, contained voids that could lead to corona and possible failure in space. This deficiency might not have shown up during testing. The possibility of critical pressure must be eliminated from all circuit parts capable of causing corona or arcing. Testing should not be relied on to catch all design weaknesses. | Standard circuit designs or parts which operate well at atmospheric pressure need to be verified for vacuum. Circuit changes to solve other problems may induce their own problems. The original problem was an instability in the TWTA power supply caused because the TWT reacted as a negative impedance load, and the power supply helix output voltage was fed back to control the voltage regulator. This problem was corrected by special focusing of the TWT's to minimize their negative load impedance characteristics and by adding a voltage doubler circuit to reduce the power supply's helix voltage output impedance. The changes that corrected the instability problem produced the large AC component on the high-voltage capacitors. | The space environment is a vital consideration in circuit design. Voids will slowly bleed down to critical pressure, thus allowing corona inception, which occurs at lower AC voltages than DC voltages. The possibility of critical pressure must be eliminated from all circuit parts having DC or AC potentials capable of causing corona or arcing. Many design weaknesses can be discovered through testing; however, testing should not be relied on to catch all. Independent analytical review of the circuit design and parts application benefitted the Voyager TWTA voltage doubler design. | JPL | 07/01/1996 | (Relevant Historical Lesson(s) Learned) A deficiency was discovered during circuit design verification which might not have shown up during testing. The condition involved capacitors having a large AC voltage between the capacitor body and its surroundings, and the capacitors having air pockets or voids between the body and the outside jacket. The finding is significant because this condition can remain harmless at atmospheric pressure, yet lead to corona and possible failure after months or years in the vacuum of space. To solve an interaction problem between the Voyager Traveling Wave Tube (TWT) and the power supply, the designer added a voltage doubler circuit having capacitors as integral parts of the circuit. The standard high-voltage capacitors initially used have the outside of the body taped to provide a moisture barrier. The doubler operates at 7.2 kHz with an input higher than 300 volts AC. The action of a voltage doubler is such that the two plates of the capacitors used change potential each time the inverter switches. The transformer winding that drives the doubler capacitors is referenced to the TWT collector through a diode bridge. Each winding output is, therefore, near collector voltage on one half cycle and changes by the transformer winding's output voltage (about 700 V) on the next half cycle. When the combined problem of the high AC voltage and the trapped air pockets was realized, the designers specified that modified capacitors, not having the tape wrapping, be procured. These were then specially prepared by vacuum coating with Scotchcast 281. | JPL has referenced the lesson as supporting Paragraph 4.12.2.3 ("Flight Electronics Hardware System Design: Electronic Packaging 0 High Voltage Designs") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/26/1995
416 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager - S/X-Band Antenna Subsystem Intermodulation Products at Cold Temperatures (~1976) | Qualification testing at extreme cold temperatures found that noise could be generated from the minute differential expansion between semi-rigid aluminum coaxial cables and their attached stainless steel shells. Beware of the intermodulation product phenomenon, and test for it during antenna subsystem pre- and post-environmental tests, after antenna installation on the spacecraft, and prelaunch. | Maintain a rigorous test program for detecting intermodulation products all the way up to launch. This would involve the use of a two-signal intermodulation test-set to assure that coaxial connectors or other components with contacting metal surfaces do not generate intermodulation products. | Testing to verify the absence of such products should be performed during the pre- and post-environmental tests at the antenna subsystem level, and also after installation of the antenna on the spacecraft in tests at the Spacecraft Assembly Facility (SAF) and as part of prelaunch preparations. The Hardware Design Engineer must be continuously cognizant of the intermodulation product phenomenon and implement design practices for its avoidance. Install the stainless steel mating shells on the semi-rigid aluminum cables with a torque from at least 45 in-lbs. | JPL | 07/01/1996 | (Relevant Historical Lesson(s) Learned) During qualification testing of coaxial cables at cold temperature (-200C for TA) it was found that intermodulation product signal levels were generated. These levels only occurred at the extreme cold temperature. On Viking it had been found that broadband noise could be generated in the mating surfaces of the aluminum four channel track connector. To eliminate that problem the Voyager connector mating parts were made of stainless steel. It was found in testing that there was minute differential expansion between the semi-rigid aluminum coaxial cables and the stainless steel shells that attach to the cables. The problem was eliminated by increasing the fabrication torque from 20 in-lbs to 45 in-lbs to prevent the loosening at extreme temperatures. Additional Keyword(s): Connector Fabrication Techniques, RF Intermodulation, Thermal Expansion Reference(s): Voyager PFR 38668 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.2.1 ("Engineering Practices: Telecommunications Design") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.5.5.1 ("Telecommunications System Design: Telecommunications System Margins - Design to Requirements")in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/19/1995
435 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Ground Support Equipment Failure Caused Damage to SEASAT-A (~1978) | A SEASAT-A subassembly was damaged during thermal-vacuum test due to the configuration of GSE test equipment. A reed relay in a commercial data scanner was connected to circuits requiring +5 volts; its failure permitted the SEASAT-A circuits to be exposed to scans as high as 31 volts. It is important to assess the design of commercial support equipment and consider what a failure of an internal part might do to the flight hardware. | The problem was caused by using a commercial piece of equipment without looking into its internal nature and considering what a failure in an internal part might do to the flight equipment. Previously, the SAR Transmitter had been tested at the contractor's facility, using the same set-up, with no problem. | This failure could have been avoided by providing an isolation resistor between each power supply terminal and the scanner. The voltmeter used to make the measurement has an input impedance of several megohms, so an isolation resistor of up to 100K ohms would have provided ample protection without affecting significantly the measurement accuracy. The difference between flight configuration and GSE configuration must be kept in mind. The normal inputs, connected to the spacecraft power converter, are isolated by at least 10K ohms. There is a need to be continuously conscious of the differences between flight and test configuration. The catastrophic potential of a reed relay failing to open was overlooked in this case. Support equipment failures must be prevented from propagating to the flight hardware. | JPL | 07/17/1996 | (Relevant Historical Lesson(s) Learned) A commercial data scanner using a bank of reed relays failed during thermal-vacuum testing of the SEASAT-A Synthetic Aperture Radar (SAR) Transmitter subassembly. Transmitter circuits requiring +5 volts were exposed to as high as 31 volts during each scan, resulting in catastrophic failure in the +5 volt circuits of the Transmitter. This problem caused about a two-week slip in the overall schedule, including the loss of 3 days of a one-week thermal-vacuum test and three days to repair the Transmitter. The nature of this problem could have caused the failure to occur anytime the sensor was operated with the ground support equipment as it was configured. The Transmitter GSE was configured with 15 separate regulated power supplies of various voltages. To allow automatic data acquisition of power supply voltage and current readings during the test, a data scanner driven by a computing calculator was implemented. This scanner consists of a bank of reed relays sequentially addressed by the calculator to acquire each power supply terminal voltage. Each power supply terminal was connected to a scanner reed relay switch terminal. The other side of the switches were then tied together to the bus, similar to a multiplexer arrangement. In the thermal-vacuum test, one of the reed relays failed to open. As a result, each succeeding power supply terminal that was scanned became electrically tied to the one connected to the relay that failed to open. The failed relay was connected to +5 volt supply. The other supply voltages ranged up to +31 volts. The JPL calibration Lab uses this type of data scanner at the present time. Additional Keyword(s): GSE Interface FMECA Reference(s): SEASAT SAR P/FR 4891 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Protection and Security of Flight Hardware: The Cognizant Engineer"), and Paragraph 7.2.5 ("Safety and Mission Assurance Practices: Reliability Engineering"), in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.5.1 ("Flight Electronics Hardware System Design: Interfaces - Flight-Support Equipment Interfaces") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/16/1995
405 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Stepping Commands Cause Positioning Problems (1970/76) | Unlike explicit commands, stepping or incremental commands, however, simply cause the device to move by the commanded increment from its current position to the new position. If the current position is incorrect, the next position and all subsequent positions will be incorrect. The use of explicit commands is recommended whenever no significant operational advantage exists using incremental commands. Should an incremental command capability be desired for other reasons, the system design should consider also implementing the explicit command capability to ensure fault tolerance. | All commands, whether stepping or explicit, have within them a potential for error. However, since explicit commands do not depend on the success of previous commands to be successful, they tend to be "fault-tolerant," in the sense that they do not perpetuate errors in the command sequence. | The use of explicit commands is recommended whenever no significant operational advantage exists using incremental commands. Should an incremental command capability be desired for other reasons, the system design should consider also implementing the explicit command capability to ensure fault tolerance. | JPL | 04/26/1996 | (Relevant Historical Lessons Learned) Mariner (M)'69 and Viking Orbiter (VO)'75 had problems because the designs used stepping commands rather than explicit commands. Explicit commands cause a device (such as the scan platform) to move directly to the desired state or position, regardless of its current position. Stepping or incremental commands, however, simply cause the device to move by the commanded increment from its current position to the new position. If the current position is incorrect, the next position and all subsequent positions will be incorrect. When a power problem occurred as M'69 was approaching its Mars fly-by, the scan platform moved inadvertently and the engineering telemetry needed to determine the platform's position was destroyed. The platform then had to be commanded by trial-and-error until Mars appeared in the returning pictures. Had this search not been successful in the short time remaining until Mars encounter, the entire science sequence would have been irretrievably lost. A less serious problem occurred on VO-1 when the position of the camera filter wheel got out of step with the picture-taking sequence. Once out of step, the several frames subsequently exposed were lost due to over/under-exposure. Correct exposure had to be restored by ground command. Additional Keyword(s): Software Reference(s): M'69 P/FR Nos. 204634, 204660 VO'75 VISA # 1450 (IOM 3623-BB-167) | JPL has referenced the lesson as supporting Paragraph 4.4.4.1 ("Information System Design: Commanding and Sequencing - Use of Toggle and Step Commands") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/16/1995
403 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Thrusters Fired on Launch Pad (1975) | Inadvertent commanding of the safing sequence while the Viking (VO-2) spacecraft was still on the launch pad enabled the RCS thrusters. The thrusters fired in an attempt to compensate for the Earth's rotation, resulting in a significant loss of attitude control gas. When command sequences intended to be exercised only in the event of abnormal spacecraft activity are stored onboard, consider the consequences of their activation during system test or the pre-launch phases. | When command sequences are stored on the spacecraft and intended to be exercised only in the event of abnormal spacecraft activity, the consequences should be considered of their being issued during the system test or the pre-launch phases. | Had the ability of the safing sequence to enable the thrusters been constrained in some manner until after launch, for example, the VO'75 problem would not have occurred. | JPL | 04/26/1996 | (Relevant Historical Lesson(s) Learned) On Viking Orbiter (VO)'75, a launch pad problem developed involving the flight software program and the Reaction Control System thrusters. The flight software, intended for use only after launch, contained within it a "safing sequence." The intent of the safing sequence was to automatically place the spacecraft in a safe state should some anomaly be detected. The safing sequence included commands to enable the Reaction Control System (RCS) and its thrusters. In spite of procedural safeguards, a problem developed which inadvertently resulted in the issuance of the safing sequence while VO-2 was still on the launch pad. This, in turn, enabled the RCS thrusters. The Attitude Control System then sensed the Earth's rotation, causing the RCS thrusters to fire in an attempt to compensate. Thruster firing continued until disabled by the test team, resulting in a significant loss of N2 attitude control gas. The launch was conducted without replacing the lost gas, rather than take the spacecraft down off the launch vehicle for replenishment. The safing sequence was also inadvertently issued several times during system test, but no adverse consequences resulted. Additional Keyword(s): Ground Operations, Pre-Launch Constraints Reference(s): VO'75 P/FR # 34869 |  | N/A |  |  | Public | Not Specified |  | 10/16/1995
415 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Radio Frequency (RF) Breakdown in Mariner Mars '71 Flight Radio Frequency Subsystem (RFS) Components and Circuits (~1971) | During final flight acceptance testing, an RF breakdown in an exciter revealed that its design was subject to RF breakdown at critical pressure. Costly design modifications late in the program were required to correct the design. All RF transmitter components and circuits should be analyzed and tested to determine their performance margin to any kind of RF breakdown. The lesson specifies the minimum margins. | All RF transmitter components and circuits should be analyzed and tested to determine their performance margin to any kind of RF breakdown. As a goal, all components and circuits should be designed to have a margin equal to a factor of four in power or a factor of two in voltage (6dB) against breakdown. | RF breakdown should be one component of the worst-case analysis normally required in the design, and it should be accomplished early in the development phase of the program. The breakdown margin must include all operating environments. Voltages, power levels, spacings should all be checked to determine the susceptibility to both multipaction and ionization (corona) discharge breakdown. The margin must be determined (tested) for each environment expected. As a minimum, a margin of 3 dB (factor of two in power; factor of 1.4 in voltage), which has been verified by testing, is required. The breakdown margin of a passive component can usually be measured by applying up to 6 dB more input power than is expected during normal operation. However, measuring the breakdown margin of an active circuit, such as a transistor amplifier, is much more difficult and requires a well thought-out testing program. | JPL | 07/01/1996 | (Relevant Historical Lesson(s) Learned) During the final flight acceptance testing of the second Mariner Mars '71 flight RFS, an RF breakdown occurred in one of the exciters at critical pressure. Investigation showed the exciter design had little or no margin to RF breakdown at critical pressure. Costly design modifications, late in the program, were required to correct the design. Also, during thermal-vacuum testing of the MM'71 RFS Proof Test Model, the RF output was found to be a function of the vacuum chamber pressure. The problem was traced to the circulator switch used to select the traveling wave tube amplifier and antenna. Investigation showed that the switch had not been analyzed nor adequately tested by the subcontractor to determine its margin to RF breakdown. Costly design modifications late in the program, were required to achieve an acceptable RF breakdown margin. The MM'71 Exciter RF breakdown investigation also determined that foam should not be used as an RF breakdown suppressant. Reference(s): JPL Technical Memo 33-573 "MM'71 RFS Subsystem", R.S. Hughes | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.3 ("Safety and Mission Assurance Practices: Reliability Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/16/1995
414 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Exciter RF Output Degradation on Mariner Mars '71 Caused by Emitter-to-Base Zenering in RF Transistors (~1971) | Because two RF transistors were overdriven, Mariner 9 exciter RF output showed slow and continual degradation throughout the mission. Short-term tests of RF circuits may not be sufficient to rule out zenering, and testing may be complicated by “healing” during the off period. | The worst-case analysis of all radio frequency circuits must include verification that transistors have sufficient margin to emitter-to-base zenering. Zenering can also occur in circuits, other than RF, if the emitter-to-base breakdown voltage is exceeded. Inflight variables, such as temperature and operating mode, make the assessment of degradation of this type extremely difficult after launch. | Short-term tests of the circuits may not be sufficient to rule out zenering. The rate of degradation is dependent upon the magnitude of zenering, and therefore changes in RF output can occur very slowly. Such changes may not be noticeable unless the circuit is operated continuously at a constant temperature for several days. Testing is complicated also by the condition of "healing." If the circuit is turned off, some of the performance degradation tends to be recovered when the circuit is turned back on. The extent of the recovery is dependent upon the off period. Healing also takes place more rapidly at elevated temperatures. | JPL | 06/26/1996 | (Relevant Historical Lesson(s) Learned) Telemetry data of the Radio Frequency Subsystem Exciter RF output on Mariner Mars '71 (Mariner 9) showed slow degradation after launch. The degradation continued at a very slow rate throughout the interplanetary cruise and the primary mission phases of the mission. By one year after launch, the exciter RF output had degraded sufficiently that the traveling wave tube amplifier power amplifier output had decreased 0.6 dB. The exciter output had decreased 2.6 dB. Investigation, including a review of the circuit design and laboratory testing, determined the exciter output degradation was caused by two RF transistors (2N3364 and 2N3375) being overdriven. Overdriving results in the permissible emitter-to-base voltage being exceeded, causing the emitter-to-base junction to be forced into a zener condition. The zenering causes the beta of the transistor to degrade, which results in a reduction of circuit gain. Reference(s): JPL IOM 3365-72-199, "Investigation of Mariner 9 Exciter Power Degradation," R.S. Hughes, 22 May 1972 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.2.3 ("Safety and Mission Assurance Practices: Reliability Engineering") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/16/1995
424 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager Unbalanced Attitude Control System and Thruster Impingement Effects on Navigation (~1977) | Shortly after the launch of Voyager, unexpected dynamic effects necessitated additional orbit determination analysis, testing, and modeling to ensure an accurate trajectory. Perform careful coordinated pre-flight analysis to determine the impact of such effects as torques induced by solar pressure and gas impingement on the spacecraft structure. Design and test to avoid impingement problems. | Orbit determination complexity is increased significantly when translational accelerations from the attitude control system must be accounted for. | Careful coordinated pre-flight analysis by both the Navigation and Spacecraft areas is needed to estimate the size and uncertainties of these effects, to establish the necessary operational interfaces, and to estimate the scope of the operations task. Spacecraft designs must be reviewed with an eye to avoiding impingement problems. If impingement is suspected, a test similar to the Voyager impingement test should be planned and executed early in the flight. | JPL | 07/10/1996 | (Relevant Historical Lesson(s) Learned) Shortly after Voyager launch, unexpected translational velocity increments and large non-gravitational acceleration effects were observed in the orbit-determination processing of tracking data. These velocity increments and accelerations were traced to the unbalanced translational accelerations produced by the attitude control system, its response to torques induced by solar pressure, and to the impingement of gas from the pitch thrusters onto other parts of the spacecraft structure. The magnitude of these dynamic effects required that they be modelled in the orbit determination process throughout the flight. This involved additional orbit determination processing and analysis, and necessitated a new operational interface between the Spacecraft Team and Navigation Team. A special in-flight impingement test was performed to provide data for modelling. The pre-flight analysis to recognize or predict the effects and uncertainties from both the unbalanced thrusters and the impingement was inadequate. The result was incomplete flight operations planning by both the Spacecraft and Navigation Teams. Additional Keyword(s): Trajectory Accuracy | JPL has referenced the lesson as supporting Paragraph 4.2.2.6 ("Flight System Design: Mechanical Configuration/Systems Design - Configuration (Plume Impingement)") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/16/1995
425 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Voyager Impact of Real-Time Commanding on Flight Operations (~1977) | Though necessary to support mission objectives, the Voyager Ground Data System and Mission Operations System design accommodated very limited real-time commanding. Correcting this required difficult modifications, and the real-time command generation capability still had limitations. Several recommendations are offered to assure that real-time commanding requirements receive careful consideration early in mission design. | Careful determination of real-time commanding requirements must be made early in mission design. | The spacecraft design should consider the ease of commandability of those subsystems most likely to require real-time commanding. Ground Software must be designed to readily accommodate the generation of the necessary real-time commands and to minimize the time and effort required to update the software initial conditions resulting from real-time command activity. MOS procedures must accommodate real-time commanding in a way which meets established timeliness criteria and is compatible with acceptable levels of risk. The resulting capabilities and limitations must be widely communicated to all Project interests. | JPL | 07/10/1996 | (Relevant Historical Lesson(s) Learned) The Voyager spacecraft system, Ground Data System (GDS) and Mission Operations System (MOS) were designed to accommodate very limited real-time commanding. Early flight experience revealed that frequent real-time commanding was necessary to support mission objectives. The required modification to the GDS and MOS was difficult and these systems still retain limiting characteristics which make real-time command generation more difficult and costly than is desirable. | JPL has referenced the lesson as supporting Paragraph 4.5.1.4 ("Telecommunications System Design: General - Telecommunications Capability for Special Mission Events") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/16/1995
360 | Rutledge, Pete - 0000000000 : NO@ADDRESS.GIVEN | Rutledge, Pete - 0000000000 : NO@ADDRESS.GIVEN |  | Single-string Pitot-static Air Data in Inherently Unstable Aircraft |  | The loss of air data from a single-string Pitot-static source due to icing or foreign object damage, can result in a departure from controlled flight (and possible catastrophic loss of aircraft) in aircraft which are inherently unstable and dependent on air data for dynamic stability. | Consider the use of a redundant air data source (one of diverse design so as to lessen the probability of common cause failure) to increase the reliability of air data. | HQ | 10/10/1995 | The X-31 is an inherently unstable experimental aircraft. Its dynamic stability is dependent on air data from the Pitot-static system. Unexpected icing of the single-string unheated Pitot-static air data source resulted in the aircraft departing controlled flight and crashing. X-31 Experimental Aircraft |  | N/A |  |  | Public | Not Specified |  | 10/12/1995
359 | Rutledge, Pete - 0000000000 : NO@ADDRESS.GIVEN | Rutledge, Pete - 0000000000 : NO@ADDRESS.GIVEN |  | Pitot-Static Heating/Icing |  | Even in normally dry, temperate environments, humidity/temperature conditions at flight altitude can be such as to result in icing of the Pitot-static probe if a heater is not provided. | Consider the use of Pitot-static heating, even in the case of experimental aircraft used exclusively in normally dry, temperate environments. | HQ | 10/10/1995 | During the course of its test program at Dryden Flight Research Center, Edwards, CA, the X-31 experimental aircraft was retrofitted with an unheated Pitot-static probe (of the Kiel probe design). Unexpected icing of the single-string Pitot-static air data source resulted in the aircraft departing controlled flight and crashing. X-31 Experimental Aircraft Pitot-Static Probe |  | N/A |  |  | Public | Not Specified |  | 10/12/1995
361 | Rutledge, Pete - 0000000000 : NO@ADDRESS.GIVEN | Rutledge, Pete - 0000000000 : NO@ADDRESS.GIVEN |  | Parachute Diameter and Pilot/Payload Descent Rate |  | In the case of an over land ejction and depending on pilot/payload weight, the 17 foot diameter main parachute in the F-18 egress system can allow a sufficiently high descent rate as to make parachute landing fall injury highly probable. | Consider use of a larger diameter main parachute, especially where ejection is likely to be over land. | HQ | 10/10/1995 | The X-31 experimental aircraft used the egress system from the F-18 fighter aircraft, including its 17 foot diameter main parachute. A test pilot ejected from the X-31 over Edwards Air Force Base, CA. The pilot's calculated descent rate was over 28 feet per second. The parachute landing fall resulted in multiple injuries. X-31 Experimental Aircraft |  | N/A |  |  | Public | Not Specified |  | 10/12/1995
407 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Helios I Communication Link Degradation Due To Interferometer Effect and Spin Modulation From Spacecraft Antenna (~1972) | The composite pattern of two Helios I low-gain antenna elements caused an “interferometer effect”, with rapidly varying phase and amplitude values occurring over a small but critical portion of the antenna pattern. Design of spacecraft antennas must include careful attention to amplitude and phase characteristics of the combined antenna system pattern, rather than to those of the individual elements alone. | Design of spacecraft antennas must include careful attention to amplitude and phase characteristics of the combined antenna system pattern, rather than to those of the individual elements alone. Communication link analysis must use sufficiently accurate approximations to the actual expected (or measured) antenna system patterns. | After the antenna pattern variations were noted during the mockup test, the Communications Ground Systems section developed a mathematical model which simulated the observed data closely. This model was used prior to launch, in conjunction with Deep Space Network station (CTA 21) to model the anticipated system degradation. It was also used to devise tracking methods to minimize the disturbing effects of the interferometer and spin modulation. | JPL | 06/24/1996 | (Relevant Historical Lesson(s) Learned) Prior to Helios I launch, the communication links to and from the spacecraft were expected to be degraded because of spin modulation and interferometer effects created by the low-gain antenna elements. The resultant signal, as measured using a mockup, had combined amplitude, phase and frequency modulation, which had not been considered in the link design. The amplitude and phase variations degraded the received uplink and downlink channels (command and telemetry) and created a marginal condition to carrier tracking (doppler). The Helios I low-gain antenna was made of two elements: (a) a linearly-polarized dipole, mounted on top of the spacecraft, parallel to the spacecraft's spin axis; and (b) a circularly polarized antenna mounted on the bottom of the spacecraft, off-set six wavelengths from the spacecraft's spin axis. The composite pattern of the two antennas caused an "interferometer effect", with rapidly varying phase and amplitude values occurring over a small but critical portion of the antenna pattern. The "look angles" associated with this portion of the pattern were important during some mission phases. Reference(s): JPL TR 32-1526, Vol. XIV "DSN Progress reports for Jan.-Feb. 1973, pp 149-160 JPL TR 42-1526, Vol. XVIII, "DSN Progress Reports for Sept.-Oct. 1973, pp 147-162 DSN Progress Report 42-20, Jan-Feb. 1974, pp.154-166 DSN Progress Report 42-23, July-Aug. 1974, pp. 87-91 | JPL has referenced the lesson as supporting Paragraph 4.2.2.7 ("Flight System Design: Mechanical Configuration/Systems Design - Configuration (RF Pattern Distortion)") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 10/05/1995
408 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Mariner'71 Fuse Incident (1970) | Mariner'71 testing was delayed when replacement of one blown fuse required the removal of a module containing other fuses necessary to the safe testing of the spacecraft, thereby postponing further testing on all the affected components. Located fuses in the fused devices instead of concentrating them in the power subsystem does leave the cabling unprotected by the fuses, but the reliability of the cabling is so high that this lack of protection is usually well justified. | Fuses should be located within the device being fused, rather than concentrating them within the power subsystem. | Fuses are normally coated in place. The unit in which they are installed must be removed from the spacecraft to replace the fuse. Removing a fused device is preferable to removing elements of the power subsystem because it causes less disturbance to the test. Moving the fuse to the device does leave the cabling unprotected by the fuse but the reliability of the cabling is so high that this lack of protection is usually well justified. Mariner'69 and Mariner'71 had fuses in various locations. Some were concentrated in the power subsystem; others were within the individual devices. Since that time, fuses have usually been located within each individual device being fuse. | JPL | 06/24/1996 | (Relevant Historical Lesson(s) Learned) Mariner'71 testing was delayed when replacement of one blown fuse required the removal of a module containing other fuses necessary to the safe testing of the spacecraft, thereby postponing further testing on all the affected components. Fuses for the Data Storage Subsystem (DSS) tape recorder and several other subsystems were located within the power subsystem. During test, several devices, including the tape recorder, were removed from the spacecraft while other tests continued. This would have reduced the electrical load below the level required for stable operation of the power conditioning unit. To ensure stability, a dummy load was connected in place of the DSS that had been removed. However, the load applied had too low an impedance. Whenever spacecraft power was reapplied, the tape recorder fuse blew at its 1 amp design value and successfully protected the power subsystem. The blown tape recorder fuse, along with other fuses were tightly packaged and conformally coated within the power distribution module. To replace the fuse, the entire unit had to be returned to the vendor for 7-10 days. This prevented further testing on all devices whose fuses were also contained within the unit, delaying the test program. Additional Keyword(s): Packaging | JPL has referenced the lesson as supporting Paragraph 4.12.1.8 and 4.12.1.8.2 ("Flight Electronics Hardware System Design: General - Use of Fuses - Fuse Accessibility") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/21/1995
423 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Viking Navigation - Unexpected Non-gravitational Acceleration Due to Lander Outgassing (1975) | Immediately after the launch of Viking I, large and unexpected non-gravitational accelerations were detected and attributed to outgassing from porous materials (e.g., parachute, blankets, etc.) in the lander. A midcourse correction made to preclude large targeting errors upon Mars Encounter. Every spacecraft design should be reviewed for its potential for outgassing (and its impact on the navigation strategy and the spacecraft) throughout flight. | Every spacecraft design should be reviewed for its potential for outgassing at any time during flight. | The magnitude of the resulting non-gravitational accelerations should be estimated and compared with the navigation requirements on non-gravitational accelerations. If these requirements are exceeded, re-design of the navigation strategy and/or the spacecraft may be required. | JPL | 07/10/1996 | (Relevant Historical Lesson(s) Learned) Immediately after the launch of Viking I, large and unexpected non-gravitational accelerations were seen when the Doppler observations of the spacecraft were processed for orbit determination. These perturbations to the spacecraft dynamics were confirmed by observations of the attitude-control limit-cycle motion. Spacecraft team analysis identified the cause as the venting of outgassing products from porous materials (e.g., parachute, blankets, etc.) in the lander. There was considerable uncertainty in the expected duration of the effect. This uncertainty raised the possibility of large targeting errors at Mars; consequently, the effect was included in the design of the midcourse correction made shortly after departure from Earth. The effect appeared to cease 1 to 2 months after launch, and did not in fact significantly increase targeting errors. The same effect was observed on Viking II. | JPL has referenced the lesson as supporting Paragraph 4.2.2.6 ("Flight System Design: Mechanical Configuration/System Design - Configuration - Plume Impingement") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.) | N/A |  |  | Public | Not Specified |  | 09/21/1995
431 | Bott, J - 0000000000 : NO@ADDRESS.GIVEN | Bott, J - 0000000000 : NO@ADDRESS.GIVEN |  | Mismate of Identical Connectors, ASTROS Project, 1988 (Repeated Events: a. Galileo b. TOPEX c. Cassini) | During the system assembly process for the ASTROS Tracker, two external interconnect cables between the Sensor Assembly and the Electronic Assembly were cross connected. This problem was repeated on the TOPEX project and in two instances on Cassini: one transposition of connectors made it necessary to remove and replace 26 over stressed transistors. Lesson #0431 provides 6 recommendations regarding connector configuration, installation, placement, identification, and inspection. | Inadequate connector identification and/or adjacent placement of identical connectors when combined with human error can result in mismating of interconnect cables, with potentially damaging effects. | Avoid placing identical connectors in adjacent locations where mating connectors can easily be transposed during installation. When the conditions noted in recommendation #1 above are unavoidable, add a requirement that all connectors to be mated are clearly identified by color codes or other means which will make it obvious if transposition is about to occur during the mating process. If feasible, configure the cables in such a manner that the cable connectors cannot readily be mated with the wrong connector. Ensure that assembly technicians are trained, and sensitized to the dangers inherent in the transposition of connectors. Mandate that any mate of identical paired connectors be verified by a second party (preferably Quality Assurance) before any application of power. Series connect unique pairs of jumpered pins in identical connectors, and terminate the series connection in an external connector. Verify installation by continuity test. | JPL | 07/15/1996 | During the system assembly process of the S/N 002 ASTROS Tracker, two external interconnect cables between the Sensor Assembly (SA) and the Electronic Assembly (EA) were cross connected.* Causes of the problem: At the EA end of the cable harness, the design incorporated the use of identical connectors. On the EA, mating connectors were installed side by side. Identification of connectors on the cables was inadequate, and not readily apparent. Inadequate attention was paid to positioning of the connectors during the installation process. Fortunately, the ASTROS Instrument suffered no damage as a result. Repeated Events: On the Galileo Project, a Data Memory System flight unit was severely damaged when two internal cable connectors were transposed. Identical connectors, installed side by side, were cross connected under poor conditions for recognition. In this case, it was necessary to remove and replace twenty-six over stressed transistors. On the TOPEX Project, a similar event occurred at the Satellite System Contractor. Unfortunately, details of that problem are no longer readily available. Due to the nature of the circuitry involved, the effects of the transposition of connectors was relatively minor. On the Cassini Project, a similar event occurred at a supplier facility. Two test cables were reversed during set-up. The unit did not experience any additional stresses as a result.** Additional Keyword(s): Assembly Practices, Cabling Reference(s): *PFR #41718 & **PFR #59732 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.17.9.1 ("Engineering Practices: Hardware Development - Electronic Packaging/Cabling Design and Fabrication") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.5.4 ("Flight Electronics Hardware System Design: Interfaces - Connector Mis-Mating"), and Paragraph 8.3.2.1 ("System Assembly, Integration and Test: System Integration"), in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/14/1995
432 | Gussner, A - 0000000000 : NO@ADDRESS.GIVEN | Gussner, A - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Observer (MO) TWTAs Were Not Qualified (while powered) for Pyrotechnic Shock (1993) | The MO Traveling Wave Tube Amplifiers (TWTAs) were not powered during qualification Pyrotechnic Shock testing. As a result, the TWTA beam and cathode heaters were not powered during the critical MO tank pressurization to allow real time telemetry during this critical event. Fully consider the cost/risk tradeoff of not qualifying critical inherited designs for new operational uses. | Unless precluded by solar system obstacles, a spacecraft should be configured to allow real time telemetry during critical events. Such telemetry may provide crucial spacecraft health and safety data for other spacecraft missions with similar systems or activities as well as for the current mission. | Fully consider the cost/risk tradeoff of not qualifying critical inherited designs for new operational uses. Potential loss of function of a redundant element may be preferable to obtaining no telemetry during high risk events. | JPL | 07/17/1996 | The MO Traveling Wave Tube Amplifiers (TWTAs) were not powered during qualification Pyrotechnic Shock testing. As a result, the contractor's operations plan included not powering the beam and cathode heaters of both redundant TWTAs (thus no downlink telemetry) during the critical MO tank pressurization. Although this was a topic of significant debate during the design and manufacturing phases, early cost constraints resulted in decisions not to perform developmental testing and analysis to show whether or not there would be a problem powering the TWTA during the MO Pyrotechnic events. Analysis was performed to determine the lateral and axial capability of the cathode support design when powered off (cold). Actual testing to qualify the TWTA for powered operation (hot) was not performed, also based on programmatic cost constraint decisions. Additional Keyword(s): RF Testing Reference(s): "MO Design & Implementation Audit": JPL D-11433 "MO Loss of Signal: Special Review Board Final Report": JPL Publication 93-28 "Report of the MO Mission Failure Investigation Board" (the Coffey Report) | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14 ("Engineering Practices: Project and System Level Functional Verification and Validation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 3.1.2.1 ("Mission Design: Communications During Mission Critical Events - Uplink/Downlink Capabilities") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/14/1995
422 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Particles Generated by Pyrotechnic Events (1967/76) | Following a Viking Orbiter pyrotechnic-actuated event, debris was viewed by the star tracker as numerous bright objects, initiating a command to change the spacecraft roll position. During and following a pyrotechnic event, place the spacecraft in roll inertial and disable any Canopus-loss fault protection software. | Always take the precaution of placing the spacecraft in roll inertial and disabling any Canopus-loss fault protection software at and following a pyrotechnic event. At these times particles are shocked loose from parts of the spacecraft, from whence they drift through the Canopus tracker field of view. | Provide at least an hour's protection period following these events before returning the spacecraft to normal roll control. Bright objects resulting from a pyro event may also adversely effect other devices such as science instruments. A one-hour delay in operating these devices should be considered. | JPL | 07/10/1996 | (Relevant Historical Lesson(s) Learned) At the time of Mariner 6 scan platform unlatching, which was effected by firing a pyrotechnic squib, several bright objects were seen by the Canopus tracker. This caused the tracker to lose lock on Canopus, causing a roll search to be initiated. For 25 minutes following the first opening of the Viking Orbiter-1 propellant pressurant supply (a pyrotechnic-actuated event), the spacecraft roll axis was commanded to roll inertial hold and the Canopus-loss fault protection software was disabled. During the first part of this period, numerous bright objects were seen by the Canopus tracker. Within a few minutes after completion of the inertial hold period, another bright particle was seen by the tracker, this time causing the spacecraft roll position to change and the on-board software to execute the Canopus-loss fault protection response. Additional Keyword(s): Attitude Control, Science Viewing | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.7 ("Engineering Practices: Project and System Level Functional Verification and Validation - Verification and Validation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.3.4.3 ("Power/Pyrotechnics Design: Pyrotechnic Function - Enabling of Pyrotechnic Functions") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 08/10/1995
413 | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN | Roberts, J - 0000000000 : NO@ADDRESS.GIVEN |  | Incorrect Actuations of Relays in Matrix (1975) | Because the Viking Orbiter power switching relays were arranged in a matrix, two relays could under certain conditions be inadvertently actuated when only one was commanded. A system control protocol should be established whereby independently requested relay actuations are executed in a predictable manner. | Relay matrices should be designed to prevent actuation of additional relays caused by multiple relays being commanded simultaneously. |  | JPL | 06/26/1996 | (Relevant Historical Lesson(s) Learned) Under certain conditions, the Viking Orbiter (VO)'75 power switching matrix permitted two relays to be actuated inadvertently when only one was commanded. This occurred twice during system test at Eastern Test Range, causing potentially detrimental state changes. The power switching relays were arranged in a matrix. Actuation of a relay required enabling the correct column (source) and row (sink). The desired relay was actuated because only one relay corresponded to a given row and column. However, when two relays are commanded simultaneously, two columns and two rows are enabled at the same time, permitting up to four relays to be actuated. Diode isolation reduced this number to three. On VO-75, when the battery was fully charged, the design provided for a power relay command to be automatically sent to reduce the charge rate to a low level. The test team was commanding other relays in the matrix, not anticipating the automatic battery charge command. On two occasions, these commands arrived simultaneously, causing a third relay to be actuated inadvertently. Additional Keyword(s): Ground Operations Reference(s): VO'75 P/FR No. 34874; 35304 | JPL has referenced the lesson as supporting Paragraph 4.4.4.6 ("Information System Design: Commanding and Sequencing - Commanding Reliability") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 08/10/1995
391 | Tyler, S - 0000000000 : NO@ADDRESS.GIVEN; Blosiu, J - | Tyler, S - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Spacecraft Safing Recovery Anomalies | The Galileo mission twice experienced difficulties with recovery from safing errors due to a lack of a formal safing recovery plan and to software/documentation that had not been kept current on spacecraft states. Maintain and update an anomaly recovery plan, log spacecraft event updates, take care in reusing previously successful command packages, and identify nonstandard ground system configurations. | No formal safing recovery plan existed. Coupled with an ambitious deadline for recovery completion, this resulted in inadequate review, inspection, checking and testing of the recovery package. Documentation relating to pre-fault and post-fault spacecraft states was not kept current, and the configuration management system to log updates to system fault protection changes was lacking. Spacecraft state is not always easy to identify and errors in spacecraft state determination are possible. This caused some confusion during this event. Software packages that have worked in the past could prove to be faulty or inappropriate for the current spacecraft state. It is risky to depend on nonstandard ground system configurations in constructing commands. | Priority should be given to maintain and update an anomaly recovery plan with an explicitly defined anomaly recovery team, with backups, and roles for each team member. Establish a configuration management system to log spacecraft event updates including documentation for software updates, commands, pre-fault and post-fault spacecraft states and anomaly resolution. Be prepared to immediately delay, delete or redo less-critical activities to enable highly reliable recovery work. Care must be taken when reusing previously successful command packages. Ensure that nonstandard ground system configurations are clearly identified in operational instructions. | JPL | 05/30/1995 | Two Galileo Spacecraft anomalies occurred during the week of September 12, 1994. Several difficulties were encountered during the recovery from these anomalies. The first anomaly was a Data Bulk Unit Memory (DBUM) parity error on the Galileo Command and Data Subsystem (CDS). This nonprivileged error resulted in spacecraft safing but did not bring down either CDS string. In response to this anomaly, the flight team developed a special privileged command program to isolate the failed memory byte. Although this program was almost identical to a recent successfully run program, it required a nonstandard ground system configuration for command translation. This configuration was not established, causing the second anomaly which brought down the CDS A-string and re-executed safing. During the recovery from this second safing, an existing recovery file was left unchanged from a year earlier, even though the one-way light time had doubled. As a result, an inappropriate Telemetry Modulation Unit (TMU) modulation index command was uplinked, causing a short data outage. During both recovery efforts, it was believed that the system fault protection associated with safing had turned off the High Voltage (HV) to the Heavy Ion Counter (HIC). In fact, a patch had been implemented a year earlier, which prevented the fault protection from turning off the HIC HV. A lack of proper configuration management along with an inadequate check of the spacecraft state created this confusion. Since a prolonged lack of HV to the HIC would permanently damage the HIC, the project was forced to consider a risky proposal to switch the HIC to the only remaining working CDS string in an unnecessary attempt to get the HIC HV back on. The overall recovery time was 12 days. Had the spacecraft been in a critical operation mode, this long recovery time could have been more detrimental. A standardized anomaly recovery plan would have helped avoid some of the above problems. Additional Keyword(s): Commanding Reference(s): IOM GLL OET-95-023-GMcS-SRT, Jan. 20, 1995, Spacecraft Anomaly Recovery and Lessons Learned for the CDS Anomalies. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.2.2 ("Engineering Practices: Mission Operations - Process and Procedure") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 04/24/1995
387 | Zenone, R - 0000000000 : NO@ADDRESS.GIVEN | Zenone, R - 0000000000 : NO@ADDRESS.GIVEN |  | NOAA-13 Satellite Solar Array Bus Short to Ground | When all contact with a weather satellite was lost, it was surmised that thermal cycling had caused one or more mounting bolts to protrude through a heat sink and short the solar array output to ground. Review packaging designs, assure ease of manufacturing and inspection, provide for adequate temperature margins, and consider the mission thermal cycle profile in design and test. | Poor packaging design and an inadequate insulation scheme allows numerous places for electrical shorts. Poor processing and insufficient inspection were major contributors to the failure. In-flight temperature extremes experienced by NOAA-13, due to increased power requirements imposed by flying additional instruments, were greater than experienced by previous NOAA satellites of this series and were near qualification temperature limits. | Packaging designs, whether new or inherited, need to be reviewed for adequacy; especially when electrical power and thermal aspects of a design can be affected by spacecraft system configuration changes. Manufacturing processes need to encompass ease of manufacturing and inspection aspects. Inspection must be performed by Quality Assurance instead of by an assembler. Adequate temperature margins between qualification temperatures and expected in-flight operating temperatures need to be assured. Consider mission thermal cycle profile in mission design and test. | JPL | 02/21/1995 | The National Oceanic and Atmospheric Administration (NOAA) weather satellite NOAA-I (NOAA-13 after launch), was launched on 9 August 1993 from Vandenberg Air Force Base. No anomalies were encountered during flight until 21 August 1993 at which time it was determined from telemetry data that while in full sun, the solar array was inoperative and that the spacecraft was being powered by the batteries. Within six orbits after observance of the anomaly, communication with the spacecraft was found not to be possible and no downlink signal from the spacecraft was thereafter detected. Upon closer examination of recorded spacecraft telemetry data, it was ascertained that the solar array was putting out electrical power, but that no power was being provided to the battery charging unit, and the batteries were not receiving a charge. Cause of the failure surmised by the cognizant operations crew and concluded by the Goddard Space Flight Center (GSFC) NOAA-13 Failure Review Board, was that the solar array bus had shorted to spacecraft ground. Specifically, constant thermal expansion and contraction in excess of previous flights was thought to have caused one or more mounting bolts protruding through the heat sink contained in the battery charging unit to penetrate isolation material and short the solar array output to ground. It is believed that a rise in temperature and resultant increase in temperature excursion were due to greater electrical power required to operate additional instruments added to the spacecraft. Reference(s): NOAA-13 Failure Report, dated August, 1994 by Goddard Space Flight Center | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.13.1.2 ("Engineering Practices: Design and Verification for Environmental Compatibility") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.12.2.1 ("Flight Electronics Hardware System Design: Electronic Packaging - Qualification of Electronic Packaging") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/02/1995
362 | Gussner, A - 0000000000 : NO@ADDRESS.GIVEN | Gussner, A - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan Radio Transmitter A Modulation Failure | Loss of Magellan telemetry data was traced to moisture contamination due to a subcontractor's failure to use dry gas in the repackaging of an operational amplifier. Recommendations involve use of fault tree analysis, appropriate component screening and qualification, minimizing power cycling, and using dry gas. | In-flight failures cannot always be conclusively analyzed using available telemetry data. Failure to qualify electronic components and assembly capabilities to mission environmental requirements (including numerous power/thermal cycles) increases risk. Power cycling can create thermal cycle effects on internal failure mechanisms for electronic components and assemblies. Not using dry gas in the repackaging process can allow moisture to be trapped inside electronic components (hermetically sealed packages with a cavity) and possibly create pinholes if they don't already exist. Water can also evolve from thermally induced decomposition of the epoxy die attach. Moisture could then combine with the phosphate glass to generate corrosive phosphoric acid that can make the electronic component inoperative. | Consider using a fault tree matrix during the design phase to identify critical telemetry parameters needed to analyze failures. Match component screening and qualification to the mission, including any expected significant thermal cyclic excursions. Minimize mission designed power cycling to reduce thermally induced stress. Use of dry gas with moisture content below 5000 PPM in repackaging electronic components is a must. | JPL | 11/04/1994 | After a star calibration during the Magellan third extended mission, the X Band telemetry and high rate data were missing from the down link (22 kHz and 960 kHz subcarriers were missing). A subsequent attempt to use the 360 kHz subcarrier also resulted in no significant subcarrier in the down link. The most likely failure is a HA 2520 operational amplifier used as a summing amplifier in the telemetry signal conditioner (although a failure in the phase modulator circuitry is also a possible cause). It failed after 20,600 hours of flight operation and 2,600 power cycles (resulting in 10-15 degree thermal cycles). A prelaunch failure on this component type indicated the possibility that during the repackaging process by the subcontractor of the HA 2520, moisture was trapped inside the electronic component. This moisture would combine with the phosphorus dopant in the glass passivation forming phosphoric acid that would enter through pinholes in the passivation layer and attack the nickel-chromium resistors causing failure. The subsystem contractor did not use a dry gas during the repackaging process; instead air with a moisture content of greater than or equal to 5,000 PPM water was used. The prime contractor, with JPL concurrence, felt that additional screening had been sufficient to identify any other faulty HA 2520 amplifiers. It was concluded that the in-flight failure may be related to stress induced by thermal cycles resulting from on-off power cycling. As a result of this failure, the degraded transmitter B had to be used to return science data at a lower rate for the remainder of the mission. Additional Keyword(s): IC Manufacturing and Packaging Reference(s): PFR #52621 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 7.5.4 ("Safety and Mission Assurance Practices: Electronic Parts Reliability, Application, and Acquisition") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 01/23/1995
346 | Platt, Marilyn - 0000000000 : NO@ADDRESS.GIVEN | Platt, Marilyn - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Heritage Designs on the Mars Observer | Although inherited designs were to be used extensively, many Mars Observer spacecraft subsystems were so extensively modified over the 8-plus year development period that their heritage was lost. Perform inheritance reviews to span differences in design usages, ensure inheritance reviews include the assessments listed in the lesson, and perform delta reviews when major mission changes occur. | Reliance on heritage hardware/software in spacecraft design, without a thorough analysis of compatibility with mission requirements and required changes, can result in the use of design and components which are inappropriate for the mission. | Perform inheritance reviews to span the differences between the previous use of existing spacecraft designs, hardware and software, and planned new usage. Inheritance reviews should include the following assessments: Verification that the inherited hardware/software designs are compatible with the spacecraft design, mission environment, qualification requirements and product assurance requirements. Verification of the necessity and mission compatibility of design changes and implementation plans. Determination of whether additional protoflight testing will be required for the inherited hardware/software. Identification of potential risks associated with documented problems of inherited hardware and software. Delta inheritance reviews should be performed when major mission changes occur. | JPL | 10/21/1994 | As originally envisioned, inherited designs were to be used for many of the Mars Observer spacecraft's engineering subsystems. During its eight-plus year development period, however, the Mars Observer mission underwent a number of significant changes. Many of the spacecraft subsystems were so extensively modified for Mars Observer that their heritage was lost. Other subsystems, whose heritage remained intact but which were designed for an earth-orbital environment, were not requalified to verify that they would function properly on an interplanetary mission of three years duration. Examples include: The failure to fully qualify the Traveling Wave Tubes (TWT) in the transmitter power amplifiers for operation during pyro-shock events. The lack of robustness in the design of the bipropellant pressurization system for long duration missions. The use of fault-management software, containing processing algorithms derived from the Defense Meteorological Satellite Program (DMSP), that was not fully understood. Reference(s): Mars Observer Loss of Signal: Special Review Board Final Report: JPL Pub. 93-28 JPL Lesson Learned, No. 3-108, Subject: Mars Observer Pressure Modulator Infrared Radiometer (PMIRR) Cooler Failure During Vibration Testing JPL Lesson Learned, No. 10-102, Subject: Mars Observer Inertial Reference Loss IOM 525-89-344, dated 12/14/89, by L. E. Baughman and R. F. Draper, Subject: MMII Inheritance Reviews | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6.2 ("Engineering Practices: Inheritance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 10/20/1994
347 | Shain, T - 0000000000 : NO@ADDRESS.GIVEN | Shain, T - 0000000000 : NO@ADDRESS.GIVEN |  | Impact of Industrial Mergers/Key Management Changes | When a contractor was absorbed by a second contractor early during the performance of the Mars Observer contract, the new contractor's management implemented methods that were not consistent with the original, agreed upon plans for integration and test. This created problems between JPL and the new contractor management. Reconfirm the contract should major changes occur in the contractors organization, document critical technical and programmatic agreements, and revalidate agreements when changes in key personnel occur. | Problems can arise when major management changes occur at the contractor such as a corporate takeover. Agreements with key personnel are likely affected by major management changes. | Reconfirm the contract should major changes occur in the contractors organization. Critical technical and programmatic agreements with the contractor should documented. Revalidate agreements when changes in key personnel occur. | JPL | 10/21/1994 | Original plans for integration and test agreed upon by the original contractors management were based on their past methods. This contractor was absorbed by a second contractor early during the performance of the Mars Observer contract. When the second contractor took over, they had other methods that were not the same as the original approach. This created problems between JPL and the second contractor management in performing the contract. Reference(s): Mars Observer Loss of Signal: Special Review Board Final Report: JPL Pub. 93-28 Report of the Mars Observer Mission Failure Investigation Board, Volume I, dated 12/31/93 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 3.5.6 ("Implementation: Roles and Responsibilities") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 10/13/1994
344 | Yell, Dena - 0000000000 : NO@ADDRESS.GIVEN | Yell, Dena - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Propellant in Contact with Porous Material, Fire |  | Porous materials, such as wood, when in contact with solid propellants may absorb/acquire the hazardous properties exhibited by the solid propellant. | Avoid the use of combustible porous materials, such as wood, as tools for working on or in conjunction with solid propellants. | MSFC | 10/05/1994 | A fire occurred on November 27, 1982 at the Arnold Engineering Development Center as a result of cutting propellants on the floor of a vertical test cell. The propellant being cut was from M-X Stage II and was a Class 1.3,88 weight percent solids, HTPB, Non-HMX type. Combustion was attributed to either impact or friction. |  | N/A |  |  | Public | Not Specified |  | 10/05/1994
320 | Little, Robert - 0000000000 : NO@ADDRESS.GIVEN | Little, Robert - 0000000000 : NO@ADDRESS.GIVEN |  | Crew Training for On-Orbit Operation of Payload Equipment |  | Training and mission simulation for crew and ground support personnel relating to on-orbit payload operation should be continued on future missions to enhance the efficiency of on-orbit operations. The training simulators and mission simulations should be of high fidelity. The number and duration of mission simulations should be based upon the length and complexity of the mission. A minimum of 2 simulations 3 to 4 weeks apart, one to include science team members, should be required. | Provide crew training which encompasses the following concepts: high-fidelity mockups available in the crew training center; the degree of fidelity should be driven by the degree of safety concern and the amount of crew time dedicated to an experiment during the mission. High-fidelity software simulators available for all experiments, which have crew interface or data output. The degree of fidelity should be driven by safety concerns and on-orbit crew time scheduled for the experiment. Provisions for hands-on crew participation in integrated tests. At least two long-duration mission simulations should be conducted with mandatory participation of the science team (principal investigator) in at least one. | MSFC | 08/04/1993 | Experience on SL-1 indicated that efficiency of orbital operations was somewhat compromised when ground training did not include exposure to high-fidelity training simulators. | Comparison of operations of equipment with training accomplished on high-fidelity mockups with operation of equipment for which good mockups were not available demonstrated the effectiveness of the recommended approach. Subsequent missions have supported this conclusion. | N/A |  |  | Public | Not Specified |  | 09/22/1994
319 | Yell, Dena - 0000000000 : NO@ADDRESS.GIVEN | Yell, Dena - 0000000000 : NO@ADDRESS.GIVEN |  | Principle Investigator Knowledge of Payload Carrier (Spacelab, Shuttle Orbiter, Experiment Support Structure) |  | Reading provided documents does not, by itself, yield sufficient information for experimenters, etc., to get a thorough understanding of payload carrier capabilities. This leads to misunderstandings and design problems, which might have been circumvented had there been face-to-face communications between experimenters and mission managers and their technical support team. | Mission managers and their technical support team should have face-to-face meetings with experimenters during the preliminary phases of development prior to the submittal of experiment requirements on the payload carrier. This will enhance the experimenters understanding of carrier interfaces and interface design philosophy and decrease the design problems which could result from insufficient communications. | MSFC | 08/04/1993 | Experience on SL-1 and subsequent missions indicated that early face-to-face meetings with experimenters were indispensible. | Collective wisdom. | N/A |  |  | Public | Not Specified |  | 09/22/1994
345 | Bernard, D - 0000000000 : NO@ADDRESS.GIVEN; Blosiu, J - | Bernard, D - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Observer Attitude Control Fault Protection | From the analyses performed after the Mars Observer mission failure, it became apparent that the MO fault protection suffered from a lack of top-down system engineering design approach. Most fault protection was in the category of low-level redundancy management. It was also determined that the MO fault protection software was never tested on the flight spacecraft before launch. Design fault protection to detect and respond to excessive attitude control errors, use RCS Thrusters to control excessive attitude control errors, and always test fault protection software on the flight spacecraft before launch. | MO fault protection did not detect and respond to excessive attitude control errors. RCS Thrusters were not used to correct excessive attitude control errors. Fault protection software was never tested on the flight spacecraft before launch. | Design fault protection to detect and respond to excessive attitude control errors. Use RCS Thrusters to control excessive attitude control errors. Always test fault protection software on the flight spacecraft before launch. | JPL | 10/10/1994 | No Attitude and Articulation Control System (AACS) or fault protection failure has been identified as a likely direct cause of the failure of the Mars Observer (MO) mission. Nevertheless, modification to the MO AACS and fault protection design could have: a) stabilized the spacecraft, and reestablished communications in the postulated "pressurant" line burst scenario and b) increased the likelihood of stabilizing the spacecraft after a power-on-reset in the electronic part latch-up scenario. By analyzing MO software algorithms and documentation, as well as performing verification test laboratory simulations of the spacecraft, it became apparent that the MO fault protection suffered from a lack of top-down system engineering design approach. Most fault protection was in the category of low-level redundancy management. It was also determined that the MO fault protection software was never tested on the flight spacecraft before launch. Furthermore, it was determined that in case of excessive attitude control errors, the spacecraft would not be stabilized by the Reaction Control System (RCS) thrusters. No RCS thruster control algorithms were present in the software code, thus there was no functional back-up to the Reaction Wheel Assemblies (RWA) for attitude control. If the RCS thrusters were used directly for control, they could have prevented a spin-up for most "pressurant" line burst scenarios. Additional Keyword(s): Software Testing Reference(s): Fault Protection Lessons Learned from Mars Observer Loss of Signal Briefing to Division 34 Staff, Douglas E. Bernard 07/20/94. Mars Observer Loss of Signal: Special Review Board Final Report: JPL Pub. 93-28. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.2.7 ("Engineering Practices: Project and System Level Functional Verification and Validation - Verification and Validation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.9.4.2 ("System Fault Protection Design: Fault Detection - Deviation from Expected Behavior") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/01/1994
343 | Chen, G - 0000000000 : NO@ADDRESS.GIVEN; Blosiu, J - | Chen, G - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Observer Inappropriate Fault Protection Response Following Contingency Mode Entry due to a Postulated Propulsion Subsystem Breach | Following the loss of the Mars Observer spacecraft, simulations showed that a postulated propellant breach would have caused angular accelerations that could have inhibited downlink and caused multi-axis gyro saturation. In this case, fault protection features of flight software would have inhibited all momentum unloading and prevented the stabilization of the spacecraft. Ensure that fault protection takes proper action regardless of spacecraft state. Fault responses should not be allowed to interrupt critical activities. | Inappropriate fault protection actions can be as hazardous as the failure the system was designed to protect against. | It is imperative that spacecraft designers consider the consequences of anomalies at all mission phases and ensure that fault protection takes proper action regardless of spacecraft state. Fault responses should not be allowed to interrupt critical activities unless they have the ability to assure completion of these activities. Final, stable fault protection modes (such as contingency mode) should autonomously assure communications. | JPL | 09/29/1994 | Verification Test Laboratory (VTL) simulations of the Mars Observer spacecraft spin-up were performed to simulate a postulated propellant subsystem breach. The results indicated that even moderately low angular accelerations caused by the postulated propulsion subsystem breach could have triggered a contingency mode entry that would have interfered with the Radio Power Amplifier (RPA) turn-on cycle. Under these circumstances, contingency mode entry would have inhibited downlink until a ground command was sent. In contingency mode, fault protection was not capable of properly configuring the telecommunication subsystem to re-establish downlink autonomously. Contingency mode was a stable state and flight software could have stayed in this mode indefinitely. This angular acceleration level would have caused multi-axis gyro saturation. If multi-axis gyro saturation was entered, flight software would have inhibited all momentum unloading thus preventing the stabilization of the spacecraft. Assuming sun on the array 33% of the time, battery depletion could be expected within 4.5 +/- 0.5 hours (sooner for even less favorable sun angle). The ground commands to re-activate RPA were not issued until about 4.5 hours after propellant pressurization since spacecraft autonomy was assumed capable to solve the issue. By the time these ground commands were issued, the batteries most likely would have been depleted. The above postulated sequence of mishaps could have been the cause of Mars Observer loss of signal. Additional Keyword(s): Sequence Interaction, Attitude Control Reference(s): Mars Observer Loss of Signal: Special Review Board Final Report: JPL Pub. 93-28 Mars Observer Fault Protection Response in High Spacecraft Spin Rates, IOM MOS 94-159, 06/17/94, G. T. Chen to D. E. Bernard. | JPL has referenced the lesson as supporting Paragraph 4.9.2.1 ("System Fault Protection Design: Fault Protection Response") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/01/1994
332 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Quality Assurance Access to Critical Areas, Management |  | If program or engineering management exercises the authority to deny QA access to critical areas, QA oversite will be severely compromized. | The quality assurance oversight function should be a separate function from program and engineering management. | MSFC | 08/16/1993 | The Hubble Space Telescope did not perform to the requirements of the contract. A spherical aberration was attributed to the spacing between the field lens and the lower mirror of the reflective null corrector. Note that the reflective null corrector is not a part of the HST but is special test equipment used to verify the curvature of the primary mirror, and to aid in the shaping of the telescope mirrors. It was concluded that the problems would likely have been discovered by quality assurance and design oversight if these functions had been conducted in acccordance with the product assurance plan. It was decided to depart from the plan and exclude quality oversight (with the consent of QA) in some areas. There were other problems, which were not as drastic as the spherical aberration which probably would have been discovered also. These problems led to considerable embarrassment to NASA, expenditure of additional funds to determine the cause and plan for on-orbit repair, and a reduced scientific return. | Collective wisdom **** Memorandum and Report from George Rodney, Associate Administrator, Office of Safety and Mission Quality, NASA. Report entitled "SRM & QA OBSERVATIONS AND LESSONS LEARNED". | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/31/1994
325 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Equipment Rack, Structural Support During Ground Operations |  | A self supporting rack (even with structural panels removed for access) would be more cost effective in personnel, equipment, and time as opposed to use of a rack support kit during staging operations | Consider designing self supporting racks in 1-G environment. (note that there are other factors to be considered such as weight and volume). | MSFC | 06/08/1993 | Spacelab utilizes racks which must be supported by a special rack ground support kit if the panels are removed for access. This required more manpower and time than would a self supporting rack. | Self-evident | N/A |  |  | Public | Not Specified |  | 08/31/1994
327 | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Propellant, Fire |  | If solid propellant is exposed to conditions for which it was not designed, the propellant characteristics will change in an unknown manner, and may create more hazardous conditions than it normally would. | When performing operations (handling, machining, transporting, disposing) on solid propellant which has been exposed to conditions for which it was not designed, assess the condition for hazard potential, especially in regard to ignition sensitivity, and modify existing normal operation procedures to account for the possible changes in propellant characteristics. | MSFC | 11/03/1993 | The propellant fire on November 27, 1982 at the Arnold Engineering Development Center, Tullahoma, Tennessee was a result of cutting propellants on the floor of a vertical test cell designated J4. The propellant being cut was the M-X stage II propellant. It was a class 1.3, 88 percent weight solids, HTPB, non-HMX propellant. The propellant had been subjected to rapid depressurization as the result of the M-X stage II motor failure November 17, 1982. In addition, the propellant fell approximately 250 feet to a concrete floor. The propellant was submerged under 50 feet of water for three days. After the water was pumped off, broken pieces of propellant that could be easily handled and the sludge were removed. The remaining large pieces were being cut to manageable sizes using a procedure patterned after that used for cutting minuteman propellant. At the time of the fire the propellant had been drying for six days. It was established that the propellant sludge had gotten dry and that the most likely cause of ignition was either impact or friction. | Engineering consensus | N/A |  |  | Public | Not Specified |  | 08/31/1994
316 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Connector Savers, Bent Pins, Open or Short Circuit |  | Frequent mating/demating of electrical connectors often result in bent pins. | Use connector savers or intermediate connectors/extension cables whenever frequent mating/demating of connectors is required. | MSFC | 08/03/1993 | In ECLSS Flight Experiment (EFE) testing, damage to the pins in electrical connectors occurred as a result of excessive mating/demating. Schedule delays resulted. | Connector savers have demonstrated their effectiveness by multiple applications on MSFC programs. | N/A |  |  | Public | Not Specified |  | 08/24/1994
333 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Evaluation of in-flight anomalies in real or near-real time via rapidly received diagnostics; safing; safemode |  | If data receipt of diagnostic data is delayed because downlink channels are not available, the ability to determine recovery action is severely compromised. This reveals a lack of systems engineering and application FMEA. | Provide the capability to rapidly receive diagnostic data when in-flight anomalies occur, especially in regard to automatic shutdown or automatic entry into the safemode state. This may require the provision of backup communications, which can be transmitted on more than one telemetry configuration. Implement systems engineering which will require test and c/o verifications and FMEA's to reveal interdiscplinarly activities. | MSFC | 06/21/1993 | On the Hubble Space Telescope, the system entered into the Safemode state, and the data to determine why this occurred was not always available in time to evaluate the causes before executing recovery steps. This occurred because the back-up communications for the Safemode Recorder was not designed for the Low Gain Antenna high/low mode (32 kbps/500bps) transmit capability. | An alternate capability for downlink of diagnostic data increases the likelihood of timely receipt of the data. | N/A |  |  | Public | Not Specified |  | 08/17/1994
331 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Quality Assurance Expertise in Special Technical Areas (e.g. optics) |  | If quality assurance personnel responsible for oversight of the quality of highly technical state-of-the-art development do not have a degree of expertise in that technical area, the likelihood of discovering QA problems decreases significantly. | The NASA organization responsible for product assurance oversight should augment their staff to provide independent expertise in special highly technical areas (such as optics technology) where major program objectives are at stake. | MSFC | 08/16/1993 | The Hubble Space Telescope did not perform to the requirements of the contract. A spherical aberration was attributed to the spacing between the field lens and the lower mirror of the Reflective Null Corrector. It was concluded that the problems would likely have been discovered by Quality Assurance oversight if these functions had been conducted in accordance with the Product Assurance Plan and monitored by personnel trained in optical technology. There were other problems, which were not as drastic as the spherical aberration, which probably would have been discovered also. These problems led to considerable embarrassment to NASA, expenditure of additional funds to determine the cause and plan for on-orbit repair, and a reduced scientific return. | Collective wisdom **** Memorandum and Report from George Rodney, Associate Administrator, Office of Safety and Mission Quality, NASA. Report entitled "SRM & QA OBSERVATIONS AND LESSONS LEARNED". | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 08/17/1994
341 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Hydro-Dynamic Vibration in the "Hot Dog" Area on the Top of the Main Combustion Chamber of the SSME Caused Fractures |  | Though it is known that two types of structural elastic flow interaction is possible, 1) vortex shedding and 2) flutter-type instability, not enough effort was spent to understand these interactions at specific locations. Reference(s): NASA technical paper 3213, dated March 1994, titled "The Role of Failure/Problems in Engineering: A Commentary on Failure Experienced-Lessons Learned", by R.S. Ryan. | To fix the high-amplitude and high frequency oscillations at the flow splitting vanes, the vane's leading edges were tapered. Later a design change was to use forging instead of casting, changing material density and increasing damping. | MSFC | 08/03/1994 | Oscillations at the inlet tee in the LOX dome of the main combustion chamber were being caused by the LOX Flowing over the two vane splitter. The vibrations were causing the vanes to crack. | No high or low amplitude vibrations now measured in this area. | N/A |  |  | Public | Not Specified |  | 08/17/1994
340 | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN | Cole, Billy - 0000000000 : NO@ADDRESS.GIVEN |  | Subsynchronous Whirl Rotor-Dynamics |  | Small differences in manufacturing (within specification) produce some pumps with whirl. | The concept and development of hydro-dynamic damping seals were the innovative solutions to inhibiting whirl. | MSFC | 08/03/1994 | A characteristic of rotor machinery has been subsynchronous whirl rotor-dynamics, most recently experienced on the SSME. This motion takes the form of whirling or whipping of the flexed rotor at one of the rotor's natural frequencies below the running speed. Both the HPFTP and the HPOTP experience this problem, and a higher performance requirement on these pumps resulted in marginal whirl situations. | Subsynchronous whirl dynamic vibration now measured 50% less in the HPFTP and 90% less in the HPOTP. | N/A |  |  | Public | Not Specified |  | 08/17/1994
328 | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Propellant, Electro-Static Discharge Ignition |  | Presently available technology (as of 1988) for determining sensitivity of solid propellant to electro-static discharge is unreliable. | Until such time as a reliable method for determining sensitivity to ESD is developed and proven, solid propellants should be treated as sensitive to ESD and appropriate measures taken to avoid exposure to ESD. | MSFC | 11/10/1993 | The accident investigation into the fire and destruction of a Pershing II stage I missile motor in Germany revealed that it was accepted that the propellant (QBJ-29) was insensitive to ESD. The cause of the accident was attributed to ESD. Older ESD sensitivity tests based upon the determination of spark energy, such as the layer test, the dust test, and the human spark test, were found to be inaccurate when U.S. hazard technologists began determining the ESD sensitivity of QBJ-29. It was found that the spark gap tests did not accurately reflect the actual energy delivered to a propellant sample. U.S. technologists, in addition, did not consider how changes in humidity or temperature affected the electrical properties of the propellant samples. Therefore, U.S. investigators borrowed the test techniques, which SNPE has been developing since 1976. The SNPE employed a three-part test methodology based on the RC discharge test, volume resistivity measurements as a function of temperature, and percolation coefficient calculations. While the SNPE test is more discriminating than the older tests, it is itself unreliable. | Guarding against the possibility of ignition by ESD is evidently more effective than not doing so because an unreliable test indicated insensitivity. | N/A |  |  | Public | Not Specified |  | 08/17/1994
326 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Experiment Dedicated Equipment Racks, Standard Utility Interfaces |  | Standard utility interfaces at each rack would save time in the long term design, physical integration, payload manifesting, and documentation control. | Consider provision of standard utility interfaces (data management, electrical power, fire detection & suppression) at each rack | MSFC | 11/03/1993 | Spacelab did not have standard utility interfaces at each rack, thus each experimenter or the integration organization had to provide design and routing for each required utility (excluding power). | Self-evident | N/A |  |  | Public | Not Specified |  | 08/17/1994
330 | White, Margo - 0000000000 : NO@ADDRESS.GIVEN | White, Margo - 0000000000 : NO@ADDRESS.GIVEN |  | Debonding Due to Pressure Trapped in Voids with Subsequent Exposure to External Reduced Pressure |  | Voids in bond lines can result in debonding if a pressure differential is created between the void and the external environment. | Eliminate voids in bond lines (as between cork insulation and the substrate) where possible; if not possible, provide vent holes at the void site. | MSFC | 06/14/1993 | KSC post flight inspections of RSRM-2 (STS 27) showed a 3.5" x 3.5" piece of JPS cork missing from the right hand center field joint at 185 degrees indicating debris. An unbond also existed between the EPDM moisture seal and the extruded cork at this missing location. The missing cork was located at the kevlar band buckle, where the JPS cork interface had been cut to fit over the buckle, creating an unvented void area under the cork. | Engineering assessment indicates that provision of vent holes at known void sites would eliminate the possibility of pressure differential causing a debond. | N/A |  |  | Public | Not Specified |  | 08/17/1994
342 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Critical Hardware Functional Verification |  | All payload systems having catastrophic hazard potential for orbiter/crew as a result of operations in or near the orbiter must use hardware and procedures that have been submitted to a rigorous verification program to verify that the functionality of the system fulfills the safety and design requirements objectives. | Perform an end to end systems engineering evaluation utilizing end to end functional testing or simulated testing to verify that the functional design is compatible with the requirements at all interfaces and to assure proper system performance and prevent loss or misapplication of safety critical functions. | MSFC | 08/09/1994 | On the STS 51/TOS mission, during payload deployment, commands intended to initiate only the primary SUPER*ZIP explosive cord actually resulted in the simultaneous firing of both the primary explosive cord and back-up explosive cord. This simultaneous explosive cord firing resulted in the rupture of a SUPER*ZIP containment tube and the release of contaminants and high energy debris into the orbiter cargo bay. | With the end to end testing of the functionality of a system, there is a higher probability of assurance that this type anomaly will be detected and resolved prior to flight. | N/A |  |  | Public | Not Specified |  | 08/17/1994
317 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Sneak Circuit Analysis |  | Sneak circuit analysis exposes problems that may escape detection during system testing. | Perform sneak circuit analysis on critical systems to prevent the undesirable events which may result from sneak circuits | MSFC | 08/03/1993 | Sneak circuit analysis was performed on Skylab to assure a high probability of freedom from undesired current paths. Forty-four sneak circuits were found on Skylab, along with a number of components that were not necessary for circuit operation and errors in the documentation. | Sneak circuit analysis was effective on Skylab; 44 sneak circuits were discovered. | N/A |  |  | Public | Not Specified |  | 08/17/1994
313 | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN | Baggs, Ellis - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Cable, Splicing |  | Splicing of electrical cables reduces the length and may increase the probability of cable malfunction. | In designs where cutting of electrical cables and subsequent reconnect by splicing may become necessary, provide sufficient slack in the cable to allow splicing. | MSFC | 08/03/1993 | The shuttle IUS was not designed to be maintained. Consequently, no electrical connectors were used. During system testing, some components failed. In the process of replacing the failed components, electrical reconnection was made by splicing. Cables that were respliced were shorter in length and less reliable. | It can be seen by review of design that provision of slack would decrease the likelihood of placing additional strain on a spliced wire, and consequently decrease the probability of cable failure. | N/A |  |  | Public | Not Specified |  | 08/17/1994
318 | Little, Robert - 0000000000 : NO@ADDRESS.GIVEN | Little, Robert - 0000000000 : NO@ADDRESS.GIVEN |  | Mission Assignment of Experiments Which are in a Very Early Stage of Development (Concept Stage or Preliminary Requirements Stage) |  | Flight assignment of experiments without appropriate development maturity often results in severe impacts to the experiment and the integrated payload. | Assignment of an experiment to a mission which is about to enter the payload analytical integration phase should be avoided if the experiment has not reached as a minimum, the following milestones: 1) Experiment has completed the preliminary requirements review, including general requirements for integration, and is approaching the preliminary design review. 2) Funding for the completion of experiment development and manufacture has been committed. 3) The experiment schedule for preliminary design review, critical design review, and software review realistically supports the integrated payload reviews. That is, the experiment reviews should lead the ipl reviews by at least six months. | MSFC | 05/24/1993 | From the inception of SL-3 until the flight, the experiment complement changed three or four times. These changes occurred during Payload integration and each time required the integration process to start over. This resulted in considerable manpower/money waste. | Collective wisdom. | N/A |  |  | Public | Not Specified |  | 08/17/1994
315 | White, Margo - 0000000000 : NO@ADDRESS.GIVEN | White, Margo - 0000000000 : NO@ADDRESS.GIVEN |  | Pressure Systems, Galvanic Corrosion, Rupture, Explosion |  | Pressure systems buried in the earth are subject to corrosion due to galvanic action or inadequate protection from galvanic or stray current; in time the strength of the system and the pressure retaining capability will be reduced to the degree that rupture or explosion may occur. | Consider installing pressure systems above ground; if not feasible, then assure the integrity of the pressure system coating at the time of installation and locate system such that it is not in proximity to sources of stray electrical current. Perform periodic proof pressure tests on pressure systems. | MSFC | 10/20/1993 | An explosion occurred at the test stand complex 500 at MSFC. The explosion was a result of a massive GH2 leak, which occurred in an underground 3.5 inch OD x 0.6 inch thickness wall schedule XX ASTM A106 grade B carbon steel line. This failure was the result of galvanic corrosion over a prolonged period of time and the application of high pressure gas to a resultant thin pipe membrane. | Proof pressure testing has been utilized for many years to recertify pressure systems, both ground and flight, and has proven to be effective. It is self-evident that avoiding stray electrical current and assuring adequate system coating would reduce the probability of catastrophic events. | N/A |  |  | Public | Not Specified |  | 08/17/1994
335 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | LARC Developed Digital Dynamic Stability Instrumentation with Less Drift and Scatter |  | With the LARC developed dynamic stability instrumentation system, data with less observed drift and scatter can be produced than that produced with the electro-mechanical analog instrumentation system it replaces. | The system is in operation at the NASA LARC unitary plan wind tunnel. | LaRC | 07/13/1994 | NASA Langley personnel successfully completed for end users a series of shakedown tests for a new dynamic stability instrumentation system. The system replaces a 25-year-old electromechanical analog instrumentation system that is obsolete. The new system is the only one of its kind in the U.S. and required 5 man years of effort for its development. It uses state of the art digital signal processors to acquire balance force and moment data; to compute, display, and plot static and dynamic aerodynamic damping coefficients; and to compute and display spectral information. All of this information is now provided in real-time during wind-on tunnel conditions. A National Aerospace Plane configuration test techniques demonstrator was tested at the unitary plan wind tunnel repeating identical tunnel conditions from a test conducted in 1990 using the old system. Data was taken at two different mach numbers and over several different angles of attack. The new system reproduced the previous data with less observed drift and scatter. NASA Langley is the only research enter in the U.S. currently conducting dynamic stability research. Personnel involved in developing this system are: Dr. Ping Tcheng, Dr. John Tripp, Douglas Wong, Tommy Jordan, Taumi Daniels, and David Hare. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 08/11/1994
336 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Ram Air Heat Exchanger Provides Increased Cooling Capacity |  | A uniquely designed ram air heat exchanger using 28 circular finned tubes, attached externally to an aircraft, provided increased cooling capacity over the conventional staggered tube array. | Wind tunnel tests performed on the heat exchanger predict significantly improved performance over the conventional design and show adequate thermal control margins. | LaRC | 07/13/1994 | A uniquely designed external ram air exchanger has been analyzed and performance tested at the NASA Langley Research Center. The heat exchanger is attached externally to an aircraft and is used to cool a laser system within the fuselage. In the limited space available, with a conventional staggered tube array, estimates showed insufficient cooling capacity. Thus, a non-conventional design was developed with larger tube and fin area exposed to the ram air to increase the heat transfer performance. The basic design consists of 28 circular finned aluminum tubes arranged in two parallel banks. Wind tunnel tests were performed to simulate air and liquid flight conditions for both the non-conventional parallel bank arrangement as well as the conventional staggered tube arrangement. Test results are used in a computer model of the heat exchanger to predict the operating performance for the entire flight profile. These analyses predict significantly improved performance over the conventional design and show adequate thermal control margins. Aircraft-borne experiments requiring large electrical power loads create a significant challenge to provide efficient thermal control for a variety of flight environments. Heat dissipation by convection within the aircraft is often limited, so the thermal load must be dumped overboard using an external heat exchanger. Due to aerodynamic restrictions, the allowable heat exchanger area outside the aircraft is usually extremely small. Thus, a heat exchanger with a small frontal area must be designed to meet the stringent thermal requirements of the experiment. For a thorough discussion of this heat exchanger see paper #902019, SAE technical paper series, "Thermal Control of a LIDAR Laser System Using a Non-Conventional Ram Air Heat Exchanger", by Brian D. Killough, William Alexander, Jr., and Doyle P. Swofford, all of the NASA Langley Research Center, Hampton, Virginia 23665 |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 08/11/1994
339 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | Measurement of Turbulence Limited by Errors in Air Velocity Measurements |  | The accuracy of airborne platform measurements of turbulence in the daytime convective planetary layer is limited in many cases by errors in air velocity measurements. | In January, 1993, Coherent Technologies, Inc., was given a $50,000.00 SBIR Grant to design, build and test a remote, air-motion sensing system. | LaRC | 07/14/1994 | The ability to measure from an airborne platform turbulence in the daytime convective planetary boundary layer has existed for several years. The accuracy of these measurements is, in many cases, limited by the errors in the air velocity measurements. current measurement techniques are typically limited by: Measurements of ambient air flow made in relatively close proximity to the aircraft and therefore influenced by the flow around the aircraft. A total "system calibration" that is not based on physical constants. An inability to make reliable measurements in clouds and in precipitation. Mechanical resonances of the aircraft which may have a detrimental influence on the data quality. |  | N/A |  |  | Public | Not Specified |  | 08/11/1994
338 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | The Deterioration of Display Hardware Structural Components |  | Rehabilitation of the Little Joe/Mercury capsule display for the Hampton Aerospace Park revealed an insidious problem with possible serious consequences for personal and public safety -- the deterioration of display hardware structural components. | All four structural members have been replaced or repaired as required with stainless steel being substituted wherever possible. All corrodable metal surfaces have been primed and painted. | LaRC | 07/14/1994 | Rehabilitation of the Little Joe/Mercury capsule display for the Hampton Aerospace Park revealed an insidious problem with possible serious consequences for personal and public safety -- the deterioration of display hardware structural components. Most aerospace public displays consist of surplus aerospace flight hardware that was never designed to withstand the adverse effects of years of outdoor display. For example, the Little Joe/Mercury display from the Hampton Aerospace Park contained four structural components that had deteriorated to an unsafe and dangerous condition: Tower Marman Band. Tower Base Ring. Base Marman Band. Little Joe Adapter Section. All four structural members have been replaced or repaired as required with stainless steel being substituted wherever possible. All corrodable metal surfaces have been primed and painted. The deteriorated condition of the Little Joe/Mercury hardware raises concerns for displays at other aerospace-parks. Display custodians should be made aware of this possible problem, urged to make periodic inspections of their displays and support hardware and make repairs where needed. |  | N/A |  |  | Public | Not Specified |  | 08/11/1994
337 | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN | Lewis, Bernard - 0000000000 : NO@ADDRESS.GIVEN |  | A Colored Water Technique for Analyzing Complex Flow Fields |  | A colored water technique which complements the oil flow and tuft techniques and gives researchers another test method to analyze complex flow fields, has been developed by NASA LARC researchers. | Wind tunnel tests have been conducted using this technique to visualize surface flows at supersonic speeds in a rectangular box cavity that was mounted in a flat plate. Both video and still photographs of the resultant flow fields were obtained. | LaRC | 07/13/1994 | For many years, LARC has been studying cavity flow fields at supersonic speeds. This research has included various flow visualization wind tunnel tests to document both the cavity surface and off-body flow fields. During one of these tests, water was injected through pressure measurement orifices located on the model surface in an attempt to visualize vortices that typically form above certain cavity configurations. Because of the low static pressure in the tunnel, it was anticipated that the water would vaporize as it exited the orifice and the resulting vapor would be entrained into the vortices and render them visible. This technique did not work, and the water instead flowed along the model surface. Although the water was difficult to discern against the model surface, it was obvious that the water was being entrained by the model surface flows and had a fast response to the cavity flow unsteadiness. This impetus led to the development of a technique that uses colored water as a medium to visualize surface flows over wind tunnel models. The colored water surface flow visualization technique basically involves injecting colored water through the pressure measurement orifice tubes installed in a wind tunnel model. The colored water exits the orifices and flows along the model surfaces to form streaklines. The resulting flow patterns are then photographed for later analysis. This method has several advantages over the conventional oil flow and tuft techniques that can make it a useful procedure for routine testing. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 08/11/1994
334 | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | Liquid Propulsion Systems; POGO, Instrumentation |  | Small changes create large effects when a system is operating near a stability boundary and has a large energy source to feed the instability. | Design high energy, large load potential problems, such as "POGO" out of the system. Stability limits must be understood to a certain g-level which is tighter than the design uncertainties related to the instability phenomenon. To understand the phenomena, analyses must be performed considering nonlinearities and adequate instrumentation must be available on ground tests and on flight tests. | MSFC | 07/28/1993 | The S-II stage of saturn had a very intriguing and baffling series of POGO or forced oscillation response culminating in the near disastrous AS-508 flight. The oscillation occurred early in the S-II stage burn and reached large acceleration amplitudes (thrust frame cross beam) of 33 g'S at 16 HZ, and the resulting large pressure oscillations shut the engine down at 160 seconds of S-II burn. POGO was not apparent for the S-II stage (probably because of poor instrumentation) until AS-503. AS-503 had a self-limiting, local POGO-type oscillation near the 480 second flight time. Concern was raised in the POGO working group over this oscillation and potential vehicle problems. After much discussion and analysis, it was generally agreed that the next vehicle could be made POGO safe by increasing the ullage pressure, which would raise the lox line frequency and decrease the gain and thus the instability. AS-504 did not follow predictions; in fact, it did the opposite. Again, the oscillation was self-limiting. A more detailed look at the pump and engine test data revealed that the increase in ullage pressure would bring into play nonlinearities, which would increase the gain and thus the instability. It was becoming clear that many things were missing; more data must be acquired which required improved flight vehicle instrumentation. The ability to model the bulkhead hydroelastic characteristics was very poor and limited to the first mode. Elimination of this shortcoming required updated analysis and a comprehensive hydrostatic test program for data and verification. Additional line and engine tests were required to better define these characteristics, particularly since no analytical approach was available. In order to maintain launch schedules, it was decided to shut down the S-II center engine 60 seconds early and avoid the POGO problem. This appeared to be the answer, since no real performance loss was incurred. AS-505 and AS-506 appeared to confirm this since no POGO was observed; however, the improved instrumentation was not on these flights but was planned for AS-507. The improved instrumentation detected several "football" bursts of oscillation during the flight of AS-507 indicating the POGO loop was marginally stable whereas nonlinear analysis was showing stable limit cycles. Further analysis on AS-508 indicated marginal to unstable conditions. The as-508 flight experienced severe POGO: oscillations started at 16 Hz producing an amplitude of 32 g'S or greater. The poor prediction was due to inadequate nonlinear characterization of the system. After the fact, modal analyses were conducted using three flights and test-determined nonlinearities, nonlinear pump gain, nonlinear damping, and pump inlet compliance. Using these nonlinearities, a reasonable analytical duplication of S-II POGO on all flights could be obtained without adjustments other than known vehicle flight-to-flight differences. The ability to accurately predict POGO enabled design fixes to be implemented. | POGO effects were eliminated or reduced to acceptable levels on future flights. | N/A |  |  | Public | Not Specified |  | 07/27/1994
324 | White, Margo - 0000000000 : NO@ADDRESS.GIVEN | White, Margo - 0000000000 : NO@ADDRESS.GIVEN |  | Hazardous Material, Toxic; Explosive; Caustic; Training for Personnel |  | Failure to provide proper training to all personnel regarding the dangers posed by hazardous chemicals can cause significant safety problems. | Provide training to all personnel who will be working with or exposed to hazardous materials. The training should be provided by safety professionals, and the procedures utilized should be reviewed by safety, and operations should be monitored by safety. | MSFC | 07/28/1994 | An explosion at the phillips 66 facility at pasadena, CA prompted this lesson. There have been accidents at MSFC which could probably have been avoided if personnel had been trained properly. | Self-evident that personnel training would decrease the probability of an accident occurrence in the handling of hazardous material. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 07/27/1994
62 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | LRU Platform Hoist and Tube Assembly; Platform Hoist Tube Assembly "UP" Limit Switch Bypass |  | Excessive wear of the load bearing surfaces on the keepers of tube "C" was the result of impact during approximately 30 retraction cycles. To stow the tubes, normal operations required bypassing the "up" limit switch and using observers to determine when to stop the upward travel. | Design tube hoist assemblies that do not incorporate fillet welds on the inside of the tubes and opposite the tubes stops. This will reduce/eliminate wearing down of the tube stops. Add "up" limit switches exclusively dedicated to tube stowage operations. | KSC | 03/05/1992 | Three sections of a telescoping tube assembly at Pad B rotating service structure (RSS) fell while being extended to incorporate a planned modification (MOD). The MOD intended to eliminate binding that had been experienced during testing and verification. The falling tubes impacted and severely damaged the RSS and orbital maneuvering system pod covers. The contributing factor to this failure is that the fillet welds on tube "D" provided an outward ramp effect that caused excessive wear on the keepers and the eventual bowing of tube "C" which allowed less surface contact area between the welded stops and the keepers. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
243 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Carbon Dioxide Fire Control Systems |  | Standard maintenance on carbon dioxide fire control systems in confined areas can become hazardous to personnel. | Remove all personnel from confined areas when checks on carbon dioxide fire control safety systems are activated. | GRC | 01/20/1994 |  | Confined space entry procedure standard has been instituted. | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/15/1994
241 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | High Pressure Steel Pipes |  | Unprotected steel pipes in below ground trenches, when under pressure, are subject to catastrophic failure due to corrosion. | Install seamless wrought iron piping with a bituminous coating protected by magnesium anodes for corrosion resistance. | GRC | 07/15/1993 | A 125 pound per square inch pressure air line in a ground trench, used to supply test facilities, failed by splitting along the longitudinal weld. The 10 inch diameter steel pipe ruptured for a distance of about 15 feet. As a result of this failure, four manhole covers were blown into the air. The air line that failed was in a covered ground trench and had been in place for about 15 years. During this time, moisture was present from surface water leakage and considerable corrosion had taken place on the pipe outside diameter. Inspection of the failed pipe revealed that the original thickness of 1/4 inch was reduced to almost zero in some places as a result of the corrosion. The failure was due to the corroded pipe no longer being able to withstand the internal working pressure. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
242 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Hydrogen Vent Stacks |  | Weather caps installed on the discharge end of hydrogen vent stacks can generate static electric charges to ignite the hydrogen gas and start unwanted stack fires. | Replace weather caps with thrust balanced vent outlets 180 degrees opposed. Toroidal rings should be installed at vent outlets to minimize sharp edges. A helium purge in the stack base will provide a means to extinguish stack fires if propagated. | GRC | 07/16/1993 |  |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
252 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Roof Penetration Coverings |  | Roof coverings which appear to be made of sheet metal may contain combustible materials. These coverings could catch fire when exposed to high temperature exhaust stacks. | Inspect all roof covers penetrated by hot exhaust systems for existing combustible materials. Replace covers if such materials are found. | GRC | 08/12/1993 | A roof penetration cover exposed to high temperature from an exhaust stack caught fire. The cover appeared to be composed of only sheet metal but, upon further inspection, was actually composed of plywood placed between two thin pieces of sheet metal. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
251 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Liquid Oxygen Spills |  | When checking sequence timers that control liquid oxygen valving, it is possible to cause oxygen spills if pressure exists in supply tank. | Design circuitry on the electrical check system to include control of fire valves so that electrical checks can be made without valve operation. | GRC | 08/11/1993 | Prior to running a test in a facility using liquid oxygen, a check was made on the sequence timer which controls the valving of the system. When the console selector switch was set at "CHECK" and the check started, the liquid oxygen fire valve opened and spilled liquid oxygen. Pressure in the supply tank is required during standby to keep air and water vapor out of the system. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
255 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Grinding Wheel Detachment |  | Grinders that have Flexovit grinding wheels pose a hazard when turned off. The wheels can detach from the flange mount on the grinder and become dangerous missiles. | Remove all Flexovit grinding wheels from service that have the 1/16 inch flat surface nuts, which are torqued to the flange on the grinder. | GRC | 08/26/1993 | The Flexovit grinding wheel, National stock number 3460-00-027-0942, abrasive, resin bound, 7" by 1/4", shape 1397, grit 24, was released from a portable air powered grinder, commonly referred to as a "Bayflex Grinder", just after the grinder was turned off. The grinding wheel was propelled across the room by its inertial force created during the grinding operation. The problem is associated with the size of the flat surface on the nut, which is torqued to the flange on the grinder. The grinding wheels were manufactured with two different flat surface sizes for the nut, 1/16" and 3/8". The 1/16" flat surface may allow the grinding wheel to unthread itself from the grinder when the air is cut off. The grinding wheel with the 3/8" flat surface is the correct one to use. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
254 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Liquified Gas Dewars |  | Glass lined dewars which are used to transport liquified gases can explode unexpectedly and endanger personnel in the area. | Wear protective equipment such as faceshield/goggles, cryogenic gloves, long sleeves and an apron when handling cryogenic fluids. | GRC | 08/20/1993 | A five liter, glass lined, liquified gas dewar exploded after workers completed a transfer of liquid nitrogen from it. The explosion propelled fragmented glass from both ends of the dewar. Fortunately, no one was in the path of the razor sharp fragments and no injury resulted. The dewar had been in use for only two years and no physical deterioration had been noted. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
253 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Surge Protectors |  | Surge protectors can fail if used as the primary means of controlling the on-off operation of computer equipment. | Assure that computer equipment is turned off before activating the surge protector switch in either the on or off mode. | GRC | 08/19/1993 | Two data shield surge protectors, model numbers 85 and s85, failed during use, causing smoke to be emitted and rendering the units unserviceable. The surge protectors had only been in use for 2-3 months. Both units were used as switches to turn the computers on and off. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
294 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Studs and Tapped Holes |  | When studs sized to fit into tapped holes are difficult to install, the use of smaller sized studs in test facility assemblies can cause test rig failure. | Inspect tapped holes for contamination such as rust or paint prior to making repetitive assemblies and chase threads with taps if necessary to make studs (which are designed for the job) fit. | GRC | 07/23/1993 | A rubber seal friction force was being measured in an altitude tank between a plate and an inlet flow duct when the mishap occurred. The failure occurred at an inlet test condition of 10.2 psia with a test cell pressure of 3.6 psia. As the inlet pressure was being increased, the mounting studs holding the seal together failed. The investigating committee determined that improperly sized studs were used to hold the rig together. The structure had tapped 1/2-13 holes to mate with the plate mount pads. 7/16-14 studs were used for assembly because of the difficulty of getting the 1/2-13 studs into the tapped holes. Further investigation revealed that the tapped holes contained rust and paint that did not allow the larger studs, designed for the assembly, to be installed. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
299 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Dry Well Transducer Installations are Susceptial to Inadvertent Removal |  | Adequate physical safeguards do not exist to prevent the inadvertent removal of dry well transducer installations from hazardous systems. See DWG 79K16420 Dry Well Assembly. | To prevent the inadvertent removal of dry wells from hazardous systems, dry wells should be secured using an appropriate restraining device, capable of holding the dry well in place while transducers are removed and replaced. | KSC | 08/18/1993 | A Hypergol technician erred in the removal of a temperature transducer from a 3-inch Hypergol line at the pad "A" fuel farm, resulting in a major fuel spill. The installation design of the dry well and temperature transducer provide a means to remove the transducer from the system for replacement or calibration without having to open the fluid volume. The dry well installation design is inadequate to preclude an untrained or careless technician from inadvertently removing the dry well from the Hypergol propellant line by mistake. Additional Comments: OMI V2196 Titled: "Hyper Fuel System Validation Storage Area-Local Control/LPS" has been updated to include the following warning: "Removing transducers from dry wells may be hazardous. A restaining retainer is designed to prevent removal of dry well while secured in place by set screws. As transducers are being removed from dry wells, PMTG shall visually verify that dry wells are not turning. Wear face shield, apron and rubber gloves and use extreme care to avoid inadvertent loosening of any temperature XDCR dry well, which could release MMH liquid. If A78633 TEMP XDCR dry well is loosened the entire storage tank contents could be released." | The supervisor was contracted to verify the installation of dry well restraining retainers. In addition, the supervisor said the dry well restraining retainers have been very effective in preventing dry well backouts. There have been no recorded instances of backouts by dry wells with the restraining device installed. Installation and effectiveness of the dry well restaining retainers was also verified at PAD B. | N/A |  |  | Public | Not Specified |  | 06/15/1994
77 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | OMS/RCS System Control Logic |  | OMS/RCS Systems program control logic does not reset each time the program is activated, allowing inadvertent over-pressurization of the system. | Add a step to all OMS/RCS system OMI's that are monitored by control logic, to adjust logic limits prior to changing pressure. | KSC | 05/20/1992 | While pressurizing the oxidizer propellant tank, a change in ullage pressure of 8 psi occurred and caused the computer program to indicate that the interface and supply valves were closed. At this point, the engineer felt it was safe to close the dome load valve, in reality opening it. He then opened the interface valve, the pressure online with the module was 190 psig, the supply valve was then opened and the pressure spiked to approximately 400 psig, which ruptured the burst disk. The computer program indicated the incorrect status of the system because the control logic limits were not adjusted/reset prior to starting the operation. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
257 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | JP-4 Fuel Leak |  | Modifications made to plumbing systems of fuel tanks that are inadvertently left off the facility drawings can lead to unsafe engine operation. Fuel system low-point drains should not be placed in close proximity to, or above, critical operating systems. | Correct facility drawings when modifications are made and notify line management responsible for the facility. Design facilities so that fuel drain lines and valves are not in a position to dump fuel on operating electrical equipment. | GRC | 01/20/1994 | Operations personnel, in an engine test facility, reported that JP-4 fuel was found leaking in the basement of the building. Emergency staff responding to the call discovered that the fuel had originated from the engine on the main floor and had leaked onto a power panel in the basement. The spill was located on and around a 480VAC motor control center that contained breakers and contactors to power the pumps, blowers, and fans in the building. The building was evacuated due to a potential explosion hazard. The power was turned off and power to the control center terminated. Absorbent pads were placed around the fuel spill for containment and the area barricaded to prevent access. It was determined that the fuel spill originated from an open fuel return low point drain valve, recently added to the facility, that was not put on the facility drawings. Operations personnel performing a walk-through inspection of the facility did not observe the added drain and therefore were not aware of the presence and open valve position of the drain. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
258 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical Ground - U-Ground |  | U-Ground electrical devices can cause electrical hazards if not installed properly. | Install U-Ground devices with the ground in top position. But, if the device is mounted horizontally, the neutral prong should be on top. | GRC | 01/20/1994 | While mounting a tray inside an instrument rack, the bottom lip of the tray made contact with the prongs of an electrical plug located below the tray. This contact caused electrical sparks which cut a hole in the tray, burned the paint off the tray, and ruined the plug. In order to preclude this electrical hazard from recurring, it is recommended that all U-Ground devices be installed with the ground in the top position. If mounted horizontally, the neutral prong should be in the top position. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
256 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Desiccator Implosion |  | Plastic desiccators can implode under a vacuum, throwing parts and desiccant with sufficient force to create a hazard to personnel. | Wear a face shield and other protective clothing when handling plastic desiccators that are under a vacuum. | GRC | 01/20/1994 | A Nalge desiccator, National stock number 6640-00-569-7964, vacuum, plastic, 250 MM, violently imploded after being evacuated about 1/2 hour before the incident. The force of the implosion threw parts and desiccant with sufficient force such that injury could have occurred if personnel were nearby. Although cautions for the use and cleaning of this device were included in the manufacturer's instructions, as near as can be determined the desiccator had been used properly. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
260 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Stainless Steel Tubing Residue |  | Stainless steel tubing, as obtained from the supplier, can contain a residue build-up that could cause a blockage in the line. | Inspect and, if necessary, clean all stainless steel tubing before installation in a plumbing system. | GRC | 09/03/1993 | Possible residue build-up in stainless steel tubing, as obtained from the supplier, could cause a blockage in the line. All stainless steel tubing should be inspected for cleanliness prior to use and should be cleaned according to the following procedure for general R&D applications: Blow down with dry air to remove majority of particles. Pass solvent-rinsed, lint-free swab through tubing to dislodge additional particles. Flush tubing with fresh solvent for about 15 seconds. Follow with another dry air blow down. Conduct cursory, visual examination of each cleaned tube to assure that all visible particles are removed. Install tight-fitting, clean, plastic caps on each tubing end. Fasten tag on each tubing section to identify that a cleaning process has been accomplished. Note: This procedure will not provide adequate cleanliness for sensitive pneumatic/hydraulic applications, oxidizing propellant service, or flight hardware applications. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
261 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Working Under Suspended Loads |  | When processing flight payloads, designs for lifting and hoisting equipment must follow strict procedures to avoid costly delays to operations. | Design hoisting operations according to OSHA requirements that prohibit having personnel working under suspended loads. | GRC | 01/20/1994 | Occupational Safety and Health Administration (OSHA) requirements prohibit having personnel work under suspended loads. Payload processing facilities will be implementing measures to assure strict compliance with OSHA requirements. It is recommended that these requirements be incorporated into present or future operational plans/designs of lifting and hoisting equipment to avoid costly delays, redesign or modifications to operations. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
78 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Insulation Baking Process for RCS Thrusters |  | Lack of redundant high temperature cut-off switches allowed 3 RCS thrusters to be over heated during insulation baking process. | Install redundant separate high temperature cut-offs on the oven power supply with appropriate alarm systems. | KSC | 05/20/1992 | Three RCS primary thruster injector/chamber assemblies were damaged when the oven temperature control system malfunctioned and permitted the temperature to reach an estimated 1400 deg F during a cerachrome insulation baking process that should have been limited to 625 deg F. These units should have been rejected at this point, but quality assurance was not notified. As a result, the full extent of damage was not determined until the severe discoloration of titanium alloy and columbium parts was noted during the post-baking weighing process, about three weeks later. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
128 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Main Landing Gear (MLG) Tire Rupture During Postlanding Operations |  | Transfer of heat from brakes to the MLG tires after maximum braking could increase tire pressure and result in rupture/blowout. Excessive tire wear due to maximum braking or FOD may reduce strength of tire structure and cause rise in tire pressure, resulting in rupture. Hydraulic fluid leakage in the hot wheel well area may ignite and cause orbiter damage and/or personnel injury. | To minimize possibility of improper braking, provide crew training with braking techniques for various landing profiles. Prior to orbiter leaving the OPF, perform anti-skid brake inspections and check electrical power/pedal calibration integrity and hydraulic control valves. A fire fighting capability is mandatory at all planned landing sites should a hydraulic fire occur after wheel stop. | KSC | 08/26/1992 | MLG tire heat generated from max. Braking due to a crosswind landing, heavy orbiter, or long landing, could cause a transfer of heat to continue to the MLG tires after wheel stop, resulting in a delayed tire blowout. An explosive tire rupture caused by increasing tire pressure, cuts, excessive loading, or skidding could injure personnel and/or damage the orbiter/chassis hydraulic system/ground support equipment. Three thermal relief plugs in each MLG tire prevent tire overpressurization, the orbiter anti-skid/brake control system prevents locked brakes, and the orbiter hydraulic system displacement limiter limits hydraulic fluid loss. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/15/1994
247 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Hydrogen Detectors |  | Hydrogen detectors that use catalyst generated flame fronts stopped by flame arrestors (to signal the presence of combustible mixtures) can become the source of hydrogen fires. | Check detectors at all combustible hydrogen-to-air volume ratios to assure that the flame fronts are stopped by the screen. | GRC | 08/09/1993 | During the filling of a liquid hydrogen test apparatus mounted in an AJ-2 airplane low-g test facility, an explosion occurred followed by a fire. The cause of the mishap was determined to be a leak due to a loose "AN" fitting on a 1/2 inch vent line that was teed to the fill line of the research package. The ignition source was found to be hydrogen detectors mounted in the airplane near the test rig for safety considerations. Proof of the ignition source was determined by bench testing the detectors. The test consisted of flowing mixtures of hydrogen and air through them to determine if the flame fronts generated by the catalyst would be stopped by the flame arrestors. At a hydrogen volume ratio of 5 percent, the detectors signaled a warning and the flame fronts were stopped by the screens. When the volume ratio was increased to 15 percent, the arrestors failed to confine the flame. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
246 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Lifting Equipment |  | When cables are threaded through eye bolts to lift heavy loads, the eye bolts may have sufficient strength in tension but can fail in shear. | Require rigging crews to follow ANSI standards B30.2 and B30.9 when lifting heavy loads and to use proper level lifting techniques to prevent undue stress on parts such as eye bolts. | GRC | 09/30/1993 | In the process of pulling a 30 foot long water pump weighing 3 tons out of a pit, two 3/4 inch eye bolts were screwed into the pump motor base and a cable sling attached to the eye bolts. The pump was pulled out of the pit setting one end on the ground. When starting to lay it down to a horizontal position, one of the eye bolts sheared off, dropping the pump to the ground. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
244 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Water System Contamination |  | Incompatibilities between SKYLAB system design and cleanliness levels caused particulate contamination, resulting in repeated water pump failures. | Establish individual system cleaning techniques to assure system status after final servicing and install filters with change-out capability. | KSC | 01/14/1993 | Prior to being operated at KSC, SKYLAB hydraulic systems were tested for contamination. If the systems were found to be clean, they were sealed and not retested. After being operated at KSC, a water system pump failed. A new pump was installed and a fluid sample was taken from the failed pump. Analysis of the fluid sample showed gross contamination. It can also be noted that in following missions, water system pumps failed repeatedly, all due to contamination. Fluid system cleanliness levels were not maintained throughout assembly operations. Plumbing, component, or installation cleaning procedures resulted in cleaning to dissimilar specifications, which were not compatible with various hardware. Component tolerances should be such as to allow particulate contamination of specification levels to pass without failing the component. Filtration, with a filter change-out capability after demonstrated life, should be placed in the system to collect particles. Additional Sources: MSFC Documentation of Significant SKYLAB Experiences, Dated 15 Nov 1973 |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
249 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | SKYLAB Pressure Vessel Rupture |  | Ruptured pressure vessels caused by overpressurization may produce projectiles and impact crew and/or rupture other pressure vessels. | Provide fluid pressure displays, overpressure alarm systems and automatic relief valves (or other protection devices) for pressure systems. | KSC | 01/27/1993 | The principal cause of pressure vessel rupture is overpressurization. This overstressing of the tank could result in failures after experiencing normal temperature pressure cycles. Tanks that contain heater elements are most likely to experience high pressures if the electrical circuitry fails to cut off the heater elements. High-pressure tanks scratched or impacted after proof testing, i.e., during installation, checkout, or crew operation, cause dangerous stress risers leading to potential tank failures. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/15/1994
311 | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN |  | STS-56 High Rate Data Channel Failure Impact to ATMOS Experiment | The high rate data channel for ATMOS failed. No complete end-to-end test had been performed either prior to or after the flight. The recommendations point out the need for end-to-end testing (including tests to identify the failure mode before the payload is disassembled), pre-planned work arounds, and channels of communication from the PI to the mission manager. | End-to-end tests are essential to identify complex system problems. When an in-flight failure occurs on a payload scheduled for reflight, it is essential that a satisfactory determination of the cause be accomplished prior to the disassembly of the payload. Functional redundancy is highly desirable for any single point failure subsystem. Investigations of the type described here require direction and coordination by a single authoritative person. | End-to-end tests must be performed. Ensure that end-to-end tests to determine failure modes are performed prior to the disassembly of the payload. If functional redundancies for single point failure modes cannot be supplied, work arounds should be established before the start of the mission. In an STS payload involving experiments and instruments from different centers, the individual responsible for a given experiment must have the opportunity to apprise the mission manager of the importance of his/her experiment to overall mission success. | JPL | 02/03/1994 | In April 1993, the Atmospheric Trace Molecule Spectroscopy (ATMOS) instrument was flown on board the space shuttle Discovery (STS-56) as part of the second Atmospheric Laboratory for Applications and Science (ATLAS-2) mission. While the instrument performed very well during the mission, a very significant event occurred in the course of the flight, which could have resulted in little or no science data being returned from ATMOS. This problem also affected other experiments, but to a lesser degree. The problem involved the shuttle's High Rate Data Telemetry System and the SPACELAB's High Data Rate Recorder (HDRR). Following payload subsystem activation, the ATMOS instrument was successfully powered up and performed the first operation -- an engineering exercise to verify the proper operation of subsystems. The primary ATMOS science data stream is normally transmitted live, or in a delayed record/dump mode on a high rate data channel. After only a few seconds of transmission the latter stream became extremely noisy and rendered the data scientifically unusable. Subsequently, NASA payload controllers attempted a work-around using the SPACELAB's HDRR and the shuttle's Lower Data Rate Telemetry Channel. This method improved the data quality, but it still contained numerous parity errors. Fortunately, the ATLAS-2 mission was the first flight of a new, dedicated ATMOS recorder subsystem. This mission was originally intended to be an engineering evaluation and test flight for the recorder. The use of this recorder permitted the independent recording of more data than was needed to meet the minimum success criteria of the ATLAS-2 mission. No complete end-to-end test was performed, either prior to or after the flight. Following the mission, KSC performed several tests on the shuttle and SPACELAB telemetry system to determine the cause of the problem. No obvious failure mechanisms were found in either the orbiter's system or in the spacelab subsystem. It has only recently been learned, after several subsystem tests, that there were two or three problem areas in the STS-56 data system, which would explain the loss of data. From the point of view of the ATMOS experiment, the post-flight testing plans, organization, and execution were ineffectively coordinated primarily because of a lack of a single authority figure to emphasize the importance of the testing activities to the success of the ATMOS experiment and the mission. The ATMOS experiment is described in some detail in SSEF # 1-104. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.1.2 ("Engineering Practices: Project and System Level Functional Verification and Validation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 06/15/1994
159 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Line Replaceable Unit (LRU) Hoisting Operations |  | Use of the east swing platform hoist trolley for lifting LRU's provides inadequate clearance/may result in flight hardware damage/personnel injury. | Provide an air hoist trolley rail on the west swing platform to allow for a direct lift from OPF floor in an area where diving boards are extended. | KSC | 10/13/1992 | The orbiter processing facility (OPF) swing platforms are used to access the space shuttle main engines (SSME's), orbital maneuvering subsystem pods, and engine heat shields. Engine heat shields are removed every flow to perform turbopump torque checks. Heat shields with handling ground support equipment weigh approximately 300 pounds and are very awkward to handle, shaped in a 10-foot semi-circle. High pressure fuel and oxidizer turbopump (HPFTP and HPOTP) LRU operations require the east diving board be extended to provide access to SSME GIMBALLING and to permit pump removal. A design oversight limits LRU lifting operations to one location, level 19 of the OPF. An extended diving board interferes with the direct decent of flight hardware to the floor. To clear the diving boards during pump lowering/raising, the pumps are manually pulled away from the diving board with tag lines. This procedure side loads the hoist, a violation of standard NSS/GO-1740.9. If the tag line operator misjudges the clearance past the diving boards, the pumps will be damaged. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
154 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Pneumatic and Fluid Quick Disconnects. |  | The pneumatic and fliud quick disconnects are the same size and located close enough to easily allow misconnection within APU carrier plates. | Replace all similar and same size connectors with keyed or different sized connectors. | KSC | 10/08/1992 | The quick disconnect/filter assemblies are designed to provide a disconnect interface and remove all solid particles which exceed 25 microns. The fluids being filtered include hydrazine (N2H4), GN2, lube oil, and water. The ground half QD assemblies interface the GSE at the ground umbilical carriers S70-0757 and S70-0758 which provide structural support and fluid containment. If the QD is mated incorrectly, it may cause the QD to leak N2H4 during fill/drain operations. |  | N/A |  |  | Public | Not Specified |  | 06/15/1994
230 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Operational Maintenance and Inspection Program (OMP) |  | The OMP inadequately provides Level II with closed loop oversight and lacks a comprehensive system to track and audit compliance with requirements. | Implement an inspection and maintenance program that will ensure flawless performance of critical space shuttle hardware. | KSC | 11/25/1992 | Requirements for the operational era was introduced into the system in early 1985. The foundation for the system, operations and maintenance requirements and specifications document, provides a sound base on which to build a mature system as future requirements are defined. Some problems have been encountered while progressing toward a mature system. Implementation of newly defined requirements is not always accomplished according to an agreed upon plan that can be supported by all involved functional areas. Level II also lacks an active closed loop audit system to check the quality of compliance with established requirements. Additionally, there is no baseline postflight turnaround schedule to use as a basis for tracking long-term trends in waivers, deferrals, additions, or deletions to the KSC flow. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
229 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Schedules |  | Requirements in support of the 1986 flight schedule provided inadequate resources to develop a capability to support an increased flight rate. | Constrain the flight rate within the capacity of the NSTS program while maintaining reserve resources to develop a fully operational capability. | KSC | 11/25/1992 | The original STS operations baseline plan defined required capabilities for the STS system before it was designed. The operational system would fly 6 flights the first year, 15 the second, 24 the third, and by the sixth year a total of 60 flights per year. To meet this flight rate, turnaround was to be completed in 14 days. The vision of the operational space shuttle was clearly much larger than the resource base eventually established to create the capability. The 1985 mission operations were successful in spite of significant remanifesting and perturbations. However, all trends prior to the STS 51-L mishap indicated that the milestones required to support preparations for the 1986 flight schedule were not being met. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
215 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) Processing and Inspection |  | Inadequacies in the processing and inspection of o-rings for the SRM may affect sealing capabilities. A lack of standardization in the SRM o-ring material formulations and processing may result in application problems. | Review o-ring processing and inspection requirements to assure they are compatible with the criticality 1 criteria. Maintain a current/updated inventory of all critical flight hardware and check records prior to use for any manufacturing changes. | KSC | 11/18/1992 | All inventory SRM case o-rings were reinspected during the STS 51-L investigation. When reinspected using original inspection equipment (mechanical micrometer), very few out-of-tolerance conditions were identified. However, when reinspected with a laser micrometer with a 0.007-inch measuring beam, numerous small localized out-of-tolerance conditions were detected. All inventory o-rings were also x-rayed, indicating numerous o-ring inclusions. Although tests proved that these conditions did not affect the sealing capability, this does indicate a potential problem and a need for processing and inspection improvements. It was also learned during this investigation that the o-ring material manufacturer had changed material formulations and processing numerous times since starting to produce srm o-ring material. While all these formulations resulted in o-ring material that was in compliance with MIL-R-83248, this lack of standardization could possibly result in application problems and is unacceptable for such a critical item. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
212 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Computer Systems |  | The current ad hoc approach of treating each computer upgrade as an independent action is proving to be unsatisfactory. | Implement a study to plan a path of evolution for all future changes in avionics computer hardware and software for the life of the space shuttle. | KSC | 11/17/1992 | The space shuttle computer system faces a continuing evolution in flight requirements and increased equipment obsolescence accompanied by greater and more expensive maintenance problems. There is a large list of waiting software change requirements covering such things as the extended duration orbiter missions, crew requested changes, mission-specific changes, and general improvements. Due to the rapid evolution of computer technology, it is difficult to keep any given generation of computer equipment in use for more than a few years. After that, it becomes increasingly difficult to obtain replacement parts. There is also the opportunity to incorporate new capabilities. In the projected 30-year horizon for the space shuttle, it will be necessary to upgrade the system several times. There now are a number of arguments that favor starting a study for long-term space shuttle avionics computer evolution. They are based on the events that can be expected in 8 to 10 years. The hardware in the "new" general purpose computer will become obsolete and require replacement in about that time period. Also within that time period, the limit on available memory in the space shuttle computers will have been reached. Expansion with the "new" general purpose computer will not be possible without major software changes that would require massive reverification. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
213 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Experience Data Base |  | A lack of easy access to certification/flight experience data base made it difficult to determine data/limits for flight dynamic/trajectory variables. | Develop a data base providing current certification information of each element and a record of flight experience ranges for dynamic variables. | KSC | 11/18/1992 | Although the MSFC data bases contain the time histories of most of the pertinent flight dynamic and trajectory variables for each launch, cumulative data for the variables were not available. This made it difficult to quickly determine the actual ranges of flight experience at any given time, as well as, what a reasonable value (within the expected ranges) should be. A computer program which updates the maximum and minimum values at each time point, the flights which produced them, and the means and standard deviations from which the values accumulated from previous flights would be beneficial. The program should include the range of environments, equipment certifications, and flight exposure. The data should be readily available to designers, flight planners, and operational personnel. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
214 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Design, Performance, and Launch Commit Criteria |  | Ambient conditions were used as a reference/base for design, performance, and launch commit criteria without specification of local conditions. | Re-evaluate design, performance, launch commit, etc. criteria and provide direct measurement data to verify/confirm adherence to the criteria. | KSC | 11/18/1992 | Criteria for design, performance, launch commit, and other operations have used "ambient" conditions as a reference or base for evaluating systems which could be affected by environmental conditions. the term "ambient" is not specific and, subsequently, results in misinterpretation. Ambient conditions are a specific set of conditions and should be measured at specific locations and clarified as to the effects of time of day, wind velocities and direction, etc. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
202 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Ice Team Inspection |  | The ice team failed to report discrepancies when analyzing flight hardware temperatures using instruments without understanding of operational limits. | Thoroughly train all evaluation teams in the use of any instruments they handle and supply appropriate criteria to evaluate results. | KSC | 11/06/1992 | In the early morning hours before launch, a KSC ice team performed an inspection of the Challenger and pad. Their specific aim was to check for the amount and type of ice. They had with them an infrared gun designed to measure surface temperatures. This instrument was focused on the external tank and Solid Rocket Boosters (SRB's) during the course of the survey. The infrared gun indicated temperatures on the right SRB of from seven to nine degrees Fahrenheit, compared to 23 to 25 degrees for the left SRB. This discrepancy was not reported to launch team officials. Later, tests indicated the infrared gun requires a minimum of 40 minutes to stabilize at the temperatures experienced at KSC on the morning of the launch. The gun was focused on the right SRB prior to the time it had stabilized, indicating the readings taken were not reliable. Ice team members displayed a lack of sensitivity to potentially hazardous conditions to which they were evaluating and, nevertheless, should have reported the low readings. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
225 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) Processing Operations |  | Case segment ovality and inadequate assembly tooling/procedures may have resulted in field joint o-ring damage during mating operations. | Develop shipping/handling aids to maintain circularity of case segments and mating aids to control entry of tang into clevis during joint mating. | KSC | 11/22/1992 | Solid Rocket Motor segments are shipped from the facility in Utah to KSC horizontally on railroad cars. During the assembly process at KSC, it has become necessary to reshape case segments to make them concentric with mating segments. This has resulted in assembly difficulties and eccentric loads on the joint o-rings. Assembly difficulties resulting from the lack of concentricity include the generation of case metal slivers produced by having to force pins into the joint pin holes. The pin-to-pin hole tolerances are such that the pin is difficult to install if the tang and clevis pin holes are not precisely aligned. Case segment ovality (which apparently results from the horizontal shipment on railcars) can cause tight tolerances in the area of the o-ring sealing surface. This can cause assembly difficulties and result in undesirable o-ring squeeze. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
224 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Hardware Performance Evaluation |  | Testing sealing surface diameters revealed diameter growth after hydroproof, which introduced unrecognized error in o-ring squeeze calculations. | Remeasure all case segments in inventory to determine reuse acceptability and require measurements to be retaken during refurbishment procedures. | KSC | 11/20/1992 | During a hardware performance evaluation, Solid Rocket Motor (SRM) clevis and tang sealing surface diameters were assumed to be stable and were not remeasured during refurbishment. Subsequent testing revealed growth in the diameters after hydroproof (and possibly flight) which introduced an unrecognized variable into o-ring squeeze calculations. The static o-ring compression after mating is influenced by these actual hardware dimensions and the degree of segment concentricity, and are critical to hardware performance. During the STS 51-L Investigation, measurements were made on refurbished and reused segments, and the data indicated that segment circumferences at the sealing surfaces change with repeated use. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
239 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Lifting Slings for Cranes |  | Improper choice of lifting slings can occur if only intuition obtained by experience is used. | Instruct crane operators to use calculations made from standard ANSI publications to determine safe sling working loads. | GRC | 07/09/1993 | During a crane disassembly, a cable sling broke, dropping a 10 ton crane counterweight. The crane crew was removing the front counterweight from the crane to place it on a flat bed trailer when the mishap occurred. The sling used was a rusty, 4 leg, 5/8 inch diameter cable about 15 feet long. Only two legs were used during this lifting operation. The investigating committee found that calculations made from a standard table published by U.S. Steel showed that the allowable working load for a new cable of this size using 2 legs was only 5.28 tons. The crane operators, based on their experience and intuition, grossly underestimated the strength of the sling. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
240 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Pneumatic Explosion |  | Maintenance programs that include disassembly and reassembly of test cell components require a check out procedure to establish work completion before initiating a test run. | Training should emphasize the importance for team members to check the actions of other members to prevent initiation of hazardous situations. | GRC | 07/17/1993 | A cover plate bolted to the top of a high pressure helium filter was blown off and the contents of the filter (pyrex wool and silica gel) were expelled. The resulting failure occurred because there were only three bolts holding the cover in place instead of the sixteen bolts required to fill all the bolt holes. The filter was pressurized to 1700 pounds per square inch with helium when the pneumatic explosion occurred. Preceeding the accident, as part of a maintenance program, the filter cover was removed for cleaning and reactivation. The bolts were frozen and difficult to remove. After three bolts were removed, the balance of them were cut off. When the cover was reinstalled, the three good bolts were put on but other bolts were not available to complete the bolt hole circle. Without knowledge of the incomplete assembly, the system was pressurized by the test crew resulting in the pneumatic explosion. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
238 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Altitude Exhausters |  | Exhausters designed for vacuum services can become pumps and cause severe damage to vacuum systems by overpressurization. Operators of stationary equipment such as exhausters and compressors can make damaging mistakes when rotated between facilities having different controls and operating procedures. | Install warning and relief devices in exhaust line piping to prevent accidental excessive pressure build-up. Standardize controls, relief devices, and operating procedures for all such facilities so that operator training will be simplified and minimized. | GRC | 07/08/1993 | Exhausters were running to provide simulation of altitude conditions in a combustor rig when the mishap occurred. The equipment operators were short-handed and, as a result, a certain amount of confusion existed. A valve at the discharge end of the exhausters was inadvertently closed. The reduced flow caused the inlet pressure to rise because a continuous quantity of air was being supplied to the exhauster inlet from the compressors in the system. As a result, the pressure at the exhauster inlet increased to almost atmospheric. The exhausters then became compressors and generated a discharge pressure level high enough to rupture the inverted, dished head of the exhauster header located 50 feet downstream. The inverted, dished head was 8 feet in diameter and 3/8 inches thick located 16 inches underneath the floor level. A hole about 30 feet in diameter was blown in the roof of the building located 35 feet above the floor level. A large number of windows were broken and the reinforced concrete floor in the vicinity of the rupture was destroyed. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
206 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Inertial Upper Stage (IUS) Propellant Tank Assemblies (PTA's) |  | With no PTA indicator to detect flight hardware anomalies, the IUS status will be uncertain and may result in undetected propellant leaks. | Provide individual pressure and temperature monitoring of the IUS reaction control system PTA's to detect potential propellant leakage failures. | KSC | 11/12/1992 | Inertial Upper Stage/Tracking and Data Relay Satellite (IUS/TDRS) instrumentation design allows active monitoring of only one of two Propellant Tank Assemblies (PTA's) during the countdown phase. The PTA's are isolated from each other until activated after IUS deployment. Therefore, the status of all PTA's can not be determined by monitoring one PTA. Pre-launch preparation procedures permit adequate determination of pre-flight PTA leakage status; pyrotechnic system design adequately protects against inadvertently commanded loss of PTA isolation; and structural design safety factors are adequate. However, no indicator is available to detect a flight-induced anomaly, thereby making the IUS status uncertain. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
209 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Time Correlation Between Multiple Telemetry Systems |  | The SSME telemetry system provides only approximate time correlation between multiple data systems, resulting in timing uncertainties. | Install a master timing unit to provide precise time correlation between multiple data systems to determine event sequencing in a system failure. | KSC | 11/13/1992 | The Space Shuttle Main Engine (SSME) telemetry system does not show absolute Greenwich Mean Time (GMT), but rather, the number of controller cycles since change in mode. Approximate timing had been established (during the STS 51-L launch process) by aligning the first guidance cycle after engine start with the engine start command time determined by analysis of the General Purpose Computer (GPC) event times. This aligned the SSME event times to the GPC event times to within a few tens of milliseconds, sufficient for normal flight analysis but insufficient for determining event sequencing for a system failure, which involves an interaction between the SSME and the rest of the vehicle. Without precise correlation between multiple data systems, there may be a delay in subsequent anomaly investigations due to timing uncertainties or a need to correct data timing. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
207 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Organizational Requirements and Responsibilities |  | The organizational system of making, archiving, and reporting environmental conditions is disorganized and responsibilities are untraceable. | Assign a single organization responsible for meeting all the environmental data requirements and providing them to the using organizations. | KSC | 11/12/1992 | A very disorganized system of making, archiving, and reporting natural environmental conditions at KSC has evolved. Several organizations make measurements and archive them in a variety of ways. Different organizations are responsible for transmitting these data to using organizations. The final report of the natural environmental conditions for the launch is the responsibility of another organization. Therefore, it is difficult to determine when and where some of the measurements were made, what type they are, and whether or not the instruments were properly calibrated. Instead of the numerous organizations, each organization that has a requirement for natural atmospheric environmental data should make its requirements known; and one single organization at each launch site should be responsible for the environmental data that could affect a launch. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
205 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Hardware Interface Module (HIM) |  | The failure of a HIM during propellant loading caused a launch delay, resulting in the loss of all fire detection and hazardous gas measurements. | Provide a back-up system or module to: (a) preclude the inability to monitor measurements taken during loading and (b) prevent propellant loading delays. | KSC | 11/12/1992 | The External Tank (ET) hardware incorporates five categories of instrumentation, sensors, and associated cabling, where the instrumentation data is recorded in the orbiter for transmittal to ground stations. The electrical system provides the propellant level, among other functions. The instrumentation is comprised of 38 sensors which control ullage temperature and pressure, liquid level, LH2 depletion, and vent valve position. During pre-launch propellant loading of the STS 51-L mission, a HIM failure caused a two hour, 20 minute delay while repairs were made. A HIM is used to interface the ET sensors with the launch control computer systems, where it is analyzed by systems engineers. The HIM failure resulted in the loss of all fire detection and hazardous gas measurements, which are required during propellant loading to provide adequate visibility of propellant leaks and fire. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
208 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Booster (SRB) Hydraulic Tank; Task Teams |  | Recent over-pressurization of a Solid Rocket Booster (SRB) hydraulic tank has been attributed to an improperly written Operational Maintenance Instruction (OMI). The use of task teams at Kennedy Space Center appears to be working well. | Increase efforts to improve the quality of OMIs, this should include the generation, review, and revision of the instructions. The task team approach should be expanded, at the same time increasing coordination among task teams. | KSC | 11/10/1992 | The task team concept that has been implemented at KSC is an approach to involving hands-on leadership at the task level. One of its benefits is that it keeps jobs moving without sacrificing quality, control, or safety. It also brings together all personnel needed to perform a particular job in conjunction with an identified leader and places responsibility at an operationally realistic level. Specific training on operating within a task team environment has been developed and used by the Shuttle Processing Contractor (SPC). Task team leaders are selected from the ranks of engineers and technicians as appropriate. In addition to the introduction of task teams, a joint NASA/SPC steering committee has been established to oversee and improve launch processing. One area the steering committee has targeted for improvement is the approach used to develop and update OMIs. The objective will be to improve the accuracy while simplifying and streamlining the processes. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
233 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Exhaust Systems - Gas Cooler Collapse |  | Large capacity exhaust systems in test facilities are potentially as hazardous as pressure systems. Failure of components due to age deterioration can occur if inspected improperly. | Perform routine inspections of the system, especially of components which have been in use for a considerable time. Warn personnel to stay out of areas that include high capacity vacuum lines when exhausters are operating. | GRC | 05/27/1994 | A deactivated exhaust gas cooler in a vacuum line collapsed under normal operating conditions of 26 inches of mercury. The cooler was destroyed. There was minor damage to a nearby wall due to negative pressure in the vicinity of the cooler. Skylights in the shop area imploded and a considerable amount of debris was drawn into the piping. The principal cause of the failure was deterioration of the cooler due to age. Poor welding during assembly and inadequate inspection of the cooler were contributing factors. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
234 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Clean Room F.O.D. |  | Epoxy paint applied to galvanized-coated workstands will chip/flake with usage, resulting in F.O.D. and clean room contamination. | In future designs, F.O.D. can be prevented/reduced by not painting galvanized/zinc-coated workstands in clean rooms. | KSC | 12/04/1992 | The Vertical Processing Facility (VPF) in KSC's industrial area is designed to accommodate all vertically processed payloads through cargo integration. The VPF consists of an environmentally controlled high bay and air lock. Two payload workstands with six fixed platforms provide access to payloads in the high bay. The workstand and platforms are currently painted with an epoxy-based paint applied over a zinc galvanized coating that prevents the paint from permanently adhering to the surface. Traffic and normal wear on the workstand causes the paint to flake, creating Foreign Object Debris (F.O.D.) and contamination in the clean room environment. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
218 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Mission Control Computer Support System |  | The mission control computer support system is out of date and does not meet current human interface system technology standards. | Implement a systematic process to replace the old mission control system with one based upon up-to-date computer technology. | KSC | 11/17/1992 | When the mission control center was first activated in the early 1960s, it was considered a technical marvel. However, this original architecture has received only modest upgrades since the Apollo program days. Until recently, it maintained a single mainframe based architecture that displayed data and largely left the job of data analysis and trend determination to the flight controller teams monitoring the consoles. The display technology utilized in this system is monochrome and primarily displays text information. The job of turning data into information, upon which flight decisions could be made is performed by the controllers through interpretation of the incoming numeric data. In cases where it was determined that additional computational support was required, small off-line personal computers were added. The controllers manually copied data from the console display screens and entered it into the small computers to perform off-line analysis. Although this system is technologically outdated, it contains years of customizing efforts and has served NASA well through space shuttle program missions to date. Several factors are now driving NASA to change the architecture of the mission control center operations. First, the primary reason seems to be to control costs. Second, automation available today can be used to expand the capabilities of controllers by eliminating some of the data reduction tasks they must perform and by increasing the amount of information they can utilize in making decisions. Third, the time required to obtain information for decision-making can be substantially reduced. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
220 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Logistics and Support Systems |  | The expansion of component overhaul and repair facilities at the launch site and in nearby areas has increased efficiency and saved money. | Continue with the philosophy of centralizing orbiter spares support and overhaul/repair activity in the KSC area. | KSC | 11/18/1992 | The logistics and support program for space shuttle is continuing to develop. The problems that persist, in general, are well documented and understood. They do, however, need continuing attention if flight rates are to be maintained without compromising safety. Development of the NASA shuttle logistics depot, which is located in Cocoa Beach is proceeding very satisfactorily, and should provide overhaul and repair facilities for a large range of shuttle components when it is fully developed and equipped. The main facility encompasses some 223,000 square feet, and an adjacent group of smaller buildings has 45,000 square feet. Among its several aims, the facility will permit more rapid turnaround of line replaceable units, reduce spares inventory requirements, and provide insurance against the cessation of Original Equipment Manufacturer (OEM) overhaul services for certain obsolescent and unique components. The manufacture and repair of some items of Ground Support Equipment (GSE) also is being provided for, and the entire facility will form a very well-equipped "back shop" for the on-site support of the shuttle programs. Completion of the required shop equipment, availability of fully trained personnel, provision of technical manuals, support, etc., for the overhaul of a chosen component earns a "certification" to perform the task. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
222 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Obsolescent Parts |  | Lack of a comprehensive plan for scheduling and accomplishing major overhaul of the orbiter fleet could leave NASA without up-to-date hardware. | Increased emphasis should be given to ensuring the availability of sufficient quantity of up-to-date hardware. | KSC | 11/18/1992 | Some of the original equipment manufacturers are not providing sufficient support for out-of-production parts. NASA and its contractors have evolved good systems for identifying and tracking these problems, but the difficulties of ensuring continuing production with small batches of obsolescent or semi-obsolescent parts inevitably will increase with orbiter age. The problem involves balancing the alternatives of purchasing and storage of excess parts, establishing manufacturing facilities and skills at KSC, or potentially facing critical shortages. The heart of the problem is that many manufacturers simply do not want to devote any more manpower or effort to revive production. The study of possible alternative source vendors for critical parts continues but is necessarily a slow and complex process. The 1990 ASAP annual report concerned with structural overhaul and dealt principally with the visit on OV-102 at the Palmdale facility scheduled to begin in June 1991. A review of the major modifications necessary to bring OV-102 up to the standard of OV-105 was included. During the work on OV-102, a "3-year" and a "6-year" structural inspection will be performed. It is assumed that this will provide the information necessary to define a basic structural overhaul program. This program would then be fitted into available intervals in the launch program up to 1995 for all four orbiters. A second element of longer term maintenance program planning has been defined but apparently is not presently funded. It is known as "orbiter supportability plan - project 2020" and is intended to provide a basis for ensuring a rational program for orderly maintenance and support of the fleet through the assembly of the SSF. The outline of the plan properly embraces the interfaces of the existing major contractors and the operating NASA centers, and outlines an organizational support formula. This formula includes detailed line replaceable unit supportability and full structural integrity accountability. The ASAP has an interest in seeing this program go forward as planned. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/08/1994
221 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Failure Analysis |  | Delays in accomplishing failure analysis causes excessively slow turnaround times for many repairable components. | Develop a methodology for streamlining the failure analysis process. | KSC | 11/18/1992 | The total elapsed repair turnaround time still can be excessive with a resulting major impact on inventory management. There are several contributing causes for this that were discussed briefly in the 1990 annual report, but one of the key issues is the average time involved in the engineering analysis of failed components. The overall trend of repair turnaround time showed a significant improvement toward the end of the year, but in some cases, notably the components overhauled by the original equipment manufacturers, the time is much too high. Management emphasis currently is being directed to the entire problem of reducing repair turnaround time and should continue. |  | N/A |  |  | Public | Not Specified |  | 06/08/1994
189 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Processing Documentation |  | The KSC work control documentation system is inadequate and may result in a shuttle processing mishap. | Revise system documentation, making it easier to comprhend, and include personnel training to ensure complete compliance. | KSC | 10/30/1992 | The KSC work control documentation system, which controls and records space shuttle processing, has evolved from three manned space flight programs: Mercury, Gemini, and Apollo. It provides the key to vehicle configuration control, proper definition and authorization of the work to be performed, the assurance of adequate work having been performed after closeouts, and traceability and accountability for actions performed. Inadequacies were uncovered in the form of a lack of timely closures recorded on completed work items; poor annotation of the steps taken in performing authorized deviations; missing signatures and quality control stamps (an average of 1/4 of 1% missing); and a lack of traceability. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
188 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | T-0 Umbilical Carrier Plate. |  | The shock load resulting from shear pin firing causes lower release pin hole elongation, causing premature T-0 umbilical disconnect. | Evaluate different design possibilities, i.e., increase the shear pin strength, or holding plate strength. | KSC | 10/29/1992 | As a result of lower release mechanism pin hole elongation, there is potential for premature disconnect of the T-0 umbilical carrier plate due to failure of the LO2/LH2 tail service mast (TSM) lower release mechanism pin hole structure to support the dropweight. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
187 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Hydrogen Vent Umbilical. |  | Hydrogen vent umbilical deceleration unit latch failure could result in the vent line rebounding during liftoff and striking the vehicle. | Design a secondary/redundant latching system that will ensure that the ET GH2 vent line is held secure. | KSC | 10/29/1992 | The ET vent line may not be secured because the deceleration unit latch mechanism fails to latch. This mechanical malfunction of the latching mechanism, possibly resulting from exposure to exhaust blast from the vehicle could cause the ET vent line to rebound and strike the vehicle. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
186 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Intertank Access Arm. |  | Lack of limit switches could allow the arm to damage the ET during a hydraulics system failure. | Design and install emergency stop limit switches that will automatically stop the arm during an inadvertent failure of the drive system. | KSC | 10/29/1992 | There are no limit switches to prevent the ET intertank access arm from overrunning its extended position should the hydraulics system fail or the snubbers not stop the arm during extension. The mechanical snubbers were not meant to absorb the loads available from the hydraulic system or, more significantly, from the momentum of the arm. This could damage the external tank. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
191 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Preintegrated Truss (PIT) Sections for Space Station Freedom |  | The capture latch guide pins and motorized bolts used to couple the assemblies are not always in proper alignment. This could damage guide pins. | Develop a hardware test encompassing the full range of misalignments, tolerances, and impacts that might reasonably be expected to occur. | KSC | 11/04/1992 | The use of truss segments, which are preintegrated with distributed systems and verified on the ground instead of erected on-orbit, has reduced technical risk and made the space station a more viable program. The preintegrated truss members (PIT) must be heavier than the original truss elements per running foot because the entire mass of the PIT is subjected to launch loads. PIT members are aluminum I-beams bolted together instead of the more flexible graphite composite elements that previously were part of the design. The heavier construction allows orbit replaceable units (ORUS) to be located in their optimum positions for accessibility. One benefit of the restructured design is that EVA time has been reduced considerably so that EVA targets are now feasible. This has been accomplished by reducing the demand for EVAs and increasing the efficiency of those that must be performed. In the assembly of the PIT sections on-orbit, a capture latch provides final alignment by engaging guide pins after the sections are brought into proximity by the space shuttle remote manipulator arm. Motorized bolts then make the final latch-up. There is a chance that these sections may not line up correctly; therefore, damage may occur to the guide pins and bolts when the motorized bolts engage. Because the PIT sections will be assembled on the ground, the opportunity exists to test the alignment and mating procedures prior to flight. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
190 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Launch Complex (LC) 39B Modifications |  | LC 39B systems operate differently than those on LC 39A, making the facilities susceptibile to launch damage. | Modify pads to operate alike and allow ground support equipment to be connected and used identically at either facility. | KSC | 10/30/1992 | Launch complex 39B demonstrated satisfactory capability during the STS 51-L launch, with a few exceptions. It was anticipated that the initial shuttle launch from LC 39B would uncover minor problems, and some discrepancies between the Pad A and Pad B systems. Damaged or loosened items due to the launch have been identified as candidates for additional pad "hardening" and other mechanical/electrical systems had minor operating differences than those on LC 39A. A freeze plan was first used during STS 51-L, which allowed vehicle operations to safely continue at below freezing temperatures. The freeze plan was successful in that vehicle operations continued but the resulting build-up in ice is not considered desirable for future operations. A water systems protection plan, to eliminate the necessity of continuously running water through pipes in very cold weather to prevent freezing inside, is being studied. If operations below freezing temperatures are essential, water system modifications will be required. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
192 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Body Flap |  | The results of flight tests indicate that turbulent flow over the body flap induces greater stresses than originaly used for structural analysis. | Evaluate as rapidly as possible, the results of new tests and loads analyses to reestablish the allowable number of flights for the body flap. | KSC | 11/04/1992 | Photoanalysis of the STS-28 (OV-102, Columbia) flight showed larger body flap deflections than were calculated. The flaps are in a turbulent flow field, which creates a hinge moment spectrum greater than that used in the structural fatigue analysis. The loads are all within the structural limits, but the fatigue analysis shows a reduction of allowable flights from 100 to 77. After the higher hinge moments were observed, additional ground tests were conducted using recalibrated strain gages on the body flap actuator as well as additional instrumentation on the rotors and stators. Three types of loads were applied. It was discovered that an additional load path existed back through the driving gear to the supporting structure. The original equations assumed only four load paths at the actuators. With a fifth load path, it is necessary to develop a new set of equations. It also was discovered that the actuators were more flexible than originally assumed and that the OV-102 (Columbia) actuators were more flexible than those on OV-103 (Discovery) and OV-104 (Atlantis). This is attributable to increased tooth width on the OV-103 and OV-104 actuators. Additional tests are planned to further evaluate the body flap structure. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
194 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Automatic Landing Capabilities. |  | Significant risk reduction will result if the space shuttle's automatic landing capabilities are fully developed and certified for operational use. | Develop a detailed test of the automatic landing system that will include all functions through touchdown and rollout to wheel stop. | KSC | 11/04/1992 | The space shuttle system presently includes an autoland system that provides automated guidance capable of navigating the orbiter to the selected landing runway. The increased duration of space shuttle flights as part of the extended duration orbiter program (EDO) has raised the issue of the need to qualify the existing system during actual flights. It also raises the issue of the possible need to fully automate all landing, rollout, and braking functions so that the orbiter could be returned safely from orbit without any crew intervention, if necessary. The existing automated approach guidance system never has been fully flight tested. The second space shuttle flight, STS-2, left the auto mode engaged until the latter part of the team region and demonstrated that the system was capable of returning the vehicle to a flyable energy state from a low energy state. STS-3 left the system in auto until the commander's scheduled takeover at 125 feet. The system was on energy and trajectory at takeover, but the pilot had difficulty getting "into the loop," and an uncomfortable situation developed. The final several thousand feet of the shuttle's descent involves relatively complex flare maneuvers with which a pilot might be expected to have difficulty when retaking command. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
196 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Launch Processing Workload |  | Manpower limitations due to a high workload created scheduling difficulties and contributed to operational problems. | Implement a more effective manpower/skill mix for prelaunch operations to minimize effects of repeated launch attempts on processing operations. | KSC | 11/04/1992 | An unusually high workload at the time of the STS 51-L ground processing caused manpower limitations, and some areas where particular skills were required, were in short supply. The major cause was the necessity of processing four orbiters, while also completing the launch complex 39B activation. Original planning called for OV-103 to be shipped to Vandenberg AFB in September 1985. The shipment was delayed in order to fly OV-103 on an additional flight from KSC. The need to delay the movement of OV-103, in turn, was caused by major work on OV-102 that had traveled to KSC. This resulted in a long processing flow prior to the STS 61-C launch. Problems in processing both orbiters were further increased by a substantial reliance on part cannibalization to support the operations. This was compounded by the STS 61-C activity, which was moved from a planned December 1985 launch to January 12, 1986. This unplanned delay, along with several intermediate launch attempts, created a higher than anticipated demand upon manpower, resulting in schedule limitations. In some skills, such as test conductors and senior engineers, the higher than normal test activities created abnormal demands upon their availability. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
195 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Software Upgrades. |  | The replacement of requested software upgrades with crew procedures is of great concern especially since software offers greater reliability & safety. | Review all crew procedures that might be performed by the computer to determine if doing them manually is better than by software. | KSC | 11/04/1992 | The movement of some requests for software upgrades to crew procedures is a matter of serious concern. The crew already has a very large number of procedures with which to be familiar. Adding to that load, particularly with items that could be handled easily with greater reliability and safety by software, does not seem wise. Procedures such as "do not touch the keyboard for X seconds after the occurrence of event Y" can be handled easily by software. If such procedures are contingencies that are employed infrequently, the chance of error when they are needed rises. A review of all computer-related procedures to ascertain whether or not there is significant potential for design-induced human errors should be mounted. This review should include crew representatives, experts on human factors, and members of safety and mission quality organization. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
146 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Fuel and Oxidizer Storage Tank Relief Valves. |  | Lack of relief valve isolation has resulted in excessive toxic vapor releases to the environment. | Install a dual relief valve system with a 3-way 2-position valve and isolation valves with aspirator access ports. | KSC | 10/02/1992 | The present method of annual calibration of fuel and oxidizer storage area relief valves involves removal of the valves, thus opening the tank to the atmosphere. Large amounts of toxic vapor may be released. During one operation for the N2O4 storage tank relief valve, a greater than expected quantity of N2O4 vapor released (28 gallons compared to the one gallon expected). The extensive dispersion of the vapor cloud exceeded the predesignated clear area of 700 ft. Downwind. Also, several personnel were exposed to the vapor due to unrelated circumstances. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
145 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Portable Hypergol Checkout Panels. |  | Configuration of the portable hypergol checkout panels hinders emergency egress from platforms 6E and 6W in the OPF. | Design and install permanently mounted hypergol checkout panels and hardlines placed out of the egress path. | KSC | 10/02/1992 | The configuration of the portable hypergol checkout panels located on platforms 6E and 6W in the OPF restricts personnel working in the area from egressing to a safe area. The checkout panels (four per high bay; two per platform) have flexhoses and electrical cables that become entangled and cannot easily be maintained in an orderly arrangement. The flexhoses and cables also present a tripping hazard and further hinder emergency egress from the platforms. Additionally, these flexhoses leak and are more prone to failure because of their tendency to kink and twist in this configuration. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
149 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME) Vertical Installer Operations |  | Material deterioration of operating parts in SSME vertical installer may cause engine to contact flight hardware/personnel and cause damage/injury. | Prior to installation/removal of SSME, inspect air piston and bore for material defects/wearing to preclude vertical installer failure. | KSC | 10/08/1992 | The SSME vertical installer is used to position the engine for mounting on or removal from the orbiter. During SSME vertical installer operations, it was discovered that the air piston had a scored land ring. This scoring was due to the end of the stop groove being peened over. This peened condition happened when the stops came into hard contact with the end of the grooves. This condition occurs when the piston sticks in the cylinder due to a lack of lubrication and/or foreign material in the cylinder. Pressure then builds up until the piston breaks free. When the piston breaks free it can travel to the stops with enough momentum to cause this peening condition. A failure of the vertical installer caused by this scoring/peening could prevent positive control over the SSME and lead to unexpected movement during the installation/removal process. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
148 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Reaction Control System (RCS) Thruster Valves |  | RCS thruster valve seats have a tendency to relax at low temperatures and low pressure, allowing liquid/vapor to leak past the seals. | To minimize the potential for a significant leak of hypergolic propellants, ensure that dual valve isolation is maintained. | KSC | 10/02/1992 | Leakage of small quantities of toxic propellants, monomethyl hydrazine (MMH) and nitrogen tetroxide (N2O4) from one or more reaction control system (RCS) thrusters could create an environment hazardous to personnel. The aft and forward RCS contain residual MMH and N2O4 under post-flight pressure. RCS thrusters have been known to leak when ambient temperature is low, orbiter valve pressure is low, and/or if there is no orbiter internal purge. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
147 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | OMS Engine Injector Ball Joints |  | Failure of the OMS engine trickle purge system lasting more than 96 hours will result in corrosion of the injector ball valves. | Design a GN2 purge detection system that could be monitored electronically and sound an audible alarm at the operations desk if the purge should fail. | KSC | 10/02/1992 | The orbital maneuvering system engine trickle purge system is used to prevent oxidation/corrosion damage to the OMS engine injector ball joints. A 1.0 - 1.5 SCFM GN2 flow is applied during post-landing ground operations. Undetected loss of GN2 purge to OMS engine injector cavities could eventually corrode the vehicle system. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
151 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Throat Plug and Purge Adapter Assembly Grounding |  | Improper/lack of assembly grounding may cause static electricity build-up and electrical sparks which may ignite any flammable vapors present. | Update OMI's to provide proper grounding procedure of throat plug and purge adapter assembly, as well as positive grounding verification. | KSC | 10/08/1992 | The throat plug and purge adapter assembly, located in the reaction control system (RCS) primary thruster, provides the means for sealing the RCS primary engine throat during activation, decontamination, and purging. The assembly consists of a tubular structure terminating in an expandable seal, which is inserted through the nozzle skirt. The plug is hand operable from the opposite end and expands the seal to a diameter larger than the nozzle throat, providing a positive mechanical interference to preclude blow-out. The plug end gasket is removable to permit inspection for cleanliness or deterioration. The assembly also includes a passage for ducting purge fluid during deactivating and purging to a toxic vapor disposal system. Improperly grounding or a lack of grounding may cause static electricity build-up and electrical sparks which could act as an ignition source for any flammable vapors present. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
152 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Reaction Control System (RCS) Primary Thruster Plug Assembly |  | Nitrogen tetroxide (N2O4) vapor leakage from primary thruster causes o-ring deterioration, allowing moisture to enter/contaminate thruster nozzle. | Install an o-ring seal compatible with nitrogen tetroxide that will prevent hypergolic leakage and water intrusion. | KSC | 10/08/1992 | The RCS primary thruster throat ferry flight plug assembly is used to prevent moisture intrusion during the orbiter's ferry operations. This assembly is installed after the orbiter lands and is removed during deservicing operations. After deservicing, the primary engine cover is used during orbiter processing to control and/or prevent moisture. This cover has a butyl rubber o-ring which acts as a moisture seal, but is incompatible with N2O4. Vapor leakage could cause deterioration of the o-ring, severely limiting the effectiveness of the thruster ferry plug to seal out moisture, as well as contaminating the thruster nozzle. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
153 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Hypergol Spill Aspirators. |  | The S70-1119-1 and -2 aspirators vent directly to the atmosphere which could contaminate hardware and/or injure personnel. | Restrict the use of these aspirators to outside areas such as landing sites and fuel farms. | KSC | 10/08/1992 | The -1 and -2 hypergol spill aspirators vent into the atmosphere when used. These were KSC's first portable models and are now identified to operate only at unconfined areas because of their venting characteristics to the atmosphere. The -3 through -6 aspirators are configured to vent into a facility vent system. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
150 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Quick Disconnect (QD)/Filter Assembly Set (POD) Operations |  | Structural failure of pod bellows or other assembly components could cause onboard reactants to be contaminated with gaseous helium and particulates. | Inspect QD/filter assembly set for cleanliness, loose/missing components, pressure loss/leaks, and damage as part of pre-operational checkout. | KSC | 10/08/1992 | The QD/filter assemblies are designed to provide a disconnect interface and remove all solid particles (exceeding 25 microns) from the servicing fluids at various system operating pressures, contaminant capacities, and rated flows. Servicing fluids include O2, H2, freon, coolant water, and potable water. Assemblies consist of a quick disconnect, filter, and associated caps, fittings, seals, and tethered nameplate/identification tags. The QD has internal bellows which permit movement of a probe assembly that opens flight-half coupling. A pod component failure may cause contamination in the orbiter onboard reactants. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
197 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Line Replaceable Unit (LRU) Cannibalization |  | The orbiter logistics system and spares supporting the 51-L mission were inadequate, causing the need for significant LRU cannibalization. | Periodically update spare parts list based on flight experience and quantities, and store spare parts in a ready-to-use condition. | KSC | 11/04/1992 | The practice of cannibalization has almost become a standard procedure during orbiter processing due to insufficient spare parts. This causes a significant increase in the overall processing effort. The removal of a needed LRU from the orbiter being cannibalized is an unplanned activity. A second activity, installing the removed LRU in the receiving orbiter, has usually been allowed for in the overall contingency planning; but the process flow time is impacted because it takes longer to cannibalize a part than to retrieve one from storage. When a LRU is obtained and reinstalled in the cannibalized orbiter, it must be retested. The replacement of the removed LRU and its retest are added work. Also, the increase in activity required for the unscheduled removal/replacement always increases the potential for damage. The follow-on tests that are performed to verify that no damage occurred are another unplanned addition to the workload. Three hundred parts were required during the launch processing of challenger for the STS 51-L mission. Of these, 45 were cannibalized from OV-103. In future decisions on whether to use a spare LRU or cannibalize, the use of a spare, when available, should be considered the first choice. Overall, cannibalization is an inefficient way to process an orbiter. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
198 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Launch Complex Systems Performance |  | Without full assessment of capability of vehicle and facility to withstand adverse environmental conditions, a potential for unexpected problems exists. | Reassess/improve the effects of adverse environmental conditions on pad systems and impose appropriate launch constraints. | KSC | 11/04/1992 | The effects of an adverse environmental condition, specifically, unusually cold weather, are not sufficiently well understood. The amount of ice formed by leaving valves open to prevent freezing inside water pipes was greater than expected. After the STS 51-L launch, photographic documentation revealed that ice released from the pad structures after engine ignition translated further toward the vehicle than predicted. The performance of some complex 39B systems was marginal due to the cold. The number of cameras that failed to operate at liftoff was three times that of the historical average. Instrumentation and analytical models were not adequate to define the unusually cold operating environment in which the launch was conducted. Additionally, the effects of such temperatures on the components of a space shuttle standing on the pad have not been sufficiently determined. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
199 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Readiness Review (FRR) |  | The FRR inadequately addressed areas involving Solid Rocket Booster (SRB) flight safety issues which later proved to be critical. | Revise the launch decision process to enlarge the engineering data base and ensure critical issues are properly addressed during vehicle processing. | KSC | 11/04/1992 | The FRR process which leads to the launch decision is a part of a total management system comprised of many reviews. The chain of events which culminated in the STS 51-L accident indicates that the management process applied to critical flight safety issues was inadequate. The basic engineering understanding of the SRB field joint and the effects of operating at low temperatures was lacking. Prior qualification testing and analyses were not adequate to support SRB use in temperature ranges forecasted for the STS 51-L launch. The management tools, including the critical items list, did not adequately protect against the possibility of a fatal mishap. The launch decision followed established directives, but the engineering knowledge base supporting the launch decision was inadequate. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
200 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Adverse Environmental Conditions During Launch |  | Ice debris created by the STS 51-L launch was greater than predicted and resulted in impact with flight hardware. | Prior to launches in icy conditions, thoroughly analyze predicted ice trajectories, effects on plume aspiration, and ice release times. | KSC | 11/04/1992 | Ice debris created by the STS 51-L launch was greater than predicted by pre-launch analysis. The trajectories of wind-driven ice falling from the Fixed Service Structure/Rotating Service Structure (FSS/RSS) were predicted using aerodynamic analysis methods. These methods accounted for drag retarding the fall and wind velocity imparting a lateral velocity component. The effects of plume aspiration and particle rebound off the mobile launch platform were not included in the analysis. Launch films show that the vehicle rising off the launch pad caused considerable aspiration. This effect drew ice toward the Solid Rocket Booster (SRB) PLUME, with some ice striking the left hand SRB. The actual FSS/RSS ice movement, as observed on the photographic documentation, did not conform to the predictions in two important respects: 1) the ice generally did not release until after main engine ignition, and 2) the ice translated further toward the vehicle than predicted. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
184 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | LO2/LH2 Vent and Relief Position Indicator Switch |  | Inaccuracies in vent/relief valve position indicator switch may cause gas leakage, resulting in fire and loss of flight hardware and/or orbiter. | Perform outdoor wind tunnel testing of vent/relief valve to provide data, quantifying leak rates below which the hazard is eliminated. | KSC | 10/28/1992 | The LO2 and LH2 vent and relief valve position indicator switch tolerance allows the valve to indicate "closed" when it may be open up to 0.30 inch. This condition could allow undetected ullage gas leakage prior to launch. Hot GO2 may auto-ignite the ET thermal protection system (TPS) after SSME ignition. GH2 in flight can cause fire and loss of TPS which could result in a catastrophic situation. The vent/relief valve uses a position indicator switch that is highly accurate. However, no matter how accurate, no position indicator can accurately assure closure because leakage rates for qualification and acceptance are roughly 5E-6 lb/sec. Therefore, a redesign to eliminate the hazard has proven to be virtually impossible. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
181 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Forward Reaction Control System (FRCS) Mezzanine Platform |  | Lack of a breaking system on the winches used to lift the FRCS mezzanine platform could result in a mishap if a winch fails. | Replace the existing winches with upgraded winches having disc brakes. | KSC | 10/27/1992 | The winches are used to lift and lower the FRCS mezzanine access platforms at the 207 foot level of the RSS. Should they fail during retraction or extension operations, the platform could fall and breakaway from its hinge and wire rope tether, resulting in possible damage to the orbiter and/or injury to personnel. As an interim control, platforms are being tethered with a 1/2" nylon rope during all lifting operations. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
185 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME) Testing |  | Demonstration of the full margin extent of critical engine components, subsystems, and systems were omitted during testing. | Continue SSME over-stress, limit, and malfunction testing to demonstrate the full engine capabilities. | KSC | 10/29/1992 | The SSME design verification specifications are evaluated by analysis, laboratory testing, subsystem testing, and/or engine hot fire testing. Tests are planned to expose problems early and consist of over-stress tests, off limits tests, and malfunction tests. The ground test program prior to the STS 51-L accident was questionable. The number of tests per month had decreased during a two year period prior to the accident. The SSME development program specifies a ground hot fire test program that includes multiple engines of the flight configuration, with maintenance and inspections, that demonstrates hot fire operational time far in excess of the orbiter fleet leader engine. It also pursues engine hot fire tests that demonstrate the limits of the engine operational parameters and margins or over-stress tests to verify the full engine capability. Further, margin tests should be conducted to the extent that they reasonably represent potential engine operation in a degraded state. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
182 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Booster (SRB) Work Platforms |  | Movement and vibration of SRB work platforms has rendered debris shields inadequate protection for personnel and flight hardware (SRBs). | Design new debris shields that will provide protection for personnel and flight hardware. | KSC | 10/27/1992 | Because of movement and vibration, debris shields provide inadequate protection against dropped or falling objects. Vibration and movement on workstands causes debris shields to move out of place, leaving flight hardware unprotected. Dropped tools and/or equipment could cause damage to the SRB's. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
183 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) Segments Transportation |  | Shipment of SRM segments in horizontal position may cause cases to assume undesirable out-of-round conditions and contribute to mating difficulties. | Reconfigure SRM segment transportation to preserve case shape and condition during shipment. | KSC | 10/28/1992 | The SRM segments are transported horizontally by standard 200-ton capacity railcars with hydraulic couplers. It was determined that the transportation design requirements for the transportation support equipment exceeded the capabilities of the railcars. There is concern for potential changes to the cases resulting from transportation in the horizontal position. As part of the case joint redesign effort, studies are being conducted to determine the effect of horizontal transportation on case ovality and, in turn, the effect of ovality on the assembly process. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
201 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Advanced Solid Rocket Motor (ASRM) Propellant Manufacturing Facility. |  | Particular problem areas related to the particle size of the propellant and the screw pump indicate that the facility may not be directly scaleable. | Scale-up of the ASRM propellant manufacturing plant should be scrutinized closely to ensure that safety and schedule are not compromised. | KSC | 11/05/1992 | The full-scale ASRM propellant manufacturing facility may not be directly scaleable from the continuous mix pilot plant. Particular problem areas relate to the particle size of the propellant and the screw pump section of the rotofeed. Many parameters and processes for the new facility have not been fully determined. However, another manufacturer has produced a substantial amount of similar solid propellant using continuous production processes, so the basic techniques are familiar. Safety devices are installed on the propellant flow line to limit the spread of fire in case of an accident. The flow line transporting the uncured propellant has several firebreaks to prevent propagation of a fire along the tube. The basic safety device is an explosive-fired guillotine valve that interrupts the flow, with a water spray on the propellant to lower the temperature below the ignition point. In addition, there is a collar in the flow line upstream of the guillotine and on the casting pit side of a firewall that can be blown to allow the propellant to flow out on the floor and prevent pressure buildup. A matter that must be considered is cleanup after an accident involving a dump of uncured propellant on the floor. The continuous mix pilot plant at manufacturer provides a way of proving a new propellant and upgrading the equipment before establishing a full-scale facility at yellow creek. The major differences between the pilot plant and the full-scale facility are equipment size and process control software. The pilot plant production rate is 1,000 to 1,400 pounds/hour with the full-scale facility producing 20,000 to 26,000 pounds/hour. The ultimate particle size of the propellant is dependent on parameters such as geometry of piping, length of lines, and fluid working pressures that may not be directly scaleable. There are many challenges such as metering of propellant solids, pre-mix of iron oxide and aluminum, and real-time process control. Upscaling the rotofeed dearator and pump equipment probably presents the greatest challenge. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
176 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) Field Joints and Configuration |  | Insufficient knowledge of performance characteristics of putty used as a thermal barrier in SRM field joints affected ability of joints to seal. During testing, putty preparation differed from that used on flight hardware resulting in SRM lacking liftoff dynamic effects on case joints. | Design a new SRM field joint which eliminates the use of putty as a thermal barrier. Configuration and processes during qualification testing must be as similar to actual performance as possible in order to verify adequacy. | KSC | 10/23/1992 | The primary reason for the use of the putty in the SRM was to act as a thermal barrier in the joints to prevent o-ring erosion resulting from circumferential hot gas flow during motor firing. Prior to the 51-L mishap, the putty was believed to perform such that it would allow pressure to the primary o-ring during the SRM ignition transient. Subsequently, it has been found that humidity and temperature enhance the characteristics of putty relative to its pressure holding characteristics. The uncertainty of these characteristic changes directly affected the ability of the field joint to seal. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
175 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) Field Joints |  | All environmental specifications imposed by NASA for the SRM were inadequately verified by test, analysis, and similarity. | Prior to each launch, conduct qualification testing of the SRM over the full range of possible environments. | KSC | 10/23/1992 | The SRM Is the primary propulsive element for the space shuttle. The SRM consists of: an insulated and lined segmented rocket motor case loaded with solid propellant; an ignition system complete with electromechanical safe and arm device, initiator, and load ignitor; a movable nozzle; raceway bracketry; instrumentation; and the necessary integration hardware. Structurally, a SRM is configured with a forward rocket motor segment, two center rocket motor segments, and one aft rocket motor segment. A field joint is that portion of the SRM segment that is assembled/stacked at KSC to create the finished SRM. These field joints are susceptible to environmental conditions and were not qualification tested to the full range of environments. This led to a lack of complete understanding of the joint design limits. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
170 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | OPF Payload Bay Bucket Limit Switches. |  | Failure of one or more components (1S8-4S8) in the closed position would prevent the limit switches from stopping downward travel of the buckets. | Design a fail safe control system that will stop all movement of the bucket if a critical component fails or fails to perform properly. | KSC | 10/22/1992 | Failure of one or more of these component switches 1S8, 2S8, 3S8, or 4S8 in the closed position would cause a short circuit of relay K11, thus not allowing any of the 16 bucket proximity limit switches on both buckets to stop travel. This can result in damage to flight hardware (payload and/or vehicle) due to buckets hitting hardware. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
172 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Access Arm (OAA). |  | Sudden deceleration of the arm and entrapment of pressurized hydraulic fluid may cause damage to the OAA and prevent crew rescue/egress. | Ensure that the position of the arm is monitored during launch countdown; initiate a countdown hold if the arm is retracted prior to T-0 seconds. | KSC | 10/22/1992 | Pilot actuated extend supply and return valves can be reset to the closed position while the access arm is being extended. This could damage the OAA and possibly prevent reextension and crew egress. Position of arm must be monitored during launch countdown. A retract signal from LPS or from the safing panel during an LPS emergency extend mode will cause the extend valves to be reset. In addition, removing the safing panel emergency extend signal prior to full extend, while the LPS or safing panel is in the retract mode, will cause the extend valves to reset. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
174 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | OPF Payload Bay Buckets. |  | There are no brakes on the bridge bucket drive units to ensure the bridge will stop if the drive chain or the electric brake fails. | Design a fail safe braking system that will include the bridge drive unit and prevent the bucket from colliding with flight hardware. | KSC | 10/22/1992 | The OPF payload bay bridge hoist system spans the length of the shuttle payload bay. Two bridges, mounted on platforms, move on rails. On each bridge are two moveable trolleys, each trolley providing a base for a suspended, telescoping bucket hoist. Each trolley has two-speed (3 ft/min and 9 ft/min), direct-drive gear motors and redundant electric brakes. There is potential for flight hardware damage because the bridge cannot stop in short distances. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
173 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Deservicing and Weather Protection at Dryden Flight Research Center (DFRC). |  | Use of the DFRC hangar for deservicing/weather protection after landing could result in fire/explosion and/or personnel injury. | Monitor for MMH, N2O4, and N2H4 continuously during deservicing operations and shut down all electrical equipment prior to entering the hangar. | KSC | 10/22/1992 | Flammable and toxic vapors can be expelled into the deservicing hangar at DFRC, providing a potential for fire, explosion and toxicity above the permissible exposure limits (PEL). No venting is planned, however, pressure bleed vents do exist on these systems and are expected to boil off and vent periodically in short bursts if the fuel cells have been secured. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
171 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Tail Service Mast (TSM). |  | Space limitations inside the TSM preclude installation of OSHA required handrails, kickplates, and ladders. | Limit access to the TSM, using only trained personnel, and require the use of safety belts or harnesses. | KSC | 10/22/1992 | OSHA requirements for handrails, kickplate, and ladders are not met. Platforms inside the tail service mast (TSM) do not have handrails to prevent personnel from falling from platforms. Kickplates are not placed on platforms with a height of four inches. Rungs on the access ladders are not evenly spaced at twelve inches as required by OSHA. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
178 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) O-ring Processing |  | Mandatory inspection points were inadvertently eliminated during STS 51-L o-ring processing. | Perform a complete assessment of all mandatory inspections to ensure that no inspections are eliminated. | KSC | 10/23/1992 | During processing, employees failed to perform checks of the mandatory inspection points of the o-rings as specified in the acceptance criteria. However, a review of inspection records for the 51-L o-rings indicates there is a high probability that the 51-L o-rings were acceptable for launch |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
180 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) Sealing Surfaces |  | Measurement of two used SRM case segments indicated tang and clevis sealing surfaces increased in diameter beyond design limits. | Redesign sealing surfaces to tolerate accepted proof pressure levels and utilize monitoring system to ensure compliance with design criteria/limits. | KSC | 10/23/1992 | A case dimensional change study performed as part of the 51-L failure analysis effort produced the diameter change results. The potential cause for this phenomenon is believed to be material related in three areas and their direct effect on the hydrostatic proof test pressure level chosen for acceptance testing prior to reuse. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
179 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) Static Testing |  | The full scale hot fire testing of the SRM's was performed with the motors in the horizontal position rather than in flight attitude. | Perform hot fire static testing in a vertical (flight attitude) position unless a deviation will produce proven sufficient results. | KSC | 10/23/1992 | A review of the considerations for the decision to fire the full scale motors in the horizontal position was based mostly on programmatic considerations and the concern of determining the thrust values more accurately. It was not obvious that the effects of this deviation in test and flight configuration received sufficient attention. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
177 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) O-ring |  | The adequacy of o-ring processing, quality control and material delivery-to-processing is questionable. | Investigate and eliminate potential problems in manufacturing process, final delivery and material cutting of the o-ring. | KSC | 10/23/1992 | The o-ring used in the SRM case joint is critical to the sealing of the joint, yet is not designated as a critical process. The adequacy of o-ring processing and quality control is questionable even though a number of o-rings in bonded storage were thoroughly analyzed and tested as part of 51-L failure analysis effort and found to be acceptable. The manufacturing process included delivery of the final o-ring rubber material to where the material is cut to the proper lengths and a scarf joint is made. This manufacturing process is a potential problem area as seen by repairs of inclusions and voids in the rubber delivered. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
166 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Post Launch Blast Cover Removal |  | A possibility exists for personnel injury while removing blast covers after each launch due to the lack of an access platform to stand on. | Install access/work platform on LH2 ET vent line at 95-foot level of the fixed service structure to provide a safe means of removing blast covers. | KSC | 10/16/1992 | After every launch, personnel are required to climb out and balance on the liquid hydrogen external tank vent line to remove blast covers. After launch, the vent line is covered with a mixture of solid rocket booster residue and sound suppression water, thus making it very dangerous to climb on the line to remove blast covers. The location under the vent line is a 20-foot unprotected drop. Personnel could fall and/or drop the heavy blast shield cover during the installation/removal process. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
167 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Forward Reaction Control System (FRCS) Access |  | Use of temporary platforms provides inadequate access to FRCS cavity for trunnion fitting maintenance, and may result in injury/damage. | Design/utilize permanent platforms which allow access to trunnion fittings in lower forward fuselage area. | KSC | 10/16/1992 | No platforms have been designed to provide personnel access to the orbiter's lower forward fuselage (foward reaction control system cavity) for repairs, maintenance, and/or inspections. The use of portable pic-boards (temporary structures) may cause personnel to fall or allow contact between the pic-board and orbiter, resulting in personnel injury and/or orbiter damage. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
164 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Handrails on the OPF Bridge Buckets. |  | Non-collapsible handrails on the OPF buckets in HB-1 are stressed when raised to full up position, creating a potential for damage or falling. | Redesign handrails to meet the original 200 pound load requirement in any direction and to be collapsible to prevent damage. | KSC | 10/15/1992 | Non-collapsible handrails are in place on the OPF buckets. When the OPF bucket (platform) is raised to the full up position, the hand rails stress, creating the potential for structural failure. The handrails must meet a 200 pound load requirement in any direction, collapse to prevent system damage (approximately 100 pounds), and must be contained so as not to fall into the orbiter P/L bay. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
165 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Heat Shield. |  | A structural diagonal brace is interfering with the installation of the heat shield and could damage the heat shield | Reposition/remove the structural diagonal brace located at the rear of platform 10 in the OPF high bays 1 and 2. | KSC | 10/15/1992 | The orbiter heat shield must be lifted through the rear of the swing platforms on platform 10 (coordinate X0=17.37, Y0=20.00). A structural diagonal is in the way and could damage the heat shield. As an interim control, OMI V5043 includes a caution note when moving the heat shield. Until the diagonal brace is repositioned or removed, personnel must use extra caution not to contact the heat shield with the diagonal brace during heat shield movement. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
157 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | External Tank (ET) Vent Deceleration Unit. |  | Low fluid level in the shock absorber could cause failure of the deceleration unit damaging the QD and result in a hydrogen fire. | Design a mechanism that will prevent the ET GH2 vent arm from rebounding back into an SRM. | KSC | 10/08/1992 | The external tank's gaseous hydrogen vent arm provides for venting of the LH2 tank, pneumatics, and electrical services to the ground umilical carrier. The deceleration unit has failed twice. These failures were caused by a low fluid level in the shock absorber. During one launch failure the QD was damaged and broke in half. Several hours after launch, the detanking of the LH2 dewer tank was started and gaseous hydrogen vented out of the broken QD/pipe, instead of venting to the Pad-A burn pond as designated. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/06/1994
160 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Payload Bay Access Bridge Bucket |  | A lack of mechanical stops/lock for payload bay access bridge buckets could result in damage/injury during maintenance/inspection. | Provide a locking device to support the bucket load when the cables are disconnected during inspection and replacement. | KSC | 10/14/1992 | The payload bay bridge hoist system is located in the orbiter processing facility, and spans the length of the shuttle payload bay. The two bridges, mounted on platforms, move on rails. On each bridge are two movable trolleys, each providing a base for a suspended telescoping bucket hoist. Maneuvering to any point in the payload bay is possible with the three directions of motion provided by the bridges, trolleys, and buckets. With no mechanical locking device to support the bucket load when cables are disconnected for inspection or replacement, a possibility exists for damage or injury. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
158 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Payload Bay Door Cycling |  | Platforms 11A-1 and 11A-6 cause an interference problem when the PBD's are opened/closed during aft propulsion system (APS) servicing. | Modify platforms 11A-1 and 11A-6 to allow them to be utilized with the PBD's in "normal" service position. | KSC | 10/09/1992 | Platforms 11A-1 and 11A-6 were retracted to support payload bay door opening. The platforms were not able to be extended for personnel access in support of aft propulsion system pod activities due to an interference when the orbiter payload bay doors were being cycled open and closed. Contact due to interference may cause damage to the payload bay doors and orbiter or personnel may be injured. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
156 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Hydraulic Control Panels. |  | The system was designed with the check valve and supply valve incorrectly positioned resulting in pressure lock-up. | Correct the design deficiency by repositioning the check valve to a location upstream of the supply valve. | KSC | 10/08/1992 | During MLP vehicle hydraulic power-up, trapped pressure between check valve A77943 and supply valve A77900 could occur if the supply valve is not open. When pressure is locked up, the supply valve has to be opened using a pry bar, sometimes breaking the valve handles. This constitutes an unsafe condition and could result in injury to personnel. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
155 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | OPF Platform 13 |  | Lack of positive stops on the OPF platform 13 tip extension provides the extension with the capability to roll off the end of the platform. | Design and install positive stops on platform 13 that will prevent the tip extension from rolling off the end of the platform. | KSC | 10/08/1992 | The OPF platform 13 tip extension could potentially roll off the end of its track into the payload bay or onto the floor of the OPF. Lock pins must be removed when extending platform 13 and re-inserted prior to use. Personnel are currently aware that the platform will not stop automatically on rollout. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
162 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter/ET Feedline Mating Stud Tensioner. |  | A potential exists for a high pressure fluid leak, over-pressurization, improper stud tensioning, and/or flexhose rupture and whipping. | Require personnel to use proper protective clothing and safety equipment during the procedure used for the stud tensioner. | KSC | 10/15/1992 | The orbiter/ET feedline mating stud tensioner unit exposes personnel to a high pressure source and could result in injury or flight hardware damage. During ratcheting of the nut onto the stud, personnel will be in the vicinity of high-pressure fluid, water, and rust inhibitor at 11,600 psig. Three stud tensioner heads, connected by six hoses through a common manifold, are used to apply a tension load of 64,000 lbs maximum to three cryogenic umbilical separation bolts by means of an air-driven hydraulic pumping unit. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
163 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | 750 psig GN2 Supply |  | Failure of the system to provide the ability to isolate and vent 750 PSIG GN2 actuation pressure to individual flodyne valves. | Install isolation and vent valves to permit depressurizing individual flodyne valves in pneumatic panels for maintenance. | KSC | 10/15/1992 | The supply system for the 750 psig GN2 is designed such that pressure may not be removed from flodyne valves for removal/replacement, a SCAPE operation, without removing pressure which actuates other relevant components. Inadequate isolation capability of actuation pressure could result in loss of valve control, allowing valve to open when it should be closed. This could allow trapped residuals in the cross country line to drain back to the storage area, possibly resulting in a hypergol spill or fire. |  | N/A |  |  | Public | Not Specified |  | 06/06/1994
134 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Power Reactant Storage and Distribution (PRSD) LH2/GH2 Fuel Cell Servicing |  | A PRSD GH2 leak may result in accumulation of flammable vapors in orbiter compartments or near umbilicals, causing injury or damage. | Provide periodic inspection/preventative maintenance on fixed hydrogen leak detection sensors and thoroughly inspect for flammable/toxic vapors. | KSC | 09/24/1992 | The orbiter PRSD system provides GH2/GO2 for fuel cell operation. The PRSD H2 T-0 umbilical vent is installed to support controlled venting of the PRSD H2 system during convoy operations. The umbilical vent is connected to the backpressure relief panel by flexhoses. Pressure must be maintained on the PRSD manifold during fuel cell cool down until vent stack and condenser exit temperatures are within 15 degrees Fahrenheit of ambient. Fixed hydrogen leak detection sensors monitor the fuel cell servicing/deservicing system areas for H2 leaks which could result in damage to vehicle/facility or personnel injury. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
132 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Power Reactant Storage and Distribution (PRSD) Pod Latching Mechanism |  | Failure to establish a preventative maintenance program for the PRSD pod latching mechanism has resulted in damage to the thermal protection system. | Establish a preventative maintenance program for the PRSD pod latching mechanism. | KSC | 09/24/1992 | The QD/filter assemblies are designed to provide a disconnected interface and remove all solid particles from the servicing fluids, which exceed 25 microns in size. The system supports the required operating pressures, contaminant capacities and rated flows. A scupper to support the pod has not been provided for Dryden Flight Research Center. This mishap was caused by a worn or deformed stop pin in the pod latching mechanism. The worn pin allows the latching dog to rotate past the mate position to the demate position. Failure has occurred on several occasions. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
135 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Vertical Assembly Building (VAB) Major Lifting Operations |  | Failure of 250/175-ton crane DC power loop or DC control loop critical components could result in damage/loss of flight hardware/GSE or injury. | Perform periodic preventative maintenance, testing, and pre-operational checks on 250/175-ton cranes to ensure support lifting operation readiness. | KSC | 09/25/1992 | The 175-ton and two 250-ton VAB cranes are used to perform solid rocket booster (SRB) stacking, external tank (ET)/SRB mate, and orbiter/ET mate. The 250-ton and 175-ton cranes operate on crane rails 466 feet and 168 feet above the VAB floor, respectively. Crane motions are controlled from the console of the crane cab. The cab is equipped with four master switches which control movement of main and auxiliary hoist load blocks and trolley and bridge travel. The main and auxiliary hoist and trolley and bridge drives are redundant configurations utilizing motor-generator sets that supply energy to the DC final drive motors. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
133 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Avionics System. |  | Cooling system flexhoses that supply the orbiter avionics system are too long, allowing hose kinking to occur. | Redesign/shorten the return and supply flexhoses to prevent them from kinking. | KSC | 09/24/1992 | Return and supply flexhoses are connected between the ground coolant boom and the LH2 check-out umbilical carrier plate. Because the hoses are too long for such a short connection area, hose kinking occurs. This situation can cause damage to the orbiter avionics systems due to overheating because of loss of freon cooling. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
143 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Engine Changeout Platform (ECP) and Engine Service Platform (ESP) Hoisting |  | Failure of wire ropes, winch components, or operator error during hoist operation with ECP/ESP could result in damage/loss of flight hardware/GSE. | Install an emergency stop switch and a redundant holding brake to ECP and ESP hoisting systems to comply with lifting equipment design requirements. | KSC | 10/05/1992 | The ESP and ECP are designed to support maintenance and replacement of space shuttle main engines (SSME's) while the orbiter is in a vertical position. Both platforms utilize the same hoisting system, located on level B of the mobile launch platform (MLP). A combination of four hoists raise and lower the platforms through the SSME exhaust hole. The platforms are secured to the MLP prior to SSME maintenance/installation. A design certification review was performed on the platforms. The review identified three non-compliances to design standards as givin by KSC-STD-Z-0002B, standard for design requirments for lifting and hoisting equipment. These are (1) no emergency stop switch, (2) no final upper limit switch, and (3) only one holding brake. However, the upper limit switch was shown to be impractical due to varying heights of the platforms, proximity of the platforms to the tail service mast, and independent operation of the winches. A failure in the hoisting system during raising/lowering could cause the platform to tip, resulting in damage/loss of a SSME, ground support equipment, or MLP. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/03/1994
141 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Radioisotope Thermoelectric Generator Facility (RTGF) Lifting Operations |  | Failure of the RTGF crane electrical components, due to an internal malfunction, increases the potential for damage to load and/or crane. | Install an emergency stop switch on the crane operator's control pendant to enable immediate power removal/setting of brakes in emergency situation. | KSC | 10/05/1992 | The 10-ton crane at the RTGF is used to lift and position radioisotope thermoelectric generators and ground support equipment. Crane electrical component failure increases the risk of load and/or crane damage. Failure of switches 3 or 4 results in bridge movement and bridge brake will not engage if a BR-1 relay failure occurs. Failure of switches 5 or 6 results in trolley movement and trolley brake will not engage if a BR-2 relay failure occurs. Failure of switches 7 or 8 results in hoist movement and hoist brake will not engage if a BR-3 OR BR-4 relay failure occurs. Failure of switch SW-2 in the fast speed position will result in the hoist operating in the fast speed even if the operator selects slow speed. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
142 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | 540A Industrial Oxygen (O2) Analyzer Monitoring |  | An oxygen analyzer system failure may cause personnel to unknowingly enter or work in an oxygen deficient atmosphere, resulting in asphyxiation/death. | Provide periodic 02 analyzer calibration checks and introduce oxygen-free gas into sample ports to verify proper operation of direct output module. | KSC | 10/05/1992 | The 540A industrial oxygen analyzer continuously monitors the oxygen content from samples of atmosphere. Monitored areas include the orbiter processing facility, vertical assembly building, mobile launch platform, and the pads. When the oxygen level in these areas drops to an unsafe level of 19.5% or less, an audible/visible alarm is activated to warn personnel to evacuate the area. The oxygen analyzer has a sensing circuit which relays data to a supervisory box assembly which triggers the battery box assembly if an oxygen deficiency is detected. The battery box assembly supplies power to the warning beacon and sends a read out to the complex center console C-2 (in the launch control center). A component failure within the oxygen analyzer due to fatigue/shorting may cause an erroneous high output signal when the oxygen level is below 19.5%, resulting in no alarm warning. Personnel may enter/work in the area, unaware of the low oxygen level, and become asphyxiated. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
138 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | GOX Vent Arm Air Receivers Bleed Manifold Venting Operations |  | Excessive noise levels during GOX vent arm air receivers bleed manifold venting operations may damage personnel hearing. | Install muffler on outlet vent to operate both air receivers during bleed operations and reduce noise level to within OSHA regulations. | KSC | 09/25/1992 | During bleed down of the 125 psi air system, a process which lasts less than one minute, the noise level at the Pad B gaseous oxygen (GOX) vent arm air receiver outlet vent exceeds permissible OSHA noise exposure limits. A noise hazard survey conducted during the bleed down operation was performed on the air system to determine the noise level near the operator's ear. This survey recorded a noise level of 126.5 DBA. OSHA 1910.95, occupational noise exposure, limits noise exposure for fifteen minutes or less to 115 DBA. A possibility exists for personnel permanent hearing loss. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
136 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Payload Canister Transporter (PCT) Diesel Fueling Operation |  | An ignition source (spark, heat, or flame) present during a PCT diesel fueling operation could possibly ignite the diesel fuel. | Prior to fuel transfer operations, inspect grounding reel for deterioration resulting in poor common ground between fueling tanker and transporter. | KSC | 09/25/1992 | The PCT is designed to operate between/within space shuttle payload processing facilities. Two transporters are used to carry the payload canisters and hardware throughout kennedy space center. Drive power is provided by a 400-horsepower diesel engine. A ground reel clip is used during fuel transfer operations to establish a common ground between the diesel supply tank and the vehicle to be filled. Fueling operations are prohibited during electrical storms within five miles of the transfer site. Flame or spark producing devices, such as matches, lighters, or smoking, are also prohibited in this area. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
137 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Operations and Checkout (O&C) 4-ton Monorail Crane Operations |  | The 4-ton monorail crane lacks a local emergency power disconnect device which increases potential for flight hardware damage or personnel injury. | Redesign crane control station to include an emergency stop switch to terminate power/set brake should crane speed control system failure occur. | KSC | 09/25/1992 | The 4-ton monorail crane is used to handle flight related equipment and flight hardware in the operations and checkout building. The crane operator is not able to control the load or terminate all power in an emergency situation because the 4-ton crane lacks required safety devices. The crane operator does not have direct access to the main circuit breaker in the event of crane speed control system failure or other hoisting failure. By removing power to the crane, the crane brakes are set and all system movement is halted. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
139 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Postlanding Orbiter Compartment Vapor Sampling |  | An undetected accumulation of toxic/flammable vapors in orbiter compartments after landing may cause damage/loss of orbiter/personnel. | Provide an onboard vapor detection/gas sensing system and purge capability for orbiter closed compartment. | KSC | 10/05/1992 | During and after landing, there are no means aboard the space shuttle orbiter for detection of hazardous gases. A hazardous gas sensing capability internal to orbiter compartments does not exist until the T-0 hookup; then only limited capabilities exist. After landing, a sampling crew approaches the orbiter to check the orbiter's exterior for the presence of toxic/flammable gases and/or leaks. Hazardous gases may cause a major problem prior to or during the time the sampling crew performs its checks. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/03/1994
140 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Suspended Load Operations |  | Failure of a critical item lifting device (crane, hydraset, or lifting beam) may result in serious injury/loss of personnel or flight hardware. | Minimize work time under suspended loads and modify lifting devices to use DC motors to eliminate erractic trolley and bridge movement. | KSC | 10/05/1992 | Solid rocket motor (SRM)/orbiter processing and stacking requires personnel to perform tasks under suspended loads, increasing risk of injury/loss of personnel or flight hardware. personnel work under a suspended static load while processing SRM's and while the orbiter is in the vertical position to remove landing gear pins. An engine/turbo pump change requires personnel to work under the main engine area. Personnel work under a suspended load when the orbiter is mated/demated to the shuttle carrier aircraft to remove/install landing gear pins and during installation/removal of the orbiter's maneuvering system pod. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/03/1994
131 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Environmental Control System (ECS) Pressure Distribution Unit |  | Similar adjacent connections on the ECS pressure distribution system allow for the possibility of misconnected lines resulting in damage. | Install keyed connectors to prevent misconnection of pressure lines. | KSC | 09/24/1992 | The environmental control system (ECS) pressure distribution unit pre-operations set-up requires several flexhose connections and leak checks prior to operation. Pressure lines could be misconnected and result in damage to flight hardware or injury to personnel. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
130 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Fuel Cell Coolant Loop Vacuum Pump |  | The check valve in the inlet line of this vacuum pump has been unable to prevent reverse flow of air through the pump and into the system. | Install an upstream solenoid valve to automatically disconnect the system if power is lost. | KSC | 09/24/1992 | The units contain a vacuum pump driven by 1/2 HP electric motor, a shutoff valve, a vacuum break valve and an oil trap tank. The -1 and -2 units consist of GFE previously used on the apollo program and modified by the addition of quick disconnect couplings, a vacuum read-out gage, and fluid hoses. Also, replacement of components not compatible with the fuel cell coolant FC-40 and electrical system modifications have been made to meet shuttle program use requirements. The pump has provision for oil separation; however, if the system's volume is sufficiently large, oil vapor may be sucked from the pump into the system. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/03/1994
129 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | The Oxygen Vent System. |  | Failure to protect the vacuum servicing unit from inadvertent actuations of the 935 psig cryo valve panel could result in damage to flight hardware. | Install a pressure actuated check valve to prevent the high cryo pressure from affecting the vacuum servicing unit. | KSC | 08/24/1992 | The vacuum servicing units provide the capability to evacuate the PRSD tanks and the relief line. The unit consists of a skid mounted frame, electrical and fluid control panels and an electric motor driven vacuum pump. If the vacuum servicing unit is left connected to the suction line, inadvertent opening of manual valve A81992 could subject the pump to 935 psig from the cryo valve panel. This is beyond the unit's capability and could expel pump oil through the vent system. |  | N/A |  |  | Public | Not Specified |  | 06/03/1994
59 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | RCS Thruster Heater Power During Ferry Flight Stopovers; RCS Thruster Ferry Plug Removal; Hypergol Exhaust System Indicator Lamp |  | Failure to power up the orbiter during ferry flight stopovers disables the thruster heaters and increases the potential for RCS thruster leakage. Propellant may spill out of RCS thrusters if they are not aspirated prior to plug removal. Due to an excessively slow panel lamp, the exhaust system was actuated several times and resulted in the system remaining off. | Develop detailed guidelines as to when the orbiter can be powered down or when it must remain powered up. To preclude spillage of propellant during plug removal from a leaking thruster, the plug should be aspirated through the relief valve. Add a flashing red light that responds without delay indicating system is operating. | KSC | 02/12/1992 | During the removal of the flight reaction control system (RCS) ferry plugs from the orbiter, between 1/4 and 3/4 cup of monomethylhydrazine (MMH) fuel spilled from the thruster. The liquid contacted the gloves and right shoe of the technician pulling the plug. The RCS thruster valve seals have a history of sensitivity to temperatures below 60 deg F. To limit the potential for leakage, the RCS thruster heater power unit should remain on throughout the Dryden Flight Research Facility (DFRF) safing and ferry period, including flight stopovers and KSC offload. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
58 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Equipment Tethering |  | Personal equipment used by repair personnel in elevated positions must be tethered to them to prevent damage from dropping. | Incorporate specific instructions in work authorization documents to tether or otherwise restrain all equipment used in elevated positions. | KSC | 02/11/1992 | While an employee was climbing out onto a steel beam to inspect debris nets on the 16th level of the VAB, a beam clamp attached to the employee's belt struck a beam and fell 16 floors to the transfer isle of the VAB. The clamp fell near personnel in the transfer isle. The clamp was not properly tethered. Continuing emphasis is required to ensure that personnel are knowledgeable of and comply with tethering requirements. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
60 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Effective Tagout and Lockout Compliance; Upper Limit Switches Utilized as Operational Stops; Momentary Switches; Wire Rope Spooling System; Access Platform Load Rating; Telescoping Tubes of the OPF Access Platform System; Commonality Between High Bay 1 and High Bay 2 Payload Bay Access Platforms |  | Use of an inadequate tagout or lockout device may allow improper restoration of a system previously tagged as hazardous. Upper limit switches being used as operational stops can not be relied upon to stop the operation during an emergency. Momentary switches that stick in the "on" position may damage equipment and endanger personnel. Hoist systems (as used in the OPF) can release excessive lengths of cable from the spool. Operations in the orbiter processing facility are limited by access platforms that are limited to loads of 500 pounds or less. Telescopic tubes have experienced binding as they were lowered, indicated by a tube descending suddenly to its proper position after becoming free. Servicing operations utilizing payload bay access platforms have shown that a common speed mode for both east and west platforms is undesirable. | Design positive lockout devices that will ensure compliance with lockout/tagout directives. Install operational stopping devices that will permit stowing of the platform vertically without the use of the upper limit switch. Momentary switches utilized in control systems should have a manual release capability designed in. Design the wire rope spooling systems to include stops that will prevent excessive amounts of wire rope from being released. Enhance the hoist system of the OPF access platforms to support heavier loads (up to 1500 pounds). Provide a device in the wire rope system that will sense excessive loads and stop the hoist when a safe load is exceeded or the cable is slack. Change the High Bay 1 access platform to operate the same way as High Bay 2, where both east and west platforms have independent speed modes. | KSC | 02/20/1985 | During final closeout operations of the space shuttle orbiter in High Bay 2 of the Orbiter Processing Facility (OPF), a payload bay access platform fell from its stowed position, damaging the orbiter's left payload bay door and injuring a technician. The platform's hoisting cable was previously weakened when technicians used the platform system while it was tagout/lockout. The weakened cable continued to stretch and break, even though the technicians returned it to its stowed position. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
61 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Crane Load Cell System |  | Failure of a crane load cell system during lifting operations contributed to the damage of a solid rocket motor segment. | Institute/write procedures for the operation, maintenance, and calibration of load cell usage. | KSC | 03/01/1992 | On November 8, 1985, the forward center segment of a solid rocket motor (SRM) was damaged during forward handling ring removal operations. During the operation leading to this incident, the crane operator was attempting to raise the hook until a load of 11,000 pounds was attained, but the load cell read zero until the segmented ring fractured and the crane was stopped. The load cell system was provided with the crane, but the requirement for its usage is not clear. Loadcell usage is not mentioned in the crane OMRSD nor is it mentioned in the system assurance analysis (SAA). |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
126 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Environmental Control System (ECS) Hardware Interface Module (HIM) Card |  | Failure of ECS HIM 161 card may cause loss of chiller GN2 control and result in high temperature/humidity damage to orbiter/payload. | Design a remote back-up capability to allow chiller control from the redundant HIM 213 card in the event of HIM 161 failure. | KSC | 08/24/1992 | Three Pad B ECS chillers condition air for the orbiter and payload changeout room. The ECS chiller GN2 control system, which regulates the amount of cooling provided by each chiller, is controlled by HIM 161 and HIM 213. The auto/direct mode select control allows chiller GN2 control via the auto or direct mode. Normally, HIM 161 controls chiller temperature/humidity in the automatic mode. If this mode should fail, chiller control is maintained by switching to the direct mode. If the HIM 161 direct mode fails, there is a potential for partial/total loss of chiller GN2 control and subsequent orbiter/payload damage. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
125 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Compartment Overpressurization |  | Normal purge air applied to the orbiter compartment while the vent doors are closed may cause major orbiter damage. | Specify in work document that vent doors must remain in standard purge configuration and all on-board vent door circuit breakers remain "open". | KSC | 08/21/1992 | The portable purge unit supplies conditioned air through ducts to the orbiter to purge and/or pressurize the payload bay's forward and aft compartments. Airflow varies between 50 lbs/min minimum to 100 lbs/min maximum. Vent door observers are always on station when a vent door is repositioned for a test or TPS tile/thermal barrier work. Overpressurization may occur if all the orbiter vent doors (normally in the purge position) for a compartment are closed at one time. Control logic program VAM09 also notifies the firing room engineers if both a right hand and left hand purge vent door set is closed. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
124 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Payload Bay Duct Heater Overtemp |  | Excessive heat from payload bay duct heaters may cause severe damage to ducting, insulation, and orbiter payload bay. | Design and install high temperature cutoff switches in payload bay duct heaters for overtemp emergency shutdown. | KSC | 08/20/1992 | The payload bay duct heater adds measured quantities of heat independently to each duct system. This raises the temperature of the process air from the cooling coils to the desired interface temperature leaving the portable purge unit and engine control system room. With no overtemp switches installed, excessive heat from the payload bay duct heaters burned through the duct insulation, causing severe damage with a potential for orbiter damage. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
127 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Protection System "Y" Curtain Wall Retraction |  | Payloads and facility damage and/or personnel injury may occur due to high impact stops of "Y" curtain wall during retraction. | Install and utilize a flow control valve in the air winch supply line to permit speed regulation of the winch in the console mode. | KSC | 08/25/1992 | During the retraction of the orbiter protection system "Y" curtain wall in the console mode, the speed attained after leaving the slow travel transition is excessive. The operator must manipulate a manual valve to reduce air flow to the winch. High impact stops from the rapid movement of the "Y" curtain wall during retraction may cause personnel injury and/or damage to payloads and facility (PAD). |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
64 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Emergency Stop (E-STOP) Switch Cover; Inadvertent Disconnection of Flex Hoses; Orbiter Tow Tug and Support Truck Emergency Stop |  | Emergency stop switch covers made of soft or pliable material allowing inadvertent actuation of emergency stop switch. When the trailing support vehicle inadvertently stops, the tow tug continues allowing the flex hoses to pull free and spew freon 14. Lack of integrated emergency stop control switches allowed the tow tug to proceed when the trailing support vehicle initiated an emergency stop. | Utilize double action switches for emergency stop switches were there is a possibility of inadvertent actuation. Add automatic cut off switch activated by a flow sensor, that will stop the flow of freon during unplanned flex hose separations. During tow operations the dead-man switches of both the tow tug and the support truck should be wired together so both trucks will stop together. | KSC | 03/12/1992 | After the towing convoy turned off the runway onto the tow way, the cool tractor/trailer suddenly stopped. The observer caused the rig to suddenly stop when his hand inadvertently came in contact with the E-STOP switch cover. This caused the boom to oscillate up and down. The boom operator lowered the boom to get maximum extension on the two coolant flex hoses attached to the orbiter. The boom's oscillation caused the flex hoses to be whipped loose before the orbiter could stop. The flex hoses fell to the ground with freon 14 spewing from them. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
63 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Overheated Baking/curing Oven Temperature Control |  | Failure to utilize redundant overtemp cutoff circuitry may result in damage to components undergoing baking/curing processes. | Add a series redundant 440 VAC cut-off switch that is actuated by the temperature shutoff circuit sensor. | KSC | 03/06/1992 | During the cerachrome insulation baking process of three injector/chamber assemblies, severe oxidation of the assemblies was observed. The required baking temperature, per MTS 1324, is 600 deg F for 48 hours. It was discovered that the oven had failed, allowing the temperature to reach an estimated 1400 deg F. A proposed design change will reduce the possibility of this happening again. The modification incorporates a direct 440 VAC cut-off initiated by series redundant over-temperature shutoff circuits, as well as, a series redundant shutoff of the temperature control. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
65 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Mercury Switch Terminals |  | Electrical terminals of mercury switches located too close to the chassis, result in electrical arcing and mercury switch explosion. | Provide electrical insulation of the switch terminals from the chassis. | KSC | 03/16/1992 | The shear mode resonant dampening (SMRD) lab is utilized to support the process of applying SMRD material to printed circuit boards. Problems were encountered with one of the ovens (blue M model POM-223) used in the SMRD application process not maintaining the set temperature. A technician sent to investigate opened the front panel to perform a visual inspection and upon closing, a mercury switch mounted close to the chassis inside the front panel arced and exploded. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
71 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Fork-lift Crown Manaboard Steering Control Electronics |  | Inadvertent malfunction of crown manaboards steering control electronics, caused the crown manaboard to jump off the control track. | Redesign the crown manaboard steering control electronics unit to reduce the possibility of future mishaps. | KSC | 04/28/1992 | Materials were being pulled for issue at the logistics facility using a fork-lift crown manaboard. The operator had already made several issues and was in the process of returning materials to their location. He was looking at the location of his next issue and when he looked up the manaboard was heading for the racks. He immediately hit the brakes but it was too late, the fork-lift hit the shelving support structure and damaged it. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
73 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | MLP 3 SRB Engine Service Platform Hoists |  | During a platform hoisting proof load test, the second layer of cable caused the end ring welds to fail, breaking the cable, and dropping the load. | Verify that all critical welds have been performed in accordance with specification 79K30047, SEC. 0510 "welding of carbon steel (structural)". | KSC | 04/28/1992 | The SRB platform testing began by loading the platform with 32,000 lbs. of sand. The load was lifted off the ground with a four winch slow speed lift. After clearing the ground, a high speed lift was initiated. An observer reported that a second wrap was beginning on the drums. A slow up mode was initiated and after approximately 12 inches of travel the observer reported the drums were coming apart at the end ring welds. The platforms' "C" corner dropped then the "A" corner dropped. The platform then flipped over, broke the cables and fell to the ground. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
74 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Pad B External Tank (ET) Platform Hoist |  | Failure of clutch to provide a positive engagement between the drum, shaft, gear train, and break allowed the hoist's drum to begin free wheeling. | Modify the hoist's clutch assembly to ensure that it provides a positive mechanical engagement that will prevent free wheeling. | KSC | 04/30/1992 | A technician was working on the ET access platform, attempting to close the bifold doors on the 155 foot level of Pad B. The brake released on the hoist that was holding the platform that the technician was standing on. The platform gave way and the technician fell about 15 feet. He suffered a broken left ankle and other minor bruises. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
72 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Lepel Brazing and Debrazing Equipment |  | Lack of an open circuit shut off switch resulted with an electric arc cracking a debrazing head and damaging a coil and purge fittings. | Develop and install a sensor that will detect open circuits and shut off the lepel brazing/debrazing machine when they occur. | KSC | 04/28/1992 | During debrazing operations of a purge fitting in an orbiter's aft compartment, the debrazing head separated, causing an electrical arc. This arc caused the debrazing head to heat up, which caused cracking of the debrazing head and damage to the coil and purge fittings. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
76 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Thermal Protection System Components |  | Incomplete documentation and instructions resulted in one of the orbiter's insulation blankets being damaged by air flow from an ECS duct. | Provide appropriate inputs to applicable standard practice instructions and work authorizing documents. | KSC | 05/02/1992 | While performing an area walkdown, a supervisor, noticed what looked like paint chips on the pick board in the forward RCS area. After further investigation it was determined that air flowing from a nearby duct was blowing against a thermal protection system (TPS) blanket causing irreparable damage. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
75 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Breakout Boxes |  | The absence of tie-off points or protective holding areas for hand portable equipment resulted in damage when breakout boxes were knocked off a work platform. | Install protective hold locations for all hand portable equipment and install eyelets on all hand portable equipment for easy tethering. | KSC | 05/02/1992 | Three breakout boxes were located on the orbiter aft compartment entrance platform. When two technicians entered the aft compartment, these breakout boxes were knocked off of the platform, falling 7.5 feet and striking the space shuttle main engine (SSME) #1 AIR/GN2 purge line. This fiberglass line was cracked. In addition, the SSME #1 main fuel position actuator was damaged. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
110 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Vacuum Read-out Stations for the MLP's LH2 system |  | Inadequate access to the vacuum read-out stations on the MLP LH2 system's vacuum jacketed lines could lead to personnel injury. | Relocate the vacuum read-out stations to an area and height convenient and safe for technicians to easily access. | KSC | 08/28/1992 | The LH2 system maintenance includes a monthly vacuum reading in the annulus space in the overhead vacuum-jacketed (VJ) high point bleed and LH2 fill lines. Access to the read-out ports in the GH2 fill line on side 1 of the MLPS is precarious. There are not adequate tie-off points for body harness and lanyards. The readout ports are 10-12 feet above the floor grating. If a technician uses a ladder for access, or climbs on existing structures to make the reading, he/she is within inches of exterior handrails and above them. This places him/her about 40 feet above the vab floor or the pad surface. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
108 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Gaseous Helium Injection During Slow LOX Fill |  | Failure of the helium injection valve or clogging of the filter could cause loss of the helium injection system. | Develop a preventative maintenance program for the critical valves and filters in this system. | KSC | 08/20/1992 | The helium injection system introduces a controlled flow of helium into the aft end of the feedline to prevent geysers during propellant loading and holds before launch. The helium is supplied from panel S72-0697-08 through one series valve (A78410) and two parallel valves. Failure of the series valve or clogging of the downstream filter could cause loss of bubbling. Loss of helium bubbling prior to 2% full or after 98% full in the external tank (ET) could result in damage due to geysering. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
109 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Maine Engine (SSME) Work Stands |  | The SSME work stands have to be split apart to clear ground support equipment, reducing work stand stability and availability. | Design a fixed work platform that will fill the gap between the work stands or totally replace them. | KSC | 08/21/1992 | The A70-1289 work stands were designed for light, mobile work. During maintenance operations on space shuttle main engines (SSME) in the vertical position the stands must be split apart to clear engine ground support equipment (GSE). This reduces work stand stability and availability of work area. Pic boards are utilized to span the open areas when the work stands are in the split configuration. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
111 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | LH2 Quick Disconnects (QD) |  | Quick disconnects utilized for providing gasses to the space shuttle main engine (SSME) are identical to each other and can be cross-connected. | Modify (KEY) one quick disconnect to prevent misconnection. | KSC | 08/27/1992 | Quick disconnects, utilized for providing gasses to the space shuttle main engine drying/purge lines and the main propulsion system LH2 prepressurization system are identical and can be cross-connected in the OPF. The MPS heated GN2 purge panel provides heated or unheated GN2 at 645 +/- 65 psig for engine drying. Should GN2 645 +/- 65 psig be introduced to the GH2 prepressurization system, flight hardware damage could occur. This condition may or may not be visible on the firing room pressure gages depending upon the status of orbiter power. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
70 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | 480 Volt Power Cable Connectors and Mating Tool; Emergency Cut Off Device for the 480 Volt Power Cables |  | An overheated 480 volt/400 AMP power cable connector exploded and then burst into flames. The power cable connectors used to provide power to the portable purge unit (PPU) require an excessive amount of force to mate them to the receptacles. During an explosion and fire of a 480 volt power cable connector, employees were not provided with a means to remove power from the cables. | Remove from service all similar connectors; dismantle and examine each for evidence of debilitating anomalies and replace defective connectors. Design a special tool so that mating forces are applied uniformly with a reasonable amount of force. Install a method of disconnecting power to the 400 amp cable connectors provided for the portable purge unit (PPU) power cables. | KSC | 04/22/1992 | During routine operation of the portable purge unit (PPU), the 480 volt power cable connectors exploded and melted, causing the unit to shut down. The explosion was caused when the connectors' overheated multi-point contact band caused the solder to melt, destroying the connectors' Integrity. It is confirmed that the force of the explosion could seriously injure or kill personnel within a 50' radius. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
67 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Retractable Platform Hinge Mounts Secured With Pop Rivets |  | Soft metal (aluminum) rivets used to secure steel hinges to heavy platforms failed, resulting in flight hardware damage. | Replace all hinge platform mounts with steel bolts, lock washers, and nuts on all similar platforms. | KSC | 03/26/1992 | A thermal protection system (TPS) technician had an access platform retracted and secured to gain access to the top side of OV-102 left wing. Upon completion of his work, he attempted to extend the platform back to its normal (closed) position. When the platform was approx. Six to eight inches from being in place, the rivets on the hinge failed causing the platform to fall on the orbiter. All hinge platform mounts need to be secured by welds or bolts and lock washers. The present practice of securing the hinge mounts with pop rivets is not adequate to support these platforms. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
69 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Explosion Proof AC Connectors |  | An explosion proof connector inadvertently faulted, causing an arc flashburn to the technicians' eyes. | Develop a test plan to study these connectors to determine the useful life expectancy (MTBF); then replace them before a more severe mishap occurs. | KSC | 03/26/1992 | Employees were checking for correct phase rotation on cross-hinds AC receptacle. One employee attempted to manually twist a receptacle with a screwdriver. During this action the receptacle faulted either phase to phase or phase to ground. This electrical fault caused an arc flash burn to both employees' eyes. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
66 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Dewar Vent Plumbing |  | Oxygen frozen in the vent line of the liquid helium dewar caused the dewar to become overpressurized and rupture. | Ensure all dewars are designed and fitted with valves designed to be used in systems utilizing vacuum pressures during operation. | KSC | 03/26/1992 | A liquid helium dewar used to service payload experiments ruptured and damaged ceiling tiles and a copy machine. In order to service the payload experiments, the dewar converts normal liquid helium to superfluid helium. During this process, air was ingested into the vent line through a valve stem. The ingested air froze, forming a solid blockage. The failure analysis of the liquid helium dewar revealed that 4 of the 8 valves used in the system were not designed for use in vacuum systems. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
68 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Unprotected Auxiliary Light Sources |  | Using an unprotected external high-intensity lamp for illumination above sensitive flight hardware resulted in damage when the lamp exploded. | Lead engineers should approve only protected light sources when there is a potential for damage to flight hardware. | KSC | 04/04/1992 | The Hopkins University Telescope (HUT) experiment was being aligned in the operations and check-out building using a bright light that had been obtained from technicolor government services. After approximately two hours of use without incident, the light bulb shattered, with pieces falling into the HUT experiment, causing contamination. Alignment of the HUT was not a scheduled activity at KSC. Therefore a light source was not furnished with the experiment. Data recorded at KSC indicated that the HUT was not aligned to the cruciform as expected and that a light source would be required. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
83 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Portable Purge Unit (PPU) Exceeds Recommended Noise Levels |  | A noise survey performed by the BOC industrial hygiene office revealed that the noise level of the PPU when operating exceeds the recommended 85 DBA. | Ensure the operations instruction document requires the use of hearing protection prior to start up of the PPU. | KSC | 05/08/1992 | The portable purge unit when operating, exceeds the recommended 85 DBA. Reference is made to noise hazard survey accomplished by BOC industrial hygiene. The noise level closer than a perimeter of 30 feet exceeds the allowable 85.0 DBA as established by the NASA Hearing Conservation Program. The DBA level near the unit ranges from 91.0 DBA to 99.6 DBA. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
80 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | SRB Holddown Stud Detensioning Operation |  | Failure to fully engage the puller bar prior to detensioning a holddown post, resulted in failure of the puller bar socket-to-holddown post threads. | Include a requirement in the OMI to take a measurement verifying that the puller bar is fully engaged prior to start of detensioning operation. | KSC | 05/22/1992 | During detensioning operations of a holddown post, while pressure of approximately 8K to 10K lbs was being applied, a loud "bang" was heard. Pressure on the tensioner fell to zero. It was later determined that the loud "bang" was the result of thread failure between the puller bar socket and the SRB holddown stud. With only 8 threads engaged, the shear stresses increased to 96,000 psi, as compared to 98,000 psi shear strength of the stud. Examination of the holddown stud revealed that 8 threads sheared on a 135 degree circumferential segment of the holddown stud. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
79 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | LH2 Flow Test at the LETF |  | Post mishap troubleshooting disclosed that the hazardous GN2 purge orifice at valve A89406 was blocked resulting in over-pressurization of the system. | Provide a pressure relief valve in this area of the system. | KSC | 05/20/1992 | During preparation for LH2 flow test at the LETF, a section of line was inadvertently over-pressurized, resulting in a protective cap being blown approximately 350 feet away. Post- mishap troubleshooting disclosed that the hazardous GN2 purge orifice at valve A89406 was blocked by corrosion and foreign contamination. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
82 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Dynatube Leak Checks |  | Inadvertent actuation of the ullage valve resulted in a valve burst disk failure and oxidizer vapor release. | Put indications in the operating instructions of exact operation end point, and require safety buy-off to ensure compliance. | KSC | 05/08/1992 | While dynatube leak checks were completed, manifolds were vented to ambient pressure. This allowed thrusters to leak. After the third flow, engineer positioned ullage valve (V4) to closed, this caused a pressure spike that ruptured the valve burst disk. The engineer was unaware of the failure, which was found during subsequent testing and data review. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
81 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Ground Wire Connections |  | Failure to connect elevator car ground wire in the machine room controller resulted in injury to personnel. | Train technicians to check for and establish a path to ground prior to and after maintenance operations. | KSC | 06/01/1992 | A General Contractor, was in the process of installing a hydraulic elevator at the centaur payload operations control center, (CPOCC) Phase I, Cape Canaveral Air Force Station, when a technician was electrocuted. The electrocution was caused by the victim's own failure to follow safe grounding procedures. For some unknown reason the victim failed to connect the ground wire in the machine room controller. The victim was familiar and educated to the proper safety precautions. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
107 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | LH2 Leakage at the 8" T-0 Flexhose QD/Interface |  | Lack of adequate LH2 Leak detection at the 8 inch T-0 flexhose QD/interface could result in fire. | Design/install a new leak detector sensor console to accommodate additional leak detectors. | KSC | 08/19/1992 | The 8 inch T-0 flexhose connects the tail service mast (TSM) with the LH2 carrier plate. Due to mechanical design the interface connection is very poor. The LO2 interface is identical and has experienced leakage in the past. Undetected leakage could cause a major fire resulting loss of life or vehicle. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
105 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | OMS Engine Nozzle Cover |  | Lack of a preventative maintenance program for the OMS engine nozzle covers resulted in a "close call" when the covers' holding clamps failed. | Evaluate OMS engine nozzle cover holding clamps to determine whether redesign or preventative maintenance should be implemented. | KSC | 08/17/1992 | During orbiter lift to vertical in the vab transfer isle between high Bays 1 and 2, the right hand OMS engine nozzle cover fell approximately 15 feet to the floor. The cover suffered enough damage to prevent it from being reinstalled. The cover was found to have three holding clamps that were probably defective on installation at the OPF. The left hand cover was inspected and several loose clamps were found and were tightened. Safety gave the ok to continue the lift without the cover. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
106 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Radiographic Inspections |  | Heat from hot weather caused the tape used to secure a tubehead assembly to soften allowing the tubehead to fall, resulting in a "close call". | Update documentation to require technicians to use rope, web straps or something of that nature in addition to tape to secure the tubehead assembly. | KSC | 08/18/1992 | Technicians were performing radiographic inspection of the insulation area in the atlas stage thrust section utilizing a 100KV machine. The tubehead was placed inside the thrust area taped into position and exposures were made to the outside. The tape failed to hold the tubehead and it slipped down 6-8 inches hitting a threaded area on a strut. There was only visible damage to the top of 2-3 threads. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
104 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Pressure System Maintenance |  | Work authorizing document failed to include instructions/work stops to verify that there was no pressure on the system; a "close call" resulted. | System engineers should update work authorizing documents to include verification of zero pressure on systems prior to making repairs. | KSC | 08/14/1992 | Performing work on S70-0613-00-001-0120 to change improperly sized flex hose restraints. When attempting removal of flex hose, gaseous nitrogen was released due to a partially opened valve in the system. Isolation valve A102736 on the F70-0014 panel was closed to stop the gaseous nitrogen flow to the flex hose. The gaseous nitrogen contained small quantities of N2H4 vapors. The work authorizing document did not contain instructions or work stops to verify that there was no pressure on the flex hose. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
115 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Payload Bay Door (PBD) Opening/Closing Operations |  | The "C" frame support hook and support jack dowel require manual manipulation and experience interference during PBD opening/closing operations. PBD damage may occur due to excessive forces incurred on it by jacking up PBD until its weight forces "C" hook to engage with support jack dowel. | Redesign the "C" frame support hook/support jack dowel to engage/disengage smoothly with use of only jack to raise/lower PBD jack support dowel. Modify PBD support jacks to allow smooth engagement/disengagement of "C" frame support hook during PBD opening/closing operations. | KSC | 07/27/1992 | During OMI V9023.F operations, the L/H payload bay door was noticed to have a slight upward bend in it due to excessive force placed on it through the L/H AFT PBD support jack. The aft half of the L/H PBD was raised eight to ten inches higher than the position of the PBD forward segment. An interference problem occurs when trying to insert/remove the "C" frame support hook from the support jack dowel. The interference problem requires the use of more than one technician to force the "C" frame support hook on and off the support jack dowel. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
113 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME) Vertical Installer |  | Lack of a preventative maintenance program for the vertical installer resulted in failure of the installer to maintain control over the SSME. | Develop and implement a preventative maintenance program for the SSME vertical installer. | KSC | 08/25/1992 | The SSME vertical installer is used to position the engine for installation and removal. Failure of this equipment to maintain positive control could lead to unexpected movement. During visual inspection of the air piston and bore of the vertical installer, it was discovered that the air piston had a scored landring. This condition occurs when the piston sticks in the cylinder (due to lack of lubrication and/or foreign material in the cylinder). Pressure then builds up until the piston breaks free. When the piston breaks free it can travel to the stops with enough momentum to cause sudden uncontrolled movement of the engine. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
114 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | The Digital Computer Unit Memory Loader |  | Inadequate grounding of the digital computer unit (DCU) memory loader can cause electrical shock injury to personnel. | Update OMI to include a ground verification test of the DCU memory loader prior to beginning operations. | KSC | 08/24/1992 | The memory and registers of the main engine controller digital computer unit interface must be loaded and read and must provide discrete controls and status indicators compatible with a punched tape reader and teletypewriter interface for automatic program loading. Inadequate grounding of the DCU memory loader (i.e., Ground cables not connected, connected improperly, or in deteriorated condition) could result in electric shock injury to personnel. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
112 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | LH2 Vent Line Valves |  | The LH2 vent system valves are elevated 8 and 10 feet above ground with no safe access provided. | Design and install permanent safe access platforms. | KSC | 08/26/1992 | The LH2 vent system valves are located in the flare stack area of Pads A and B. The valve control handles are elevated between 8 and 10 feet above ground. Operational personnel are frequently required to climb up on the 12", 14", and 18" vent lines to operate the valves. The use of safety belts/harnesses is not practical in this situation since the tether-off point is not available. Also, use of a pipe as a work platform is not in keeping with good safety practice. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
116 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | External Tank (ET) and Solid Rocket Booster (SRB) Demating Operations |  | Improper installation of support brackets creates insufficient clearance between ET and SRB's during demating operations. | Update OMI to reflect correct support bracket installation, including caution of clearance limitations if improperly installed. | KSC | 07/28/1992 | While demating the ET from the SRB's during OMI S0033, TPS foam damage occurred on the +Y forward crossover area. Scraping noises were heard and interference was observed. The operation was stopped while a deviation to the OMI was written to allow north movement of the crane in an attempt to relieve the interference. The operation proceeded but foam damage was unavoidable due to insufficient clearance. This insufficient clearance was due to incorrect installation of support brackets caused by inaccurate OMI procedures. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
118 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Mobile Launch Platform (MLP) Air-arcing Operation |  | Hydraulic fluid, dripped by hydraulic pumping units onto floor insulation may be ignited by hot particles propelled into the area during air-arcing. | Design and install drain pans to catch and contain leaking hydraulic fluid beneath hydraulic components. | KSC | 07/30/1992 | During air-arcing operations under mobile launch platform-1 (MLP), a welder smelled smoke through the hole he was working on and found a fire in the floor insulation of compartment 16B. Investigation revealed that air-arcing under MLP-1 ignited hydraulic fluid that had accumulated in the floor insulation of compartment 16B. Hydraulic pumping units leaked hydraulic fluid onto the insulation for several years. Hot particles released by air-arcing blew into compartment 16B as the welder penetrated the MLP bottom panel, and the fluid ignited. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
117 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Helicopter Hydraulic Line Chafing |  | Vibration during helicopter rotor operation may cause shortened hydraulic lines to become rub-fatigued/chafed at the spacer block contact points. | Periodically inspect flight control lines and spacer blocks for chafing and replace as necessary, ensuring that proper size lines are used. | KSC | 07/29/1992 | Immediately after becoming airborne at the SLF, the pilot of a KSC NASA helicopter noticed a failure in the No.1 hydraulic system (which supports helicopter flight controls). The loss of this system is an emergency. An inspection was conducted on the hydraulic system which revealed the line was approx. 0.5 inches shorter than required for optimal operation. Due to the curvature of the line passing through the spacer block, the line was not seated flush in its hole. The spacer block, with rotor vibration, caused the hydraulic line to experience strand separation, resulting in a puncture. |  | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 06/02/1994
93 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Loose Access Door Reporting and Securing; Contamination Air Plenum Access Door Hinges |  | Hinged access panels frequently lose structural integrity near the hinge line and may break off. Pop rivets used to secure access door hinges frequently work their way out leaving the door and hinges dangerously loose. | Access panel hinge regions that show excessive wear should be repaired upon discovery. Replace all access door rivets with plate nuts and screws. In addition, adding a safety chain/lanyard would further increase the safety margin. | KSC | 07/29/1992 | An access panel located at the aft end of the orbiter just right of the rudder, broke loose from its attaching hardware and the contamination air plenum. The access panel fell and hit the orbiter maneuvering system (OMS) pod handling fixture below. The access panel did not touch the vehicle or the OMS pod. OMS pod removal operations were in progress when the door fell. The door started working loose approximately three weeks prior to the incident, and a trouble call was made. Blue tape was found on the door edges except for the hinged side. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
92 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Spent Booster Segment Handling Operation |  | Determining the center of gravity of spent booster segments prior to a lift operation is very difficult, often allowing dangerous conditions to exist. | Design a handling sling device that will self-adjust to the load as it is lifted and keep it steady throughout the lifting operation. | KSC | 07/28/1992 | During forward center segment on-load to rail car for transport to the furbishment facility, the segment began to slide out of the confines of the handling sling. Approximately 90% of the segment was suspended 10' to 15' feet above the rail car when the aft end of the segment slipped out of the sling, coming to rest on the rail car. The forward end of the segment stayed suspended approximately 10' above the rail car. No damage to the segment was noted and the rail car received only three scratches by the handling ring. The instability of the segment is due to the difficulty in determining its center of gravity. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
91 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | External Tank Electrical Components |  | Inadvertent connection/disconnection of ET electrical components with power applied, could cause sparks, damaging flight hardware or injuring personnel. | Verify and ensure all connectors meet MIL STD with shielded pins on male connectors to preclude personnel contact. | KSC | 06/18/1992 | Potential ignition of SRB due to possible arcing at switch or relay contacts or at circuit connections due to inadvertent connection/misconnection, is controlled by design. Connections are connected within the intertank by electrical plugs and receptacles, which are secured by threaded sleeves. Power and return lines are not routed through adjacent pins on the same connector. The connector dielectric is rated at 1000 VRMS at 60 Hz. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
94 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Thruster Purge Operations |  | Failure to require a specific hose route resulted in a liquid trap being inadvertently formed causing liquid MMH to leak from a thruster nozzle. | Update operational procedures to include a requirement to ensure proper hose configuration and routing prior to beginning purge operations. | KSC | 07/30/1992 | During removal of the purge adapter from thruster R4D, liquid MMH was observed leaking from the thruster nozzle. When the leak was discovered the OPF high bay hypergolic exhaust fans were actuated, the high bay evacuated, and fire and medical support were requested to stand by. The leaking MMH was caused by a liquid trap present in the fuel suction hose. The trap was formed by excessive hose length, which was routed to the next level above, then down to the purge adapter. The routing and hose length was left over from a previous operation on the left side of the orbiter. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
95 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | OPF Extendable Platforms |  | Failure to measure and verify adequate clearance, prior to platform extension could result in damage to orbiter thermal protection tiles. | Review platform extension procedures to ensure verification of ample clearance prior to extending platforms. | KSC | 07/31/1992 | Technicians were in the process of extending platform 10-2 in OPF HB-1. After extending the platform about 3 feet, the observer noted that the platform would not clear the body flap and signaled a "halt." Before the platform could be stopped, it contacted two tiles, damaging them. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
96 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Lift Operations Utilizing a Hydraset or Dynamometer |  | Develop procedures that require the use of hydrasets and dynamometers when lifting unknown amounts of weight. | Review platform extension procedures to ensure verification of ample clearance prior to extending platforms. | KSC | 08/03/1992 | Replacement of the upper floating beam forward roller support shaft was in progress to eliminate a stress corrosion concern. The 5-ton bridge crane and a sling were being used to lift the Pad B PGHM side 2 upper floating beam Z bar off of the Z roller when a small block with two 5/8" bolts apparently sheared, allowing Z Bar to travel up, contacting a portion of the upper floating beam causing the web strap to be cut. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
99 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | APU Fuel Isolation Valve Assembly |  | Failure to properly package an APU isolation fuel valve when it was removed from the APU fuel system resulted in a close call. | Revise/update standard practice instructions (SPI) to include bagging and tagging of components exposed to hypergols prior to transporting them. | KSC | 08/06/1992 | An APU hydrazine isolation valve assembly was removed and sent to the shipping section of logistics without being properly packaged for safe handling. In addition, there was no Q.A. check sheet and no decontamination tags with safety buy-off as being sniffed at zero parts per million. There was a conditional decontamination tag with the part indicating that it was from a fuel system, and conditionally decontaminated but absorbed or trapped fuel could out-gas. The OPF was called for safety and technical support to come and check out the valve; the valve tested positive for hydrazine and was immediately safed. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
97 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Oxygen (O2) Meter Installations |  | Lack of safety procedures to document the presence of an O2 meter and constrain movement of the OMS pod resulted in a close call. | Add a safety call-out to the wad authorizing installation of an O2 meter in flight hardware, constraining movement of hardware with meter installed. | KSC | 08/04/1992 | During rotation of the L/H OMS pod (LP04) an O2 meter was heard rolling inside the pod. The pod was being raised to a vertical position per V5016. Also a "light thud" was heard during the lift. The lift was stopped but it was determined that it would be difficult to remove the meter while it was in this position. The pod was lifted to the vertical position and then the meter was removed. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
98 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Displacement Leak Detector |  | Failure to require tethering of a flow meter used to perform leak checks resulted in damage to the orbiter when the meter fell and hit the orbiter. | Add handles and tethering aids to the flow meters prior to use in or around the orbiter. | KSC | 08/05/1992 | A technician was performing leak checks at ports on the right side of the orbiter (OV-099) using a displacement leak detector. The tygon hose became tangled and the leak detector fell and hit the side of the vehicle damaging seven tiles. The detector was damaged when it finally hit the floor. The bay manager, safety, and the operations desk were notified of the incident, and the area was cleaned of spilled fluid & debris. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
102 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | High Pressure Shutoff Valves; Vacuum Pump Isolation Valve |  | Failure to establish a preventative maintenance program for two 6000 psi shutoff valves resulted in a close call when they began leaking Failure to use valves capable of withstanding system pressures resulted in a "close call" when a valve exploded. | Establish a preventative maintenance program for components installed in critical high pressure systems. Ensure that any isolation valve used in a pressure system can withstand the highest pressure of the overall system. | KSC | 08/11/1992 | A vacuum pump isolation valve burst at the Pad B high pressure gas storage battery. The cause of the incident has been attributed to the seepage of pressure from the wheel valves after they were turned off as part of a safing operation. The wheel valve o-ring does not always seat properly. Normally this would not affect the remainder of the system, the seepage pressure would be confined. However, when the vacuum pump was connected to the system, the seepage pressure (1500 psi) was greater than the design capacity of the vacuum pump isolation valve and thus overpressurization occurred. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
101 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Proof Load Test Fixture |  | Lack of a safety cut-out switch on the proof load test fixture resulted in a "close call" when a "D" ring was distorted (over pulled). | Modify system by adding a safety cut-out switch to prevent over loading any fixture. | KSC | 08/10/1992 | The proof load test operator installed a 3 leg sling H77-0235 in the tensile machine to proof load test a "D" and/or an "O" ring to 72,000 lbs and 52,000 lbs. The tensile puller pump motor stopped and the operator shut down the machine immediately and discovered tensile puller over pulled the "D" ring, deforming it, also distorting 3 pins in the tensile puller. The "D" ring was distorted beyond a salvageable limit. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
100 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Silver Zinc Battery |  | Use of batteries that have not completed qualification testing caused employees to receive caustic electrolyte exposure to their hands. | Institute requirements that will prevent the use of batteries that have not completed qualification testing. | KSC | 08/07/1992 | Two employees received caustic electrolyte exposure of hands during removal of two batteries from containers for installation in the ET. Installation was to support OMI S0008. Immediate cleanup procedures were initiated and area cordoned off. Personnel contamination was neutralized and employees reported to medical facility for evaluation. Batteries were relocated to the battery lab. Batteries are of a new design still under qualification testing. Four batteries had been activated, two were installed on the SRB's, the two ET batteries were maintained at ambient temperatures until the time of the incident. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
103 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Draeger Pump |  | Failure to secure/tether a draeger pump during toxic vapor checks resulted in a "close call" when the pump fell, striking the orbiter. | To ensure continued tetherability, provide a permanently attached tether for the draeger pump. | KSC | 08/13/1992 | An engineer was utilizing a draeger pump to perform toxic vapor checks on A/C motor valves on the 207' level of the rotating service structure. When the engineer attempted to retrieve protective apron from the platform, the draeger pump was pulled from the platform and fell, striking the orbiter's FRCS blanket area and landing on the 193' Level. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
87 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Payload Retention Latch Assembly (PRLA) |  | Improper jumper procedures during testing cause shorts or cross connection of live 120 volt and 28 volt electrical lines, damaging orbiter interfaces. | Design a status tester and jumper verification device to ensure proper jumper connections of the PRLA prior to interfacing with the orbiter. | KSC | 06/16/1992 | OMRSD S073A.90 thru .230 requires verification of voltages, phasing, and talkbacks to the orbiter. Present talkback verification method for the payload retention latch assembly (PRLA) involves extensive "hot" pin jumpering during testing using a 79K07833 breakout box and test leads. Improper jumper procedure by inserting a jumper at an incorrect location could result in inadvertent shorts or cross connection of live 120 volt and 28 volt electrical lines. This improper procedure could cause PRLA electrical system damage, orbiter interface damage and/or electrical shock/personnel injury. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
84 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Environmental Control System (ECS) Purge of Orbiter Compartments |  | Inadvertent closure of the vent doors during environmental control system (ECS) purge of orbiter compartments will result in over-pressurization. | Require aproprieate operations instructions to verify that all orbiter vent doors are in the standard purge configuration prior to start of venting. | KSC | 06/09/1992 | The OPF environmental control system (ECS) supplies conditioned air through ducts to the orbiter to purge and pressurize the forward/aft compartments and the payload bay. Over-pressurization could occur during ECS purge if the ventdoors are closed. No automatic monitoring and/or control exists to preclude simultaneous application of ECS purge air while all orbiter vent doors are closed, or to automatically relieve excess pressure under these circumstances. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
86 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Maintenance of Environmental Control System (ECS) fans |  | Inadvertent actuation of ECS fans S1 and S2 at the payload changeout room (PCR) during maintenance will cause injury or death of personnel. | Add a requirement to the operations instruction manual requiring the technicians to lock out electrical power prior to beginning maintenance. | KSC | 06/15/1992 | The fans are located on the 107 foot level of the rotating service structure (RSS) and controlled from the computer console for ECS in the PTCR. The circuit breakers providing power to the fans are located in the hoist room on the 207 foot level of the RSS; therefore, there is no local control. When maintenance personnel are working on the fans, it is possible that someone could re-apply power to them. Also, if local switches were located immediately outside the locked fan rooms, should a problem arise with the fans that generated excessive noise, smoke, etc. They could be shut down by personnel and reduce damage. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
85 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Lifting Portable Purge Units |  | Lifting portable purge units (PPU) has caused cracks and damage to operating components which result in damage to an orbiter system. | Redesign lifting sling mechanism to prevent stress from being applied to the PPU's operating components during lifting operations. | KSC | 05/08/1992 | The portable purge units are lifted on and off the MLP. The existing lifting sling design induces stress into the unit's operating components and overstresses the unit's lift points. Cracks are present on the lifting lug plates and elongation of the lifting lug holes has occurred. Failure of these components could result in damage to ground support equipment (GSE). |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
90 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Radio Communications During SCAPE Operations |  | Loss of radio communications during SCAPE operations has resulted in injury to personnel. | Ensure all personnel involved in SCAPE operations have backup radio communication systems available prior to starting the SCAPE operation. | KSC | 06/18/1992 | Personnel in SCAPE are required to have portable backup communications. GP-1098 requires using the buddy system. Also, in the event of loss of RF communications, two people must be designated to observe each other's safety when in a dangerous situation. The system requires a visual contact and a proximity that allows each buddy to help the other in an emergency. When and if communications are lost, the operation shall be terminated immediately and will not resume until communications are restored. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
88 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Weather Protection System |  | When the -Y curtain wall is extended with the -Y strut in any position except fully extended, the wall could contact and damage the STS vehicle. | Design redundant interlock system to ensure the -Y curtain wall is fully retracted and locked in its support frame prior to moving the -Y strut. | KSC | 06/17/1992 | Extension of the -Y curtain wall with the -Y strut in any position except fully extended, the curtain wall could contact the STS vehicle or the RSS structure. This can result from human error or human error coupled with mechanical failure of the key-lock and interlock valves. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
89 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Structural Integrity |  | During launch ice may be dislodged by vibroacoustic or aerodynamic forces and impact the orbiter's windows or TPS with enough force to cause damage. | Ensure all lines are maintained with proper insulation and all surfaces are visually inspected for excessive ice build-up prior to clear for launch. | KSC | 06/15/1992 | During launch and ascent, ice from the ET, SRBs, and orbiter may be dislodged by ignition vibroacoustic or aerodynamic forces and impact the orbiter windows or thermal protection system (TPS) with sufficient force to dislodge TPS or damage windows. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
123 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Loads Imposed on Stabilizing Frame During Mate/demate Operations |  | Excessive loads may be imposed on the stabilizing frame assembly while hoisting during mate/demate operations. | Maintain crane lift cables vertical and sling assembly level to prevent excessive loads imposed on stabilizing frame center segment. | KSC | 08/19/1992 | The H70-0743 sling assembly consists of a forward and aft spreader beam assembly connected together by a segmented stabilizing frame assembly. With the two mobile crane concept, the sling assembly is used to lift and demate the orbiter to the shuttle carrier aircraft. At the contingency landing site, the two mobile crane concept is used with a 800-ton T-C 4000 truck crane for the aft lift and a 250-ton link belt for the forward lift. Visual observation must be maintained at all times during hoisting operations due to extremely limited clearances between the orbiter and facilities. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
119 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Solid Rocket Motor (SRM) Segment and Handling Ring Mating |  | Documentation lacking cross references between serial numbers and model numbers may result in inadequate configuration or missing hardware. Improper work authorization contributed to the unauthorized removal of six attachment bolts from the SRM aft segment lifting bracket. | Implement documentation to allow work to be traced to hardware serial numbers and personnel performing the task. Revise documentation to include hardware inspections and to correct discrepencies for all transportation support equipment transferred. | KSC | 08/10/1992 | On September 25, 1987, The solid rocket motor (SRM) aft segment was being mated to the aft segment handling ring in the H77-0386 stand. The SRM segment and handling ring assembly was hoisted from the stand and moved to the breakover beam. The handling ring was mated to the breakover beam and the SRM segment was tilted to the horizontal position and placed on the rail car. At this time it was noticed that a total of six bolts were missing from the SRM end-ring assembly. It is unknown when or who removed the bolts. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/02/1994
121 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Vehicle (OV) Hydrogen (H2) Tank Removal |  | Cranes used to remove slack and transfer loads from tank struts to a ground support equipment lifting fixture may cause a momentary vertical overload. | Update OMI procedure to utilize hydraset units (in place of cranes) during transferring of loads to avoid overloading tank assemblies. | KSC | 08/18/1992 | During removal of the H2 tank from the OV-104 mid-body, a crane was used to take up the initial cable slack and transfer the load from the tank struts to the GSE lifting fixture. The move director called for a crane movement of "up at 1 in/sec" and the crane controller relayed the command to the crane operator. The actual lift rate was on the order of "up at 3 in/sec" and a momentary vertical load of 800 lbs was applied to the tank assembly. This load was immediately reduced and the tank bolts removed. The normal transfer load is made up of a 150 lb tank lifting fixture and a 235 lb tank weight. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
120 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Liquid Tanker (LT) Liquid Level Indicator (LLI) Reliability, Float Assembly Movement, and Float Assembly Specific Gravity (SG) |  | Shocks/vibrations induced into a magnetic liquid level gauge may affect the position of individual flag indicators and lead to erroneous readings. Fluid contamination may cause a restriction of the float assembly movement within the chamber, leading to an inaccurate reading. Fluid in the LT having a SG which is less than the float assembly is weighted for, indicates a fluid level lower than actual, and may lead to a tank overfill. | Redesign flags to lock and remain stationary (until acted upon by external force) as fluid raises magnetic float to interact with each flag magnet. Filter all fluid loaded in LT's to eliminate particulate contamination which may collect on chamber walls. Install float assemblies weighted to a fluid SG of approx. 1.0 so fluid concentrations will register maximum level and avoid tank over filling. | KSC | 08/12/1992 | On July 13, 1988, hydrazine was being transferred from partially filled drums into LT-44. There were seven drums for a total of 343 gallons. Adding the 134 gallons in LT-44 resulted in 477 gallons - well within the tank's 500 gallon capacity. As the hydrazine was being transferred from the last drum, a mechanic saw liquid spray from the vent hose and immediately closed the vent and fill valves. After securing the area, mechanics reported that all the flags at the top half of the LLI indicated the tanker was full. This suggested the magnetic liquid level gauge's reliability is questionable due to erratic operations. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
122 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Slack Removal from Hoisting Sling |  | The speed associated with crane commands is a matter of operator judgement and may result in an overload to the instrument pointing system (IPS). | Utilize hydrasets to apply a desired load at a predetermined speed to the IPS during hoisting operations. | KSC | 08/17/1992 | Task leader started hoisting operation with a "slow micro" command to take up sling slack until 337 lbs was obtained. A joystick controls hoist movement which may be controlled at a low rate, but only by operator judgement. A switch energizes the hoist motor and disengages the brakes when depressed. If the joystick is in the null position when the button is depressed, load movement will occur with speed dependent on stick position when the brake is released. An overload at 900 lbs in the IPS resulted when "slow micro" was requested and the brake button was depressed with the joystick not in the null position. |  | N/A |  |  | Public | Not Specified |  | 06/02/1994
53 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Keyed Connector Mismating; Mating of Electrical Connectors in Areas of Limited Visibility; Kapton Wire Insulation Breakdown |  | During engagement, electrical connectors that are improperly aligned may mate inadvertently with an incorrect connector half. Technicians attempting to mate connectors in areas of restricted visibility can mismate connectors. Kapton wire insulation can breakdown and sustain an electrical arc, igniting the insulation and causing damage to associated harnesses and connectors. | Issue an alert describing the possibility of inadvertent electrical mating of differently keyed connector halves that are out of alignment. Revise connector procedures to permit greater visibility or redesign connectors to preclude inadvertent connections. Designers of future wiring harnesses should avoid using Kapton insulated wires. | KSC | 01/10/1992 | The primary cause of the Magellan mishap was the inadvertent mating of at least two pins of the spacecraft harness connector P2 to connector J3 of battery 1. The mismate of these connectors created an electrical short circuit within the J3 connector that resulted in electrical arcs and additional short circuits that, using the energy stored in the battery, produced damage to battery 1, connector P2, and the battery thermal blanket. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
54 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Excessive Release of Nitrogen Tetroxide (N2O4); Public Address Statements; Pinhole Leaks in SCAPE Suits |  | Failure of an OMI to require calculation of quantities of N2O4 to be released could result in loss of life or personnel injury. During hazardous operations (OMI V2197) public address statements were out of sequence with events and did not accurately depict conditions which were to occur. Maintenance for SCAPE Suits does not include checking for pinhole leaks, allowing SCAPE suit deterioration to go unnoticed, endangering personnel. | Revise OMI's to address the need for calculating estimated vapor release quantities and use those values in establishing an area clearing. Hazardous operations public address announcements should be tailored to specific hazardous operations. Establish a test program to accurately determine the integrity of protective suits after the normal maintenance recycle following each use. | KSC | 01/20/1992 | The nitrogen tetroxide (N2O4) vapor release, which occurred during a storage tank relief valve changeout, greatly exceeded the "one gallon quantity" specified in the task OMI V2197, sequence 03-014. Also, sequence 03-074 states, "total amount of commodity involved: 1 gallon." Post incident calculations estimated the total release to have been 28 gallons. The vapor cloud of N2O4 far exceeded the 700-foot clear area called out in the OMI. Unless the magnitude of the release is accurately predicted, the downwind clear area cannot be properly established and personnel may be endangered. |  | N/A |  |  | Public | Not Specified |  | 06/01/1994
55 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Quick Disconnect F.O.D.; Quick Disconnect (QD) Design; SCAPE Operations |  | Fuel contaminants can lodge between the poppet and dynamic head of a QD preventing leak-free closure. QD poppet and dynamic head may fail to actuate properly, allowing liquid to flow through the QD and exit in the release collar area. A design flaw in the quick disconnects provides an additional leak path, allowing liquid to flow through the QD and exit in the release collar area. SCAPE technicians need ready access to fire fighting equipment when working with hazardous/combustible materials. | Modify procedures to include testing for fuel contamination prior to flow through the system. Quick disconnects designed with positive seals in the release collar would reduce accidental leakage. Leaks detected during future hypergolic operations should be terminated prior to scuppers overflowing. Prior to beginning SCAPE operations, SCAPE personnel should prepare a fire handline (charged and layed out) nearby for emergency use. | KSC | 01/28/1992 | During servicing of the oxidizer on the forward reaction control system (FRCS), a ground half quick disconnect (QD) failed. The failure mode was such that an open flow path was created to the outside of the QD and 15 to 20 gallons of oxidizer (N2O4) flowed overboard prior to isolating the flow sources. The failure of the ground-half QD was attributed to an accumulation of iron nitrate lodged between the probe and the dynamic head. The presence of iron nitrate was traced to contaminated fuel. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
57 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Fuel Farm Fire Detection, Suppression and Alarm System; Fuel Farm Firex Deluge System Operations; SCAPE Van Personnel Protective Equipment; Communications During Hazardous Operations |  | Fire detection system high temperature detectors must be located near areas where conflagration is likely. The fire detection system high temperature detectors did not activate, resulting in no automatic fire suppression system activation. Lack of fire alarm activation boxes along the evacuation route could prevent egressing personnel from activating the system. During operation of Firex Deluge Systems, the deluge spray may miss the fire if high winds exist. SCAPE Van personnel were not properly equipped or prepared to take contaminated personnel onboard during a spill/fire mishap. Switching to an emergency channel (without monitoring the primary circuit) may prevent effective communication. | Fire service organizations should evaluate fire detector locations to ensure sufficient detector coverage. Fire service organizations should evaluate fire detector locations and assure that sufficient detector coverage exists in high activity areas. The fire services organization should install additional activation boxes along the egress routes or at the fallback area. Fire service organizations should relocate or add additional nozzles to provide coverage in all likely wind conditions. SCAPE Van personnel should be fully prepared to take contaminated personnel onboard during all phases of the operation. Primary communication channels must be monitored, even when switching to emergency channels. | KSC | 02/03/1992 | During the replacement of a faulty flodyne valve, a leak occurred which resulted in a spill of approximately 20 gallons of MMH. Several minutes after the spill was reported, spontaneous combustion of the MMH occurred. The fire detection system high temperature detectors (HAD's) did not activate, therefore, no automatic system activation or alarms occurred during the fire. The locations of the HAD's (roof beam mid-line, one at apex and one each half-way down on roof underside) are unlikely to detect fires occurring near the farm edges, where much of the hypergolic maintenance is performed. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
56 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Inadvertent Quick Disconnect (Q.D.) Nipple Separation |  | Lack of anti-rotational devices may allow Q.D. nipple to separate from the Q.D. when a technician attempts to remove the Q.D. cap. | Design and install locking anti-rotational devices to prevent inadvertent removal of fuel system Q.D. nipples. | KSC | 01/27/1992 | During hydrazine servicing of the left hand SRB tilt system, the fill/drain quick disconnect (Q.D.) nipple separated during cap removal, allowing the entire 3 1/2 gallon load to drain onto the MLP deck. The Q.D. nipple separation occurred because of nipple to cap thread seizure, caused by pressure build-up between the Q.D. and cap. Current design allows the possibility of Q.D. nipple removal while trying to remove Q.D. cap. The technician had no visual clue that the nipple was turning because of the scupper installation. The technician was drenched with hydrazine during the incident. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
33 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | External Tank (ET) Vent System Withdrawal Weight Securing Device |  | A withdrawal weight support failure during shock absorber maintenance may result in personnel injury/fatality and/or equipment damage. | Incorporate a removable withdrawal weight securing device that will prevent unintended downward movement of the withdrawal weight. | KSC | 09/17/1992 | The 1500-pound withdrawal weight for the ET LH2 vent line must be raised to access the withdrawal weight shock absorbers to perform maintenance. Personnel work directly beneath the withdrawal weight, held in place with a 125 psi air-operated winch and 5/8" diameter wire rope. The system design does not include a secondary means to secure the weight if the winch or wire rope fails, so workers shore the weights with pieces of wood or other available material that will brace the weights. The improperly used shoring devices could break under the load of the weights, causing injury to personnel. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
34 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Cryogenic Loading/Draining of the Main Propulsion System (MPS) |  | Cryogenic loading/draining operations may produce a leak/fire, resulting in loss of shuttle vehicle and/or loss of personnel life. | Minimize leakage by utilizing welded connections, pneumatic systems for controlling cryogenic valves, and purging system for valves flowing LH2. | KSC | 09/17/1992 | The main propulsion system's (MPS) LH2 system operations include the transfer of LH2 from the pad storage tank to the orbiter and pressurization of the external tank during drain operations. A leak/fire during cryogenic loading or draining operations may result in loss of vehicle and/or life. This risk remains active until shuttle liftoff from the fixed service structure, for a flight readiness firing, or for a countdown demonstration test. LH2 leaks may occur via structure/component failure, purge loss due to flow restriction (clogs, regulator/valve fails closed), or flow diversion (relief valve fails open, flexhose ruptures). |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
32 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Displaced Heating, Ventilating, Air Conditioning (HVAC) Controls |  | With displaced power controls, an inadvertant actuation of the HVAC system may result in maintenance personnel injury/fatality. | Provide a local means of controlling the start/stop controls and circuit breakers which provide power to the HVAC pumps and systems. | KSC | 09/17/1992 | The HVAC chilled water boost pumps are located on the 120-foot level of the rotating service structure (RSS). The start/stop controls and circuit breakers (disconnects) providing power to the pumps are located in the motor control center at the RSS 215-foot level; therefore, there is no local control. When maintenance personnel are working on the pumps, a possibility exists that someone could re-apply power. The start/stop controls and circuit breakers can not be locked out, physically, to prevent inadvertant actuation. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
35 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Unprotected NASA Standard Initiators (NSI) |  | NSI's are unprotected against excessive radio frequency (RF) fields during pyrotechnic operations/post-landing safing and may result in injury/damage. | Closely monitor pyrotechnic connection, testing, and safing operations, to ensure rf field levels are maintained within safety plan guidelines. | KSC | 09/16/1992 | NASA standard initiators (NSI) are used to ignite a charge of boron potassium nitrate pellets, which begin the solid rocket booster (SRB) ignition sequence. These pellets start a pyrogen igniter and its igniter motor flame starts SRB propellent burning. NSI's can not be protected against inadvertant detonation while in excessive radio frequency fields. The electromagnetic interference may cause a premature firing of a NSI, possibly resulting in personnel injury/loss of life and damage to flight hardware or ground support equipment. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
36 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Back Pressure Regulator |  | Failure of the diaphragm in the back pressure regulator of the FCSS, PRSD T-0 safing system could release GH2 in the vicinity of the orbiter. | Install an isolation valve upstream of the back pressure regulator, thereby allowing manual vent line pressure regulation. | KSC | 09/18/1992 | The T-0 vent support assemblies are mounted on the orbiter T-0 Interface to support controlled venting of PRSD tanks after landing. In the event of regulator diaphragm failure, GH2 or GO2 can vent to atmosphere near the orbiter through the back pressure regulators. Leaking GH2 could cause a fire or explosion. Leaking GO2 could contribute to failure of the diaphragm in the back pressure regulator of the FCSS, PRSD T-0 safing system could release GH2 in the vicinity of the orbiter. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
38 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Undetected GH2 Release in the OPF |  | Failure to establish controlled venting of PRSD tanks prior to exceeding tank relief pressures, could cause inadvertant venting and danger of fire. | Ensure all OMI's are updated to establish controlled venting at the SLF (or other safe area) after landing and prior to OPF roll-in. | KSC | 09/18/1992 | After landing and prior to fuel cell deactivation, PRSD tank pressures normally will increase. The GH2 pressure will vent from the right side of the orbiter when pressures reach approximately 290 psi. This venting has occurred during roll-in of the orbiter to the OPF and could cause a fire if an ignition source is present. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
39 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | SSME Oxygen Lines |  | Helium leak detector roughing pump failure during mass SPEC operation could cause contamination of SSME oxygen lines. | Design and install vacuum controlled isolation valves that will prevent contamination of SSME oxygen lines, in the event of loss of pump vacuum. | KSC | 09/18/1992 | The mass SPEC is used to leak check the SSME heat exchanger (HEX) coil, to evacuate the MPS fuel vacuum jacketed (VJ) lines and for external leak checks using the hand-held probe. The heat exchanger converts liquid oxygen to gaseous oxygen for pressurizing the shuttle external oxygen tank. The MPS fuel line vacuum jackets provide the insulation necessary to meet SSME pre-start pump inlet temperatures. If mass SPEC vacuum is lost for any reason (power loss or belt breakage) vacuum roughing pump oil may be sucked into the SSME heat exchanger (back-streaming) unless the hex is isolated immediately. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
37 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Vacuum Servicing Unit |  | Loss of GN2 purge to the vacuum servicing unit could result in fire or personnel injury | Design a GN2 pressure sensing safety interlock switch that will inhibit use of the vacuum servicing unit when GN2 purge is not present. | KSC | 09/18/1992 | The vacuum servicing units will provide the capability to evacuate the power reactant storage and distribution (PRSD) tanks and relief line. The unit provides a place for GN2 to accumulate, and an ignition source to ignite these gases. Loss of GN2 purge to the vacuum servicing unit could result in fire or explosion leading to flight hardware damage or injury to personnel. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
51 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Dry Well Transducer Installations are Susceptible to Inadvertent Removal; Disposal of Contaminated Waste |  | Adequate physical safeguards do not exist to prevent the inadvertent removal of dry wells/transducer installations from hazardous systems. Failure to test for hazardous levels of MMH within the sump tank, resulted in the release of contaminated waste water to the environment. | Design of dry well/transducer installations should be modified to preclude the inadvertent removal of dry wells from hazardous systems. SPC-wide publicity should be given to the requirements for proper hazardous waste disposal and testing as contained in SPI SO-O37(4)KV. | KSC | 12/27/1991 | A hypergol technician erred in the removal of a temperature transducer from a 3-inch hypergol line at the "Pad A" fuel farm, resulting in a major fuel spill and hypergol burns to himself. The installation design of the dry well and temperature transducer provides a means to remove the transducer from the system for replacement or calibration without having to "open" the fluid volume. The dry well installation design is inadequate to preclude an untrained technician or a careless technician from inadvertently removing the dry well from the hypergol propellant line by mistake. |  | N/A |  |  | Public | Not Specified |  | 06/01/1994
48 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | System Component Identification Tagging |  | System components are not all identified with find number tags, allowing for erroneous component selection during maintenance operations. | All systems operations and maintenance contractors should install find number tags on all components of configured systems. | KSC | 12/20/1991 | The Firex system components at the VPF are missing numerous identification/find number tags. These are used to identify components in procedures and work authorization documents when opening, closing and removing components is required. The lack of coordinated numbers between components and the maintenance instructions generated a confusing atmosphere and led the technicians to choose the wrong components. This action resulted in the erroneous activation of the VPF Firex water deluge system. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
52 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | The "Call Contractor" System; Complicated Platform Operations |  | The "Call Contractor" is often required to work with incomplete drawings & written instructions, possibly creating hazardous conditions. Lack of formal training for complicated platform operators and observers may allow some hazards to go unnoticed until a mishap occurs. | Prior to work start, provide the contractor with a list/drawing of critical items/safety issues and their significance to the system. Require all complicated platform operators to undergo formal training and certification. Safety should verify training is current prior to setup. | KSC | 01/02/1992 | The "Call Contractor" system utilized by the contractor MOD management has the least control of "how" a modification is performed. The "Call Contractor", utilizing "good construction practice", was given free reign in the method to accomplish the project. Drawings and instructions were incomplete. No formal briefings on associated hazards were held, allowing for unknown hazards to jeopardize the safety of the project and the workers. The working relationship between contractor MOD management, contractor DE, NASA DE, and the "Call Contractor" is not clearly defined and appears less than adequate. |  | N/A |  |  | Public | Not Specified |  | 06/01/1994
50 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Delta Wiring Harness Connectors and Installation |  | Wiring harness connectors of critical components must be capable of withstanding vibration induced stresses. Failure to protect wiring harnesses from abrasive surfaces and sharp edges of structural members will lead to wire damage caused by flight vibration. | Identify and implement improvements in the quality review, inspection, and testing of connectors in proportion to their criticality. Prior to future launches, perform megger checks of all critical wiring harnesses and inspect harnesses to verify quality of installation. | KSC | 12/24/1991 | Premature shutdown of the main and vernier engines occurred as a result of an electrical malfunction in the vehicle's power bus, specifically a short circuit to ground. A Mishap Board investigation concluded the most probable cause of the failure was flight vibration that induced mechanical damage to wiring insulation resulting in a short to ground. |  | N/A |  |  | Public | Not Specified |  | 06/01/1994
49 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Firex Deluge Valve Configurations |  | The OPF Firex deluge remote manual arming and firing valves do not conform to industry norms, allowing for misinterpretation of their configuration. | All Firex deluge system valves should be in accordance with industry norms and provided with specific open and closed position markings. | KSC | 12/23/1991 | The remote manual arming and firing valves are in the "on" position when perpendicular to the water lines, which is not the industry norm for hydraulic systems. This contributed to the OPF GSE technicians believing they were closing the valves by positioning them perpendicular to the water line when, in fact, they were opening the valves. This misinterpretation resulted in the activation of zones 1,2,3,4, and 5 of the bay 2 Firex deluge system. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
42 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Sneak Circuitry; Down Range Control Area; Electrical Ground Connections for Folding Fin Aircraft Rockets (FFAR); Corrosion of Dissimilar Metals |  | Use of a conductive lanyard to arm payloads having internal power sources may introduce a potential current path for a sneak circuit. Whenever a potentially "hot" rocket is on a launch pad, down range clearance must be assured. The current design of FFAR's does not provide a reliable electrical ground connection between the fins and the nozzle plate. Aircraft rocket launcher assemblies may produce a potentially dangerous galvanic current if dissimilar metals are used in fabrication. | Design arming devices to provide electrical isolation from batteries by using a non-conductive lanyard for the withdrawal cylinder. Require the down range impact area and air space to be clear of all unauthorized personnel and aircraft during all phases of live testing. Analyze grounding circuits and take appropriate action to assure grounds exist -- specifically, the grounding of the ignitor circuit. Design launcher assemblies to use materials that are not chemically reactive, or use insulating devices between dissimilar, reactive metals. | KSC | 12/02/1991 | The following mishap occurred during preparation of three mighty mouse rockets (2.75" FFAR) at the NASA Atmospheric Sciences Field Laboratory: The last step before arming the FFAR motors was to replace the activation plug on the payload. With the rocket in position in the launcher tube, the plug used during launcher loading was removed through an access hole in the side of the tube and another plug, attached by a lanyard to a pneumatic withdrawal cylinder, was inserted in the payload. While the worker was performing this lanyard insertion step, the rocket motor ignited and launched. Investigation of the mishap revealed the high probability of a sneak circuit causing the inadvertent firing of the rocket. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
40 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Space Shuttle Main Engine (SSME) Access |  | Post landing access to SSME's for installation of the ferry flight kit is inadequate and could cause personnel injury. | Redesign orbiter aft access platforms to provide greater security and more access to space shuttle main engines. | KSC | 09/18/1992 | Space shuttle system design necessitated clearance and weight constraints, which in many cases, made SSME access limited. Workarounds and temporary structures have been utilized by maintenance personnel with some success. However, there is still inadequate access to the engine area after landing for installing rain protection plugs or the ferry flight set. Injury to personnel or damage to equipment can occur as the result of actions required to perform post flight maintenance and ferry flight set installation operations. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
43 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Clamping Procedures |  | Vinyl tape may act as a lubricant, preventing the secure clamping of an object to a workstation, possibly resulting in damage to the object. | Ensure that any surfaces that are clamped together are clean and free of tape, tape adhesive residue, oil, dirt, or other lubricating elements. | KSC | 12/05/1991 | A mishap occurred when technicians did not follow the sequence of events specified in the PR disposition for assembly of the thruster and fixture. The T-shaped mounting fixture was secured with only one C-clamp to an access platform's kick plate that had vinyl tape on both sides. The C-clamp was improperly used to prevent rotation and the vinyl tape acted as a lubricant between the clamped surfaces. These conditions allowed the offset weight of the mounting fixture/thruster assembly to overcome the clamping force and rotate about the single C-clamp and fall. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
41 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Emergency Power-Down Procedures for Multiple Fuel Cells; Fuel Cell Helium Ingestion; Crew Module Fire Alarm and/or Electrical Component Activations; Vehicle Data Down Link |  | When emergency power-down procedures are being performed, ensure that an operating bus is the last one disconnected. Failure to maintain GSE helium pressure below vehicle reactant pressure when fuel cells are operating may result in FC degradation or failure. Orbiter fire alarm and electrical components operate intermittently and erroneously when main bus voltage is lower than minimum required. Vehicle data to the firing room is lost when fuel cell power down sequences are initiated with no vehicle ground power applied. | Configure operations and GSE design to minimize times when fuel cells are operating without redundant ground power. Institute a positive means of isolating the vehicle from GSE supplied fluids, by GSE design or procedural means. Instruct orbiter integrity clerks (OIC), electrical techs/space craft operators and operations personnel to monitor main bus voltage and alert test team upon occurrence of low voltage. Implement an obvious flag/color change on the data display indicating data has stopped updating. Maintain ground power to vehicle whenever possible. | KSC | 11/25/1991 | Fuel cells are connected to the orbiter power busses via a motorized switch. OMI emergency procedures for powering down fuel cells assume redundant ground power is connected to the orbiter and calls for only one disconnect sequence fuel cell 1, 2, then 3. The power to disconnect the FC is delivered through the same busses they are being disconnected from. During a multiple fc failure (i.e. FC 2 & 3) with no ground power connected, the OMI requires FC 1 to be disconnected first. Since FC 1 was the only one operating correctly and suppling the busses with power, switching it off first removed the power needed to disconnect the rest. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
44 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Electrical and Mechanical Equipment; Overhead Pipe Supports; Emergency Procedures for Critical Utility Systems; Utility Annex Emergency Power Shut Off Capability |  | Utility annex water lines routed above unprotected high voltage electrical equipment may rupture causing power outages and equipment failures. Pipes with less than adequate support will rupture or bend excessively when external forces are applied. Operations and maintenance instructions for critical utility systems must identify potential emergency conditions and provide emergency procedures. When there is no capability of shutting off utility annex power in an emergency, damaged equipment continues to operate without stability. | Provide splash guards or water resistant barriers for electrical and mechanical equipment subject to possible water damage. Place pipe supports within one foot of each change of direction and space the remaining supports to prevent excessive sag, bending and shear stress. Update OMI's for utility annexes and critical facilities, identifying emergency conditions and providing appropriate emergency procedures. Install local power disconnects at utility annexes for safing power during emergency situations. | KSC | 12/05/1991 | A painter in the utility annex stepped on a pipe, causing it to fracture at the interface of an attached valve. The pipe remained attached to the valve, but the leak sprayed water onto the motor control center located beneath the pipe, causing a short circuit in the switch gear and a subsequent power outage for several facilities. This power outage resulted in the suspension of test operations that were being performed on the hubble space telescope. |  | N/A |  |  | Public | Not Specified |  | 06/01/1994
46 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Assembly and Adjustment of Crane Components; Crane Load Charts; Calculating Crane Loads; Reporting Equipment Problems Across Contractor Interfaces |  | Improper assembly and adjustment of boom hoist brake releasing mechanism may allow the boom and load to lower rapidly and uncontrollably. Using improper load charts when determining the load radius will create a hazardous situation that may cause the crane to tip over. Neglecting to add the weight of heavy rigging and the weight of the crane load block will result in a miscalculated load. A crane with a history of problems, including "boom running", caused a mishap because the past problems were not properly reported. | Develop a checklist documenting the proper assembly and adjustment of all crane components as specified by the manufacturer and verified by safety. To prevent improper load chart usage, physically mount or attach the proper load charts in the crane's cab. Place warning placards in the crane and special instructions in the loadchart requiring all rigging weights to be included in load calculations. Develop a positive, enforceable system for reporting equipment problems across contractor interfaces. | KSC | 12/13/1991 | A 65-ton mobile crane was hoisting a 40,000 pound test weight from payload canister #2 to a flatbed truck. The test weight was 8 to 10 feet above the canister doors when the boom of the crane slipped, falling toward the canister and lifting the front wheels off the ground. The test weight contacted the inside of the canister door and slid inside the canister, damaging the side of the canister. One employee sprained his right foot as a result of the mishap when he quickly jumped from the canister door to avoid being hit by the crane boom. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
45 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Remotely Located Control Room Communications; Consistent use of Nomenclature; Purge and Vent Port Capping; Integrated Systems Maintenance |  | Remote location of control rooms creates a natural barrier to communications and observation of work. Inconsistent or misleading use of nomenclature that does not conform to the OMI may cause confusion for technicians as they perform OMI procedures. Technicians are so well versed in "good shop practice" that inadvertent capping has occurred to purge and vent ports. Unfinished PR's that require disconnecting wires to other systems create operations constraints which may be transparent to systems engineers. | Locate new control rooms within the facilities they service, centralizing the test team in one location for optimum performance. Review and correct orbiter and GSE displayed nomenclature to maintain consistency with OMI's. Educate all employees on the importance of communicating all problems and unusual occurrences during tailgate meetings or with a shop-wide awareness. Establish a procedure to notify system engineers that removal of electrical grounds will be a constraint to testing and system operations. | KSC | 12/10/1991 | The geography of KSC facilities does not lend itself to ease of team unity. The launch control center control rooms, from which systems engineers conduct tests, are a considerable distance from the OPF where technicians perform work on the vehicle. The remoteness of the two facilities impedes communications between engineers and technicians. As the program plans new control rooms and equipment, these new rooms could be located in the OPF between the two bays. Having the engineers in close proximity to technicians and the vehicle would improve the overall efficiency of orbiter processing. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
47 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | Mercoid Pressure Switch; Inadvertent Water Deluge Activation |  | Mercoid pressure switches are overly sensitive to system pressure fluctuations and may cause inadvertent activation (switch bouncing). Water deluge systems are unable to adequately absorb water line transients, thus jeopardizing the integrity of the valves & pump controller switches. | Protect systems that utilize mercoid switches from pressure transients to prevent inadvertent activation. Provide a means to attenuate pressure transients and fluctuations to assure the integrity of water deluge system components. | KSC | 12/19/1991 | The primary cause of the mishap was an activation (closing) of the fire pump mercoid pressure switch which prematurely started the fire pump. This produced transient pressures that exceeded the 2:1 mechanical advantage of the deluge valves, forcing them open. The switch activation was caused by potable water system pressure fluctuations external to the local facility. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
25 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Release of Toxic Hypergolic Fluids/vapors During Payload Processing |  | Unmonitored payload processing and propellant transfer operations may result in personnel exposure to toxic hypergolic fluids/vapors. | Monitor concentrations of hypergolic vapor prior to, during, and after all hypergol operations/perform GSE leak checks to minimize potential spills. | KSC | 09/04/1992 | Following its arrival at one of the paylaod processing facilities, a payload is removed from the transporter/container and installed in a test or assembly stand. Facility activities include propellant loading, installation of solid propellant motors, ordnance separation devices, and other explosive or hazardous items. After completing hazardous operations, the payload is transferred to the vertical processing facility and then to the payload changeout room. Leakage or spilling of toxic propellants is a real possibility during payload ground operations and may allow propellant residuals to accumulate in/on equipment/flight hardware. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
24 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Hydraset Remote Control Console Pressurized Flexhose |  | Disconnecting pressurized flexhose between k-bottle or facility GN2 supply and hydraset control console may damage equipment and/or injure personnel. | Update OMI to remove GN2 pressure by opening control valves and verifying pressure on k-bottle or facility supply, prior to disconnecting flexhose. | KSC | 09/04/1992 | The hydraset control console is a self-contained system for the storage, metering, and regulation of compressible GN2. The pneumatic system delivers pressurized GN2 to the accumulator of the hydraset hoist control unit, which controls load movement in small increments. The source for GN2 can be either facility or k-bottle supply. The design of the hydraset remote control console is such that high GN2 pressure may be present in the flexhose between the k-bottle or facility GN2 supply and the remote control console. Disconnecting the flexhose under pressure may damage equipment and/or injure personnel. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
23 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Payload Canister Manual Flow Control Valve |  | Moving the flow control valve from neutral while payload door speed control valve is in open/closed position may damage payload or canister door. | Install locking device on the flow control valve to hold neutral position until door speed valve is fully closed/locked upon desired door position. | KSC | 09/04/1992 | The payload canister consists of a canister shell and two cargo bay doors driven by air motors. The cargo bay door operations are controlled by a flow control valve with three positions (open, neutral, closed). If the door speed control valve is in the open or closed posititon and the flow valve is inadvertently moved out of neutral, the cargo bay doors will open or close. Unscheduled operation of the payload canister doors could result in personnel injury or damage to a payload or canister door. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
26 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Critical Gaseous Helium (GHE) Purge Operations |  | Failure/corrosion/clogging of critical hardware in fuel cell servicing service system panels may cause ineffective purge and/or explosion. | Redesign purge system to modify purge path and relocate interface with vent system to provide adequate purge capability. | KSC | 09/04/1992 | The launch operations area fuel cell servicing system (FCSS) LH2/GH2 system provides for the loading of LH2/GH2 to the orbiter at pads A and B. The LH2 FCSS low pressure sample panel and the fixed service structure FCSS GN2/GHe service panel are utilized for the helium sweep flow purge to the FCSS hydrogen vent stack. Three critical items are in the GN2/GHE service panel and two are located in the low pressure sample panel. Failure of a critical item will disable the sweep flow purge to the vent stack, which is performed prior to initiating hydrogen steady state venting from the dewar. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
28 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Extension of Orbiter Access Arm (OAA) |  | Failure of relay K41 or K44 will disable control of primary and secondary extend pilot valves and prevent extension circuit from being activated. | Design a redundant hardwire control of the primary and secondary pilot valves using individual relays to control each valve function. | KSC | 09/11/1992 | Failure of relay K41 to activate or relay K44 to deactivate will disable hardwire safing panel control of both the primary and secondary extend pilot valves A101409 and A101410. The command path for the hardwire safing circuits, which controls the orbiter access arm, runs through these relays. If relay K41 fails to activate or relay K44 fails to deactivate, the OAA would not extend. If a failure occurs, the hardwire safing system would not activate the extension circuit and emergency re-extension could not be accomplished. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
27 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Environmental Control and Life Support System (ECLSS) Servicing Console |  | Failure of ECLSS servicing console regulator could introduce gaseous nitrogen into astronaut's breathing supply. | Redesign the ECLSS GO2 panels to eliminate the use of gaseous nitrogen while supporting the flight crew breathing test. | KSC | 09/04/1992 | The G02 supply from the ECLSS GO2 servicing console can be utilized to feed oxygen directly into the astronauts' helmets in support of the flight crew breathing test during OMI S0017 (at T-4 minutes). The existing oxygen panel uses gaseous nitrogen as the regulator "push" pressure (6000 psig) to operate the ECLSS servicing console. There is a possibility of nitrogen intrusion into the oxygen feed line if a regulator failure occurs. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
29 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Installation/Removal of Access Platforms at Mate/Demate Device (MDD) |  | Loss of access platform control while raising/lowering from service position may cause platform to fall on orbiter, resulting in major damage. | Provide winch and cable arrangement for safely extending/retracting platforms from mate/demate device side access platforms. | KSC | 09/11/1992 | After the shuttle carrier aircraft/orbiter reaches its park position within the mate/demate device, the side access platforms, which parallel the major part of the orbiter fuselage, are lowered into service position to demate the orbiter. Flip down platforms are extended from the side access platforms to allow personnel to reach the 50-1/50-2 doors. ropes are used to lower the platforms to the orbiter and technicians have minimal control of the speed at which the platforms are lowered. A potential exists for a loss of platform control and subsequent orbiter damage/personnel injury. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
30 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Gaseous Nitrogen (GN2) Tank Lifting Operations |  | The lifting adapter prohibits tank from sitting flush in cradle due to a 1.8" tank boss extension, allowing boss threads to support total load. The strap securing the GN2 tank to the lifting adapter provides an inadequate securing capability during lifting operations. | Redesign/modify lifting adapter and cradle to relieve boss from supporting the total GN2 tank load during lifting operations. Design a more adjustable strap that will more effectively tighten around the tank for a more secure fit. | KSC | 09/11/1992 | During installation of the orbiter GN2 tanks, the H70-0649 lifting adapter is used to raise the GN2 tank from the orbiter processing facility floor to the orbiter payload bay. The adapter is designed for the tank to sit flush in the cradle, but its configuration allows only the GN2 tank boss threads to sit on the adapter cradle. As a result, the tank boss supports the total tank load. This "improper fit" condition contributes to the inability to properly secure the GN2 tank during lifting operations, possibly resulting in damage to the tank, the orbiter payload bay, and/or personnel injury. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
31 | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN | Musgrave, Lisa - 0000000000 : NO@ADDRESS.GIVEN |  | Maintenance of High, Exposed Equipment |  | Technicians working at high, exposed locations could fall due to a lack of secure footing/approved tie-off points for safety lanyard/harness. | Install permanent access platforms wherever possible for personnel safety during component servicing or mainenance of high, exposed equipment. | KSC | 09/10/1992 | Post launch checkout and semi-annual GOX vent arm maintenance requires technicians to service the GOX vent arm upper hinge and associated flexhoses. The GOX vent arm upper hinge cover panel must be removed to gain access to the hinge for inspection and maintenance. Once the hinge cover panel is removed, it must be maneuvered past the upper hinge support structure. The configuration requires technicians to perform this task at unprotected heights. Because there are no work platforms or approved tie-off points where a safety lanyard/harness can be attached, technicians are at risk of a 255-foot fall. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 06/01/1994
350 | Gussner, A - 0000000000 : NO@ADDRESS.GIVEN | Gussner, A - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Spacecraft Telemetry Degradation due to Antenna Multipath | After Galileo completed its second Earth flyby, communication signal levels received on Earth decreased and fluctuated unexpectedly. The cause was determined to be interference that was not detected during test because the test article was not consistent with the orbiter telecommunications functional requirements document. Recommendations involved use of concurrent engineering, verification of requirements compliance, updating of requirements documents based on hardware ECR's, post test evaluation of non-flight like characteristics, and assuring that hardware used for functional testing properly simulates the characteristics of the flight hardware. | Approval of hardware Engineering Change Requests (ECR's) which conflict with functional requirements documents, without concurrently updating the requirements documents, can result in subsystem functional testing which does not adequately simulate the characteristics of the flight hardware. | "Concurrent engineering" is required between requirements, design, fabrication and test engineering functions. Verification of requirements compliance must be performed. Requirements must be adhered to, changed to match hardware characteristics, or waived through the ECR process. Requirements documents should be continuously updated based on hardware ECR's. Post test evaluation of non-flight like characteristics is required. Hardware used for functional testing must properly simulate the characteristics of the flight hardware. | JPL | 11/11/1994 | After the spacecraft completed its second Earth flyby, communication signal levels received on Earth decreased and fluctuated unexpectedly. The cause was determined to be interference when the Radio Frequency (RF) radiation angle from the boresight of the Low Gain Antenna (LGA-1) to Earth exceeded 90 degrees causing the signal to pass through the High Gain Antenna tip sunshade. The tip sunshade is constructed of 9 conductive ribs and a circumferential wire supporting an RF transparent shade. Phasing of the direct signal with the signal reflected off the 9 conductive ribs of the sunshade caused multipath signal fluctuations that varied with the rotation of the spacecraft. Since the orbiter telecommunications functional requirements document stated that "the outer portion of the tip sunshade is RF transparent," the LGA antenna pattern tests used a totally RF transparent tip sunshade model, and multipath interference was not detected. Additional Keyword(s): RF Performance Verification Reference(s): ISA# 2125 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.1.1 ("Engineering Practices: Project and System Level Functional Verification and Validation - Planning") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 2.3 ("Introduction: Compliance Assessment") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.” | N/A |  |  | Public | Not Specified |  | 05/31/1994
322 | White, William - 0000000000 : NO@ADDRESS.GIVEN | White, William - 0000000000 : NO@ADDRESS.GIVEN |  | Radiation, Effect on Windows and Optical Instruments |  | Exposure to radiation results in the impairment of transparency of the glass in ports and optical instruments. | Use quartz glass with low content of impurities, and coat with cerium oxide to reduce radiation effects on glass. | MSFC | 05/28/1993 | Experience on the Soviet Space Station showed that long exposure to space radiation affects the transparency of glass and that this effect is reduced by using quartz glass coated with cerium oxide. | Soviet experience demonstrated the effectiveness of the recommended action. | N/A |  |  | Public | Not Specified |  | 05/28/1994
321 | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | Spring Actuated Deployables, Design Considerations |  | Spring actuators for deployables are susceptible to many single failure modes which must be considered in the design. | Provide the following features in the design of spring operated deploy mechanisms: redundant release mechanisms, guide provided for spring, spring and guide lubricated with low outgassing lubricant, few pivots (decreases static friction and lowers spring stored energy), spring stress no greater than 80% of the spring material yield stress damper incorporated into any high energy spring (decreases transient shocks which could damage sensitive instruments). | MSFC | 05/26/1993 | Data indicates that there have been several deployment failures which were attributable to inadequate design. | There have been fewer deployment failures since incorporation of the actions recommended. The specific figures were not provided in the back-up data. | N/A |  |  | Public | Not Specified |  | 05/26/1994
193 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Damage to Wind Tunnel Components |  | Unsecured equipment left in a wind tunnel during a test run can cause damage to wind tunnel components. | Modify the test operations checklist to require a pre-run tunnel walk through to verify compliance with all safety considerations and pre-operation procedures. | GRC | 01/20/1994 | The mishap occurred in the air drive section of a research wind tunnel. During an evening research run, a six foot stepladder was drawn into the wooden drive blades of the tunnel. The stepladder was destroyed and the wooden blades were damage. The investigating committee determined that the principal cause of the mishap was the unsecured stepladder left in the tunnel by day shift personnel who used it for inspection purposes. Factors that contributed to the mishap were: the distraction of tunnel operator/mechanic by other duties, inadequate checklist elements that would require verification that the tunnel is clear for operation, and no requirement for a pre-run tunnel walk through just prior to a test run. | Recommendations made by the review board have been approved by the director and procedures to prevent this mishap from re-occurring have been instituted. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 04/19/1994
228 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Vacuum Brazing Furnace |  | Vacuum chambers can inadvertently be overpressurized, causing damage to the furnace and injury to personnel. | Install pressure relief devices on vacuum furnaces to provide automatic venting above 700 torr, even though the furnaces are designed for vacuum service only. | GRC | 06/21/1993 | A new vacuum furnace was being checked out when it was inadvertently pressurized to much higher than one atmosphere of argon gas. The furnace door was held closed by 3 clamps designed to seal the door "o" rings while pumping a vacuum. Under pressure the door clamps failed. The door swung open, striking a person who was standing next to it. He was thrown to the floor and sustained a head injury. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
227 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Air Compressors |  | Mechanical controls on Brown-Boveri air compressor starter assemblies can become damaged, leading to extensive fire damage to the compressor motor. | Remove follower arm and walking beam assemblies from Brown-Boveri starters and use indicating lights to establish contactor status. | GRC | 06/21/1993 | A 500 HP service air compressor stayed engaged after a stop command was issued from the central control dispatcher after a test run. The motor came to an abrupt halt and started to burn, causing extensive damage. The primary damage occurred to the compressor motor as the coils were burned. Damage also occurred to the starter in the form of blown fuses and burned contacts. The cause of the mishap was a direct result of an inadvertently bent follower arm on the starter. When the central control dispatcher commanded the control circuitry off, the DC field was turned off but the starter stayed engaged. The angle of the bent follower arm allowed it to fall behind the walking beam assembly preventing the starter from disengaging. The running of the motor out of synchronism without field exitation caused overheating of the cage windings to the point where the motor started to burn. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
211 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Fluidized Bed Furnace |  | Electrical contactors on heater circuits can fuse shut unless a proper back-up design is incorporated. | Install an independent over-temperature control system using solid state electrical switch gear instead of a mechanical contact system. | GRC | 06/14/1993 | The furnace involved was a procedyne high temperature fluidbed furnace with an 1850 degrees F maximum operating temperature. The furnace medium consisted of 1000 lbs of an alumina sand and was set to idle at 1200 F overnight. During the run fluidized media was found to be spewing out of the furnace and running down a wall in the furnace room. During the following investigation the alumina sand showed signs of sintering that suggests overheating conditions in the range of 2000 to 2200 F. Cause of the overheating was found to be the main electrical contactor that had welded shut on 2 of the 3 legs allowing an uninterrupted supply of power to the furnace heater. Further investigation determined that a contributing factor to the mishap was the condition of the retort wall that contained a brittle fracture appearance and evidence of a stress failure rather than a thermal failure at meltdown. The retort failed as a result of the increased thermal stress, due to the continued power supply from the stuck electrical contact, and the inherent mechanical defects in the retort wall that was not able to withstand the 2200 F temperature. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
216 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Altitude Tanks Vacuum Pumps |  | Excessive oil consumption by vacuum pumps should be evaluated as a problem prior to adding oil to prevent overfilling the pump reservoirs. | Check oil level in vacuum pumps only after the pumps are pulled through or run to assure that all oil is in the reserviors and not in the inlet cavity. | GRC | 06/15/1993 | Before starting up vacuum pumps to lower the pressure in an altitude tank, the reservoirs of the pumps were checked for proper oil level. The levels were found to be low and about 5 to 7 gallons of oil were added to the reservoirs of each pump. The pumps were then turned on to start pumping against their isolation valves. When the valves were opened to the tank to allow high gas flow to the pump inlet, oil was discharged through the vent system to the roof of the building. Because of the pressure build up, an elbow in the vent line separated and spilled oil on the pump room roof and the parking lot next to the building. The investigating committee determined that a false reading was obtained when the oil levels of the pumps were checked prior to starting them up. The missing oil was in the inlet cavities of the pumps and not in the reservoirs where the oil level is measured. When the pumps were started, the excess oil was forced from the inlet cavities to the pump reservoirs, thereby overfilling them. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
309 | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN | Pennington, David - 0000000000 : NO@ADDRESS.GIVEN |  | High Intensity Discharge Lamps |  | Metal halide bulbs provide good illumination but require specific mounting hardware for operation. | To protect personnel and flight hardware, all metal halide bulbs should be covered with a lens assembly capable of withstanding the impact produced when one of these bulbs explodes. | KSC | 02/04/1994 | A metal halide high intensity light bulb in the O&C high bay ceiling inadvertently exploded. Glass fragments were spewed to the O&C high bay floor, which was clear of personnel and flight hardware at the time of the incident. The subject light fixture was inspected and cleaned of all debris. Metal halide bulbs are very bright and increase the amount of available illumination by 50%. The explosion of the metal halide bulb caused concern so the bulb's fragments were collected and sent to NASA's malfunction lab for evaluation. The malfunction lab observed discoloration of some bulb fragments. According to the lab the discoloration suggests that the lamp was reaching the end of its useful life. It is not known what the manufacturer's recommended life for these particular lamps is, but once they reach that particular number of hours, under continued use, they have an increased propensity to explode. In addition, the lab studied the interface area between the lamp bulb and the metal housing, no anomalies were noted. | Several O&C facility support personnel were interviewed regarding the exploding bulbs. One person said protective covers/lenses had been installed to contain the bulb fragments if one were to inadvertently explode. This person said he knew of at least one bulb that had exploded since the installation of the protective covers and said the bulb's fragments were contained with no problem. After contacting several more O&C facility support personnel, no other evidence of additional bulb explosions was found. The last time burnt out bulbs were replaced approximately 125 bulbs had burned out and not one of them had exploded. Comments: NASA document number SPP 0-01 titled "Shuttle Payload Ground Operations Contractor Standard Practices and Procedures", Section D Requirements and Responsibilities: Tool, equipment, and material control (paragraph #43) states: "Glass is forbidden in/on or over flight hardware unless the glass is equipped with a shatterproof protective cover that will contain all fragments in case of glass breakage. Unprotected light sources are not allowed in/on or over flight hardware." | N/A |  |  | Public | Not Specified |  | 04/19/1994
169 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Fire in Fueling Station During Piping Modification |  | Modification to aircraft fueling station piping that requires grinding should only be initiated with proper safety precautions. | Completely drain fuel tanks and lines prior to conducting any grinding operations where flammable liquids have been stored. Insure that spark shields and/or fire blankets are used to prevent contact with combustibles. | GRC | 01/20/1994 | A fire started at the flight operations aircraft fueling station when a pumping station was in the process of being connected to a new, in-ground, aviation fuel storage tank. Residual fuel had been left in the refueling unit because the connection was to be made with no disruption to any of the unit piping. The workers installing the unit, when faced with a six inch difference in the tank piping from the unit inlet, decided to modify the piping. When the workers broke into the unit piping and saw some residual fuel leaking they assumed the amount to be negligible. A stand was set up within 10 feet of the pipe opening and a grinding operation was started to add a short section of pipe. The investigation committee determined that the ignition source of the fire was from sparks generated by the grinding operation. | Recommendations were approved by the LERC executive safety board. | N/A |  |  | Public | Not Specified |  | 04/19/1994
226 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Valve Seats |  | Nylon seats deteriorate when used in valves controlling oxygen gas systems and can cause fires. | Replace all nylon valve seats used for oxygen service with material that is compatible with oxygen. | GRC | 06/21/1993 | A tube trailer was being filled with oxygen with a 1000 psi differential between the trailer and supply when a flash was observed in the area of the remotely operated control valve. A subsequent rush of gas and fire followed. The fire continued for about 40 seconds and was extinguished by the onrush of gas from the ruptured stainless steel manifold lines that had been burned off. The investigating board concluded that the nylon seats in the valve had deteriorated to the extent that the ball was able to vibrate freely under the high flow conditions present. The vibration would most likely be severe while attempting to flow oxygen against a closed ball valve with missing or deteriorated seats. This would have generated sufficient energy through impact and heat to cause ignition. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
236 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Hydraulic Lift Gates |  | Improper loading and unloading of heavy wheeled equipment with hydraulic lift gates can result in severe accidents and fatalities. Unsecured loading of heavy, marginally stable equipment by means of a hydraulic lift gate can result in severe accidents. | Revise safety operating procedures to require handling of heavy wheeled equipment on hydraulic lift gates to be a two-person operation. Secure all heavy, wheeled equipment with wheel chocks and tie down ropes before moving lift gate. | GRC | 07/06/1993 | An employee was loading a wheeled welding cart onto a truck equipped with a hydraulic lift gate when the welding unit fell from the lift gate. The employee, working alone, pulled the welder onto the lift gate from the vehicle's right side. He then turned the front wheel 90 degrees to help stabilize the welder and chocked the rear wheels with the aluminum ramp. Using the lift gate control on the right side of the vehicle, he raised the gate to the truck bed level. After reaching the truck bed elevation, the welding cart began to shift or slip towards the right side of the vehicle. The high center of gravity of the welder, the inadequacy of the aluminum ramp as a wheel chock, and the adverse slope of the lift gate, all contributed to the instability of the welding cart that resulted in the welder falling from the gate. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
237 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Control Valves |  | Fail-safe position of control valves in supply lines must be set correctly to prevent damage to pressure vessels. | Set all valves for fail safe operation (open or closed) according to needs before installation in pressure or vacuum systems. | GRC | 07/08/1993 | A test Centaur 1-E tank, on standby, was damaged. The bulkhead between the liquid hydrogen tank and the liquid oxygen tank failed due to a series of events. Air services to the building were shut down for repairs so that the facility switched to an emergency nitrogen supply. Failure to switch back to service air when it became available, led to the mishap. The emergency supply became depleted and two valves in the normal nitrogen purge system failed in the open position releasing the high pressure nitrogen gas from the manifold into the liquid hydrogen tank. The gas flow raised the liquid hydrogen tank pressure to 4.5 psig. That was sufficient to rupture the bulkhead wall. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
168 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Hydrogen Detonation in Propellant Piping Systems |  | Small amounts of hydrogen (0.027 lbs) and air (0.26 lbs) at 350 psia and an ignition source can cause detonation and damage in a confined area. | Design backflow prevention devices in propellant piping systems to prevent the accumulaion of combustible mixtures in confined areas. | GRC | 07/01/1993 | A three inch diameter stainless steel manifold containing hydrogen (0.27 lbs) and air (0.26 lbs) at 350 psia ruptured during experimental operation. The hardware was off-the-shelf, slightly modified, pre-safety checked and analyzed by the supply vendor. The test apparatus was in an altitude tank at simulated altitude conditions at the time of the mishap. Damage was restricted to the manifold and some of the experimental package valves. The cause of the rupture was a detonation of an unplanned hydrogen and air mixture inside the manifold. A contributing factor was the deviation from preplanned test procedure by the test crew while attempting to make the device work. The investigation team determined that the principal cause of the mishap was the lack of backflow prevention devices in the hydrogen and air supplies to the test package. That deficiency permitted the accumulation of the detonation charge within the manifold. | Recommendations were approved by the LERC executive safety board. | N/A |  |  | Public | Not Specified |  | 04/19/1994
235 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Wind Turbine Generator |  | When servicing wind turbines with unbalanced blades, releasing the rotor brake allows the heavy end to fall, causing blade damage and injury to personnel. | Secure unbalanced blades with appropriate crane supported slings or tied- off lines before releasing the rotor brake. | GRC | 07/02/1993 | A wind turbine was lowered from its tower and secured to a ground level assembly stand. A blade tip was then removed and the work crew broke for lunch. After lunch the rotor brake was released. Personnel on the ground realized the unbalanced rotor condition as the blade came rapidly to the ground. The direct cause of the accident was a failure of several knowledgeable personnel in the immediate area to realize the unbalanced conditions of the rotor. A crane operator was available in the immediate area. The crane should have been used to secure the unbalanced rotor and slowly lower it to the ground. This procedure of lowering an unbalanced rotor has been standard procedure in many blade, spool piece, and tip changes in the past. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
231 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Cooling Towers |  | Off-design operation of cooling towers during winter months can cause severe damage to the wooden structure. | Develop written standards and operating procedures which include permitted deviations from normal operating conditions depending on seasonal changes. | GRC | 06/22/1993 | During winter operation of a cooling tower that was operating in a standby mode, a large section of the tower collapsed due to an unusual accretion of ice in the central portion of the tower. The dead load of the ice overloaded the structural members and caused the collapse. When the mishap occurred the tower was not running within its design parameters. Valves controlling the minimum water flow to prevent freezing and to inhibit corrosion in the heat exchangers were opened wider than usual to reduce noise because of workmen in the area. An additional pump was also turned on to maintain the required flow. The combination of the increased water flow rate and restricted flow through the pipes returning water to the tower basin created a back pressure sufficient to permit water to flow up the riser pipe and into the tower distribution system. Because the tower was in standby, with no heat load, the water and air temperatures were both low enough to cause the water to freeze. The resulting accumulation of ice created the load that led to the structural failure. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
232 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Exhaust Gas Cooler |  | Aging test facility equipment such as deactivated gas coolers that are being used as part of vacuum lines are subject to catastrophic structural failure. | Inspect piping and components of aging vacuum systems at regular intervals to assure reliability using Zyglo, X-Ray and Ultrasonic techniques. | GRC | 06/25/1993 | A deactivated exhaust gas cooler in a vacuum line collapsed under normal operating conditions of 26 inches of mercury. The cooler was destroyed. There was minor damage to a nearby wall due to negative pressure in the vicinity of the cooler. Skylights in the shop area imploded and a considerable amount of debris was drawn into the piping. The principal cause of the failure was deterioration of the cooler due to age. Poor welding during assembly and inadequate inspection of the cooler were contributing factors. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
219 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | High Pressure Steam Line Valves |  | High pressure steam valves made of gray iron can rupture when exposed to severe water hammer. | Replace all ferrous high pressure steam valves not positively identified as cast steel, bronze, brass, stainless steel, or ductile iron. | GRC | 06/18/1993 | A high pressure steam valve ruptured in the basement of the building, releasing steam that damaged walls and floor tiles. The mishap was caused by dynamic loading to the line resulting from severe water hammer. Heavy rainfall preceeding the incident flooded the steam trench. The steam line enclosed with cool water set up a heat exchange process forming excessive condensate that was put into motion by the building demand. Slugs of water generated dynamic loads in the piping. The cast iron steam valve (Chapman gate valve model 59 1/2) then ruptured. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
223 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Cable Pulley Assemblies |  | Counterbalance cables on single flange mount pulley systems can be dislodged easily from the pulley by physical contact on the counterweight. | Install pulley assemblies with double flanges to prevent cable from being dislodged during assembly or maintenance operations. | GRC | 06/18/1993 | A counterbalance cable had become disengaged from the upper support beam pulley during assembly operations. This was caused by the work scaffold (used to access the upper beam area) making contact with the counterweight. The tension in the cable was relieved, allowing it to slip from the pulley groove. When the load was reestablished, tension was reapplied to the counterbalance cable, pulling the weight free and allowing it to fall. |  | N/A |  |  | Public | Not Specified |  | 04/19/1994
314 | White, Margo - 0000000000 : NO@ADDRESS.GIVEN | White, Margo - 0000000000 : NO@ADDRESS.GIVEN |  | Contamination, Silicone; Effect on Bonding |  | Silicone, being colorless and fluidlike, can easily contaminate equipment if not subjected to thorough fabrication controls. Silicone contamination can interfere with bonding. | Provide an isolated area for silicone application, exclude hardware from the area when possible except for the hardware requiring silicone application, and provide personnel training. | MSFC | 04/15/1993 | Silicone was used to compensate for the differences in coefficient of thermal expansion between electrical components and the basic epoxy module material. The silicone was transferred in some manner to the module baseplates and resulted in a poor bond and subsequent cracking. | The source data indicates that separate silicone application facilities and controls were established to prevent reoccurrence. | N/A |  |  | Public | Not Specified |  | 04/15/1994
348 | Savino, J - 0000000000 : NO@ADDRESS.GIVEN | Savino, J - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan AACS RAM Upset During SRM Pyrotechnic Initiation | An NSI may have shorted to chassis ground a few seconds after the SRM separation pyros were activated on Magellan, causing the loss of at least 2K of AACS memory RAM. Six recommendations are made for improving designs for electro-explosive-device initiation. | Based on Magellan analysis and test plus work recently performed in support of Mars Observer, the design for electro-explosive-device initiation may be inadequate. | Reconsider induced chassis current mechanisms along with coupled voltage transients for all spacecraft designs being developed. Consider eliminating the return path through the chassis back to the firing source (do not connect the firing source to the frame), thus isolating the firing source. Consider reducing the NSI activation current - NSI spec.: 1 amp, no fire; 3.5 amps, all fire. Consider locating the current limiting resistor in the "high-side" line. Consider grounding the fire circuit shield at both ends. Consider opening the enable relay for the initiators just fired, before firing of the next pyro sequence devices (not between redundant pairs). | JPL | 10/25/1994 | On August 12, 1990, 7.3 seconds after the SRM separation pyros were activated on Magellan, erroneous alert codes were received by CDS. These alerts were caused by the failure of the AACS Memory B of at least 2K of the TCC244 RAM. JPL was able to build a failure model which accurately matched the symptoms on the spacecraft. Through ground tests, it has been determined that by firing one or more NASA Standard Initiator (NSI) a short to the chassis ground could take place. The short path could be due to the direct contact between the unburned portion of the squib bridgewire with the chassis, or more likely, due to the presence of conductive gases/materials (plasma generated by detonation) between the squib bridgewire and chassis. When a short occurs, a large current can flow through the ground structure and thus a large differential voltage can be induced across the shorting path. Since the energy available during the short is very large (2.2 J), the intense source of electro magnetic interference can affect sensitive victim electronic circuits causing upsets or damages. The shorting hypotheses are not unique to Magellan. The impact of NSI shorts on space systems is strongly dependent on grounding and cabling configurations of each spacecraft, with potential mission risks. Additional Keyword(s): Shielding Reference(s): PFR 52235, ISA 8899 Magellan Anomaly Investigation, IOM 340-93-JLS 301, dated 12/9/93 Summarized Findings and Recommendations of the Mars Observer Investigation Groups, IOM GEC: 250-94-009, dated 1/28/94 Mars Observer Loss on Signal: Special Review Board Final Report; JPL Pub. 93-28 | JPL has referenced the lesson as supporting Paragraph 4.10.4.4 ("System EMC/EMI Design: Control of Susceptibility - Immunity to Simultaneous Pyro Firings") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/31/1994
312 | Zydowicz, M - 0000000000 : NO@ADDRESS.GIVEN | Zydowicz, M - 0000000000 : NO@ADDRESS.GIVEN |  | ACTS Pyro Separation Band Anomaly (Shuttle Orbiter) | Minor damage to the Shuttle was caused when the firing of the primary explosive cord to deploy the payload from the cargo bay also triggered the backup cord. End-to-end system tests had validated the erroneous design rather than the end function. Document electrical-mechanical interfaces, protect hazardous systems against any possible unintended operation, and consider use of a single cord configuration. | End-to-end system checks should be performed to verify proper connection, wiring, signal level and function. If necessary, as in the case of pyrotechnic circuits, simulators should be used. | Develop end-to-end schematics/diagrams for electrical mechanical interfaces including software driven interfaces. Require that potentially hazardous systems have demonstrated protection against any possible unintended operation. Consider use of a single cord configuration which will prevent this type of event. | JPL | 03/24/1994 | During the successful deployment of the ACTS/TOS Payload from the STS-51 cargo bay on September 12, 1993, the "SUPER*ZIP" pyrotechnic separation joint ruptured, producing debris that caused minor damage. Two explosive cords were initiated and operated in the subsystem (when functioning of one cord was desired), causing considerably more energy to be imparted into this subsystem, resulting in the rupture of the containment tube, doubler plates, lead sheathing, silicone rubber extrusion and in the emission of carbon particles (smoke). One affected plate penetrated through the shuttle orbiter aft bulkhead insulation blanket and punctured a 1/8 x 1/2 inch hole in the aft bulkhead. Flight/crew critical equipment exists immediately behind the bulkhead. Other debris caused at least nine small tears in cargo bay insulation blankets, three gouges in wire tray covers and possibly a gouge in a thermal protection system tile. The primary cause of the separation system anomaly was a circuit design error, which resulted in firing one end of both the primary and back-up cords, rather than firing both ends of the primary cord. The direct cause of the design error could not be determined. This embedded error remained undetected throughout a series of comprehensive requirements, design and certification reviews and systems tests with wide participation by both the government and contractors. The end-to-end system tests, end-to-end verification Ground Support Equipment (GSE), and procedures were established in a manner that validated the erroneous design rather than the end function. This was due in part because of lack of adequate systems engineering in the TOS program and because the SUPER*ZIP end-to-end drawings were spread among several individual drawings and never aggregated into a single end-to-end functional electrical/mechanical schematic. | JPL has referenced the lesson as supporting Paragraph 4.3.4.3 ("Power/Pyrotechnics Design: Pyrotechnic Function - Enabling of Pyrotechnic Functions") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 03/22/1994
210 | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN | Michalson, G - 0000000000 : NO@ADDRESS.GIVEN |  | High Voltage Electric Circuits |  | Injury from electrical shock and/or hardware damage can result if a circuit is energized while working on it. | Use an active means such as a multimeter, hot stick, sounding devices, spiking, etc., to make a positive check / verification of a circuit's de-energized state before working on it. | GRC | 11/13/1992 | A qualified high voltage electrician was injured when he cut into a 34,500 volt cable that was thought to have been de-energized. The cable was located in a cable tunnel in the substation. The primary cause of the accident was the misidentification of the power cable. This was attributed to the fact that two of the cables had their identifying tags interchanged. Because maintenance personnel felt that they had the right cable identified, there was no attempt to determine by sounding devices, spiking, etc. that the cable they were about to cut was energized. The cable had been previously isolated and no further switching was felt to be deemed necessary. |  | N/A |  |  | Public | Not Specified |  | 11/18/1993
204 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Wind Tunnel Model - Analysis Failure |  | To prevent failure, stress calculations should include the action of all forces on a model in a wind tunnel, taking into consideration the material of the model and method of attachment. | Evaluate wind tunnel model integrity and stability by including both dynamic pressure and drag forces in the stress calculations. | GRC | 07/06/1993 | During a test run on a model in a wind tunnel, several components of a wooden test rig could not withstand the loads on them with the tunnel at maximum speed. Stress calculations made prior to the mishap indicated an acceptable factor of safety. However, the assumptions in the calculations for stress neglected to consider the drag force on a flat plate which is a multiplier to the dynamic pressure, resulting in a force 80 percent higher than was used in the calculations. The stress calculations on the model also made certain assumptions that were not consistent with the quality of its material and construction. The investigating committee found that the failed parts were fabricated from inferior wood with numerous knots and that glue was not used to help keep the parts together. The inferior strength of the wood was not noted initially because the model was painted over when delivered to the test site. | The recommendations from the mishap report were approved by the LERC executive safety board. | N/A |  | Aeronautics Research, Exploration Systems | Public | Not Specified |  | 10/19/1993
250 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Pressure Testing of Piping Systems |  | Piping systems with expansion joints can fail at less than their rated pressure if not adequately supported during pressure testing. | Assemble piping systems containing expansion joints for testing with both ends of the joints restrained before pressurizing. | GRC | 10/07/1993 | A section of a piping system was removed from a test facility for outside pressure testing. The pipe section had an expansion bellows mounted on the end that was not restrained and under nitrogen gas pressure the bellows ruptured injuring several employees. Although the pressure in the system was under the design maximum, it was determined that the primary cause of the accident was failure of the bellows. While properly designed for its application, it was not tested under conditions for which it was designed. |  | N/A |  |  | Public | Not Specified |  | 10/19/1993
11 | Carroll, D - 0000000000 : NO@ADDRESS.GIVEN | Carroll, D - 0000000000 : NO@ADDRESS.GIVEN |  | Addition of X-Rays to Screen for Defects (Embedded Wood Chips) in Shuttle Orbiter Tires that Visual and Holographic Techniques May Not Detect |  | Visual and holographic inspections of critical use tires can fail to reveal defects such as embedded wood chips and lead to tire failure. X-Rays may be required. | X-Rays of shuttle orbiter tires were added as an inspection technique. Existing orbiter tires were X-Rayed to screen for similar defects. | JSC | 06/17/1991 | Inspection of the Nose Landing Gear (NLG) tire revealed a 1/4" cut which appeared to have a small piece of wood embedded in it. The investigation of the tire included: (1) X-Rays that verified the position and size of the wood chip; (2) review of the standard holography inspection data that verified the technique failed to reveal the defect; and (3) sectioning of the tire to determine the origin of the chip. The wood chip came from the cart used to transport the tread gum rubber to the tire builder and was built into the tire. The wood chip became visible only after inflation. All existing orbiter tires were X-Rayed to screen for similar defects and tire inspection techniques were changed to include X-Rays. The wood chip caused a delamination sufficient to produce a tire failure under some worst case, but feasible, landing scenarios (maximum permissible cross wind at KSC). However, the other NLG tire would have supported the orbiter following this failure. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/27/1993
245 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Cartridge Powered Tools |  | Using cartridge powered Ram-Set tools to drive studs into walls can cause accidents if lacking knowledge of the structure of the walls. | Require approval from qualified personnel whose knowledge of building structure can attest to the safety of using Ram-Set powered tools on building surfaces. | GRC | 01/21/1993 | An electrical contractor employee was driving studs into a Haydite wall with a cartridge powered Ram-Set. The stud went through the wall and traveled approximately 25 feet across the room to hit an employee working on a scaffold about 4 feet off the floor. The stud hit him in the back of the left thigh penetrating approximately one inch into the leg. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/27/1993
14 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Fail Safe Electrical Heaters; Lack of Fluid Level Shutoff Capability for Portable Heaters Used for Heating Aqueous Solutions |  | Use of electrical heaters without fail safe capability can lead to fire and subsequent equipment and facility damage. | The mishap investigation board recommended that all equipment with the potential for overheating or causing a fire should be intrinsically safe, and there should be adequate safeguards to disconnect power in an anomalous situation. Use only heaters with automatic shut off to prevent overheating and combustion. | JSC | 07/21/1991 | In Bldg. 9 at JSC, a 1000-watt quartz immersion heater was being used to heat a small amount of water for a chemical mixing operation in a precious metals shop. The heater, which was not equipped with a safety device to shut it off automatically in case of high temperature caused by the water level falling below the level of the heater element, was inadvertently left on overnight. Once water in the polypropylene bucket had evaporated, the heater's protective quartz sheath melted, and subsequently ignited the bucket, leading to a fire with damages estimated at $350,000 to a NASA facility. A simulation conducted as part of the mishap investigation confirmed the plausibility of this scenario. The mishap investigation board recommended that all equipment with the potential for overheating or causing a fire should be incapable of overheating to an ignition temperature, and there should be adequate safeguards to disconnect power in an anomalous situation. Lesson Revised: June 17, 1997 | All heaters with out automatic liquid control shut off were removed from use in the area. Ref. Investigation report 4-5-91 | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/27/1993
13 | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN |  | Fluid Sampling Techniques for Spacecraft Ground Support Equipment (Auxiliary Power Unit) |  | Incorrect sampling techniques for spacecraft Ground Support Equipment (GSE) fluid that fail to preclude downstream contamination can potentially damage critical flight hardware. | Proposed actions to resolve this problem were: (1) modification of the GSE to provide for fluid sampling at the GSE/airborne interface, and (2) require filter inspections and replacement on a regular basis. | JSC | 07/16/1991 | The gaseous nitrogen service coupling of the shuttle orbiter Auxiliary Power Unit (APU) #2 fuel tank was found to be leaking after servicing for shuttle mission STS-3. It was determined that this leakage was the result of contamination/corrosion at the ground/airborne Quick Disconnect (QD). The probable source of the contamination was believed to be a stainless steel filter in the Ground Support Equipment (GSE). Moisture being trapped and held between the filter and its support screens had corroded the filter elements thereby causing the filter to fail and allowing contamination to migrate to the QD's where it was deposited on the poppet seat. Sampling of the fluid had been conducted at the GSE cart upstream of the filter. Investigation has shown that there are many types of contamination and corrosion present in the QD's. Leaking of nitrogen from the APU fuel tank could potentially result in the inability to restart the APU for orbiter re-entry. The following actions were proposed to resolve this problem: (1) modification of the Ground Support Equipment (GSE) to provide for fluid sampling at the GSE/airborne interface, and (2) change the procedures to require filter inspection and replacement on a regular basis. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/27/1993
259 | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN | Havenhill, Maria - 0000000000 : NO@ADDRESS.GIVEN |  | Vacuum Detection Systems |  | Vacuum detection alarm systems are not sufficient for monitoring air-cooled flight or prototype equipment | Change detection systems to a positive air flow indicator with an audible alarm signal | GRC | 03/08/1993 | General purpose computer S/N 00513 at the JAEL test facility operated for 11.5 hours without cooling. The lack of forced air ventilation was caused by an air duct cover left on during installation. According to personnel working in JAEL and the results of JAEL's investigation, the factors which contributed to the problem were inadequate supervision of individuals involved, a lack of discipline in the practice of handling flight equipment, and failure of JAEL and quality assurance personnel to follow and/or verify existing procedures. |  | N/A |  |  | Public | Not Specified |  | 09/16/1993
248 | Papell, S - 0000000000 : NO@ADDRESS.GIVEN | Papell, S - 0000000000 : NO@ADDRESS.GIVEN |  | Cleaning Fluids |  | Cleaning tanks containing residual nitrogen tetroxide and hydrazine with inert trichloroethylene can cause explosions. | Analyze the contents of the tanks to be cleaned, including the cleaning fluid to be used, to determine chemical stability of the mixture. | GRC | 08/06/1993 | An explosion occurred during the cleaning operation of a tank containing nitrogen tetroxide and residual hydrazine. The cleaning fluid used was trichloroethylene, considered to be inert and compatible with the chemicals involved. The intensity of the explosion killed two workmen. Bench tests were run with conflicting results and further tests were planned. |  | N/A |  |  | Public | Not Specified |  | 09/16/1993
310 | Chien, G - 0000000000 : NO@ADDRESS.GIVEN; Blosiu, J - | Chien, G - 0000000000 : NO@ADDRESS.GIVEN |  | Mars Observer Inertial Reference Loss | Mars Observer experienced inertial reference loss on several occasions during its cruise to Mars. These incidents were due to the lack of a detailed code walk-through, and to use of gyro noise values, obtained from in-house test, that were more optimistic than the manufacturer's specifications. Do not depend on hardware performance being better than the manufacturer's specification. Perform detailed code walk-through of critical software modules. Pay special attention to inherited critical software. Design the flight computer and software to permit necessary changes in flight. | Hardware performance based on in-house tests are not substitutes for manufacturer specifications for components whose performance varies (degrades) over mission life (gyros, etc.). Non-performance of detailed code walk-through for critical software could have serious effects on spacecraft operation. The covariance program "bugs" in the flight software should have been caught even before testing of the code. Inherited software designed for earth orbiting satellites may not be directly applicable to interplanetary spacecraft missions. Design flexibility of the flight computer and software is critical to the ability to uplink software patches for the correction of unexpected in-flight spacecraft anomalies. | Do not depend on hardware performance being better than the manufacturer's specification. Perform detailed code walk-through of critical software modules, and particularly of flight software patches. Special attention should be paid to flight critical software performance that is inherited from previous applications. Prior anomalies must be addressed. Allow sufficient flexibility in the flight computer and software to permit necessary changes in flight. | JPL | 03/03/1994 | Mars Observer experienced inertial reference loss on several occasions during its cruise to Mars. Two classes of inertial reference loss have been observed: A. In early January 1993, the flight software was unable to identify any star that transited the celestial sensor assembly field of view. The unidentified stars count exceeded the "loss logic limit," and the fault protection software commanded the spacecraft to the sun coning attitude contingency mode. This occurred three times before a temporary software script to widen the star identification tolerance was uplinked in order to artificially increase the attitude uncertainties, or covariances, used by the software. Design flexibility of the fight computer and software allowed the software patch to be easily performed. It was suspected that the cause was due to the use of the more optimistic gyro noise parameters and values obtained from the in-house test results rather than the manufacturer's specifications. Recovery time: 3 days per occurrence. B. During April and May 1993, three more incidents caused the spacecraft to declare inertial reference loss when the "sun monitor ephemeris" test, which compares the expected new position with the measured positions, was violated. An algorithm error in the inherited flight software caused the spacecraft attitude to be incorrectly estimated under certain conditions. A similar problem occurred on the Defense Meteorological Satellite Program (DMSP), an earth orbiting spacecraft built by the same contractor, that was using the same flight software. This algorithm error puts the spacecraft in additional jeopardy when the attitude covariances are large. Since the script that was intended to prevent the January incidents increases the covariances, the script acted as a catalyst for the three April/May anomalies. The review of the data indicated that no detailed code walk-through was performed on the software patch that widened the star identification tolerance. Recovery time: 5 days per occurrence. Additional Keyword(s): Attitude Determination, Star Scanner | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.5.1 ("Engineering Practices: Mission Operations - Critical Events and First Time Events"), and Paragraph 6.6.2 ("Engineering Practices: Inheritance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.1.7.3 ("Flight System Design: General - Operability") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 09/16/1993
264 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | Control of Operations Involving Adjustment, Modification, or Maintenance of Fluid or Pressurized Systems (Such as Wet Pipe Fire Suppression Systems) |  | Unauthorized modifications to a wet pipe fire suppression system without depressurization and safing caused damage to the system which led to a discharge of fluid and a close call for equipment damage. | Contractor procedures were changed to specify that modifications or adjustments to pressurized systems are not to be accomplished until the system is secured and depressurized. This procedure was disseminated to all personnel. | JSC | 06/30/1993 | Construction personnel were performing renovations to room 194 in building 16A at JSC. The renovation project included installing a suspended ceiling in part of the room. While in process of installing the ceiling, a pipefitter for the facility construction contractor noticed that the fire suppression system sprinkler head fusible link guard on one head was not consistent with the other heads in the room. Since the sprinkler would not operate effectively with this misalignment, the pipefitter tried to correct the problem. As he was attempting to adjust the misaligned guard, the wrench slipped breaking the fusible link on the sprinkler head causing water to be discharged into the room. Although the water pressure was immediately shut off, the broken head continued to drain water for approximately 30 minutes. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
265 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | Spontaneous Ignition of Tar Saturated Mops used for Roof Repairs |  | Dousing of a cotton hot tar mop with water is insufficient for preventing spontaneous ignition and fire. | Safety procedures were modified and documented to place mops in a container of sand and lower them to the ground. | JSC | 06/30/1993 | Following completion of a repair, a work crew laid a hot cotton tar mop on a piece of roofing insulation material on the roof. Although they doused the mop with water, it subsequently ignited spontaneously after approximately two hours and started a fire on the roof. Damage was limited to the mop, the insulation, and a small area of the roof. The undocumented procedure to immerse tar mops in a bucket of water and then lower to the ground after job completion was not performed. To prevent recurrence, the maintenance contractor modified the safety section of the annual roof plan as follows: mops will be disassembled, placed in a sand filled container, lowered to the ground, and disposed of by the environmental support department according to existing regulations. The spontaneous ignition of tar mops is well documented in existing literature, e.g., "Fire Protection Handbook", 17th edition. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
263 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | Emergency Planning - Fire Fighting |  | Emergency planning that does not include compatibility of extinguishants (including water) with hazardous materials can cause delays in fire fighting and additional losses. | Advanced planning documentation was changed and distributed to include an inventory of all areas containing hazardous materials plus determination of appropriate extinguishants. | JSC | 06/29/1993 | During a fire in a precious metal workshop (where hazardous materials were used), fire fighting efforts were delayed while information to determine the compatibility of water as an extinguishing agent was obtained. Additional damage resulted from the delay. The fire department has now been provided a listing of recommended extinguishants to be used in specific locations. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
300 | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN |  | Fire Extinguisher Placement Delayed Firefighting Efforts in an Aircraft Maintenance Area |  | Extinguishers placed further than standard requirements from potential fire areas can delay firefighting efforts and increase potential losses. | Fire extinguishers placements were adjusted to meet NFPA requirements. | JSC | 08/19/1993 | Two aircraft maintenance personnel were preparing a test run on engine No.2 of a NASA turboprop aircraft at Ellington Field. During the bleeding of air from the engine fuel system, a flash fire occurred. One worker jumped from a ladder and injured his left heel. The other worker burned his hand while attempting to combat the fire. Additional personnel responded to the scene and extinguished the fire with portable fire extinguishers. An investigation of the incident noted the placement of the extinguishers approximately 150 feet from the aircraft. NFPA code recommends placement of no further than 50 feet. Investigators recommended placing the extinguishers within NFPA maximum allowable distances. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
292 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Selection of Critical Test Parameters and Conditions for Monitoring Hardware or System Performance (Such as Temperature of Computer Electronics) |  | Measurement/monitoring of indirect indications for critical hardware performance parameters can lead to improper determination of status and equipment loss or damage. | Mishap board recommendations: Consider using positive air flow indicators rather than indirect vacuum sensors. For cold plate mounted equipment, consider a pyrometer or thermocouple on the case as a redundant direct temperature indication. | JSC | 07/15/1993 | During burn-in testing of an orbiter General Purpose (Flight) Computer (GPC) in the JSC avionics engineering laboratory, a "fail to synchronize" error was detected. This error indicates that the computer is out of synch with other GPCs involved in the test, and may be the result of a computer hardware problem. The GPC in question was discovered to be very hot to the touch, and inspection of internal sensors indicated the GPC had been overheated beyond design limits. An ensuing investigation showed that the unit had operated without cooling for 11.5 hours due to failure to remove the ventilation system air duct cover prior to installation of the GPC in the test bed. This event was a direct result of not following installation procedures described in the Test Preparation Sheet (TPS). Additional factors contributing to this event included: The design of the cover plate for the GPC cooling duct did not prevent installation of the GPC with the cover in place. Most of the cover plates used in the laboratory were modified with additional foam to preclude installation of the GPC without removing the cover. The alarm system used to monitor GPC cooling depended on vacuum sensing instead of positive airflow indications. With the air duct cover in place, the vacuum sensor on the GPC in question showed a normal range reading even though there was no air flowing through the computer. The monitoring of an indirect parameter (vacuum) rather than a direct indication of absence of a critical parameter (cooling air flow) or the existence of the hazardous condition of concern (temperature of the GPC) did not guarantee that proper cooling was provided. Only one junior technician was assigned to install the GPC. This was a violation of instructions on the TPS, which required two technicians to perform this task. As a result, the quality assurance assignee for the task helped to perform the installation procedure rather than performing his intended monitoring function. There was no formal program of training or certification in place for technicians in the laboratory. The training received was principally an undetermined amount of on-the-job training. Factory evaluation of the GPC involved in this event determined that it was fit for use only as a test or prototype unit and not as a flight unit. The difference in cost between a flight GPC and a test GPC is approximately $700,000. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
295 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | Manufacturing Defects (Burrs) Becoming Loose Particles and Jamming Meshing Parts of Critical Components (Orbiter Hydraulic Pump) |  | Burrs left remaining during manufacturing processes can become loose particles, migrate into meshing machine parts, and cause operational failures to critical components (orbiter hydraulic pump). | Inspections for burrs, improved cleaning methods, and flushing of the pumps were added to the manufacturing processes. | JSC | 07/29/1993 | During the shuttle STS-4 mission, an orbiter (OV-102) hydraulic pump failed. A post flight examination discovered an aluminum particle wedged into one of the high pressure pump gears. The probable source of the particle was determined to be in some drilled oil passages where evidence of burrs were found at the intersection of the holes. The pump manufacturer: Implemented requirements for an inspection of all oil passages prior to assembly. Added a flushing of the pump with clean hydraulic fluid following vibration testing and before continuing further acceptance testing. Reviewed the pump cleaning process. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
293 | McGee, John - 0000000000 : NO@ADDRESS.GIVEN | McGee, John - 0000000000 : NO@ADDRESS.GIVEN |  | Component Failure due to Application of Identification Markings on Sealing Surface |  | Design specifications that do not adequately address all process requirements (such as application of component identification) can result in damage to functional parts. | Design drawings were changed to include specifications for the allowable position and technique for identification markings. | JSC | 07/21/1993 | A transducer failed a mass spectrometer leak check. The serial number of the transducer was vibro-etched onto the sealing surface causing the leak. The design drawing provided no specifications to preclude the application of the serial number onto the sealing surface. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
298 | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN |  | Conflagration of a High Pressure Gaseous Oxygen System from Rapid Venting and Particle Impact Following a Unexpected (Well Below Rating) Burst Disc Failure |  | Rapid venting (following a ruptured burst disc) of a high pressure gaseous oxygen system can result in the ignition and burning of downstream vent piping due to ignition by particle impact. | The burst disc was relocated very near the end of the vent piping, outside of the facility, and directed away from personnel access areas. In line filters were added to prevent particles from entering the vent. | JSC | 08/18/1993 | At the White Sands Test Facility (WSTF) a burst disc on a high pressure (9700 psi) oxygen system ruptured at 5700 psi, well below the system and rated pressure of the disc. Ignition of the vent system downstream of the burst disc occurred, partially destroying it. The burst disc was a safety relief device placed in an oxygen recharger pumping system and was subjected to rapid cyclical pressure pulses during recharging operations. It was concluded that the cycling fatigued the burst disc metal much more rapidly than would be expected in a static system application. Although the exact source of the ignition is not known, it was assumed that either particles from the ruptured disc or accumulated debris from the oxygen pumping system impacted the vent system in the presence of the high pressure oxygen that flowed past the ruptured disc. This served as an ignition source for the base vent material (stainless steel) fire, which progated until the venting oxygen pressure fell below the level that would support combustion. The fire then self-extinguished. The design of the vent line was changed to place the burst disc very near the end of the vent line, exterior to the facility, and with the discharge oriented away from personnel access areas. In-line particle filters were relocated closer to the oxygen source to reduce the probability of debris exiting at high velocity from the vent system if a burst disc rupture occurs. All WSTF high pressure oxygen vent system designs were reviewed and two additional systems of similar configuration were eliminated (they were no longer needed). |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
203 | McGee, John - 0000000000 : NO@ADDRESS.GIVEN | McGee, John - 0000000000 : NO@ADDRESS.GIVEN |  | Corrosion of Base Materials by Reaction Products Resulted from the Expected Release of Small Quantities of a Hypergolic Propellant (Nitrogen Tetroxide, N204) Reacting with Externally Applied Tape on Nearby Component. |  | Failure to consider expected releases of fluids into the external environment as part of an integrated materials compatibility assessment led to leakage from system tubing. | Integrated compatibility assessments now performed for externally applied materials subjected to expected fluid releases to preclude any potential degradation and subsequent deleterious effects. | JSC | 11/10/1992 | External corrosion of tubing material caused leakage in a shuttle orbiter Reaction Control System (RCS) helium Quick Disconnect (QD). Neoprene tape was applied to the tubing in the vicinity of the N2O4 source. The corrosion was due to chemical attack by the products of a chemical reaction between nitrogen tetroxide (N204), propellant oxidizer, and the neoprene tape material. The products formed were nitric acid and various chlorides. Due to the presence of the nearby QD, small quantities of N204 were routinely present in the external environment upon mating and demating of the QD. An integrated materials compatibility assessment would have identified this incompatibility issue. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
291 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Design of Dust Covers for Systems Requiring Forced Air Ventilation (Such as Electronics Systems) |  | Design of dust covers for ventilation systems which do not require their removal before hardware installation can result in equipment damage due to interruption of critical cooling air. | Corrective actions recommended by the mishap investigation board include modification of all cooling duct covers to ensure that equipment cannot be installed without first removing the cover. | JSC | 07/15/1993 | During burn-in testing of an orbiter General Purpose (Flight) Computer (GPC) in the JSC avionics engineering laboratory, a "fail to synchronize" error was detected. This error indicates that the computer is out of synch with other GPCs involved in the test, and may be the result of a computer hardware problem. The GPC in question was discovered to be very hot to the touch, and inspection of internal sensors indicated the GPC had been overheated beyond design limits. An ensuing investigation showed that the unit had operated without cooling for 11.5 hours due to failure to remove the ventilation system air duct cover prior to installation of the GPC in the test bed. This event was a direct result of not following installation procedures described in the Test Preparation Sheet (TPS). Additional factors contributing to this event included: The design of the cover plate for the GPC cooling duct did not prevent installation of the GPC with the cover in place. Most of the cover plates used in the laboratory were modified with additional foam to preclude installation of the GPC without removing the cover. The alarm system used to monitor GPC cooling depended on vacuum sensing instead of positive airflow indications. With the air duct cover in place, the vacuum sensor on the GPC in question showed a normal range reading even though there was no air flowing through the computer. The monitoring of an indirect parameter (vacuum) rather than a direct indication of absence of a critical parameter (cooling air flow) or the existence of the hazardous condition of concern (temperature of the GPC) did not guarantee that proper cooling was provided. Only one junior technician was assigned to install the GPC. This was a violation of instructions on the TPS, which required two technicians to perform this task. As a result, the quality assurance assignee for the task helped to perform the installation procedure rather than performing his intended monitoring function. There was no formal program of training or certification in place for technicians in the laboratory. The training received was principally an undetermined amount of on-the-job training. Factory evaluation of the GPC involved in this event determined that it was fit for use only as a test or prototype unit and not as a flight unit. The difference in cost between a flight GPC and a test GPC is approximately $700,000. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
290 | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN | Gregg, Larry - 0000000000 : NO@ADDRESS.GIVEN |  | Training/Certification for Personnel Installing Hardware |  | Lack of a formal training/certification program can result in an improper installation of hardware, which may contribute to significant damage or loss. | Mishap board recommendations: Use only certified technicians for critical installations and document training/certification. Use written procedures that include cautions, warnings, and operational (cooling) verification. | JSC | 07/14/1993 | During burn-in testing of an orbiter General Purpose (Flight) Computer (GPC) in the JSC avionics engineering laboratory, a "fail to synchronize" error was detected. This error indicates that the computer is out of synch with other GPCs involved in the test, and may be the result of a computer hardware problem. The GPC in question was discovered to be very hot to the touch, and inspection of internal sensors indicated the GPC had been overheated beyond design limits. An ensuing investigation showed that the unit had operated without cooling for 11.5 hours due to failure to remove the ventilation system air duct cover prior to installation of the GPC in the test bed. This event was a direct result of not following installation procedures described in the Test Preparation Sheet (TPS). Additional factors contributing to this event included: The design of the cover plate for the GPC cooling duct did not prevent installation of the GPC with the cover in place. Most of the cover plates used in the laboratory were modified with additional foam to preclude installation of the GPC without removing the cover. The alarm system used to monitor GPC cooling depended on vacuum sensing instead of positive airflow indications. With the air duct cover in place, the vacuum sensor on the GPC in question showed a normal range reading even though there was no air flowing through the computer. The monitoring of an indirect parameter (vacuum) rather than a direct indication of absence of a critical parameter (cooling air flow) or the existence of the hazardous condition of concern (temperature of the GPC) did not guarantee that proper cooling was provided. Only one junior technician was assigned to install the GPC. This was a violation of instructions on the TPS, which required two technicians to perform this task. As a result, the quality assurance assignee for the task helped to perform the installation procedure rather than performing his intended monitoring function. There was no formal program of training or certification in place for technicians in the laboratory. The training received was principally an undetermined amount of on-the-job training. Factory evaluation of the GPC involved in this event determined that it was fit for use only as a test or prototype unit and not as a flight unit. The difference in cost between a flight GPC and a test GPC is approximately $700,000. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
266 | McGee, John - 0000000000 : NO@ADDRESS.GIVEN | McGee, John - 0000000000 : NO@ADDRESS.GIVEN |  | Seal Manufacturing Design and Inspection Error (Indirect Measurement of Critical Dimensions) Resulted in Material Yielding |  | Critical dimensions, measured indirectly during inspection, may allow for excessively thin material, resulting in permanent yielding and component failure. | For this component, the manufacturing and tooling process was revised to add direct measurements of critical dimensions during inspection. | JSC | 07/07/1993 | A K-Seal drawing and manufacturing instruction specified measurement of inner and outer diameters, but no measurement of the K-Seal legs. Following the failure of a batch of seals during an Acceptance Test Procedure (ATP), an investigation revealed that they had all yielded and provided insufficient sealing forces. The yielding was caused by thin leg sections that occurred due to no direct measurement of leg thickness during manufacturing. Failure of this K-Seal could result in hot high pressure oxygen leakage during the orbiter launch phase with its associated hazards and also a lack of sufficient oxygen for external tank autogenous pressurization. Note: A drawing of the subject seal is available with the source documentation. |  | N/A |  |  | Public | Not Specified |  | 09/13/1993
10 | Carroll, D - 0000000000 : NO@ADDRESS.GIVEN | Carroll, D - 0000000000 : NO@ADDRESS.GIVEN |  | Repair of a Failed Component (Shuttle Orbiter General Purpose Computer Hardware Interface Soldered Pin) Before Investigation of the Cause of the Failure |  | Repairing a failed component (GPC IOP Soldered Pin) before investigating the cause of a failure can destroy evidence important to the investigation. This reduces the probability of implementing effective recurrence controls. | Rework procedures were changed to provide an inspection of failed parts before attempting repairs. | JSC | 06/17/1991 | A shuttle orbiter General Purpose Computer (GPC) at Input Output Port (IOP) No.2 was voted out of a set with other computers. The computers were exchanged and the computer connected at IOP No.2 also malfunctioned, indicating the problem was with the IOP. A pin solder joint was found to be fractured. The unit was repaired without investigating the cause of the joint failure. Rework procedures were revised to require an investigation of the cause of a failure before any attempt to repair the failed component. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
12 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Leak Checks of Critical Systems (Orbiter APU Coolant) After Installation, Maintenance, or Modifications Which Require System Disconnects |  | Inadequate leak check requirements may allow defects such as cross threaded fittings to remain undetected. These defects can cause leakage on critical fluid systems (orbiter auxiliary power unit coolant system). | Procedural requirements were changed to include leak checks on fittings after initial installation and any time they are opened or disconnected. | JSC | 07/07/1991 | During post ascent shutdown of an orbiter OV-102 Auxiliary Power Unit (APU) on shuttle mission STS-2, the unit increased in temperature. Flight data indicated stoppage of coolant (water) flow to the APU. Post flight tests indicated proper operation of the coolant control valves and no flow restrictions. During disassembly, a coolant inlet filter interface fitting was found to be cross threaded. It was concluded that this fitting leaked during ascent and while on orbit. The leak caused water to flash freeze in the line, blocking the flow. The ice thawed on entry and removed evidence of the blockage. Initial installation and maintenance procedures were revised to add leak checks and visual inspection for proper alignment of fittings. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
9 | Michael, T - 0000000000 : NO@ADDRESS.GIVEN | Michael, T - 0000000000 : NO@ADDRESS.GIVEN |  | Lubricant Particles Clogging Spacecraft System Filters |  | Use of assembly lubricant materials with suspended particles too large to pass through system filters can cause clogging of the filters and reduce flow rates below minimum requirements in critical spacecraft systems. | Contaminated system components were disassembled, cleaned, and replaced. | JSC | 06/13/1991 | Low flow rates were observed in the shuttle orbiter freon coolant loops when the temperatures in the radiator panels dropped below minus 60 degrees Farenheit during a mission. An investigation of the problem revealed that the system filters were clogged with teflon particles. The origin of the particles was traced to the krytox fluoropolymer thread lubricant grease used during loop assembly. Corrective actions were taken to remove, clean, and replace the system filters, several valves, a flow proportioning module, and a pump assembly. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
17 | Seiwell, R - 0000000000 : NO@ADDRESS.GIVEN | Seiwell, R - 0000000000 : NO@ADDRESS.GIVEN |  | Shorted Wires (From Pinching by an Uninsulated Harness Clamp) due to Reassembly Errors and a Poorly Located Cut Off Switch Resulting in a Heater "ON" Condition of an Orbiter APU Fuel Line |  | A reassembly error (a dislocated wire pinched by the uninsulated area of a harness clamp) causing a short in a fuel line heater and a poorly located cut off switch can combine to cause a control failure, and lead to potentially catastrophic damage. | Changes recommended to systems or procedures included tieing of wire bundles before clamping, using totally insulated clamps, and relocating automatic cut-off switches. | JSC | 07/29/1991 | A shuttle orbiter Auxiliary Power Unit (APU) heater system failed in the "ON" condition in flight. A post-flight investigation determined that a heater ground-side wire shorted to the uninsulated part of a wire harness clamp. The automatic shut-off switches were located such that they did not turn off the heater due to the short eliminating the switch from the circuit for the fuel and water lines heaters. The heaters were manually switched "OFF" by the crew. The short was caused by an earlier repair that opened the wire harness. When reassembled, the heater wire separated from the bundle, dislocated into the uninsulated part of the clamp, and was pinched by the clamp when it was tightened. Subsequent wear and tear resulted in premature failure of the wire insulation resulting in the short. Had this anomaly remained undetected or manual shut-off not been achieved within five minutes of the occurrence, the hydrazine fuel could have heated to the explosive auto-decomposition temperature within the line. The APU would then have failed and effects of the explosion could potentially have resulted in severe damage to the orbiter. It was further determined that under some failure modes, a shorted condition could remain undetected by both the automatic cut-off sensors and the temperature indicators that alert the crew or ground controllers of over-temperature conditions. Corrective actions included: (1) tying the wire bundles together before tightening the clamp, (2) using a clamp that has all surfaces insulated, and (3) a review of the electrical system design for relocation of temperature sensors. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
16 | Carrol, Donna - 0000000000 : NO@ADDRESS.GIVEN | Carrol, Donna - 0000000000 : NO@ADDRESS.GIVEN |  | Reversed Installation of a Check Valve Spring (Main Propulsion), Subsequent Spring Failure and Uncontrollable Reverse Flow |  | An incorrect installation of a critical component (orbiter main propulsion system check valve spring) can cause additional stresses, lead to a material failure, and result in costly launch delays. | X-Ray techniques were developed and implemented to assure correct installation of existing check valve springs and a mandatory inspection point was added for the assembly of new valves. | JSC | 07/28/1991 | When the shuttle orbiter main propulsion system oxygen manifold was pressurized to obtain gas samples, oxygen line to engine No. 3 also pressurized. The prevalves to all engines were closed and pressurization should not have occurred downstream of the prevalves. A small check valve is provided parallel to each prevalve and allows expanding fluid trapped in the manifold legs of each engine, between the prevalves and the engine valves, to relieve back into the main manifold. Upon removal of the No. 3 check valve, it was discovered that the spring holding it closed was broken and had been installed backwards. The error in installation contributed to additional stresses on the spring during earlier flow tests that lead to this failure. If the faulty installation of the spring had remained undetected and the spring had failed during cryogenic operations, uncontrolled flows into the engine leg could have caused launch delays. An X-Ray technique was developed to inspect existing valves for proper installation of the springs. A mandatory inspection point was added to the fabrication assembly procedures to preclude installation errors for this spring. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
15 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | Torque Requirements Aligned to Fitting Sizes |  | Failure to call out proper torque requirements for fittings with different sizes caused a hydraulic leak in a critical orbiter system. | Inspections are performed prior to flight to check the flex hose connections for proper torquing and for the absence of leaks. | JSC | 07/23/1993 | Hydraulic fluid leakage was noted at the interface of the flex hose and Rosan fitting on a hydraulic pump. The fittings were a different size at each end of the flex hose. Different size fittings require different torque values, which the specifications did not identify. The hydraulic system is inspected prior to each mission of the shuttle vehicle. Review of the procedure used during installation of the hydraulic system shows that one end of the flex hose was torqued to 120 foot pounds. The installation drawing does not specify that the other end of the flex hose has a smaller fitting that should require a lower torque. Leakage was corrected by a hose replaced and torqued properly. |  | N/A |  |  | Public | Not Specified |  | 09/10/1993
20 | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN |  | Debris Causing Component Failure in a Critical Piece of Crew Equipment (Shuttle Orbiter Launch/Entry Coverall Pressurization System) |  | Lack of debris protection for critical components during maintenance can result in potentially catastrophic component failures. | Corrective actions included:(1) documenting the procedural steps to require component removal, (2) protecting the components with plastic sheeting, and (3) vacuuming and inspecting the inner volume of the coverall. | JSC | 08/21/1991 | A dual suit pressure controller failed to pressurize a crew coverall during manned suit testing and the shuttle flight STS-37 Terminal Countdown Demonstration Test (TCDT). The coverall is donned by an orbiter crew member during launch and entry. No previous failures of this type had occurred before. Upon disassembly of the suit, a small piece of fabric reinforced elastomer material (from a seal called a neck dam that separates the head and torso parts of the coverall) was found lodged inside the controller on the primary diaphragm assembly seat. Before the TCDT, a rapid replacement of the neck dam was performed. The usual, but undocumented, step in the replacement procedure that called for component removal before changing the neck dam did not occur. The piece of elastomer from the old neck dam remained in the suit as debris and migrated to the diaphragm during the pressure cycling. The corrective actions included: (1) documenting the procedural steps to require component removal, (2) protecting the component area from debris by adding plastic sheeting, and (3) vacuuming the inner volume of the coverall and inspecting it following all maintenance work. A failure of a coverall of this type during flight could result in the loss of the crew member if cabin pressurization failed. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
18 | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN |  | Eddy Current Inspection for Cracks in Flight Hardware Components (Shuttle Orbiter Brake Retainer Washers) |  | Cracks in components of critical flight hardware may go undetected during pre-flight visual inspection and can lead to hardware failure and equipment damage. | The supplier implemented the use of a different riveting tool and a change in the inspection procedure to include the use of the Eddy Current inspection technique. | JSC | 07/30/1991 | The shuttle orbiter right hand inboard brake failed during the STS-7 landing, even though there was very little braking action. A post-flight tear down and evaluation of the brakes determined the cause of the failure to be defective retainers (washers), which hold together the carbon lining and the carrier plate. These retainers are made from Titanium/Zirconium/Molybde-Num (TZM), which is very resistant to high temperature and very brittle. Numerous cracked retainers were found during the inspection. The cracks, in many cases, were not perceptible with the human eye and were only detected by Eddy Current inspection. The retainers were visually inspected and replaced as required before the STS-7 flight. As corrective actions, the supplier implemented the use of a different riveting tool to minimize cracks and a change in the inspection procedure to include a 100% use of the Eddy Current inspection technique. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
19 | Crittenden, W - 0000000000 : NO@ADDRESS.GIVEN | Crittenden, W - 0000000000 : NO@ADDRESS.GIVEN |  | Erroneous Electrical System Drawings and Failure to Verify Deenergization Causing a Potentially Serious Electrical Shock Injury |  | Undocumented drawing changes to hazardous systems (480 volts AC), coupled with failure to follow required verification of system deenergization as part of lockout/tagout procedure, can lead to potentially serious injuries to electrical workers. | System drawings were updated; greater emphasis was applied to enforcing the deenergization verification steps of existing lockout/tagout procedures. | JSC | 08/21/1991 | In Building 30 at the Johnson Space Center, a contractor electrician received an electrical shock to the hand and forearm from contacting an energized (480 volt AC) power panel lug. A separate contractor, from a remote location that contained the control devices for the power panel, had switched off, tagged, and verified all circuits deenergized. An electrical drawing was used to assure all circuits were included in the safing procedure. However, a modification was performed earlier to add a lug set and wiring to the panel that was not routed through the same remote controls location as the original wires, and was not reflected on the facility master drawing. The injured electrician did not verify the lug was deenergized by testing with a meter or other device. The injury was minor (small entrance and exit burns), but could have resulted in severe injury or death had the current passed through the torso. Corrective actions included updating the facility drawings and emphasis on enforcement of existing procedures for testing circuits as part of the lockout/tagout process. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
22 | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN |  | Emergency Equipment Design to Preclude Failures (Shuttle Crew Equipment Flotation Bladder) due to Abrasive Zippers |  | The sharp edges of zippers bearing against adjacent materials can wear and penetrate the materials, resulting in potentially critical failures (shuttle orbiter crew emergency flotation assembly bladder). | A zipper protective flap was added along the entire length of the zipper. | JSC | 08/28/1991 | A bladder on a shuttle crew emergency rescue equipment inflatable flotation assembly was abraded by the zipper on the flotation sleeve, causing it to leak. Three of the flotation assemblies were flown on the orbiter for two flights and used twice in training sequences, which resulted in the zippers wearing and cutting the bladder where it passes around an emergency oxygen bottle. The corrective action taken was to add a zipper guard flap to all existing sleeves and to units to be manufactured. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
21 | Martin, S - 0000000000 : NO@ADDRESS.GIVEN | Martin, S - 0000000000 : NO@ADDRESS.GIVEN |  | Use of Particle Impact Noise Detection Test to Detect Contamination |  | Use of particle impact noise detection test will detect metallic and non-metallic particles that remain from fabrication processes. | Suppliers perform a Particle Impact Noise Detection (PIND) test on all limit switches prior to delivery. | JSC | 08/29/1991 | During various shuttle orbiter missions, several anomalies occurred which were subsequently attributed to particle contamination within limit switches. In three such instances the particles were metallic substances and of a sufficient size (greater than 0.015 inches) to create a premature state change. In a fourth instance, the particle contamination was non-metallic which resulted in a high contact resistance and the loss of a "closed" indication. These switch failures were attributed to contamination from metallic (weld expulsion, less than 0.010 inches), glass from headers, ceramic from insulators, rubber from back-filling equipment, polymers, and polyesters. Limit switches are often used to: (1) prevent systems or components from reaching damaging stress levels and, (2) inhibiting unwanted events or conditions. The primary corrective action to prevent recurrence of these failures was to impose Particle Impact Noise Detection (PIND) testing on all future limit switch manufacturing. additional techniques included improved cleaning processes and the addition of filters to purging and drying fluids to preclude particle introduction into the components. |  | N/A |  | Aeronautics Research, Exploration Systems, Space Operations | Public | Not Specified |  | 09/10/1993
3 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Hazard Potentials Associated With Maintenance in High Valued, Mission Critical Areas (Mission Control at JSC) |  | Additional preparedness and precautions are necessary to preclude damaging incidents during installation or maintenance operations performed in high value and mission critical areas. | The investigation board recommended correcting deficiencies in the work procedures, emergency plans, and mission control allowable work policies; and training of personnel for these changes. | JSC | 03/31/1991 | While installing electrical cables into a conduit in the Johnson Space Center Mission Control Room, the conduit was displaced from its mounting, and then contacted and broke a chilled water line. A portion of the room was flooded. The installation procedures did not include details for using sufficient lubrication on the cables being pulled through the conduit. Also, no cautions or warnings were provided to alert the electricians to take additional precautions to prevent accidents in a high value, mission essential area. Other factors that increased the extent of damage included; (1) an emergency plan that did not include water leaks, and (2) no information was available to the maintenance or operations personnel on the location of or access to shutoff systems. The investigation board recommended correcting the deficiencies in the work procedures, emergency plans, and mission control allowable work |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/09/1993
2 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Solder Defects Reduction by Training/certification of Technicians |  | Contamination of solder can result in connection defects and failures in electrical systems. | Training and certification of the solder technicians was upgraded to aerospace quality specifications DOD-STD-2000. | JSC | 10/17/1989 | Following the shuttle mission STS-34, it was determined that a vent door actuator operated on two of the three electrical phases. The vent door actuator was replaced. During the failure analysis, a defective solder joint was found on a lead connection to a printed circuit board, analysis indicated the solder was contaminated with room temperature vulcanizer (RTV) silicone potting compound. Records revealed that this defect occurred prior to the requirement to train and certify the solder technicians to the aerospace quality standard DOD-STD-2000. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/09/1993
7 | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN | Underwood, Leroy - 0000000000 : NO@ADDRESS.GIVEN |  | Debonding of a Mounting Device (Shuttle Orbiter TV Monitor Bracket) due to Growth of a Pressurized Vessel such as the Crew Cabin Wall Following Launch |  | Deformation or growth of base material (wall of orbiter crew cabin) from pressurization can cause debonding of hardware attached with adhesives. | Stiffeners were added to a section of the crew cabin wall to reduce the growth effects from pressurization. | JSC | 04/29/1991 | During two successive missions of the shuttle orbiter OV-99, a television monitor secured by a bracket that was bonded to the wall of the crew module, became detached from the wall (debonded). Following the first incident, it was assumed that an improper bonding technique was the cause of the failure. Remounting was accomplished under close surveillance by quality inspectors. Following the second incident, it was concluded that growth of the structural skin of the wall due to pressurization during flight caused the failure. It was explained that this did not occur on orbiter OV-102 because its wall is thicker and subject to less growth from pressurization. An object as large as a TV monitor detaching from its mount during any phase of a mission could become a hazard to personnel or equipment. The wall section of OV-99 used for mounting the monitor was stiffened with wall doublers to reduce growth from pressurization during launch. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 09/09/1993
8 | Chappee, J - 0000000000 : NO@ADDRESS.GIVEN | Chappee, J - 0000000000 : NO@ADDRESS.GIVEN |  | Hazard Criticality in the Design and Manufacture of and the Selection of Materials for use in High Pressure Gaseous Flow Systems (Oxygen) |  | Failure to minimize flow passage configurations which can trap debris or create stagnation points in high pressure oxygen systems may lead to compression or shock heating effects causing fire, injury, and equipment damage. Failure to consider resistance to ignition and a tendency to propagate a fire in the selection of materials for use in high pressure oxygen may lead to fire, injury, and equipment loss. | The mishap investigation board recommendations included: high pressure oxygen components should be designed to minimize flow configurations which may trap debris or create stagnation points, and minimize the generation of internal contamination. The mishap investigation board recommendations also included: evaluation of existing high pressure oxygen systems and replacement of existing metallic and non-metallic materials (silicone for silastic 675 in o-rings and monel for aluminum in regulators). | JSC | 06/10/1991 | A flash fire occurred during a performance record test of the shuttle Extravehicular Mobility Unit (EMU). This fire occurred when a shutoff valve was opened, supplying 6,500 psi oxygen to the EMU. Ignition occurred and a very high temperature oxygen- rich aluminum fire ensued. The shutoff valve melted in the fire, relieving the system pressure and causing the metallic fire to extinguish. Residual fires were extinguished using carbon dioxide extinguishers. A finding of the mishap investigation board was that the most probable ignition site was within the regulator module in a flow restrictor. This flow restrictor consists of two drilled passages, which intersect in a "V" shape. Manufacturing practices allow some overdrill at the intersection of these two passages, which may have formed a stagnant volume at the base of the "V". This stagnant volume allows compression heating (adiabatic compression detonation) and/or shock heating, which ruptured and ignited a thin section of aluminum and spread to the other metallic components of the module in the oxygen enriched atmosphere. Other possible ignition mechanisms included (in priority order): Compression and/or shock heating of contaminant(s) entrapped in the stagnant volume of the flow restrictor (all five other regulators disassembled and inspected showed some particulate debris within the system). Mechanical heating of or by particulate contamination impinging on a surface. Compression and/or shock heating of one of the silastic o-rings in the shutoff assembly. Testing at White Sands Test Facility was unable to duplicate these events in over 2200 attempts or confirm any of these ignition mechanisms. |  | N/A |  | Exploration Systems, Space Operations | Public | Not Specified |  | 09/09/1993
4 | Michael, T - 0000000000 : NO@ADDRESS.GIVEN | Michael, T - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Hardware Damage (Tires) due to Ground Test System Operational Conditions Outside of Design Limits |  | Lack of fidelity between ground test system configuration and the flight system configuration can result in costly and damaging test failures to flight hardware during ground testing. | The test stand configuration was changed to operationally duplicate the flight system (the switching valves and other hardware and software items). Also a procedural step was added to stop the skidding if it occurs. | JSC | 04/19/1991 | On November 21, 1989 two shuttle orbiter tires skidded sufficiently to cause blowouts following the application of brakes during a ground test at Wright Patterson Air Force Base. The skidding was caused by the brakes locking due to the failure of the anti-skid system. This failure was due to the use of non-flight switching valves as part of the test stand. Additional damage occurred to a hydraulic hose and quick disconnect fitting. An investigation also discovered an error in the abort software and the addition of excessively restrictive non-flight orifices in the brake hydralic lines. All of these findings contributed to the failure. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/09/1993
5 | Michael, T - 0000000000 : NO@ADDRESS.GIVEN | Michael, T - 0000000000 : NO@ADDRESS.GIVEN |  | Inadequate Electrical Cable Strain Relief Design Leading to Shorts and Ignition |  | Inadequate strain relief design for electrical cables can result in electrical shorts and subsequent ignition within closed environments such as the shuttle orbiter crew cabin. | The orbiter teleprinter cable strain relief device was redesigned and the wire insulation was changed from kapton to teflon. Designs of other orbiter system cables were reviewed and existing cables inspected. | JSC | 04/21/1991 | A pair of shuttle orbiter teleprinter 28 VDC power cable wires shorted together. A short section of wire and insulation ignited and burned releasing a small amount of contaminants within the crew cabin. The burn through produced an open circuit, but was of insufficient duration (150 milliseconds at 50 amps) to open the circuit breaker. The crew manually opened the breaker and removed the cable. An investigation determined the cause of the failure was inproperly designed strain relief at one end of the cable where mated. The resultant flexure of the cable caused 360 degree annular breaks in the insulation of the power wires adjacent to each other. The cable was redesigned to utilize a more effective 90 degree bend strain relief device. The wire insulation material was changed from kapton to the more flexible teflon. Other orbiter cables of similar design were inspected and designs reviewed to preclude problems in similar configurations. This incident involved a non-mission essential component and the crew was potentially exposed to voltages below human shock hazard levels. However, the failure produced an ignition source. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/09/1993
6 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Orbiter Exterior Panel Separation During Flight due to Incorrect Installation (Washers not Provided Under Fasteners) |  | Incomplete assembly or installation instructions (no reference to the use of washers) can result a in poorly fastened exterior mounted component (orbiter OMS carrier panel) causing loss of the component and potentially hazardous debris. | Procedures were changed to include detailed instructions for installing washers. All similar orbiter panels were inspected to preclude recurrence of the anomaly. | JSC | 04/28/1991 | Following the shuttle mission STS-27, the right side orbital maneuvering system (OMS) pod carrier panel on the orbiter OV-104 was missing. It was concluded that the panel was installed incorrectly. Six flat washers were not installed under the mounting fasteners. This caused damage to the base panel material upon installation. The panel became loose during flight, produced a gap, and was pulled off by the air flow. No additional damage was sustained by the orbiter thermal protection system or other orbiter components. The panel installation procedures did not clearly identify the requirement for the washers. The procedures were revised to include the steps for installing the washers. Approximately 100 orbiter panels of similar configuration were recommended for inspection to assure this anomaly was not present elsewhere within the orbiter fleet. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/09/1993
1 | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN | Underwood, L - 0000000000 : NO@ADDRESS.GIVEN |  | Implementation of Procedural Controls in Additional Procedures Beyond the Procedure Under Investigation and Correction |  | Recurrence controls to prevent an original manufacturing defect should be expanded to address any items already deployed in field including those to be reprocessed or reworked. | Ensure that any process modifications are considered for implementation in all units that were previously distributed or deployed - not just to those units processed after the process was modified. | JSC | 04/09/1991 | During prelaunch check out of shuttle orbiter OV-104 for flight STS-36, the AC2 buss phase a voltage fluctuated between 112 and 122V for one minute. The inverter supplying that buss was removed and replaced. The vendors' inspection of the failed inverter found loose mounting screws on the electrical buss internal to the inverter, which caused the voltage fluctuations. An identical problem had been previously discovered that prompted a change to the manufacturing procedures to include a specified torque for the mounting screws. The failed flight unit had been reworked, but the manufacturing procedural change had not been incorporated into the rework process. |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 09/09/1993
304 | Gussner, A - 0000000000 : NO@ADDRESS.GIVEN | Gussner, A - 0000000000 : NO@ADDRESS.GIVEN |  | SIR-C Low Noise Amplifier Recovery Time too Long | Excessive Low Noise Amplifier (LNA) recovery time had not been detected because testing had been done in transmit-only or receive-only modes. Hardware should be functionally end-to-end tested. Early module level functional tests should be performed to detect RF timing/leakage issues. | Hardware should be functionally end-to-end tested. | End-to-end system tests to simulate actual use must be performed as early as possible in the test sequence. Early module level functional tests should be performed to detect RF timing/leakage issues. | JPL | 09/15/1993 | When the C-Band pulse from the transmitter was present in the antenna panel, the Low Noise Amplifier (LNA) in the receive chain had a long recovery time of up to 200 microseconds. The transmit/receive module of the antenna received transmit pulse leakage into the LNA which shifted the operating bias and caused the long recovery time before the LNA was enabled. All previous testing of the panel had been done in transmit-only or receive-only modes. Correction of the problem required extensive rework of the panels. Covers, harnesses, and printed wiring boards were removed to gain access to the transmit/receive modules. Then two resistors were replaced and five capacitors were removed from each of twenty-eight modules in each of the nineteen panels. Additional Keyword(s): RF Performance Verification Reference(s): PFR #56187 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.1.2 ("Engineering Practices: Project and System Level Functional Verification and Validation - Planning"), and Paragraph 6.17.6 ("Engineering Practices: Hardware Development") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 09/02/1993
297 | Lord, D - 0000000000 : NO@ADDRESS.GIVEN | Lord, D - 0000000000 : NO@ADDRESS.GIVEN |  | Integrated Circuit Damage due to Capacitor Residual Charge | When a discrete capacitor was installed in an electronic assembly, a residual charge on the capacitor discharged through an integrated circuit itself and damaged the input circuit of the IC. Run tests to verify that procedures for the handling and storage of capacitors eliminate residual charges, and short capacitor leads just prior to installation. | Capacitors can accumulate a residual charge, through normal handling and storage, sufficient to damage an integrated circuit. Assembly procedures may not adequately address the concern regarding the possibility of residual charges on capacitors, and the potential damage to integrated circuits. | Tests should be run to verify that procedures for the handling and storage of capacitors to be used in electronic assemblies result in the absence of capacitor residual charges. Assembly procedures should require the shorting of capacitor leads just prior to installation. Capacitor leads should be shorted from manufacturing through storage. | JPL | 08/04/1993 | Following installation of a discrete capacitor on an electronic assembly of a non-JPL project, an integrated circuit (IC) on that assembly was found to be inoperative. Further analysis indicated that the IC was damaged and that one of the chip inputs had likely been subjected to an excessively high current (the IC damage was similar to that which results from an Electrostatic Discharge (ESD) condition). It was not clear whether or not the assembly procedures being followed included the use of established techniques designed to protect components from ESD. Additional review concluded, however, that the excessive current likely originated from a residual charge on the capacitor that had just been installed, and which was electrically connected to the IC input that failed. Laboratory tests were conducted and verified that, unless special precautions were taken, capacitors could accumulate a residual charge, through normal handling and storage, that is sufficient to destroy an integrated circuit if allowed to discharge through one of its inputs. The conclusion was that the subject capacitor likely had a residual charge, and when it was electrically connected to the input of the IC, it discharged through the IC itself and damaged the input circuit. Additional Keyword(s): Electronic Parts Handling Reference(s): JPL IOM #523-WRW-91-390, W. R. Woods, Circuit Damage due to Assembly with a Charged Capacitor. | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.4 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 08/26/1993
329 | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | Insulation, Solid Rocket Motor Case, Bonding, Effect of Contamination |  | The potential exists for contamination on rocket motor case walls, which can interfere with bonding of insulation. | Assure that contamination on internal rocket motor case walls is acceptably low by (1) performing bonding tests on "witness" samples which have been subjected to the same processes as the flight hardware, and, (2) inspecting the case walls by techniques such as ultraviolet light to determine if the cleanliness level is equal to or better than the witness samples. | MSFC | 06/11/1993 | Loss of Challenger | Self-evident that a clean surface will provide a better bond than a contaminated surface | N/A |  |  | Public | Not Specified |  | 06/11/1993
323 | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN | Fisher, Mark - 0000000000 : NO@ADDRESS.GIVEN |  | B-nuts, Fluid Lines, Leakage, Inadequate Torque |  | B-nuts are difficult to torque properly and are prone to leak | Avoid the use of b-nuts in fluid systems | MSFC | 06/08/1993 | Coolant leak developed on the Skylab which was attributed to B-nuts. | If B-nuts are not used, there is no B-nut problem. Other methods have been shown to be superior | N/A |  |  | Public | Not Specified |  | 06/08/1993
296 | Gresham, L - 0000000000 : NO@ADDRESS.GIVEN; Blosiu, J - | Gresham, L - 0000000000 : NO@ADDRESS.GIVEN |  | Glitches on the Discrete Command Outputs of the Remote Interface Unit (RIU) due to Inherent Integrated Circuit Race Condition | RIU glitches that resulted from a known design problem were benign for Voyager, but posed a serious problem for Topex due to its requirement for faster circuit response. When the glitches occurred during Topex assembly level acceptance test, costly modifications were necessary. Electronic parts should be utilized only as per manufacturer's recommendations. Fully consider new assumptions, performance requirements, and potential risks when adopting an inherited design or inherited test plans. | Misuse of electronic parts can cause unexpected chip output response with serious mission impact. RIU's are frequently utilized in executing critical subsystem spacecraft function. Use of "inherited" designs does not preclude the need to perform in-depth analyses of all elements. | Electronic parts should be utilized only as per manufacturer's recommendations. Cognizant design engineers must consider fully the difference between the current and prior assumptions, electrical performance required, and potential risks when adopting an inherited design. Extreme care should be taken when applying any inherited designs since they do not ensure reliability. Similar care should be exercised when implementing inherited test plans. | JPL | 08/04/1993 | At assembly level acceptance test, 90% of the Topex RIU's used on the discrete command channels experienced malfunctions (glitches). This problem resulted from the decision to do strobing of the power VCC on/off line rather than using a designated strobe line. This type of unconventional strobing generated a voltage race problem, which translated into an unequal voltage propagation delay internal to the chip, thus causing chip malfunctioning. This design decision dates back to the Voyager project. The RIU glitch phenomena occurred in Voyager, but was considered benign due to slower circuit response required by Voyager. On Topex, resolving the glitch problem required A) screening and assigning of sixteen RIU's to locations less affected by glitches, and B) inserting RC filters on the central unit harness connector to eliminate glitches in spacecraft commands from the central processor. The described costly Topex modifications were necessary to reduce the risk associated with the misuse of this part. Additional Keyword(s): Poseidon Reference(s): PFR #C04068 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.6.2 ("Engineering Practices: Inheritance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 03/25/1993
306 | Lord, D - 0000000000 : NO@ADDRESS.GIVEN | Lord, D - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo/Ulysses Helicoil/Bolt Problems on RTGS | During installation of the Pressure Release Devices (PRD) to the Galileo's RTGs, the four screws anchoring each PRD failed to pull snug to the RTGs. A year later, a screw attaching a PRD to the Ulysses RTG seized and sheared. The problem was attributed to inexperience with the helicoil locking feature. Avoid use of helicoils, and provide detailed assembly procedures for locking devices. | Helicoil locking devices can cause problems in applications requiring repeated engagements of the locking feature. Potential problems, associated with temporary screw insertions into helicoils, can be minimized if shorter lubricated screws are used to assure minimal penetration of the locking mechanism. | The use of helicoils should be avoided. The use of locking devices should require the generation and use of detailed assembly procedures, clearly identifying potential problem areas and torquing limits for both temporary and final installations. | JPL | 09/15/1993 | On October 7, 1989, during installation of the Pressure Release Devices (PRD) to Galileo's RTGS, the four screws anchoring each PRD failed to pull snug to the RTGS when the assembly crew applied what was considered to be acceptable torque. Further insertion of the screws was halted and washers were added to allow a snug fit. Analysis and a vibration test indicated that the thread engagement was sufficient to proceed with the launch. On October 2, 1990, during installation of the PRD to the Ulysses RTG, the fourth and last attachment screw seized and subsequently sheared. Extensive analysis and consultation with General Electric indicated that a sufficient safety margin existed to proceed with the launch even with the PRD anchored by only three screws. Neither of these incidents in any way compromised the safety or functionality of the PRD/RTG. On October 16, 1990, a PRD anomaly review board was established to investigate the cause of these anomalies and make recommendations. The board has found that the Galileo anomaly resulted from inexperience with the helicoil locking feature. The Ulysses screw seizure most likely resulted from prior use of an unlubricated cover screw and/or some earlier degradation of the helicoil. Additional Keyword(s): Fastener Reference(s): JPL D-9625, Galileo/Ulysses Pressure Release Device (PRD) Anomaly Review Board Report; PFR #54340 AND #54365. |  | N/A |  |  | Public | Not Specified |  | 02/04/1993
349 | Clawson, J - 0000000000 : NO@ADDRESS.GIVEN | Clawson, J - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan (MGN) High Rocket Engine Module (REM) Temperatures | Early in the flight, Magellan REM temperatures exceeded predictions by over 20 degrees C. for certain spacecraft orientations. This necessitated changes in the mission profile. Subsystem thermal design modifications had been made based solely on analysis and implemented without any test verification. Design changes should be verified by test. The prime contractor should be responsible for thermal integration of the REM. The REM should be subjected to a series of solar thermal vacuum orientations at the subsystem level. | Subsystem thermal design modifications based solely on analysis and implemented without any test verification can result in unexpected system level constraints. System thermal integration analysis and testing can function as an independent verification of subsystem thermal design. | Thermally isolated subsystems with complex geometries such as the REM should be subjected to a series of solar thermal vacuum orientations at the subsystem level. Given the lack of a REM subsystem solar thermal vacuum test, the spacecraft system thermal vacuum test fixturing should allow much greater flexibility in orientation simulation. Design changes should be verified by test. Had a flight spare (or developmental) REM existed, such a retest would have easily shown that the problem was not solved. Thermal integration of the REM should be the responsibility of the prime contractor, not the REM supplier. | JPL | 10/26/1994 | Early in the MGN flight, REM temperatures exceeded predictions by over 20 degrees C. for selected ranges of spacecraft orientations. During the MGN System Thermal Vacuum Test (STV) in July 1988, the REM exhibited a similar problem in that temperatures were about 25 degrees C. warmer than expected. There were no REM subsystem solar thermal vacuum tests conducted prior to the STV. Since the only solar thermal vacuum test was conducted at the system level, attainable REM orientations during that test were restricted. Following the STV, modifications based solely on analyses by the REM supplier were implemented without any test verification. Current thinking (based on flight data) is that in addition to nozzle entrapment of solar energy, the thermal model was too simplified; and the thermal surface properties of the engines were different than originally thought. The REM high mission temperatures caused two major impacts: 1) the mission attitude profile had to be significantly modified to avoid overheating the REMS, which was a major constraint on mission operations, 2) a major ground test program was required to demonstrate temperature capabilities above the original upper limits. Additional Keyword(s): Design Fix Verification Reference(s): PFR #52226 (ISA #5069), PFR #52227 (ISA #5552) | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.14.1.3 ("Engineering Practices: Project and System Level Functional Verification and Validation - Planning") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.8.1.1 ("System Thermal Design: General - Design Tailored to Specific Application") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 01/29/1993
283 | Clawson, J - 0000000000 : NO@ADDRESS.GIVEN | Clawson, J - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan (MGN) High Electronic Temperatures | Magellan electronics bays ran 20 degrees C. hotter in flight than was anticipated. Contaminants were believed to have off-gassed in flight and accumulated on the thermal tiles, thus increasing solar absorptance. Evaluate vacuum outgassing procedures, and demonstrate system operation at temperatures beyond those expected in flight. For missions to inner planets, the spacecraft system thermal control design should minimize or avoid solar exposure on critical thermal control surfaces. | Effects of contamination on critical thermal control surfaces can be more severe than previously assumed, resulting in higher than expected flight temperatures. The Mariner 10 thermal control concept (a sun pointing spacecraft with a large sun blocking thermal shade) would result in fewer thermal issues than the transient attitude thermal design employed on Magellan. | Vacuum outgassing procedures should be evaluated for consistency and effectiveness. System operation at temperatures beyond those expected in flight should be demonstrated during ground system thermal vacuum tests. For missions toward the sun from earth, the spacecraft system thermal control design should minimize or avoid solar exposure on critical thermal control surfaces. | JPL | 07/12/1993 | Early in the MGN mission, sun viewing bus bays (and associated electronic subsystems) were at least 20 degrees C. hotter than anticipated. This effect increased as the mission continued. Temperatures were at or above flight acceptance levels, and for short periods of time, at or near qualification levels for some bays. Fortunately a special margin test phase during the MGN solar thermal vacuum ground test had demonstrated system operations at these temperatures. Even higher equilibrium temperatures were anticipated as the mission progressed. The apparent solar absorptance increase (derived from the flight temperatures) for MGN is generally global and appears to be approximately twice that expected based on known data bases. Fairly recent theoretical and experimental work shows the possibility that contaminants (organic molecules in particular) outgassed by the spacecraft and/or solar panels may be the cause of increased absorptance (through interaction with solar ultraviolet radiation) and thus higher temperatures. The MGN effect may be due to the greater ultraviolet energy at Venusian solar distances compared to Earth (about 2 solar constants). The MGN solar panels received only minimal outgassing prior to flight (20 hours). The impacts of these high subsystem temperatures were significant. Extensive unplanned analyses and mission planning activities were required, including spacecraft attitudes to prevent even higher temperatures, and some mapping science was lost. Were it not for the confidence gained during the solar thermal vacuum test at these higher temperatures, significantly more science would have been lost. The long life of MGN is certainly threatened: concerns exist for both electronic part life and solder joint fatigue. Additional Keyword(s): High Temperature Reference(s): PFR # 52228, ISA # 5649 | JPL has referenced the lesson as supporting Paragraph 4.8.2.1 ("System Thermal Design: Temperature Control Design Performance - Temperature Control Design Margin") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006. | N/A |  |  | Public | Not Specified |  | 01/29/1993
351 | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN; Wagoner, B - | Guernsey, C - 0000000000 : NO@ADDRESS.GIVEN |  | Galileo Messerschmitt-Bolkow-Blohm (MBB) Ten Newton Hot Start Phenomena | During confidence testing of the MBB Galileo Ten Newton (N) Engine at MBB in November 1988, rapid increases in combustion chamber temperature (“hot starts”) were sometimes observed immediately after ignition of the engine. Examination of test data from the previous flight engine acceptance tests showed evidence of hot starts, but JPL had not witnessed these earlier tests. The lesson recommends several measures to assure that rocket engine development and qualification test instrumentation and test documentation are sufficient to detect and diagnose combustion instabilities. | Lack of appropriate rocket engine development and qualification test instrumentation and test documentation can result in failure to detect and diagnose combustion instabilities. Bubbles saturated in the propellant can be a contributing factor to triggering rocket engine combustion instability. | Critical rocket engine component subsystem test procedures and actual performance should be carefully monitored by appropriate technical and quality assurance personnel. Test data from all qualification and flight acceptance testing of critical rocket engine component subsystems should be obtained, reviewed, and archived by JPL. The stability of new rocket engine designs should be intensively studied early in the development and/or qualification cycle. Rocket engines should be tested with propellants which have been verified to be saturated with pressurant gas. | JPL | 11/14/1994 | During confidence testing of the MBB Galileo Ten Newton (N) Engine at MBB in November 1988, rapid increases in combustion chamber temperature were sometimes observed immediately after ignition of the engine. These "hot starts" required manual intervention to stop the test before overheating could produce engine damage. Subsequent examination of test data from the previous flight engine acceptance tests revealed that the "hot start" phenomena had also been present in those tests. JPL did not witness, or request detailed data from, these earlier tests. The "hot start" phenomena was eliminated by moving the engine trim orifices downstream of the engine valve and changing the flight operating mode of the thrusters. The design change was based on empirical testing of several configurations, since the instrumentation available did not allow the nature or cause of the phenomena to be precisely determined. Over 20,000 firings were conducted after the orifice change without further occurrences of "hot starts". Other combustion instabilities (NCR 892) and unacceptable thermal performance (NCR's 884, 889, AND 894) were, however, noted in some pulse mode and continuous firings. The Galileo mission was redesigned to avoid continuous firings of the 10 N thrusters and to restrict pulse mode duty cycles so that the impacts of "hot starts" or other thermal instabilities, should they occur in flight, would be minimized. The "hot start" phenomena is now known, based on subsequent data collected for other spacecraft projects, to be a 30 KHz acoustic instability of the MBB 10 N combustion chamber and injector. It is likely that the instability was triggered by severe ignition transients which were alleviated by the new orifice configuration. Bubbles saturated in the propellant, produced by the original orifice configuration, also appear to be a contributing factor to triggering the instability. Additional Keyword(s): Supplier Testing Reference(s): NCR #883 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.6 ("Engineering Practices: Project and System Level Functional Verification and Validation - Planning") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. In addition, JPL has referenced the lesson as supporting Paragraph 4.7.1.2 ("Flight System Design: Propulsion System Design - Demonstration of Operating Point") in the JPL standard "Design, Verification/Validation and Operations Principles for Flight Systems (Design Principles)," JPL Document D-17868, Rev. 3, December 11, 2006.” | N/A |  |  | Public | Not Specified |  | 10/01/1992
267 | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN | Wagoner, B - 0000000000 : NO@ADDRESS.GIVEN |  | TOPEX/POSEIDON Near-Drop Incident | In preparing Topex/Poseidon for system test in 1993, the lifting fixture was severely damaged while lifting the spacecraft. Conduct rigorous analysis to verify and demonstrate that the lifting configuration is stable. Ensure qualified, experienced personnel are on site during critical hazardous operations. | The reuse of a residual lifting fixture from previous programs is encouraged, but requires analysis by the current planned user for its application. Lifting activities and other critical operations may involve unanticipated risks to spacecraft. | Analysis of the design, load application and stability of a lifting fixture assembly, and the center of gravity of the load to be lifted, must be rigorously performed to verify and demonstrate that the final configuration is stable. Ensure qualified, experienced personnel are on site during critical hazardous operations. | JPL | 07/07/1993 | As part of the preparation for the testing of the TOPEX/POSEIDON spacecraft, the spacecraft and its thermal vacuum fixturing assembly were being lifted and positioned above the thermal vacuum chamber when the assembly began a slow overturning rotation. The assembly rotated approximately 135 degrees before it was halted by the entanglement of the Spacecraft Horizontal Support Structure (SHSS) with one of the four lifting fixture suspension cables. While resting in this anomalous position, the test team visually determined that the lifting fixture spreader bar (inherited from the Galileo program) had sustained considerable damage and might fail. A decision was made by the Fairchild Systems spacecraft manager to lower the assembly to the chamber floor as quickly as possible to protect the spacecraft and remove the load from the damaged spreader bar. The assembly was lowered to the chamber floor where it was temporarily secured. While no major spacecraft damage resulted from the incident, it would have been catastrophic to the TOPEX/POSEIDON Program if the satellite had actually been dropped. Additional Keyword(s): Handling, Hardware Safety Reference(s): PFR #53523 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware"), and Paragraph 6.6.3 ("Engineering Practices: Inheritance") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 09/24/1992
273 | Iskenderian, T - 0000000000 : NO@ADDRESS.GIVEN | Iskenderian, T - 0000000000 : NO@ADDRESS.GIVEN |  | TOPEX/POSEIDON Solar Array Drive (SAD) Drop | Two days prior to the planned delivery of the flight Solar Array Drive, the unit was accidentally dropped on the floor. An employee who was unfamiliar with the device tilted the assembly to take a measurement, unaware that the SAD was not fastened to the fixture. The recommendations center on training and procedures, examination of the fixtures before use, and QA involvement. | There is a potential for damage whenever flight hardware is handled, even for operations that may appear to be very routine. Utilization of existing fixtures for purposes other than as originally designed increases the risks involved in handling of flight hardware. When new personnel are brought onto a job, or duties are shared among existing personnel, hardware handling operations incur additional risks. | Employees should be familiarized with clear, safe handling practices and instructions written and agreed upon by both the NASA center and the contractor. These standards should be posted in work areas and enforced by quality assurance. Perform a careful examination and review of potential risks prior to utilization of existing fixtures for additional handling operations. Quality assurance personnel should review and approve all fixturing and setups for flight hardware prior to use. Inexperienced personnel should be supported by experienced personnel for a time sufficient to assure that they have been adequately trained in handling of flight hardware and are thoroughly familiar with the hardware and associated procedures. Use special awareness in the development of handling procedures and techniques in the event that someone other than the originator may be required to perform those functions. | JPL | 07/08/1993 | Two days prior to the planned delivery of the flight Solar Array Drive, the unit was accidentally dropped on the floor. Final dimensional inspection was being performed on the SAD at the contractor's facility. The device was cradled in its drilling and alignment fixture, but in order to accommodate inspection, was not fastened down. There were no instructions to fasten the SAD to the fixture during manipulation, nor were any warnings posted to indicate that special caution was necessary during the inspection process. There were no documented requirements for quality assurance (QA) or other cognizant personnel to witness the inspection, and none were present. An employee who was unfamiliar with the device tilted the assembly to take a measurement, unaware that the SAD was not fastened to the fixture. The SAD tumbled out of the fixture, rolled across the surface plate, and fell about 40 inches to the floor. Its housing was damaged in at least two areas, and there was concern that the output bearings had also been damaged by the impact. The SAD was disassembled to facilitate damage assessment, and extensive analysis, testing, and inspection were performed to determine its flight worthiness. No evidence of bearing damage was noted, but repair of the damaged housing areas was required. The Material Review Board (MRB) agreed with the proposal to reassemble the SAD without replacement of any major components. Following the reassembly and inspection, flight acceptance tests (including environmental tests) were successfully repeated. The incident resulted in a two month delay in the SAD delivery and considerable cost increase to the program. A major effort was required by the review board and the JPL/Contractor SAD teams to assess, rework, and retest the SAD to assure its flight worthiness. Reference(s): PFR #55704, MRB 00036 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.12.5.3 ("Engineering Practices: Protection and Security of Flight Hardware") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 09/24/1992
268 | Borden, T - 0000000000 : NO@ADDRESS.GIVEN; Wagoner, B - | Borden, T - 0000000000 : NO@ADDRESS.GIVEN |  | Cracks in the Body of Dual Inline Package (DIP) Components in the ASTROS Star Tracker Electronic Assembly | Functional testing of the ASTROS Star Tracker Electronic Assembly revealed a hairline crack that appeared to have been caused by lead bending tools used to form the part leads for installation. The tooling had been previously used successfully on this part type but a different lot number. Part types requiring mechanical lead forming should have approved procedures and qualified processes with adequate sample testing prior to forming component leads for installation into flight hardware. | Lead bending tooling used on a particular component part type may not be acceptable for use when the part is from a different lot number or a different vendor. | Component part types, requiring mechanical lead forming, should have approved procedures and qualified processes with adequate sample testing prior to forming component leads for installation into flight hardware. | JPL | 07/07/1993 | During functional testing of the S/N 002 ASTROS Star Tracker Electronic Assembly at Kennedy Space Center, the unit indicated an incorrect brightness level when viewing a test star. Careful inspection of the assembly electronics revealed a hairline crack near the middle of the body of one of the dip components. Investigation showed the crack could be duplicated on this component part type by use of lead bending tools required to form the part leads for installation. The tooling had been previously used successfully on this part type but a different lot number. Additional Keyword(s): Cracked Components Reference(s): PFR #33998, #41720 |  | N/A |  |  | Public | Not Specified |  | 07/16/1992
275 | Borden, T - 0000000000 : NO@ADDRESS.GIVEN; Wagoner, B - | Borden, T - 0000000000 : NO@ADDRESS.GIVEN |  | Stressed or Damaged Solder Joints on Flight Hardware Due to Thermal Cycling | Over the years, numerous incidents of failed solder joints have occurred to electronic equipment at JPL and contractor facilities. The problem was traced to thermal cycling of conformal coatings. The lesson recommendations pertain to prediction of the thermal cycling environment, application of conformal coatings, packaging design reviews, and packaging design and fabrication processes, procedures, and documentation. | Solder joints will be damaged due to fatigue stresses induced by thermal cycling in the presence of high thermal coefficient of expansion materials, or by the exposure of conformal coatings to some cleaning solvents. Excessive conformal coating material between the printed circuit board and bottom of the electronic component, combined with environmental factors, can create forces sufficient to cause solder joint fracture. | Solder fatigue life should be treated as a mission consumable for the packaging design. Estimate the total mission thermal cycling expected in ground and flight operations, and compare with the demonstrated fatigue life capability of the hardware. The space between the printed circuit board and the electronic components must not be filled with conformal coat material unless thermal heat sinking is needed, and then the material must not exceed the thickness specified in approved documentation. Packaging design reviews should assure that approved design processes and procedures have been met. Electronic packaging design and fabrication must follow proven and qualified processes and procedures, and documentation must be regularly updated and maintained to meet current design needs. | JPL | 07/09/1993 | During recent years numerous incidents of failed solder joints in electronic equipment have been identified in hardware fabricated both at JPL and JPL Contractor facilities. Examples include: GALILEO, PFR #52012, Command Data Subsystem: Intermittent failure in solder joints at flat pack lead attachment to the printed wiring board. ASTROS Star Tracker, PFR #33998, Electronic Assembly failure: Solder connection open at a Dual Inline Package Integrated Circuit (DIP IC) lead to the printed wiring board. MAGELLAN, PFR #55263, Data Formatter, Electronic Assembly failure: Solder connection open at a DIP IC lead to printed wiring board. WF/PC-1 PFR #53914 Microprocessor failure: Solder connection open at a DIP IC lead to printed wiring board. ACRIM II, PFR #44478: Electronic Module solder joints were observed to have stressing/cracking at the DIP IC lead to printed wiring board interconnect. MLS, PFR #43374: Solder joint on input bias wire had stress cracks. Investigation of the above items reveal a common element of cause. Conformal coating (polymeric substance applied to protect from the environment) material filled the space between the printed circuit board and the bottom of the electronic component, and thermal cycling, and/or prolonged exposure to solvents, created the large forces required to cause solder joint fracture. |  | N/A |  |  | Public | Not Specified |  | 07/16/1992
272 | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN | Schaper, P - 0000000000 : NO@ADDRESS.GIVEN |  | Flight Anomaly of Atmospheric Trace Molecule Spectroscopy (ATMOS) Instrument, Risk Assessment | The ATMOS instrument experienced a randomly occurring failure on the ground that was fixed each time by resetting the instrument. After an extended investigation that failed to identify the failure mechanism, the workaround was employed successfully on repeated Shuttle flights. For low-cost, reflyable experiments, generate preplanned in-flight workaround procedures for random performance anomalies to enable successful repeated flights, consider cost tradeoffs in risk assessments, and view the testing and qualification rules established for single flight projects as guidelines only. | Low-cost experiments with plans for repeated flights can yield a large volume science return in spite of random performance anomalies. Low cost STS-borne experiments with plans for repeated flights, exemplified by the ATMOS spectrometer, require risk assessments different from those used for single launch experiments. The lack of second instruments (breadboard or prototype) for low budget projects makes thorough testing of flight instruments difficult when flight schedules need to be met. | Generate preplanned in-flight workaround procedures for random performance anomalies to enable successful repeated flights of low-cost experiments. Base risk assessments for reflyable experiments on considerations involving data quality versus cost tradeoffs. In the case of low cost reflyable instruments, view the rules controlling testing and qualification established for single flight projects as guidelines only. Less than perfect performance can be accepted during any given mission. | JPL | 07/08/1993 | On March 24, 1992 the ATMOS instrument, a fourier transform spectrometer, flew on the Atmospheric Laboratory for Applications and Science (ATLAS 1) payload aboard the shuttle (STS) Atlantis with an open problem/failure report (PFR). The events leading to this state of readiness can be briefly summarized as follows: since the experiment for which this instrument was built was proposed as a low cost effort at a very early time in the STS program, the proposal did not plan for a breadboard or prototype model. The instrument had its maiden flight on the SPACELAB 3 mission in 1985 and was expected to be reflown several more times at 12 month intervals on STS missions. During the hiatus of reflights, caused by the Challenger accident, ATMOS was extensively used for making significant ground based observations. During these operations an infrequent, and apparently randomly occurring failure was observed in the startup sequence, in that the moving slides stopped. The failure could always be overcome by resetting the instrument. In spite of concerted efforts to isolate the cause of this anomaly, the failure mechanism was not identified even though certain suspect parts were exchanged. An in-flight workaround was devised for the ATLAS 1 mission and the instrument was committed to flight, knowing that a non-catastrophic failure might be experienced. In fact, during the course of the ATLAS mission, the slide failure did occur and the workaround was employed successfully. No data was lost and the mission was concluded without further reoccurrences of slide motion problems. The decision to take this risk was reached taking into account the consideration that in a low cost, reflyable instrument the acquisition of a large quantity of quality data was worth the loss of small quantities of specific runs. Reference(s): PFR #52055 | JPL has referenced this lesson learned as additional rationale and guidance supporting Paragraph 6.3.1.1 ("Engineering Practices: Mission Operations - Controlling Documentation") in the Jet Propulsion Laboratory standard "Flight Project Practices, Rev. 7," JPL DocID 58032, September 30, 2008. | N/A |  |  | Public | Not Specified |  | 06/11/1992
269 | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN | Blosiu, J - 0000000000 : NO@ADDRESS.GIVEN |  | Magellan Star Scanner Unit False Star Sightings | False star sightings by the Magellan star scanner during cruise to Venus prevented spacecraft attitude updates and occasionally caused false updates. Two causes were identified: 1) high energy solar protons sensed by the star scanner detector, and 2) quartz particles ejected from thermal blankets due to thermal shock. Selection of spacecraft sensors should consider all environmental effects. Consider the tendency of spacecraft materials to shed particles. System design must take into account the limitations of sensor and spacecraft material performance and show that the risk is acceptable. | Spacecraft star scanner detectors can sense high energy solar protons as false stars. Quartz particles ejected from spacecraft thermal blankets cloth, when illuminated by the sun, can be sensed as false stars by onboard detectors. Selection of spacecraft sensors which will be unaffected by mission environments, and selection of spacecraft materials which will not shed particles, may not be fully achievable. | Selection of spacecraft sensors should include a consideration of all environmental effects, including all sources of radiation. The selection of spacecraft materials that will be exposed to solar and other environments should include consideration of their tendency to shed particles that would be detrimental to the sensors of the spacecraft's subsystems or instruments. When the above selections cannot be fully attained, then system design must take into account the limitations and show that the risk is acceptable. | JPL | 07/07/1993 | During cruise to Venus, the Magellan star scanner detected false stars. These false star sightings prevented spacecraft attitude updates and occasionally caused false updates. Two causes were identified: 1) High energy solar protons sensed as false stars by the star scanner detector, and 2) Quartz particles, from the spacecraft thermal blanket cloth, were probably ejected when the material was thermal shocked by sudden shading or unshading from the hard ultraviolet light of the sun; these quartz particles can be sensed as false stars when illuminated by the sun. The first problem was solved by revisions to the onboard software in the attitude determination filter. The filtering worked well except during heavy solar flares. The second problem was solved operationally by keeping the star scanner in the spacecraft shade during star scans. The revisions to the onboard software (the fix for the first cause) also helped to reduce the probability of false star detection caused by quartz particle ejection. Additional Keyword(s): Workarounds, Optical Sensors Reference(s): PFR #52222 |  | N/A |  | Aeronautics Research, Science, Exploration Systems, Space Operations | Public | Not Specified |  | 05/20/1992